Annual Review - Summary Sheet

PROGRAMME TITLE: Global Serious Organised Crime (SOC) Portfolio including the Community and Institutional Resilience and Upstream Transformation Programme
Country and Region:	Global (excluding Western Balkans)
IATI Unique ID:	CSSF-12-000001, CSSF-12-000002, CSSF-12-000003
HMG Partners / (LEAD in bold)	Home Office (HO), National Crime Agency (NCA), Her Majesty’s Revenue and Customs (HMRC), Department for International Development (DFID), Foreign and Commonwealth Office (FCO)
Total Budget:	ODA: £7,000,000			Non-ODA: £3,000,000
Budget this FY	ODA: £7,000,000			Non-ODA: £3,000,000
Spend this FY	ODA: £6,624,565			Non-ODA: £2,938,274
Original Programme Start Date: July 2018		Planned End Date: 2024/5
Outputs					Score
Upstream Transformation Programme
SOC Joint Analysis (SOCJAs): shaping and informing regional and thematic strategies, enabling a more joined up and collaborative government response to upstream SOC.					B
A SOC network (SOCnet) deployed overseas supporting cross-government development, delivery, coordination and reporting on regional and thematic SOC strategies.					A
Community and Institutional Resilience Programme
Priority countries have increased capacity and willingness to protect vulnerable people from Sexual Exploitation and Abuse, both online and offline.					B
Public/private sectors improve financial information sharing for SOC investigations in priority developing countries.					B/C
Promote Gender Equality in priority Countries' response to SOC.					B
Overall output score: B
Outcome Assessment: Good pockets of programme activity are not translating to a systematically effective Portfolio because of differing programming issues, particularly in how the portfolio has been structured. A particular difficulty lies in trying to wrap portfolio coherence around two programmes of ultimately quite disparate activity, spread across different geographies and addressing different SOC threats.
Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	19/20	20/21	21/22	22/23	24/25
Programme Score	B/B*	-	-	-	-
Risk Rating - low/medium/high	M	-	-	-	-
*output/outcome scores
How has the programme changed during this period?			First year of programming activity in its current form and with two SOC programmes brought under one global portfolio.

What support did the UK provide in FY 19/20?
The Upstream Transformation Programme provided in-depth analysis of global SOC dynamics, through the production of a series of SOCJAs analysing different parts of the world and different SOC threats. The programme promoted an improved and more coherent cross UK Government and host nation response to SOC threats globally, through the deployment of 18 SOC experts across the globe as part of the SOCNetwork (SOCNet). The Community and Institutional Resilience Programme used the evidence and analysis from the SOCJAs to inform discreet programming activity across a number of SOC priorities, within different countries. This included technical capacity building in priority countries to understand and tackle Child Sexual Exploitation and Abuse (CSEA) and work to enhance understanding of the impact of SOC interaction on Gender and Conflict dynamics.

Key results for FY 19/20:
Programme One: Upstream Transformation Programme
- Successful deployment of 18 SOCnet policy leads and establishment of Joint Serious Organised Crime committee (JSOC) processes in embassies worldwide.
- Eight SOCJAs were completed and endorsed. Six out of ten regional strategies as well as a global Illicit Finance Strategy are now in place having drawn on SOCJA studies. SOCnet leads are now developing and delivering regional strategy implementation plans and country action plans for the Illicit Finance Strategy in several of the regions.

Programme Two: Community and Institutional Resilience Programme
- UK Government supported technical capabilities established in the Philippines and Kenya to tackle CSEA have buy-in from host countries and are already demonstrating results, including establishment of the Philippine Internet Crimes Against Children Centre, bringing together a number of Philippine and International agencies to combat CSEA through an enhanced response.
- The WeProtect Global Summit provided a platform for 94 countries, industry and civil society organisations to better understand impact of CSEA. Messages from the summit reached 5 million twitter users and 12 new countries became members of the WeProtect Global Alliance, giving a total of 97 member states. Over 400 senior representatives from governments (94 countries, 33 ministers), industry and civil society organisations attended the summit.
- Improved NGOs’ and public prosecutors’ awareness in key jurisdictions of Traveling Child Sexual Offender threat, through targeted activity in priority countries by the National Crime Agency, which has a resulted a more victim-led response to CSEA.
- A comprehensive scoping study was developed to deepen DFID's understanding of the scale of the challenge posed by SOC to development in Ghana. The study undertook a detailed assessment of different drivers and enablers of SOC in Ghana and outlined potential entry points and programming options, which led to a significant programme being implemented in 2020-21.
- Initial crime sensitivity guidance tool for both SOC and non-SOC programmes was developed by DFID, which enabled development programme officers to understand the indirect SOC consequences of their activity.
- A conference run by DFID brought 34 key women from the field of law enforcement and justice together, from a number of African states, to foster coordination and support networks. The meeting/conference aimed to support a better-connected SOC network in the region, enabling knowledge sharing, and promoting gender equality in a profession in which it is important to understand how women are differently affected.

Key Lessons:
- Urgent operational need in establishing the portfolio has led to activity being split across two programmes. There is logic in this approach but efforts to then consolidate the two programmes under one ‘portfolio’ (upon advice from the Joint Funds Unit) have re-instated concerns around re-integration of split programmes.
- The above has been compounded by a lack of full time Monitoring and Evaluation (M&E) capacity supporting the portfolio and led to results frameworks and M&E processes that do not necessarily accurately capture programme/portfolio outcomes.
- This has led to difficulty in measuring the results of activity within the portfolio. In the Upstream Transformation Programme which, as mainly political influencing and access activity, required specialised monitoring and evaluation tools, this was a complicated proposition for M&E in the first place.
- Delays in setting up the programme management processes around the portfolio, along with substantial challenges with Departmental commercial and financial systems, significantly delayed the commencement of activity, which has impacted portfolio delivery both in terms of results and finances.
- Although programming has been aimed at mitigating the above, clearer strategic direction from the SOC community, above and beyond the work of the SOCNet, was needed on global prioritisation of interventions. This would improve the interaction between programmes and overall portfolio coherence.
- More resource was required than anticipated to manage day to day programmatic activity, given the significant challenges faced within the Department, specifically on commercial and finance issues. High staff turnover in the programme team and finance team exacerbated these challenges.
- Speed of the programme’s creation and limited access to conflict or gender advisors, as a new programme, has meant those areas have not been given sufficient focus or drawn-out key lessons that would benefit wider HMG programming.

Summary of Recommendations for FY 20/21
- Establish separate programmes but maintain clear links between them – i.e. SOCJAs should feed SOCNet analysis which is then used to decide on potential interventions.
- Secure cross government endorsement of the UK’s approach to tackling SOC, creating a Global SOC theory of change. From this a new M&E framework should be developed to include how SOCNET undertakes political influencing/access activity.
- SOCNet should embed a measurable capability to identify gaps in SOC interventions globally and to utilise the Global SOC Fund within the Community and Institutional Resilience Programme,
– amongst other tools (diplomatic, operational etc) - to fill those gaps.
- The SOCJA process should develop a revision/renewal timetable to inform SOCNet considerations around gaps in the global response.
- Going forward, all SOCJAs should include express analysis of the interplay of SOC with gender and conflict in any given region.
- Develop a gender strategy for the SOCNet and SOCJA process and improve gender mainstreaming across all programmes and projects.
- If SOCnet policy leads continue to undertake programming, they should undertake the CSSF Programme Management course and be provided with clear guidelines at the outset of the financial year on the allocation and spending of funds.