#### Annual Review - Summary Sheet

PROGRAMME TITLE: Sri Lanka: Delivering Increased Stability and Reducing the Risk of a Return to Conflict
Country and Region:	Sri Lanka, South Asia
IATI Unique ID:	CSSF-09-000003
HMG Partners / (LEAD in bold)	Foreign & Commonwealth Office (FCO), Ministry of Defence (MOD)
Total Budget:	ODA: £10.05m			Non-ODA: £700,000
Budget this FY	ODA: £3,325,000			Non-ODA: £200,000
Spend this FY	ODA: £3,281,424			Non-ODA: £176,666
Start Date: April 2019		End Date: March 2022
Outputs					Score
Capacity building programme builds deep relationships and improves delivery of community policing in diverse communities.					B
Non-kinetic training, capacity building, and professional military education delivered to foster greater awareness of the importance of human rights and gender with key military officials.					A
Officials (e.g. lawyers, solicitors, judges, legal drafters) have increased capability to process judicial cases.					A
United Nations (UN) coordinated peacebuilding plan is adequately resourced through the Joint Plan for Peace (JPP).					A
Increasing percentage of mined land returned to victims of conflict for resettlement.					A
Resettled communities have livelihoods and psychosocial support.					A
UK interventions are gender sensitive and/or support Women, Peace & Security.					A
Assessment made of options for UK support to greater cross-party cooperation on reconciliation.					A
Overall output score					A
Outcome Assessment: Progress was made towards outcomes of promoting more capable and fairer justice institutions, as well as improving post conflict community relationships. Good results were achieved through support for parliamentary cooperation, community policing and defence training, and demining and resettlement activities. However, wider changes in the context limited full achievement of the milestones set at the beginning of this period.
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2016/17	2017/18		2018/19		2019/20*
Programme Score	A	A	B	A	B	A	A
Risk Rating - low/medium/high	M	M		M		M
*output/outcome scores / The programme has become more streamlined based on annual reviews and has adapted over the course of the 2018-20 period as political and then pandemic factors combined to pause or pivot activities.

What support did the UK provide in FY 19/20?

The CSSF programme in Sri Lanka is designed to support reconciliation and strengthen democracy and the rule of law to ensure long-term stability, through targeted project activity in six key areas:

- Peacebuilding: support to the UN Joint Programme for Peace (JPP), including the government’s commitment to Sustainable Development Goal 16 (on peace, justice and strong institutions) and sustainable resettlement of Internally Displaced Persons (IDPs).
- De-mining: clearing high density mine contaminated land and delivering mine risk education in the North and East enabling the resettlement of Internally Displaced Persons (IDPs).
- Parliamentary support for reconciliation: support to parliamentarians in cooperation on reconciliation.
- Policing: support to police reform and training based on a community policing approach that is gender sensitive and respects human rights.
- Defence: strengthening the defence relationship through targeted non-kinetic training and high-level dialogue which aims to foster greater awareness of the importance of accountability and reconciliation.
- Anti-corruption: sharing UK expertise to strengthen government capability to tackle bribery and corruption.

Most of this work is ODA eligible under the Organisation for Economic Co-operation and Development (OECD) Development Assistance Committee's revised directive on peace.

Key results for FY 19/20:

- Cleared 327,397 square metres of high-density minefield contributing towards the Government of Sri Lanka’s commitment of being mine impact free in 2020[1], and enabling the return of 101 internally displaced persons (IDPs), with a further 702 IDPs registering for resettlement. There were over 4391 direct beneficiaries from this project.
  [1] Although the 2020 target is now being extended for a period of 2-3 years, which will be reflected in next year's CSSF programme
- Recently returned IDPs (a total of 791 families) in the conflict-affected Northern and Eastern provinces received immediate resettlement support, strengthened livelihood initiatives and improved living standards.
- Targeted anti-bribery and corruption capacity building delivered with the judiciary and Legal Drafting Department of Sri Lanka, including participation of UK Ministry of Justice Permanent Secretary and globally recognised UK legal drafting experts. A number of outcomes were delivered: the programme established networks between UK and Sri Lankan judiciaries, Sri Lankan courts now have the ability to receive a higher tier of cases as a result of work on commercial courts. There were also multiple exchange visits of officials between the UK and Sri Lanka.
- Technical support provided on community policing and police response to gender and human rights, leading to the creation of tangible new structures to facilitate gender sensitive policing and a greater degree of gender inclusivity within the Sri Lankan Police (SLP).
- Development of psycho-social support materials to provide assistance to conflict affected populations in year 2. This intervention helps to support victims of conflict to heal psychological wounds and rebuild social structures.

Summary of progress and lessons learnt/actions taken since last review:

This review was conducted 6 months later than would normally have been expected due to delays arising from the Covid-19 pandemic. As such, the authors have sought to capture the period of time under review, but introduce observations on the subsequent intervening period where it was thought helpful to do so.

The review comes at the end of a period of rapid and profound political change in Sri Lanka following the Easter Bombings (April 2019) and Presidential and Parliamentary elections in 2019 and 2020. The updated context has important implications for the BHC’s programme portfolio, much of which is already evident and has resulted in adaptation of projects within the period covered by this review.

The Sri Lanka CSSF programme is a well-managed and structured programme which has proved resilient and adaptive in response to a rapidly changing political environment. The programme team, and to a large extent implementing partners, demonstrate a willingness to learn and adapt.

Programme key highlights:

- The programme supports HMG’s priority areas in Sri Lanka and is led by an integrated High Commission team with colleagues from across the FCDO policy and programme teams each taking leadership of different strands, overseen by a cross-HMG Programme Board.
- The programme has continued to enhance UK visibility and influence on areas for which the UK has a unique historic and technical offer; this is notable in the parliamentary and judicial support programmes, which are both critical in supporting State institutions responsible for the rule of law, stability and reconciliation.
- In the period under review, the programme has made a significant positive difference to the lives of Sri Lankans directly, for example through the demining projects where tangible and rapid progress has been made in demining and supporting communities to resettle, while also making a positive and important contribution by investing in a values-based approach to institutional strengthening, notably in policing and the judiciary.
- Most of the projects have pivoted to what is now possible given the new political, structural and practical parameters that prevail in Sri Lanka. The portfolio overall did not reach some of its milestones and the level of ambition originally envisaged (largely due to these substantial shifts in context), however it is already moderating its approach in a number of important ways. In contrast, it exceeded levels of ambition elsewhere, notably on demining and resettlement.
- The programme team has sought to invest in Political Access and Influence tools since the last review, in view of the importance of these areas to guiding adaptation while evaluating performance. Further evaluation, third party monitoring and support on monitoring and evaluation (M&E) will be important in building on the learning of the period under review.
- The programme has responded to recommendations of the previous annual review by, for example, formalising reporting of Defence Engagement and seeking to bolster the M&E capacity of that work, adding greater gender focus to community policing work and revising the Results Framework to moderate levels of ambition in light of the context.
- UK support is largely accepted as non-partisan, yet is responding to a changed political landscape. Over the next year, the UK should work to support a stable and peaceful country underpinned by strong institutions that command the confidence of all communities.

Summary of recommendations for the next year

1. Invest in refreshed analysis to reflect the profound changes in the context. Ideally this would include a new Joint Analysis of Conflict and Stability (JACS) to underpin policy and programmatic design.
2. As part of the JACS, consider undertaking an analysis of the emerging elite bargain[2] underpinning the new political context.
  [2] Stabilisation Guide, 2019
3. Invest in Monitoring and Evaluation (M&E), harnessing the new resource available, to ensure that each of the projects are evaluating progress and/or adaptation continually through the programme cycle. Consider using more than one methodological approach where helpful to do so.
4. Evaluate relative strengths and weaknesses of the CSSF programme model for each project (including aspects of fiscal management such as payment in arrears and/or overhead recovery) to be aware of unintended incentive structures for implementing partners.
5. Revise Results Framework so that outcomes and their indicators reflect the strategic shifts now being designed into each project area.
6. Use the space created by Covid-19’s enforced slowdown/pause on activities to invest in a XHMG review of the programme’s Theory of Change in light of the new Sri Lankan government’s priorities and trajectory.
7. Consider HMG Fusion principles in linking projects where useful to enhance their combined impact.
8. Consider the role of UN Women in advancing gender programming, for example with the police reform project or as part of the JPP.