Annual Review - Summary Sheet

PROGRAMME TITLE: Consolidating Democracy in Pakistan Programme (CDIP)
Country and Region:	Pakistan, South Asia
IATI Unique ID:	CSSF-08-000001
HMG Partners / (LEAD in bold)	Department for International Development (DFID), Foreign & Commonwealth Office (FCO)
Total Budget:	ODA: £31.5 m (Total Spend)		Non-ODA: N/A
Budget this FY	ODA: £6.92 m		Non-ODA: N/A
Spend this FY	ODA: £6.92 m		Non-ODA: N/A
Original Programme Start Date: July 2016		Planned End Date: March 2021
Outputs				Score
Election management and election oversight processes are more credible, transparent and inclusive.				B
Parliamentary processes are more inclusive, parliamentarians are more effective in holding government to account.				B
Political parties across the mainstream political spectrum better represent, respond to and deliver for their constituents.				A
Expanded democratic space allows improved policy dialogue, political debate and public discourse.				A
Overall output score				B
Outcome Assessment: Outcomes partially met expectation.
Outcome Score: B		Risk: Medium

Summary of Programme Performance
Year		2016/17	2017/18*	2018/19*		2019/20*
Programme Score		A	A	A	A	B	B
Risk Rating - low/medium/high		Medium	Medium	Medium		Medium
*output/outcome scores
How has the programme changed during this period?	There was no major change in the approach of the programme during the last year. The Theory of Change (TOC) was updated to better align the project’s vision with the change in context in the post-election period. Focus was shifted towards institutionalisation of reforms and sustainability of the capacity built in the democratic institutions.

What support did the UK provide in FY 19/20?
The “Consolidating Democracy in Pakistan (CDIP)” Programme represents the UK Government’s cross-departmental support to democratic institutions. It aims to support a democratic system in which: government institutions are more capable; parliament is more accountable; and the state is more responsive to the needs and aspirations of the Pakistani people. The programme aligns with Objective 5 (‘Support accountable and representative institutions and good governance’) of HMG’s Integrated Delivery Plan (IDP) and contributes to DFID’s strategic objective of building peace and stability, and acts as an enabler of economic development and the transformation of the lives of women and girls.
The programme is managed by the Department for International Development (DFID) and the Foreign and Commonwealth Office (FCO) at Post. It exists within a broader framework of the UK’s cross-departmental programming, bilateral political engagement and interventions from other development partners and diplomatic missions. The CDIP programme has a budget of up to £31.5m and is implemented by the United Nations Development Programme and Development Alternatives International (DAI).
The Programme supported the Election Commission of Pakistan’s (ECP) to function more openly, consultatively and inclusively; enabled some political parties to establish strong foundations for evidence-based policymaking on climate change and Sustainable Development Goals (SDGs), and tells an excellent gender story across all outputs, exemplified by good progress with the Women’s Parliamentary Caucuses and high registration of women on the electoral roll[1].
[1] The nationwide, ECP led Women Voter Registration campaign, enabled an additional 5 million more women to be added to the electoral roll before 2018 Elections through community level registration effort. Out of which, the programme directly supported over 800,000 women to be registered

Programme Components:

Elections: This focus on programme’s support to the Election Commission of Pakistan (ECP) in a post-election year, to conduct a post-election review and use the findings to inform the strategic planning, and institutional development of ECP.

Key results for FY 19/20:
- 43 recommendations from the Post-Election Review are adopted and tested during the Elections held in Newly Merged Districts of Khyber Pakhtunkhwa (KP).
- ECP Strategic Plan (2019-23) developed and put an implementation plan in place. The plan includes strengthened and/or new institutional and electoral reforms, on Public Financial Management (PFM), budget, procurement and human resource management; legal framework, communication & ICT; voter registration, inclusion and gender mainstreaming. ECP established its oversight and implementation committees to monitor delivery of the Strategic Plan.
- ECP’s Federal Election Academy upgraded its training plan, training modules and led on ECP’s ex-Federally Administered Tribal Area (FATA) polling staff training, ministerial staff training and anti-harassment training (ToT).
- Four institutional measures taken by ECP as demonstrations of commitment to inclusion, comprising inclusion of G&DEWG (Gender and Disability Electoral Working Group) in ECP’s Strategic Plan; the appointment of Directors (Gender) in two provinces in addition to one already working in KP; the revision of the group’s ToRs to improve structure, coordination and governance, and institutionalisation of external partnerships.
- ECP proposals to increase electoral inclusion presented through the National Database and Registration Authority (NADRA) Ordinance, 2000 amendment bill; the Elections Act (Gender) amendment bill; and the Reform in the Elections Act, 2017

Parliament: The objective of this work stream was to build the capacity of Parliamentarians to better perform their legislative role and strengthen their oversight of government. Support was provided to parliamentary committees, multi-party fora and constituency outreach mechanisms – all of which should have been priorities in a post-election year.

Key results for FY 19/20:
- Parliamentary Committee Secretariat functions and house business improved through the revision of rules of procedures for committee strengthening, the establishment of a Comms Wing in the Punjab Assembly, the development of standard operating procedures (SOPs) for the use of social media and for stakeholder engagement for the Senate, and enabling Parliamentary reforms such as PM Hour, Backbenchers’ Day, Public Petition to be adopted.
- Parliamentary forums’ functioning improved, for example women’s leadership inclusion in the Baluchistan Assembly strategic plan process, and the improved sustainability of KP Assembly Secretariat training initiatives.
- Increased access to the National Legislative Archive for 89 members of the Womens Parliamentary Caucus (WPC) and 37 MPs from various committees and parliamentary houses. Training of 57 MPs on leadership & negotiation skill.
- Parliamentary committees strengthened (Senate’s Law and Justice Committee and the National Assembly’s Climate Change Committee)
- Parliamentary committees strengthened, leading to five WPC bills presented in the national and provincial assembles; and Punjab Assembly’s Committee on Women’s Development presenting the Punjab Child Marriage Restraint Bill 2019. The programme supported the KP Assembly’s Task Force on the Sustainable Development Goals (SDGs) to form clusters and assisted the KP Assembly WPC members to draft two laws on HIV/AIDs and Civic Education.

Political Parties: The focusses on support to political parties, was to assist them to be more inclusive, better at using evidence to inform policy, and with stronger systems of internal governance.

Key results for FY 19/20:
- Political parties undertook seven institutional reforms, including agreement to form a multi-party Women in Politics Support Group (WPSG), endorsement of the Charter of Inclusion, delegation of key offices to young political workers trained under Young Politicians Fellowship Programme (YPFP), training of aspiring women candidates, establishing policy wings in 5 parties, of which 4 have 50% women and youth representation.
- Political party policy wings developed policies on 15 citizens’ issues and launched them at their policy conventions.
- Political party policy wings initiated innovative approaches to issues, for example Pakistan Muslim League (Q) (PMLQ) formed a young activists’ network to promote the environment and climate change policy (Eco-Friends), and the National Party (NP) drafted two amendments in the anti-harassment bill.
- 4 parties committed to reform candidates’ selection process as per the programme’s selection criteria and independently pilot tested this in by-elections.
- All 10 political parties complied with financial and audit requirements; updated their membership databases as per ECP requirements and no party was delisted; received briefing on SDG framework and agenda in their manifestos, facilitated and mobilised around 0.5m women from marginalised communities to obtain National Identitiy Cards (NIC); initiated 5 policy-level changes relating to relaxation in documentation requirements implemented (Nikah-nama; family witness, Grade-17 officer attestation, NIC processing from non-Federally Administered Tribal Areas (FATA) districts etc.), delivered a radio/TV campaign reaching >120million.

Democratic Space: The Programme worked on the enfranchisement of women and other excluded groups, improving Civil Society Organisations (CSO) and the media’s ability to engage with democratic institutions, and encouraging healthy dialogue/debate on emerging issues.

Key results for FY 19/20:
- Over 1.1 million women and people with disabilities mobilised and more than 700,000 received their Computerised National Identity Cards (CNICs).
- The Programme facilitated 22 Civil Society Organisations (CSOs) in engaging with state institutions for drafting the Person with Disabilities (PWD) bill, supporting drafting of the Transgender Persons Protection Act with WPC, developing a ‘unified’ policy for the registration and regularisation of international non-governmental organisations (INGOs) with the Senate Speaker, SDG Task Force and MPs.
- The Programme facilitated 100+ CSOs to be institutionally integrated with Civic Information Portal (CIP)-PakVoter and supported 5 citizen-led online channels.
- Supported 10+ public universities/schools for research/youth.

Key Lessons
The Programme’s immediate focus is rightly focussed on the role of parliaments, political parties and civil society in the Covid-19 response. In doing so, the Programme should re-consider – with an eye on the medium-term – what is most important, to inform a fresh vision for how it will deliver change relevant to people. Programmatic focus on a narrower slice of the democratic ecosystem, with a strong local component tested in discrete parts of the country, should enable the programme to link systems with people (and the CSOs which represent their interests), thereby enabling a better story at the outcome level, where responsiveness, accountability and capability remain relevant proxies. Implementing partners (IPs) will need stronger technical leadership to own and drive this vision and lean more heavily on a higher quality Results Framework (RF), and stronger Monitoring, Evaluation and Learning (MEL), to articulate ambition at the right level and track progress. They will also need to get better at unpacking a problem to ensure that their intervention effects measurable change. British High Commission (BHC), meanwhile, should focus on output-level indicators and progress towards outcomes in its dialogues with partners. Strong progress on gender and inclusion across the system should be consolidated. ECP supported work should reduce, replaced by more strategic work with political parties and their policy wings, constituency outreach as an interface between politicians and people, and targeted work with a handful of parliamentary select committees relevant to HMG’s broader interests.

Summary of Recommendations for FY 20/21
1. BHC’s Democracy Team should foster stronger strategic and technical links with other CSSF/DFID-led Programmes (AAWAZ II, SNG II, Rule of Law) in order to demonstrate the continued relevance of the Democracy Programme to HMG’s priorities in Pakistan.
2. BHC’s Democracy Team should build better partnerships with other donor-led democracy projects to generate efficiencies and more coherent policy lobbying.
3. Implementing Partners should provide monthly updates on up-coming interventions so that FCO Political Section can attend.