#### Annual Review - Summary Sheet

PROGRAMME TITLE: The Maldives Conflict, Stability and Security Fund Programme
Country and Region:	The Republic of Maldives, South Asia
IATI Unique ID:	CSSF-09-000005
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Ministry of Defence (MOD)
Total Budget:	ODA: £750,000			Non-ODA: £750,000
Budget this FY	ODA: £500,000			Non-ODA: £25,000
Spend this FY	ODA: £332,386			Non-ODA: £29,800
Original Programme Start Date: January 2019		Planned End Date: March 2022
Outputs					Score
Capacity building programmes strengthens democratic institutions, whilst addressing women’s participation and leadership.					B
UK builds influence and credibility in supporting parliament on process, inclusion and accountability.					B
Inclusive decentralisation processes are supported, with focus on women and youth; and technical assistance for justice and legislative reform. UK develops better diagnosis, with buy-in of difficult to reach partners.					B
Capacity-building supports Maldivian Police Service (MPS) to implement community and values driven policing. UK establishes relationship based on shared values and empowers MPS leadership; and builds credibility to influence through years two and three.					A+
Capacity building and mil-mil engagement helps UK build relationship as trusted partner for Maldivian National Defence Force, with credibility to influence through years two and three.					A
Overall output score					B
Outcome Assessment: The Maldives Programme is a multi-year programme that began in January 2019. The programme is one of several being run by the UK at the inception stage of an ambitious, but well forecast and subsequently planned, intervention in the Maldives. It was run at distance from the British High Commission (BHC) in Sri Lanka at first, ahead of the establishment of the British High Commission in the Maldives. Early delivery was affected by the impact of the Easter bombings in Sri Lanka in April 2019. The emphasis throughout this first year has been to take advantage of the opportunity that has arisen and our comparative advantage to enhance our political access and influence, demonstrating that the UK is a reliable, consistent and committed partner. There have been strategic, operational and tactical activities, combining top-down and bottom-up approaches within a single programme. While the various programme strands have continued to build productive relationships, further work is now required to deliver at output and outcome level within an overall strategy. The inception stage during year one was loosely framed within programme documentation, which is currently undergoing a review with external support, and adapting as contextual understanding develops. Governance, increased stakeholder co-ordination, and outreach, balanced across different programmes and their synchronisation, places considerable demands on a small programme management team and its implementers. In parallel, the fact that staff in key areas of security are shared with Sri Lanka means they will have to be innovative moving forward.
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*		2019/20*
Programme Score	-	-	-	-	-	-	B	A
Risk Rating - low/medium/high	-	-	-	-	-	-	Med	Med
*output/outcome scores
How has the programme changed during this period?			It is a new programme.

What support did the UK provide in FY 19/20?

The Maldives CSSF Programme has provided support to:
Parliamentary processes and resilience. Through the Westminster Foundation for Democracy (WFD), the programme provided support for the development of a Members of Parliament (MP) code of conduct, legislative drafting, a strategic plan and committee guidelines, which included gender and inclusivity components. Signs of strengthened parliamentary committee oversight functions and practices, with WFD support, are evident. Additionally, the relationship between the Maldives Parliament and National Assembly for Wales has been developed and strengthened for future collaboration.

Strengthened Rule of Law, Justice Sector and Governance reform in the Maldives. During the 2018 scoping mission, judicial reform was identified as a priority for the Maldives’ nascent democratic institutions.  This led to a pilot project with the United Nations Development Programme (UNDP) in 2018/2019 on justice sector reform. The evidence built through this project formed the baseline to continue work on justice sector reform under the 19/20 CSSF programme. Having laid the groundwork for key initiatives related to decentralisation and justice sector reform, consultations with key partners including the Attorney General’s Office, the President’s Office, Local Government Authority and Judicial Service Commission have taken place to discuss the planned interventions for the year and ensure national partner buy-in from the initial stages.

The Maldives Police Service (MPS) supported the implementation of the MPS Strategic Plan, including through embedding a Senior Policing Advisor who focused particularly on women in policing, professionalising workforce development and other high priority areas identified under their action plan.

The Maldivian National Defence Forces (MNDF). Despite a limited time accredited in the Maldives, the Defence Advisor (DA) (who is based in Colombo) has used engagement with MNDF to enable the attendance of a junior officer on the Short Commissioning Course at The Royal Military Academy Sandhurst, for three months. This has enabled the delivery of the Exclusive Economic Zone Naval Course in South Asia, which was attended by individuals from the Maldives, Sri Lanka and Bangladesh. The UK was also able to send a team from the Joint Force Headquarters to assess response options in the event of a Humanitarian Assistance and Disaster Response.

Coordination of donors. The UK, under the Counter Terrorism Programme Fund (CTPF) umbrella, co-ordinated a donor meeting in February 2020 in conjunction with the Office of the President, to demonstrate leadership in areas of UK interests and help coordinate international support. Subsequently, through meetings with the High Commissioner in the Maldives, the United Nations Resident Coordinator has taken over this donor coordination role.

Key Lessons
There is no blueprint for countries like Maldives and the opportunities that have arisen. While a micro-mission is setting itself up and trying to initiate a CSSF programme, flexibility should be provided to allow a risk aware and not risk adverse approach.

The combination of a Protect and Prepare Coordinator and a Senior Policing Advisor allowed the development and implementation of a strategy that has significantly enhanced the UK’s position, giving an edge to engagement in the security sector. The combination of individuals and the approach of developing relationships (which are much more easily done when in-country medium-long term) and linking UK policy goals to implementation by embedding a Policing Advisor, allowed wide-ranging access across the organisation to understand and assess the current context.

Security Sector Reform/Development design. Maldives is in a key strategic location, and defence engagement has enabled the use of Maldives as a ‘stop over’ for military flights travelling to South Asia and Asia Pacific. Currently this is facilitated by the UK DA, working with the Maldivian DA based in Colombo. To support this small post, build strong relationships in this area and to implement defence engagement dovetailed with the CTPF and CSSF, it is clearly extremely beneficial if the DA can spend extended periods in-country.

Summary of Recommendations for FY 20/21
Transition arrangements of governance for CSSF programming must be handed over as soon as BHC Male is ready to take on the responsibility and operate autonomously.

Theory of Change (ToC) / Results Framework (RF). As has been identified, the programme team should consider revising the programme documentation, Theory of Change and Results Framework appropriately.

Devolution of Financial Management to The Maldives. To avoid repeating delays in payments and project delivery, it is strongly recommended that the Maldives programme team hold the relevant authority to conduct all financial management processes to feed directly to the South Asia and Afghanistan Directorate Programme Team.

- Policy and Programme working together. The following areas require development, and it is critical that programme(s) and policy strands must work hand-in-hand:
  - Engagement Plan and Stakeholder Mapping.
  - Project / Programme Coordination.
  - Access and Influence mapping. The team are achieving significant levels of access, influence and understanding, providing useful channels of engagement for the UK. This should be recognised as an outcome.

Security Sector Reform Development. If Outcome two, ‘Supporting Security Sector Reform through engagement with the MPS and MNDF is to continue, it will be important to develop a sustainable plan for the MNDF that goes beyond capability building and supports democratic norms and sound principles of good governance, and so contributes to a well-functioning security framework.

Westminster Foundation for Democracy (WFD). To enable a better understanding of WFD and its processes, it is recommended that ITAD (Monitoring, Evaluation and Learning service) conduct a review. Communications should be improved to enable situational awareness for both BHC and WFD.

Gender Mainstreaming across all projects and programme strands is required, considering deeply entrenches societal views regarding women and girls. There has already been some good work in identifying areas of potential, but these now need to be programmed effectively from the start.

Suppliers. As the programme develops, the programme team should consider suppliers beyond those that are currently being used.

Sustainability and Exit Strategies. Future programming should ensure that sustainability and exit strategies are defined and incorporated for various programme strands / projects with implementers.