Annual Review - Summary Sheet

PROGRAMME TITLE: Rule of Law in Pakistan Programme
Country and Region:	Pakistan, South Asia.
IATI Unique ID:	CSSF-08-000002
HMG Partners / (LEAD in bold)	Department for International Development (DFID), Foreign and Commonwealth Office (FCO), Ministry of Defence (MoD), Home Office (HO), Crown Prosecution Service (CPS), National Crime Agency (NCA)
Total Budget:	ODA: £ 49m (final allocation)		Non-ODA figures redacted
Budget this FY:	ODA: £9.05m (final allocation)		Non-ODA figures redacted
Spend this FY:	ODA: £9.57m		Non-ODA figures redacted
Original Programme Start Date:1/4/2016			Planned End Date: 31/3/2021
Outputs				Score
Improved cross-institutional policy frameworks to support safer security and justice outcomes (25%)				A
Improvement in institutional governance, including, systems & structures, of targeted criminal justice institutions (25%)				B
Improved capability of targeted criminal justice actors and institutions to comply with agreed organisational and/or professional standards (25%)				B
Rights violations are prevented, and rights promoted and increasingly protected, of victims, witnesses, defendants and convicted persons, especially women and juveniles (25%)				A
Overall output score				A
Outcome Assessment: Moderately meets expectations.
Outcome Score: B		Risk: High

Summary of Programme Performance
Year	2015/16		2016/17	2017/18*		2018/19*		2019/20*
Programme Score	A+		A	A	A	A	A	A	B
Risk Rating - low/medium/high	Moderate		Moderate	Major		Major		Major/High
*output/outcome scores
How has the programme changed during this period?		Until March 2020, prior to the disruptions caused by Covid-19, FY19/20 was a stable year for the Rule of Law Programme, with all main projects active. Under the Strengthening Accountability in Pakistan (SAP) project, a component focusing on support for gender-based violence (GBV) survivors was added in August 2019.

What support did the UK provide in FY 19/20?

The CSSF Strengthening Rule of Law in Pakistan (RoL) Programme aims to increase public confidence and trust in the Rule of Law in Pakistan. It focuses on delivering outputs which improve the justice system for victims, witnesses and offenders, including vulnerable women and girls.
The components are summarised below:
Justice System Support Programme (JSSP) (DFID): Uses a roadmap approach,[1] as well as targeted technical assistance to help criminal justice institutions (police, prosecutions, judiciary, Home Department (prisons & probation)) to improve performance, deliver priority reforms and strengthen coordination. The project is focused on Punjab/ Khyber Pakhtunkhwa (KP).
[1] The roadmap approach is built around the principles of a) prioritisation of a limited set of shared indicators, b) ensuring system leadership and political buy-in, c) investing in data-driven policy-making, d) establishing clear routines to sustain these ways of working, and e) emphasis on learning and iterative adjustments en route.

United Nations Office on Drugs and Crime (UNODC) in Balochistan and Sindh / (DFID): Supports roll out of the roadmap approach in Balochistan and Sindh.

Strengthening Accountable Justice in Pakistan (SAP) / (DFID): Supports civil society advocacy for inclusion of vulnerable groups in criminal justice reform. Focuses on child-sensitive justice and services for survivors of gender-based violence (GBV).

Key results for FY 19/20:

1. Rule of Law Roadmaps in four[2] provinces carried out byJSSP/UNODC have established governance structures (Steering Committee/Cabinet Sub-Committee, Delivery units) and high-level indicators shared across police, forensics, prosecutions, Home Departments and the judiciary.
  [2] Punjab, Khyber Pakhtunkhwa, Sindh and Balochistan
2. JSSP strengthened internal accountability of Investigation Officers (IO) and Prosecutors by training 59% of IOs and 44% of Prosecutors in 2 target districts in KP, facilitating inspection of 10% of serious sexual violence and homicide cases and putting in place an internal quality assurance mechanism for prosecutors.
3. JSSP improved use of forensic evidence in target districts by raising the number of prosecutors issuing case-specific forensic evidence advice to 100% in KP and improving Standard Operating Procedures (SOPs) for crime scene preservation, management and use of technical evidence in serious sexual violence and homicide cases.
4. Accountability partners have worked with provincial judiciaries to establish four child courts (with 4 more in the pipeline). An age determination protocol for juvenile offenders supported by the project has been used in 863 cases, all of which have then been passed through the child courts in line with the protocol.
5. Accountability partners have secured agreement from targeted gender-based violence (GBV) response services and government to implement human rights-based standards and protocols in government funded shelters for women who have experienced GBV.

Key Lessons
Lessons from this review focus on programme design for future programming:

1. Avoid too many components, especially from pre-existing programmes.
2. Ensure the Programme Senior Responsible Officer (SRO) has adequate oversight.
3. Make sure governance structures reinforce coherence and accountability.
4. Avoid programming split across departmental baselines.
5. Promote policy-programming links.
6. Make clear who “owns” policy for programmes.
7. Ensure programming reflects CSSF characteristics.
Summary of Recommendations for FY 20/21:

1. Adjustments for Covid: Project-specific Theories of Change (ToCs) should be reviewed in light of the implications of Covid-19 on key assumptions. All other activity should be adjusted for feasibility in the context of Covid-19 - by end of July 2020.
2. Exit Strategies: All project SROs should also ensure they have in place clear exit strategies and agreed learning and evaluation approaches – by end of October 2020.
3. Exit roadmap in Punjab: In Punjab, JSSP should refocus its attention and resources on supporting initiatives that reinforce the roadmap principles, promote inter-departmental coordination and are likely to be sustained by government after the end of the project.
4. Shift UNODC emphasis from Balochistan to Sindh: The UNODC project should shift more time and resources into work in Sindh. To facilitate this, the Programme SRO should seek to bring forward the planned transfer of the UNODC’s roadmap work in Balochistan into the European Union’s Rule of Law programme.
5. Move GBV work under JSSP: Any follow-up work identified by accountability partners as part of their rapid scoping on the needs of survivors of GBV under Covid-19 should be implemented through sub-granting by JSSP - by end of June 2020.
6. Update Results Framework: The RoL Programme SRO should submit an updated results framework to BHC leadership for approval by end of September 2020.
7. Improve Value for Money (VfM) tracking: The Programme SRO should ensure that by end of September 2020 all components establish VfM baselines and gather periodic data against them, with an emphasis on unified indicators and consistent methodologies across the Programme.