## Table Key
TRANSMISSION OWNER MAJOR PROJECT STATUS UPDATE - JUNE 2021
KEY explaining individual columns
Ref No cross refers to the associated map showing the geographical location of projects. cross refers to the associated map showing the geographical location of projects.
Project TEXT Grey | Grey text denotes Project is on hold | Dark Grey | Dark Grey denotes project is complete | Light Blue | Light blue shading denotes minor change since previous update. | Dark Blue | Dark blue shading denotes significant change since last update, e.g. revised delivery date.
TO identifies the relevant Transmission Owner i.e. Scottish Hydro Electric Transmission plc (SHE Transmission) Scottish Power Transmission (SPT) and National Grid Electricity Transmission (NGET).
Project/Component/Driver(s) describes the project.
Area/Transmission Boundary provides the geographical area and boundary zone(s) showing where projects are and the boundaries they will affect where relevant.
Project with Mutiple TO's: highlights duplicate projects due to the involvement of multiple TO's
Increase in Transfer Capacity or Generation Accommodated shows how much the network capacity is expected to grow allowing greater transfer of electricity across the boundaries and/or allowing new generation to connect.
Current Project Stage: 1.Scoping – Identification of broad need case and consideration of number of design and reinforcement options to solve boundary constraint issues; 2.Optioneering – TO believes that the need case is firm; design of a number of design options provided for public consultation so that a preferred design solution can be identified; 3.Design – Designing the preferred solution into greater levels of detail and preparing for the planning process; 4.Planning – Continuing with public consultation and adjusting the design as required all the way through the planning application process; 5.Construction – Planning consent has been granted and/or contracts have been awarded and manufacturing underway.
RAG Status (Project Stage) presents an assessment by the TO of any issues affecting the particular project stage and how they impact on the expected completion of that stage. This and the other RAG Status column only apply to projects where the TO believes that the need case is firm and has not moved (although the need case might not yet have been submitted to Ofgem for assessment). So, projects at the earliest 2 stages (scoping and optioneering) do not generally have a RAG rating. Where a project does have a RAG status, below are the indicators;
| Green means that particular project stage is within 6 months of expected completion date |  |  | Amber indicates a delay of 6-12 months; |  |  | Red a delay of over 12 months.
Issues presents any substantive issues or risks identified by the TO.
Comments provides information on mitigating actions, recent or upcoming milestones, etc.
Earliest completion date refers to the date included in the ENSG 2020 Vision Update Report from Feb 2012. This indicated the earliest date a project could be completed. This is not necessarily the same as the delivery date (see below).
Delivery date is the TO's view of when the work will be completed. Implicit in some of these dates are certain assumptions about planning permission, but these entries do not prejudge those decisions. Also, these entries are not used for regulatory purposes, and might not reflect the dates in the transmission licences: for some projects, the date in this table differs from the existing date in the TO's transmission licence; for others, a date will not be determined and put into the licence until a later date. Note: The Delivery Year quarters are based on the financial year calendar. Take for example the 2017 year, Q1 2017 = April - June 2017; Q2 2017 = July - September 2017; Q3 2017 = October - December 2017; Q4 2017 = January - March 2018
RAG Status (against delivery date) is an assessment by the TO of meeting that delivery date: The indicators are described below. Where the TO does not yet have a set view of the delivery date, this entry is blank.
| Green indicates within 6 months of required delivery date; |  |  | Amber indicates a delay of 6-12 months; |  |  | Red a delay of over 12 months.
Weblink provides web references for further project information from the TO.

## TO Major Project Update
TRANSMISSION OWNER MAJOR PROJECT STATUS UPDATE - JUNE 2021
Ref No | TO | Project / Component/Driver(s) | Area / Transmission Boundary, where appropriate | Project with Multiple TO's | Increase in Transfer Capacity or generation accommodated (MW) | MARCH 2021 Update | JUNE 2021 Update | MARCH 2021 Update | JUNE 2021 Update | MARCH 2021 Update | JUNE 2021 Update | MARCH 2021 Update | JUNE 2021 Update | Earliest completion date (as per 2012 ENSG) | MARCH 2021 Update | JUNE 2021 Update | MARCH 2021 Update | JUNE 2021 Update | Weblink (where available)
[6 empty] | Current Project Stage (previous status where different): 1. Scoping 2. Optioneering 3. Design 4. Planning 5. Construction | Current Project Stage (previous status where different): 1. Scoping 2. Optioneering 3. Design 4. Planning 5. Construction | RAG Status (Project Stage) - TO view | RAG Status (Project Stage) - TO view | Issues (including reasons for slippage, etc.) | Issues (including reasons for slippage, etc.) | Comments (Mitigating actions, etc.) | Comments (Mitigating actions, etc.) |  | Delivery Date - TO view | Delivery Date - TO view | RAG Status (Against Delivery Date) - TO view | RAG Status (Against Delivery Date) - TO view
1HP | SHE Transmission | Beauly-Denny 400kV line to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from North to South of Scotland | Northern Scotland (B1) | Yes | 850 | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | http://www.sse.com/BeaulyDenny/
3H | SHE Transmission | Knocknagael 275/132kV Substation | Northern Scotland (B1) | No | 50 | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
3NHP | SHE Transmission | Eastern HVDC Link to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and improve security of supply | NE Scotland (B4) to NE England (B6, B7, B7a) | Yes | 2200 (B4) 2200 (B6) 1000(B7) 700 (B7a) | 2. Optioneering | 2. Optioneering |  |  | The joint Transmission Owner Strategic Wider Works Initial Needs Case was submitted to Ofgem in Oct 2020 for the Peterhead - Drax (2029) and the Torness - Hawthorne Pit (2027) HVDC links. Continued engagment with Ofgem throughout early 2021 with a formal response to the INC expected in Q2 2021 | Ofgem published the Eastern HVDC - Consultation on the project’s Initial Needs Case and initial thinking on its suitability for competition on 12th May 2021. Initial Needs Case was submitted to Ofgem in Oct 2020 for the Peterhead - Drax (2029) and the Torness - Hawthorne Pit (2027) HVDC links. TOs and ESO are continuing to work collaboratively to develop the Final Needs Case. | Joint TO working group and ESO engagement with Ofgem to agree and colaboratively develop the Final Needs Case Cost Benefit Analysis methodology. Marine Surevy works scheduled for Peterhead - Drax in early Q2 | Final Needs Case CBA is progressing along with continued engagement with supply chain and key stakeholders. Marine Survey has commenced for Peterhead – Drax. Survey expected to be conmplete by August 2021. | 2018 | The EISD for Torness - Hawthorn Pit is 2027; EISD for Peterhead to Drax is 2029 as per NOA 20/21 | The EISD for Torness - Hawthorn Pit is 2027; EISD for Peterhead to Drax is 2029 as per NOA 20/22 |  |  | http://www.sse.com/EasternHVDClink/
4H | SHE Transmission | Beauly - Blackhillock - Kintore 275kV Reconductoring to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from North to South of Scotland | Northern Scotland (B1) | No | 300 | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | 2014 Q4 | Complete | Complete | Complete Q2 2016 | Complete Q2 2016 | https://www.ssepd.co.uk/BeaulyBlackhillockKintore/
7H | SHE Transmission | Beauly - Dounreay - 2nd 275kV circuit | Northern Scotland (B0) | No | 100 | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | 2012 Q4 | Complete | Complete | Complete | Complete | http://www.sse.com/dounreaybeauly/
9H | SHE Transmission | Shetland HVDC Link to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and Onshore wind and marine for Scottish Islands | Island Link | No | 600 | 5. Construction | 5. Construction |  |  | Construction continues as per programme at Kergord, Shetland and Noss Head, Caithness with mobilisation, access and bulk earthworks underway . Manufacturing of HVDC cable for Type Test complete. Orders placed for majority of HVDC main circuit equipment. Detailed design continuing on all work packages. Preperations in place for mobilisation of land cable installation teams and off shore pre-lay surveys in Q2 2021. COVID-19 remains a key risk to productivity and programme. | Construction continues as per programme for all aspects of the project. Substantial progress on civil design and primary electrical design for both sites. Platform construction at Kergord nearing completion with commencement of substructure construction of HVDC Convertor Station. Completed bulk earthworks at Noss Head and commenced substructure construction of Switching Station. Commenced 600MW Cable Type Test and commenced land and subsea cable manufacturing. Commenced offshore pre-lay survey work and site establishment for land cable installation works in Caithness and Shetland and mobilised Horizontal Directional Drill (HDD) contractor at Noss Head. | Stakeholders continue to be engaged and kept informed of progress and SHE Tranmssion is working closely with Viking Energy Wind Farm as the other major developer commencing works on the islands to ensure the COVID risk to Shetland is minimised by our workforces. | Project is on programme. Stringent COVID Risk assessments and processes inplace for the project with specific testing procedures in place for all work on Shetland, in alignment with Scottish Government requirements and recommendations. Emerging issues with construction materials shortage and price inflation flagged by supply chain, immediate impact mitigated and mitigation plans being put in place to prevent future impact. Stakeholder engagement continues with active engagement with local communities and Viking Energy Wind Faram | 2017 Q4 | 2024 Q2 (tbc) | 2024 Q2 |  |  | http://www.sse.com/Shetland/
11HP | SHE Transmission | East Coast 400kV Upgrade to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from North to South of Scotland | Northern Scotland (B2/B4) | Yes | ECU2 (610MVA) ECUP (480MVA) | 3. Design | 3. Design |  |  | The Incremental approach to 400kV Operation in the Eastern Transmission Network through ECU2 (2023) and ECUP (2026) are included in our RIIO T2 business plan Certain View. No significant issues have been encountered with the need. Key consenting works for the substation and overhead lines all progressing to programme. Stakeholder enagagement events took place in Sep/Oct 2020. | The East Coast 275kV and 400kV upgrades are progressing through the development and refinement stages. Kintore, Alyth, Peterhead and Tealing substation works and overhead line works are progressing in line with programme. | Works continue to progress to deliver the required outputs for 2023 and 2026 respectively. Works to deliver the 2023 scope (ECU2) are progressing, including applications for consents where applicable and tenders. Works to deliver the 2026 scope (ECUP) are ongoing with landowner negotiations commenced and design works progressing. | Works continue to progress to deliver the required outputs for 2023 and 2026 respectively. Works to deliver the 2023 scope (ECU2) are progressing, Alyth has commenced works on site as have the OHL reprofiling, tenders are ongoing for Tealing PSTs. Works to deliver the ECUP scope are also progressing with tenders undertaken for the OHL and Kintore 400kV Substation works, with detailed design ongoing. Development works for Fetteresso and the Blackhillock PSTs are ongoing to inform tenders and detailed design requirements. | 2017 Q1 | ECU2 - 2023 ECUP - 2026 | ECU2 - 2023 ECUP - 2027 |  |  | http://www.sse.com/ECR400kV/
12H | SHE Transmission | Beauly - Mossford 132kV Line & Switch Substation to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from North to South of Scotland | Northern Scotland (Radial circuit) | No | 300 | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | 2014 Q4 | Complete | Complete | Complete Q2 2016 | Complete Q2 2016 | http://www.sse.com/beaulymossford/
13HP | SHE Transmission | Hunterston ‐ Kintyre 240MVA AC subsea link to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from North to South of Scotland | Northern Scotland (B3) to Central Scotland (B3) | Yes | Up to 350MW additional generation | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | 2015 Q4 | Complete | Complete | Completed in Q2 2016 | Completed in Q2 2016 | http://www.sse.com/KintyreHunterston/
14H | SHE Transmission | Western Isles HVDC Link to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and Onshore wind and marine for Scottish Islands | Island Link | No | 600 | 3. Design | 3. Design |  |  | The current 600MW HVDC Link programme has been reviewed with a plan to prepare for AR4 in 2021 approved. This drives a new connection date for customers. | The current 600MW HVDC Link programme has been reviewed with a plan to prepare for CfD award in Q2 2022. This drives a new connection date for customers. | Project will be re-established in Q1 2021 to undertake minimal development works to ensure any future energisation dates would be met following any developer success in AR4 and subsequently developers proceeding with their project. | Project restarted in April 2021 to maintain programmed energisation date of Q1 2027. Several activities ongoing including Optioneering, CBA to the Needs Case and securing of the Arnish convertor station site; with a view to holding wider stakeholder roundtable meeting in Jun/July 2021 and being ready for construction by Q4 2022. | 2015 Q4 | Q1 2027 | Q1 2027 |  |  | http://www.sse.com/WesternIsles/
17H | SHE Transmission | Orkney 220kV Subsea Link to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from North to South of Scotland | Island Link | No | 220 | 3. Design | 3. Design |  |  | Ofgem has conditionally approved the Needs Case subject to at least 135 MW of generation demonstrating commitment to proceed by December 2021. This condition has not yet been met. | The deadline for conditionality being met has now been extended to December 2022 enabling consented projects to bid into Allocation Round 4 for a CfD, and for the results of that auction to be published. | Preliminary design works have been completed as far as possible prior to the meeting of Ofgem’s conditions. | Indicative programme based on 12 month extension of Ofgem conditionality means project completion in Q2 2027. | 2015 Q4 | Q2 2026 | Q2 2027 |  |  | http://www.sse.com/OrkneyCaithness/
21H | SHE Transmission | Caithness-Moray HVDC Reinforcement to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from North to South of Scotland | Northern Scotland (BO,B1) | No | 800 (BO), 850 (B1) | Complete | Complete | Complete | Complete | The HVDC link was successfully commissioned, energised and handed over to the System Operator in line with baseline plan during December 2018. | The HVDC link was successfully commissioned, energised and handed over to the System Operator in line with baseline plan during December 2018. | There is currently no change to the delivery date. | There is currently no change to the delivery date. | 2016 Q4 | Complete | Complete | Complete 2018 Q3 | Complete 2018 Q3 | http://www.ssepd.co.uk/CaithnessMoray/
1HP | SPT | Beauly-Denny 400kV line to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from North to South of Scotland | Northern Scotland (B1) to Central Scotland (B4) | Yes | 1200 (B4) | [8 empty] | 2014 Q4 |  |  |  |  | http://www.spenergynetworks.co.uk/pages/beauly_denny_overhead_line_upgrade.asp
2NP | SPT | Incremental Reinforcement: (a) Series Compensation (b)) East-West 400kV Upgrade To accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from Scotland-England | Central Scotland (B6) to Northern England (B6) | No | 1100 (B6) | 5. Construction | 5. Construction |  |  | (a) All installation and commissioning works are complete. (b) ) The installation and commissioning of both circuits (TORN ECCLS2) and (TORN ECCLS1) are complete and in service, with the second circuit being completed in April 18. Minor modifications were completed on both circuits in May 19. All works now complete. |  | (a) Series compensation - Complete (b) East-West 400kV Upgrade - Complete |  | (a) 2015 (b) 2016 Q4 | April 18 - In service May 19 - minor modifications complete |  |  |  | N/A
1NP | SPT | Western HVDC link to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and improve security of supply | Central Scotland (B6) to NW England (B6, B7, B7a) | Yes | 2200 (B6) | 5. Construction | 5. Construction |  |  | Following final tests and commissioning works undertaken in November 2019, the link was taken over on 22 November 2019 |  | Following final tests and commissioning works undertaken in November 2019, the link was taken over on 22 November 2019 |  | 2015 | Following final tests and commissioning works undertaken in November 2019, the link was taken over on 22 November 2019 |  |  |  | http://www.spenergynetworks.co.uk/pages/western_hvdc_link.asp
11HP | SPT | (i) East Coast 400kV Upgrade to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from Scotland-England | Northern to Central Scotland (B4) | Yes | TBC |  |  |  |  | Subject to network conditions, some final noise and EMF are likely to take place during October, these do not impact link performance |  | Subject to network conditions, some final noise and EMF are likely to take place during October, these do not impact link performance |  | 2017 Q1 | Subject to network conditions, some final noise and EMF are likely to take place during October, these do not impact link performance |  |  |  | N/A
| SPT | (ii) Central 400kV Upgrade (Denny – Wishaw ) to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from Scotland-England | Northern to Central Scotland (B4), Central Scotland (B5) and Central Scotland to Northern England (B6) | No | 1700 (B5) | [8 empty] | 2017 |  |  |  |  | N/A
3NHP | SPT | Eastern HVDC Link to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and improve security of supply | NE Scotland (B4) to NE England (B6, B7, B7a) | Yes | 2200 (B4) 2200 (B6) 1000(B7) 700 (B7a) | 2. Optioneering | 2. Optioneering | See 'RAG Status Notes' | See 'RAG Status Notes' | We have been looking at a range of options as part of the Strategic Wider Works process to provide the capacity onshore and offshore. NOA 18/19 recommended two links: one for delivery in 2027 and one in 2029. | We have been looking at a range of options as part of the Strategic Wider Works process to provide the capacity onshore and offshore. NOA 18/19 recommended two links: one for delivery in 2027 and one in 2029. |  |  | 2018 | The EISD for Torness - Hawthorn Pit is 2027; EISD for Peterhead to Drax is 2029 as per NOA 18/19. |  |  |  | N/A
13HP | SPT | Hunterston ‐ Kintyre 240MVA AC subsea link to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from North to South of Scotland | Northern Scotland (B3) to Central Scotland (B3) | Yes | Up to 350MW additional generation | [8 empty] | 2015 Q4 |  |  | Completed in Q2 2016 | Completed in Q2 2016 | http://www.spenergynetworks.co.uk/pages/kintyre_hunterston_link.asp
1P | SPT | South West Scotland Collector Network to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from Scotland-England | Southern Scotland | No | Up to 800MW of additional generation by 2018 | 5. Construction | 5. Construction |  |  | Complete | Complete | Complete | Complete | n/a | Complete | Complete |  |  | http://www.spenergynetworks.co.uk/pages/south_west_scotland_connections_project.asp
1NP | NGET | Western HVDC link - HVDC cable and converters to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and improve security of supply | Central Scotland (B6) to NW England (B6, B7, B7a) | Yes | 2200 | Complete | Complete | Complete | Complete |  |  |  |  | 2015 | Formal take over of the link took place on 22nd November 2019 with the link now fully operational in both directions. (2250MW continuous and 2400MW short term) Final noise and EMF assessments, which do not impact link performance, are to be scheduled when network conditions allow. | Formal take over of the link took place on 22nd November 2019 with the link now fully operational in both directions. (2250MW continuous and 2400MW short term) Final noise and EMF assessments, which do not impact link performance, are to be scheduled when network conditions allow. | Completed November 2019 | Completed November 2019 | http://westernhvdclink.co.uk/
2NP | NGET | Scotland-England Reinforcement (Series and shunt compensation) to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and improve security of supply | Central Scotland (B6) to Northern England (B6) | No | 1000 | [8 empty] | 2015 |  |  | Completed in 2015 Q1 | Completed in 2015 Q1 | N/A
3NHP | NGET | Eastern HVDC Link to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and improve security of supply | NE Scotland (B4) to NE England (B6, B7, B7a) | Yes | 2200 (B4) 2200 (B6) 1000(B7) 700 (B7a) | 2. Optioneering | 4. Planning |  |  | NOA 2020/21 gave a 'Proceed' for the E4D3 and E2DC projects. We continue to progress key onshore design and consenting work in parallel to the offshore seabed surveys to maintain programme. The Initial Needs Case for both projects has been submitted to Ofgem and is curently being reviewed. | NOA 2020/21 gave a 'Proceed' for the E4D3 and E2DC projects. We continue to progress key onshore design and consenting work in parallel to the offshore seabed surveys to maintain programme. Non-Statutory Consulation has commenced for the NGET onshore works for both projects. The INC is currently out for consultation by Ofgem. | None identified at this stage. | None identified at this stage. | 2018 | The EISD for Torness - Hawthorn Pit is 2027; EISD for Peterhead to Drax is 2029. | The EISD for Torness - Hawthorn Pit is 2027; EISD for Peterhead to Drax is 2029. |  |  | https://www.nationalgrid.com/uk/electricity-transmission/network-and-infrastructure/segl1 https://www.nationalgrid.com/uk/electricity-transmission/network-and-infrastructure/segl2
4N | NGET | Western HDVC Link: - Deeside / Connah's Quay substation Works only | Northern Wales and NW England | No | N/A | [8 empty] | 2015 |  |  | Completed in 2014 Q3 | Completed in 2014 Q3 | N/A
5N | NGET | Scotland-England Reinforcement (Harker-Hutton reconductoring) | Northern England (B7) | No | 1400 | [8 empty] | 2014 |  |  | Completed in 2013 Q4 | Completed in 2013 Q4 | N/A
6N | NGET | North Wales (New 400 kV, Pentir – Wylfa Transmission circuit) to accommodate connection of large amount of offshore wind and nuclear generation in the North Wales and renewables connection from Ireland | North Wales (NW1) | No | 3800 | [8 empty] | 2018 |  |  |  |  | http://www.northwalesconnection.com/
7N | NGET | North Wales (Second Pentir – Trawsfynydd 400 kV Transmission circuit) to accommodate connection of large amount of offshore wind and nuclear generation in the North Wales | North Wales (NW2) | No | 2220 | [8 empty] | 2016 |  |  |  |  | http://www.northwalesconnection.com/
8N | NGET | North Wales (Deeside – Trawsfynydd series compensation) to accommodate offshore wind and nuclear generation in North Wales | North Wales | No | TBC | [8 empty] | 2015 |  |  |  |  | N/A
9N | NGET | North Wales (Reconductor Trawsfynydd – Treuddyn) | North Wales (NW3) | No | 2800 | [8 empty] | 2014 |  |  | Completed in 2014 Q4 | Completed in 2014 Q4 | N/A
10N | NGET | Wylfa-Pembroke HVDC Link to accommodate connection of large amount of offshore wind and nuclear generation in the North Wales | North Wales (NW1, NW2, NW3, NW4) | No | 2000-2500 | [8 empty] | 2017 |  |  |  |  | N/A
11N | NGET | Central Wales (Mid Wales 400kV substation and Transmission circuit) to accommodate connection of new onshore wind in Mid Wales | Central Wales | No | 1800 (Infeed Loss Risk Criterion) | [8 empty] | 2016 |  |  |  |  | http://www.midwalesconnection.com/
12N | NGET | Humber - Killingholme South New Substation (KISO); and new transmission circuit from KISO to West Burton to accommodate connection of new Round 3 offshore windfarms and new CCGT generation within Humber area | NE England (EC1) | No | 3900 | [8 empty] | 2018 |  |  |  |  | N/A
13N | NGET | East Anglia (i) Reconductoring Bramford-Norwich + | East Anglia (EC5) | No | 400 | [8 empty] | 2015 |  |  |  |  | N/A
13N | NGET | East Anglia (ii) Bramford Substation Reconfiguration to accommodate connection of new offshore windfarms (Round 2, 2.5 and 3) and new CCGT generation in East Anglia |  | No | N/A | 5. Construction | 5. Construction |  |  | While there have been delays in delivery, the network remains compliant and we are able to connect customers at the dates requested. | While there have been delays in delivery, the network remains compliant and we are able to connect customers at the dates requested. | While there have been delays in delivery, the network remains compliant and we are able to connect customers at the dates requested. Progress of works is supported by cost-benefit analysis. | While there have been delays in delivery, the network remains compliant and we are able to connect customers at the dates requested. Progress of works is supported by cost-benefit analysis. | 2015 | 2022 | 2022 |  |  | N/A
14N | NGET | East Anglia (New Bramford – Twinstead 400kV Transmission circuit) to accommodate connection of new offshore windfarms (Round 2, 2.5 and 3), nuclear and new CCGT generation in East Anglia | East Anglia (EC5) | No | 2600 | 1. Scoping | 4. Planning |  |  | A reinforcement of this nature was given a 'Proceed' recommendation in previous NOA cycles and is part of customer connection agreements. Work is ongoing to determine how the project is taken forward. | The project has progressed and a round of non-statutory consultation has been completed. |  |  | 2018 | The EISD for the project in NOA is 2028/29. | The EISD for the project in NOA is 2028/29. |  |  | https://www.nationalgrid.com/uk/electricity-transmission/network-and-infrastructure/bramford-twinstead
15N | NGET | London (Uprate Hackney – Tottenham – Waltham Cross circuit to 400kV+ Pelham Rye House Reconductoring) to accommodate connection of new offshore windfarms (Round 2, 2.5 and 3) and new CCGT generation in in East Anglia and high demand in London as well as possible coincidental interconnector exports | London (B14) | No | 800 | [8 empty] | 2015 |  |  |  |  | http://www.northlondonreinforcement.com/
16N | NGET | South West (Hinckley Point – Seabank and assoc. infra. Works) to accommodate connection of new nuclear in South West | SW England (B13) | No | 2400 | 5. Construction | 5. Construction |  |  | None identified |  | Programme aligned to customer connection dates and requirements |  | 2019 | 2024 |  |  |  | http://www.hinkleyconnection.co.uk/
17N | NGET | North West Coast Connection - (Harker to Middleton and assoc. infra. works) to accommodate connection of new nuclear in Cumbria | Northern England (B7) | No | 3387 | [8 empty] | None |  |  |  |  | http://www.northwestcoastconnections.com/