## Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. This review took place in October 2020.
Title: China Prosperity Fund Phase One
Programme Value: £85m[1]	Programme Value: £85m
[1] As announced in the 2020 Spending Review, the UK will temporarily reduce how much we spend on Official Development Assistance (ODA). We will spend 0.5 per cent of our national income (GNI) on ODA, rather than 0.7 per cent. As a result, documents which pre-date that reprioritisation may not accurately reflect the programmes in their current form.

Summary of Programme Performance
Year	2018	2019	2020
Programme Score	n/a	A	A
Risk Rating	n/a	Major	Major

Summary of progress and lessons learnt since last review:
The China Phase One programmes have made significant progress since the last Annual Review (AR). All four programmes (Energy & Low Carbon Economy, Infrastructure in Third Countries, Financial Services and Business Environment) moved from inception to implementation during the June 2019 to June 2020 review period, with a few comments about progress since that date, where it is material.

China Business Environment (BE)
The main programme began its inception phase in November 2019, completing in May 2020. One of the key approaches to delivering its strategic objective is to improve the business environment in China, by strengthening the legal and regulatory framework through grants and contracts. The programme is looking to sign its first grants in autumn 2020, working in sectors such as protecting intellectual property for UK/international firms, strengthening anti-money laundering and improving commercial dispute resolution. The sub-programme with British Standards Institute (BSI) completed its inception phase in November 2019, then moved into implementation; working to raise Chinese standards to UK/international levels across 11 sectors. The programme has already contributed to three major business environment reforms: China’s Foreign Investment Law Implementation Regulation, the revision of the Anti-Monopoly Law and the Chinese Supreme Court’s judicial interpretation of force majeure clauses in contracts.

Energy and Low Carbon Economy (ELCE)
In August 2019, inception for the main programme began. This ended in December 2019. In November 2019, the call for bids was launched for grants for the programme across the different pillars (promoting clean energy technologies, pushing the transition away from coal, reform of the power sector, and pushing China to be a more responsible player in engagement with third countries, and the international energy fora). This led to 25 projects being awarded over summer/autumn 2020. The sub-programme with Chatham House on assessing climate risk in China began in November 2019, with inception finishing in May 2020. It is on track to deliver its first set of reports. The programme is also working with the World Bank in Shanxi province (China’s 2nd largest coal producer), helping assist its transition away from coal. Our funding of the programme is conditional on Shanxi province capping coal production and restricting the number of new coal plants.

Financial Services (FS)
The main programme’s inception began in September 2019 and ended in February 2020. From January, projects were formulated across different pillars of the programme (financial stability, pension reform, insurance reform, financial inclusion and fintech). Both the call for bids (for grants) and invitation to tender (for contracts) were launched in summer 2020. As of October 2020, the programme is seeking to sign off approximately 20 projects. The inception period for the sub-programme with the International Finance Corporation (part of the World Bank Group) on climate change adaptation for farmers ended in March 2020. The first pilot ran successfully in summer 2020; 5,884 households purchased crop insurance, some of whom received pay-outs following extreme weather. Negotiations are now ongoing to extend the pilot to more provinces.

Infrastructure in Third Countries
This programme moved into implementation in September 2019, identifying a list of over 30 innovative infrastructure projects from which to select pilots. This has been subject to some change, with some proposals (e.g. in Nepal) withdrawing at a later phase. Nonetheless, the programme successfully launched its first pilot, a sustainable roads project in Kenya, which is now nearing financial close. This will run in parallel with the development of technical assistance products that will inform policy and practice to bring long-term impacts beyond the life of these projects (e.g. Environmental and Social Governance (ESG) standards and best practice). The programme also held investor facilitation events in third countries.

The PF China Portfolio has taken on-board lessons from the last AR:

The team developed an overall narrative for ODA in China in December 2019 and June 2020, to make the case for development programming; but also to set out the transition as China graduates out of ODA (though COVID-19 will have set back progress).

The Primary Purpose and Secondary Benefits strategies were embedded in the inception reports for the main programmes across the four Phase One programmes. G&I outcomes are better integrated in programme ToC and logframes. Progress on G&I is also reflected in the G&I scorecards.

VfM strategies were also set out as part of the inception reports; with progress reported upon as part of the VfM scorecards.

The central team developed an overarching communications strategy in November 2019. The Counsellor and central team have since developed multiple communications documents, narratives and databases to articulate the aims of the programmes. This includes what is being achieved under primary purpose, secondary benefits and global good, as well as Chinese stakeholder engagement (e.g. matched funding). The products are also tailored to suit a variety of audiences.

All programme Steering Boards have clear ToRs; and have representation from the FCDO development team (ex-DFID) or JFU to advise on development impacts.

All logframes have been updated with clearer indicators and additional milestones/targets. Most have been finalised, but some will need minor revisions to take account of budget changes in the light of ODA reprioritisation.

- Procurement has greatly improved with the hiring of a Head of Procurement in the central team. All outstanding issues are collated and discussed weekly.
- The central team updated its Learning & Development plan in autumn 2019. The team has also organised core training (e.g. on Prince2). A decision log has been developed, putting all procurement/finance decisions into a matrix.
- A programme of peer-learning sessions addressing cross-cutting issues were facilitated by programme and central teams, covering a range of topics from fund-management models to best practice on working with CPG (Corporate Procurement Group).

UK expertise has been invaluable; for example in macro-economic stress testing (Chinese stakeholders stated that they value the Bank of England ’s expertise in this area); working with Oxford University to model climate risk; and developing transparent models of procurement, and models of Public Private Partnership for infrastructure projects.

The programmes have started to deliver impressive outcomes: recommendations from a Business Environment programme report have fed verbatim into post COVID-19 Chinese business law; Chinese stakeholders stated that before the Energy and Low Carbon Economy programme, they did not consider how the risk of climate change impacted disadvantaged groups (including women) disproportionately; the Financial Services programme has reached nearly 6,000 rural farmers with all-weather insurance products to help them adapt to climate change - multiple times the number of similar programmes in other middle-income countries over the same time period; and the Infrastructure programme’s sustainable road project was the first of its kind in bringing together Chinese and UK construction companies/institutional investors, integrating ESG into construction design and delivery opportunities to encourage local pensions firms to invest.

As covered in the last AR, there were delays to the start of the programme, substantially caused by delays to procurement. In addition, COVID-19 has had a negative influence, for example on the inability to hold events with Chinese stakeholders. Furthermore, at the start of the COVID-19 pandemic, PF staff were moved into crisis work, for example in repatriating UK nationals in China or procuring PPE equipment for the NHS. The teams have moved swiftly to mitigate some of the delay, for example online engagement with Chinese ministries as well as the implementing partners.

Looking ahead, the biggest risks are that:

The past delays mean that the programmes now have a maximum of 18 months implementation to deliver outcomes. The PF China team has requested that programmes be extended for at least an extra year, but this has not been possible; as that will move into a new Spending Review period.

The 60% plus ODA in-year cuts that the programmes faced in 2020/21 are made permanent (or that the financial envelopes are reduced even further) for the 2021/22 year. The programme’s contracts, grants and MoUs have built in clauses to allow the FCDO to reduce budgets at short notice, but as we have seen with this year’s budget reductions, this takes significant time and management oversight.

Both these risks could significantly reduce the impact the programmes will have, including on promoting gender equality and achieving the SDGs. Such risks are reflected in the recommended higher risk rating for this programme (Major).

List of overarching recommendations for the next year:

STRATEGIC ISSUES:

Make the case for extending programming in China, with a portfolio that evolves in line with FCDO priorities. Where interventions remain aligned to HMG priorities, giving implementers more time to deliver them is essential. Extending implementation beyond March 2022 would do more than anything else to enable PF China to achieve its objectives.

Primary purpose. There is more to do if PF China is to have a significant impact on G&I, in a challenging, enabling environment; in particular, there is much still to be done to increase capacity of ‘third hand’ delivery partners, especially Chinese institutions (such as those that are the target for the Climate Risks programme, or the BSI standards work).

Steering Board effectiveness. An overarching PF Steering Board, alongside the Steering Committees for each programme would be welcome, to assess and make the strategic case for Prosperity Fund. Looking ahead, we will need to cover ex-DFID programmes as well.

Consider submitting a change request, when the extent of budget cuts becomes clear. By 'change request' we mean a note informing the prosperity fund portfolio board that the programme no longer expects to achieve the same outcomes now stated in the business case, and explaining the main reasons why (budget cuts, procurement delays and COVID-19.)

List of Acronyms:

AML	Anti-Money Laundering
AR	Annual Review
BC	Business Case
BE	Business Environment
BEIS	Department of Business, Energy and Industrial Strategy
BRI	Belt & Road Initiative
CDR	Commercial Dispute Resolution
CTSG	China Technical Support Group
DFID	Department for International Development
DIT	Department for International Trade
EL	Evaluation & Learning
ELCE	Energy and Low Carbon Economy
FATF	Financial Action Task Force
FCO	Foreign and Commonwealth Office
FDI	Foreign Direct Investment
FS	Financial Services
G&I	Gender & Inclusion
IFC	International Finance Corporation
IIOC	FCDO Investment Committee
IP	Intellectual Property
JFU	Joint Funds Unit
KPI	Key Performance Indicator
M&R	Monitoring & Reporting
MoU	Memorandum of Understanding
MREL / NDCs	Monitoring, Reporting, Evaluation & Learning / Nationally Determined Contributions
OBC	Outline Business Case
ODA	Official Development Assistance
PDP	Primary Delivery Partner
PF	Prosperity Fund
PFDU	Prosperity Fund Delivery Unit
SBs	Secondary Benefits
SDA	Social Development Advisor
SDGs	Sustainable Development Goals (SDGs)
SRO / TA	Senior Responsible Owner / Technical Assistance
ToC / ToR	Theory of Change / Terms of Reference
UNFCCC / VfM	United Nations Framework Convention on Climate Change / Value for Money

SRO Commentary
This has been a hugely challenging year for the China prosperity fund team. Not only did they need to navigate the complexities of a pandemic which started here; they also had to manage an in-year budget cut of 68%, adapting and flexing programming to meet Ministerial instruction around a sharpened focus on post-COVID health and pre COP26 climate change. It is testament to the abilities of our expert teams, their contacts, their inventive approaches and their programming experience, and that the portfolio managed not only to continue to deliver throughout, but that they considerably outperformed reduced expectations associated with vastly reduced budgets.
I endorse the recommendations of this report fully. Programming in China is essential to opening and keeping open the doors and the mechanisms that ensure permanent policy changes here in China that contribute to better equality and inclusion domestically, global good, and UK benefit. A sharp end to the teams, their contacts, the resources in April 2022 would undo considerable benefits in areas that matter to the UK. This includes gender and inclusion on which teams have worked hard but this agenda has suffered considerable COVID era setbacks in China (and globally).
COVID has also impacted on frequency and effectiveness of our steering board, which did not manage to meet during the crisis. The high likelihood of further change means that embedded further change requests will also be important to managing expectations of what can and cannot be achieved in health, climate change, and regulatory change for the better and global development on reduced budgets.

JFU Commentary
China Prosperity Fund Phase 1 Programme operates in areas of critical strategic concern for HMG, and the year under review demonstrates the importance and potential of ODA spend in China to support global economic resilience and global goals – but rightly under high scrutiny.
JFU is happy to see some impressive policy and other benefits coming through, especially on Financial Services and Business Environment. Good progress has also been made on embedding G&I across the programme, although we agree that more remains to be done & it will be important to set out a concrete plan to ensure that progress towards inclusive growth & poverty reduction is targeted and tracked. It is good to see progress on operational areas of concern flagged in last year’s Annual Review, in particular procurement and MREL. Progress during the year under review has been significantly hit by COVID, but the team appears to have managed COVID disruption well, and is to be congratulated on this.
JFU supports the recommendations of the review and recommends a mechanism for tracking response & implementation to Annual Review recommendations, including those from 2019 that are still underway, particular those that focus on strengthening coherence of the overall programme, particularly on Primary Purpose, VFM & secondary benefits.  JFU would also draw the programme team’s attention to JFU AR guidance on documenting changes to logframes.

## A. INTRODUCTION AND CONTEXT

DevTracker Link to Business Case:	TBC
DevTracker Link to Log frame:

The China Prosperity Fund (2017-2022) Phase One Portfolio has a budget of £85 million for ODA activities, and comprises of four programmes: China Business Environment, Financial Services, Energy and Low Carbon Economy, and Infrastructure in Third Countries. The portfolio is expected to lead to:
- an improved business environment through enhanced legal and regulatory framework and its implementation;
- a more efficient and inclusive financial system, less exposed to significant shocks;
- China making a quicker transition to a low carbon economy; and
- increased and more sustainable investment in China and ODA-eligible partner markets in higher quality infrastructure projects.

The Outline and Full Business Cases for Phase One have been approved. The China portfolio is led by the FCDO and managed by the Prosperity Fund team within the British Embassy in Beijing. For Phase One outcomes, see below:

- Outcome 1: New policies issued that facilitate China’s transition to a low carbon economy and an improved multilateral governance.
- Outcome 2: Strengthened policy environment and successful pilot infrastructure projects developed and integrated, leading to increased project quality and bankability.
- Outcome 3: Increased international expertise and private capital investment in Chinese outbound infrastructure projects.
- Outcome 4: Financial resilience for underserved populations through increased access to financial services following regulatory innovation and increased market competition.
Outcome 5: inclusive growth and poverty alleviation globally through more robust commercial dispute resolution mechanisms, stronger controls on money laundering, improved investment environment and intellectual property right protection; and increased trade and investment cooperation between Chinese and UK/international businesses.

Annual Review

This is the second PF China Phase One Annual Review. The review covers the period from the receipt of transition funding in June 2019 to June 2020. In addition, this review covers some key programme events after this period, including the ODA in year cuts, where these events are likely to have a significant impact on delivery. The period covered by this review comprised of programme mobilisation; moving programmes from inception to implementation.
In terms of limitations, the Phase One review covers a complex portfolio, including four substantial strands at different stages of procurement and transition to multi-year programmes, and has had, out of necessity, to be a light touch review.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment (Primary Purpose – inclusive growth, gender equality, women’s economic empowerment and poverty reduction)
The Portfolio has already achieved three major intermediate outcomes in its Business Environment programme, and has had some impact in the Financial Services programme.[2] Interventions are, in general, well designed and impressively ambitious, but in terms of outcomes, the programme needs more time to achieve full potential and meet expectations set by the Business Case. This is because time is short. After three years of design, approvals and procurement, most implementers have just 12-18 months to facilitate large-scale, lasting change. Extending the programme, or parts of it, would allow the programme to achieve or exceed expected outcomes. Doing so would also allow the programme to measure more of its outcomes, enhancing recognition for the UK’s cooperation with China.
[2] The IFC component of the programme has supported agricultural insurance pilots that have enabled 5884 households to insure their crops against weather hazards.
As well as the number and size of outcomes, this review has also considered how inclusive PF China’s outcomes are likely to be. The 2019 AR raised concerns here and made recommendations. Specifically, it recommended that the Portfolio better identify and monitor risks that project activities potentially harm women and disadvantaged groups. Equally, it recommended that the Portfolio identify and monitor how its activities contribute positively to gender equality and social inclusion, and use findings to mitigate risks and maximise positive contributions.
The programme has responded well, with HMG staff and delivery partners now understanding G&I better, and showing greater commitment to achieving it. When probed on how the programme would avoid certain scenarios whereby activities harm the interests of disadvantaged women and men, the review team found answers convincing. The programme has developed G&I strategies and action plans, and reflected G&I better in Theories of Change. Staff and delivery partners were able to explain how their activities would contribute either to gender equality or wider social inclusion.
Worryingly, some of the Portfolio’s progress on G&I could be undermined by budget cuts. Some Financial Services interventions that contribute to G&I have already been cut, and others risk being cut, as part of PF China’s 60% plus calendar year budget reduction. Given just how much money the programme needs to save this year, some reduction in G&I activity seems inevitable. There is a strong case, however, for PF China to protect those activities that contribute the most to gender equality and social inclusion.
Below we summarise progress towards outcomes, for each of the Portfolio’s four programmes.

Through Business Environment, Programme-funded independent expert advice contributed to China’s Foreign Investment Law Implementation Regulation and the revision of the Anti-Monopoly Law. Together, these two reforms should spur greater investment, innovation, productivity and consumer welfare.

The third programme-supported business environment reform is an excellent example of adaptive programming. As COVID-19 restrictions took effect in China in early 2020, many companies found themselves unable to fulfil contractual obligations. Companies felt forced to invoke the force majeure clause in their contracts, which until then, was relatively rare in China. Upon request, the programme collated and shared international experience on how judiciaries handle force majeure, producing recommendations for the Chinese context. These have fed directly into the Supreme People’s Court's guiding opinions on handling civil cases involving the COVID-19 epidemic, enhancing legal certainty, supporting SMEs and improving investor confidence.

In Energy and Low Carbon Economy, the programme has agreed to fund 25 projects providing research, training and technical assistance on how to decarbonise China’s power, heating and transport sectors. Programme interventions with key policy bodies in China are well placed to put forward policy recommendations based on research findings to the policy makers, as they develop the 14th Five Year Plan over the next year. Separately, programme support for a clean energy transition in Shanxi Province is likely to deliver additional environmental benefits. Programme-funded experts will assist Shanxi’s provincial government to plan a reduction of coal in the province’s energy mix, whilst managing the costs and effects on jobs. The pillar also has a third component, which also shows strong prospects of achieving outcomes; modelling of low carbon technology costs and climate risks is expected to inform China’s climate ambition, national and subnational climate change adaptation strategies.
The Financial Services programme is the first to go beyond intermediate outcomes, and record measurable benefits for disadvantaged women and men in China. The IFC component has helped to design and pilot new, digitally-enabled business models for agricultural insurance in China. At the time of writing, 5,884 households bought agricultural insurance from companies participating in the pilot. 71 per cent of these households included female farmers and 41 per cent are poor.[3] Households whose crops were exposed to a range of hazardous weather conditions received payouts, protecting them from worsening poverty. As this pilot moves into a wider roll out in late 2020, and running into the next financial year, the plan is to offer weather-based agricultural insurance across 50 counties in China; if participating businesses can attract enough customers to make the business viable over the long-term, large numbers of low-income farmers could benefit by protecting their food and incomes from weather hazards – and the worsening effects of climate change.
[3] IFC data. To decide which households count as ‘poor’, IFC has used the Government of China's poverty definitions.
In Infrastructure, programme support has been instrumental in progressing development of a landmark PPP road project in an impoverished region of northern Kenya, ensuring resilience to the effects of a changing climate; and help local people and businesses adapt to climate change. In Kenya and other developing countries, Chinese and UK companies are showing greater appetite to collaborate, and greater awareness of their respective strengths, as a result of the programme’s activities. However, the length of time that major infrastructure takes to design, approve and build means that infrastructure users will only begin to benefit sometime after March 2022, when the project is scheduled to end. Whilst the shortage of time for implementation is a concern across all four programmes of the China portfolio, it is particularly acute here, given how long infrastructure projects take to complete. Gender and social inclusion are important elements of outcomes in this pillar, for example disaggregating data on people with access to new or improved infrastructure, and measuring community engagement and consultation by Chinese and third country project delivery companies supported by the programme.
Annual outcome assessment (Secondary Purpose)
The PF China programme has made impressive contributions to international, including UK exports, investment and soft power. Whilst pursuing their primary purpose of inclusive, green growth and poverty reduction, PF China programmes have strengthened UK-China relations and showcased UK expertise. HMG has leveraged relationships built through ODA programming to encourage reforms in China which will benefit the wider world, including the removal of market access barriers. The programme has also leveraged its relationships and expertise to help DIT attract Chinese investors to the UK, to encourage reforms that support UK investment in China, and to support China in adopting international standards. Using non-ODA, and leveraging relationships strengthened through ODA programming, the Prosperity Fund has so far contributed to £912 million of UK exports. Through the non-ODA UK-China Infrastructure Academy, the Fund has also facilitated £5.6 billion of Chinese investment in the UK.
Overall output score and description
The programme scores an ‘A’ in this Annual Review. The score reflects the fact that programmes have progressed as much as can be expected in the review period. Procurement delays, COVID-19 and UK-China political tensions have affected progress. However, the way that the programme has continued procurement and delivery despite COVID-19 is a notable positive, and has helped to maintain momentum. For a more detailed assessment of progress in each programme pillar, see section C.

Key lessons
- Continued updates and refinements of logframes have been important. Firstly, to maintain clarity about what the programme expects to change, as the number and choice of interventions changes (e.g. in response to COVID-19). Secondly, to adapt measurement plans, so that measurement remains focused on what the programme expects to change.
- We cannot assume that the programme will be extended beyond March 2022. It is therefore critical to consider how to maximise impact when time is short for implementation.
- More of PF China’s portfolio contributes to climate change adaptation and mitigation than previously recognised. For example, interventions on agricultural insurance and climate risk analysis in the Financial Services programme; on climate resilient road building in northern Kenya in the Infrastructure programme; raising standards on battery technology, sustainable cities and remanufacturing in the Business Environment programme, make valuable contributions to climate change adaptation and risk management.
- Requiring lead delivery partners to tender most implementation to third organisations has exacerbated delays. Where HMG has partnered with multilaterals or allowed lead (commercial) delivery partners to implement activities in-house, progress has been faster; all four interventions that have achieved intermediate outcomes are delivered by multilaterals or lead delivery partners in-house. On the positive side, calls for bids have been well publicised, and interest from Chinese institutions has exceeded expectations.
- Delivery partners have performed better when their teams include both deep development expertise and China expertise. For example, in the Infrastructure programme, the recent involvement of development experts has greatly improved understanding of how interventions can contribute to gender equality and social inclusion. PF China should consider how to share some of the more recent G&I analyses across PF and HMG more widely, as examples of good practice.

Summary of changes to the logframe since the last Annual Review
The programme team created an interim logframe for the last AR. As programmes were still being designed, the interim logframe focused on progress in procurement and the results of activities paid for with transitional funding. The China Phase One Portfolio now has fully developed logframes for each of its four programmes. This AR uses the fully developed logframes to assess progress.
Each logframe has been revised in the year under review. Many of the changes were necessary updates. In each programme, PF China has either changed what it plans to deliver, or clarified what it plans to deliver. Adapting measurements in line with changes in strategy will help to keep the measurements relevant. Logframe quality and completeness have also improved with each iteration.
Three of the four programmes have also revised their output targets to reflect delays in starting implementation (caused mainly by protracted procurement). Financial Services and Business Environment have reduced output targets; Infrastructure now expects more of its targets to be hit in FY 21-22, as opposed to FY20-21. Energy have also considered timing when revising the logframe; targets now reflect an expectation that the programme's research, technical assistance and training will influence China's 14th Five Year Plan – seen as a golden window of opportunity for climate ambition.
## C: DETAILED OUTPUT SCORING

Programme:	Infrastructure in Third Countries Programme

Output	Indicator	Milestone		Progress / A few lines/one paragraph relevant to each output.	Score
		Mar 2020	Mar 2021
Knowledge products and capacity building on sustainable infrastructure delivered for officials and programme stakeholders through international expertise and methodologies adapted to the China and Third Country context	Indicator 1.1 / Number of knowledge products (e.g. reports, guidelines, methodologies and policy papers) on best practice for sustainable infrastructure, including Gender & Inclusion considerations, delivered to officials and programme stakeholders	3	5	Four initial Technical Assistance (TA) products have been developed in response to NDRC requests, on transparent procurement, financing mechanisms, ESG and dispute resolution (forming key parts of the infrastructure project lifecycle). These have been supplemented by additional outputs to support Chinese companies increase the quality of their projects, including guidance on PPP models, case studies of successfully financed projects in Africa and Asia and deep dives into Kenya and Uganda market requirements.	A+
	Indicator 1.2 / Number of programme stakeholders (e.g. officials, SOE staff, Partner government staff etc.) trained in best practice methodologies for sustainable infrastructure delivery	60	100	Several training events were scheduled for March 2020 but had to be postponed due to COVID-19. However, TA reports have been shared with and feedback received from 21 Chinese organisations as part of consultation and user testing. Dissemination of these reports and best practice methodologies will contribute to capacity building in lieu of formal training which will be delivered in the next phase of work. / It is hoped that training can take place in late 2020/ early 2021 enabling progress towards the milestone of 100 stakeholders trained.	B
Pilot infrastructure projects identified, and project preparation technical assistance delivered	Indicator 1.3 / Number of pilot infrastructure projects jointly agreed with NDRC and other programme stakeholders	1	2	One pilot project – the Kenya Lot 3 roads project - has been selected with further projects assessed. / Around 40 projects have been put forward by Chinese companies via the China programme sponsor and assessed as potential pilots. A key challenge has been the quality and stage of projects put forward, including ability to deliver outcomes and learning within the programme timeframe. Initial agreement was reached on two earlier projects in Kenya and Nepal, but the companies ultimately pulled out as they took alternative funding routes for the project. / COVID19 has also had a significant impact with many projects that were due to progress paused. Initial agreement has been reached with a Chinese company on a Malawi wind power project, but the project has been delayed by c.9 months by COVID-19 travel restrictions, and it has not been possible to progress the project as a pilot at present.	A
	Indicator 1.4 / Number of project preparation technical assistance interventions delivered (e.g. feasibility studies, business plans, environmental, G&I and poverty impact reports, funding plans etc.)	0	3	Progress against this indicator was delayed due to the first pilot only being selected in July. However, the programme has agreed 4 interventions on the Kenya project, including financial structuring to secure international financing, implementing a robust governance framework, independent monitoring during the construction phase, and support to meet international ESG, climate and G&I standards. / These interventions will lead to case studies that can be disseminated for wider impact (delayed to next FY due to budget reduction). / We expect to have delivered 3 technical assistance interventions relating to the Kenya pilot by March 2021, achieving the milestone.	A
Identifying and supporting new sustainable financial channels (especially with the use of international private capital) on Chinese-led infrastructure projects, including identifying and matching sponsors, developers and investors	Indicator 1.5 / Number of investor facilitation events held	3	5	Investment Facilitation activities have included: / In Dec 2019 the first UK-China collaboration event was held in Kenya with c.40 attendees from c.25 UK and Chinese companies as well as representatives from UK and China governments / A further 5 events in East Africa were planned for February and March 2020, but COVID19 meant that it was not possible to hold the events in person. Plans to move them online were deferred following the reduction in the programme budget. An event is planned in Kenya in Q4, building on the pilot project and previous UK-China event. / 2 insurance roundtable events were held in Hong Kong with c. 10 Chinese and international insurers to identify key barriers for participation of international insurers in Chinese-led infrastructure projects. / 2 financing roundtables were also held with 10+ major Chinese and international financers and multilaterals to test barriers for their participation and cooperation.	A

Key Points
There have been delays and limitations as a result of COVID-19, but this programme has made the transition from inception to implementation, and into initial period of implementation. Progress has been made on raising awareness and strengthening the capacity of Chinese companies to implement international best practice and standards. This has been achieved through the development of technical assistance products and the selection and initiation of the first pilot project.

It has taken time to identify the Kenya pilot project, and two other potential pilots were withdrawn at a late stage. Although there are hopes of identifying a Malawi wind power project as a pilot, COVID-19 travel restrictions are impeding progress.

On output 1, the initial focus was on preparatory work to analyse and understand the policies, behaviours and practices that impact the current approach by Chinese firms to delivering projects in third country markets. Activities included developing case studies, technical assistance (TA) reports, investor and business consultation and China policy research – all of which will support the programme in designing tailored interventions to bridge the gap from current practice to the desired future state. Building on this solid evidence base, activities then shifted towards influencing behaviour change through stakeholder capacity building and dissemination of TA products. This has included working with the NDRC to take forward TA reports in key areas, as well as holding the first UK-China Collaboration Event in Kenya.

The intention had been to move towards large-scale capacity building in Y2, but progress on this has been impeded by COVID-19. In response, the programme has adopted remote working practices. This has enabled delivery of many outputs, but formal training and capacity building events (indicator 1.2) that would follow (or be delivered alongside) the development of written outputs have been delayed.

The programme is innovative in design, and has potential to deliver significant benefits both to international businesses seeking to work with Chinese infrastructure companies, to third party countries and to beneficiaries (including those in disadvantaged groups) in those countries. However, some of that innovation comes from the interaction of the pilot programmes and the capacity building that is the focus of the first two output indicators. There are risks in having only one pilot programme, especially given that this pilot has yet to reach financial closure.

The programme team recognised the need to strengthen G&I and Primary Purpose approaches in this programme. This has led to the appointment of a specialist G&I and PP advisers, and a new G&I Lead. These appointments will allow the programme to draw on best practices, going forward. Early G&I interventions include an in-programme G&I review and recommendations to improve mainstreaming of G&I and Primary Purpose approaches.

A strategic planning exercise was completed at the start of Year 2 (April 2020) and was refined following the budget cuts arising from the ODA review in August. In response to the reduction in the Year 2 budget, adjustments have been made to the programme management regime to reduce the cost of programme management as a proportion of overall programme spend, while maintaining or improving quality of deliverables.

Summary of responses to issues raised in previous annual reviews (where relevant)
INF.1. Ensure sufficient China policy expertise internally and engagement with key policy influencers in China. Response: New approaches to China engagement were developed as part of the Year 2 workplan. This included substantial engagement and consultation with key stakeholders in output delivery. It also included confirmation of the stakeholders that will be delivery partners (including for future policy research) and those that are end users to test outputs with. The programme budget reduction will impact the timing and scope of activities this year, but engagement with China stakeholders remains the key focus for the programme. This has included engagement with 20+ stakeholders (including infrastructure companies and financing institutions) to obtain feedback on existing and future TA products. This was delivered through the Lead China Delivery Partner supply chain, including the China International Contractors’ Association (CHINCA), to ensure access to end users and obtain their engagement. The completion of the first China Research report has also included engagement on the current barriers and issues for project delivery, including identification of potential policy areas for further development. Finally, through our relationship with delivery partner Overseas Development Institute (ODI), we have developed dialogues with stakeholders in the China not-for-profit sector e.g. Syntao, working in partnership with CHINCA.
- INF.2 New Programme Logframe indicators and Key Performance Indicators (KPIs). Response: New indicators and KPIs were agreed at the end of Inception, following the last Review. A further refresh is currently taking place following the budget re-profile.
- INF.3 Clearer links to primary beneficiaries needed in Logframe, ToC and choice of activities and inputs. Response: The logframe has been updated to reflect results expected from the Kenya pilot, with a focus on the impacts on poor women and men.
- INF.4 More and multiple lines of communication and dialogue with Chinese stakeholders required. Response: See INF.1.

Lessons learned
Shifting focus in response to user insights: The programme has used lessons from the Kenya Annuity Pilot and other evidence to select four areas of focus for technical capacity building.[4] Selecting themes based on feedback from end-users of technical assistance should mean that they value this technical assistance more.
[4] These are: contracting, risk management, financial feasibility and financing strategy.
Prioritisation of activities for maximum impact: Following the budget reduction arising from the ODA review, discussions between the programme SRO and Delivery Partner took place to agree which of the activities planned for delivery in Year 2 should be prioritised. It was agreed that the activities that would best enable the programme to maintain momentum and make progress towards its overall objectives were the China workstream activities (priority TA development, technical capacity building and China policy research and enablement) and the Kenya pilot project. The revised Y2 budget was allocated accordingly.
Digital engagement: In response to the restrictions on in-person activities imposed due to COVID-19, the programme has accelerated the transition to virtual / digital-based activities and engagement with stakeholders. This includes delivering events including webinar-format training and virtual engagement meetings in lieu of in-person meetings.
Recommendations
INF. 1: Budget permitting, KPMG as lead delivery partner should invest in deepening its relationships with Chinese infrastructure financiers and construction firms. This will be important to avoid over-reliance on one or two individuals to share technical assistance with Chinese stakeholders, and to ensure that decisions are informed by up-to-date insights into what Chinese stakeholders view as feasible and desirable.

Programme:	China Business Environment Programme

Output	Indicator	Milestone	Progress	Score
Component 1 – PWC project
High-quality Technical Assistance (TA) products & services produced, including reform recommendation, training and knowledge exchange events on Commercial Dispute Resolution (CDR), Intellectual Property (IP) and Anti-Money Laundering (AML)	Number of strategic research pieces and reports developed	1	The programme has taken an adaptive approach to respond to emerging TA request on post-COVID economic recovery in the CDR strand. Most notably, the recommendations produced on contractual disputes involving force majeure have fed into the Supreme People’s Court's guiding opinions on handling civil cases involving the COVID-19 epidemic.	A
	Number of knowledge exchange and advocacy events completed	1	The ‘Copyright Protection in the Digital Environment’ project established a successful partnership with e-commerce company Alibaba to deliver an IP Webinar for IP rights holders, targeting Small and Medium Enterprises (SMEs).	B
Component 2 – BSI project (Standards strand)
Enhanced technical knowledge and capacities within the Standards Administration of China (SAC) and National Medical Products Administration on the adoption of international standards	International standardization process landscape mapping	6	BSI has delivered 6 sectoral mappings of the international standards adoption landscape, in comparison with the Chinese national standards. They formed the foundation of sector work plans, which were subsequently developed.	A
Improved SAC and SAC Technical Committees’ capacity on proposing international standards	Number of capacity building activities on processes for developing new work items for international standardization bodies	12	BSI has designed the training programme and material. Largely due to COVID-19, the activities were postponed to Q3 2020.	B
Component 3 – World Bank project (Investment Environment Strand)
Improved technical knowledge and capability of the Government of China to align with international best practices in investment environment	Number of diagnostics and policy recommendation paper	10	The World Bank produced 10 policy papers on Foreign Direct Investment (FDI) reform, competition and competitive neutrality to key government departments. / The World Bank contributed to the improvement of the Foreign Investment Law Implementation Regulation and the revision of the Anti-Monopoly Law. The World Bank also successfully advocated the National Development and Reform Commission to remove specific restrictions on Foreign Direct Investment and further liberalise the entry regime and negative list. This included recommendation on foreign investment in the health sector, following specific request from the Chinese government in response to COVID-19.	A
Improved technical knowledge and capability of the Government of China in delivering better Ease of Doing Business (EoDB) measures	Number of beneficiaries receive EoDB training	50	The World Bank delivered training on EoDB methodology to 80 national and regional government officials in Chongqing.	A

Key Points
The Business Environment Programme (BE) has supported China’s momentum on business environment reform as a key strategy to stimulate economic growth and promote post-COVID economic recovery. BE has delivered three major legal and regulatory changes at the Intermediate Outcome level, including on a) FDI, b) anti-monopoly and c) strengthening China’s legal regime on ‘force majeure’, supporting SMEs and improving investor confidence.
The PwC and BSI projects have moved from inception to implementation phase in May 2020 and November 2019 respectively. The inception phase and early stage of implementation served to establish a robust strategic direction for the programme and foster stakeholder relationships to drive forward delivery. The PwC project launched an investment environment Competitive Grants Facility in June 2020.
The BSI project has established a high-level working group between the UK and China’s National Standards Bodies to oversee project delivery. By engaging China within existing standards development organisations, BE is mitigating the rise of bilateralism in global standardisation and reducing the risk of fragmentation. The project has also developed the strategy and methodology for undertaking novel research on the social and economic impacts of international standards in China, to support evidence-based standard setting.
The BE programme team recognise that the chain - from BE interventions in legal and policy areas, which relate to predictability of the legal process and improvements in the business environment, to G&I outcomes - is a long one. In some cases, the G&I impact is reliant on assumptions that encouraging the growth of small businesses and increases in jobs in less developed areas of China in the medium to long term will automatically increase inclusive growth. However, the G&I strategy developed for the main programme is thorough, detailed and covers all work streams, exploring implications for the programme, and setting out ideas for areas of intervention.
Summary of responses to issues raised in previous annual reviews (where relevant)
- BE has developed an ODA justification paper to demonstrate how it will deliver its ODA impact in China through the programme interventions and Theory of Change.
- The delivery partners have developed a Gender and Inclusion Action Plan to address the gap of G&I strategy identified when the programme was still at its infancy design stage.

Recommendations
1. If the programme lifecycle is not extended beyond March 2022, then scale down the scope of PwC project on Workstream B.
2. Continue to monitor IP strand delivery capacity. Work with PwC to take mitigation action.
3. Deprioritise further training on Ease of Doing Business, due to concerns around its efficacy and other activities being better aligned with current HMG priorities.

Programme:	Energy and Low Carbon Economy Programme

Output	Indicator	Milestone	Progress	Score
Technical assistance activities (e.g. including feasibility studies, cost curve reduction, policy design, regulation, standards, and system integration) that support China’s increased deployment of clean technology.	Number of TA deliverables that support the increased deployment of clean energy technologies acknowledged by Chinese policy-makers	Baseline (0) / Planned: / Jun-21 (10) / Mar-22 (20)	These indicators are on track for delivery. Milestone deliverables from the first round of the approved grants projects are expected to achieve these indicators. / The joint effort from FCDO and Delivery Partner (ICF/Deloitte) programme teams during the COVID outbreaks did not cause major delay of 1st round of call-for-bid. The call-for-bid preparation started from inception phase, including getting the comprehensive grant manual agreed with both FCO commercial and PMO. In order to get the high quality bids from the market, the programme team in parallel conducted several market engagements in different regions in China. A series of webinars were delivered including on the bidding procedure, primary and secondary benefits, G&I, VfM etc. to the grantees. The awarded 25 grants gradually started their implementation since early Aug 2020. The selected grants cover 4 pillars of the programme with various policy intervention activities, More importantly they are endorsed by China National Energy Administration who will give strong government support during project delivery.	A
	Number of new collaborations with international partners (including the UK) with China that share best practices/lessons learnt and help overcome barriers and increase renewable technology deployment (such as policy, cost, deployment)	Baseline (0) / Planned: / Jun-21 (2) / Mar-22 (3)
	Number of new agreements (e.g. a new technical or industry working group, regulatory exchange, MoU, etc.) that increase the deployment of clean energy technology	Baseline (0) / Planned: / Jun-21 (1) / Mar-22 (2)
Technical assistance activities that support China's efforts to reduce coal consumption & production and support China develop approaches to managing socio-economic consequences (incl. G&I) of its energy transition.	Number of TA deliverables support China's efforts to reduce coal consumption & production and support China develop approaches to managing socio-economic consequences (incl. G&I) of its energy transition acknowledged by Chinese policy makers	Baseline (0) / Planned: / Jun-21 (5) / Mar-22 (10)	These indicators are on track for delivery. Milestone deliverables from the first round of the approved grants are expected to achieve these indicators. / Beside the 4 TAs that programme awarded under this pillar, the World Bank Programme to help reduce coal mines in Shanxi province is another programme under ELCE programme portfolio to contribute this output. The World Bank has agreed 3 core policy recommendations with Shanxi DRC and they’re now under internal review with all programme funders to reach agreement.	B
	Number of new collaborations sharing best practices/lessons learnt and help overcome barriers to reduce emissions from coal consumption & production help improve capacity to develop approaches to managing socio-economic consequences (including G&I) of its energy transition	Baseline (0) / Planned: / Jun-21 (2) / Mar-22 (3)
G&I activities are integrated in the technical assistance activities in order to promote increased awareness	Number of organisations trained	Baseline (0) / Planned: / Jun-21 (30) / Mar-22 (60)	These indicators are on track for delivery, / G&I strategy created during inception phase and will be updated once all grant awards are completed. / G&I information sessions are delivered to grantees at the different stages of call-for-bids. G&I training and materials for grantees have been delivered.	A
	Number of G&I toolkits (guidelines, checklists, formats) developed to be used by organisations	Baseline (0) / Planned: / Jun-21 (2) / Mar-22 (3)
(Chatham House) Policy analysis and outreach products are developed	Number of policy analysis and outreach products produced and positively reviewed and received by stakeholders including government and UK and international business	Baseline (0) / Planned: / Mar-21 (3) / Mar-22 (10)	These indicators are on track for delivery. / The Climate Risk Programme delivered by Chatham House started its implementation in May 2020. The programme team has established positive relationships with all government stakeholders centrally and locally, including the State Council. 1 policy analysis report was delivered in the first quarter of implementation, and 2 more are expected to be met by Mar 2021. Several workshops were planned to take place both online and offline to engage with wider stakeholders.	A
	Number of reads/downloads/access/views of products including by key stakeholders from Government and private sector international and UK business	Baseline (0) / Planned: / Mar-21 (2,500) / Mar-22 (10,000)

Key Points
ELCE moved from inception to implementation during the review period. The review period began with the programme launch event, as part of the UK-China Energy Dialogue, where a bilateral agreement on a Clean Energy Partnership was signed. The 1st call-for-bids then quickly started to build momentum during the inception phase; some minor delays were caused by COVID-19 and subsequent lockdown and travel restrictions in China and the UK. Several rounds of evaluations were conducted by the programme delivery partner, FCDO Energy policy team and Evaluation Committee which consists of BEIS, PF, and FCDO. The Programme Steering Committee and Advisory Board were also informed of the selected grants afterwards to secure their support to maximise the impact. These procedures are in place to ensure selected TA projects can best align with HMG objectives and China’s energy transition needs. The delivery partner is now finalising the second year work plan draft to be presented to the National Energy Administration (NEA) to for signing later this month with BEIS.
For the Climate Risk component, the implementation phase of the programme began in May 2020 and has been progressing within the designed framework, with outputs largely delivered as scheduled and ongoing deliverables anticipated to achieve intermediate outcomes in terms of bringing policy change. However, the COVID-19 pandemic brought difficulties to the programme including staffing and the implementation of programme activities.
However, in September President Xi announced in the United National General Assembly that China would strive to be carbon neutral by 2060. This is an extremely important statement globally, as it increases international attention on the NDC process of the UNFCCC and it raises the attention on China’s 14th Five Year Plan. Also, the breakout of pandemic brought about discussion on natural resource governance. It has been recognised by government officials that the work of this programme, and in particular in its previous phases, has positively contributed to the discussions about introducing more ambitious targets and increasing mitigation actions in China.
In terms of G&I ambition, both the Climate Risk and the energy and low carbon components are committed to achieving the minimum level – do no harm, although, given the subject matter, it could be queried whether this programme should be seeking at least to achieve empowerment levels of change in key areas.
Summary of responses to issues raised in previous annual reviews (where relevant)
ELC1: A more clearly articulated line of sight to achievement of primary purpose should be developed. One way to do this will be to strengthen the approach to gender and inclusion through commissioning an evidence piece on gender equality and energy sector reform from the Work and Opportunities for Women (WoW) helpdesk. Logframe indicators to show this a little more clearly should be developed.
Response: programmes have embedded G&I elements to every layer of the logframe with relevant indicators to measure the success, a robust G&I strategy and action plan that focus on energy and climate change sectors were developed during the inception phase, dedicated G&I experts will facilitate the programme implementation to continue strengthen the approach.

ELC. 2:	Now that the programme is moving steadily into inception and thereafter implementation, construction/formulation of the output should be modified to take account of that changed situation. Something along the lines of “Generation of evidence to inform improved programme primary and secondary benefit output objectives” is more appropriate, and the Strand team is encouraged to revise the logframe and indicators appropriately. Risks of non-attainment of the overall programme objective are probably Major, rather than moderate (discussed in ELC 6).
Response: The logframe has been updated right after the first call for bids to reflect selected TA interventions to the overall programme output. The logframe will be reviewed and updated regularly.

ELC 3. Building on the transitional phase achievements, this output should be reviewed and modified. The programme team should look at what it is that the Delivery Partner(s) are going to deliver – those are the new outputs, and then construct a supporting set of metrics than ensures that they can and do deliver. The identification and procurement of suitable additional training resources is part of that requirement.
Response: The logframe has been updated with new indicators to measure.

ELC.4. The formation of a fully functioning Energy Expert Exchange is a highly desirable output. The transitional phase focus of this section on internal governance arrangements as a measure of the success of that kind of forum can now be built upon to provide additional programme objective “stretch”. It is recommended that the team look outwards to what it is that adequate governance processes and structures are trying to achieve in China and with international counterparts, and set those metrics as outputs.
Response: The programme is using the golden policy window of the formulation of China’s 14th Five Year Plan to provide the most needed and urgent expert support. The NEA-BEIS Clean Energy Partnership workplan is the cornerstone of this programme.

ELC.5: Partnerships, with suitable defining metrics are perfectly sound output(s). The approach to work being undertaken is strongly endorsed (subject to caveats on “line of sight” to Primary Benefits)
Response: The programme team will continue using this approach.

ELC.6: RISKS: Overall are Major. Contracting & Procurement delays, need for better understanding and dialogue, and vulnerability to relationships with key Chinese interlocutors all combine to increase risk.
Response: The British Embassy has established a strong relationship with Chinese government after more than 10 years of strategic prosperity fund projects cooperation in energy sectors. During the call for bids, the programme has created links and working opportunities with new Chinese ministries. Regular meeting at working level and dialogue in ministerial level is ongoing. A new workplan is planned to be signed between BEIS-NEA for next year’s programme intervention areas. A MoU is considered to be signed with MEE as well.

Recommendations
1. China’s recent 2060 carbon neutrality announcement delivered a clear message that climate change and energy transition is the priority in China. Chinese government will take immediate actions to implement this top-down requirement, and extending the programme lifecycle beyond March 2022 can better contribute this agenda.

2. Delivery partner staffing capacity is severely impacted by COVID-19. Continue to monitor the team resources and take mitigation action if the situation remains unchanged.

3. Better digital communication channels to supplement traditional visits need to be further investigated.

Consider the costs and benefits of accepting additional proposals that have already been submitted, versus relying more on a second round of bids.

Programme:	Financial Services Programme

Output	Indicator	Milestone	Progress	Score
Programme fosters relationships with stakeholders, enhancing access and creating ‘windows of opportunity’	Average stakeholder interest score	Baseline (0) / Planned: / Mar-21 (3.5) / Mar-22 (4)	The FCDO Programme Team and Delivery Consortium Teams have continually engaged key stakeholders through the Inception Phase and early Implementation Phase, including significant stakeholder participation in: Greenhouse Sessions (3 days’ worth) in December 2019, Market Engagement Seminars (2, c. 200 participants) in May 2020 and continued ad-hoc engagement to develop project plans (multiple meetings with PBoC, CBIRC, CSRC, MoF, MoHRSS, NDRC). Plus PBoC Governor (Minister-level) sign-off of a plan of 50-project list that was approved internally by multiple Chinese ministries. Further stakeholder interest best gauged once projects underway.	A
Responding to learning, consultation and implementation context, programme delivers high-quality research, capacity building, dialogue and exchange, toolkits, frameworks and pilots	# of high-quality project deliverables produced, by category (cumulative) / (a) Research or learning product / (b) Capacity building / (c) Dialogue or exchange / (d) Toolkit, framework or blueprint / (e) Pilot (regulatory or market)	Baseline (0) / Planned (Mar-21): / (a) 29 / (b) 3 / (c) 22 / (d) 22 / (e) 3	After a stringent procurement process for grants and contracts, as well as development of a number of proposals designed by the Delivery Consortium, the Programme has a list of 19 “Green” projects ready to go right away, and a further 14 “Amber” projects that may get underway soon, depending on Steering Committee views. We have confidence the projects are of the highest quality and will deliver excellent impact; these projects will be starting in October/November and should be delivering a number of key deliverables this FY. The planned numbers will have to be revised down, including cancelling a planned second procurement round. A “Quick Win” project on pensions that recently concluded successfully engaged key regulators and policy experts in both the UK and China, and the final report was a high-quality piece of research that furthered our engagement with the regulators in China.	N/A
Programme introduces international (including UK) expertise, practices and/or experiences into China's financial services sector	£ of project deliverables utilising or highlighting international (including UK) expertise, practices and/or experiences	To be forecast in Oct-20 based on full project proposals	Given delay in finalising project list due to difficulties arising from the ODA reprioritisation process we have not got a final number for this as yet, though it should be finalised soon.	N/A
IFC: Conduct market surveys and work with an insurance-tech company and insurance companies to design agri-insurance products for farmers in the market	1a. Number of market surveys conducted / 1b. Number of new agri-insurance products designed	1 a. Baseline (0) / Planned: / Mar-21 (2) / Mar-22 (5) / 1 a. Baseline (0) / Planned: / Mar-21 (8) / Mar-22 (40)	The pilot project kicked off in March as planned and has progressed well despite impact of COVID-19. An initial desk research was conducted to gather evidence for pilot provinces selection, followed by extensive stakeholder engagement, including a number of online seminars with central and local governments, insurance industry experts and academia to collect views and relevant experience for improved product design. Two visits were conducted by the IFC team and its partners to Gansu and Guangdong respectively to meet up with local officials, insurers and others from the eco-system. The market survey for Guangdong has been designed drawing on experience from insurers and insur-tech companies, and will be disseminated to the market soon. / In the meanwhile, a UK-based insurance broker will support this intervention, with a team of 20 people based in China who possess extensive knowledge in China and other Asian market of WII products. The team will verify insurance modelling and review product design using their expertise to secure best interest of farmers. Commercial opportunities have also been identified in this market to secure project sustainability and prove secondary benefit.

Key Points
The programme has progressed well despite setbacks due to procurement delays and COVID-19. All inception phase activities were completed and the programme moved into implementation.
The team have managed stakeholder expectations against a particularly difficult backdrop of ODA reprioritisation. The programme has engaged external stakeholders continuously and there is still a huge demand for the work that will be done.
The programme team has driven a focus on achieving G&I outputs and outcomes, including through an emphasis on G&I during partner selection, and they have been supported by development specialists in the delivery team. G&I is effectively integrated into the Theory of Change and into the MREL plan, and the ambition of each intervention (minimum, empowerment, transformation) is clearly identified.
The programme has a clear set of innovative and thought-through project interventions, which make up an exciting suite of projects that will: support necessary engagement with China in financial services regulation, reducing risk to the global economy including the UK’s; create trade opportunities for UK companies in China’s nascent pensions and insurance markets, that will soon become the world’s largest; work with China to ensure climate change is accurately captured in financial risk measurements and that its considerable investment power is focused on ESG-positive assets; and, deliver consumer protection and financial education interventions that help poor and disadvantaged groups.
Summary of responses to issues raised in previous annual reviews (where relevant)
- Outcome statement “very ambitious”. Response: This will be revised down once a finalised list of projects is clear (target Q4 2020).
- FS1: “better articulate how the engagement has addressed, and where relevant, improved the design of programmes - from both a primary purpose and secondary benefit perspective”. Response: Significant progress in this element, particularly thanks to the development expertise of one of the delivery consortium partners, and through training.
- FS2: “Procurement, contract and programme management processes and guidance need to be further refined and tailored for Prosperity Fund China.” Response: A comprehensive Procurement Manual was created, and use in procurement processes.
- FS3: “For the future, the team should increase its expertise in monitoring progress with its projects and holding implementing partners to account.” Response: An excellent MREL strategy is in place including project level results chains to ensure impact is delivered.
- FS4: “Consider adding development expertise to the skills and knowledge base of the Steering Group.” Response: Over the review period, the programme team tried to engage DFID with some success. FCDO creation should solve this.
- FS5: “Complete missing third milestone & review all milestones.” Response: Logframe was completed.
Recommendations
FS1. Be prepared to reduce some projects to ensure lasting impact in other areas. But if possible, reflecting HMG priorities, protect the agricultural insurance work and other primary purpose elements of the programme, as well as the climate change and COVID-19 related work. Noting that the agricultural insurance work is also one of the best contributions to climate change adaptation in the Prosperity Fund's global portfolio, as well as a measurable contribution to women's economic empowerment.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
There was a significant underspend against the allocation (£5.8m, or 30.6%).. There was a low level of spend between July and October 2019 – mainly contracting and procurement delays - and a second slowdown between December 2019 and February 2020 – caused by national holidays and then the start of the COVID-19 crisis.
As a result of programmes moving into full implementation, we expected to see the level of underspend reduce in future. However, the impact of ODA reprioritisation over July-September 2020 will result in a lower FY 2020/21 spend than originally planned, but in line with the new budget allocations.
Financial year 2020/21 ODA reprioritisation budget revision overview
	Infrastructure	Financial Services	Energy and Low Carbon Economy	Business Environment	Total
Original Forecast	£4,480,000	£6,530,526	10,900,000	£6,900,000	£28,810,526
Revised Budget Allocation	£1,260,000	£2,060,000	£5,770,000	£3,170,000	£12,260,000

Financial spend in review year June 2019-June 2020
	Allocation	Actual spend	£ Variance	% Variance
STAFF COSTS (UK & local)	1,206,343	1,154,895	-51,448	-4.30%
TRANSITION FUNDING	401,987	492,532	90,546	22.50%
PLATFORM CHARGES	347,268	347,268	0	0%
PROGRAMME DELIVERY
BE Programme	5,377,066	3,861,205	-1,515,861	-28.20%
ELCE Programme	6,166,274	3,412,133	-2,754,141	-44.70%
FS Programme	1,457,251	1,406,945	-50,306	-3.50%
Infrastructure Programme	4,044,486	2,514,908	-1,529,578	-37.80%
TOTAL	19,000,675	13,189,886	-5,810,789	-30.58%

Administrative spend was 11.4% of all spend, primarily as a result of programme underspend. This was also caused by the stage in the programme lifecycle, with three programmes only starting inception some way into the year, and gaps between inception and implementation impacting delivery. Had the programmes delivered at the initial budgeted rate, administrative costs would still have been 8.2% of total spend.
The 22.5% overspend on transitional funding is the result of extending the period for this to take place, to maintain momentum given the delays in multi-year programme procurement. All four main programmes underspent against their allocation, as a result of procurement and contracting delays, COVID-19 issues and the start of ODA reprioritisation:
- Financial Services’ variance was lower than the other three programmes, as it had already made some adjustments to take account of the delays in moving to inception and beyond (although there were further in-year delays);
- Energy’s original forecast was overoptimistic in assuming that grants would be well into implementation during the review period, given that contracts are unlikely to be finalised until the end of Q2 FY2020/21;
- For Business Environment, the World Bank component was close to forecast, and, for the standards component, there was only a -7% variance, as underspend in the final quarter was balanced by a late payment once BSI had revised inception deliverables to bring them up to standard. The main variance was driven by the PwC main programme, caused by delays in completing inception and re-contracting delays between inception and implementation;
- Infrastructure experienced more impact from COVID-19 delays than other programmes due to third-country implementation, and also had planned for pilot work to be more advanced.

The key cost drivers for the programme have been identified as fee days and expenses for the six main commercial contracts. Within this, there are some factors that have driven variances, for example:
- Significant reduction in expenses due to reduced international travel since the start of COVID-19, limiting visits by international consultants and making study tours and exchanges impossible.
- Unexpected additional workloads. This Portfolio is breaking new ground in China, and much is unknown in relation to key drivers of contractors’ time. For example, the number of concept notes reviewed for Energy’s first call for grants was five times larger than had been expected, and consequently, five times as many full proposals had to be evaluated than had been planned. This required an increase in consultancy inputs to deal with the volume of work.

VfM performance
There has been considerable focus on VfM after the recommendations of the last annual review. Each programme or programme component has prepared a VfM strategy setting out indicators. There is, however, still no overall VfM framework for the China programme. This means that there are no overall VfM indicators to assess performance of the programme as a whole, or to support programme governance through identifying which programmes or parts of programmes are delivering better or worse VfM.
Performance against business case benefits estimation
To some extent, the economic appraisal conducted in the business case (BC) for phase one is still valid. There is no fundamental issue about the validity of the ToCs. The September 2019 Evaluation identified that the ToCs for the four Phase 1 programmes were at an early stage of maturity, but judged the overall direction and logic set out in the BCs was to be valid (with the possible exception of the Business Environment programme, which appeared over ambitious at that point). Thus, envisaged benefits set out in the outline business case have the potential to be realised.
However, there are some compelling reasons why performance may be lower than the original business case benefits estimation:
- Budget reductions and, in particular, time lost as a result of procurement and contracting delays are likely to reduce the overall level of outcome delivered.
- Business Environment and Financial Services models are based on small increases to Chinese economic growth. When dealing with an economy of the scale of China’s, and the underlying growth rate, which has already been restored since the COVID-19 pause in early 2020, even a conservative estimate of impact (as set out in the BC) gives high returns. However, it also means that small deviations in the variables to the models can result in significant changes up or down.
Overall, the China PF programme will still deliver VfM, but the level of benefits may be reduced in light of budget reductions, delays to project delivery meaning limited time to implement programmes, and changes in the political climate between China and the UK.
Performance against the 4 E Framework
The experience and expertise of the FCDO’s delivery partners has helped promote VfM, in particular economy and efficiency across programme delivery, including establishing VfM frameworks. All six commercially contracted programme components completed a VfM scorecard as a part of the preparation for the AR. Overall, the VfM frameworks are strong in relation to economy and efficiency, but are less strong on effectiveness and equity.
Economy
FCDO’s procurement framework was used for the appointment of suppliers. This was a competitive process in which bids were assessed on cost, the quantity and quality of proposed deliverables and suppliers’ capability and capacity to deliver. Where it was appropriate to work through multilaterals (essentially the World Bank or International Finance Corporation), this delivery option was selected.
Several programmes are managing competitive tenders and grants processes for third-party subcontractors. Considerable attention has been placed on the procurement frameworks for these, and evaluation for all contains a significant commercial component to ensure economy of spend.
The main economy measures in the various VfM frameworks benchmark daily average fee rates, and promote effective cost management by ensuring daily fee rates and unit costs for expenses do not exceed those agreed during the procurement process. The fact that there are separate VfM frameworks for each programme means there is some variation between VfM indicators collected at programme component level, which reduces the opportunities for benchmarking. A unified programme level VfM framework would assist this. Nevertheless, there was a useful exercise at the end of this review period to compare, and where possible benchmark costs across the programmes.
Efficiency
The VfM frameworks are also strong on efficiency indicators. Although there will be scope to report on and compare costs for delivery of key outputs, the early stage of implementation means that there have been few opportunities to report on these. All programmes are reporting management changes in delivery mechanisms, as a result of COVID-19 limitations to travel and face-to-face meetings. Almost across the board, they report no significant change in progress to delivery of outputs as a result of these (apart from the loss of study visits and face-to-face meetings which, in some sectors – for example standards in Business Environment, or moving forward the selection of Infrastructure pilots with Chinese official partners - is causing issues). A shift to digital platforms for meetings, presentations and training has worked well for a reduced cost. This could support efficiencies going forward, even when international travel resumes.
The process of reducing budgets in line with ODA reprioritisation decisions was managed smoothly. This reduction in budget has led to removal of some planned outputs completely, and also reduction in programme management costs. Both Business Environment and Financial Services have identified ways of reducing cost in project management overheads, by identifying the core requirements on both FCDO and supplier sides. Some programmes are also identifying the resources and funding leveraged from official partners or from the private sector.
Delivery partners commented in interviews that the fund management model carries a high administrative overhead, as well as taking time to work through the structured phases of procurement. A structured fund management approach may not be the most efficient means of widening the market, and alternatives (such as ring-fenced budgets for call-off contracts) could be more efficient.
Effectiveness
VfM effectiveness can only be measured by achievement of outcomes. Given that only one programme was in implementation (rather than inception) during the review period, it is too early to make a judgement on effectiveness. However, there are some initial results at intermediate outcome levels (mainly through ‘quick win’ projects and pilots, for example PwC’s work on commercials disputes around force majeure created by COVID-19, the World Bank’s support for the Foreign Direct Investment Law amendments for Business Environment, and the achievements in terms of financial inclusion of the IFC weather index insurance in the Financial Services programme). These indicate that there is a positive trajectory already in relation to effectiveness. Achievement of desired intermediate outcomes, will, however, become clearer in coming years.
Programme ToCs have recently been revised and are considered much better and robust than they were at the time of the last review. The China programme is now better placed to deliver against effectiveness measures.
As noted below, there is a major risk to VfM, in relation to effectiveness, which is the loss of time for implementation. This is further discussed below.
Equity
As noted elsewhere, the component programmes have done much to improve their focus on G&I and to integrate this into the ToC, and reflect it in the logframes and indicators. This has been supported by supplier expertise, and advice from PFDU social development advisers, and offers significant potential in achieving equitable outcomes. Most suppliers have only one or two equity measures at output level (given that research and policy interventions are the main outputs produced), but have focused their attention on the impact of these interventions at intermediate outcome and outcome levels, which is appropriate for this type of programme.
In the case of Financial Services, there is clarity about the ToC pathway to equity. Good quality measurement is planned from intermediate outcome to impact level. Disaggregated data on gender and inclusion in relation to the ICF weather insurance index pilot has already demonstrated that 71% of the farmers that benefitted were women. The roll out currently under design has used demographic data, and learning from the pilot to ensure that similar impact on equity is achieved. The PwC programme in Business Environment also has two clear equity indicators, and the Infrastructure programme sets clear targets at output level that all commissioning notes (the tool for governance of all interventions) builds PP and G&I into the intervention, and then seeks to measure equity at outcome level(for example disaggregating data on people with access to new or improved infrastructure, and measuring community engagement and consultation by Chinese and third country project delivery companies supported by the programme. In relation to Energy, the ICF programme has indicators at each logframe level, but recognises that it needs to revise these once the contracting of grants is completed and projects to be delivered are known. The Chatham House climate risk programme accepts that it needs to do more to integrate G&I considerations, but has good contextual understanding, and clear indicators at output and intermediate outcome levels, even if there is need to strengthen at outcome level. The BSI standards programme in BE remains relatively weak (as reflected in its G&I scorecards), looking only to provide evidence that it has attained PF minimum G&I standards. However, the most important factor is the increased level of capacity and commitment in the programme teams. As a result, the momentum that has grown over the past 12 months on G&I is likely to drive tangible results and is already starting to provide evidence of influence and impact.
Assessment of whether the programme continues to represent value for money
As noted elsewhere, the biggest threat to VfM for the China programme is the delays created by procurement and contracting challenges, and the reduction in allocations as a result of ODA reprioritisation. The time left for implementation of the main programme is now only around 17 months. It may impact sustainability and already, potential impact has been reduced.
Recommendations
- The central team should, within the next 6 months, develop an overall VfM framework, drawing on the VfM frameworks already established at individual programme level, and identifying indicators for those programmes not yet covered. This should build on the comparison exercise done in mid-2020, and provide information on VfM going forward, to assist in programme governance to enhance economy and efficiency.
- Once the VfM framework is completed, and all main programmes are in full implementation, the central team should work with the programme teams to identify uncompetitive costs, and renegotiate these.
- Although it is too late to change programme design for the China programme, any future programme design process (such as Phase Two in China, or future Prosperity Fund programmes) should be aware of the long timescales and lack of flexibility of formally procured grants and contracts, and consider alternatives such as ring-fenced call off mechanisms to be managed by the supplier. Programme teams should work with suppliers over the next 6 months to Include measures of quality as well as quantifying outputs delivered into KPI regimes (for example in relation to ELCE and BSI (BE)), to enhance overall effectiveness.
- Delivery partners which are implementing through fund management approaches need to review their financial manuals and guidelines over the next 3 months, to make sure that they have systems to receive good quality forecasts and financial information from their grantees and contracts, to enable them, in turn to forecast programme spend accurately.

Quality of financial management
The 2019 Annual Review recommended developing a Financial Operations Manual to build on the finance team’s growing involvement with procurement and monitoring of all budget lines. This has been addressed, with a PFDU-reviewed Financial Guidance document to support the programme team and external delivery partners. This includes an expectation of monthly reporting on actual spending and updated budget profile, which is used to monitor overall programme spend against the original budget. The spreadsheet is updated on a monthly basis. To date, this process has worked well – delivery partners are experience in providing effective project management including financial management and reporting.
There is scope to improve forecasting, where the key responsibilities are in obtaining realistic forecasts from delivery partners, and encouraging programme teams who review these forecasts to exercise more judgment to moderate them. However, the volatile context makes forecast accuracy difficult. There may be difficulties, once the grants and contracted projects to local organisations (some of which are part of the Chinese public sector) are in implementation, in ensuring that the flow of financial information remains timely and accurate. The responsibility for ensuring this lies with delivery partners, and all of those who are delivering through fund management approaches have prepared manuals and guidelines to ensure that the process is in place.
The finance team undertake monthly scrutiny of costs, and identification of financial risks (alongside assessment of wider risks to delivery). They undertake cross-checking of basic finance information, examining receipts, validating deliverables and monitoring management of subcontractors. There is particular scrutiny of accruals, which is carried out jointly between the PF China finance team and PFDU, to ensure that any large accrual is evidence-based. The last time this was done was April 2020 (covering Q4 of FY2019/20), which was concluded with PDFU on 20 April 2020.
Suppliers are expected to provide an internal or external finance audit report which covers their PF contracts (all of the main delivery partners are large organisations with well-established financial management systems of their own and external auditors). There are also clear processes to control and manage the risk of fraud and corruption, set out in a summary document, which has been shared with NAO during their May 2020 audit of PF FY2019/20. If serious discrepancies or incompliance were to be identified process, China PF will hire an external audit firm to conduct further investigation.
Date of last narrative financial report	Financial reports provided monthly – the last on 25 September 2020
Date of last audited annual statement	None to date, but China PF was included in the NAO audit of PF FY 2019/20 undertaken in May 2020

## E: RISK

Overall risk rating: Major
Overview of programme risk
Below we outline the major risks that the programmes face, and their likely consequences if left unmitigated. We then end this section with brief reflections on how programme staff and partners manage risks.
Running out of time. Procurement, ODA reprioritisation, and COVID-19 have all delayed the delivery of programme activities. Most delivery partners have just 12-18 months to deliver results, instead of the 3-4 years of implementation initially envisaged. As a result, the programme’s impact will be much smaller than it could potentially be. For example, in the Infrastructure programme, widespread UK-China collaboration to deliver better infrastructure may not happen; impact may be limited to a small number of pilots and collaborations.[5] While in the Financial Services, Business Environment and Energy programmes, many grantees will lack time to support policy makers, regulators and energy companies to adopt their recommendations. The programme’s outcomes and impact could be substantially lower as a result.
[5] In the Infrastructure pillar, the programme is likely to end before any of its pilot infrastructure projects are complete. This is worrying. By the time these pilots are complete, HMG will no longer have resources dedicated to showcasing them. As a result, the opportunity to persuade UK and Chinese firms that they can achieve more by collaborating on infrastructure in third countries will be missed.
COVID-19. Restrictions to stem the spread of the virus have meant that delivery partners are unable to deliver capacity building in-person, particularly where international travel is required. Whilst some capacity building has happened online, this is less effective when language barriers and issues around use of online alternatives are significant. COVID-19 has affected the project in other ways too. In the Infrastructure programme, planned visits by Chinese and UK stakeholders to Southeast Asia to identify pilot projects are on hold. In the Financial Services programme, HMG staff were deployed to join FCDO’s wider crisis response, reducing time available for programme oversight.
UK-China political environment. This has slowed certain project approvals from the Chinese government. Equally, willingness to cooperate on a small number of sensitive issues has diminished. Activities implemented by multilaterals have been less affected.
Budget cuts and uncertainty over future funding. The UK spends 0.7% of its Gross National Income on ODA. As the UK’s Gross National Income falls due to the effects of COVID-19, HMG’s budget for ODA has likewise fallen. For the PF China programme, this has meant a 60% reduction in calendar year spend, from September to December 2020. Whilst some payments can be deferred to 2021, overall budgets are likely to remain smaller. Delays in paying delivery partners, and the prospect of contracts no longer being affordable, pose important commercial risks. For SMEs subcontracted by lead delivery partners, long delays in receiving payment can even pose insolvency risk.[6]
[6] As announced in the 2020 Spending Review, the UK will temporarily reduce how much we spend on Official Development Assistance (ODA). We will spend 0.5 per cent of our national income (GNI) on ODA, rather than 0.7 per cent. As a result, documents which pre-date that reprioritisation may not accurately reflect the programmes in their current form.
Management of risk
The programme has performed well in mitigating political risk, conducting due diligence to avoid unintentionally harming the interests of disadvantaged women and men, and in adapting to travel restrictions resulting from COVID-19. In a difficult political environment, the programme has managed to secure Chinese government endorsement for almost all its proposed activities. Specialist, technical expertise and China expertise have helped; so has the presence of Chinese and multilateral delivery partners. In terms of due diligence/ ensuring that project activities do no harm, we found a number of good examples. In Infrastructure, the programme has: a) selected projects that align with the goals of the Paris Agreement; b) planned to use climate data to inform infrastructure design; c) checked that the cost of an infrastructure pilot that it supports is in line or lower than the cost of equivalent projects in the region, to avoid shouldering the partner government (Kenya) with an unreasonable debt burden. A second example comes from Energy and Low Carbon Economy, where the programme plans active support for Shanxi provincial government to identify and mitigate the risks of workers being left long-term unemployed due to closure of coal power plants.
In managing the risk of running out of time, there are positives. Delivery partners in the FS and BE programmes have been able to make use of the facility built into the original programme design to ‘fast forward’ interventions without going through a time-consuming tender process. However, in managing the risk of running out of time, there is also room for improvement. Even as delays have worsened, the programme has largely stuck to a time-consuming procurement model – tender for a lead delivery partner and then require them to conduct several more tenders, outsourcing most of the implementation to subcontractors. Allowing lead delivery partners to collaborate with other organisations without lengthy bidding would have allowed activities to move faster. More flexible, equal partnerships might have helped in other ways too. Giving lead delivery partners greater delegated authority to spend would reduce delays caused by implementers waiting for HMG to approve activities. Meanwhile, for the more influential Chinese organisations with which the programme has partnered, an emphasis on partnership rather than competitive bidding might have strengthened relationships, avoiding the tensions sometimes created by hierarchical HMG-contractor-subcontractor relations.

Outstanding actions and recommendations from risk assessment
We recommend the following to reduce the risk that PF China runs out of time to achieve or measure its outcomes/impact:
1. Make the case for extending programming in China, with a portfolio that evolves in line with FCDO priorities.
2. Consider giving lead delivery partners greater delegated authority to spend, and greater flexibility to collaborate with other organisations outside bidding windows.
3. Explore opportunities to reduce the amount of time delivery partners spend reporting to HMG. Freeing up delivery partners' time to focus on delivering results within the remaining time available for implementers.

The programme already has mitigation strategies in place to manage the risk of renewed tensions affecting UK-China cooperation. One additional action to ensure that UK stakeholders continue to feel comfortable with the China programme is to give the climate benefits of the programme greater prominence in communications, especially in programmes like Infrastructure and Financial Services where climate benefits risk going unrecognised. Climate change is a topic where UK-China collaboration is almost certain to continue.

## F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
At the start of the COVID-19 outbreak, several programmes had to re-profile their activities with suppliers, as well as moving activities to online platforms. Since July 2020, all programmes have had to negotiate with implementing partners on how to handle ODA in-year cuts.

Performance of Partnership(s)
All programme teams engage with implementing partners regularly on budgets and commercial decisions. Implementing partners have accepted the need for cuts, though inevitably the process of negotiation has occupied significant time (2-3 months) for both the programme teams and SROs.

Asset monitoring and control
Many stakeholders complained that PF processes were resource intensive (compared to Chinese programmes) or even those from other donors such as the EU. Payment in arrears upon delivery is accepted, but the gap between completion of activity and payment being 2-3 months, and sometimes as long as 9 months, can be difficult, especially with multiple stakeholders, and having to finance sub-contractors. For the Energy programme, grant awards had to insert a no profit requirements clause to ensure FCDO provides a fair opportunity to all eligible bidders, however this requirement was added at a very late stage, which in turn delayed the programme by approximately one month.

## G: BUSINESS ENVIRONMENT

How has the business community and business environment responded to the programme?
The China portfolio has made impressive contributions to UK market access, exports, investment and soft power. It is on track to deliver value for money in terms of secondary benefits and may exceed both the central and higher estimates in the Business Case. Section B summarised PF China’s overall contributions to UK and international exports and investment in China. Below we provide examples.
Market access: the Financial Services programme has already supported the Chinese government in planning the opening of its pensions and insurance sectors to international firms. With sales of insurance in China worth an estimated £35 billion per year, this market opening presents an enormous opportunity for the UK’s world-leading insurance sector. If successful, the programme’s work in aligning Chinese insurance regulations with international equivalents will cut the cost for international insurance firms entering the sector.
Importantly, we can expect these secondary benefits to have positive knock-on effects on the programme’s main goals of inclusive growth and poverty reduction. Greater pension coverage, for example, will help more of China’s ageing population to protect themselves from falling into poverty upon retirement. Similarly, agri-insurance for poor farmers growing crops that are not currently covered, and health insurance are core areas of focus for the programme, which will benefit vulnerable groups. If greater competition in the insurance sector spurs greater insurance coverage, Chinese consumers can expect to benefit – including women and men at risk from falling into poverty due to uninsured losses.
Improving conditions for investment: British and other international companies in China desire greater legal certainty. The programme’s support to China’s Supreme Court, described in the previous subsection, makes an important contribution here. When COVID-19 first caused economic disruption in early 2020, UK and international businesses (as well as SMEs in China) found themselves in disputes with suppliers in China. The Supreme Court’s clarification of how judges across China should interpret force majeure clauses, which reflected international experience, will have provided greater legal certainty to affected companies.
Showcasing UK expertise: The Infrastructure programme has identified clear areas where UK expertise complements that of the Chinese construction industry. This UK expertise can add value to Chinese infrastructure projects in Africa, South Asia and Southeast Asia. Supported by non-ODA funding, early successes include facilitating a partnership between UK and Chinese manufacturers, to co-develop trains for a Cairo monorail.
The programme has also sought to showcase public sector expertise. For example, collaboration between the Bank of England and Chinese counterparts have highlighted and shared UK expertise on macro-economic stress testing, and on assessing climate risk in economic planning. Robust macro-economic stress testing will support financial stability in China; this in turn will support financial stability in the UK and wider world. Planned sharing of lessons on managing local government debt can further contribute to this objective. Meanwhile, assuming that advances in climate risk modelling support a sophisticated understanding of the economic costs of climate change for China, this will help China’s policymakers to consider these costs, and thus the benefits of ambitious investment in climate change mitigation and adaptation.
Supporting China to adopt international standards: The Prosperity Fund has provided technical assistance to support China to adopt international anti-money laundering standards. Similarly, collaboration between the Standards Administration of China and the British Standards Institute is supporting China to contribute to the rules-based international system for standards setting.[7] This will benefit UK and international firms operating in China, who will avoid additional costs if they can apply the same standards in China as elsewhere. Given China’s major international influence, the least developed countries should ultimately benefit from this trend too. It will avoid countries choosing between investors who prefer Chinese standards, and investors who use standards in operation elsewhere, bolstering international trade and investment.
[7] China's recent removal of the requirement to test cosmetics on animals is one example of this.

What role has non-ODA spending played in promoting programme objectives?
Non-ODA, specifically the Prosperity Fund/DIT’s UK-China Infrastructure Academy, has been the leading catalyst behind the Chinese investment in UK renewable energy, infrastructure and regeneration mentioned above. Other parts of HMG have also contributed substantially to the results mentioned above, notably diplomats. In the case of the UK-China business partnership to supply trains to the Cairo monorail, lending to Egypt by UK Export Finance has played a valuable enabling role. In short, the programme appears to be working effectively with wider HMG to deliver benefits to UK and international businesses, as well as delivering its primary purpose.

## H: MONITORING & EVALUATION

Evidence and evaluation
We have been able to review ToCs and logframes for all programmes, some of the MREL strategies developed in inception, and the comparison exercise to identify weaknesses and good practice in MREL undertaken by the central team. We have reviewed quarterly reports and quarterly submissions from delivery partners. In addition, we have reviewed progress against recommendations from the September 2019 evaluation, which built upon the previous Annual Review and, with an enhanced focus on impact level objectives.
 Overall, there is a good body of evidence that monitoring and evaluation processes are well embedded and that the information collected is being used to make programming decisions – for example during the ODA reprioritisation exercise. As of June 2020:
- Key recommendations from the 2019 evaluation have been actioned, including improved articulation of global good in ToC narratives, improved distillation of learning and expertise from other depts. (e.g. DFID) and development of mechanisms to identify cross-cutting learning and synergies across programmes
- ToCs were nearing their final form, following sign off of inception deliverables for each programme;
- Logframes were still works in progress. Overall logframe structures and indicators were largely finalised, but there is still work to do in some programmes to agree milestones and targets. This process is further complicated by the fact that programmes using a fund management model cannot finalise milestones and targets until the procurement of grants and contracts is completed. Finalising logframes is still ongoing.

Despite ongoing development, the monitoring and evaluation processes are established and working well. Delivery partners have helped shape the MREL process, and the support from FS and BE main programme providers was singled out. Continuity of staffing has also helped embed processes, with limited changes in programme teams, central programme management and project management/MREL leads in delivery partners. Programme team members identified that having a Prosperity Fund Counsellor with in-depth understanding of monitoring and evaluation of development programmes, and driving adoption of good practice, has been important in building momentum.
There have been issues relating to monitoring and evaluation:
- Ensuring effective monitoring down all the links in the chain of delivery is going to be a challenge, in particular to those organisations delivering through a fund management model. Programme teams perceive that there are gaps in guidance from London on how to put systems to ensure effective monitoring and reporting in place, in particular for the process elements (such as G&I, delivery of PP etc.);
- Finding mutually acceptable approaches to monitoring and evaluation of World Bank delivered components. Although both FCDO and the Bank are committed to good monitoring and evaluation, and – at least in the case of IFC - effective workarounds that meet the requirements of both parties have been identified, this is another area where the experience from elsewhere in PF and wider across Whitehall that could have been drawn on sooner.

Monitoring progress throughout the review period
The turmoil over the review period caused by external events and the impact on monitoring and reporting processes cannot be over-emphasised. Although programmes continued delivery after only a short COVID-19 hiatus in most cases, processes such as results monitoring were more affected. Reporting on paper continues, but with some complications given: IT issues; that programme teams were sometimes deployed on other priority tasks, and that the central MREL lead was in the UK in a different time zone with limited overlap of working days.
The big positive shift between the last AR period and this is the understanding on the side of programme teams about how the ToC and logframe are at the heart of monitoring and evaluation, and how the processes of regular reporting on and scrutiny of progress is key to effective programme management. This understanding has taken time to develop, but is now embedded. In parallel with this understanding, has been the process of improving logframes and indicators and targets. This has been an iterative process, and much was not completed until after the review period, as revisions to key tools were made as programme components were refined during inception. Following the budget reductions as a result of ODA reprioritisation, further revisions to logframe indicators and targets still need to be made, which will reduce outcome ambitions in line with reduced resources.
Learning
The programme team’s commitment to learning has continued, despite the major logistical issues created by the COVID-19 lockdown. There is a dedicated learning budget, and a training needs analysis in late 2019 clearly identified priorities, primarily in programme management (contract management; financial management; risk management; stakeholder management; monitoring and evaluation and G&I). PRINCE2 and AgilePM Foundation and Practitioner training was found to be thought-provoking, stimulating programme teams to identify how they might better manage their programmes. There is limited use of PFLearning, although it is a useful reference repository of documents. Peer-learning continues to be the most valuable approach, and this has been ongoing, even despite delays, dispersions of team and lockdown in the early part of 2020.
The central team are in the process of reviewing the 2019 learning strategy to address key areas of learning for next year, which will be focused more on what has been learned from the process of designing and delivering PF programmes in China, and identifying what does and doesn’t work.