Colombia Prosperity Fund Programme
Annual Review 2020

Title: Unlocking Economic Opportunities in Colombia’s Post-Conflict and Conflict-Affected Regions
Programme Value: £25.5m		Review Date: 4 December 2020
Programme Code: / PF COB 921001, PF COB 921002, PF COB 924001, PF COB 924002, PF COB 925001, PF COB 925002, PF COB 925003	Start Date: / November 2017	End Date: / March 2022

Summary of Programme Performance
Year	2018	2019	2020
Programme Score	A	A	A
Risk Rating	Moderate	Moderate	Moderate

Summary of progress and lessons learnt since last review
- The Colombia PF Programme has been operational for just over two years. Out of its 34 projects, 23 are in the implementation phase, 10 are in the design stage and 1 has been completed. For the remaining 16 months of the Programme, the PF Team will take all the lessons learnt to date on project design, contracting and implementation to improve efficiency in delivery.
- All projects promote active participation of women and other excluded groups in the design and implementation processes, and many of the Programme’s early wins demonstrate that this ambition is being fulfilled.
- Even though implementation of most projects started just over a year ago, the PT has identified three that are possibly already delivering results at the intermediate outcome level: two Agritech Catalyst projects (LISTO and Vegan chocolates), and the OCP Open Procurement. This will be explored further in the Cycle 2 evaluation.
- Over the last year, the PF progressively provided more tailored support to individual companies to help them land in the Colombian market, and has focused on targeted activities that have higher impact on outcomes. As a result, the programme has generated 10 additional secondary benefits (see Section B).
- COVID-19 has generated significant delays in the delivery of the programme, but it has also generated creative and innovative ways of delivering results remotely. There are important lessons from these new ways of working that will be captured and promoted, even when the crisis is over.
- Working with JFU and the PF’s climate consultants has provided useful suggestions to improve the alignment with the Paris agreements.
- Last year’s Annual Review made 25 recommendations. Of these, 14 have been actioned, four are in progress, five have been actioned by other teams of the Embassy or are no longer relevant for the PF and two have not yet started. These include analysing cost-drivers across the seven projects and updating the cost benefit analysis calculations and VfM for each activity. The latter is included as a recommendation this year too.

List of recommendations for the next year
There are a total of 19 recommendations in this AR. The table below summarises the top ones for next year.
Top Recommendations	Detail	Lead
Assess the possibility of extending the programme, to counterbalance slowdown of activities due to the Spending Review and COVID-19.	B	Prog Team & JFU
Update the Umbrella Theory of Change and logframe to reflect the current programme (by March 2021)	B & H	Prog Team
Review and update the cost benefit analysis calculations and VfM for each Programme activity	D	Prog Team & PFDU
For the remaining new projects, ensure implementing partners and suppliers have a clear understanding of the PF’s G&I requirements.	B & C	Prog Team
Update the overall lessons learned paper about G&I, to reflect new knowledge acquired (by Feb 2021).	B & C	Prog Team
Develop a strategy to ensure infrastructure projects supported by the PF at the feasibility study stage will lead to successful commissioning, construction and operation of projects (jointly with DIT and UKEF, by March 2021).	B	Prog Team
For the remaining projects, ensure PF-funded projects are co-financed with the Colombian Government (by June 2021).	B&D	Prog Team
In order to ensure the PF contributes to Colombia’s green recovery, new projects should incorporate a stronger environmental component	B	Prog Team
Update the Secondary Benefit (SB) plan with a PFDU economist support to make sure that SB expectations are still realistic as a result of the PF investment in the three strands (by April 2021).	G	Prog Team & PFDU
Create a strategy to support the delivery of SB during the last year of implementation and maximise non-ODA activities to achieve SB realisation in the short term (by Feb 2021).	G	Prog Team
Document lessons on the unexpected speed of the innovation-uptake in Colombia from the Agritech Catalyst project to share among the UK network.	C	Prog Team
Develop an ODA narrative for Colombia to ensure coherence between ODA funds and maximise impact (by March 2021).	B	Prog Team

SRO Commentary
The PF Programme in Colombia is a dynamic and mature programme that is strategically aligned with the Embassy’s priorities, and which is already delivering impressive results across the three sectors it operates in. The Programme is an essential tool to deliver both the primary benefits of reducing poverty and improving gender equality across Colombia, and the secondary benefits of improving the business environment in Colombia and attracting UK business. To highlight three areas: firstly, the PF is operating in key productive sectors (infrastructure, agriculture) which Colombia will need to reactivate the economy post COVID; secondly, the PF’s soft power in Colombia is important, it opens doors and deepens relationships important to the wider UK network, especially in the regions and cities where we would otherwise not be present; and thirdly, the PF has successfully attracted new UK business to Colombia and will continue to open new markets for UK companies.

The recommendations set out in this Annual Review come at time where the Programme has learnt a number of lessons as to what works and what could be done better. The PF in Colombia has delivered results at such a fast pace, that these lessons could be beneficial to others in the network. Despite the challenges, the team has powered ahead delivering excellent value for money and remarkable benefits for the UK and Colombia.

JFU Commentary
This Annual Review takes place at the midpoint in the programme’s lifecycle, where activities are gaining traction and results are broadly on track. It provides evidence of progress against both primary and secondary objectives across the three target sectors. The Review identifies particular strengths in the strong engagement and cooperation (including through significant matched-funding) the programme enjoys with government officials, and in demonstrating a good understanding of its beneficiary groups. There is room to improve the overall articulation of PF impact so far and JFU agrees with the recommendation to develop a clearer headline narrative across all ODA in Colombia, noting the PF’s contribution. JFU supports the recommendation to review the logframe and ensure indicators facilitate a full assessment of progress against outputs; this will support a greater understanding of where the programme is against the overall vision for change. This in turn will support transparency and active programme management.

List of Acronyms
ANI – National Infrastructure Agency
AR – Annual Review
BC – Business Case
BE Bogota – British Embassy, Bogota, Colombia
BIM – Building Information Modelling
CAF – Latin America Development Bank
CCE – Colombia Compra Eficiente (Colombia’s National Procurement Agency)
Confecameras – Colombian National Federation of Chambers of Commerce
COP – Colombian Peso
CSSF – Conflict, Stability and Security Fund
C2 – Cycle 2
C-19– COVID-19
DANE – National Statistics Administrative Department
DD – Due Diligence
DFID – Department for International Development
DIT – Department for International Trade
DNP – National Planning Department
ECHO – Economic Horizons
EL– Evaluation & Learning
FCDO – Foreign, Commonwealth & Development Office
FDI – Foreign Direct Investment
FDN – Colombian Financial Institution for National Development
Finagro – Colombian Agricultural Development Bank
Findeter – Colombian Financial Institution for Development of the Regions
G&I – Gender and Inclusion
GACP – Prosperity Fund Global Anti-Corruption Programme
GESI – Gender Equality and Social Inclusion
GHG – Greenhouse Gases
GIP – Prosperity Fund Global Infrastructure Programme
GNI – Gross National Income
GTP – Prosperity Fund Global Trade Programme
HMG – Her Majesty’s Government
HQ – Headquarters
ICA – Colombian Agriculture Institute
ICF – International Climate Finance
ICL – Imperial College London
IDEAM – Colombian Institute for Hydrology, Meteorology and Environmental Studies
IP – Implementing Partners
IPRG – Internal Programme Review Group
IUK – Innovate UK
JFU – Joint Funds Unit
KPIs – Key Performance Indicators
MADR – Colombia’s Ministry of Agriculture and Rural Development
MoU – Memorandum of Understanding
MREL – Monitoring, Reporting, Evaluation, Learning
NDP – National Development Plan
OCP – Open Contracting Partnership
ODA – Official Development Assistance
ODI – Overseas Direct Investment
PACT – Partnering for Accelerating Climate Transitions
PF – Prosperity Fund
PFCF – Prosperity Fund Commercial Framework
PFDU – Prosperity Fund Delivery Unit
PIP – Performance Improvement Plan
PSAP – Private Sector Advisory Panel
PT – Prosperity Fund Team
SB – Secondary Benefits
SECOP II – The Second version of Colombia’s on-line State System for Public Procurement
SG – Stakeholder Group
SIGRA – Risk Information System for the Agriculture Sector
SIP – Sustainable Infrastructure Programme
SRO – Senior Responsible Officer
ToC – Theory of Change
ToRs – Terms of Reference
UPRA – Colombian Unit for Rural Agricultural Planning
VfM – Value for Money

## A. INTRODUCTION AND CONTEXT
The Colombian PF Programme aims to support economic development, unlock economic opportunities and drive growth in Colombia’s post-conflict and conflict-affected regions. The Programme will benefit more than 3 million people with a focus on women, girls and minorities in Colombia’s poorest regions and is expected to achieve up to £1.99bn of primary benefits to Colombia over 10 years (according to preliminary estimates set out in the business case). The potential secondary benefits, set within the context of a peaceful, prosperous Colombia, are considerable. The estimated benefits to the UK alone are around £265mn by 2026 (according to the business case).
The Programme targets seven activities within the three sectors:
Institutional Strengthening
Regional competitiveness: strengthen economic development in Colombia’s regions by improving their competitiveness.
Open, public procurement: more transparent, less corrupt public procurement in Colombia’s regions.
Corporate governance reform of Colombia’s National Infrastructure Agency (ANI).
Infrastructure
Urban development: strengthen SMART urban development in Colombia’s second tier cities.
Rail development: support the rehabilitation of Colombia’s narrow gauge rail network.
Agriculture
Agri-insurance: develop and roll out agri-insurance to Colombia’s smallholders and agricultural micro and small enterprises (MSEs).
Agri-Tech Catalyst Challenge Fund: increase productivity and incomes for Colombia’s smallholders and agricultural MSEs through adoption of agri-innovations and technologies from the UK.
Programme Implementation
Programme implementation began on 1 April 2018. Since the last AR, a number of important contextual changes have taken place:
1. COVID-19. The COVID-19 crisis has had a profound impact on Colombia’s economy and a varied effect on the Programme. About 9 million Colombians (almost 20%) have had their incomes cut significantly. Poverty levels are expected to rise from 27% to 42%[1], while inequality is likely to return to a level not seen since 2002. Lockdown measures have resulted in a 10% monthly GDP drop. At the programme level, the most immediate impact is evident on programme outputs, principally through delays in activities due to travel and other restrictions, and constraints on beneficiaries and implementing partners’ bandwidth. This may require further re-programming in the immediate future.
  [1] Observatorio de coyuntura económica y social del Centro de Estudios sobre Desarrollo Económico – CEDE (2020). “Efectos en pobreza y desigualdad del Covid-19 en Colombia: un retroceso de dos décadas”. Nota macroeconómica No. 20. Universidad de los Andes.
2. UK ODA. Like many other nations across the world the UK is experiencing a severe economic downturn as a result of the COVID-19 pandemic. The First Secretary led a cross UK Government review to identify savings in this year’s ODA budget. The Colombia baseline is £4.8m for FY20/21, which was agreed by both the First Secretary and the Prime Minister in July 2020. The UK Government’s 2020 Spending Review was concluded on 25 November, and the Integrated Review has been launched. The Spending Review has had implications on when disbursements to implementing partners (IPs) could be made to launch contracts during the AR period. Project implementation depends on those pre-payments as IPs require the resources in advance to initiate the contracting processes. Although the PT continues to make progress on project design, contracting is currently on hold.
Previous ARs described in detail how individual projects were identified, how regions and cities were selected, and how implementing partners were contracted. Due to the C-19 crisis, this AR has adopted a lighter touch approach, with a scaled down scope. The Programme’s governance bodies and relevant stakeholders were interviewed, and focus groups were held with relevant Embassy teams, all online. The Cycle 2 Evaluation, planned in April 2020 and delayed, is taking place at the same time as the AR. As the Evaluation cannot now feed into this AR, its evidence and results will not be used in this exercise, as is usually the case. However, it is important to note that the EL team joined the AR team to contribute insights as appropriate, given the overlap.
Despite the delays in programme implementation generated both by COVID-19 and the Spending Review, the Colombia PF Programme is still on track to meet most of its third year milestones (see Section C).
Changes in Cities and Regions
The original target regions were Antioquia, Atlántico, Caldas, Cundinamarca, Magdalena, Meta, Santander and Valle del Cauca. The first six target municipalities were Cartagena, Ibague, Manizales, Santa Marta, Valledupar and Villavicencio. Colombia held municipal and departmental elections in October 2019 and a new raft of mayors and governors entered office in January 2020. The PT has now met all the new leaders in areas with existing or planned Programme investments and steps are already underway to fast track the next set of PF projects. The PT has also added Bolivar to the list of regions as both its new governor and the new mayor of Cartagena requested support from Open Contracting Partnership (OCP) on open procurement. Programme operations in both Cartagena and Villavicencio, which had been put on hold due to reports of electoral or financial irregularities, were able to resume following the elections. Bucaramanga was also added in January 2020.
Primary and Secondary Benefits
The Programme has been operational for 2.5 years, and is currently implementing 23 projects, 10 are in the design phase and one has been completed. These projects and initiatives reduce poverty and gender inequality through inclusive economic development, and current estimates show that over 13 million people are expected to benefit from it. The Programme has taken a number of steps to strengthen its gender and inclusion (G&I) focus. The Programme has developed a comprehensive G&I Strategy which has guided the integration of G&I commitments throughout all projects, as well as capacity-building initiatives with implementing partners, stakeholders and suppliers (see detail in Section B). A Social Development Adviser joined the team in March 2020 to oversee the full implementation of the agreed G&I targets throughout the Programme.
This past year, as implementation has progressed, an increase in secondary benefits has been realised (see Sections C and G). A full description of expected secondary benefits can be found in the Colombia PF Programme Secondary Benefits Plan.
Updated Logframes
An in-depth review and updating of the programme’s theories of change, took place in early March 2020, with a visit of MREL Teams and PFDU to Bogota. Assumptions behind each ToC were reviewed and refreshed when required. The adjustments also captured better the reality of most activities after starting implementation. The outputs in the Umbrella Logframe were also updated, and this AR exercise has evidenced the need to review the remaining levels of the Umbrella Logframe as well as the intermediate outcomes of the ToC.
Joint Working
The Colombia PF Programme coordinates closely with other UK government funds operating in Colombia such as the PF Global Infrastructure Programme (GIP), the PF Global Trade Programme (GTP), the PF Global Anti-Corruption Programme (GACP); the International Climate Finance (ICF) especially on the Sustainable Infrastructure Programme (SIP), the Partnering for Accelerating Climate Transitions (PACT) Programme; the Conflict, Stability and Security Fund (CSSF), the Newton-Caldas Fund for research and innovation and the UK’s Chevening Scholarship Programme. Until the onset of the COVID-19 pandemic, within the Embassy, the PT held fortnightly Economic Horizons (EcHo) coordination meetings between all the programmes and DIT to share lesson learning and to enhance collective progress and impact on the UK’s development objectives for Colombia.

## B: PERFORMANCE AND CONCLUSIONS
Annual outcome assessment (Primary Purpose)
The Cycle 2 Evaluation for the Programme, originally due to feed into this AR, was delayed because of the ODA reprioritisation exercise and will be submitted in February 2021. This evaluation will provide the evidence to assess whether the Programme is on track to achieve the intermediate outcomes it has set out. The relative maturity of the Colombia programme will allow the EL team to integrate an early contribution analysis into the evaluation process.
Even though implementation of most projects started just over a year ago, the PT has identified three that are possibly already delivering results at the intermediate outcome level: two Agritech Catalyst projects (LISTO and Vegan chocolates), and the OCP Open Procurement. The C2 EL team is undertaking due diligence to assess these specific claims, and the final selection of the agritech results is pending review of by the evaluation team.
LISTO, a platform developed to facilitate access of smallholders to markets without requiring intermediaries, had 593 users by August 2020. In the Vegan Chocolate project, female cocoa farmers participating in the pilot received an increased income due to the project (£3.52 per kilo for the three harvests, compared to £1.46 per kilo initially paid by Fedecacao). Both of these successes relate to the agritech intermediate outcome on adoption of new agricultural technology by smallholder farmers. Progress in this area suggests that the ambition for the programme to improve production and access to markets by adopting agricultural innovations is on track. On Open Procurement, indicators show good progress on the intermediate outcome related to governments being held accountable by different non-governmental actors on procurement design and implementation. This suggests that the programme is making progress towards achieving increased confidence in open and competitive procurement.
Annual outcome assessment (Secondary Purpose)
Over the last year, the PF progressively provided more tailored support to individual companies (using non-ODA funds) to help them land in the Colombian market, and has focused on targeted activities that have higher impact on outcomes. As a result, the programme has generated 10 secondary benefits: the setup of 3 UK companies new to the market (); 2 MOUs (); 4 partnerships between Colombian and UK stakeholders to develop joint projects in the Agriculture sector; and 1 export win worth £100K in infrastructure.
Several of these and other secondary benefits are related to soft power, network effects, and market access so far, which in turn may enable longer term benefits in the form of exports, FDI and ODI. Out of the 10 individual secondary benefits achieved this year, 8 are in agri-tech, a sector that appears to offer great potential for quick commercial opportunities for the UK and international businesses. The programme has also contributed to the creation of 62 partnerships between Colombian and international business (50% UK business) to date, which have bid for 16 PF contracts. Early stages, but these results suggest that the foundation of increased international business engagement, including with the UK, has advanced over the past year.
Overall output score and description
A – Outputs met expectations
Across the board, outputs have performed well, with particular successes in landing agriculture innovations, progressing with infrastructure feasibility studies and expanding the public procurement work. Notable this year was the progress the programme has made on increasing the capacity of public officials (especially in urban development). The overall performance of the Programme this year must be understood in the context of significant world events (e.g. C-19), which have clearly been challenging; and areas of focus (G&I, climate) where the level of ambition for the Programme has progressed and the management of activities has adapted to reflect that. These issues are discussed further below.
Impact of COVID-19
The impact of COVID-19 (C-19) on Programme activities has been varied. In most cases, there have been significant delays in implementation, which have slowed down (but not halted) project activities. Travel restrictions created the need for projects to innovate and deliver activities in different ways. In some instances, this has amplified the results achieved (for example, delivering training to a wider audience using online tools).
Almost all urban development, regional competitiveness and open procurement projects suffered delays, as mayors and governors have been preoccupied with managing the C-19 crisis in their respective regions. Agritech projects, which work with rural communities, have also been adversely affected, given their lack of access to online tools. These were given no-cost extensions to allow the projects to deliver the expected results. Workshops planned for 2020 had to be postponed until Q1 2021, hoping that lockdown measures and travel restrictions continue to ease.
On the plus side, the pandemic has put public procurement under the spotlight, making these activities more attractive to both local governments and external stakeholders. The OCP project was granted a 5-month extension to complete activities in the 9 target regions, while including participants from elsewhere given the virtual trainings. Suppliers have also had to be creative to shift from face-to-face interactions to virtual and phone tools. With some innovative thinking, the EY/IDOM consortium (with support from Findeter and the PT) used a combination of high and low-tech solutions to overcome C-19 restrictions and conducted thorough beneficiary engagement for a pilot Smart City project in Santa Marta. These methodologies, and the resulting influence that women and excluded groups will have over this project design, provide lessons that may be of use to other BE Colombia and PF programming; their example has been followed by other projects and suppliers already.
The PT quickly designed a new project to contribute to Colombia’s C-19 response and recovery priorities. A collaboration between Imperial College London (ICL) and Colombian Ministry of Health on epidemiological modelling to support public health response to C-19 pandemic in Colombia is currently being agreed.
An indirect effect of C-19 on the Programme is the uncertainty around prepayments. Given that country-level allocations within the Spending Review have not yet been agreed, the PT is unable to transfer funds to the IPs so that they can initiate contracting processes. This has aggravated the delays described above.
Coherence with other ODA funds operating in British Embassy Colombia
The Programme coordinates closely with other UK government funds operating in Colombia. Specifically with the International Climate Finance (ICF), the Newton-Caldas Fund for research and innovation, and the Conflict, Stability and Security Fund (CSSF). The AR Team held focus groups with members of these teams to explore the coherence between the different funds, and how they could operate better to have more impact.
As the different funds have positioned themselves in Colombia, they have each developed expertise in their respective areas. These capabilities which have been built up over the past few years, collectively create a real strength in the Embassy. As an example, the PT has developed expertise in gender and inclusion, and in agriculture; the ICF holds the Embassy’s expertise on climate and environmental issues; and the CSSF leads on issues related to conflict and peace-building. As such, the areas of confluence in the programmes have naturally been areas where expertise from various parts of the Embassy have come together.
One example of this has been in a project to create capacity building schemes for tilapia producers, where the CSSF, which has been supporting agri-projects with former FARC combatants, and the PF, which specialises in economic recovery, have joined forces. Another example is linked with the PF cattle ranching production costs project, which aims to standardise a methodology to assess production costs of specific agricultural productive systems. ICF colleagues have been instrumental in including environmental components to promote sustainable cattle farming practices in the project, such as intensification of silvopastoril systems. There are other areas which BE is exploring around sustainable mobility, where the PF and ICF both have common ground.
The aforementioned ICL/MOH project is being designed with the Newton Fund given the double objective of producing scientific evidence and strengthening the health system. Discussions around nature-based solutions and bio-economy projects have also been held, and will be advanced when opportunities arise.
As well as the expertise built, all interviewees in charge of managing these funds agreed that their strength lies in the different objectives and areas of operation each fund has. For example, the CSSF operates in the most conflict-affected areas of Colombia, whereas the PF operates in areas where both primary and secondary benefits can be pursued. Funds can be used in a complementary way to maximise impact. It was agreed that an ODA Narrative should be developed for Colombia, for these synergies to be consolidated, and exploit further potential.
Progress on G&I activities
Overall, the Programme is situated at an ‘empowerment’ level of ambition within the PF G&I Framework. Most of the projects comply with level 1 of ambition (voice) and some are advancing into level 2 (empowerment), such as the Manizales project. The G&I plan for this project is being developed both for the feasibility stage and for future execution, including a pillar on access to employment opportunities for women and the LGBTI community. All projects promote active participation of women and other excluded groups in the design and implementation processes, and many of the Programme’s early wins demonstrate that this ambition is being fulfilled.
Some projects are even more ambitious, aiming for results at the level 3 (transformational change). The PF has brought the gender chapter of Colombia’s National Development Plan to life by integrating social development priorities for the first time into key infrastructure projects. An example is the Aerocafe airport plans, for which comprehensive stakeholder engagement is already delivering valuable results for socially inclusive design. The Programme has also undertaken two important consultation processes with women and marginalised groups for projects in the cities of Manizales and Santa Marta. Listening to a cross-section of society means that the interventions will meet the needs of all citizens. For example, in response to the recommendations of people with visual disabilities, both tactile signals and audio announces will be included in the design of buses and bus stations. Better lighting around bus stops will also make women feel safer about travelling across town after dark. Consultation processes are key to develop inclusive projects, and creative adaptation was required due to C-19.
In addition to engaging directly with women and excluded groups, the Programme seeks to maximise its impact by training and sensitising decision makers on the importance of women’s economic empowerment and the inclusion of vulnerable groups. To date, 168 new mayors and governors were trained in Nov 2019 to integrate G&I in their development plans; and a follow-up training to deepen G&I in these plans took place between February and March 2020 with 14 municipal and departmental authorities.
Although progress is tangible, the Programme has also faced challenges. Some of the first projects had gaps in defining G&I requirements, and levelling expectations with suppliers required significant efforts at advanced stages. In the Confecámaras project, the G&I diagnoses produced by the supplier did not meet minimum expectations and support from an external expert was required. Similarly, the PT and Innovate UK conducted comprehensive G&I reviews with agritech project teams, and improvement plans were requested from projects that were not compliant with level 1 of the G&I Framework.
Climate and Environment
The Climate and Environment Audit in Sept 2019 identified 11 recommendations for the Programme, which were addressed (see Annex A). The initial climate review concluded that the Programme is not doing harm and that implementing partners have the capacity to incorporate environmental considerations. Since then, the PT has worked closely with JFU and climate consultants to develop TORs to support to the Programme as part of a Climate Change Strategic Review of FCO Prosperity Fund Programmes. The results of this work will help the PT develop a strategy for climate-sensitive programming.
Key lessons learnt from the AR process
COVID-19 has generated significant delays in the delivery of the programme, but it has also generated creative and innovative ways of delivering results remotely. There are important lessons from these new ways of working that should be captured and promoted, even when the crisis is over.
IP management continues to be critical to achieving timely outputs. Despite large investments of time in previous years dedicated to strengthening our working relationships with two of the implementing partners in particular, there is still work to do. Lack of progress on the new Regional Competitiveness projects, and slow progress on those already advanced resulted in one the IPs being issued with a PIP (see Section F). As a result, three projects turned around, but no further projects will be procured through this IP.
A number of infrastructure and agri-insurance projects suffered delays this year due to contractual processes; they will proceed, but not with the secondary benefits expected. Therefore, when defining new projects, it is important to first conduct market surveys to confirm market appetite, especially on water and sanitation projects in rural areas.
Cities and regions have started to co-finance PF-funded feasibility studies of rail and urban development projects, which demonstrates their ownership of the studies and increases the likelihood of feasibility studies reaching the implementation stage quickly.
The PT has invested substantially in raising IPs’ knowledge of UK and PF priorities and modalities, and the Programme is in a much stronger place. However, the PT should still ensure that project suppliers have a clear understanding of PF expectations on G&I at beginning of any given contract. The G&I initial meeting in Santa Marta Project demonstrated value in this. Having project designs and contracts or agreements underlining actions to deliver G&I change does not guarantee success.
With Findeter, the PF co-funded a ‘Mayors and Governors capacity building event’ in Santa Marta in Nov 2019, followed by more in-depth workshops in Feb/March 2020. This was a good opportunity to influence new politicians on inclusive project design and implementation, and to promote integrating G&I into local development plans. Given that incorporating a G&I perspective into infrastructure and agriculture projects is new for Colombia, capacity building among local government beneficiaries should be continued, especially for projects designed and ready to go to tender.
Working with JFU and the PF’s climate consultants has proved useful to brainstorm ideas on improving the Programme’s alignment with Paris’ agreements. An initial workshop, held with all relevant stakeholders, to discuss options for reducing GHG emissions associated with airports, was very successful considering the complexity of such projects, and should be replicated.
A highly successful agritech mission in March 2020 is already delivering secondary benefit wins. This is a largely unexplored sector between the UK and Colombia, in which there is scope for huge wins in the future. COVID-19 travel restrictions meant that a tilapia commercial mission to the UK had to be cancelled. The PF should replicate this as soon as possible.
Non-ODA spend, which has concentrated on landing specific UK companies, has had more impact than spend on generic promotion. The PF Commercial Adviser used her analysis of all non-ODA supported activities to eliminate or reduce those activities which delivered a lower rate of return when designing the 2020/21 secondary benefits (SB) plan for Colombia.
Working jointly with other ODA funds operating in Colombia does not necessarily mean finding ways of joint-financing projects. A narrative on ODA in Colombia, led by the PF team, would help tease out the coherence and potential impact of the different funds operating synergistically.
Key actions
1. The delays in receiving the Colombia ODA allocation for FY 21/22 and COVID-19 have resulted in delays in the implementation of the programme. The PT should assess the possibility of extending the programme, to counterbalance this slowdown of activities.
2. Update the Umbrella Theory of Change and logframe to reflect the current programme (by March 2021), and ensure that IPs report on all updated logframes correctly (ongoing).
3. For the remaining new projects, ensure implementing partners and suppliers have a clear understanding of the PF’s G&I requirements. The PT needs to be satisfied that all stakeholders are on the same page.
4. Update the overall lessons learned paper about G&I, to reflect new knowledge acquired (by Feb 2021).
5. Develop a strategy together with IPs and beneficiaries, to ensure that infrastructure projects supported by the PF at the feasibility study stage will lead to successful commissioning, construction and operation of projects (jointly with DIT and UKEF, by March 2021).
6. In order to ensure the PF contributes to Colombia’s green recovery, new projects should incorporate a stronger environmental component.
7. Update the Secondary Benefit (SB) plan with a PFDU economist support to make sure that SB expectations are still realistic as a result of the PF investment in the three strands (by March 2021).
8. Create a strategy to support the delivery of SBs during the last year of implementation (including soft power) and maximise non-ODA activities to achieve SB realisation in the short term (by Jan 2021).
9. Develop an ODA narrative for Colombia to ensure coherence between ODA funds and maximise impact (by March 2021).
Summary of changes to the logframe since the last Annual Review
A comprehensive revision of the ToCs, both at the activity level and at the programme level, took place between March and September 2020, in which the ToCs and logframes were updated, and environmental indicators were incorporated. The logframes for the seven activities have been uploaded onto Prospero. The umbrella logframe was updated at the output level to better reflect the current implementation reality of the Programme
Although C-19 was considered when thinking about the milestones for this year, the PT acknowledges that the critical economic situation in Colombia should be considered in more detail to understand how it can affect outcome and impact level indicators. More evidence needs to be collected (see section H).
## C: DETAILED OUTPUT SCORING

Output Title	Increased technical capacity of producers and providers in agricultural insurance and agricultural technology, especially female and male smallholders and small companies (including cooperatives, associations and MSMEs)
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	12%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones 2020/21	Progress
Number of female and male producers and providers trained	Planned / Agritech Catalyst Challenge: 300 / (At least 50% female)	Achieved by October 2020 / Agritech Catalyst Challenge: 171 / (Female = 121, Male = 50)
Number of training sessions and/or modules dedicated to gender and inclusion	Planned / Agritech Catalyst Challenge: 7	Achieved by October 2020 / Agritech Catalyst Challenge: 9

Agri Tech Catalyst
- C-19 has impacted agritech projects significantly. This activity was due to finalise by November 2020, but travel restrictions delayed technical activities and projects, which had to request up to 6 months no-cost extensions. C-19 restrictions have also affected progress on training producers; just over half of the planed 300 have been able to receive training since the last annual review. The conditions of Colombia’s rural population, and the lack of access to online tools, makes it almost impossible to deliver training using virtual methods. The project is ready to deliver face-to-face workshops as soon as travel restrictions ease.
- Some projects have achieved significant results, with a growing evidence base of how they are helping to improve the lives of women and men living in poverty. Two examples are: (i) an innovative web-based market platform LISTO from Farming Data is helping 593 (current users) small farmers to increase their sales price and avoid exploitation; and (ii) the business plan developed by the vegan chocolate project, has increased the incomes of three targeted female farmers, allowing them to connect directly with chocolate makers in UK. The bean-to-bar business plan has empowered cocoa producers in Colombia, and Nottingham University is now exploring potential scalability opportunities with Fedecacao, but additional funding may be required.
- There is clear potential for UK-Colombia business partnerships. Projects have demonstrated that agritech knowledge can be transferred to Colombia to provide useful tools for smallholder farmers to improve production and access to markets.
- The focus on G&I has been a challenge because it was not highlighted during the initial call for proposals (although it was included in the grant agreements between IUK and grantees). G&I reviews for all agritech projects took place in September 2020 and projects that were not meeting the minimum compliance level, were required to produce an improvement plan before the end of the project.
Agri-insurance
There is one training component envisaged in the agri-insurance activity, which will start in 2021 (following the capacity building project and after the agricultural risks management study is finalised).
Summary of responses to issues raised in previous annual reviews
There were two specific recommendations for this Output in 2019 AR, which the PT took action on (see Annex A, recommendations 10-11).
Recommendations
1. Ensure lessons learnt from the agritech challenge fund are applied to agri-insurance pilots, especially on G&I.
2. Develop a plan to amplify the impact of the technical capacity built with the agritech projects to ensure these learnings reach a wider audience in Colombia (by April 2020).
Output Title	Increased capacity of public officials to design and structure inclusive and sustainable urban, rail, regional competitiveness, ANI, Open Procurement and agri-insurance investments
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	18%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones 2020/21	Progress
Number of female and male public officials trained	Planned / Urban Development: 50 (at least 30% female) / Rail: 50 (at least 30% female) / OCP: 119 (70 public officials and 49 other stakeholders) )(at least 50% female) / Regional Competitiveness: 80 / ANI: 30 / Agri-insurance: 40 (at least 50% female) / Total: 289	Achieved by October 2020 / Urban Development: 693 / Rail: 52 (Female: 25; Male: 27) / OCP: 149 (Female: 85; Male: 64) / Regional Competitiveness: 0 / ANI: 0 / Agri-insurance: 32 (G&I training for institutional beneficiaries) / Total: 926
Number of training sessions and/or modules dedicated to gender issues	Planned / Urban Development: 2 / Rail: 2 / OCP: 2 / Agri-insurance: 3 / Total: 9	Achieved by October 2020 / Urban Development: 9 / Rail: 1 / OCP: 2 / Agri-insurance: 2 / Total: 14

An output score of A+ reflects the total progress made across both indicators, which exceeds original expectations. Activities planned in Q1 2021 for Regional Competitiveness and ANI will ensure all milestones will be met in this FY.
Rail
The National Government's vision to reactivate the rail sector recognises the need to build back capacity among public officials on how to plan, deliver and manage railways. In coordination with the infrastructure group of the National Planning Department, the PF delivered a four-day masters-level training on rail management for the Colombian government, in collaboration between Manchester Metropolitan University and Javeriana University. This collaboration between the UK and Colombian universities resulted in a new longer-term agreement between them, to continue joint research projects around sustainable mobility.
Urban Development
The PF also worked closely with the Ministry of Housing, especially the Vice Ministry of Water to build capacity among officials working in the water and sanitation sector. Despite C-19, the PF organised a webinar convening international specialists who shared best practices on water management in arid regions like La Guajira – the region with the lowest continuity of water service in the country. Lessons learnt in such challenging conditions may be successfully replicable in other parts of the country and in cities like Ibagué and Valledupar where the PF is developing water and sanitation projects.
Regional Competitiveness
- The project working with Regional Competitiveness Commissions (RCC) to formulate or adjust their Competitiveness Agendas, and produce poverty and inclusion diagnoses, was completed in September 2020. This project worked with RCCs, taking as a basis a methodology developed by the Ministry of Trade to create the agendas, and improved it to incorporate a G&I perspective. The methodology was successfully transferred to the RCCs, for them to be able to update their agendas on their own, as their needs evolve. This project did not initially include a G&I annex or specific guidance, and the initial G&I deliverables were not adequate. The PF provided support through an external consultant to improve them, while also creating capacity at the delivery partner (Confecámaras) to complete the process.
- A second project on improving the governance of the Regional Competitiveness Commissions with a G&I focus, started in May 2020. The region-specific diagnoses have been completed and the proposed governance model is being socialised. The project includes a component to create and strengthen their members’[2] capacity on project structuring and evaluation, incorporating a ‘gender equality for competitiveness’ perspective (based on the former components), which are scheduled for Feb/March 2021.
  [2] Public officials from regional governments, and non-government stakeholders, such as the Chamber of Commerce, media, academia, other regional sectorial boards.
- Aerocafé project has one of the widest outreach to external stakeholders through its technical components. Besides the Aerocafé organisation as the main beneficiary, Aerocivil (the aviation agency), the National Infrastructure Agency and the Colombian Association of Engineers participate in the project, which allows to promote technical, managerial, social and environmental good practices beyond the main beneficiary.
- After the Agendas project, all subsequent PF projects included G&I annexes. Based on the aforementioned Confecámaras experience, the annex was reviewed again to identify key messages or opportunities for clarification. This review was made for Atlántico and Barrancabermeja projects, and the winning proposals committed to specific actions across the three levels of ambition of the PF G&I Framework, a higher ambition than previous infrastructure projects implemented by CAF.
Open Procurement
- Open Contracting Partnership (OCP) finalised work at the two pilot departments Caldas and Valle del Cauca. The PF received and accepted a request from Bolívar region to be included in the project (now 9 regions). Based on lessons learned from the pilots, OCP started work in November 2019 with Atlántico, Magdalena and Bolívar.
- OCP’s schedule of scoping missions and ‘open contracting talks’ (workshops) for those 3 regions were affected by the transition to new local governments, and then by the pandemic. The team quickly moved to online delivery, challenging still as local governments were fully focused on the pandemic. The emergency put public procurement in the spotlight, which made the project more relevant. As a result, the structure and timing of workshops were modified to facilitate the delivery of the virtual sessions, while allowing increased participation by stakeholders from other regions, promoting peer to peer exchange. In this case, the pandemic led to innovation, greater relevance and greater participation.
- OCP worked together with the PT to incorporate a G&I specific session during the trainings, as recommended in the 2019 AR. So far, 109 public officials have been trained (61 women and 48 men), together with 40 non-government stakeholders (24 women and 16 men).
- The PT worked with Colombia Compra Eficiente (CCE), the national procurement agency, to finalise the design of the second phase of the open procurement activity (i.e. rolling out SECOP II to 9 departments). The project was approved in March 2020, but Findeter and CCE did not complete the ToRs by June 2020, when the reduction of ODA was announced. The project is ready to resume, subject to the confirmation of resources.
Corporate Governance Reform of ANI
- This project had a significant delay, but started implementation in April 2020. The MoU with CAF was extended at no cost until August 2022 to allow for the 18-month evaluation. The project is currently on track.
- The diagnosis identified 70 recommendations, of which 35 will be addressed through the project as action plans. Those 35 action plans will be consolidated in 18 documents/policies for ANI to implement, currently being developed (phase 2). A training on the new citizens’ overseeing schemes will be conducted for ANI’s staff and external stakeholders (communities, interventorías[3], concesionarios, regional and national agencies), likely to be early December 2020.
  [3] Independent quality assurance contract
- The project incorporates a G&I perspective throughout all its stages. The diagnosis conducted in the first stage was socialised with ANI staff and external stakeholders (147 women, 93 men and 7 participants not specified)[4].
  [4] The report on people who participated in socialisations is not counted as trainings, but is in the Output 1 of the activity-level logframe.
Agri-insurance
- The agricultural risk management survey project started implementation in Q1 2020. This is a qualitative study to identify gaps and opportunities to increase knowledge in agricultural risk management tools and increase capacity of public officials to design and structure programmes that will reduce vulnerability of smallholders from climate and financial risks. Four productive systems (rice, corn, potato and cattle) were prioritised by the Colombian Government based on exposure to different types of agricultural risks (including climate), and the number of smallholders participating in the productive activity[5]. All PF agri-insurance activities are part of this strategy of looking to increase resilience and to implement risk management tools such as insurance. During the Logframes review in March 2020, indicators were adjusted to reflect these outcomes.
  [5] https://www.minagricultura.gov.co/noticias/SiteAssets/Paginas/Forms/AllItems/Estrategia%20360%20grados%20-%20Ministro%20Andr%C3%A9s%20Valencia.pdf
- The Ministry of Agriculture established in the National Development Plan 2018-2022 a network of 8 public institutions responsible for developing tools and strategies to manage risks in the agricultural sector. The agri-insurance activity works with 4 of them: UPRA, DANE, Finagro, and IDEAM, which lead on the project’s technical components (for SIGRA, Geoagro, Forecast systems and production costs), and defined technical teams responsible for drafting ToRs, assessing proposals and approving technical deliverables. To ensure VfM and primary/secondary benefits, CAF provides technical, legal and administrative advice to all technical teams. Incorporating G&I into the projects was a challenge, mostly because public officials and technicians from agri-institutions have little to no knowledge on gender matters. To include G&I and secure primary benefits, CAF organised G&I training sessions with technical teams from UPRA, MADR and Finagro. To date, 32 public officials have received training.
Training on G&I
Recognising the appetite from newly elected local Governments for improving technical capacity on G&I to build their local development plans, the PT held a significant number of workshops between November 2019 and March 2020. A G&I workshop for newly elected Mayors and Governors, took place in the City of Santa Marta in November 2019 with 168 participants. After that, follow up sessions involved public officials from 14 municipalities and departments between February and March 2020 (390 participants). Both processes were organised together with Findeter. In addition to the above the G&I specialist consultant that provided the trainings, also gave technical inputs and feedback to public officials from Risaralda, Armenia, Cali, and Cundinamarca on their specific local development plans.
Summary of responses to issues raised in previous annual reviews
There were four specific recommendations for this Output in 2019 AR (two related to G&I, one to open procurement and one to transparency in the construction sector), which the PT took action on (see Annex A, recommendations 12-15).
Recommendations
1. Explore mechanisms and opportunities to promote engagement from the private sector in the open procurement activity (by Feb 2021).
2. Develop a lessons learned note from working on SECOP II and open procurement data standards, especially at subnational level, and share to PF Network as good practice (by April 2021).
3. To ensure VFM, the Programme should leverage the GIP’s training activities to build capacity among public officials from prioritised cities and departments.

Output Title	Innovations aimed at inclusive, sustainable development piloted and tested in agri-tech, agri-insurance, urban, rail and regional competitiveness
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones 2020/21	Progress during the first 6 months
Number of projects supported by the PF that incorporate innovations in products, processes, marketing or organizational innovations	Planned / Agritech: 7 / Agri-insurance: 2 (Geoagro, SIGRA) / Urban Development: 4 (Manizales, Santa Marta, Valledupar, Ibagué) / Rail: 2 (Bogotá-Zipaquirá, Dorada-Chiriguaná) / Regional Competitiveness: 4 (Aerocafe, Logistics Hub, Agrologistics centre, Tilapia) / Total: 19	Achieved by October 2020 / Agritech: 7 / Agri-insurance: 2 (Geoagro, SIGRA) / Urban Development: 4 (Manizales, Santa Marta, Valledupar, Ibagué) / Rail: 2 (Bogotá-Zipaquirá, Dorada-Chiriguaná) / Regional Competitiveness: 4 (Aerocafe, Logistics Hub, Agrologistics centre, Tilapia) / Total: 19
Number of UK-Colombia official partnerships formed	Planned / Urban development: 9 / Rail: 6 / Regional Competitiveness:12 / Agri insurance: 15 / Agritech: 7 / Total: 49	Achieved by October 2020 / Urban development: 9 / Rail: 7 / Regional Competitiveness: 15 / Agri insurance: 3 / Agritech: 7 / Total: 41

Key Points[6]
[6] In order to have a definition of innovation for our logframes, the definitions established by Innovate UK and the OECD will be taken as a reference (please see Umbrella Logframe for details).
Infrastructure (Rail and Urban)
- Both rail projects are implementing BIM (Building Information Modelling). Bogotá-Zipaquirá, developed by a Deloitte-led consortium, is adopting Transport Oriented Design approaches. Manizales’s new public transport system, also structured by a Deloitte-led consortium included smart ticketing systems, smart fleet monitoring, user information systems and traffic light controls. EY led consortium’s proposals to revitalize Santa Marta’s historical centre are based on smart city solutions and Valledupar’s designs will be guided by User Centred Design approach.
- In relation to innovations directly linked to climate and environment, the Manizales project is looking to update the integrated public transport fleet with electric buses. The project will also integrate the whole transport system, including the public bicycle system.
- One of Santa Marta’s technological solutions is aiming to monitor the city’s vulnerability regarding climate risk, to make it more resilient.
- The project of Ibagué is aiming to prevent sewage water from reaching the city’s rivers. The system to be developed will have communication with a monitoring centre that will facilitate management of the new sewage network in real time.
Regional Competitiveness
The 4 Regional Competitiveness projects (Aerocafé in Caldas, Logistics hub in Santander, Agro-logistics centre in Atlántico and Tilapia value chain in Magdalena) have adopted (or are about to) a range of innovations including new methodologies, systems and tools to improve the efficiency and effectiveness of each project (see Annex C for details). Beneficiaries have reacted very positively to the innovations proposed around project management and capacity building. They see them as an enormous value added that can allow them to improve their regular work beyond the specific project they will be working on with the PF.
Agritech Catalyst
- Each of the 7 agritech projects has its own specific technology and innovation. Some projects like LISTO will soon reach market-ready stage, and technologies like the banana irrigation systems reached the product-prototype level.
- The main innovations piloted were: digital irrigation systems for bananas; digital agri-produce trading platform; scientifically improved cocoa bean fermentation; digital cocoa production; satellite remote sensing systems for coffee; digital control of coffee pest; and scientifically improved tilapia breeding. Other unintended innovations were also identified and achieved positive results such as the bean-to-bar business model in the vegan chocolates project.
- The PF has raised awareness and encouraged partnerships outside of the Programme itself, as is the case of Farming Data and the Chambers of Commerce of Barrancabermeja and Guajira that have formalised MoUs.
Agri-insurance
- Innovations have been developed in this activity in SIGRA, Geoagro and IDEAM (see Annex C for details). SIGRA is the most important project of the agri-insurance activity. It is a digital platform that will integrate data sets from relevant public institutions to develop Interactive Actuarial Maps (IMAP) to help different actors to identify, evaluate and assess financial, market, climate and pest-related risks in different agricultural systems. The Geoagro platform will consolidate all databases on financial incentives with geolocation data, to contribute to better informed decision-making on policies and products.
- This activity has been greatly welcomed by entities in charge of designing and implementing agricultural policy in Colombia. MADR, UPRA, IDEAM, Finagro, and most recently DANE, repeatedly express their interest in the project and even formalised their relationship through an official agreement.
Commercial considerations
Companies in the commercial framework have shown little appetite for water and sanitation projects. This was evidenced in the first round of tenders for water and sanitation projects, when Findeter did not receive any bids. Rural projects have been less attractive than urban ones (Valledupar vs Ibagué). Working with rural communities, including indigenous groups, is perceived as challenging by the commercial framework companies. That is one of the reasons why fewer partnerships have been made.
Summary of responses to issues raised in previous annual reviews
There were three specific recommendations for this Output in 2019 AR (one linked to agri-insurance, another to non-ODA resources and activities, and a third related to innovation for the entire programme), which the PT took action on (see Annex A, recommendations 16-18).
Recommendations
1. As new regional development projects are designed with FDN, explore how innovations can be incorporated, taking lessons learned from CAF’s experience, as well as FDN’s specific experience on digitalisation (i.e. using BIM following UK and international standards).
2. Document lessons on the unexpected speed of the innovation-uptake in Colombia from the Agritech Catalyst project to share among the UK network.

Output Title	Urban, rail and regional competitiveness and agriculture projects are designed, structured based on international best practice and ready for investment in an inclusive and sustainable way
Output number per LF		4	Output Score	A
Risk:		Moderate	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones 2020/21	Progress
Number of inclusive projects supported by the PF (urban, rail, agriculture and regional competitiveness) which start implementation, contracted by Implementing Partners	Planned / Urban Development: 4 (Manizales, Valledupar, Ibague and Santa Marta) / Rail: 3 (Bogota-Zipaquira, La Dorada-Chiriguana, TCV) / Regional Competitiveness: 4 / (AeroCafe Caldas; DALA Atlántico; Tilapia Value Chain Magdalena; Logistics Hub Santander) / Agri-insurance: 5 / TOTAL: 16	Achieved by October 2020 / Urban Development: 4 (Manizales, Valledupar, Ibague and Santa Marta) / Rail: 2 (Bogota-Zipaquira, La Dorada-Chiriguana) / Regional Competitiveness: 2 / (AeroCafe Caldas and Tilapia Value Chain Magdalena) / Agri-insurance: 3 / TOTAL: 11
Number of urban, rail, agriculture and regional competitiveness projects/products/services designed, structured and ready for investment	Planned / Urban Development: 2 / (Manizales and Santa Marta) / Rail: 0 / Agritech: 2 (LISTO and Agricompass) / Regional Competitiveness: 0 / Total: 4	Achieved by October 2020 / Urban Development: 0 (Manizales and Santa Marta are on track to conclude this FY) / Rail: 0 / Agritech: 0 / Regional Competitiveness: 0 / Total: 0
Number of women and people from disadvantaged groups who participate in the project design consultations	Planned / Urban Development: 200 (50 per project) / Rail: 100 (50 per project) / Agritech: 50 / Regional Competitiveness: 200 (50 per project) / Agri insurance: 50 / Total: 600	Achieved by October 2020 / Urban Development: 462 (300 women; 162 people from disadvantaged groups) / Rail: 507 (459 women; 48 people from disadvantaged groups) / Agritech: 56 (33 women; 23 men) / Regional Competitiveness: 0 (Aerocafe began this process, but reporting pending) / Agri insurance: 0 / Total: 986
Number of anticipated beneficiaries from urban, rail, agriculture and regional competitiveness projects	Planned / Urban Development: 1,645,413 / Rail: 6,204,049 / Regional Competitiveness: 5,185,272 / Agritech: 556,932 / Total: 13,591,666	Achieved by October 2020 / Urban Development: 1,645,413 / Rail: 6,204,049 / Regional Competitiveness: 5,185,272 / Agritech: 556,932 / Total: 13,591,666
Number of new Commercial Opportunities as a result of PF work	Planned / 0	Achieved by October 2020 / 1 (Manizales)
Value of new export opportunities for International and UK businesses as a result of PF activity (urban, rail, agriculture and regional competitiveness) (Portfolio KPI 17)	Planned / 0	Achieved by October 2020 / £100,000 (Manizales)

Key Points
Project Fichas built in 2019 remain the principal source of information on anticipated beneficiaries. Most project fichas considered direct and indirect employment generation, and people with access to improved infrastructure. Feasibility studies will refine the number of potential beneficiaries for each project, including users, indirect beneficiaries and potential labour needed for construction and operation of new assets.
Infrastructure
- Feasibility studies for Manizales and Santa Marta are expected to be completed by December 2020 and January 2021, respectively.
- Though the final decision for investment is vested on each project sponsor (i.e. municipal authorities), PF outputs will provide them with full business cases including the necessary information for such decision.
- The Programme has leveraged substantial co-financing from partners of the Colombian Government to design three train rehabilitation projects integrating UK expertise and technologies. The UK contribution of £4.8m ODA for these investments has attracted £9.1m of matched funds from the Colombian government.
Regional Competitiveness
- Competitiveness Agendas project: completed in September 2020. The agendas were successfully formulated and approved by the RCCs, and the gender and poverty annexes improved to satisfaction. Currently finalising them for publication in the Ministry of Trade National Competitiveness portal http://www.competitivas.gov.co/
- Governance models (Deloitte): contracted in May 2020 and completion due in March 2021. Region-specific diagnosis have been completed and the governance model has been formulated. Currently the model is being socialised with target regions.
- Aerocafé in Caldas (KPMG-Aertec): contracted in June 2020 and completion due in June 2021 (likely to be extended). This project is currently completing the analysis and validation of existing studies, which has taken longer than planned, given the impressive amount of information available. Those results should be received by the end of 2020. Simultaneously, the PT has promoted and led discussions on how to strengthen the environmental components of the airport which has been well received.
- Tilapia value chain in Magdalena (Secure Harvest): contracted in October 2020 and completion due in May 2021. The project plan was presented to the main stakeholder. The supplier formulated criteria to prioritise farms, and data was gathered both by the supplier and the governor’s office. Technical committees discussed data and selected the two farms where the analysis will be conducted.
- Logistics hub in Santander (EY-IDOM) and Agro-logistics centre in Atlántico (EY-CEBAR). Both these projects have now been awarded. Contracts should begin in December 2020 and end in January 2022.
- Antioquia: Project being defined with FDN as new implementing partner. Definition (estimated): December 2020. Design and Tender (estimated) before March 2021.
G&I Aspects of Infrastructure and Competitiveness Projects
The PF has undertaken consultations with women and marginalised groups as a standard for infrastructure and regional competitiveness projects. This has been the case for Manizales, Santa Marta, and Aerocafé and will happen for the Bogota-Zipaquira project. Tools used for consultations range from social cartographies, focus groups, perception surveys, semi structured interviews and participative planning workshops.
The level of participation of women and people from disadvantaged groups has been higher than initially anticipated. For the period between November 2019 and October 2020, the following summarises participation in different stages of the projects:
- Manizales participative workshops stage: 82 women; 38 people from disadvantaged groups (people with disabilities, ethnic minorities, conflict affected population, LGBTI, others).
- Santa Marta diagnosis stage: 61 women; 24 people from disadvantaged groups.
- Santa Marta participative workshops stage: 166 women; 100 people from disadvantaged groups.
- Bogota-Zipaquira diagnosis stage: 459 women; 48 people from disadvantaged groups.
A similar exercise took place for Agritech projects, principally through perception surveys, focus groups and workshops that allow project teams to identify needs and current access to technology of smallholders. Most projects identified the need to develop low-tech modalities, such as SMS and voice messages in order to adapt to these needs.
Secondary Benefits
In the infrastructure strand, the PT originally anticipated that secondary benefits were likely to be soft power in the short term. However, the programme has already had an early export win worth £100,000 that was confirmed by Deloitte in August 2020. Manizales Mayor’s Office was impressed with the designs produced by the Deloitte-led consortium for the PF’s Manizales Intelligent Transport Project, that they requested Deloitte to include a cable car component into the project. The company signed a contract to make this feasibility study that will complement the PF project.
Summary of responses to issues raised in previous annual reviews
There were seven specific recommendations for this Output in 2019 AR. The PT made progress in all recommendations, except for two (see Annex A, recommendations 19-25). One of these two recommendations required action from the Economics and Analysis Directorate in London. However, due to reduced capacity this year, it was agreed not to prioritise the update of the cost-benefit analysis. The second one was related to explore funding to advance research related to the Urban activity, but due to additional pressures related to Covid-19 and administrative delays, the PT decided not to pursue further actions regarding this recommendation and focus efforts on current projects.
Recommendations
1. The PT has learnt a range of lessons on designing and implementing projects, and working with IPs. In order to improve the efficiency of the entire project cycle, the PT should ensure that lessons on G&I, TORs development and contracting are incorporated into the remaining projects (by June 2021).
2. Since the Business Case was approved, the PT’s estimates of beneficiaries to be reached have changed, as have some of the assumptions underpinning the original cost-benefit analysis. Reaching four times as many beneficiaries represents a significant change in the Programme’s effectiveness. The review team therefore recommends that it would be prudent to review and update the cost benefit analysis calculations and VfM for each Programme activity, as this would be a useful tool for Programme management purposes.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE
Key cost drivers and performance
The Programme’s key cost drivers are linked to i) the processes required of Implementing Partners (IPs) as projects are prepared for the market; ii) the strategies for scope of project design; and iii) responses to C-19.
Against the backdrop of C-19, the PT and IPs are continuing to deliver results by adapting to the new virtual world. Travel restrictions within Colombia meant that IPs delivered meetings and workshops online, with the exception of the Agritech Catalyst activity, which requires fieldwork. Six of the seven agritech projects requested a no-cost extension, so they are now expected to finish in March 2021.
By the end of the FY20/21, the Programme will have spent £15.41m (60%) of the total available budget of £25.5m. A further £10.09m is programmed for FY21/22 as most of the projects are classified as prepayments (see further information below in the financial section).
Financial spend to date in Financial Year 2020/2021
	Allocation	Forecast Spend	£ Variance	% Variance
STAFF COSTS (UK & local)	£312,000	£324,000	£-12,000	3.8%
PLATFORM CHARGES	£176,529	£176,529	£0	0%
PROGRAMME DELIVERY
Urban Development	£35,000	£35,000	£0	0%
Rail Development	£1,530,000	£1,530,000	£0	0%
Regional Competitiveness	£1,090,000	£1,090,000	£0	0%
Reform of ANI	£0	£0	N/A	N/A
Improved Public Procurement	£150,000	£150,000	£0	0%
Agri-Insurance	£30,000	£30,000	£0	0%
Agri Tech Catalyst Challenge Fund	£1,295,000	£1,295,000	£0	0%
TOTAL	£4,618,529	£4,630,529	£-12,000	3.8%

The budget for FY 20/21 reflects a small overspend due to the staff costs, primarily driven by the exchange rate and additional costs for the new Colombia Director of the Prosperity Fund. By the end of October 2020, expenditure stood at £3,708,780, leaving £921,749 for the rest of the FY. The payments below for rail development and regional competitiveness have been classified as prepayments due to new PF accounting procedures. These amounts were disbursed last FY to the IPs, but the activities have started this FY.
Expenditure from FY 18/19 to FY 20/21
COLOMBIA PROSPERITY FUND PROGRAMME
Activity	FY 18/19 (£m)	FY 19/20 (£m)	FY 20/21 (£m)
Urban Development	3.16	0.07	0.04
Rail Development	0.54	0.15	1.53
Improved Public Procurement	0.09	0.09	0.15
Regional Competitiveness	1.87	0.00	1.09
Corporate governance reform of Colombia’s National Infrastructure Agency (ANI)	0.24	0.00	0.00
Agri-Insurance	2.09	0.14	0.03
Agri-Tech Catalyst Challenge Fund	0.15	0.85	1.30
FCO Staff Costs	0.38	0.47	0.49
FCO Delivery Costs	0.03	0.05	0.01
Gender and Financial Expertise	0.00	0.02	0.08
Communications and Dissemination	0.00	0.04	0.01
Policy Reform Support	0.00	0.03	0.08
Transitional Fund	0.12	0.00	0.00
Total Cost to PF	8.69	1.92	4.80

Administrative spend was £85,619 (1.86%) by October 2020. This figure is based on the 2.5 admin FTE. Taking the previous spend for FYs 18/19 and 19/20 and forecast spend over the remaining years, it is estimated that the Programme’s administrative spend will be 3.1% of total expenditure over the lifetime of the programme, assuming all programme budget is spent. The admin rate is 3.18% over the Annual Review period, within the 3.5% cap rate that PF programmes are required to meet.
Economy
The Programme first offers contracts to competition on the PF Commercial Framework (CF), and then open to international procurement, ensuring competition is built into the procurement process. The Valledupar project was awarded to a Colombian consortium after four attempts within the PF CF. UK non-CF companies as well as local and international companies can enter into consortia with PF CF companies, or compete as ‘Prime Suppliers’ (i.e., leading the contracts) through the secondary route.
The Programme has faced delays in getting ToRs out to tender as per the original timetables agreed with two of the IPs. All projects tendered by one of the IPs received several expressions of interest and bids, even from UK companies new to the Colombian market. However, due to an unsuccessful Performance Improvement Plan for this IP, no new projects will be delivered through them (see Section F), and the remaining budget was allocated to another IP, who have a proven performance record. Another IP’s performance has also improved since the last administration.
Under the Infrastructure strand, the procurement process for every project has been competitive, which generated savings between 3% and 8% compared with the originally estimated budgets (approximately £315,000). Estimates are based on market price assessments prior to launching the tenders. The PT also complements these assessments with costs of similar projects.
Innovate UK selected projects via a competitive process. They did not charge overheads to maximise funding for programme delivery, had an average ROI of up to £7.30 for every £1 invested, received co-funding from grantees, awarded projects based on potential to contribute towards activity outcomes and appointed a Monitoring Officer to ensure value for money from public funding.
In the open procurement activity, some savings were realised due to C-19 travel restrictions. There were delays in the project schedule, primarily due to the change in local governments in January 2020 and C-19 leading to local capacity being diverted. OCP and the PT rapidly formulated alternatives to complete the programme and a 5-month extension (including a new target region) was approved, at a minimum cost (less than 4% of original budget).
Efficiency
Over the past year, the expansion of specialists in both the PT and IPs enabled the pursuit of more comprehensive projects, whilst ensuring compliance with local regulations. This structure allows the PT to be strategic and flexible, and mediate when needed. For most projects, CAF establish technical boards together with the beneficiaries, increasing their capacity around projects of this nature (aligned with the ToC). Technical boards bring relevant experts together from consultancies, beneficiaries, programme, and suppliers to ensure each deliverable can be reviewed by them. However, to reduce risks to efficiency CAF will not be given any new projects as they were not able to deliver activities at the speed required by the programme.
The PF governance structure facilitates the escalation of issues and support from various stakeholders (e.g. monthly SRO meetings, IPRG, PFIG as needed for project initiation, private sector and wider stakeholder governance bodies). The IPs benefit from their in-house capacity and external consultants to support the PT to supervise the delivery of projects. Each project has different levels of technical requirements and need different types of expertise, some of which cannot be sourced internally. For example, the water and sanitation project warranted high levels of engineering expertise. Therefore, some PF projects require an independent quality assurance contract called “interventoría” that supports delivery.
Indicators at the output level show that the cost of the feasibility studies was originally underestimated, due to the implications of procuring more comprehensive feasibility studies, to underscore the importance of G&I and the need to structure projects that are ready to advance into capital investment phase. However, to mitigate these costs, the Programme sought public co-funding to complement the PF investments. This fortunately ended up demonstrating a strong commitment from project sponsors, which should increase the likelihood of the project designs being executed to realise expected primary and secondary benefits (SBs). A £100k SB has already materialised through the Manizales project at an earlier stage than anticipated.
Benefits realisation of infrastructure interventions relies upon rigorous project design. With a view to strengthen feasibility studies, the PT has strived to incorporate UK methodologies promoted by the GIP in relevant projects (e.g. BIM in Regiotram Norte and Aerocafé, Routemap on Dorada-Chiriguaná), demonstrating synergies between global and bilateral PF programmes.
Effectiveness
In 2020 a comprehensive review of the Programme ToC was undertaken with the support of the MREL Team and PFDU. To reflect the changes in the activity level logframes, the umbrella logframe was also updated at the output level. For example, under the Regional Competitiveness activity, some of the indicators have changed to make sure they are capturing more substantive progress, where previously they mainly captured progress on procedures. This reflects the transition to implementation. After the C2 evaluation concludes, the PT aims to finish updating the umbrella logframe by March 2021 at higher levels to ensure intermediate outcomes are well captured.
Most of the infrastructure projects have secured co-funding, which demonstrates a high level of interest from the Colombian government. For example they will co-fund 70% of the new railway project: however, the capital invested by both parties is at risk if these designs do not lead to project execution due to a lack of funding. To reduce this risk: i) the PT is working with the development banks who mainly invest in Colombian infrastructure projects, including those selected for support by the PF; ii) as part of the financial component of each feasibility study, UK companies are expected to scour British and global capital market opportunities to come up with the right mix of domestic and overseas investment resources; and iii) the PF has selected projects where national, departmental or municipal resources are already earmarked for their execution.
Across the programme, capacity building for public officials has progressed adequately despite the restrictions imposed by C-19, by working remotely to deliver online training sessions. This allowed projects to undertake more workshops with a broader audience than planned, demonstrating the ability to reach more people via digital tools. This improved output will increase the likelihood of realising outcomes in the ToC. Programme delays posed by C-19 have been explained elsewhere in the AR (agritech projects required a no-cost extension, the open procurement activity was extended and projects managed by IPs moved to virtual delivery). For the contracts to be signed, additional clauses have been added to allow flexibility to return to face-to-face delivery once conditions allow. The review team does not foresee any major impact on benefits realisation due to direct C-19 delays, and the PT still expects to achieve results in the original timeframe. However, the PT assesses that the original estimated benefits may no longer be valid, as indicators in Output 4 show a fourfold increase in the projected number of beneficiaries, which would represent a significant change in the Programme’s effectiveness. An indirect impact of C-19 has been delays in Spending Review announcements, which has temporarily stalled implementation of new projects. It is unclear as of yet what the longer term effect of this might be.
Within the public procurement activity, aimed at working with procurement data at regional and local level, two pilots were selected due to the novel nature of the projects. The project was successfully conducted in those two regions, and the lessons learnt were translated into specific modifications of the methodology, content and delivery model. Only a few modifications in the methodology were needed. The project is delivering tangible results at the output level in terms of increased capacity of local governments, and the PT is seeing results in the procurement process set out in the intermediate outcomes. The C2 Evaluation will assess this further.
Equity
Gender Equality & Social Inclusion (GESI) strategies have been put in place for all projects. The logframes have embedded disaggregation by sex. Information on quintiles is scarce in Colombia, especially for high-level indicators. Nevertheless, at the output level the PT has included disaggregation by other types of excluded groups such as people with disabilities, LGBTI community, ethnic minorities and others.
Efforts dedicated to the social analyses and G&I activities during the development of feasibility studies will ensure that the provision of new infrastructure services be more inclusive and gender sensitive (e.g. G&I plan for the implementation of the future public transport system in Manizales). The PT ensure requirements are in place to facilitate the meaningful participation of communities and future users of the new infrastructure in the design phases, which enhance active participation of women and excluded groups, increases the sense of public ownership and makes the projects more inclusive.
Clear requirements and regular oversight activities by the PT have helped the projects to create spaces for active participation of women and excluded groups during the design phases (e.g. focus groups in Manizales, online interviews and workshops in Santa Marta, initial consultations in Regiotram Norte), and ensure suppliers take in consideration their inputs when designing the project solutions.
The agritech projects delivered G&I action plans to ensure benefits for female smallholders, taking into account social inclusion considerations. The PT reviewed these plans to ensure compliance with the G&I PF Framework.
OCP incorporated a G&I component in its capacity building process on the back of a 2019 AR recommendation. OCP started its own research process, and incorporated recommendations from the PF external consultant and PF advisers, resulting in new versions of workshops including a G&I session. The session considers gender equality basic concepts and how they can be linked to procurement, from women-led SMEs, to considering how MSMEs can participate, while emphasising that G&I considerations are crucial when designing projects.
Assessment of whether the programme continues to represent value for money
Overall the programme’s VfM performance, based on analysis of these drivers and a self-assessment using the EL VfM scorecard, is “good”. The C2 evaluation will assess VfM to confirm or alter the PT’s self-assessment.
The programme has made significant progress on monitoring and evaluation and is already delivering results at the output level and, for some activities, early results at the intermediate outcome level. The programme continues to expect sustainable long-term outcomes and impacts. Engagement from beneficiaries is very high, taking into account the new Mayors and Governors who took office in January 2020. PF projects are high up in the agenda of our beneficiaries; most of them are included in the Regional Competitiveness Agendas and/or the Regional Development Plans, and some even in the national sectoral plans or the National Development Plan. The programme also promotes a regular and close relation between local authorities and the SRO to keep momentum. The PT engage with the national-level relevant agencies and ministries, to make sure the PF is on their agenda and aligned to manage challenges.
C-19 and the ensuing challenges to the Colombian economy will mean that the impact indicators on growth and poverty may be harder to achieve. Despite this, the review team believe that the Programme is well placed to help bring Colombia back on track by operating in productive sectors which are key to its economic recovery.
Quality of financial management
Development banks, CAF and Findeter, receive quarterly payments in advance while Innovate UK, CIAT and OCP, as not for profit organisations, are paid quarterly in arrears. The PF requires that payments from IPs to suppliers be made only against approved deliverables, which help to assure quality of deliverables and creates incentives for efficient delivery. Complaints were received from the PF CF companies about some IPs taking longer than expected to review the deliverables, thus delaying payments. The PT is working with IPs to identify ways to mitigate this.
As highlighted in the previous AR, the Programme faces funding risks (both positive and negative) depending on exchange rates. The IPs OCP and CAF are paid in US Dollars and Findeter and FDN in Colombian Pesos. Innovate UK is paid in GB Pounds. However, some exchange rate risk may still occur if the smaller grant-funded projects are purchasing Colombian goods and services.
When awarding a contract to a company, the IPs conduct a rigorous a due diligence for all suppliers. Equally, in the agritech projects on completion of projects an Independent Audit Report for each project is required.
Changes in staffing
The PF recruited a Social Development Adviser C4 (L) position in March 2020 and a PF Delivery Officer A1 (L) in January 2020. In October 2020, the new PF Director joined the team and the PF Deputy Head was appointed.
Recommendation
For all the remaining projects, the PT should ensure PF-funded projects are co-financed with the Colombian Government (by June 2021).
Date of last narrative financial report	27 October 2020
Date of last audited annual statement	January 2020

## E: RISK

Overall risk rating
Moderate

Overview of programme risk
C-19 features prominently in the Programme’s revised risk matrix, due to the delays caused in the Programme and the ensuing uncertainty. Similarly, the Programme’s inability to make payments for projects which go into next financial year has caused delays. Below are the Programme’s main risks (including those which are amber), a complete risk matrix is attached at Annex D.

Risk: Lack of clarity over pre-payments means many outstanding projects may not be able to launch as planned in FY20/21, meaning they may not be completed by the end of the current programme in 2022.
The Programme’s main implementing partners require resources in advance to be able to start the procurement process for all projects. The PT currently have several projects that are ready to go out to tender, but for which activities will only commence next FY. This is due to the time it takes (5-6 months) to request, receive and evaluate proposals before the award of a contract. The PT therefore needs to make prepayments now for projects which commence next calendar year, and must conclude before the Programme end date of 31 March 2022. However, payments cannot be made until an allocation for next FY is agreed.

Risk: Impact of COVID-19 and associated national lockdown measures and travel restrictions reduce delivery capacity and delay implementation.
- Most of the Programme is research and design-based, which can continue with suppliers working from home. However, projects that require greater consultation, field visits and stakeholder engagement have slowed down and need to be extended (namely AgriTech and Open Procurement)
- VfM calculations may be changing, as projects are forced to adapt under extended lockdown conditions.
- Programme to maintain constant contact with implementers and review COVID impact on each activity and project on monthly basis, assessing any changes to delivery capacity as lockdown is extended and infection rates increase.

Risk: Economic impact of COVID returns Colombia to poverty levels experienced 20 years ago, impacting ability of Programme to realise anticipated poverty reduction targets
The Programme will continue to monitor economic data, especially in the regions and cities where it operates. If needed, the Programme should commission research to examine the economic impact of COVID-19 on beneficiaries, factor these findings into reporting and evaluation data, and make appropriate programme adaptations where possible.

Risk: Sustainability of interventions affected by COVID-related delays and consequent inability of programme to scale-up and entrench mechanisms to assure durable impact beyond the current life of the programme.
The combination of the first and second risks above may mean the Programme is not able to achieve anticipated milestones, and therefore not realise impact of adequate depth and breadth to be sustainable. Even if the PT manages to complete the design and pilot projects, adequate time must still be factored in to allow the Programme to draw out best practices and consolidate this learning in policy formation and capacity building.
While the Programme will make all efforts to keep projects on track (as outlined above) and make realistic adaptations to timelines where necessary, it is important that the Programme be extended beyond the current 2022 deadline to consolidate the gains it delivers into sustainable change, both for primary purpose and secondary benefits.

Outstanding actions and recommendations from risk assessment
None

## F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
All seven activities of the Programme are on track, but throughout the year several amendments were made to adequately reflect project timetables affected by administrative processes, and changes resulting from adapting project delivery to the C-19 reality.
- CAF MoU amendment approved and formalised in May 2020. The amendment extended the MoU until August 2022 for SIGRA and ANI’s governance reform projects, at no additional cost. The implementation of these 2 projects require almost 2 years, which fell beyond March 2022.
- OCP grant agreement amendment approved in September 2020. The amendment extended the grant agreement for 5 months, added a target region and resources (under 4% of original value).
- Innovate UK: Due to C-19, 6 of the 7 projects required no-cost extensions, to finish in March 2021.
- FDN MoU amendment in progress. The amendment will include the Valle light rail project and budget, as well as the regional development activity and budget in Antioquia.
Performance of partnerships
CAF
- Despite delays and challenges in implementing projects, the PF and CAF teams have strengthened their working relationship and communication channels, and have been able solve issues, take projects forward, and embrace challenges as partners.
- PF CF Companies appreciate CAF’s organised way of working and transparency; but complain about long administrative processes (both the tenders but specially signing the contracts once awarded), as well as that CAF does not provide feedback from the tenders, and that the deliverables’ approval process takes long time. The PF team has insisted on feedback being crucial for companies to improve, and on optimising administrative procedures. The Agriculture and Governance advisers meet the team regularly.
FINDETER
- The changes in Findeter’s team through 2019 continue to have a positive impact in the relationship with the PT, and facilitated mutual understanding to take projects forward. The PF Infrastructure Adviser meets with the Findeter Team regularly, as does the Governance adviser for the institutional capacity project (see changes in delivery plan).
- Taking into account previous feedback, the PT advised Findeter to improve interactions with the private sector to facilitate processes and promote participation and competition in their tenders. Findeter adjusted their procurement procedures by incorporating activities like Early Market Engagements and public hearings to clarify ToRs of projects. Improvements are evident in terms of the numerous bids received for projects unsuccessfully tendered several times before. For example, Ibagué received 2 and 5 bids for designs and interventoría respectively (from 15 companies); and Valledupar received 9 and 4 bids respectively (from 34 companies).
- PF Commercial Framework companies continue to complain about Findeter’s contracting process. Although they recognise that ToRs are clearer and more aligned with market prices, they indicate that some administrative processes are confusing, mix legislation, and are not flexible. One company complaint about their deliverables’ approval process, and mentioned Findeter’s difficulty to facilitate the relationships among projects teams and local authorities.
FDN
- FDN is the PF’s newest delivery partner. They have proven to have robust technical capacity, which allows them to lead demanding technical discussions. On the other hand, they are a relatively new and small organisation, allowing them to internally articulate processes to be responsive and agile, while keeping technical delivery at a high standard. Important to note they also fund projects, so they also contribute that strategic and market-oriented mindset to the programme. The Infrastructure Adviser meets them regularly.
- Companies indicated that FDN was the best implementing partner by far, technically and administrative clear and effective.
- FDN was offered/asked by the PF team to take the lead of the remaining regional development projects, which they accepted. The Infrastructure and Governance Advisers meet with them regularly.
Innovate UK
- A new official was appointed by IUK to lead the Colombia Agritech Challenge Fund. This action has brought positive changes to the activity in terms of communication and performance. PF stablished weekly catch-up meetings with the IUK official, which has dramatically improved activity management.
- IUK has a Monitor Officer (MO) appointed to manage all projects. The MO holds quarterly project review meetings with all project’s partners to review reports, timing, budget, G&I and future activities. PF supports G&I components and works closely with the MO to ensure that minimum requirements in terms of G&I are reached. G&I reviews for all projects was led by PF and IUK participated actively. After the reviews, IUK followed up all commitments and liaised with project leaders to include the feedback into the projects.
OCP
- OCP always delivers their work on time to a high standard. They have proven to be a modern and flexible organisation, able to accommodate to the changing environment, but also to new requirements.
- Their commitment to incorporate G&I sessions is highly valued, as well as their engagement with regional and local governments. This year new activities were envisioned, such as the data hackathon, which were successfully executed. The Governance Adviser meets with them on a regular basis.
Changes in the Delivery Plan
On regional competitiveness, it is expected that all remaining resources for the last projects will be transferred to FDN.
Phase 1 of the tilapia competitiveness project was meant to begin implementation in Q1 2020. Most of the work of phase 1 required field visits and experts traveling from UK to Colombia. Due to C-19 travel restrictions, the PT decided to postpone the beginning of the implementation until adequate conditions were met. Unfortunately, this reduced the timeframe for the execution of a phase 2 and PF decided to limit the project to its first phase. The resources initially intended for Tilapia 2 will be used for a new agri-insurance pilots. Given CAF’s lengthy processes, the PF decided to procure for a different implementer to deliver this activity, in order to obtain better VfM and capacity to deliver a grant challenge fund.
Originally, Findeter was to manage the 2 projects of the Open Procurement activity. Open Contracting Partnership (OCP) is successfully implementing the procurement data capacity building in the regions. It is still planned for Findeter to manage the second project with Colombia Compra Eficiente to roll over SECOP II. However, Findeter and CCE failed to meet the deadline to have ToRs ready (June 2020) and the project was put on hold until resources are available following the Spending Review.
Plans to deliver all the rail projects through Findeter were adjusted as it was evident that their ability to prepare such complex projects was limited (Bogotá-Zipaquirá is the first rail project in Findeter’s portfolio). The PT decided to collaborate with FDN to deliver the remaining rail projects, taking into account their broader experience in this type of projects (FDN successfully structured the first metro line of Bogotá).
Similarly, Findeter failed to reach an agreement on time with Santa Marta authorities to deliver the second Urban Development project in that city (i.e. Sustainable Drainage Systems) and therefore the PT decided to deliver only one project in Santa Marta (i.e. Smart City Pilot), and instead prioritised two projects in Cartagena.
Asset monitoring and control
The Programme is not generating any assets nor is expected to later on.

## G: BUSINESS ENVIRONMENT

How has the business community and business environment responded to the programme?
- Our programme engaged and has strong relations with several Colombian ministries and governmental agencies, as well as a large number of UK and Colombian businesses that have supported the implementation of the bilateral PF Programme.
- There is limited appetite from Commercial Framework companies to work in Colombia due to the value of some PF projects (less than £1m). In addition, Commercial Framework companies have struggled to comply with Colombian public procurement requirements and associated bureaucracy. The PF has invested significant time in negotiating adaptations to implementing partners’ contracting processes to meet the needs of UK and international companies. Despite a difficult operating environment, 16 PF projects have been awarded this year and 62 consortiums have been created to present bids for PF tenders.
- There are sectors in the UK with an enormous appetite to expand into the Colombian market, such as Agriculture. UK companies and Colombian stakeholders are very keen to look for synergies and support the agri-tech and agri-insurances activities, as evidenced by the KTN mission report (using non-ODA).
- In March 2020, PF with support from KTN and CIAT organised the second agri-tech mission to Colombia. The results indicate that 15 out of 17 companies anticipated commercial wins with an indicative value between £1.43 million and £5.88 million sales per year. The Mission also facilitated the signature of a MoU (Bionema & Scientia); the set-up of two UK companies in Colombia (Agropy and Challenge Group); and the creation of four partnerships between Colombian and UK stakeholders to develop joint projects in the Agriculture sector (Petiole, Mercaririsk, Trade in Space and Fruto del Espiritu).
What role has non-ODA spending played in promoting programme objectives?
- Colombia Prosperity Fund non-ODA resources play a key role in enabling opportunities created by the bilateral Programme to translate into commercial wins and secondary benefits for international businesses, including UK companies. Non-ODA resources have allowed us to i) support companies to develop, or reinforce their commercial foothold in Colombia through private sector partnerships; ii) create or strengthen company access to commercial opportunities at the sub-national and national levels; and iii) assist companies to strengthen their capacity to win additional contracts in Colombia.
- During the past year, the PT has promoted PF commercial opportunities through: i) Non-ODA activities and virtual events which include outreach to infrastructure and agriculture sectors; ii) advertising all 16 PF-generated contract opportunities to the PF Commercial Framework companies and local, international, and other UK enterprises to promote the creation of consortiums; and iii) using of different communication channels as monthly commercial bulletin, LinkedIn, Facebook and Twitter.
- This year non-ODA activities were negatively impacted by COVID-19. Several commercial events were cancelled or postponed during March to September due to outbreak restrictions, but also because the non-ODA allocation for commercial activities was approved in August. However, the programme was able to deliver several virtual events at no cost that helped raise awareness of wider commercial opportunities between the UK and Colombia, attracting new companies to explore Colombia virtually, to understand how they can pursue not only PF contracts, but other business opportunities in the country too.

## H: MONITORING & EVALUATION
Evidence and evaluation
The Cycle 2 Evaluation for the Colombia Programme was initially planned to take place between June and October 2020. Evaluation planning took place in April and training for VfM for the Advisers was conducted in May. Nevertheless, due to effects of Covid-19 and instructions from London, the C2 Evaluation was put on hold. Authorisation to move on with the evaluation was issued in October and the updated approach paper was approved on 12 October. The EL Team and the PT had the kick off meeting of this evaluation cycle on the 26th October. To date, most of the documentation required was sent to the evaluation team, and the key informants’ information was submitted. According to the timeline, a first draft of the evaluation should be ready on 7 January 2021 for the programme team’s review. The final C2 evaluation report will be submitted to JFU on 15 February 2021. EL is also working with the PT to undertake a gender and inclusion case study due in early 2021.
An in-depth review and updating of the programme’s theories of change took place from early March, with a visit of the MREL Teams and PFDU to Bogota, to September 2020. Assumptions behind each ToC were reviewed and refreshed when required. The adjustments also captured better the reality of most activities after starting implementation.
Programme Governance Structures
In addition to the weekly PT meetings and monthly meetings with the Ambassador as SRO, the Colombia PF Programme has three main governance structures to measure progress against primary and secondary objectives, review spend, evaluate risk and recommend improvements. These are the Internal Programme Review Group (IPRG), the Private Sector Advisory Panel (PSAP) and the Stakeholder Group (SG)[7]. All three groups used to meet twice a year, but due to the frequency of meetings on project progress and during official visits from London PF staff, the PSAP and SG changed their timings to once a year. In addition, the Colombia PT meets every six months with its counterparts in Brazil, Mexico and London at the Americas PF Regional Conference to harmonise policies and practices at the regional level and to share lessons learned. This did not happen in 2020, due to C-19, but a new space for regional exchange was established on a monthly basis between programme Heads and Deputy Heads.
[7] The IPRG is composed of representatives from the UK’s Joints Funds Unit (JFU) and the Prosperity Fund Delivery Unit (PFDU) of the Foreign and Commonwealth Office (FCO). The PSAP is made of British businesses with a presence in Colombia especially the 10 companies of the PF Commercial Framework. The SG comprises the three implementing agencies (Findeter, CAF and Innovate UK) and representatives of the Colombian government at the central, departmental and municipal levels.
Monitoring progress throughout the review period
The PT monitors the Programme through various mechanisms. Implementing Partners develop quarterly reports, including updates on risks and results in activity level logframes. These quarterly reports are reviewed by the relevant technical Advisers and the programme Coordinator. The PT also produces monthly and quarterly reports on advances, including a section on risks identification and mitigation. Monitoring of the projects is also done through project follow-up meetings (weekly to monthly) with IPs, suppliers and beneficiaries. Field visits were made frequently before Covid-19 lockdown restrictions started. This happened for Agritech projects and for the Manizales project (which started implementation in 2019). Monitoring is currently made through virtual and phone channels.
Annual Review Process
This annual review took a lighter touch approach. Beyond the aforementioned effects of C-19, this is also related to the travel restrictions and lockdown measures in Colombia and the UK. The AR interviews, needed to identify progress made and receive feedback from the different types of stakeholders, took place virtually, including: a kick-off meeting, meetings with each IP, with the stakeholders and private sector groups, with other teams of the British Embassy in Bogota and with former Director of the Programme.
After collecting all the information provided by the stakeholders and reviewing key documents, the review team wrote up the findings and produced a draft annual review document with recommendations, using the standard annual review template provided by JFU. The document was sent as a draft to London and especially to the Economics Unit to complete Quality Assurance of the Value for Money section.

ANNEX A: ACTION TAKEN ON 2019 ANNUAL REVIEW RECOMMENDATIONS
Recommendation 2019	Action Taken
Working closely with a Climate and Environment Adviser, the Colombia PF Programme should prioritise and implement the 11 Colombia PF Climate and Environment Audit Report recommendations. / In progress	The PT Agriculture Adviser is currently leading on Climate and Environment, after former Deputy Head moved to be the Head of ECS. / The PT made progress in most of the 11 recommendations, especially in those related to reviewing ToCs and logframes to identify opportunities to incorporate climate and environment. This revision took place with the support of a climate and environment expert during the visit the PT had from the EL and MR Teams in March 2020. / There is also further progress made in collaboration with the ECS Team and Pengwerner Associates, through JFU. The PF Team sent initial ToR to Pengwerner Associates from a sample infrastructure (rail) project. Currently, ToRs for continuing support to the programme on climate and environment are been agreed between the PF Colombia and Pengwerner Associates, through JFU. / Regarding the need to develop a targeted risk management programme for the Aerocafe Airport project, we have advanced all the steps, and during the Portfolio Fund Meeting, the project was approved. Further action is on track for the next months, with support of our implementing partner (CAF) and the supplier for this project.
The PF Team should consider additional support to Findeter and CAF (perhaps through a short-term consultancy assignment) to develop proposal(s) for the Green Climate Fund (GCF). For example, a possible proposal could seek to aggregate several WASH projects from a range of secondary cities, building on those in Valledupar and Ibague. By aggregating relatively small urban resilience projects into a single proposal, the BE team would be well placed to unlock GCF concessional finance. / In progress	Findeter is still in the process of becoming compliant to operate as a project implementing agency of the Green Climate Fund. One of the pending requirements relates to gender equality. Since November 2019 we have offered support to Findeter on this specific issue as it relates to the PF’s core work and we considered that it could bring further benefits to advance gender equality in Colombia. As Findeter would be the main beneficiary of a consultancy to develop a Gender Equality Policy within the organisation, the PF agreed to provide 50% of the total value and Findeter to fund the remaining 50%. However, they notified the PF in September that they did not have available funds for this activity. / On the other hand, CAF already received funding from the GCF for undertaking a research on “environmental, social and gender impact studies and analyses for the Low Emission Agriculture and Resilient to Variability and Climate Change - Colombia".
Nature Based Solutions (NBS) is an area that the PF Team could explore with regard to both future funding proposals (for the Green Climate Fund) and with regards to the needs/requests of their city government clients. Two cities, Montería and Valledupar, are seeking to plant trees (a simple form of NBS) at 10-meter intervals along the future sidewalks of their entire new arterial road networks. NBS are important measures for reducing the impact of urban flooding, one of the key constraints facing many secondary cities in Colombia. / Action with ECS	Nature Based Solutions was selected as one of the campaigns in COP26, in which we are working with ECS to include Colombia as a priority country to lead this campaign. Achieving this policy goal will require a one HMG approach to work towards Colombia’s climate ambition. / Considering this, we will work in coordination with ECS to engage with the cities in which PF projects are operating to assess how we could contribute to the national campaign. In a meeting between the ECS Team and the PF Team, opportunities to continue working cooperatively were discussed and will be followed up, both on influencing Colombian government at national and local levels. / It is worth clarifying that, the project for Valledupar is a water and sanitation project, focused on the municipality’s rural areas and Montería is not a city prioritised by the PF.
As part of the preparations for COP 26 in 2020, HMG is engaging with the C40, a global city network dedicated to tackling climate change. Bogota and Medellin are already C40 members. The PF Team should explore whether the cities of Cartagena and Cali or others are willing to join the C40 and commit to developing Paris Agreement compatible climate action plans. Given the nature of the work that the PF Team is delivering this could be a relatively quick policy win. / Action with ECS	As ECS is leading on COP 26, the PT is coordinating all actions related to climate with them. We discussed the potential inclusion of some PF priority cities in the C40 Group. The C40 Group is one of the implementers for the ECS Team, so they have a strong relationship with them. / In this sense, anything that has to do with engaging at a local or national level with C40, is managed by ECS. To date, ECS has requested the PF only to identify opportunities to support them with communications related to COP 26 and C40. Any further actions will take place in close coordination with ECS.
The PF Team to investigate whether international companies are more efficient and effective at delivering high quality feasibility studies than local companies, by reviewing and evaluating the data collected from the first set of rail, urban development, regional competitiveness and agri-insurance projects. This information to be used to decide routes to market for future PF Colombia projects. / Actioned	Initial feedback from Findeter on the Manizales, Bog-Zipa and Santa SmartA projects indicates that they do not perceive significant difference on the quality of feasibility studies delivered by PF suppliers and that of usual Findeter suppliers. However, they have found them, on average, more expensive. / They do recognise that contrary to what they are used to, our projects incorporate ambitious G&I requirements that will derive in solutions which are not only technically feasible but that also ensure the key social impacts. / Further inputs from CAF and FDN will be required when the projects they are leading are further advanced.
The PF Team to work with implementing partners (IPs) to complete the remaining baselines, milestones and targets in the Programme-level logframe before the next Annual Review in November 2020. / Actioned	The PT reviewed and updated the seven activity level logframes after the ToC revision workshop that took place in March 2020. The final versions were approved after receiving feedback from the EL and MR Teams in August 2020. Six out of the seven logframes were updated into Prospero in September 2020. ANI’s logframe took longer as PT required confirmation of sources by IPs, suppliers and the ANI itself, and has been already approved. The PT also reviewed and updated the Umbrella log frame at the output levels. A review of intermediate outcomes, outcomes and impacts is expected to happen during the C2 evaluation (due in February 2021).
The PF Team, working with the JFU Economist, more systematically analyses cost-drivers across the seven projects to identify appropriate mitigating measures. / Not actioned	Former programme Director contacted the Economics and Analysis Directorate in London to advance on this recommendation on the 3rd July 2020. / The Team received a reply on the 7th July recommending not to act on this recommendation due to constraints linked to Covid-19. Instead, updating milestones in logframes, was pointed out to be sufficient.
When reporting Colombia PF Programme budget figures, the PF Team to use past financial year numbers combined with forecasts for the year in which the AR is taking place. / Actioned	Yes, we added a table with the information on expenditure including previous years.
The PF Team to monitor and control risks which could damage the Programme’s value for money (VfM) position. / Actioned	Every quarterly report we update our risk matrix, including those risks that can affect VfM. An example of monitoring and control of these risks are the systematic market studies carried out by our IPs. As there are similar projects, it is possible to spot excessive costs coming up.
Once the pilot phase of the Agri Tech innovations has been completed, the seven projects will need to rapidly prioritise scalability and sustainability to achieve primary and secondary benefit targets. The PF Team to look at crowd-in funding to provide Agri Tech projects with longer term sustainability if necessary. The Global Innovation Fund, for example, supports successful tech projects which are scalable. / In progress	The Agriculture Advisor undertook a review of the sustainability action plan per project on September 2020. After doing this, guidance and recommendations were given to each project (according to their current situation). With this review, the PF also identified opportunities to support the search for further funding. / In some cases, when projects have reached their last commercial scale, the PF have provided support and advice about other funding opportunities. An example of this is DIT, Procolombia (Colombia Investment Roadshow). / Due to Covid 19 restrictions, most projects were extended for 3 to 6 months, to enable finishing the activities proposed at this stage. / The Global Innovation Fund has been identified as a possibility, among others, such as Alpha Mundi (impact investment), Fedecacao, Federación Nacional de Cafeteros, etc.
For agri-insurance activity, CAF to ensure that it is ready to measure i) number of producers trained; and ii) number of training sessions provided that include G&I modules, starting in 2020/21. / Actioned	In all the contracts with suppliers, we included this deliverable as mandatory. In addition to this, CAF has hired a gender and inclusion consultant for all the PF projects, that must develop G&I workshops. This was also established in the logframe for the agri-insurance activity.
There is strong demand from newly elected mayors and governors for support with preparing the G&I chapters in their development plans and, possibly going beyond that, to support the implementation of their G&I policies and programmes. Working with IPs, the PF Team will need to establish an open and transparent process for selecting and supporting a small number of additional municipalities and departments, beyond those already included in the Programme. / Actioned	At the Santa Marta Conference we offered 168 Mayors and Governors technical training on G&I. / To cover the demand from newly elected mayors and governors, the PF provided a series of workshops on gender equality and social inclusion, through 9 training sessions in 7 municipalities and 7 departments, reaching both public servants from the Municipal and Department levels (Cali, Manizales, Villavicencio, Bucaramanga, Santa Marta, Cartagena). The G&I expert who was commissioned for this activity also provided technical inputs and feedback to public officials from Risaralda, Armenia, Cali, and Cundinamarca, on their draft development plans or on specific questions. / After this initial session, we have contacted participant municipalities and departments to assess current demand for further support. But due to Covid 19, the attention of decision makers has focused on responding to the emergency, and only two municipalities replied that were currently interested in receiving further technical support.
OCP to plan and deliver separate G&I sessions during its technical training courses on the International Open Procurement Standards in the departments. / Actioned	OCP worked closely with the Governance Adviser and the Social Development Adviser, to prepare the contents of G&I modules for the Open Procurement Standards in the departments. They have presented a structure of the training session on G&I and they started to implement sessions in two departments. / In addition to the above, we have identified actions in process on G&I undertaken by CCE and UN Women in Colombia, and are exploring ways to both, point those out in the training modules and explore further cooperation possibilities.
When SECOP II is ready for rollout to the departments, the PF Team should work with OCP and CCE to ensure the 8 PF departments are prioritised. Prepare lessons learned from the first pilots to ensure second set of departments benefit from those. / Actioned	The CCE support project includes the 9 prioritised departments, making this and OCP’s projects coincide. / The lessons learned during the first phase of OCP project have been discussed and incorporated for the second phase. This is reflected in the quarterly reports.
The PF Team should continue to support Colombia’s membership of the Construction Sector Transparency Initiative (CoST) and offer to support the CoST application to PF projects such as AeroCafe and the two railway lines. / Actioned	To begin with, the PF sponsored a scoping study on Colombia’s public procurement and a workshop. We have facilitated a conversation between CoST and the Secretary of Transparency from Presidency. The PF sent a letter of support to CoST initiative, acknowledging Colombia’s intention to join them and that we recognised an alignment with the principles of CoST initiative. / The Secretary of Transparency sent an application letter to require CoST membership. Currently, a Programme Implementation Plan, advanced by the Secretary of Transparency, is pending. Internal changes in the Secretary have delayed the submission of the plan, but CoST is in constant contact with them in order to advance.
The PF Team should ensure that lesson learning from the PF Centre for Global Disaster Protection Programme, specifically on its insurance work, is incorporated into the Colombia agri-Insurance activity. / In progress	The Agriculture Adviser contacted the PF Centre for Global Disaster Protection Programme to obtain Annual Review monthly and quarterly for the Global disaster protection programme and organise a call about lesson learnt. / A meeting took place on the last week of August, with an initial agreement to receive support from the specialists that work in agri-Insurance, in reviewing ToRs for the pilots and the review of proposals. Currently the agri-insurance pilots will be implemented by a different IP.
In addition to the regular activity budgets, the PF Team will need to ensure that non-ODA resources are targeted as appropriate to supporting the formation of UK-Colombia partnerships as per the secondary indicator in Output 2. / Actioned	Non-ODA resources have been used in the past to organise networking events, including SMEs that have a great impact on: i) business development mainly with Colombian businesses; ii) generating opportunities to create consortia with PF Commercial Framework companies; and iii) communication about the status of PF projects and tender processes related to our 3 strands. / Non-ODA funding was finally allocated for Colombia in July 2020. Most of the activities planned for spending these resources are targeted as appropriate to supporting the formation of UK-Colombia partnerships and some of the efforts are already showing early results.
Five of the seven Colombia PF Programme activities will need to have adequate resources and approaches in place to measure the benefits of UK-led innovations. / Actioned	ToRs have been modified so companies include “innovation opportunities” and define how they can integrate these innovations into project design. Innovation will be evaluated and awarded a score of between 10 and 20 points (CAF and Findeter Processes). / In terms of longer-term benefits, the indicators to report on innovation were updated on the Umbrella Logframe to better reflect PF activities at the Output level. A review of upper-level indicators will be undertaken after this annual review and will also bring inputs from the C2 Evaluation that will undertake an initial contribution analysis (and did not happened as planned between June and October 2020).
About three months prior to the next Annual Review in November 2020, it would be prudent to review and update the cost benefit analysis calculations and VfM for each Colombia PF Programme activity given the number of anticipated beneficiaries looks like it will change from the original figure of 3 million recorded in the Business Case. This information should be shared with JFU and the FCO Economics Unit. / Not actioned	Former programme Director contacted the Economics and Analysis Directorate in London to advance on this recommendation on the 3rd July 2020. / The Team received a reply on the 7th July recommending not to act on this recommendation due to constraints linked to Covid-19. Instead, updating milestones in logframes, was pointed out to be sufficient.
The PF Team should work with the implementing partners (Findeter and CAF) to map out and agree on realistic assumptions for the rail and urban projects regarding the: length of time required for each phase in the project cycle; and costs for each phase of the project cycle, particularly those with higher budgets. This could be aided by having a common visual schematic of the project cycle and building it into the risk register for the programme. Having a shared understanding of the project cycle is crucial for the PF Team to achieve the relevant logframe target under output 4 – “number of urban, rail and regional competitiveness projects designed, structured and ready for investment”. / Actioned	A better understanding of the project cycle and its stages has been achieved with Findeter and FDN. We have work plans and schedules in place. This has allowed us to have a better monitoring of the projects. Overall, there is more accurate planning to have more realistic targets regarding output number 4. / With CAF we have achieved a better understanding of the project cycle, as well as the mechanism to react on budget considerations. However, compliance with scheduled times remains a challenge with them. / Given constant delays, in November 2019 the PF Team requested from CAF a Performance Improvement Plan. Unfortunately, CAF did not meet its targets by March 2020, and the PF decided to go ahead only with the most advanced projects, and not to pursue any further projects with CAF. As a result, the PF asked FDN to be our implementing partner for the remaining regional development projects (taking out these from CAF’s portfolio).
The Manizales Intelligent Transport project will be identifying data on journey times, incomes, job locations, etc. and the contractor should use this information to spot priority areas for improved reliability which can be the determinant of public transport use that cost or speed. / Actioned	Data on journey times, incomes, job locations was collected by the contractor UT Deloitte-Transconsult-Duran & Osorio. All the information collected for the demand studies was considered for the technical and financial components. There is a product that has all the information on diagnostics for this project. / This analysis will soon be updated with the integration of other transport modes that the city’s new administration requires. These new activities are going to be partly funded by the city.
The PF Team should explore how they can work with UK organisations (Arup, Argent, TfL, etc.) to develop a transit-oriented development (TOD) approach that is bespoke to Bogota, drawing on case studies from other cities, the World Bank’s 3V methodology and CAF’s expertise. Codifying that TOD approach could be a task supported by the Global Infrastructure Programme team who may be able to subsequently roll it out as a HMG methodology. / No longer relevant	On the advice of UK Rail Expert, Marcus Mayers, the PF Policy Advisor contacted Transport for Greater Manchester, potentially in relation to a COVID-related transport policy proposal from Pro-Bogota. Further discussion with TFGM pending confirmation of availability of Policy Connections budget. / On another front, the Regiotram Norte project, requirements to include a TOD approach in the designs are part of the contract. This project benefits Bogota, as almost 50 per cent of its trajectory is within the capital city. In addition, in the Valle Intercity Rail Project, we will aim to incorporate TOD approaches in the feasibility studies.
The PF Team should seek to engage Transport for London’s Commercial team to determine whether there is scope to engage them as a strategic adviser for the rail and urban mobility projects. TfL may be well placed to provide advisory support to the City of Bogota, building an institutional partnership that would demonstrate the impact of UK expertise on integrated transport planning for a major city in the Global South. / No longer relevant	The PF Team contacted Transport for London, through DIT Team, as they had a relationship with them. / An email contacting Rebecca Venn, was sent in early August asking for support in contacting someone in TfL for our request on ‘special advisory in some transport infrastructure questions’. We also requested to arrange a call that week, but until today we have not received a reply. / Although Bogota City was not initially prioritised by the PF, they are now participating in the Regiotram Norte project. Before continuing with possible communications with TfL, we will wait to have more clarity on our financial reality for the 2020 and the unsolved prepayments issue.
Findeter should provide evidence of impact with regard to ‘control centres’ that they have implemented in other secondary cities. The draft ToR sets out the need for an integrated control and operations centre (CICO) in Santa Marta but the scope and objectives of the CICO is unclear. The purpose and objectives of the CICO should focus on the tools and technology that will be used for one specific sector (e.g. mobility management), possibly two at most. In parallel, the BE team should encourage Findeter to explore global initiatives that are seeking to use data/technology to improve urban planning including the World Bank’s Municipal Spatial Data Infrastructure, which has been applied in Bogota and Cali and the Bank’s City Planning Labs initiative. / Actioned	Findeter advanced the procurement process for a consultancy (UT EY-IDOM) that will provide evidence on specific needs of Santa Marta to advance and define the scope and objectives of the CICO in the city. The consultancy also included benchmarking activities from international and national good practices.
The PF Team should consider developing a proposal for funding to the Global Challenges Research Fund (GCRF), possibly in collaboration with UCL and New York University. The proposal could build on global research initiatives and tools that are relevant to the aims of the programme, specifically the Urban KNOW[1] and NYU’s Urban Expansion Initiative[2]. / No longer relevant	The Delivery Officer of the PF advanced a search to understand better the opportunities offered by each one of the funds and research centres. It was identified that the Urban Expansion Initiative is already working with some cities in Colombia, including Santa Marta and Valledupar, which are also prioritised by the PF. / Now, due to additional pressures related to Covid-19 and administrative delays, we have decided not to advance further actions regarding this recommendation and focus our efforts in advancing current projects.