Mexico Prosperity Fund Cycle 1 Evaluation Report

Prosperity Fund Evaluation and Learning

August 2019

Table of Contents

List of Annexes

List of Tables

Table of Acronyms
Abbreviation
ACROL	Anti-corruption and Rule of Law
AMLO	Andrés Manuel López Obrador, President of Mexico
APF	Agile Programming Fund
API	Application Programming Interface
BC	Business Case
CDU	Central Delivery Unit
CNBV	Comisión Nacional Bancaria y Valores (National Bank & Securities Commission)
CONEVAL	Comisión Nacional de la Evaluación de la Política de Desarrollo Social (National Commission for the Evaluation of Social Development Policy)
DFID	Department for International Development
DIT	Department for International Trade
E&L	Evaluation & Learning
EQ	Evaluation Question
FCO	Foreign and Commonwealth Office
FDI	Foreign Direct Investment
FIC	Fintech Innovation Centres
FRG	Family Reference Group
GEA	Gender Equality Act
G&I	Gender & Inclusion
IBS	Industrial Baseline Study
ICF	International Climate Fund
IIOC	The FCO’s Infrastructure, Investment and Operations Committee
JFU	Joint Funds Unit
KII	Key Informant Interviews
KPI	Key Performance Indicator
M&R	Monitoring & Reporting
MREL	Monitoring, Reporting, Evaluation & Learning
MSME	Micro-, Small and Medium-Enterprise
NDP	National Development Plan (of the Mexican government)
OBC	Outline Business Case
ODA	Official Development Assistance
ODI	Overseas Direct Investment
PEL	Programme Evaluation Lead
PF	Prosperity Fund
PFDU	Prosperity Fund Delivery Unit
PM	Programme Manager
PMC	Programme Management Committee
PT	Programme Team
PwC	PricewaterhouseCoopers
SB	Secondary Benefit
SDG	Sustainable Development Goals
SGB	Strand Governance Board
SoR	Statement(s) of Requirement
SRO	Senior Responsible Owner
TAC	Transparency & Anti-Corruption (family)
ToC	Theory of Change
UK	United Kingdom
VCC	Voice, Choice and Control
VfM	Value for Money
VT	Virtual Team
WRI	World Resources Institute
WOW	Work and Opportunities for Women

Version History
D16_02	Mexico Programme Cycle 1 Evaluation Report
		Revision
Revision	Written By	Checked By	Approved By
Revision 0	xxxxxxx, xxxxxxxxx, xxxxxxxxx, xxxxxx	xxxxxxx,xxxxxxx. Xxxxxxxxxxxxxxxxx xxxxxxxxxx, xxxxxxxx
Revision 1	xxxxxxx, xxxxxxxxx	xxxxxxxxxxx; xxxxxxxxxxxxxxxxxxx
Revision 2	xxxxxxx, xxxxxxxxx	xxxxxxxx
Revision 3	xxxxxxxx

# Executive Summary
## Overview
This Cycle 1 evaluation report for the Mexico programme covers the period from June 2017 (submission of the Outline Business Case – OBC) through May 2019 - the mid-point in the inception phase. The evaluation will be implemented in annual cycles through to 2021, to provide an iterative process of insight, learning and adaptation. The objectives for Cycle 1 are to:
1. Ensure the design and positioning of each strand and the programme as a whole are strong and align with overall Fund objectives.
2. Provide findings and insights to the programme team (PT) at mid-point in the Inception Phase, to enable adaptations necessary to achieve outcomes and goals.
3. Support the preparation of the programme’s first Annual Review.
4. Provide findings and insights on family and thematic issues, to inform the Joint Funds Unit and other Fund-wide stakeholders.
5. Support adaptive programme management within PF Mexico and share lessons with other programme teams via the PF Learning website.
The Mexico Programme comprises four strands: Energy, Financial Services, Future Cities and Anti-Corruption and the Rule of Law (ACROL). The programme builds on previous Embassy initiatives which informed the 2017 OBC and provided real-world examples of programme potential.
In the inception phase, all four strands are revising their respective theories of change and developing implementation plans. This is to assure the logic within each design, strengthen alignment with the overall programme theory of change and consolidate the programme’s positioning with respect to the government which took office in December 2018.
The PT has actively participated in the evaluation, through the evaluation scoping and planning process, contributing key informant interviews in the fieldwork stage, and commenting on the draft report. All conclusions are those of the evaluators. The timing of this evaluation was established in agreement with the PT to have evaluation findings that can inform strand programme managers as the end of inception approaches, and as the PT prepares its annual review.
## Key findings
There is good evidence that the iterative approach adopted by the PT between issuing SoRs for strand contracts and the Inception Phase has produced strand designs with stronger theories of change (ToCs).
There is clear evidence that the current design and positioning of all of the strands create plausible causal pathways from intervention up to impact level, and that these have the potential to achieve the Mexico programme’s objective: improved conditions for growth in Mexico, through increased capacity and an improved environment for trade and economic growth. While the strand designs are largely now in place, it is important that strand implementers select appropriate indicators for measuring progress, to consolidate the causal pathways. Indicators will be finalised in August for Financial Services, Future Cities and ACROL, and in October for Energy.
While there is good reason to expect the programme will contribute to greater inclusive growth and reduced levels of poverty, it is important to avoid challenging outcomes by including robust risk mitigation measures and appropriate indicators in implementation plans.
The PT has made significant effort to ensure gender considerations are mainstreamed, and the programme scores ‘good’ on all five dimensions of E&L’s Gender & Inclusion scorecard. While the ways in which Energy and Financial Services will promote inclusive growth are clear, there is scope to clarify and strengthen this for the Future Cities and ACROL strands. The implied inclusion of marginalised populations in these strands should be more clearly identified and articulated in final designs and indicators.
Evaluators recommended the programme adopts Mexico’s official multidimensional definition of poverty (programme documents make reference both to this and to the World Bank’s separate definition). This will help the PT and suppliers identify and articulate various elements of inclusion in the final versions of ToCs and logframes. This metric will also better capture the nuances between ‘inclusive economic growth’ and ‘poverty reduction’ and align with the definition used by federal and state-level actors.
Programme design, procurement, management and governance arrangements provide good reason to believe that over time the programme will represent value for money (VfM). Overall, the programme scores 3.9 on E&L’s VfM Scorecard, where 3 represents ‘adequate’ evidence and 4 ‘good’ evidence that VfM is likely to be achieved. Addressing the issues mentioned above would increase this score.
The PT has put substantial effort into identifying and planning for secondary benefits. As a result, there are very good resources for achieving these, including DIT staff time and resources available within the supplier networks for each strand. Plans for achieving SBs could be further refined by considering when specific opportunities may arise during the full course of the implementation phase and defining the resources and activities to be brought into play to realise these.
## Issues of interest to JFU, PFDU and other PF programmes
A number of programme management arrangements stand out as examples of good practice. The Embassy’s Virtual Teams (VTs) bring commercial, programme and policy staff together in a single team and should be of interest to other posts delivering PF programmes. These VTs are an effective mechanism for ensuring strategic direction and coordinated work and have helped each strand adapt to changing political economy contexts, as well as helping the programme serve broader UK interests in Mexico.
There is evidence that the PF programme is well structured to ensure regular review and discussion of PF and strand policy, stakeholder engagement, and emerging challenges. Fourteen separate cross-cutting themes have been identified and allocated to PT members. There is strong evidence that this has helped to improve the design of the strands and promoted ongoing peer learning within the PT.
The programme’s use of Agile Programme Funds (APF) is an innovative element of the Mexico programme design. APF allocations within supplier budgets aim to fund innovative or complementary work outside or in addition to the core strand interventions. While this evaluation cycle comes too soon to assess the value of the APF, future cycles will assess this programme feature.
The Mexico programme is one of the first movers among PF bilateral programmes and has tested processes at an early point in PF’s formation. As a result, it has encountered challenges and sought guidance earlier than many of its programme peers. In some cases, the absence of guidance has meant the PT created requirements or documents based on existing UK experience and then secured JFU/PFDU approval prior to their use. The PF has the potential to draw on these resources to support other programmes as they enter the same phases. This would also mitigate the risk of having too many variations emerging across the PF.
The PT has identified a number of areas where it would like guidance and training support from the JFU as the programme moves through inception and into implementation. These include further training on contract management; monitoring financial reporting; Annual Review support; and in relation to the technical specificities relevant to each strand, for example Payment by Results measures. Guidance on how to administer change control at the strand level is sought, as the Schedule 11 form is challenging and oriented to changes at the programme level.
Other considerations for JFU include:
- Clarifying future Statements of Requirements (SoRs) on what can be included in inception phase spending. Strand suppliers noted that greater investment during inception would promote better delivery during the implementation phase.
- Ensuring contract documentation is compliant with the Gender Equality Act by replacing references to Man Hours and Man Days with gender-neutral terms such as Personnel Hours/Days or Worker Hours/Days etc.
- Considering the Mexico PT’s request for job shadowing and other development opportunities for programme teams, in order to promote cross-Fund peer learning. This could help ensure that management of programmes is coherent globally, which may be especially important when strands/projects in different parts of the world are working with the same suppliers. PF Learning offers some space for this, but it may be helpful to further explore the shadowing opportunities.

# Introduction
## Report structure
The findings for the design and positioning of the strands and programme of this report are presented to enhance readability and utility, rather than presenting each evaluation question (EQ) in numerical order. Each of the 12 Prosperity Fund (PF) EQs has been incorporated into this evaluation. At the beginning of each section in this report and in the strand annexes, the relevant EQs are signposted to help orient the reader. A mapping of the EQs to the respective report sections is found in Annex 2.
The evaluation of the Mexico Prosperity Programme forms the main body of this report. Individual strand evaluations follow the same structure as the programme evaluation and are found in the following annexes:
- Energy – Annex 3
- Financial Services – Annex 4
- Future Cities –Annex 5
- Anti-Corruption and Rule of Law (ACROL) – Annex 6
The other annexes provide more detailed analysis for the three thematic areas covered in Cycle 1 of the Mexico Programme:[1] Gender and Inclusion (G&I), Value for Money (VfM) and Secondary Benefits (SBs). The annexes are concluded with a summary of prior PF programming, a checklist of Theory of Change (ToC) criteria, a bibliography of evidence sources, the work plan for Cycle 1 with a tentative timeline for Cycle 2, and biographies of the evaluation team.
[1] The Anti-Corruption theme was not finalised when the Mexico Approach Paper was accepted.
## Purpose, scope and objective of the Cycle 1 evaluation
This first cycle evaluation report for the Mexico Prosperity Programme covers the period from June 2017 through May 2019, which corresponds to the approval of Mexico’s Outline Business Case (OBC) to the current inception phase of the programme’s four strands. As noted in the Mexico Programme Cycle 1 Approach Paper (see Annex 1), the objectives of this Cycle 1 evaluation are to:
1. Ensure that the design and positioning of each strand and the overall country programme are strong, drives interventions toward the stated outcomes and goals (as defined by the PT), and aligns with the overall Fund objectives.
2. Provide findings and insights to the PT at the mid-point of the inception period so that the PT and suppliers have the opportunity to make any necessary adaptations to better achieve outcomes and goals (as defined by the PT) and to support the Fund's primary and secondary benefits.
3. Support the PT as it prepares to draft the first Annual Review of the PF Mexico Programme.
4. Provide timely findings and insights to the Family Leads and Thematic Leads so that aggregated evaluations and findings can inform the Joint Funds Unit (JFU), the Prosperity Fund Delivery Unit (PFDU) and other Fund-wide stakeholders.
5. Offer learning insights to support adaptive programme management within PF Mexico and share with other programme teams via the PFLearning website.
The Prosperity Fund Theory of Change (ToC) primarily defines economic parameters of inclusive growth which set the preconditions for poverty reduction. The Mexico Programme and its four strands have aligned their designs to the existing Fund ToC, particularly to its intermediate outcomes. The Mexico Programme supports the statement "The Prosperity Fund aims to remove barriers to economic growth and promote the economic reform and development needed to reduce poverty in partner countries.[2]"
[2] https://www.gov.uk/government/publications/cross-government-prosperity-fund-programme
## Audience and stakeholders
The timing for this evaluation was established by consensus with the Mexico Programme Team (PT) and Evaluation and Learning (E&L) during a January 2019 evaluation planning workshop, described in the Mexico Cycle 1 Approach Paper (Annex 1 on Page 48). The primary audience for this evaluation is the PT as it seeks to secure E&L’s early insights and findings on the design and positioning of the programme by the mid-point of the inception phase. This timing allows the PT to make any necessary course correction and supports the PT as it begins its first annual review process.
Other stakeholders for this analysis include the Department of International Trade (DIT) and other Foreign and Commonwealth Office (FCO) teams at post in Mexico City, who can use this evaluation to complement their analysis and programme positioning in country. Within PF, the family and theme leads may utilise the evaluation to inform their aggregated analysis upwards. Other PF teams with peer strand projects may also benefit from this evaluation as each pursues its pathway from design to inception. The JFU and PFDU may take away insights from a front-leading programme which is facing challenges and learning lessons earlier than most other PF programmes.
As the primary audience, the PT has been included in the evaluation process in two ways since its engagement in the planning of the evaluation detailed in the Mexico Programme Cycle 1 Approach Paper. The first was in the key informant interviews (KIIs) undertaken with the strand programme managers and their officers at FCO. Each interview lasted three hours and included time for questions from the PT for the evaluators. Interviews with Her Majesty’s Ambassador and Senior Responsible Officer, the Policy and Prosperity Counsellor and the Head of the Prosperity Fund in Mexico ran between one and two hours, again, with time for the interviewees to ask questions and highlight areas of focus.
The Head of the Prosperity Fund in Mexico, and the SRO reviewed the Evaluation and are happy with the document as it describes in a clear and helpful way the findings of the evaluation of our programme in the first cycle. The findings are relevant and timely. We have provided comments and suggested changes, which have been taken on board.
 Head of PF in Mexico

The second way in which the PT has been engaged in this evaluation process is in reviewing the draft evaluation report to make comments and edits. At the request of the programme manager, the evaluators doubled the original amount of time in the production schedule from one week to two weeks to accommodate that extended review and comment period.
## Methodology
The evaluation methodology noted in the Approach Paper (Annex 1) builds on the approach and methodology outlined in the E&L Inception Report[3]. In this first cycle, the evaluation seeks to establish a contextual baseline using a realist approach. The methodology used for this Cycle 1 evaluation was discussed and agreed to with the PT during the evaluation planning workshop held in January 2019 to launch the cycle.
[3] Available on PFLearning here: https://www.pflearning.co.uk/x/K4a8
By exploring the design and positioning of the Mexico programme’s individual strands, the evaluation is intended to support the team in understanding how and why interventions may and may not work. This, in turn, will support the PT to make informed decisions about which strand elements to use and how to adapt them to the evolving programme environment. This approach allows a careful examination of which change mechanisms come into effect in a given context, leading to a range of outcomes. This approach is also well-suited to lesson learning and, for the Mexico programme in its inception phase, adaptive management as the strands consolidate designs and foundational strategies prior to moving into actual implementation.
In subsequent evaluation cycles where implementation begins to yield results, evaluations will use contribution analysis as the main evaluation methodology to assess the extent to which the programme is responsible for observed results.
## Data collection and sampling
In January 2019, the PT opted for a landscape evaluation of its emerging programme and strand designs as a way of baselining the bilateral programme[4]. Therefore, the four strands are weighted equally in this Cycle 1 evaluation. The evaluation incorporates the 12 PF Fund EQs and sub-questions, as well as interrogates elements from the G&I scorecard, the VfM scorecard and the SB assessment.
[4] Mexico has three global programmes – Health, Skills and Trade – which are run from London.
The data for this evaluation has been sourced from PF documents, secondary sources, KIIs with Embassy, PF and suppliers, and MREL workshops with PT and strand suppliers[5]. The interview guides used for the KIIs were discussed among the E&L team, including input from relevant family and theme leads, prior to their use to ensure alignment into those future analyses.
[5] A joint MREL visit to Mexico City 1-4 April 2019 provided timely information to the changing ToCs and logframes of all the strands and the overall bilateral programme itself.
The Financial Services strand will be sampled into the global Financial Services family synthesis. Additionally, these findings and evidence will be used to inform the analysis of the other three PF families associated with the Mexico Programme, including (i) Energy and Low Carbon, (ii) Infrastructure and (iii) Transparency and Anti-Corruption.
## Limitations
The point at which this first evaluation of the Mexico Prosperity Programme is conducted creates challenges. The programme and its strands are in the earliest months of inception. The programme level ToC and the strands’ ToCs and logframes, G&I strategies, climate resilience strategies, regional and municipal strategies, and costed work plans are months away from finalisation which means that what is available for analysis is likely to change to some degree[6].
[6] Financial Services, Future Cities and ACROL have a six-month inception period from March to August; Energy has a nine-month inception period March to November.
While intermediate outcomes and impacts have largely been identified, outputs, indicators and baselines have yet to be finalised.
## Risks
In the Cycle 1 Approach Paper, E&L identified risks (Table 1, below) associated with the Mexico Programme’s implementation. All risks are operational in nature and should be read together with the limitations set out above. The table reflects the risk mitigation efforts of E&L and the PT during Cycle 1.
Table 1: Risks and risk mitigation for Cycle 1
Risk	Likelihood (1–5)	Impact (1–5)	Risk score	Cycle 1 Mitigation Status	After mitigation
					Likelihood (1–5)	Impact (1–5)	Risk Score
Operational risks to Cycle 1 evaluation
Lack of engagement among the PT and/or stakeholders with the E&L team affects the capacity of the E&L team to obtain, develop or validate evaluation findings.	2	4	8	The E&L team and the PT have built a functional relationship. Appropriate access to suppliers has been granted during Cycle 1.	1	3	3
Timing of the availability of relevant data affects the E&L team’s ability to obtain, develop or validate evaluatation findings.	2	4	8	Available materials were provided up to 17 May.	1	4	4
PT does not upload monitoring data onto Prospero in timely manner.	2	3	6	No issues to date.	1	2	2
Turnover in PT staff leads to loss of institutional knowledge.	3	3	9	Staffing has remained consistent during the evaluation period.	1	3	3
Non-compliance by the contractors generates deficiencies in the quality and / or terms of the deliverables within the strands’ designs and metrics.	3	4	12	This scenario has not materialised to date.	1	3	3
E&L team does not have sufficient expertise to undertake high-quality evaluations.	2	4	8	Short-term technical assistance recruited and technical evaluation expertise of Financial Services and Future Cities for Cycle 1 strengthened.	1	2	2
Illustrative strand-level risks to Cycle 1 evaluation

# Context
## Timeline of Prosperity Fund in Mexico
This section provides succinct information which present in brief the context of the Mexico programme rather than responds to specific EQs. This contextual information includes a chronology of PF-branded programme events (see Table 2 below); a summary of early PF and transition activities that preceded the current multiyear PF programme which is the focus of this evaluation; and a presentation of the current strand summaries.
Table 2: Chronology of PF programme
Document / Activity	Timing	Function
Dual Year of UK and Mexico	2015	Coordinated binational celebration at the highest levels of government to celebrate the arts, culture, innovation and business of the UK and Mexico.
Prosperity Fund programmes in Energy, Financial Services, Future Cities and ACROL	2017-2018	Small-scale programmes which introduced UK PF to Mexican national and state-level stakeholders, creating primary and secondary benefits and building a platform to design multiyear PF programme.
Outline Business Case approved	Mar 2018	Presented the strategic, appraisal, commercial, financial and management case for a multiyear PF programme in Mexico for 2018-2021
Transition projects launched	Apr 2018	Defined details of the multiyear programme; Supported election engagement; Maintained PF momentum
Statements of Requirement to market	Aug 2018	Procurement for four strands of multiyear PF programming (Energy, Financial Services, Future Cities, and ACROL)
Bid selection review	Dec 2018	Selection teams reviewed bids against SoR criteria and provided recommendations to London for final approval.
Final Business Case approved	Dec 2018	Updated the strategic, appraisal and management case for a multiyear Mexico PF programme, including new timelines.
Supplier Contracts signed	Feb 2019	Contracts signed with all four selected suppliers between 6 and 18 February 2019.
Transition projects concluded	Mar 2019	Final report submitted April 2019 with “A” rating of transition objectives.
Inception Phase begun	Mar 2019	All four strands began their inception phases
Transition to Implementation	Aug 2019	Financial Services, Future Cities and ACROL
	Oct 2019	Energy
Implementation Phase begins	Sep 2019	Financial Services, Future Cities and ACROL
	Nov 2019	Energy

## Summary of previous PF initiatives/transition
The current Prosperity Fund programming emerges from several years of programme engagement. During FY/2016-2017 and FY 2017-2018, PF interventions enabled the strands to cultivate networks and relationships as well as generate underlying analyses which have informed the design of the current multiyear PF programme. In addition, transition funding in FY 2017-2018 enabled the strand teams to engage all political forces ahead of the June 2018 elections and further inform the design and positioning of the current multiyear PF programme.

## Strand Summaries
The strand summaries have remained unchanged since they were presented in the SoRs in August 2018. Strand programme managers note that there may yet be changes made to this narrative once the inception phase milestones have been submitted and approved in the coming months and as the programme crafts a comprehensive, strategic communications effort which is synchronised with broader UK Embassy messaging.
Energy. The Energy Strand focuses on three main interventions: (i) developing a local male and female workforce that has the necessary skills and/or international certifications to fulfil industry demand; (ii) building the capacity of female- and male-owned Mexican small and medium-sized enterprises (SMEs) to support increased supply chain integration; and (iii) capacity-building for energy regulators and male and female officials to promote best practice in the implementation and enforcement of regulation. These interventions are designed to contribute to the promotion of inclusive economic growth and social development through more productive and resilient men and women, businesses and government officials who are best placed to lead Mexico’s transition to a low-carbon economy. Cleaner and more affordable energy, as a result of a successful transition to a low-carbon economy, will positively impact on the quality of life for low-income families through increased use of labour-saving, energy-intensive technologies and higher disposable income.
Financial Services (FS). The problem of financial exclusion is expected to be integrally addressed through three main interventions: (i) financial education to create a more confident and informed user-base of FS; (ii) policies that lead to improvements in the regulatory framework and (iii) support for Fintech companies that offer innovative solutions for micro, small and medium-sized enterprises and male and female users. Through this strategy, we expect to have a more inclusive and competitive FS in Mexico that contributes to poverty reduction and positively affects inclusive economic growth.
Future Cities (FC). The FC strand seeks to address the challenges of mobility in Mexican cities through two main interventions: (i) improving connectivity within cities through better governance and planning mechanisms for urban mobility services and; (ii) implementation of pilots to test solutions within a wider integrated transport strategy to deliver inclusive, safer, resilient and sustainable urban mobility services in target cities. The strand exists for women and men in Mexico who can benefit from more accessible urban mobility services, enhancing productivity, improving personal well-being and increasing the levels of social inclusion, including gender equality.
Anti-Corruption and Rule of Law (ACROL). The ACROL strand seeks to address the problem of corruption and unequal access to justice through three main interventions: (i) increasing the accountability of public service by streamlining and standardising processes for identifying and investigating serious crime and corruption; (ii) capacity-building for male and female officials working in the investigation and detection of serious crime and corruption to increase the quality of public service in ensuring justice and security for all and; (iii) improving the coordination between security, justice and anti-corruption institutions. Through this strategy, we aim to benefit the poorest and positively affect inclusive economic growth and development, leading to a more inclusive and competitive business environment.

# Programme design and positioning
This section responds to the following evaluation questions (EQs):
- EQ1. What evidence do you see to support the potential of the emerging Theories of Change (ToCs) to reduce poverty and support inclusive economic growth?
- EQ2. How has the programme managed political change to ensure alignment and relevance to position achievement of expected primary benefits?
- EQ5b. What factors may deter the achievement of primary benefits and what measures have the programme team (PT) taken to mitigate these?
- EQ7. Which assumptions and causal pathways outlined in the ToC remain valid, which have been adapted and what refinements have been made?
See Annex 2 for the mapped EQs within the evaluation report. Individual strand analyses are found in Annexes 3–6.
The programme’s four strands identified two types of key performance indicators (KPIs) in the Statements of Requirement (SoRs), the service and the strand. The strand indicators are unique to each strand and defined in the forthcoming logframes.
## Service key performance indicators
The six service KPIs are shared across the strands and have been put in place to ensure strong management and delivery of the interventions (See Table 4 below). There is strong evidence that these service indicators will be addressed, as they are incorporated into inception phase milestone documents and future regular reporting for the PT to monitor.
Table 4: Service key performance indicators and associated documents
#	Service KPI	# of Indicators	Relevant Document(s)
1	Quality and Delivery	5	Strand Governance Board; ToC and final logframe
2	Financial Management and Forecast	4	Costed work plan; Monthly financial reports
3	Personnel	6	Key Personnel and Resource Pool
4	Client Relationship Management	4	Stakeholder Engagement Strategy, Risk Registry
5	Continuous Improvement & Innovation	4	Monthly reports, Lessons logs
6	Corporate Social Responsibility	4	Gender and Inclusion (G&I) Strategy, Climate Resilience Strategy

Each of the service KPIs include specific definitions and measurable success criteria which will be assessed in future evaluation cycles as information becomes available. The service KPIs identify clearly when and how either the PT or the supplier must respond or take action if an indicator is at risk of falling short.
The clarity of these shared service KPIs and the fact that they are readily identified in milestone documents, management meeting minutes, or regular reporting all facilitate future monitoring and evaluation. The related documents for these service KPIs will be finalised in August 2019, with the Energy strand finalising its inception milestones in October 2019 as it was designed with a nine-month inception period rather than a six-month one, which the other three strands have.
## Strand key performance indicators
Since the first outline business case (OBC) was submitted in June 2017, the team has continuously adapted its designs and positioning to meet with changing realities. The evidence shows that the changes made to programme and strand designs were driven by three key factors: (i) a changing political environment; (ii) overly ambitious initial designs; and (iii) resourcing realities. The final business case (BC) approved by the FCO’s Infrastructure, Investment and Operations Committee (IIOC) in December 2018 is a portfolio of four distinct strands with cross-leveraging particularly around G&I.
In preparing the SoRs, the PT from each of the strands worked with consultants from Palladium to reconcile the wide designs in the OBC with the available resources and the political momentum of early 2018. The overall programme consolidated around a central theme of building capacity within the specific areas of need of the four strands. It was understood that there would be further refinements after the strand supplier selection, due in part to Mexico’s changing context.
There is evidence that some of the programme and strand redesigns were also prompted by the presence of other UK programmes in Mexico[7], most specifically the Newton Fund and the International Climate Fund (ICF), which have scopes that could incorporate some of the initiatives which the PF had shed. The Energy strand, in particular, refocused its design prior to going to market with the expectation that certain elements (e.g. climate-related activities) would be incorporated into ICF’s portfolio.
[7] KIIs held 23-24 April with PM and PT.
It is possible to evaluate the programme and strand ToCs at an initial level given the available documentation and the point at which each strand is in its design and planning. Using the ToC checklist (see Annex 11) against fourteen criteria, Table 5 below depicts the current level of strength within the strands and in the programme itself. These ratings are likely to change as the strands complete their final design during the inception phase and prepare to transition to the implementation phase. This is particularly true for the Future Cities strand where many of the details of the design will emerge once pilot cities are selected and their methods are known.
Table 5: Cycle 1 Theory of Change evaluation for the Mexico Programme and strands
ToC Checklist Criteria*	Programme	Energy	Financial Services	Future Cities	Anti-Corruption and Rule of Law
Context	Robust	Robust	Robust	Robust	Robust
Beneficiaries	Reasonable	Reasonable	Reasonable	Reasonable	Reasonable
Actors	Robust	Robust	Robust	Reasonable	Robust
Assumptions	Reasonable	Robust	Reasonable	Reasonable	Potential
Pathways	Reasonable	Robust	Reasonable	Reasonable	Reasonable
Coherence	Reasonable	Reasonable	Reasonable	Reasonable	Reasonable
Deliverability	Reasonable	Reasonable	Reasonable	Reasonable	Reasonable
G&I	Reasonable	Reasonable	Reasonable	Reasonable	Reasonable
Value for Money (VfM)	Reasonable	Reasonable	Reasonable	Reasonable	Reasonable
Secondary Benefits (SBs)	Reasonable	Robust	Reasonable	Potential	Reasonable
Sustainability	Reasonable	Robust	Reasonable	Potential	Potential
Additionality	Reasonable	Reasonable	Reasonable	Reasonable	Reasonable
Fund ToC	Reasonable	Reasonable	Reasonable	Reasonable	Potential
Fund linkage	Potential	Potential	Potential	Potential	Potential

*Weak – insufficient, superficial or uncritical; Potential – some coverage, but challenges in important areas or in critical thinking; Reasonable – fairly complete and critical thought in most areas, but some yet to be developed; Robust – clear, comprehensive, well-formulated, strong critical thinking
## Factors driving design refinements
The PT anticipated the need for design changes and built those expectations into the SoRs, inviting the bidders to offer ideas for innovation, impact and efficiency. The PT’s expectation for adaptations were primarily linked to the political changes in country following the Presidential election and the fact that the bids were prepared during the transition period from the 1 July elections to the 1 December inauguration.
## Factors positioning the strand to achieve
Managing the relationships across multiple levels of government in a period of historic change and managing the expectations that had been built up in the eighteen months between the OBC and the BC have been a significant challenge for the PT and the Embassy overall.
There is strong evidence that the iterative approach the PT took between the SoRs and the inception phase adaption of the strand designs achieved more relevant and stronger ToCs and created channels into the new government to secure long-term buy-in into the PF’s objectives in Mexico. The strand ToC adaptations are described in detail in the strand analyses annexed to this report.
For example, the Mexico Programme speaks directly to the challenges identified in the government’s six-year National Development Plan (NDP). In the NDP, the government identifies three themes as its priorities: justice and rule of law, well-being and economic development. It also identified three transversal axes: gender equality, non-discrimination and inclusion; fighting corruption and improving public management; and territory and sustainable development[8]. The coherence between the challenges identified in the NDP and strand activities is presented in Table 6 below.
[8] National Development Plan 2019-2024. 27 April 2019.
Table 6: Strand resonance to National Development Plan
Strand	NDP Challenge	Strand Activity
Energy	67% of youth between 15 and 29 work in the informal sector	Create youth apprenticeships in the energy sector to build high-quality job skills
Financial Services	A key point of inequality is a financial system that is shallow and concentrated	Create Fintech solutions that extend services to women and the marginalised
Future Cities	Gender-based violence creates profound threats to the daily lives of women	Design mobility solutions that support the safe use by women and the marginalised
ACROL	The illicit cost of accessing services totals 7 billion pesos annually	Reduce the flow of illicit use of public funds for personal enrichment

The NDP frames national priorities for the next six years which ensures that when the PF Mexico Programme moves into the implementation phase, it will have a national partner for the duration of planned engagement. The prospect of federal-level continuity strengthens the PF Mexico Programme’s ability to deliver achievements on primary benefits.
The PT have demonstrated that it will engage state and municipal partners and stakeholders to optimise the positioning of the strands. Final regional strategies are not yet in place to evaluate for this cycle, however, in PF documents (OBS, SoRs, bids and early inception planning), there is abundant evidence that each strand will have an evidence-based selection for state and/or municipal engagement in such a way that advances the delivery of the planned interventions. These strategies are specifically captured in several inception phase milestone documents which will be reviewed in the next evaluation cycle: The Gender & Inclusion Strategy, the Stakeholder and Community Engagement Strategy, and the Regional Strategy.
## Designing for inclusive growth
### Summary pathways
The design documents beginning with the OBC and continuing forward provide strong evidence that inclusive growth has been factored into the Mexico Programme and its four strands (see Table 7 below).
Table 7: Mexico strands and pathways to inclusive growth
Strand	Pathway to Inclusive Growth
Energy	Better trained women and men are more employable for higher wages. National SMEs are certified and known by and more attractive to larger project developers.
Financial Services	Women and marginalised people have higher financial literacy and access to ethical financial services.
Future Cities	Women and men in urban areas have affordable, safe and reliable transport solutions to promote access to a wider range of economic opportunities
ACROL	Reduction in illicit use of public funds improves the quality and impact of public services to reach the populations for which they are intended.

Throughout the Mexico Programme, there is an assumption that greater inclusive economic growth will translate into poverty reduction. While there is evidence that this is true, it is not an absolute given. For example, in the energy sector, large development projects may have a direct and opposite result on the surrounding communities and deepen poverty if they are delivered without appropriate social and environmental considerations. In the financial sector evidence shows that predatory practices and uneducated consumers could exacerbate poverty. In the future cities space, greater mobility may not directly result in poverty reduction, but can support easier, more affordable access to economic opportunities. And finally, in ACROL, the strand supplier concedes that poverty reduction is likely to be an “indirect” result. The strand teams have the opportunity during the inception phase to ensure that these possible, less desirable, outcomes are avoided by ensuring designs and implementation plans have robust risk mitigation efforts and appropriate indicators are identified and quality assured.
### Sustainable Development Goals
In addition to contributing to the Prosperity Fund’s global ToC, there is evidence that the PT assessed and incorporated alignment to the United Nation’s Sustainable Development Goals (SDGs) into their designs. This evidence is found in the OBC and final BC, the SoRs, the suppliers’ bids and emerging design and analysis during the inception phase. According to the OBC, the Mexico Programme seeks to support progress in the following SDGs:

Figure 1: United Nations Sustainable Development Goals in the outline business case

The alignment of the strands to the SDGs is seen in Table 8 on Page 24, overleaf.
Table 8: Specific strand alignment per Statements of Requirement
Strand	SDGs
Energy	7. Clean and Affordable Energy; 8. Decent Work and Economic Growth; 9. Industry, Innovation and Infrastructure; 11. Sustainable Cities and Communities; 13. Climate Action[9]
Financial Services	1. No Poverty; 5. Gender Equality
Future Cities	1. No Poverty; 5. Gender Equality; 11. Sustainable Cities and Communities; 13. Climate Action
ACROL	1. No Poverty; 5. Gender Equality; 10. Reduced Inequalities; 16. Peace, Justice and Strong Institutions
[9] SDG 13 Climate Action as not indicated in the OBC, but was included in two strands in SoRs.

## Deterrents and mitigation
Creating effective ties to new government. During the inception phase, the PF leadership raised that there is a need to make a concerted effort to develop channels into the new government in light of the changes in personnel in relevant ministries and agencies. As the government of López Obrador consolidates and the strands finalise their respective approaches, the PT use the whole-of-Embassy Virtual Team (VT) system[10] to engage government and private sector stakeholders. PF also noted that the quality of the suppliers’ key personnel is facilitating the emerging conversations with relevant government officials.
[10] See Section 5.3 on Page 20 and the strand annexes (Annexes 3–6).
Strand consortia members falling short. Two of the PF strands have already faced this challenge and dealt with the situation quickly and in coordination with the Tier 1 supplier. Delivery on milestones was not impacted in either case, but time and focus were required for both the PF teams and the strand suppliers. Overall, however, these changes early on improve the strand suppliers’ strength and positioning to further support the delivery of primary benefits over time.
Ensuring designs are supported by high-quality indicators. The strand suppliers are working to identify indicators that will best capture the changes desired through the PF investments. Good indicators will support the strands and the Mexico Programme to tell its story, bad indicators risk showing little to no change, or seek to provide data that is not directly relevant to the scope of the strands or programme. The monitoring, reporting, evaluation and learning (MREL) providers each have a supporting role in optimising indicator selection, mapping and use. The PT have reached out to M&R and E&L for support during the Inception Phase so that there is less risk of revisions or false-footing in the early days of implementation and beyond. The support will conclude after the timing of this evaluation cycle and will be considered in the Cycle 2 evaluation.
# Guidance, governance and management
This section responds to the following evaluation questions (EQs):
- EQ8a. How well do Prosperity Fund (PF) institutional governance structures operate and to what extent have they helped or hindered in the design phase of the programme or strands?
- EQ8b. What recommendations from both Evaluation and Learning (E&L) and from the programme team (PT) are there for improvement?
- EQ9. What types of programmes, approaches and governance and management arrangements have been more or less effective for achieving results and demonstrate good approaches to supporting inclusive growth and Value for Money (VfM)?
See Annex 2 for mapped EQs within this report. Individual strand analyses are found in Annexes 3–6.
## From the centre
Guidance, governance and management systems across the Mexico Programme extend from the centre of Whitehall through the Embassy, into the PF and the strands and down into satellite hubs and working groups of the suppliers. The Mexico Programme has been routinely among the vanguard in bringing the PF from design to inception. As such, it frequently needs guidance before many of its PF colleagues. The Head of PF in Mexico noted the value she finds in the annual London PF gathering in December as an efficient way to connect with peers and share challenges and approaches to strengthen the early evolution of PF programmes.
These guidance systems support and improve programme design and positioning when information is timely, fulsome, and relevant. When guidance arrives too late, or not sufficiently detailed or too generic, it can cause delays.
The evaluation team heard repeatedly that some guidance and training from the Joint Funds Unit (JFU) or the Prosperity Fund Delivery Unit (PFDU) tends to be too generic to utilise in-country without substantial adaptation. The PF team note that sometimes it has requested guidance from London and has been told that the guidance was in development and to wait. But it has found that waiting can create programme delays. To overcome the situation, the PT has sought outside support and capacity-building or designed tools or process proactively and sought London approval. For example, the team utilised the time between outline business case (OBC) submission and Statements of Requirement (SoRs) to build internal capacity, particularly around Gender and Inclusion (G&I) skills as well as programme management skills[11]. Examples of document creation include finance, commercial, contract management, monitoring and reporting requirements and methods; tolerances (i.e., the flexibility within the terms and conditions of the contracts); the SoR pricing schedule, and carbon offset credits for travel and safeguarding requirements. These were all adapted from previous best practice and existing UK formats, including from Department of International Trade (DIT) and the Department for International Development (DFID).
We don’t know what we don’t know so we can’t ask for the training.
 PF Mexico KII
KII 25 April 2019

[11] The PM required all PT staff to undergo PRINCE 2 programme management training to strengthen the future implementation of the four strands.
It is not always clear to the PT why London requires a document. Several PF staff told evaluators about preparing a Secondary Benefits (SBs) plan in early 2018, but little feedback was received. “It went to the JFU and that was it.” It was, indeed, used by stakeholders in London, but that information did not make its way back to the PT in Mexico.
At mid-point in the inception phase, the PT is particularly eager to receive JFU/PFDU Guidance for change control at the strand level. The Schedule 11 form is complex and oriented to changes at the programme level. There is no clarity about how individual strands submit these forms, yet now is the time that the strand teams are submitting changes that require oversight.
PFLearning has also been behind the informational needs curve of the Mexico PT to date. The PT expect that once other programmes enter implementation, the online platform will be of greater utility to the Mexico team and its strand suppliers. Until then, Mexico joins selective PF presentations or sources key documents from the platform on a limited basis. The greatest area of interest is in the family reference groups, but the PT notes that the intense focus required to bring the strands through procurement and inception limits time available for other, albeit relevant, information sharing.
## At post
The governance structures of the PF in country are a series of committees and boards which aid the decision-making and oversight processes required of the PT.
Programme Management Committee (PMC). The PMC meets monthly and includes representatives from all the UK programmes underway in Mexico. The committee has a clear terms of reference (TOR), including membership, data required of it prior to its meetings, voting rights and reporting requirements. The Head of the PF in Mexico attends with voting rights, while each PF strand and global programme has observer status on the PMC. The primary function of the PMC is to “ensure proper strategic oversight of all Embassy programmes,” including budgets, risk and mitigation, and to provide guidance where necessary.
Virtual Teams (VTs). First used in the PF with the drafting of the 2017 OBC[12], the VTs include representatives from the Embassy’s departments that have a direct relationship with the PF’s goals and processes – the strand programme managers, FCO’s political and global issues teams, DIT, communications leads, commercial experts, and representatives from other programmes, including Newton, ICF and the International Fund. The VTs provide strategic direction and ensure rigour so that the logic and relevance of each strand is optimal and adapts to national political economy contexts as well as serving broader UK interests in Mexico. The VTs make use of cross-Embassy sector plans, which are approved by heads of sections in the PMC, and enable different departments within the Embassy to see and understand clearly what their colleagues are doing and to identify linkage and leverage points. Plans also identify the breadth of interventions, including communications, resources and risk. Impact pies consolidate the goals of the respective Embassy departments set against metrics so that a whole-of-Embassy perspective is maintained.
[12] Mexico Prosperity Programme Outline Business Case, June 2017. Page 148.
“The programme and the strands are like oil tankers, but the Agile Programming Fund is a flotilla of little life boats.” / KII 23 April 2019

Agile Programming Fund (APF). The APF is a budgeted allocation within the strand suppliers’ budgets which is versatile, aligned and has the potential to fund innovative or complementary work that is either outside the boundaries of the core strand interventions or in addition to what the strand teams have already accounted for in their respective intervention budgets. The APF is being used to mitigate risk and to pick up opportunities that align with primary interventions that may not be specified within implementation work plans or facilitate cross-programming among the strands. The three strand suppliers who have APF funds within their allocations (Energy, Financial Services and Future Cities) will set up their systems up by end of the inception phase. No APF use will occur in the current evaluation period, but future cycles will consider the use, role and impact of this mechanism.
## Within the Prosperity Fund
There is evidence that the PF programme is well structured to ensure regular review and discussion of PF and strand policy, stakeholder engagement, and challenges. The mechanisms noted below also serve to identify cross-strand leverage and mitigate gaps and/or redundancies in programme implementation.
Prosperity Fund Strategy Advisory Board. The PF Strategy Advisory Board provides a venue for high-level discussions which include senior UK and Mexican authorities to ensure strategic oversight and proper alignment of the PF and “to maximise the impact of the PF programme on Mexican economy/society.” The writ of the Board plays a role in positioning the PF in key ministries in the new administration, the private sector and relevant associations and civil society. The board meets quarterly and has a clear TOR, including membership, voting rights, reporting requirements and agenda format. The TOR will be reviewed internally in March 2020 to ensure that the board is meeting expectations.
Cross-cutting theme leads. Another mechanism created by the Head of the PF in Mexico to promote cross-learning and ensure that complexity is managed is that each member of the PF team holds a cross-cutting theme which they manage for a year in addition to their technical team roles. The 14 themes include:
- Programme planning
- Risk management
- Gender and inclusion
- Non-ODA
- Safeguarding
- Stakeholder management
- Latin American engagement and conference
- Lessons learned
- Celebrating success
- Learning and development
- Monitoring, reporting, evaluation and learning (MREL)
- Information management
- VfM
- Annual review.
While there is confluence among these themes, there is no duplication and specific ToRs provide definition and focus. Theme leads invest time for learning, sharing and coordination within their respective assignments, which enables them to develop their professional capacities, mitigates stove-piping and strengthens cross-team learning and action related to the themes.
There is strong evidence that these cross-cutting themes have improved the design of the strands and supported peer learning within the PT. For example, the G&I considerations between the OBC and the SoRs were much improved in part due to the attention and coordination that the cross-cutting theme lead for G&I invested in her role. This improvement was noted in the G&I Stocktake conducted in February 2019 (see Annex 7).
Another example is seen in the way that the PF teams in Latin America regularly exchange information and ideas through informal and formal channels, including the regular LatAm regional meetings[13]. There is evidence that models, such as the VTs, or the insights into contract management are already leading to adoption of regional best practice.
[13] The next LatAm regional conference is scheduled to take place in Mexico in September 2019.
Gender and Inclusion (G&I) Group. The G&I Advisors/Leads from each of the strand supplier teams meet monthly with the PF’s gender theme lead to discuss the mainstreaming and the cross-strand leverage opportunities for G&I. In addition to providing evidence that these discussions support the integration of G&I into strand designs, there is also evidence that unexpected strand coordination can occur from this group’s discussions. For example, during one of the earliest G&I Group meetings, the ACROL and Financial Services strands identified common stakeholders and agreed to collaborate on engaging them strategically. The G&I group is also seeking to identify common indicators as necessary to enable the Mexico Programme to tell as strong a G&I story as possible.
Other thematic groups. The PT plan for similar cross-cutting supplier groups related to the APF, SBs and communications. Whilst none of these groups had met by the time this report was drafted, plans are for these groups to convene during the inception phase and beyond.
Strand Governance Boards (SGBs). Each strand has its own SGB. The SGB will provide accountable, responsible and transparent delivery oversight for the Energy, Financial Services and Future Cities strands. The final function of the SGB for the ACROL Programme is still under discussion at the time of the drafting of this evaluation. The SGBs ensure the collaboration of key stakeholders who are strategic decision-makers, thereby ensuring continued alignment to Mexican government priorities. The membership of the SGBs is at the working level and in some cases includes key government agencies and actors to fulfil the board’s mandate, which is to ensure that the programme is oriented to support and help drive the aligned government objectives of key departments.
## Within strands
Based on the Call-Off Contracts and the KIIs, there is strong evidence that strand suppliers have put into place management structures and procedures that support the design and positioning of their respective strands during the inception phase. Many of these management structures are similar across the strands, whereas others are bespoke to a specific strand.
Central Delivery Units (CDUs). The CDUs are the main delivery unit for each strand and include common elements such as in-country staff, head office support from the supplier’s headquarters in the UK and access to the resource pools that each strand supplier identified in their bids. All CDUs are based in Mexico City to facilitate coordination with the PT and federal government stakeholders. All strands will have CDU satellites or hubs to facilitate improved and sustained engagement with local stakeholders (see Table 9 below).
Table 9: Central Delivery Unit satellite/hub by strand
Strand	Satellite/Hub	Details of Satellite/Hub
Energy	Tabasco	Outreach to the oil & gas centres
	Jalisco	Outreach to the renewable energy centres
Financial Services	Two states TBD by end of inception	Financial Innovation Centres
Future Cities	Cities TBD by end of inception	Pilot cities which test mobility solutions
ACROL	Mexico City/State of Mexico	Centre of policies and largest populations
	Jalisco/Tabasco	Rapid growth area

Monthly reports. There is evidence that the PF Mexico Programme has built learning and development into the reporting system. The PT have incorporated weekly activities logs and monthly logs that capture lessons learned, issues and risk updates from each strand. These logs are reviewed by the respective PF strand management teams and then circulated within strand VTs to ensure that insights, learning and challenges are known to the relevant counterparts within post. These logs are entered into other management systems, including Prospero, the PF programme debriefs and PT–supplier discussions.
Data quality. Each strand supplier will create an agreed plan for MREL engagement and compliance by the end of their respective inception phases[14]. The template for this document was prepared by the monitoring and reporting hub and introduced in April’s joint MREL workshops. The introduction of this template coincided with the release of the guidance notes on data quality, which enabled specific discussions regarding data quality with strand programme managers and strand supplier teams as the revisions to ToCs and logframes were beginning. Once completed by each strand supplier, the plan will include details on the collection, frequency, storage, flows and quality assurance for each indicator identified in the strands’ final approved logframes. Because these details are collected in a single document, it will be easier for this data to be monitored by the PT and in subsequent evaluation cycles.
[14] Milestone 2.1 in the Call-Off Contracts.
## Bespoke systems within strands
Within each of the strands there are advisory or working groups, additional oversight bodies or other management and governance systems designed to extend programme reach or improve the positioning of the respective strands closer to their stakeholders and partners. Links to these sections of the strand report are here: Energy, Financial Services, Future Cities and ACROL.
The Energy strand has an innovative goal for its CDU in that it is not only a strand management body, but it is designed to anchor the strand’s sustainability strategy post-PF (See Annex 3). There is good evidence that the design of the CDU has been well-reasoned, but it will only be relevant to evaluate progress on this goal later in the implementation phase.

# Thematic analysis
## Gender and inclusion
This section responds to the following Evaluation Questions (EQs):
If you support women, you support families. If you support families, you support children.

KII 25 April 2019

- EQ9.2 Which approaches, governance and management arrangements have been adopted in relation to gender and inclusion (G&I)?
- EQ10. To what extent have the Prosperity Fund (PF) interventions contributed to results that support gender and equality, women’s economic empowerment and social inclusion?
### Initial stocktake
Table 10: Initial and current gender and inclusion scorecard scoring
Programme	Programme Design	Internal capability / institutional incentives	Financial resources	Accountability mechanisms	Partnerships
Mexico 2/2019
Mexico 5/2019

In February 2019, Evaluation and Learning’s (E&L) Gender and Social Inclusion Lead evaluated the Mexico Programme’s G&I scorecard (Annex 7) with a generally “good” finding, based on the 2018 revisions to the programme and strand designs between the outline business case (OBC) and the statements of requirement (SoRs). The Mexico Programme Team (PT) sought and secured G&I guidance and support from the Joint Funds Unit (JFU) and the Work and Opportunities for Women (WOW) Helpdesk as the PT reworked its strand ToCs ahead of the upcoming tenders[15].
[15] See PF Gender Policy March 2018: https://www.pflearning.co.uk/x/C4OK and SoRs “Appendix 8: Prosperity Fund Gender and Inclusion Requirements.”
Recent information indicates that there is now an evolving operational understanding of G&I with equal emphasis on the inclusion of marginalised populations which programme teams should reflect in their designs and metrics in addition to the sustained focus on gender. There is evidence that the Mexico PT and the four strands have accounted for the inclusion of marginalised groups in their evolving strand designs, albeit to a lesser extent as the guidance up to this point has emphasised gender[16].
[16] Guidance call 4 December 2018 in which PT, E&L G&I lead and PEL/Mexico joined JFU, inter alia.
The weakest element in the February 2019 stocktake was related to financial resourcing of the G&I elements, due to the absence of information, including strand budgets, which inform this aspect of the G&I scorecard.
### Gender and inclusion update
Programme design
The new evidence available since the February stocktake includes the technical and commercial bids, the Call-Off Contracts, strand suppliers’ staffing, and early milestone documents. In the awarded contracts, each strand supplier is obligated to prepare a Gender and Inclusion Mainstreaming Strategy and Action Plan in their acceptance criteria for payment. Whilst each strand supplier has the flexibility to tailor its final strategy and action plan, the evidenced core elements of these analyses include:[17] (i) an assessment of the social and gender context; (ii) an assessment of the national and international legal frameworks and covenants by which Mexico is bound as these relate to the strand; (iii) a gap analysis as it relates to gender and/or end beneficiaries of PF interventions; (iv) a defined strand G&I strategy; and (v) a delivery and learning action plan. These strategies will detail the monitoring and reporting of G&I into the monthly, quarterly and annual reporting cycles.
[17] Based on initial outlines submitted by strand suppliers to their respective PF strand team.
The outlines for these documents[18] have been submitted by the four strand suppliers with final versions due for completion in August 2019 (October 2019 for Energy), after this evaluation report is concluded. The strand suppliers are currently fielding research and undertaking fact finding to inform their individual G&I strategies and action plans. This research includes surveys and focus groups which reach into the prospective stakeholders of the sectors. There is a delicate balance between engaging potential end beneficiaries and ensuring room to further define the strand designs without setting unintended expectations – a concern noted both by strand programme managers and strand suppliers in their KIIs.
[18] Milestone 1.4 in the contracts for each of the four strand suppliers.
There is high degree of confidence that gender considerations will be further factored into final strand designs and stakeholder engagement approaches. The incorporation of inclusion dimensions, for reasons noted above, may have to be further strengthened in what remains of the inception phase. Already there is a clear link for social inclusion in the Energy and Financial Services strands with their objectives to boost employability of low-skilled women and men in the energy sector and improve financial services to women and poor or vulnerable populations. The evidence of social inclusion in the Future Cities and Anti-Corruption and Rule of Law (ACROL) strands is currently being developed, although there is an implied inclusion of marginalised populations in each of these strands that could be more further identified and articulated in final strand designs and metrics.
The OBC offers two reference definitions for “poverty”.[19] This has caused confusion among the strand teams in their causal analysis to create their respective ToCs, logframes and baselines regarding the “inclusion” aspect of G&I. E&L has recommended that the PT opt for the CONEVAL[20] definition based on four factors: (i) it is a national source, which is important to the positioning of the programme; (ii) it is well established and offers the programme a longitudinal basis from which to work; (iii) it is multi-dimensional and may better capture some of the nuance and linkage between "inclusive economic growth" and "poverty reduction;" and (iv) it is the reference point of federal and state actors, which will facilitate communications about challenge and opportunity.[21]
[19] World Bank’s poverty assessment and Mexico’s CONEVAL multi-dimensional poverty index.
[20] CONEVAL - Comisión Nacional de la Evaluación de la Política de Desarrollo Social (National Commission for the Evaluation of Social Development Policy)
[21] Email exchange between PEL and PM 2-05-2019 as a KII follow-up.
There is strong evidence that the PT take a learning and adaptation approach to their programme design and management. This approach has led to insights and impacted not only strand design, but also resulted in identifying desirable requirements previously missing from the PF framework.
For example, in addition to the WOW Helpdesk support the PF team received[22], the PF ACROL team sought technical guidance from Mexican G&I experts who specialise in ROL to ensure that their pre-SOR designs were gender inclusive. During that consultancy, the team realised it had limited its thinking to women as opposed to broader gender analysis. This insight led to an understanding of different ways to reduce gender inequality.
[22] See Section 6.1 on Page 24.
Safeguarding was introduced to the programme’s cross-cutting themes prior to SoRs being finalised. Additional guidance from DFID was incorporated later once the theme lead identified the potential for the PT to deepen its safeguarding requirements of the strand suppliers.
Internal capability/institutional incentives
The Head of PF Mexico has identified a G&I Thematic Lead within the PT. That staffer’s role is to champion G&I as a theme in PF and Embassy discussions and ensure that the theme is adequately reflected in PF communications, designs and planning. There is a similar Thematic Lead from within the PT for safeguarding issues.
There is clear evidence that each strand has committed financial resources to bring in top talent, female and male, as well as design strand initiatives which inform, include and train women. This includes the hiring of G&I experts within the senior management team of the strand suppliers’ Central Delivery Units. This is consistent with the SoR instructions that these G&I advisors should be “gender and inclusion champions” with sufficient seniority and responsibility to ensure delivery[23].
[23] Mexico strand SoRs “Appendix 8: Prosperity Fund Gender and Inclusion Requirements.”
DAI, which holds the contracts for two strands (Energy and Financial Services), has a policy of equal pay for equal work within its own ethics and standards, assuring equal pay even when female candidates ask for lower salaries during the recruitment process.
Financial resources
The Value for Money (VfM) assessment for Criterion #8 (Equity) found that “the programme has made significant efforts to mainstream gender issues throughout the programme, and there is good evidence that this has been achieved successfully across all strands, which are therefore scored 4. Some elements of the Financial Services strand have the potential for a transformative impact on gender issues, so this is scored 5. There is also evidence that wider inclusiveness issues (i.e. beyond gender) have been considered, though with less focus than gender[24].”
[24] See Section 6.2 on Page 28.
A final, costed year-one implementation phase work plan is due at the end of inception in August for all strands but Energy, whose work plan is due in October. However, given the VfM score for equity and the evidenced trend of committing resources to gender and social inclusion operations and programming, the previous amber score in this dimension in February 2019 is now green. The PT has the ambition to reflect gender-sensitive budgeting in the strands’ costed work plans for the implementation phase. This rating will be validated once the strands have all entered the implementation phase during the Evaluation Validation Workshop scheduled in the autumn of 2019 (see Annex 16).
Accountability mechanisms
There is good evidence the programme has established strong governance structures which support the primary and secondary objectives of the PF in Mexico. For inclusive growth, the PT received specific guidance from the JFU/PFDU and the WOW Helpdesk related to gender, but less so on inclusion. This resulted in the designs of the strands and the overall programme concentrating on gender inclusivity and equality over the inclusion of other marginalised groups. Nevertheless, there is no indication that the governance and management systems in place cannot be adjusted to ensure that the broader understanding of G&I and its elements are accounted for prior to strands moving into their respective implementation phases.
During the inception phase, the full-time strand G&I advisors meet bi-monthly with the PT’s cross-cutting G&I Lead to explore synergies and leverage points for gender and social inclusion within and across the strands. The G&I advisors revert discussions and findings to their respective strand teams to incorporate relevant elements and inform the emerging strand designs. Their early challenge is to clarify and harmonise some of the definitions and baselines for Mexico emerging from strand-specific design research as these relate to gender and social inclusion so that all the strands share common reference points and, potentially, indicators. This clarity is crucial to ensure accountability across the Mexico Programme to ensure equitable gender and social inclusion.
Partnerships
During the procurement process, the PT rated the bids with strong, mainstreamed gender and social inclusion elements highly,[25] and discounted those that presented G&I as a stand-alone element.[26] According to the KIIs with strand programme managers and bid selection notes, only those bids with strong G&I elements were awarded contracts[27]. The strand coalitions noted in Annex 11 serve as evidence of the strength of G&I expertise within these partnerships and are further supplemented by technical experts on-call within each strand supplier’s resource pools, which are formalised in the suppliers’ Call-Off Contracts.
[25] As defined in Appendix 8 of each strand’s SoR and Invitation to Tender.
[26] Section 4 of the SoRs’ Evaluation Criteria included: “(i) (Explain) how you will design and deliver the Strand interventions to take into account the social context and ensure GEA compliance, support gender equality, women’s economic empowerment and inclusion; and (ii) (Prove) An understanding and knowledge of how to maximise economic, social and environmental benefits and opportunities for local stakeholders, including women and men and communities, to do no harm and to access and benefits from the Strand interventions.”
[27] PT used the JFU PF Bid evaluation guidance note, April 2018 to rank the submitted proposals.
Recommendations
As the strands generate insights and findings via their respective inception phase diagnostic research and outreach to stakeholders and potential end beneficiaries, they should identify how marginalised groups and vulnerable populations will be impacted by their interventions, account for this with specific indicators and outline how they intend to build these into their work plans.
G&I advisors, through the G&I Group, should exchange inclusion indicators and interventions that promote both gender and social inclusion in their discussions before the close of the inception phase and identify shared indicators to enable the programme to assess its G&I impact in a more holistic and balanced manner.
For strand-specific G&I details, please see the strand evaluation annexes (Annexes 3–6).
## Value for Money
This section responds to the following EQs:
- EQ4: What evidence is there that the changes supported by PF interventions will be sustainable and ensure environmental sustainability, will be self-financing and lead to inclusive growth that reduces inequality?
- EQ 9.1: Which approaches, governance and management arrangements have been adopted in relation to VfM?
### Procurement process
The tendering process completed in December 2018 and final selections were sent to London for contracting. The negotiations between the PF and the selected strand suppliers continued through January, with each contract concluded in February.
### Summary of Value for Money scorecard results
This section summarises the results of the VfM scorecard process. The process is described in more detail in Annex 8, along with the results for each strand and for the programme as a whole for the eight VfM criteria.
In Cycle 1 the VfM analysis has focused on process issues, in other words, to what extent has the PT selected suppliers and established processes and systems that are likely to generate VfM in future? Actual achievement of VfM will be assessed in future cycles.
Each criterion was scored from 1 to 5, on the basis of whether evidence to support the criterion is not available, weak, adequate, good or strong. The grounds for making this judgement is set out in the E&L guidance note on VfM.
Overall, the programme is scored at 3.9 (out of 5), on the basis that there is good evidence the programme has put in place suitable arrangements likely to generate VfM over the course of implementation. Scores for each strand are illustrated in Table 12 below.
Table 12: Summary of Value for Money Criterion scores, for each strand and the programme as a whole
VfM Criterion	Energy	Future Cities	Financial Services	ACROL	Average programme score
1 – VfM indicators	3	3	3	3	3
2 – Procurement and cost containment	5	5	5	3	4.5
3 – Efficient use of resources	4	4	4	4	4
4 – Valid causal pathways	3	3	3	3	3
5 – Sustainability	3	4	3	4	3.5
6 - Governance	4	4	4	4	4
7 – Risk management	5	5	5	5	5
8 - Equity	4	4	5	4	4.25
Average Strand score	3.9	4.0	4.0	3.8	3.95

It is notable that the average programme score was 4 (‘good’) or above for five of the eight criteria.
Those criteria with scores of lower than 4 indicate areas for improvement. Of these, less attention is required for: VfM Criteria 1 (Relevance and robustness of VfM measures in place) and 5 (Sustainability of programme activities). In these instances, a lower score reflects the fact that logframes and some other documents (e.g. Climate Resilience Plans) have not yet been finalised and therefore could not be included in this analysis. However, when they are completed by the end of inception, these scores seem likely to rise on account of work that is already in progress.
VfM Criterion 4 (Validation of PF ToC causal pathways for generating primary and secondary benefits) is scored 3.25 for the programme as a whole. There is scope to improve this for the Future Cities, Financial Services and ACROL strands, and it is also important to do so because in assessing the “four E’s for VfM” this criterion is the main test for Effectiveness[28].
[28] The others are Economy, Efficiency, and Equity.
- The broader evidence on financial inclusion supports the view that the Financial Services strand could lead to inclusive economic growth and lower inequality. However, positive impacts on inclusion are only likely to occur in the context of supporting conditions, which are not currently within the ambit of the strand. The strand ToC should therefore be clarified to include the assumption that these supporting conditions do in fact occur, and to highlight the risk that the strand may not achieve inclusive growth if they do not.
- For Future Cities, it is important that the pilots for each city set out the specific causal pathways from strand outcomes to inclusive growth and poverty reduction, including defining how women and girls or other disadvantaged groups will benefit.
- For ACROL, the evidence that greater cyber-security, improved homicide investigations and better access to justice will reduce poverty is indirect. The logic that improved commercial, administrative and security dimensions at the state and federal level will improve economic growth is better substantiated. The final design of the ToC and the indicators selected for the strand should therefore set out clearly the pathways for achieving this.
Strand scores for VfM Criterion 4 (Validation of PF ToC causal pathways for generating primary and secondary benefits) could also be improved by developing clearer actions plans for Secondary Benefits (SBs) along the lines indicated in the next section (and in the annex for each strand).
## Secondary benefits
This section responds to the following EQs:
EQ3. Which types of interventions, sectors and country settings have been more or less successful in contributing to the achievement of SBs?
- EQ5. What factors have contributed to the achievement of primary and secondary benefits?
- EQ6. How has the balance and relationship between primary and secondary benefits across the portfolio influenced the achievement of results?
### Overview
Analysis of SB issues in Cycle 1 has focused on whether plans and processes for achieving them are appropriate compared to the scale of ambition set out in programme documents. DIT Mexico indicates that the PF programme has already helped to secure some SBs (see below). Nonetheless, analysis of actual SB achievements will be undertaken in future cycles rather than at the current moment when the programme is still in the inception phase.
The analysis in Cycle 1 has also focused on the specific sub-questions for SBs set out in the Approach Paper:
- What factors were taken into account to make decisions on the balance and focus of the programme in terms of primary and secondary benefits?
- How has the programme team incorporated SBs into programme and strand designs? Are these adequately defined in programme documentation, including in supplier designs?
- To what extent does the PT have the necessary capacity to monitor and measure SBs?
For reference, the E&L Secondary Benefits team have defined six possible types of SBs[29]:
[29] The E&L team has produced some short videos on Secondary Benefits which define and explain each of these in more detail (available on PFLearning). As explained in the introductory video, the E&L definitions map precisely to those used by DIT, although DIT uses slightly different terminology.
1. Increase in UK exports to Mexico
2. Increased investment from the UK into Mexico (overseas direct investment (ODI))
3. Investment from Mexico to the UK (foreign direct investment (FDI))
4. Better market access (imports and access to new resources e.g. skills for UK businesses)
5. Network effects – partnerships between UK and Mexican firms or institutions that support innovation or create new markets
6. Soft power – an improved perception of the UK that helps achieve other commercial or diplomatic goals
### Key findings
Overall, the Mexico Programme has good assets with which to achieve SBs, and has also put significant effort into planning and setting up delivery mechanisms.
There is an overall Secondary Benefits Plan for the programme, supplemented by a Prosperity Sector Plan and Impact Pie[30] for each strand. DIT currently has 45 staff in Mexico, and from this team has assigned staff to each strand to deliver SBs over time. These are supported by a new DIT Head of Renewable Energy (financed through non-ODA funds) who will also coordinate and monitor SB delivery efforts over time.
[30] These are visual (pie chart) representations of the types of activities the embassy will undertake to generate commercial benefits for the UK, including timescales and expected results.
The Embassy’s virtual teams (VTs) are also likely to be key in maximising SB opportunities, by bringing together policy, programme and commercial staff in a single team[31]. The VTs are worth flagging as an organisational innovation which should be of interest to other PF programmes and the posts involved in delivering them. There is also some evidence that links with between the programme and central DIT teams in London work well (the Financial Services strand mentioned DIT’s financial services team in London had been very helpful in designing the intervention).
[31] The Head of DIT in Mexico also suggested the VTs have already helped secure early SB wins.
Although significant work has gone into planning for delivery of SBs, the programme would benefit from further refinement of existing plans for each strand. The overall programme Secondary Benefits Plan provides a good framework, setting out the types of SBs that are expected for each strand, and the types of high-level activities that will help to deliver them. This plan is supplemented by the Prosperity Sector Plans and associated Impact Pies, which set out activities for the forthcoming year.
However, these plans do not match clearly with the kinds of SB opportunities identified by the PT and address issues of when SBs might be delivered. They currently set out activities for the forthcoming year (rather than the length of programme). Furthermore, while they may serve well as internal embassy documents, they are challenging to interpret and therefore may not be easy as a guide to suppliers on which of the specific opportunities for each strand are being addressed and how. As such, refined SB plans for each strand should help to inform the suppliers own SB plans which they are due to develop in the implementation phase.
It is therefore suggested that an SB plan is developed for each strand, building on Prosperity Sector Plans, but also making explicit:
- Which SBs can realistically be delivered at different stages of implementation. Some SBs may be realised relatively early during design and planning work, while others may depend on some or all of the stand’s objectives already having been achieved.
- Whether there are specific challenges to UK firms realising these opportunities (e.g. general business environment issues, the availability of required skills, specific standards and regulations for goods and services or knowledge of local procurement processes), and what role if any DIT can play in addressing these.
- Which activities will be carried out by DIT in relation to the specific SB opportunities identified for that stage of implementation.
- How the supplier might support achievement of these opportunities, building on the excellent resources they have identified for doing so, but also taking into account that this support can only be provided as part of their work to deliver primary benefits
- How achievement (or otherwise) of these SBs will be monitored by DIT.
- How SB opportunities can be delivered over the course of the PF programme, rather than just during the forthcoming year (which is the timescale addressed by each Prosperity Sector Plan).
### Monitoring achievement of Secondary Benefits
Initial discussions with DIT’s team in Mexico show that there are monitoring systems which should capture the first four SB types (exports, ODI, FDI, market access) through its formal monitoring systems. In future cycles, E&L will critically review these to assess the contribution of the PF programme to particular achievements. The Embassy’s ‘Impact Bank’ – a record of areas where the embassy believes it has contributed to a particular outcome – may also provide the basis for assessing network effects and soft power. This will be tested by working through specific examples listed in the Impact Bank in Cycle 2.

# Challenges and lessons
This section responds to the following evaluation questions (EQs):
- EQ11. How is the Prosperity Fund (PF) learning and why is action on this learning happening more or less successfully?
- EQ12. Which PF lessons in translating outputs into intermediate outcomes are sufficiently robust for wider learning?
This section explores the challenges that the PF Mexico Programme Team (PT) has faced and the lessons it has learned as it responded to those challenges. Some challenges also have recommendations from the evaluators associated with them, which can be found in Section 9.
Taking advantage of PF Mexico’s initiative. The challenges to timely and fulsome guidance were noted earlier in this report. It is less than optimal to have PTs in a position where they are creating documents and formats. However, the JFU and PFDU have an opportunity to take stock of the various forms, reporting requirements and approaches generated by PF Mexico and determine the degree to which these mechanisms are appropriate and relevant for other bilateral or global programmes. Learning from or adopting the Mexico PT’s innovations may save time and improve implementation across other programmes.
Utilising all assets for managing expectations and boost communications. Eighteen months passed between the submission of the outline business case (OBC) and the final business case and the close of the procurement process. A key lesson is that successful management has required an integrated, all-Embassy effort. The virtual teams (VTs) and the different departments and teams within the Embassy that they represent have been vital in distributing the responsibility of maintaining and moderating expectations through the election period and since the new government took office. The regular meetings of the Programme Management Committee also facilitate close coordination and messaging.
Being explicit about coordination and communication opportunities. There is room to improve communications, particularly in the way that London-based global programmes communicate with the Mexico-based strands, and likely vice versa. Some global programme teams assume that once they have spoken with someone in the Embassy, the information will convey to the corresponding strand team. Within the Embassy, the VTs were an attempt to mitigate those communication blind spots, which has generally been effective. However, the PF tends to lead the conversations. Starting in 2019, the Embassy will now identify task leads for actions in the impact pies, which is designed to bridge the gaps at post. However, global programme teams should also educate themselves as to the Embassy-based stakeholders and communicate appropriately and comprehensively.
Addressing skills gaps proactively. During the preparation of the OBC, the Head of the PF in Mexico saw gaps in G&I awareness and overall programme management skills. She required that all PF staff in Mexico take the PRINCE2 programme management training. Similar training was since offered within the PF services, but these came after it was relevant to the Mexico team. The lesson that the PT offer is that once a technical gap is identified, seek support immediately and cultivate that skill within the team as soon as possible. Another way to bridge those gaps is to hire an expert and use the ensuing consultancy to both provide substantive information as well as to model or train the team on relevant approaches.
Protecting firewalls and facilitating digital-based communications. The PT noted that the high-security firewalls of the Embassy’s IT systems prevent or delay communications with external partners. Not all documents that should be available to specific stakeholders are shareable. Evaluation and Learning experienced this directly in seeking the Anti-Corruption and Rule of Law strand supplier contract, which, after two weeks of attempts to share it electronically, as the other strand supplier contracts were sent, the PT had to courier the document at a higher cost and higher carbon footprint. The PT respects the need for the secure firewalls, but they wonder whether a neutral technical space could be created to facilitate electronic communications with what will inevitably be a greater set of stakeholders and programme partners without compromising diplomatically and commercially sensitive data and communications.

# Conclusion
The Mexico Programme is a well-designed programme that has adapted to a changing political, social and economic context in country. The evolution of the four strand designs has been iterative, which has at times tested the patience of strand programme management teams eager to bring their ideas into reality. Strand programme managers acknowledge the important role that the Embassy-based virtual teams have had in the evolution of the specific strands as well as in the positioning of the projects from when the Prosperity Fund (PF) programme was first announced to where the programme and the strands stand at mid-point of the inception phase.
The submission of early milestone documents and the draft ToCs and logframes give a strong indication that the strand suppliers are meeting the obligations to design and position interventions and projects that will promote inclusive economic growth. Each strand has an identifiable causal pathway to contribute to the Mexico Programme’s outcome statement: Improved conditions for growth in Mexico, through increased capacity and an improved environment for trade and economic growth. However, the causal pathway to achieve poverty reduction varies across the strands.
The Mexico Programme has often been among the earliest movers among PF bilateral programmes. As such it has broken ground and tested processes at an early point in PF’s global formation. In this process, it has encountered problems and sought guidance and solutions earlier than many of its programme peers. The programme team (PT) has been pro-active when guidance was slow in coming or was overly generic to be put to use without substantial revisions. Along the way, when the PT did create new forms, requirements or documents, it based these on existing UK experience and secured Joint Funds Unit/Prosperity Fund Delivery Unit approval prior to using these tools and approaches. The PF has the potential to draw on these resources to support other programmes as they enter the phases for which these tools and approaches were created. This would also mitigate the risk of having too many variations emerging across the PF.
There have been challenges in preparing this evaluation due to the tentative nature of the most basic of documents, including strand and programme ToCs and logframes. The 12 evaluation questions in the evaluation framework presuppose that these documents have been finalised and are operational. Nevertheless, the timing of this evaluation was established by consensus between the PT and the Evaluation and Leaning (E&L) team in January 2019 and all were aware that key documents would still be in draft form. The timing was deemed correct as the evaluation findings would inform the strands and the programme at mid-point of the inception phase to allow for any design or positioning corrections and also to support the PT as it prepares to draft its initial Annual Review. The PT and the E&L team have co-created the ongoing E&L cycle (Annex 16) to build on this iteration of insight, learning and adaptation.

# Recommendations
The recommendations below apply to the Prosperity Fund (PF) central and Mexico Programme levels. Strand-specific recommendations are found in the relevant strand analyses (Annexes 3–6).
## Fund level
Joint Funds Unit (JFU)/Prosperity Fund Delivery Unit (PFDU) guidance. The programme team (PT) identifies a number of areas on which it seeks guidance and training support from the JFU as the programme moves through inception and into implementation. This includes further capacity training on contract management[32]; monitoring financial reporting; Annual Review support; guidance on moving from inception to implementation; and in relation to the technical specificities relevant to each strand. Particularly critical at this point in mid-inception is guidance for change control at the strand level. The JFU and PFDU are recommended to consider these requests for guidance so that the Mexico Programme can ground-truth the recommendations and share its insights and experiences with other programmes that are quickly moving into similar inception and implementation phases.
[32] A two-day contract management training took place on 22-23 May after KIIs with the PT.
Virtual Teams (VTs). The VTs in the UK Embassy in Mexico have strengthened the design of each strand, ensured that both primary and secondary benefits were planned into the strand designs, facilitated coordinated communications and stakeholder engagement and leveraged non–Official Development Assistance (ODA) activities that supplemented ODA strand interventions. The Brazil Embassy is currently looking into adopting the VT model, but other country posts may also benefit from a review of the model as a way to support the quality of technical design and promote both primary and secondary benefits of the PF.
Cross-cutting thematic leads. Another innovation within the Mexico PT is the cross-cutting thematic roles that each member of the PF team holds. There are 14 themes, which challenge each staff member to learn about, teach and guide their colleagues, and take ownership in advancing their particular theme as it impacts the design, positioning and delivery of the PF programme. Other PF programme teams might review this methodology as a way of building the capacity of individual staff as well as integrating cross-cutting themes more effectively throughout their own programmes.
Invest in programmes to ensure strong beginnings. Each of the strand suppliers noted that the limit of the total budget for the inception phase constrained their ability to gather their top talent and undertake strand launches in the strongest way possible. The Contracting Team in London may want to assess if clearer guidance on what can be included in inception phase spending should be included in future SoRs.
Strengthen peer-to-peer engagement among programme teams. The PT in Mexico suggest providing development opportunities/job-shadowing opportunities for PTs. This will help to ensure that management of programmes is coherent globally, which may be especially important when strands/projects in different parts of the world are working with the same suppliers. PFLearning offers some space for this, but it may be necessary and helpful to further explore the shadowing opportunities.
## Programme Level
Define poverty. The OBC gives two different reference points from World Bank and CONEVAL which risks suppliers selecting different indicators and targets to support their causal pathways from strand to programme to Fund to best achieve poverty reduction and inclusive economic growth. The new administration will use the CONEVAL’s multidimensional definition of poverty. PF Mexico is advised to use the CONEVAL’s definition for several reasons. The CONEVAL definition offers country-specific relevance. First, it is from Mexico, which is important to the positioning of the programme. Second, it is well established and offers the programme a longitudinal basis from which to work. Third, it is multi-dimensional and may better capture some of the nuance and linkage between "inclusive economic growth" and "poverty reduction." Fourth, it is the reference point of federal and state actors, which will facilitate communications about challenge and opportunity.
Link climate resilience metrics. Similar to the logic for using the CONEVAL definition of poverty, the PT is recommended to utilise the Sendai Framework for indicators within the strands’ climate resilience strategies. The new administration has announced in the National Development Plan that it would be utilising the Sendai Framework for such purposes[33], and adopting similar indicators will facilitate communications with the new administration on climate change and climate resilience priorities.
[33] NDP 2019-2024. Page 77.
Optimise G&I strategies. Each of the strands has made progress in its G&I planning as noted in Section 6.1. From a delivery and management perspective, the strategies are strong. The final G&I strategies would be further advanced if the strand suppliers fully account for financial information.
Optimise utility of monthly reporting. The challenge remains in identifying what lessons and opportunities are most relevant to share forward into PFLearning or other cross-Fund learning platforms.
A summary of key recommendations identified in this main report and in the strand summaries are noted in Table 13 overleaf which also identifies the optimal timing for addressing these recommendations and the time frame in which the corresponding actions will have the greatest relevance and potential impact.

Table 13: Summary of key recommendations, lead and timing
Priority	Recommendation	Lead	Time Frame
Fund
1	Reconsider inception phase budget limits in SORs to mitigate unrealistically limited inception/launch budgets	JFU / PFDU	Immediately
2	Identify and evaluate the approaches and documentation used by Mexico to date to draw on lessons learned.	JFU / PFDU	By 31 Oct 2019
3	Utilise approaches and documents across other programmes to mitigate risk of duplication or deviation.	JFU / PFDU	By 31 Dec 2019
4	Assess Mexico’s virtual teams models to optimize programme designs and positioning, including stronger basis for achieving SBs.	JFU / FCO / DIT	By 31 Dec 2019
5	JFU may consider consolidating future approval processes to reduce the risk that key actors will leave their posts during the interim	JFU / PFDU	By 31 Dec 2019
6	At the point of going to market, potential bidders in the Framework receive training and guidance on the procurement processes and the evidentiary details required in each bid.	Programme Heads	By 31 Dec 2019
7	Assess cross-cutting theme assignments within programme teams to mitigate siloing and to offer staff capacity building.	JFU / Programme	By 31 Mar 2019
8	Create peer-to-peer engagement or job-shadowing opportunities across programmes (perhaps bilateral to global programmes) to strengthen coherence and offer staff capacity building	JFU / PFDU	By 31 Mar 2020
Programme
1	Define “poverty” to ensure common baselining	Head of PF/Mexico	Immediately
2	Use Embassy’s Impact Bank assessments to provide basis for assessing SB network effects and soft power.	PMC	Aug-Sept 2019
3	Align high-level metrics to National Development Plan (2019-2024) sources to boost strategic communications and improve likely availability of indicator data.	Head of PF/Mexico and all Strand PMs	Aug-Sept 2019
4	Account for gender and inclusion allocations in costed workplans to reflect fully the Financing dimension in the G&I scorecard.	Suppliers and Strand PMs	Aug-Sept 2019
5	Make strategic communications central to effort, backed up by verifiable actions, including message discipline within and across strands to build consistency.	Head of PF/Mexico and Strand PMs	Aug-Sept 2019
6	Prior to implementation, map all strands for regions, stakeholder, and interventions to identify all areas of synergy, overlap or gaps.	Head of PF/Mexico and Strand PMs	Aug-Sept 2019
Strands
1	Reintroduce Transit-Oriented Development into Future Cities’ design	FC PM	Immediately
2	Capture potential and mitigation efforts related to supplier in risk registry	ACROL PM	Immediately
3	Push for interventions that provide incentives for the use of financial services to increase income, productivity and education, rather than consumerism.	FS PM (all PMs should take note)	Aug-Sept 2019
4	Review indicators to ensure full reflection of gender and inclusion metrics	All Strand PMs	Aug-Sept 2019
5	Articulate the linkage to improving inclusive economic growth	ACROL PM (all PMs should take note	Aug-Sept 2019
6	Review assumptions within ToCs and logframes prior to inception phase sign-off to test rigour and causal pathways.	All Strand PMs	Aug-Sept 2019
7	Prior to implementation, review strand level groups, boards and committees to ensure no duplication with other governance and management bodies.	All Strand PMs	Aug-Sept 2019
8	Create sustainability plans which consider institutional, financial, environmental, technological and social elements, as well as the practical levers available to the programme in relation to each of these.	All Strand PMs	By 31 Dec 2021

Annex 1: Cycle 1 Approach Paper

Annex 2: Mapping evaluation questions in the Cycle 1 Evaluation Report
The methodology used by Evaluation and Learning (E&L) to evaluate Prosperity Fund (PF) programmes is structured around 12 Fund-level evaluation questions (EQs). The sections of this report in the programme and the strand analyses are designed to respond to these questions in a way that enhances readability and utility, rather than respond to each question in order. Given that the Mexico Programme is in its inception phase and final design and planning documents are not yet available, it is not possible to provide a response to some questions.
This guide is intended to support the EQUALS review by noting locations of EQ responses in the main report but does not attempt to address quality of content requirements. The page numbering in this mapping does not include the strand-level evaluations in Annexes 3–6 which follow a similar flow of analysis.
Table 14: Evaluation questions and location in the Cycle 1 Evaluation Report
Outline	Evaluation Questions	Location
Executive Summary	Summary of programme design and positioning today; findings; recommendations	Pages 8 -10
Introduction	Report structure; purpose and scope; audience and stakeholders; data collection and sampling; limitations	Pages 11 - 14
Context	Background information to clarify current PF multiyear context	Pages 16 – 17
Programme Design and Positioning	EQ1. What evidence is there that the Prosperity Fund is likely to contribute to the intended outputs and intermediate outcomes in the Theory of Change (ToC), as well as any unintended or unexpected effects?	Pages 18 - 24
	EQ2. Which types of interventions, sectors and country settings have been more and less successful in contributing to the achievement of primary benefits?
	EQ5.2. What factors may deter the achievement of primary benefits and what measures have the programme team (PT) taken to mitigate these?
	EQ7. Which assumptions and causal pathways outlined in the ToC remain valid, which have been adapted and what refinements need to be made?
PF Guidance, Governance and Management	EQ8a. How well do PF institutional governance structures operate and to what extent have they helped or hindered in the design phase of the programme or strands? / EQ8b. What recommendations from both E&L and from PT are there for improvement?	Pages 25 - 30
	EQ9. What types of programmes, approaches and governance and management arrangements have been more or less effective for achieving results and demonstrate good approaches to supporting inclusive growth and Value for Money (VfM)?
Gender and Inclusion	EQ9.2 What approaches and governance and management arrangements have been adopted in relation to gender and inclusion?	Pages 31 - 34
	EQ10. To what extent have the PF interventions contributed to results that support gender equality, women's economic empowerment and social inclusion?
Value for Money	EQ4. What evidence is there that the changes supported by the PF interventions will be sustainable and ensure environmental sustainability, will be self-financing and lead to inclusive growth that reduces inequality?	Pages 35 - 36
	EQ9.1. What approaches and governance and management arrangements have been adopted in relation to VfM?
Secondary Benefits	EQ3. Which types of interventions, sectors and country settings have been more and less successful in contributing to the achievement of Secondary Benefits?	Pages 37 - 40
	EQ5. What factors have contributed to the achievement of primary and Secondary Benefits?
	EQ6. How has the balance and relationship between primary and secondary benefits across the portfolio influenced the achievement of results?
Challenges & Lessons	EQ11. How is the PF learning and why is action on this learning happening more and less successfully?	Pages 41 - 42
	EQ12. Which PF lessons in translating outputs into intermediate outcomes are sufficiently robust for wider learning?
Conclusions		Page 43
Recommendations		Pages 44 - 47

Annex 3: Strand evaluation: Energy
This section responds to the following evaluation questions (EQs):
- EQ1. What evidence do you see to support the potential of the emerging Theories of Change (ToCs) to reduce poverty and support inclusive economic growth?
- EQ2. How has the strand/programme managed political change to ensure alignment and relevance to position achievement of expected primary benefits?
- EQ5.2. What factors may deter the achievement of primary benefits and what measures have the programme team (PT) taken to mitigate these?
- EQ7. Which assumptions and causal pathways outlined in the ToC remain valid, which have been adapted and what refinements have been made?
## Design and positioning
Strand design evolution
The Energy strand ToC has steadily evolved from outline business case (OBC) to statement of requirement (SoR)[34], driven by the changes which have emerged due to events in Mexico. The PF Energy PT was supported throughout the iterative design process through the Embassy-based virtual team (VT) that included the Department of International Trade (DIT), and the Political and Global Issues departments within the Foreign and Commonwealth Office (FCO).
[34] The SoR ToC was used for this evaluation. See Annex E, Page 75.
Prior to going to market, the strand programme team conceded that the scope was too broad for the likely available resources, and it honed in on capacity-building as its central theme. Many of the programme elements that were moved out of the PF sphere have the potential to secure funds through other channels within the UK Embassy (Newton Fund, International Climate Fund, Agile Programming Funds, etc.), enabling the PF Energy team to mitigate duplication, better focus PF fund and more closely hew to official development assistance (ODA) requirements. The team cites these programme design decisions as pre-procurement Value for Money (VfM), as they improved the efficiency and effectiveness of UK taxpayer-funded initiatives.
Factors driving design refinements
There is strong alignment within the current Energy ToC, featuring a plausible causal pathway to the Mexico Programme’s impact. In the May 2019 monitoring, reporting, evaluation and learning (MREL) plan[35], the PF Energy team and the strand suppliers identified three pillars to support strand impact: more productive, resilient and equitable workers, businesses and government officials that are better placed to lead Mexico’s transition to a low carbon economy.
[35] Milestone 2.1 in DAI’s inception work plan. 17 May 2019.
These pillars are a refinement to the SoR outcomes and better linked to PF objectives:
- Developing a resilient, socially-inclusive workforce that has the necessary skills and/or international certifications to fulfil industry demand;
- Building the capacity of female and male-owned Mexican small and medium-sized enterprises (SMEs) to support increased supply chain integration; and,
- Building capacity for energy regulators, with a focus on gender inclusion, in order to promote best practices in the implementation and enforcement of regulation.
Through these pillars, the strand seeks to generate eight outcomes which provide a clearer pathway to inclusive economic growth and poverty reduction:
1. Increase income of people living in the lowest or middle quintiles in the Hub’s two regions of influence.
2. Facilitate greater participation of women in the energy industry.
3. Increase the number of skilled women and men in the Mexican energy sector.
4. Increase local content in the supply chain pipeline.
5. Grow the local energy industry in the priority regions.
6. Increase energy sector trade and investment opportunities between Mexico and the UK.
7. Improve regulator agencies’ performance and accountability to align with international standards.
8. Support domestic legislation to achieve international climate change commitments.
The planned indicators are specific and relevant at each level, including gender disaggregation for both individuals and SME ownership. The Energy MREL plan includes a data quality and data management plan. Once final indicators are identified, the strand supplier commits to review each of them against these quality and management criteria.
Factors positioning the strand to achieve
One factor that predisposes the Energy strand to achieve its primary objectives is the rigour that it has demonstrated in basing its designs in evidence. Since the OBC drafting stage, the PF Energy strand PT has reinforced its analysis of the energy market and how it links particularly to labour, inclusion and poverty reduction through commissioned reports (2017–2018). The strand supplier has just begun two industrial baseline studies (IBSs) to further refine the interventions associated with the Energy strand[36].
[36] An Oil and Gas IBS focused on suppliers in the oil and gas sector located in the priority states that will be served by the Oil and Gas Hub (Tabasco, Campeche and Veracruz); and a Clean/Renewable Energy IBS focused on suppliers operating in clean and renewable energy supply chains located in the priority states that will be served by the Clean Energy Hub (Jalisco and Aguascalientes, with the potential for increased regional scope).
One factor which supports the positioning of the strand is the Energy strand PT’s refinement of the strand’s narrative to emphasise the capacity of growth and distribution to the Mexican people, with its objectives to build Mexico’s energy-sector labour force; increase the national content into the supply chain through better trained and better connected SMEs; and improve the quality and implementation of regulations and standards.
 “If you support women, you support families. If you support families, you support children.”
Energy Strand Supplier KII
Designing for inclusive growth
The PF Energy strand programme team and the strand supplier agreed that the primary benefits of inclusive economic growth and, less directly, reduced poverty will focus on the individual, institutional and regulatory levels. The strand design seeks to bring women and men into programme training, including apprenticeships, develop industry-recognized skills and improve both their employability and earnings potential.
In addition to the IBSs noted above, the PF is finalising an analysis of women in Mexico’s energy sector labour force to test assumptions made within the strand’s design related to inclusive economic growth and poverty reduction. The strand supplier is fielding a wide-ranging survey from a pool of 700 SMEs across Mexico which will generate baseline information, including gender and inclusion (G&I) metrics. First drafts of these evidential studies are due in late June, and are expected to further refine the inclusive growth dimension of the strand’s interventions.
Deterrents and mitigation
The likelihood of managing rapidly changing energy policies well lies in the strand’s strategy to engage at the federal and state levels. On the one hand, the strand supplier has developed interventions which align with current federal government announcements to facilitate programme engagement. The Energy teams complement that positioning by identifying work with support of local government or specific federal institutions.
DAI takes a “Do No Harm” approach to programme engagement across its stakeholders and programme environments which include commitments and procedures to mitigate against the following: (i) the backlash against women that can occur when women’s agency and access are increased; (ii) increasing tensions during indigenous consultation and planning and approval of vast renewable projects; and (iii) the violence related to non-state actors which include not only narcotics actors but also broader networks and vested interests.
## Strand guidance, governance and management
This sub-section answers the following EQs:
- EQ8a. How well do PF institutional governance structures operate and to what extent have they helped or hindered in the design phase of the programme or strands?
- EQ8b. What recommendations for improvement are there from both E&L and the PT?
- EQ9. What types of programmes, approaches and governance and management arrangements have been more or less effective for achieving results and demonstrate good approaches to supporting inclusive growth and VfM?
In addition to the governance and management bodies of the bilateral programme (see Section 5), the strand supplier has a series of management structures to guide strand development and delivery. Early indications are that the Central Delivery Unit (CDU) and the strand’s consortium members have been an asset to the redesign of the strand’s ToC and in facilitating stakeholder conversations to position the strand during the inception phase.
Virtual Teams. The Energy strand programme team has valued the input and guidance of its VT since the earliest days in 2017 of the OBC design. Comprised of DIT, and FCO’s Global Issues and Political sections, the PF Energy team noted that the VT supported three separate designs of the strand as time passed and priorities evolved. The VT continue to facilitate communications to government and private sector stakeholders, which has proved critical for engagement with the Ministry of Energy.
Strand Governance Board (SGB). The details of the Energy SGB is still in the design process with the composition of the SGB and the frequency of its meetings yet to be determined at the time of this evaluation.
In addition to the formal governance systems noted above and in the main body of this evaluation report, there is a human dimension to the Energy strand’s governance and management systems. This is the genuine respect that the PT and the suppliers have for one another’s capacities and roles combined with the shared understanding of the goals of the strand. This shared understanding frames all discussions, planning and strategic decision-making by both teams and was apparent during the key informant interviews (KIIs) held in late April.
This relationship has helped the Energy strand teams navigate early challenges, including contract terms and conditions around payment schedules and the final branding and location of the CDU/Centre.
The PF Energy strand PT anticipates an important flow of inception milestone documents for which they seek support from London. The PT notes that a thorough review of the annual work plan, updated regional strategy, gender strategy and climate resilience strategy from a central perspective may be beneficial. The caveat to this review would be that timeliness of the comments will drive the utility of the review.
## Thematic analysis
Gender and inclusion
This section responds to the following EQs:
- EQ9.2. Which approaches, governance and management arrangements have been adopted in relation to G&I?
- EQ10. To what extent have PF interventions contributed to results that support gender and equality, women’s economic empowerment and social inclusion?
Programme Design
The Energy strand design incorporates gender and inclusion as a transversal element, “getting women engaged at all levels.”[37] Gender and social inclusion have been well articulated as evidenced in the strand supplier’s proposal, Call-Off Contract and early designs, including its milestone document 2.1, Agreed Plan for MREL Engagement and Compliance. The inclusion of vulnerable or marginalised individuals or communities is reflected in the first of its eight impacts: Increase income of people living in the lowest or middle quintiles in the hub’s two regions of influence. The indicator for this objective will be finalised in September prior to the strand’s transition to the implementation phase.
[37] KII with strand supplier, 25 April 2019.
Internal Capability/Institutional Incentives
DAI uses an internal model, called “Voice, Choice, and Control” (VCC), to identify and address inequalities in specific programming contexts to achieve gender and social inclusion, which were key components to its bid.[38] The five-stage VCC methodology includes the following:
[38] DAI has used the VCC model in other programmes around the world, including the PF Mexico Financial Services for which it also holds the lead.
1. Identifying key stakeholders to assess existing G&I policies and practices
2. Updating G&I analysis to confirm our understanding of the challenges to jobs and supply chain opportunities that exist for Mexican women at federal and state level and impact their productivity and resilience
3. Developing a G&I strategy in terms of methodologies, activities, and results
4. Ensuring that the team is accountable for delivering the strategy by integrating G&I into the monitoring framework, key performance indicators (KPIs) and staff terms of reference (TORs)
5. Communicating our approach to partners and stakeholders, ensuring that the strategy provides clear guidance for all.
From an incentives perspective, in a KII in April 2019, the strand supplier told evaluators that it has built gender equity into its administrative and management practices. These actions include: equal pay for equal work within the staff structure; senior strand leadership divided among women and men; planning interventions which account for the environmental, health and safety requirements of women and vulnerable groups; and planning communications and outreach strategies designed to reach women who are in, or could be recruited to, Mexico’s energy labour force. The ratio of senior experts in the CDU is observable and bear out this statement, however, the evaluation team did not have access to budgets which would support the “equal pay for equal work” claim.
Financial resources
The VfM assessment (See Section 6.2 in the main report) notes that the Energy strand shows a clear link with inclusive growth, with four of the five main activities demonstrating this, and gave a score of 4 out of 5 for this criterion. The five interventions planned by the Energy strand supplier as evidenced in its MREL plan include: SME training and certification; occupational skills development; technical and vocational education and training (TVET) and academic institution partnerships; an apprentice programme; and training for regulators. With the exception of the TVET and academic partnerships, each of the other interventions include a gender and/or social inclusion element. Therefore, it can be safely assumed that the strand supplier will commit financial resources to G&I to fulfil its programme objectives and those of the PF. A triangulation of this assumption will not be possible until October 2019 when the strand supplier is due to finalise and submit its costed Year 1 implementation work plan.
Accountability mechanisms
The team plans to disaggregate 59% of primary indicators according to the April 2019 logframe (see Table 15 overleaf). Baselines for these data are forthcoming when inception milestones are due from the strand suppliers in the early autumn. There is an opportunity for the Energy strand to reinforce its accountability mechanisms in the context of social inclusion and articulate indicators which reflect social inclusion of marginalised or vulnerable populations as already identified in its impact statement noted above.
Table 15: Primary Energy indicators disaggregated by gender
Level of Impact	# of Primary Indicators	# of Indicators Disaggregated by Gender
3 Outcomes	14	11
3 Intermediate Outcomes	11	5
8 Outputs	19	10

There is evidence that the strand supplier will hold itself accountable to good G&I practices, as it has identified three challenges it must ensure inclusive participation. First, women must have a safe environment that permits appropriate conditions, which means addressing issues such as sexual harassment in the work place. Second, women must be aware of the programme opportunities across the sector. Third, the programme must ensure that women get trained and certified. In its strand design and engagement plans, these challenges are being addressed as seen in the Stakeholder and Community Engagement Plan and its emerging Gender and Inclusion Strategy and Action Plan.
These challenges are likely to apply to marginalised or vulnerable individuals who are end beneficiaries of the strand’s interventions. An expansion of the strand’s analysis to reflect how the interventions will address these challenges for the marginalised population is recommended.
Partnerships
The strand supplier has built a senior management team with strong G&I expertise and national credibility that is supported by a strong consortium (See Annex 12) and resource pool. The two CDU regional hubs are designed to strengthen local and sub-sector specific partnerships that further advance the reach and delivery of the strand’s interventions. Stakeholders, partners and outreach will be finalised in September as the strand prepares to transition to the implementation phase which begins in November 2019.
The strand governance board is another mechanism by which the Energy strand will build partnerships that support and improve the overall delivery of its interventions. (See Section 4 in the main report).
A comparative analysis of the programme’s G&I status is found in Section 6.1 of this report.
Value for Money
This section responds to the following EQs:
- EQ4. What evidence is there that the changes supported by PF interventions will be sustainable and ensure environmental sustainability, will be self-financing and lead to inclusive growth that reduces inequality?
- EQ9.1. Which approaches, governance and management arrangements have been adopted in relation to VfM?
Following a rigorous selection process using the Most Advantageous Economic Tender criteria, a DAI, Europe Ltd-led consortium won delivery for Energy[39]. The PF Energy strand programme team note that DAI’s bid brought added value to the strand design and had internalized the goals of the strand and programme. The bid also offered a superior G&I platform for both programming and management.
[39] DAI UK also won the PF Mexico Financial Services strand in a separate and distinct bid.
Intervention sustainability
The Energy strand has several mechanisms to be sustainable beyond PF timelines:
1. Capacity-building of regulators, by which standards will be embedded into standard government practices.
2. Strategical alliances with UK and Mexican academic institutions which could build in skills training into their on-going curricula.
3. Tested apprenticeship programmes which could be adopted by big companies in Mexico and abroad as part of their own human resource development practice.
4. Creation of an independent Centre intended as a place of “common ground where information, ideas and actions related to energy can be found and networks developed[40].”
  [40] Energy strand supplier KII, 25 April 2019.
This fourth sustainability element, the Centre, will serve initially as the supplier’s CDU. The CDU/Centre will have three locations: Mexico City to engage central stakeholders and the PF team; Tabasco to anchor engagements with the oil and gas sector, focusing on certification of environmental, health and safety specifications; and Jalisco to anchor the renewable energy activities.
The strand supplier engaged resource pool partner, Ogilvy Mexico, to develop the Centre’s brand through a complex, sequenced process. By early August 2019, the branded CDU/Centre will launch in Mexico City, followed by hub launches in Tabasco and Jalisco.
The long-term aim is that the branded Centre will become independent of the PF, DAI and the government, able to self-finance through fees for activities and subscriptions to proprietary databases of SMEs and other information. The Centre’s sustainability is likely measurable only after the PF programme concludes, although early trends in years three and four may provide some indication.
An example of the fee for information which may support the Centre over time comes from the strand activity to train female- and male-led SMEs to improve their market offers to both oil & gas as well as renewable energy projects. As SMEs are certified, the strand supplier plans to create a database of these national providers. This database will be marketed to larger companies looking to boost the national content in their energy project bids in the future.
A comparative analysis of the programme’s VfM is found in Section 6.2 in the main evaluation report and Annex 8.
## Secondary Benefits
This section addresses the specific sub-questions for SBs set out in the Approach Paper:
- What factors were taken into account to make decisions on the balance and focus of the programme in terms of primary and secondary benefits?
- How has the programme team incorporated SBs into programme and strand designs? Are these adequately defined in programme documentation, including in supplier designs?
- To what extent does the PT have the necessary capacity to monitor and measure SBs?
What factors were taken into account to make decisions on the balance and focus of the programme in terms of primary and secondary benefits?
The business case (BC) makes a compelling argument for the programme delivering primary benefits, citing energy’s role as Mexico’s highest value sector and the scope for increased production to provide significant resources to develop infrastructure and reduce poverty. The advent of the new administration brought a change in government focus for the sector, emphasising the need for local benefits. The Embassy has responded by highlighting the potential of the Energy strand to contribute to this goal, to the extent that it supports development of Mexican SMEs and workers in the sector.
There is also clear potential for the Energy strand to achieve significant amounts of SBs. Interviews with the strand and supplier team for Cycle 1 suggest that the most likely areas of benefits will be in the oil & gas sector, including professional services, training and consultancy, specialist energy services, re-insurance and improved opportunities for overseas direct investment (ODI).
What mechanisms within strand governance and management are in place to potentially identify and deliver SBs?
While there are good mechanisms and resources in place to help achieve SBs, the strand would benefit from a clearer articulation of how these will be delivered through the course of implementation. Positive factors that will support SBs include:
- Clear identification of UK target markets. The Energy strand programme team identifies key targets including trainers and skills providers, and consultancies (for both skills and regulation). It has also commissioned studies which will contribute to identifying commercial opportunities for UK firms (covering electrical networks and energy storage markets, and mapping the wind energy supply chain).
- Close alignment with DIT objectives and work plans. DIT Mexico has High Value Opportunity campaigns (HVCs) in both oil & gas and renewable energy, which align with the strand’s work.
- A dedicated DIT team member who supports the delivery of SBs in the strand, and also coordinates delivery of SB activities across the programme.
- A mechanism for coordinating and sharing information with other embassy teams. The existing Energy VT provides a good mechanism for ensuring coordination and knowledge-sharing across DIT, policy and programme staff (and by extension with the strand supplier). This is likely to be important for maximising opportunities from DIT’s work, and also for creating synergies between the PF Mexico Programme and other Embassy-managed programmes (PF skills and infrastructure programmes, ICF, Newton Fund). It should also enable links with UK-based DIT resources (e.g. DIT’s recently recruited renewable energy coordinator).
- An Energy Prosperity Sector Plan, which includes details on how different embassy activities will be implemented through the financial year to support achievement of SBs
- A regular cross-strand SB meeting in which suppliers can discuss SB issues with the PT and each other.
There is however a need to define more clearly how SBs will be achieved as implementation of the strand progresses. While the Energy Prosperity Sector Plan provides a good starting point it provides primarily a list of activities to be implemented throughout the year, rather than an analysis of what SB opportunities will arise from PF activity, and how activities can be delivered to realise these in practice. It is therefore suggested that further planning work is undertaken which explicitly:
- Assesses which SBs can realistically be delivered at different stages of implementation. For example, while some, such as consultancy, may be realised relatively early, others, such as delivery of skills training programmes, will only be possible once a certain amount of progress has been made (e.g. they will depend on the Centre being up and running, etc.)
- Links the activities to be carried out by DIT to specific SB opportunities
- Describes the supporting role that the supplier might play in delivering these opportunities, taking into account that this role can only be part of their work to deliver primary benefits (because of restrictions on what ODA funding can be used for)
- Summarises how achievement or otherwise of these SBs will be monitored by DIT.
- Considers how these things can be achieved through the course of the PF programme, not just during the forthcoming year (which is the timescale addressed by each Prosperity Sector Plan).
This does not necessarily need to be a long document, and should build on existing work including the existing Secondary Benefits Plan and the Prosperity Sector Plans and impact pies.
To what extent are suppliers’ emerging implementation plans aligned to the PF designs to deliver both primary and secondary benefits in a complementary way?
Overall, there is good evidence that the strand has a coherent approach for delivering SBs, and is organising its work to achieve these.
The supplier (DAI) is in regular discussion with DIT about SBs, and illustrated good awareness of UK skills strengths and therefore likely opportunities.
DAI’s bid also outlined a credible mechanism for delivering SBs while working to achieve primary benefits – i.e. the Centre, which the supplier contract says will work to match opportunities in Mexico with UK companies. As part of its work as the supplier, DAI has commissioned initial studies on how UK skills map with gaps in Mexico’s capabilities in upstream and downstream oil and gas activities. This provides evidence of serious early work by the supplier to start to identify SB opportunities, as do initial discussions with academic institutions and industrial actors on the renewable energy side.
The resource partners (Robert Gordon University, OPITO, Vivid Economics and the former DIT adviser mentioned in its bid) should also strengthen the strand’s capacity to deliver SBs, to the extent that they can be mobilised to do this while delivering primary objectives.
## Challenges and lessons
This section responds to the following EQs:
- EQ11. How is the PF learning and why is action on this learning happening more or less successfully?
- EQ12. Which PF lessons in translating outputs into intermediate outcomes are sufficiently robust for wider learning?
This section explores the challenges that the strand PT has faced and the lessons it has learned as it responded to those challenges. Some challenges also have recommendations from the evaluators associated with them. Recommendations are found in the following section.
Challenges internal to the Prosperity Fund
The primary challenges within the PF relate to timely, fulsome guidance from the JFU, which are discussed in the main body of this report (see Section 5).
Challenges within the strand
Sector policy pending. During the April KIIs, the PF Energy strand PT and the strand suppliers noted that they were awaiting Mexico’s NDP, released 27 April 2019, to finalise the strand’s design. Ancillary policies related to energy – both for oil and gas as well as renewable energy – are expected to emerge now that the NDP has been published. The strand supplier delivered a Stakeholder and Community Engagement Plan[41] which provides a clear and deliberative pathway for engaging government officials and other stakeholders and taps into the networks of both the UK Embassy as well as those of the supplier consortium.
[41] Milestone deliverable 1.1
Federal vs. state action. The oil and gas sector interventions will be driven by federal government priorities and actors in light of the emphasis on national content. There is greater policy movement potential in the renewable energy sector. To respond to this, the CDU will have two hubs: one in Jalisco, to take advantage of renewable energy interests in that region, and one in Tabasco, to anchor the interventions in the oil and gas sector. The IBS will further inform the strategies best used for strand delivery.
Team gap. The strand supplier quickly identified one of the consortium partners to be unequal to its commitments and brought the situation to the attention of the PF Energy strand programme team. Together they identified an organisation present in Mexico which did have the requisite expertise and networks and brought the group into the strand’s consortium. The original sub-contractor has been eliminated from the contract and the milestone was delivered on time. The lesson was that defending a consortium partner that was clearly falling short was not worth the reputational and delivery risk it represented, and that there was no stigma in working to replace the weak link with a more able consortium member.
## Conclusion
The Energy strand is well designed and founded on original research to explore and incorporate the components of inclusive economic growth in the energy sector. There is strong evidence that the intervention will bring women and men into the labour force through the capacity training and apprenticeships. The indicators which will track and measure these changes are due to be finalised in the autumn of 2019.
The strand supplier has made significant commitments to the three thematic areas of G&I, VfM, and SBs. The quality and sustainability of these commitments will be monitored and assessed in subsequent evaluations, but the starting point for each is strong.
## Recommendations
Adopting innovations. The Energy strand features several innovations which might be considered by other PF programmes and their strand managers.
CDU as sustainability element. Utilising the CDU as a platform from which to build self-sustaining sector resources is innovative. While this is not an approach suited to all types of programming, it is one worth considering as the Mexico experiment yields insights.
Cross-strand planning. It was noted previously that the Energy strand and ACROL have a potential overlap when working with rural communities. It is recommended that the two strands collaborate, particularly with communities that have been negatively impacted by previous harmful energy project developments.

Annex 4: Strand evaluation: Financial Services
## Design and positioning
This sections responds to the following evaluation questions (EQs):
- EQ1. What evidence do you see to support the potential of the emerging Theories of Change (ToCs) to reduce poverty and support inclusive economic growth?
- EQ2. How has the strand/programme managed political change to ensure alignment and relevance to position achievement of expected primary benefits?
- EQ5.2. What factors may deter the achievement of primary benefits and what measures have the programme team (PT) taken to mitigate these?
- EQ7. Which assumptions and causal pathways outlined in the ToC remain valid, which have been adapted and what refinements have been made?
Strand design evolution
In the Outline Business Case (OBC), the Prosperity Fund (PF) Financial Services strand PT presented several challenges which prevent the sector from reaching its development potential, such as lack of access from base-of-the-pyramid and women, regulatory uncertainty, lack of innovation and lack of understanding of financial mechanisms and products.[42] The Financial Services strand's designed impact for a “more inclusive and competitive financial services sector, accessible to all segments of Mexican society and new market entrants” has remained constant since its initial articulation and is supported by three outcomes:
[42] The SoR ToC was used for this evaluation. See Annex E, Page 78.
1. More financially literate male and female consumers who feel greater trust in Financial Services institutions and have the ability to use formal financial services.
2. Supportive regulatory environment for the fintech sector that works both for men and women.
3. Increased number of micro, small and medium enterprises (MSMEs) procuring fintech solutions that provide financing alternatives and allowing for more accessible cashless transactions for men and women.
A clear pathway is observed from outputs to impact – more financial inclusion, better regulation and more and better fintech solutions would directly overcome some of the challenges and lead to more inclusive and competitive financial services. There is a caveat to this causal pathway, however. Sector evidence clearly shows that poverty reduction is not always a direct result of a stronger inclusive financial system. Indeed, the opposite could also happen when there are predatory practices and uneducated consumers. The Financial Services teams have demonstrated attention to this fact and note that they are pushing for interventions that incentivise the use of financial services to increase income, productivity and education, rather than consumerism[43].
[43] KIIs on 24 and 25 April 2019
There is evidence that backs up the relationship with the development of the financial sector and positive economic growth and poverty reduction. For example, an Asian Development Bank report identified that economic growth and financial sector development in high and upper-middle-income economies, such as Mexico, offer a positive backdrop that can enhance financial inclusion and poverty reduction. This is because higher income countries tend to have stronger institutions that can support financial inclusion, such as larger banks, a financial regulatory system or funded fintech start-ups, and the general economic conditions of the countries empower people to use access to finance for productive activities or to invest on education.[44]
[44] Cyn-Young Park and Rogelio V. Mercado, Jr, “Financial Inclusion: New Measurement and Cross-Country Impact Assessment”, ADB Economics Working Paper Series, No 539, March 2018
The Financial Services strand is the only one of the four Mexico strands that is sampled for family review in this first cycle of evaluations. The Financial Services outcomes relate to the following UN Sustainable Development Goals (SDGs):
- SDG 1 – End poverty in all its forms everywhere
- SDG 5 – Achieve gender equality and empower all women and girls
- SDG 10 – Reduce inequality within and among countries.
Factors driving design refinements
During the design of the SoRs, the Financial Services strand PT, in conjunction with the virtual teams (VTs), met with key actors of the three major political parties before the elections, to hear their priorities and engage them with the Financial Services proposals. The strand design underwent modifications to adapt to the new political situation and become more efficient.
The three interventions, as presented in the SoRs, have pathways towards the Financial Services strand outcomes and inclusive growth and poverty alleviation, under specific circumstances. Interventions 1 and 2 of the Financial Services strand had their origins in the previous 2017–2018 PF and were considered as a continuation and scale-up of that work. Meanwhile, the third intervention is completely new.
All the assumptions from the original ToC are still valid. New assumptions have been added by the supplier at the output level to specify the involvement of external parties (both from public and private sector) with the interventions[45].
[45] When asked in the KIIs about output level assumptions, the supplier mentioned that they didn´t have them but they would include them, as a result of the question. A couple of days afterwards, they sent the new ToC with the output-level assumptions included.
The Call-Off Contract with the Financial Services strand supplier includes the same ToC presented in the SoRs and in the supplier’s bid. Since the inception phase began, the strand supplier has proposed changes to outputs in the logframe, which are under review by the PF Financial Services team[46].
[46] The final draft of the FS logframe is due 7 June 2019; with final versions due 2 August 2019.
Intervention 1 was originally planned to include supporting actions to continue the work from the previous PF to help the transition from closed loop to open loop bank accounts for Prospera[47] beneficiaries with a training and behavioural component. The new rules of operation for the Prospera were announced in early March, but in the interim, the Financial Services teams adapted the output to focus on the financial educational component of beneficiaries (mainly women) of future cash-transfer programmes, rather than anchor interventions on a single programme.
[47] One of 8 Government to People transfer programmes for the poor in Mexico, Prospera was the largest. The new administration in December if would overall the programme, citing reasons of abuse and corruption.
During the inception phase, the strand supplier made a substantive change in the output to deliver behavioural and financial education not only to Government to People recipients but to the agencies serving them. The strand supplier has identified that financial inclusion for base-of-the-pyramid and female clients is heavily influenced by the quality of client service and targeted products offered by financial institutions. The objective is that financial institutions regard and treat this population as clients and not as beneficiaries, which should motivate the client base to increase their use of financial services. This change improves the strand design, as it increases the likelihood that individual change based on clients’ financial education combined with changes in institutional perspective of the client base will lead to a more inclusive and competitive financial sector, which in turn is assumed to contribute to inclusive economic growth.
For intervention 3, the supplier also amended an output for greater clarity, which relates to a socially-focused adoption programme for fintech companies. This change clarifies the reach of the intervention. Rather than create a new organisation, the supplier will partner with existing entities to business acceleration or incubation organisations, microfinance institutions, universities or business associations in different states to help fintech firms grow and secure greater market share. This approach avoids duplicating existing initiatives or organisations in the market. The selection of the states and the hosting partners is underway and will be confirmed at the close of the inception phase.
Intervention 3, which includes the acceleration of fintech companies attending male and female users at the base-of-the-pyramid, and MSMEs through the creation of Fintech Innovation Centres (FIC) in selected states, is a good complement to the financial education of individuals in the first intervention. Plans are for FICs to be hosted by business acceleration or incubation organisations, microfinance institutions, university or business associations in the states, and supported by qualified mentors, which will position the supplier with major players of the fintech ecosystem around the country. Intervention 3, being a new intervention with the private sector, was not affected by the changes in the political arena prior to the procurement process.
Factors positioning the strand to achieve
The Mexican government has shown interest on financial inclusion and fintech development and have expressed a willingness to work together with the PF. The Financial Services strand PT and the strand supplier have worked to map and engage the new government actors, especially in the Minister of Wellbeing, the Ministry of Education and the National Savings and Financial Services Bank (known as Bansefi[48]), to assess their priorities[49]. During the implementation phase, there may be private sector investments, mainly from financial institutions, for the training of their personnel in intervention 1 or from private (individual and/or corporate) investments to accelerate fintech firms in intervention 3.
[48] Bansefi is a government bank that holds most of the saving accounts of the cash transfer programmes beneficiaries.
[49] The Stakeholders and Community Engagement Strategy has a comprehensive list of key stakeholders.
Evidence shows that the Financial Services strand is positioned to take advantage of the increased number of cash-transfer programmes the government plans to implement. The government is already interested in migrating from cash to electronic transfers, and was working on that in previous years with the help of the PF. Strand interventions represent an opportunity to promote the access of women, who have been the main recipients of cash transfers, and the-base-of-the-pyramid[50] population to financial services beyond bank accounts.
[50] According to INEGI (2014), about 70 million Mexicans -60% of the population- make less than three minimum wages a day (approximately $13), with the average salary in rural areas being 3 to 4 times less than that of urban areas in Mexico. And only 36.9% of adults 15+ in Mexico own a bank account. (Global Financial Inclusion Index, World Bank, 2018).
There is clear evidence that UK expertise, particularly with open banking standards, regulatory sandboxes and SupTech/RegTech[51], strengthens the PF Financial Services strand’s positioning with Mexican counterparts. The strand supplier is leveraging UK and VT strengths to engage relevant UK actors such as the Financial Conduct Authority, responsible for regulating financial institutions and overseeing fintech regulation and consumer protection, and the Open Banking Implementing Entity, which leads on developing standards and regulation for open banking in the UK.
[51] Regtech refers to applications of innovative technologies that support compliance with regulatory and reporting requirements by regulated financial institutions. Suptech refers to technologies used by supervisory agencies themselves.
The strand design provides an opportunity to create a broad stakeholder set which includes universities, business associations (e.g. Mexican Fintech Association), and other invested parties which complement the government, financial sector institutions and clients. Collaborating with a broader base of stakeholders increases the likelihood that the strand’s interventions will gain support from multiple actors in the financial services sector.
Designing for inclusive growth
Inclusive growth has been factored into all layers of the planned Financial Services strand, from outputs to impact. The Financial Services strand aims to empower women and base-of-the-pyramid individuals to increase their financial independence by addressing the challenges they face in accessing financial services. Evidence suggests that women and marginalised individuals who receive financial education will result in financially literate consumers who trust and use financial services such as digital transfers, digital services payments, personal credits or investments.
For the regulatory interventions, the impact on inclusive growth and poverty reduction is indirect, but the output is intended to help set the framework for the development of the fintech sector in Mexico. An improved regulatory environment is intended to support the progress of the Financial Services strand’s other two outcomes.
The newest outcome, Intervention #3, relates to a socially focused accelerator programme intended to support inclusive growth by overcoming challenges to financial inclusion related to distances to financial institutions, fear of technology and lack of electronic payments, cash transfer or access to credit. The intervention’s focus on developing fintech apps will likely reduce the transaction costs of remittances, which could have a direct impact on those who are at the base of the economic pyramid in Mexico.
Deterrents and mitigation
The Financial Services strand PT and the strand supplier must remain vigilant in supervising the design of services and products to help turn financial inclusion in income-generating activities and human capital creation, as contracting excessive debt and using credit only for consumption could worsen poverty.
The strand supplier has already had several strategic meetings, including with the person in charge of the eight main cash transfer programmes at the Ministry of Wellbeing. The decision of which transfers programs to work with is still underway at the time of this evaluation. Nevertheless, the Financial Services teams continue working to engage private financial institutions, such as Bancomer and Santander, and create partnerships with finance and microfinance groups and organizations. The strand supplier has finished working on the criteria to select the states to begin intervention 1.
However, some delays may be expected, due to the change of government, in the publication of the new fintech regulation, as some of the major positions inside the National Banking and Securities Commission (CNBV[52]) have yet to be filled.
[52] Comisión Nacional Bancaria y de Valores
## Strand guidance, governance and management
This sub-section responds to the following EQs:
- EQ8a. How well do PF institutional governance structures operate and to what extent have they helped or hindered in the design phase of the programme or strands?
- EQ8b. What recommendations for improvement are there from both E&L and the PT?
- EQ9. What types of programmes, approaches and governance and management arrangements have been more or less effective for achieving results and demonstrate good approaches to supporting inclusive growth and VfM?
In addition to the governance and management bodies of the bilateral programme (see Section 5), the strand supplier has a series of management structures to guide strand development and delivery. Early indications are that the Central Delivery Unit (CDU) and the strand’s consortium members have been an asset to the redesign of the strand’s ToC and in facilitating stakeholder conversations to position the strand during the inception phase.
The Call-Off Contract requires the Financial Services strand supplier to form a CDU and a Strand Governance Board (SGB) to ensure coherent, efficient, effective delivery of the strand. The strand supplier also intends to create two guidance groups. It is not possible to evaluate the effectiveness of these bodies in this evaluation cycle.
Strand Governance Board. The SGB is intended to provide strategic oversight and guidance to the strand’s CDU and wider delivery team. The board includes representatives from the CDU, the approved resource pool and the government and stakeholders from beneficiary institutions, private sector, civil society, amongst others. The board will meet once during the inception phase and quarterly for subsequent PF years. The composition of the SGB has already been drafted by the strand supplier and approved by the PF Financial Services team.
Central Delivery Unit. The CDU is responsible for the day-to-day implementation which provide DAI with a resource pool of short-term experts and advisers brought in for specific tasks. In addition, the CDU receives support from the Head Office Team, based in UK, which provides mobilisation, technical, operational (including financial), quality and backstopping support.
Two other strand-specific management bodies are under consideration within the Financial Services strand, although final discussions are required before FCO approval is granted to establish them. These include:
- Open Banking Working Group, which is envisioned to be comprised of key government and private sector stakeholders and will be consulted to achieve buy-in at high levels
- Application Programming Interface (API) Standards Group, which is intended to manage all aspects of the fintech Law and be empowered to deliver API standards[53].
  [53] Open API or Public API is a free-to-use, publicly available application programming interface that provides developers with programmatic access to a proprietary software application.
Learning and adaptation
Both the Financial Services strand PT and the strand supplier have learning and adaptation mechanisms to transform challenges and solutions into lessons learned. The Financial Services strand PT has a lessons learned log, as well as periodical exchange of experiences with other Latin-American countries in regional conferences. The strand supplier plans to use an internal learning hub to share lessons across the supplier team in order to provide feedback loops that help adapt and improve overall programming.
Managing the political landscape. During the inception process, the Financial Services strand PT, the VT and the strand supplier mapped new key government players using their respective networks. The Financial Services teams have since secured appointments with these government principles, listened to their ideas and adapted interventions.
The Financial Services strand VT brings together representatives from the PF (including commercial and communications leads), and Global Issues on the FCO side, DIT teams (trade and inward investment) and representatives from other programmes (ICF) from across the Embassy. The VT has been essential in making sure the UK interests are considered in the Financial Services strand design, as well as in pointing out key political actors and facilitating the strand PT and supplier interactions with them. For example, Global Issues and DIT facilitated the meeting of the Lord Mayor of the City of London with key players across the financial branch of the government, such as the Ministry of Finance and the CNBV. As part of both ODA and complementary non-ODA activities, the VT is currently working on bringing a delegation from the public and private sector to London for UK Fintech Week (April 2019).
Managing the Statement of Requirement to inception phase process. The Financial Services strand PT has learned lessons during the procurement and contracting process, particularly around contract negotiations and oversight. Other challenges relate to the IT firewalls in the Embassy which limit or even prevent some digital communication with external parties.
Managing intra-strand delivery. The supplier has adapted its management style to improve collaboration across the delivery teams for the three interventions, as it seeks to optimise resources and impact. During the inception phase it launched inter-intervention team discussions to promote internal and external information sharing. Most of the internal processes and structures are still under design during the inception phase, nevertheless, through this learning hub, the strand supplier has demonstrated adaptive management and a learning disposition.
## Thematic analysis
Gender and inclusion
This sections responds to the following EQs:
- EQ9.2 Which approaches, governance and management arrangements have been adopted in relation to G&I?
- EQ10. To what extent have the PF interventions contributed to results that support gender and equality, women’s economic empowerment and social inclusion?
Programme design
The Financial Services strand and its interventions are well designed to reach women and Mexico’s base-of-the-pyramid population. The Financial Services strand supplier has clearly articulated gender and social inclusion interventions and associated indicators by which to monitor and report its delivery and progress. The strand supplier is basing the strand’s approach to gender equality on its global best practice developed through delivery of the DFID’s Arab Women’s Enterprise Fund.
Internal capability/institutional incentives
From an internal capacities and institutional incentives perspective, there is evidence that the CDU team has accounted for G&I. The team features experts in G&I, including team members and short-term contractors that have worked with women and base-of-the-pyramid population directly in the field, experts who have done statistical research about gender and finance, and others who have founded groups of women in venture capital.
The strand supplier has brought women into leadership positions and committed to the active support of ethics standards, including safeguarding and sexual harassment training.
The strand supplier, DAI, also holds the contract for the delivery of the Energy strand. The firm has also indicated that it will utilise its signature Voice, Choice and Control (VCC) model to design, deliver and monitor its G&I activities. The five-stage VCC methodology includes the following:
1. Identifying key stakeholders to assess existing G&I policies and practices;
2. Updating G&I analysis to confirm our understanding of the challenges to jobs and supply chain opportunities that exist for Mexican women at federal and state level, impacting their productivity and resilience;
3. Developing a G&I strategy in terms of methodologies, activities, and results;
4. Ensuring that the team is accountable for delivering the strategy by integrating G&I into the monitoring framework, KPIs and staff TORs; and
5. Communicating our approach to partners and stakeholders, ensuring that the strategy provides clear guidance for all.
Financial resources
The VfM assessment for Criterion #8 (Equity) (see Section 6.2 in the main report and Annex 8) highlighted the Financial Services strand’s “aim to deliver ‘transformative change’ against the G&I framework, and this is evident in particular in its intervention on financial education for female beneficiaries of Mexican social development programmes. For this reason, the strand is scored as 5.”
The degree to which the Financial Services strand supplier allocates financial resources to its G&I interventions will be detailed when it submits its costed Year 1 implementation phase work plan in August. Given the centrality of G&I in the overall design of the strand, however, there is a high degree of confidence that the strand budget will reflect a serious allocation, especially in light of the transformative goal the strand has set for itself.
Accountability mechanisms
G&I is transversal in the Financial Services Strand and is observed at all logframe levels. The strand’s indicators, due to be finalised in August, are to be disaggregated by both gender and income quintile wherever relevant and whenever the data is available (see Table 16 below)[54].
[54] According to April 2019 available documentation received from the strand supplier.
Table 16: Primary indicators disaggregated by gender and income quintile
Level of Impact	# Primary Indicators	# Disaggregated by Gender	# Disaggregated by income quintile
1 Impact	3	3	3
3 Outcomes	10	5	5
3 Intermediate Outcomes	11	6	4
6 Outputs	10	8	7

Partnerships
The Financial Services strand supplier has submitted an outline of its G&I strategy. Within the strand supplier’s broader resource pool is the Women’s World Banking which is available to provide gender expertise if there are gaps found within the strand supplier’s internal capacity.
The SGB is another mechanism by which the Financial Services strand will build partnerships that support and improve the overall delivery of its interventions. (See Section 5 in the main report).
A comparative analysis of the programme’s G&I status is found in the Section 6.1 of this report and in Annex 7.
Value for Money
This section responds to the following EQs:
- EQ4 What evidence is there that the changes supported by PF interventions will be sustainable and ensure environmental sustainability, will be self-financing and lead to inclusive growth that reduces inequality?
- EQ 9.1 Which approaches, governance and management arrangements have been adopted in relation to VfM?
Value for Money in procurement
The Financial Services strand was tendered to the firms pre-approved in the Framework in Lot A2 (Finance Trade).”[55] The bids were evaluated using the Most Economically Advantageous Tender. DAI (Europe) Limited won the Financial Services tender. DAI and a separate consortium won the PF Energy bid in Mexico. Holding two strands has already allowed DAI to offer scale economies for programme mobilisation and costs such as with office space.
[55] Adam Smith International, BDO LLP, Cardno Emerging Markets (UK) Ltd, Crown Agents, DAI Europe, Deloitte, EY, KPMG, McKinsey, Nathan Associates, Oliver Wyman, Oxford Policy Management, PA Consulting Services Ltd, Palladium and PwC.
Environmental sustainability
The existing evidence that Financial Services has accounted for environmental sustainability are the references in key documents (OBC, SoRs, Bid and Contract) to the importance of being aware of the possible positive or negative effects of the interventions on the environment and how to promote or mitigate them, respectively. The supplier is expected to deliver an inception milestone document, the Climate and Resilience Strategy and Action Plan, in August.
Intervention sustainability
The Financial Services strand sustainability strategy is based on the adoption of modelled practices by individuals, firms, public institutions and the overall fintech ecosystem. These approaches to sustainability are reflected in the interventions and assumptions built into the ToC.
Individual. Sustainability comes as new clients for financial services and Fintech products, such as personal loans, insurance or money transfers apps, continue to demand these services if/when they see social or economic benefits (time saving, security, consumption smoothening, access to credit or lower transaction cost). An additional element of sustainability comes when these individuals recommend these services to families and friends in their community.
Financial and fintech firms. The supply side of sustainability lies in the financial and fintech institutions as they develop services and products for the base of the pyramid and women; as they understand and comply with the new fintech law and regulations; and, to develop from a corporate perspective. As the market expands and costs of regulatory compliance diminish, these firms will increase their profitability and sustain the products and services offered to the new market segment. Other firms may observe this new market opportunity and compete for the clients where previously they had been either unserved or under-served.
Public institutions. The government engagement with fintech solutions is expected to continue after the PF programme, as far as the benefits of lower transaction cost and improved well-being indicators for the poor (financial inclusion, household income, education, savings and poverty) also continue.
Fin-tech ecosystem. The Financial Services strand interventions intended to create linkages among public institutions, investors and fintech firms will remain after the PF programme. The strand also seeks to collaborate with selected business acceleration organisations, which will host Fintech Innovation Centres (FICs). The strand supplier is planning to use its network to strengthen the FIC linkages in the fintech ecosystem, such as its membership of the Global Accelerator Network and their access to a Mexican network of fintech ecosystem actors, such as Fintech Hub, Finnovista or Orion Startups[56]. The strand supplier plans to develop a pool of qualified providers and qualified mentors for the FICs to support development of fintech products and services that serve the target audience of the PF.
[56] According with their bid, the supplier has extensive experience incentivising, building and managing value-driven partnerships, coalitions and co-investment models to leverage additional funds to further the development impact of its programmes.
A comparative analysis of the programme’s VfM is found in Section 6.2 in the main evaluation report and in Annex 8.
## Secondary Benefits
This section addresses the specific sub-questions for SBs set out in the Approach Paper:
- What factors were taken into account to make decisions on the balance and focus of the programme in terms of primary and secondary benefits?
- How has the PT incorporated SBs into programme and strand designs? Are these adequately defined in programme documentation, including in supplier designs?
- To what extent does the PT have the necessary capacity to monitor and measure SBs?
The programme team and strand supplier expect that
- The first intervention (financial education, to promote financial inclusion) may generate SBs indirectly, for instance, where greater resulting use of bank accounts benefits UK banks operating in Mexico, or by creating opportunities for UK behavioural insights firms.
- The second intervention (technical assistance for fintech regulation, standards and supervisory solutions) may also create opportunities for SBs indirectly, opening a new market for fintech in Mexico and making it attractive to foreign participation, including from UK firms.
- The third intervention (the fintech accelerator programme) may create idirect opportunities for SBs by UK financial institutions and fintech companies. Interventions 2 and 3 may also create supporting SBs for professional services firms.
DIT Mexico mentioned that the embassy’s work has already been influential in encouraging a UK fintech company to establish a presence in Mexico (with a planned £5 million initial investment, counting as ODI). The strand team said that its work has helped to establish the UK as a partner of choice and point of reference for fintech. It noted that officials from the Finance Ministry, Central Bank and Banking and Securities Commission visited London to discuss fintech among other topics and that when the Finance Ministry subsequently had discussions with USAID on fintech it proactively invited UK representatives to the meeting.
What mechanisms within strand governance and management are in place to potentially identify and deliver SBs?
The Financial Services strand PT has a clear view of where SBs might be realised, both in terms of establishing an open market for fintech where UK has strengths and by creating specific opportunities for UK financial services and related firms. There are also good resources and mechanisms available to deliver SBs for this strand, including the following:
- DIT Mexico has dedicated staff who will work to deliver SBs.
- The Embassy’s Financial Services VT provides a good platform for sharing information and coordinating with other staff working in this area.
- DIT High Value Campaigns in financial services are also likely to support achievement of SBs.
- The DIT Inward Investment team also has an element of focus on fintech from an investment perspective. A link with DIT’s financial services team in London and its fintech adviser has already proved helpful, and provides the mechanism to help bridge the gap between opportunities in Mexico and UK firms.
- There is also an overall SB plan for the Mexico PF programme, and a corresponding Financial Services Prosperity Sector Plan and Impact Pie.
Overall, this suggests good governance and management arrangements are in place. Nonetheless, there is a need to define more clearly how SBs will be achieved as implementation of the strand progresses.
The overall Mexico PF programme Secondary Benefits Plan provides a good overall framework, and an outline action plan. The Financial Services Prosperity Sector Plan (updated each year) also provides a good starting point. However, currently, it is primarily a list of activities to be implemented throughout the year, rather than an analysis of what SB opportunities will arise in the course of implementing the strand, matched with how activities to help realise these in practice. It is therefore suggested that further planning work is undertaken which explicitly:
- Assesses which SBs can realistically be delivered at different stages of strand implementation.
- Links the activities to be carried out by DIT to deliver these specific SB opportunities.
- Describes the supporting role that the supplier might play in delivering these opportunities, taking into account that this role can only be part of their work to deliver primary benefits (because of restrictions on what ODA funding can be used for).
- Summarises how achievement of otherwise of these SBs will be monitored by DIT.
- Considers how these things can be achieved through the course of the PF programme, not just during the forthcoming year – which is the timescale addressed by each Prosperity Sector Plan.
To what extent are suppliers’ emerging implementation plans aligned to the PF designs to deliver both primary and secondary benefits in a complementary way?
The resource partners listed in DAI’s bid provide a range of expertise and contacts that suggest very significant potential to support achievement of SBs for the strand, while delivering activities to achieve the strand’s primary goals. This will be greatly facilitated if the supplier team have a good understanding of what SB opportunities might arise at which point in implementation, and in which areas (and therefore underlines the need for a clearer SB plan for the strand as described above). Mechanisms already put in place by the programme team (i.e. the ongoing SB meetings for all suppliers) should also help.
## Challenges and lessons
This section responds to the following EQs:
- EQ11. How is the Prosperity Fund learning and why is action on this learning happening more or less successfully?
- EQ12. Which PF lessons in translating outputs into intermediate outcomes are sufficiently robust for wider learning?
This section explores the challenges that the Financial Services strand PT has faced and the lessons it has learned as it responded to those challenges. Some challenges also have recommendations by the evaluators associated with them. Recommendations are found in the following section.
There have been challenges in the Financial Services strand from design to inception. Some of them translated into lessons learnt while others are in the process of being resolved. Some challenges, mainly the ones related with design and procurement are common across strands and are addressed in the programme analysis sections.
Policy and personnel. The government recently finalised the rules of operation for the main cash transfer programmes related to intervention 1, in March, creating uncertainty about target populations and details of the expected government plans during the initial months of the inception phase. The strand supplier realised that this gap, as it continues to engage with available actors of the ministries and the government financial sector, offers an opportunity to understand the new rules and regulations before their publication.
Prosperity Fund reporting requirements. The strand supplier has noted challenges around elaborating minutes of every meeting and the PF standardised formats for the monthly report, which are not best suited for the inherent dynamism of the inception phase. These formats may be better suited for the implementation phase when there is greater stability in the content being reported.
There is every need for due diligence and several of the strand programme managers have requested additional guidance and training on contract management[57] and oversight so that all parties can balance reporting with delivery obligations, ensuring sufficient compliance to relevant UK legislation and best practice for programmes of this scale and complexity.
[57] A two-day contract management training was held in Mexico City on 22–23 May 2019.
## Conclusion
From design through inception, the Financial Services strand PT has created a strand design with logical pathways to overcome challenges to inclusive economic growth. Previous PF initiatives in Mexico brought evidence, experience and credibility to the current Financial Services strand design. The Financial Services strand programme team and its supplier have demonstrated flexibility and focus as they adapt to government changes.
The current strand design accounts well for the themes of G&I, VfM and SBs. G&I is transversal in the Financial Services strand and is measured in the expected outcomes. Final indicators will show the degree to which this incorporation is consolidated. Sustainability, a component of VfM, is considered throughout the intervention from the individual, to fintech firms, to public institutions and to the general fintech ecosystem. SBs have been factored into the strand design since the earliest OBC and continue to be refined and adapted to best position the strand activities into the new, still evolving, government platforms and policies.
In conclusion, the process is proceeding as planned in spite of some challenes. There is no evidence that the Financial Services strand in its current state requires corrective change.
## Recommendations
Poverty reduction. Sector evidence clearly shows that poverty reduction is not always a direct result of a stronger inclusive financial system. Indeed, the opposite could also happen when there are predatory practices and uneducated consumers. The Financial Services teams should continue to be attentive to this fact and push for interventions that provide incentives for the use of financial services to increase income, productivity and education, rather than consumerism.
Human resources turn-over. The Financial Services strand PT noted that turn-over among key players, both in the PF London operations and in the Mexican government, particularly since late 2018, have impacted the procurement and inception processes. This turn-over creates delays and, importantly, loses important experience and institutional memory. While this is a situation out of the team’s hands, the JFU may consider consolidating future approval processes to reduce the risk that key actors will leave their posts during the interim.
Bid quality. In the Financial Services KIIs it was mentioned that the quality of the bids was not what was expected. The strand PT suggested that, during the framework inclusion process, potential bidders receive training and clear guidance on the procurement processes and the evidentiary details required in each bid. This early investment in framework qualifiers would potentially reduce the time required to vet lower-quality bids across the PF portfolio and improve the quality of bids received globally. Alternatively, a similar process could take place when programmes are presenting their market offers prior to the release of the tenders.

Annex 5: Strand evaluation: Future Cities
## Design and positioning
This section responds to the following evaluation questions (EQs)
- EQ1. What evidence do you see to support the potential of the emerging Theories of Change (ToCs) to reduce poverty and support inclusive economic growth?
- EQ2. How has the strand/programme managed political change to ensure alignment and relevance in order to position achievement of expected primary benefits?
- EQ7. Which assumptions and causal pathways outlined in the ToC remain valid, which have been adapted and what refinements have been made?
The objective of the Future Cities strand is to improve the efficiency of urban development in Mexico’s cities, resulting in safer, resilient and more sustainable mobility services for citizens, particularly women and girls[58]. It comprises two interventions:
[58] The SoR ToC was used for this evaluation. See Annex E, Page 77.
Intervention 1: Work with transport authorities in selected Mexican cities to improve governance, planning and coordination between transport and urban development authorities and deliver urban mobility services that are more inclusive, safer and more sustainable. The experience of Transport for London is a key point of reference.
Intervention 2: Design and deliver pilot projects that support more inclusive, safer and more sustainable urban mobility services in Mexico’s cities, particularly for women and girls. The process of selecting cities that the strand might work with was in progress but not yet complete as this report was being drafted.
Strand design evolution
After a competitive process, PwC was selected as strand supplier along with its resource partners, Steer, World Resources Institute (WRI México), Institute for Transport & Development Policy (ITDP) and C230 Consultores. PwC offered the best combination of experience and time allocated for the programme’s delivery.
During the inception phase the strand supplier has developed working relationships and started to implement the process of selecting city pilots for intervention 2. A short-list of potential cities was developed, contacts made with a range of stakeholders and on this basis five metropolitan areas (Mexico City, Guadalajara, Monterrey, Hermosillo and Queretaro) have been invited to present bids to be included in the strand, based on their own perception of needs.
The strand supplier has also worked on inception milestone documents, including the Stakeholder and Community Engagement Plan, a Draft Gender and Inclusion Mainstreaming Strategy & Action and a Draft Climate and Resilience Strategy and Action Plan. Although not a contracted output, a Secondary Benefits outline strategy and action plan will be produced by the supplier by the end of inception.
There is good evidence that the Future Cities strand has the potential to deliver the intended primary benefits, but the way this will be achieved in practice needs to be further defined in the emerging plans for implementation.
The outline business case (OBC) presents a strong case that mobility issues are key challenges to inclusive economic development. Its diagnosis highlights the negative externalities rapid urbanisation has had in Mexican cities, including the economic losses caused by traffic congestion, diseases associated with air pollution and environmental damage. At the same time, inadequate transport and mobility planning leads to long journeys, exposure to pollutants and inefficient transport, which particularly affect vulnerable populations, including women and girls. As such, the OBC generally provides a strong link between the strand and the Fund’s primary objectives to remove barriers for economic growth and reduce poverty.
In its planning research, the Future Cities strand programme team (PT) found evidence that good mobility planning and projects have a direct impact on access to job opportunities and services, which directly relate to more inclusive economic growth and poverty reduction. The Statements of Requirement (SoRs) refer to the strand ToC and repeat the same impact description, as well as highlighting alignment with Sustainable Development Goal (SDG) 11 (Sustainable Cities and Communities) on the basis that the strand will support access to safe, affordable, accessible and sustainable transportation systems for all, with special attention to vulnerable people, including women and children.
There is a slight disconnect between the OBC and SoRs. The OBC highlights the fact that integrating gender equality in transport projects has demonstrated advantages for the economy in terms of increased return on investment, better access to public services, work and education, improved productivity and better personal well-being for women. However, this is not observed in the other documents.
Factors driving design refinements
There is currently no clarity within the emerging ToC about the specific mechanisms and ways in which the strand interventions will have an impact on poverty reduction. A key reason for this is that, at the time of drafting this report, bids had not yet been received from the city administrations wanting to undertake pilot projects. The supplier team said it will be better able to identify and establish approaches to poverty reduction in the strand once the cities are defined and the interventions to be executed are selected.
While this should contribute to greater clarity in the final design of the logical framework and indicators, it is important that the pathways to achieving inclusive growth and reduced poverty are specified. In particular, it will be important to define the specific disadvantaged groups, and explain how they will benefit from the strand’s interventions.
Political change was identified as an important factor by the Future Cities strand PT after the July 2018 elections, following changes in administration not only at the national level but also in most of the state and municipal and governments of the short-listed cities. To manage this uncertainty the Future Cities strand PT adopted a flexible attitude to respond to changes, and used various channels to communicate with new government actors at different levels. This confirmed broad support across parties and levels of government on the need for better integrated, connected and efficient urban centres.
There is evidence that the strand aligns with broader political priorities, which is an important pre-condition for successful implementation. Although political changes do present a potential risk, the Future Cities strand PT emphasise that political economy analysis at both the federal and local levels indicates that it is not a significant at this stage.
Another factor limiting political risk is the fact that the pilot city (intervention 2) will be endogenously developed by the city administrations themselves, and therefore based on the reality and needs of cities. This should also contribute to ongoing sustainability.
Factors positioning the strand to achieve its objectives
The strand supplier team has engaged extensively with stakeholders to ensure that their views are considered correctly and understood. The strand supplier has also made efforts to build trust relationships with stakeholders of the five cities and manage the landscape of existing programmes, donors and activities in the target cities.
Key elements in undertaking this included developing a detailed Stakeholder & Community Engagement Plan for the inception phase and also appointing a ‘city manager’ from within the supplier team, tasked with following the situation in cities closely, listening carefully, showing a regular presence with the city administration, and leveraging existing PwC, Steer and WRI relationships to increase access to senior stakeholders. This has been helpful generating engagement and rapport in a short timeframe with all cities.
The Future Cities strand held an official launch event with the UK Embassy in April to mark the start of the pilot city application process. This aimed to gather stakeholders together, promote understanding of the application and selection process, and highlight the UK’s experience in the strand’s themes. Both the Future Cities strand PT and strand supplier agree this launch provided a useful opportunity to secure further buy-in from a wide and diverse community of actors from all levels of government.
## Strand guidance, governance and management
This sub-section responds to the following EQs:
- EQ8a. How well do Prosperity Fund (PF) institutional governance structures operate and to what extent have they helped or hindered in the design phase of the programme or strands?
- EQ8b. What recommendations for improvement are there from both Evaluation and Learning (E&L) and the PT?
Discussions with the Future Cities strand PT and strand supplier identified a high degree of coordination between the two, good alignment between the programme and strand objectives and coordination in the early work of the supplier to implement these. The strand supplier recognises that coordination and engagement with the Future Cities strand PT has been very effective in developing the implementation approach in the start-up phase. For its part, the PT also expressed faith in the work trajectory of the supplier, based on trust and good communication. Finally, both teams were able to articulate a common understanding of the programme and its different lines of action.
There is also good evidence that appropriate governance structures have been established to oversee the work of the strand, including regular meetings with the PT monthly meetings of the PT’s Programme Management Committee, and a strand governance board (SGB).
There is also evidence that the strand supplier has designed and deployed clear and accountable operational approaches with transparent governance structures, ways of working, communication channels, risk and reporting procedures and processes for results and performance management.
The strand is being delivered by an alliance of companies that have previously worked together, allowing the strand supplier to make an efficient start. PwC has established an operational structure with a senior management team based in Mexico City, with some programme operations managed from the UK. The senior management team includes:
- The programme director who has overseen inception activities from the UK but has also been present for key activities and a team leader who leads the supplier team in Mexico. Both have a long previous experience of working together on issues of cities, transportation and urbanization, and this has been a significant help in developing key relationships, engaging with city officials and managing stakeholders during the inception phase.
- A technical director based in Mexico City who has responsibility to ensure interventions will deliver the desired outcomes from a technical point of view.
During the implementation phase the strand supplier will have a delivery team (including a cities manager for each project location, a gender and inclusion (G&I) manager, a climate and environment manager, a Secondary Benefits (SBs) manager, an agile programming funds (APF) manager and a programme officer). There will also be an operations team covering communications, finance and procurement and monitoring, reporting, evaluation and learning (MREL). The senior management team technical and operational leads meet weekly and the whole team meets on a monthly basis to review progress and assess risks.
## Thematic analysis
Gender and inclusion
This sub-section responds to the following EQs:
- EQ9.2 Which approaches, governance and management arrangements have been adopted in relation to G&I?
- EQ10. To what extent have PF interventions contributed to results that support gender and equality, women’s economic empowerment and social inclusion?
Programme Design
The strand design in the SoR does account for the inclusion of other marginalised or vulnerable groups, through its reference of SDG 11 (Sustainable Cities and Communities) on the basis that the strand will support access to safe, affordable, accessible and sustainable transportation systems for all, with special attention to vulnerable people, including women and children.
In its bid, the strand supplier highlighted the ambition for the strand to bring about transformative change by addressing power relations and helping eliminate systemic challenges that prevent women participating and benefitting fully from economic activity. What is evidenced is that the strand has been designed to incorporate a gender-sensitive approach in two ways: (i) through a transversal approach, cutting across the design of the strand as a whole and (ii) as a specific result of interventions during implementation. This is in line with the specification in the ToC that the two interventions should give priority to solutions for women and girls.
However, the emerging designs and monitoring systems for social inclusion are less robust than for gender due to previous guidance from the centre. As the pilot cities submit their proposals, there is an opportunity for the Future Cities strand PT and the strand supplier to build up the social inclusion element in their strategy to complement the extensive G&I that has already been incorporated.
Internal capability/institutional incentives
Evidence from inception work so far illustrates that a gender perspective is indeed being integrated throughout the strand. The appointment by the strand supplier of a gender champion ensured expert technical support[59]. The champion led the development of the Gender and Inclusion Strategy and Action Plan Outline which:
[59] In KIIs on April 24 and 25, both PF FC team and the strand suppliers noted this point.
- Provides general guidelines on how G&I issues should be integrated into work including during the selection of the city pilots.
- Requires that G&I activities are included and aligned within the updated Regional Strategy, the Climate Resilience Strategy and Action Plan and the Stakeholder Management Plan.
- Requires the views of marginal groups, including women and girls, indigenous people and young people to be included in strand design and implementation.
The strand supplier conducts internal training on issues such as the concept of gender, the impact of gender-differentiated mobility, the importance of language, etc. to strengthen the skills of its Central Delivery Unit (CDU) team.
Financial resources
The Value for Money (VfM) assessment for criterion 8 (Equity) (see Section 6.2 in the main report and Annex 8) for Future Cities notes that the specific criteria for assessing inclusion still need to be defined for the second intervention (city pilots), as the cities had not yet decided on their respective focus at the time of writing this report. Nonetheless, guidance from the Future Cities strand PT made it clear that there should be a clear focus on promoting gender-sensitive and inclusive growth.
While there can be little doubt that gender inclusion will be reflected in the costed work plan, there is some degree of uncertainty as to the degree to which social inclusion will be reflected. This will become clearer once the Future Cities strand supplier allocates financial resources to its G&I interventions when it submits its costed Cycle 1 implementation phase work plan in August.
Accountability mechanisms
The Future Cities strand PT has been consistently clear about the need to ensure opportunities for women's participation in all the processes of the programme, and the need for a gender perspective to be considered in design, delivery and monitoring. There are however three ways in which this could be further strengthened.
1. The outputs in the ToC for Intervention 2 clearly states that pilots must have a specific impact on women and girls. However, this is not the case for Intervention 1, where the link between the integrated transport strategies outputs and the impact on women and girls is not explained. This should be addressed before finalising implementation plans.
2. Specific indicators, perhaps drawn from SDG 11 sub-indicators, related to social inclusion of vulnerable or marginalised groups should be included and/or the existing gender-based indicators should also include a disaggregation that relates to social inclusion.
Partnerships
The Future Cities strand PT and the strand suppliers are building partnerships that complement the strand alliance[60] and its resource pool. When drawing up the criteria for selecting cities, for example, there is evidence that the strand will assess the degree to which city bids demonstrate strong participation by civil society, business and academic institutions. These criteria assume that these actors can help sustain pressure on authorities to continue with their interventions even in the case of political changes.
[60] See Annex 11 of this evaluation report.
The SGB is another mechanism by which the Future Cities strand will build partnerships that support and improve the overall delivery of strand interventions (see Section 5).
A comparative analysis of the programme’s G&I status is found in Section 6.1 and in Annex 7.
Value for Money
This sub-section responds to the following EQs:
- EQ4 What evidence is there that the changes supported by PF interventions will be sustainable and ensure environmental sustainability, will be self-financing and lead to inclusive growth that reduces inequality?
- EQ 9.1 Which approaches, governance and management arrangements have been adopted in relation to VfM?
The principal tool to assess these EQs is the analysis of VfM scorecard results. This focused in Cycle 1 on assessing the extent to which strand design and implementation plans are set up in ways likely to lead to VfM being achieved over time. The overall scorecard score for the Future Cities strand is 4 – indicating there is currently good evidence to expect this. Actual achievement of VfM for the strand will be assessed in future cycles.
Sustainability
This section assesses the sustainability of the strand, both in terms of environmental sustainability, and project sustainability, i.e. whether activities are likely to be continued after the strand has been implemented. These correspond to the sub-questions for EQ4.
Environmental sustainability
There is very good evidence that environmental sustainability has been integrated throughout the strand design. Both interventions are informed by the principles of Transit Oriented Development, which aim to promote high density urban models complemented by efficient and sustainable public transport systems. Both the Future Cities strand PT and the suppliers provided a compelling explanation that a defining feature of the strand is that it embodies a broad concept of sustainability that focuses not only on reduced carbon emissions, but also considers poverty and social inclusion considerations. Under this concept, sustainable urban mobility and unified transport services promoted by the strand will improve access in particular for people living in poor and peripheral areas of the participating cities, as well as addressing climate change and resilience issues.
There are already good examples of this being put into practice, including for instance incorporating technical assistance through the figure of a ‘champion’ to develop climate change impact strategies, including the "Climate and Resilience Strategy and Action Plan" which was in preparation at the time of drafting this report.
Project sustainability
Both the Future Cities strand programme and supply teams highlighted project sustainability as a challenge for the strand. They noted in particular that municipal presidents are elected every three years in Mexico, and therefore it is important for the strand to develop strategies that ensure the continuity of the interventions. Discussions with the Future Cities strand PT illustrate that detailed consideration has been given to this issue, and to practical measures that can help to ensure project sustainability over time. Specific issues mentioned included the following:
- Ensuring that relevant government officials participate in meetings and workshops throughout the inception phase.
- Paying special attention when deciding the final list of participating cities to the level of commitment demonstrated in the cities' applications, in relation to
1. willingness to provide funding to for post-pilot larger-scale projects;
2. the potential for proposals to have a lasting and sustainable impact; and
3. the potential for the pilots to be replicated in other areas.
- Taking into account whether city bids demonstrate strong participation by civil society, business and academic institutions, based on the assumption that these actors can help sustain pressure on authorities even in the case of political changes (e.g. new municipal presidents).
- Each city’s bid must also be accompanied by a letter of commitment signed by different levels of government, with this issue taken into account in the final choice of cities.
The Future Cities strand PT noted that a comprehensive sustainability plan will be developed once the cities are selected and the precise nature of the city pilots defined. It will however be important to ensure that this plan is actively implemented through the course of the strand, and in particular during the later stages when the possibility of replicating or mainstreaming the pilots becomes live.
Detailed analysis VfM is set out in Section 6.2.
## Secondary Benefits
This section addresses the specific sub-questions for SBs set out in the Approach Paper:
- What factors were taken into account to make decisions on the balance and focus of the programme in terms of primary and secondary benefits?
- How has the PT incorporated SBs into programme and strand designs? Are these adequately defined in programme documentation, including in supplier designs?
- To what extent does the PT have the necessary capacity to monitor and measure SBs?
What factors were taken into account to make decisions on the balance and focus of the programme in terms of primary and secondary benefits?
Future Cities was selected initially as an area for work on the basis that Mexico faces very significant urban development challenges and could benefit from the UK’s substantial expertise in this field. In this regard, there is a good case that the strand aligns well with the focus of the PF’s primary purpose on inclusive growth.
The Future Cities strand PT focusesd on mobility issues, with a greater emphasis on individual cities rather than the national level, and with a clear focus on women and girls. Key informant interviews (KIIs) with the PF cite this as an example of increasing the emphasis on the PF programme’s primary benefits rather than the SBs, given the UK’s significant strengths in this area.
What mechanisms within strand governance and management are in place to potentially identify and deliver SBs?
The main mechanisms for delivering SBs for the strand are in place, but further work needs to be done to put in place a detailed plan to achieve this.
The Future Cities strand PT has a clear general sense of the ways in which SBs might be realised from the strand, focused on areas of proven UK expertise. It also highlighted the fact that Transport for London (TfL) already has an excellent image in Mexico as an example of best practice in integrated transport management, as does the Oyster Card. This perception creates a source of ‘soft power’, which may well support future export wins by UK firms (e.g. those who have previously worked with TfL).
DIT staff who will be tasked with delivering SBs also have a good understanding of the UK’s commercial offer in this area. The strand participates in the Embassy’s Future Cities virtual team (VT), which provides an excellent mechanism for knowledge sharing and coordination of effort.
There is also a Secondary Benefits Plan for the programme as a whole, and a Prosperity Sector Plan and Impact Pie for Future Cities. However, while these elements provide a good starting point, the strand would benefit from development of a more detailed plan for delivering SBs over the course of implementation, as is the case with the other strands. This should explicitly:
- Set out which SBs can realistically be delivered at different stages of strand implementation, taking into account the fact that some SBs will only be achievable once some or all of the strand’s objectives have been achieved.
- Link the activities to be carried out by DIT to specific SB opportunities
- Describe the supporting role that the supplier might play in delivering these opportunities, taking into account that this role can only be part of their work to deliver primary benefits.
- Summarise how achievement of otherwise of these SBs will be monitored by DIT. Discussions with the strand team indicate there is scope for improvement here. For instance, they noted that they had only found out by chance about an artificial intelligence-related contract won by a UK firm for a public bike sharing scheme.
- Consider how these things can be achieved through the course of the PF programme, not just during the forthcoming year – which is the timescale addressed by each Prosperity Sector Plan.
To what extent are suppliers’ emerging implementation plans aligned to the PF designs to deliver both primary and secondary benefits in a complementary way?
PwC’s bid identified a variety of mechanisms through which its work could promote the achievement of SBs for the UK. These include citing PwC’s UK networks and naming staff who could support this (e.g. the head of PwC's International Cities & Urbanisation practice). The bid also included the Transport Systems Catapult (now subsumed in the Connected Places Catapult) to help in linking UK businesses with international opportunities. It also listed possible UK city-regional transport agencies with whom the strand might work, albeit presenting these as possible options rather than as a concrete plan.
The strand supplier was also able to articulate broad ideas about which of the two interventions might produce SBs (expecting intervention 2 – city pilots – to produce most of these), and also an understanding of some of the key challenges (e.g. understanding the procurement process in each different city).
Given these resources, there is strong potential for the supplier to support delivery of SBs. However, this will be greatly facilitated if there is a clear plan (along the lines outlined above), so that the supplier understands how it might support achievement of SBs while delivering its primary objectives.
## Challenges and lessons
This section responds to the following EQs:
- EQ11. How is the PF learning and why is action on this learning happening more or less successfully?
- EQ12. Which PF lessons in translating outputs into intermediate outcomes are sufficiently robust for wider learning?
This section explores the challenges that the Future Cities strand PT has faced and the lessons it has learned as it responded to those challenges.
During the inception phase, the Future Cities strand has made significant advances in strengthening the design, specifying the pathways to contribute to inclusive and sustainable development in Mexican cities. Efforts to ensure that the strand continues to fit with the priorities of changing administrations stand out in particular as good examples of a learning approach at this stage. There is also strong evidence that the strand has made consistent efforts to integrate the G&I, sustainability and VfM considerations into the design in a cross-cutting way. Work by the supplier to explore a broad range of private sector and civil society stakeholders is also notable in this regard.
The integration of a G&I perspective in a transversal way across the strand is a key opportunity for the strand. Although there are ways in which this could be further strengthened, this is also an area for ongoing learning, for the strand itself but also for other projects in the Future Cities family and for other PF programmes more generally.
There are a number of challenges in the remainder of the inception phase. These include ensuring that the selected pilot city proposals have the potential for long-lasting and sustainable impact, and that can be replicated in other locations. A further challenge will be to align the times, budgets and achievements of the Future Cities interventions to the times, budgets and administrative achievements of the cities.
## Conclusion
The Future Cities strand has had a sustained focus on supporting safe, reliable and cost-efficient mobility as a driver for inclusive economic growth and poverty reduction. The strand was unaffected by the change in government in December 2018.
The strand integrates well each of the three cross-cutting themes examined in this cycle, including G&I, VfM and secondary benefits. The strand is wholly designed to strengthen gender and inclusion of marginalised individuals as indicated in the interventions and outcomes in the ToC. Nevertheless, the strand’s programme team is advised to critique the forthcoming bids for pilot cities for strength of G&I and VfM in particular.
The strand will be challenged by local election cycles, which occur every three years, to a greater degree than the other three PF Mexico strands. The strand programme team are anticipating this challenge and seeking to mitigate associated risks through the careful selection process of the five invited cities, by developing pilot city selection criteria, by requiring broad local stakeholder support and engagement, and by the sequencing of specific outputs and outcomes. Nevertheless, navigating this challenge and achieving primary and secondary goals will require constant monitoring and vigilance from all strand stakeholders, partners, suppliers and the strand team itself.
## Recommendations
Theory of Change
The strand’s ToC could be strengthened in the following ways:
- The fact that earlier versions of the strand ToC made reference to the concept of Transit Oriented Development was a strength. This was removed from later versions, but the PT is encouraged to reintroduce the concept.
- Revise the ToC for intervention 1, such that the ways in which the development of integrated transport strategies in the selected cities will improve the lives of women and girls is made clear.
- Also make the link clear between the interventions and inclusive economic growth and poverty reduction, for instance, by incorporating the analysis from the OBC on this issue.
Logframe
The emerging logframe provides relevant and appropriate information. However, the gender focus of the strand could be improved by:
- Disaggregating certain indicators by gender, including for example indicators 1.1a, 2.2a and 2.3c.
- Introducing some qualitative indicators that provide a better indication of changes in the subjective experience of women and girls (and other vulnerable groups where these are the focus of interventions). These could include, for instance, quality of experience when travelling (taking into account women’s distinctive travel patterns), and/or perceptions of security. This would provide a useful supplement to indicators measuring e.g. reduction in travel time.
Gender and inclusion
A gender perspective should be more closely integrated into intervention 1, to clarify in which ways the transport strategies in the selected cities will have an impact on women and girls. This requires working with those public officials in the different transport and mobility authorities to ensure these issues are genuinely integrated into the pilots.
For intervention 2, there is currently no definition of social inclusion, and each city is instead allowed to define this in terms of its own needs and priorities. This could cover measures to promote the inclusion of people with disabilities, young people, older adults, indigenous people, poor people or other groups. It will be essential however, that the strand takes into account the fact that women are also part of any of these vulnerable groups. Whatever perspective of vulnerability is adopted as the target for the pilot, it is essential that the specific situation of women in these groups is made visible and taken into account.
Sustainability
It is important that the sustainability plan to be drafted by the end of inception provides effective measures to ensure the continuity of the pilots, enabling them to have the desired catalytic effects promoting transformative change in Mexican cities. In doing this it should consider institutional, financial, environmental, technological and social elements, as well as the practical levers available to the programme in relation to each of these.

Annex 6: Strand evaluation: Anti-Corruption and Rule of Law
## Design and positioning
This sub-section responds to the following evaluation questions (EQs):
- EQ1. What evidence do you see to support the potential of the emerging Theories of Change (ToCs) to reduce poverty and support inclusive economic growth?
- EQ2. How has the strand/programme managed political change to ensure alignment and relevance to position achievement of expected primary benefits?
- EQ5.2. What factors may deter the achievement of primary benefits and what measures have the programme team (PT) taken to mitigate these?
- EQ7. Which assumptions and causal pathways outlined in the ToC remain valid, which have been adapted and what refinements have been made?
The PF Anti-Corruption and Rule of Law (ACROL) strand programme team (PT) note that anti-corruption and the rule of law cuts across all other strands[61]. Weak rule of law and corruption is the biggest barrier to Mexico’s economic growth, which is evidenced in the outline business case (OBC) and a number of global indices[62]. Businesses face high costs to mitigate security risks and endemic corruption constrains business operations and access to markets.
[61] The Cycle 1 Approach Paper was approved prior to the formal adoption of the Anti-Corruption Theme within PF, but it will be incorporated from Cycle 2 onward.
[62] Transparency International Corruption Perception Index, 2018, Mexico fell to 138 of 180 countries, the worst rating of all OECD countries and a 3-point fall from 2017 findings.
The ACROL strand has gone through several distinct iterations due to changes in the political environment and the opportunities these represent. There was strong evidence included in the OBC that substantiated the strand’s assumption that improved commercial, administrative and security dimensions at the state and federal level would lead to more inclusive growth.[63]
 “Corruption along with impunity is the main problem in the country because it decreases the confidence of the population in the government and its institutions, increases the yoke of crime in society, upsets the rule of law, distorts the national economy, and prevents that Mexicans exercise their fundamental rights.”
National Development Plan of Mexico (2019-2024)
[63] The SoR ToC was used for this evaluation. See Annex E, Page 76.
The ACROL strand PT made a detailed analysis in the OBC of how the London-titled Business Environment (Anti-corruption and Security & Justice) strand would overcome weaknesses and barriers to market growth. Specifically, the strand was designed to “reducing negative externalities associated with weak Rule of Law such as direct economic loss to business, increase cost of ownership and operating a business in Mexico, lack of investment, and associated job loss[64].” Prior to going to market, the strand was retitled “Anti-Corruption and Rule of Law” due to the prominence of the theme in all presidential campaigns then underway.
[64] Mexico Prosperity Programme, OBC. Paragraph 167.

Factors driving design refinements
The ToC that accompanied the Statement of Requirement (SoR) needed further development than the OBC version in that there was a gap in the causal pathway to primary objectives. The changes had been in response to the political changes that were anticipated during presidential elections. The bids[65] received in response to the procurements identified potential changes to the strand design which have prompted another round of refinements.
[65] PA Consulting won the ACROL strand.
Using an iterative process, called Agile,[66] the ACROL strand PT and strand supplier have again redesigned the strand’s working ToC. Part of this evolution was precipitated by a PT initiative which brought UK cyber-security experts to Mexico in March. The ACROL strand PT started conversations with the new authorities which resulted in a third pillar being added around cyber security, including identity theft and fraud.
[66] Agile is a PA Consulting approach to inclusive, iterative design, planning and implementation which featured prominently in its bid. PA Consulting constructed Prospero using the Agile approach.
Given the recent evolution of the design, there is a likelihood that the ACROL strand will deliver primary benefits around inclusive growth, if not poverty reduction. Since the Mexico Programme’s ToC is squarely focused on inclusive growth[67], the ACROL strand is not considered out of alignment.
[67] During the Cycle 1 evaluation period, the programme level outcome was: Improved conditions for growth in Mexico, through increased capacity and an improved environment for trade and economic growth. The programme TOC is under revision at this time.
In a recent KII, the ACROL strand PT summarized that with a reduced perception of corruption and improved government effectiveness, the overall business environment will improve. This linkage is consistent with weakens identified in the Rule of Law Index[68] and the Ease of Doing Business Index[69] for Mexico. The ACROL strand supplier notes that the impact of improved homicide investigations to reduce poverty is “highly indirect.”
[68] Mexico receives poor ratings for timely and effective adjudication (.29), absence of corruption (.29), and respect for due process (.38); http://data.worldjusticeproject.org/#/groups/MEX
[69] Mexico has a low rating of 54 out of 190, and receives only 2 points for contract enforcement. http://www.doingbusiness.org/en/rankings?region=latin-america-and-caribbean
The ACROL strand PT and strand supplier have identified impunity as the greatest factor blocking the potential for inclusive economic growth and poverty reduction in the context of anti-corruption and the rule of law. The revised impact is now: Reduced impunity to strengthen counter corruption and the rule of law. Three outcomes support this:
- Improve the (effectiveness) of investigation of homicides
- Improve the (effective) detection and investigation of embezzlement of public goods and illicit enrichment.
- Improve the (effective) detection and investigation of fraud and identity theft.
The assumptions identified in this new design reflect the ways in which impunity limits progress towards PF primary objectives, which improves the alignment of the design over the SoR version. In the first outcome (rule of law), the assumption is that impunity results in only 3 per cent of homicides being investigated. In the second outcome (anti-corruption), the assumption is that the diversion of pesos from public budgets into private hands has a direct impact on the availability and quality of public services which should go to the community, including the poor. In the third outcome (cyber-crime), the assumption is that identity theft inhibits a more robust digital economy and erodes the digital business environment.
Factors positioning the strand to achieve
The key factor influencing the positioning of the strand for programme effectiveness has been the change in government and policy focus. To maintain communications and engagement with key stakeholders, the ACROL strand PT used 2018 transition money, but also reserved funds to engage with the new government in late 2018/early 2019, which included the visit by UK cyber-crime experts noted above.
The strand supplier views the change of government at the federal level and in many states as an opportunity to explore and introduce new approaches to reduce crime and corruption with political leaders that are eager to make a tangible, positive impact on reducing crime and corruption at all levels throughout Mexico. Key government stakeholders took part in the discussions which led to the strand’s redesign, which is likely to strengthen the positioning of the strand as it transitions to implementation.
There is clear evidence that the current design of the strand is well positioned to engage federal authorities, given President López Obrador’s daily briefings which focus on anti-corruption themes. The National Development Plan (2019–2024) was released in late April, and confirms the centrality of the fight against corruption, including a strong focus on addressing impunity throughout official systems[70]. The continued messaging and channel-opening created by the strand’s virtual team (VT) and the Embassy further support and improve the positioning of the strand.
[70] This new framing aligns well with the government’s focus as presented in the 27 April 2019 National Development Plan which states to government’s goal to: “Combat levels of impunity within the Federal Public Administration through prevention actions; attention to citizen complaint; the use of investigation and intelligence mechanisms that include money laundering and asset recovery strategies; the identification of conflicts of interest; and the sanction of administrative faults and acts of corruption.” (NDP, page 75)
Designing for inclusive growth
The current strand design aims to reduce the barriers that erode the environment required for economic empowerment and financial inclusion, rather than supporting mechanisms that promote economic empowerment and financial inclusion. Inclusive growth is addressed by ensuring that federal funds invested in the communities reach their intended beneficiaries. Another aspect of inclusive growth lies in the plans to protect digital identities so that individuals and businesses can participate in the booming digital economy with greater confidence.
Another aspect of inclusive growth is potential for cross-linkages with the Financial Services strand of the Mexico Programme, in which digital services for the poor is a feature. See Annex 4 for the Financial Services strand analysis. This finding is consistent with the cross-cutting role that the ACROL strand PT see as implementation of the Mexico Programme advances. The two teams (Financial Services and ACROL) have the opportunity to make this potential linkage explicit in final strand designs in the remaining time of the inception phase.
Deterrents and mitigation
There are a number of factors that may deter progress towards the primary benefits of a strand which seeks to address homicide investigations, tackle corruption, and address cyber-crime in a country such as Mexico. The ACROL strand PT and the strand supplier sought to identify key challenges and account for these through the Agile process that created the emerging strand design and indicator selection.
The detection and prosecution of corruption, specifically the illicit use of public funds, is a priority of the new president, who currently holds an 86 per cent approval rating[71]. Within the first five months of his presidency, more than 120 individuals have been arrested and are facing prosecution[72]. Policy and public momentum favour the new design and goals of the ACROL strand, and the ACROL strand PT is in the process of finalising its regional strategy to ensure the greatest strength of positioning possible. The forethought demonstrated by the ACROL teams increases the likelihood of mitigating future challenges.
[71] https://mexiconewsdaily.com/news/amlo-enjoys-86-approval-rating/
[72] Andres Manuel López Obrador daily briefing, 17 April 2019.
Another challenge relates to the data for indicators and evidence gathering due to record availability and the safety of those seeking information. This risk was identified in the Mexico Approach Paper. The ACROL strand PT and strand supplier have factored in the availability of data to support its emerging indicators, which includes the safety of the personnel required to deliver the project and collect subsequent evidence for monitoring and evaluation purposes. They based their analysis on the long-term experience of one of the strand consortium members who has collected relevant, timely data without any incidences of safety breaches.
## Strand guidance, governance and management
This sub-section responds to the following EQs:
- EQ8a. How well do PF institutional governance structures operate and to what extent have they helped or hindered in the design phase of the programme or strands?
- EQ8b. What recommendations for improvement are there from both Evaluation and Learning (E&L) and the PT?
- EQ9. What types of programmes, approaches and governance and management arrangements have been more or less effective for achieving results and demonstrate good approaches to supporting inclusive growth and VfM?
In addition to the governance and management bodies of the bilateral programme (see Section 5), the strand supplier has a series of management structures to guide strand development and delivery. Early indications are that the Central Delivery Unit (CDU) and the strand’s consortium members have been an asset to the redesign of the strand’s ToC and in facilitating stakeholder conversations to position the strand during the inception phase.
Central Delivery Unit. The CDU is responsible for overall strand delivery, through driving, managing and coordinating activities over the life of the Strand at federal, state and municipal level. The CDU is based at PA Consulting’s pre-existing Mexico City offices. Given the dual role that PA Consulting has with regards to the Mexico Programme – as a monitoring and reporting (M&R) hub and as ACROL strand supplier, there is need for ongoing vigilance to avoid a conflict of interest. Both parties are aware of this concern and to date there is no evidence that PA’s dual roles have presented any challenge to strand development. (See the “Challenges and lessons” section for further analysis.)
Strand Governance Board (SGB). The SGB is obligated to meet bi-annually and include representatives from the ACROL supply chain as well as key stakeholders and beneficiary groups. It has a robust terms of reference (TOR) which identifies membership, voting rights and meeting frequency. The purpose of the SGB is to ensure coordination and synergy with donor programmes beyond the UK portfolio. Its planned inclusive membership provides a good basis on which to expect future cross-coordination and leveraging of donor programme investments.
Non-Executive Board (NEB). The NEB is due to meet quarterly to review strand initiatives and ensure that they are fully aligned with UK and local authorities and government institutions objectives. The composition of the NEB will be decided by the SGB and will be evaluated in subsequent cycles.
Operational Delivery Board. The Operational Delivery Board is a review body which will include representation from across the supply chain and the PF. It will meet monthly to track progress, manage risks, allocate resources and review contract variations. It will be reviewed for relevance and effectiveness in subsequent evaluation cycles as it has yet to launch.
Advisory committees. The strand supplier plans to create four advisory committees with Mexican experts and managers in the crime and anticorruption sector: a Social Inclusion and Gender Steering Committee[73], an Anti-corruption Committee, a Serious Crime Investigation Committee and a Cybercrime Prevention Committee. The strand supplier intends for these committees to meet at least three times yearly to provide technical expert criteria in each of the interventions. The strand supplier and the ACROL strand PT may find that these advisory committees are particularly useful during the inception and early implementation phases to ensure full inclusion and participation of Mexican stakeholders and experts. However, there is a risk of having many meetings with the number of management committees and boards. The implementing team may choose to consider other variations of these management bodies or the frequency of which each meets as delivery advances.
[73] The proposed Social Inclusion and Gender Steering Committee is distinct from the PF Gender and Social Inclusion Group which gathers the G&I advisors from each strand on a monthly basis.
Evidencing adaptive management. There is good evidence that the management practices of the ACROL strand programme team, the wider PT, and the Embassy more broadly have played an important role as the strand and programme have evolved.
Managing the political landscape. The ACROL strand PT has utilised VT assets in the Embassy and quickly tapped into strand supplier’s networks to manage the diverse mix of stakeholders identified in the SoR and the sweeping changes in government personnel and policy. Through the Political and Global Issues (FCO) teams in the VT, political and private sector networks were tapped which enabled high-level communications and access to relevant authorities. This enabled the strand team to develop channels into the new government as official portfolios were consolidated and key actors took up their roles. The ACROL strand PT specifically noted the calibre of the strand supplier’s resource pool as one key advantage to its bid, and that the networks have already been an asset to align and refine the strand design to political momentum.
Managing stakeholder engagement. The ACROL strand PT and the strand supplier plan to facilitate stakeholder engagement by establishing two regional hubs to reach into key regions most relevant to strand objectives. Through stakeholder engagement and document analysis, the ACROL teams have selected Centre/Mexico City and Jalisco/Guanajuato. The factors contributing to this selection include size of population, areas of economic diversity and inequality, areas of rapid economic expansion and centres of policy. Both teams agree they need to manage the expectations of the primary stakeholders as discussions with relevant regional authorities continue.
Managing intra-strand delivery. PA Consulting uses a system of programme management, called Agile which is designed to reduce management costs and ensure ground-truthing of programme interventions against an iterative process of design, implementation and reflection. From the CDU, it plans to manage its team through a series of 12-week programme increments, each consisting of six two-week “sprints.” In the final sprint, the team focuses on evaluation and reflection of the overall 12-week period for learning and programme adaptation. Subsequent evaluations of the Mexico Programme and the ACROL strand will assess the relative strengths and weaknesses of the various CDU models used by the Mexico Programme’s four strands.
## Thematic analysis
Gender and inclusion
This section responds to the following EQs:
- EQ9.2 Which approaches, governance and management arrangements have been adopted in relation to G&I?
- EQ10. To what extent have PF interventions contributed to results that support gender and equality, women’s economic empowerment and social inclusion?
Programme design
The OBC noted that weak rule of law and endemic corruption are the biggest barriers to Mexico’s economic growth and have a negative impact across all the PF strands in the programme.
Although it is relatively easy to assume gender and social inclusion elements within the ACROL strand, the current documentation is developing this area to support evidence of the design and intended impact on women, girls and vulnerable or marginalised individuals. One challenge in evidencing the strand’s design and positioning is related to the timing of the evaluation and the status of the strand’s revisions during early inception.
The ACROL strand PT and the strand designers are encouraged to explicitly identify descriptions and metrics for both gender and social inclusion interventions, results and indicators in the final inception milestones.
Internal capability/institutional incentives
The strand supplier has gathered an impressive and highly regarded set of individuals to provide strand leadership within the CDU, the majority of which are women. This management team is complemented by a strong consortium (see Annex 12) and includes some of the leading NGOs in Mexico to address issues of gender and corruption.
One of the ACROL strand programme officers is the theme lead for safeguarding within the PT’s cross-cutting theme assignments.
Financial resources
The VfM assessment for Criterion 8 (Equity) of the ACROL strand (see Section 6.2 and Annex 8) noted that “the ACROL strand had adopted the same measures as the other strands to ensure G&I considerations are adequately taken into account” and scored the strand a 4 out of 5.
As such, there is a high degree of confidence that there will be ample budgeting against gender related outcomes. However, the links and interventions for social inclusion are less clear. In addition to fortifying the strands accountability mechanisms for social inclusion, the strand teams should give due consideration as the ACROL strand supplier allocates financial resources and submits its costed Cycle 1 implementation phase work plan in August.
Accountability mechanisms
The working version of the revised ToC made available to the evaluation team indicated three areas of intervention which correspond to the outcome level, but was absent any assumptions or indicators. It is therefore not possible to assess the accountability mechanisms of the ACROL strand other than the monitor and reporting schedules contained in the Call-Off Contracts.
Partnerships
The strand supplier has complemented its CDU and consortium with a deep resource pool of national agencies, organisations and specialists to inform the strand design, support its positioning, and extend its outreach when the strand reaches the implementation phase in October.
The SGB is another mechanism through which the ACROL strand will build partnerships that support and improve the overall delivery of its interventions, although the final structure of the SGB is in discussion at this time (see Section 5).
A comparative analysis of the programme’s G&I status is found in Section 6.1 and in Annex 7.
Value for Money
This section responds to the following EQs:
- EQ4. What evidence is there that the changes supported by PF interventions will be sustainable and ensure environmental sustainability, will be self-financing and lead to inclusive growth that reduces inequality?
- EQ 9.1. Which approaches, governance and management arrangements have been adopted in relation to VfM?

Value for Money in procurement
The ACROL strand PT questioned the use of the framework, noting that it limited tendering to pre-approved UK-based organizations. The team noted that there are other organizations in Mexico and elsewhere capable of delivering complex programmes, and that there may have been better VfM if the tender had been more widely competitive. As it was, VfM considerations were included in the SoRs so that the bidders had to account for the benchmarking.
Invitations to tender were sent to the 20 IIOC approved Lot A1 Framework[74]. Given PA Consulting’s role as the monitoring and reporting (M&R) service provider for the global PF, the PF ACROL team raised the question of the potential conflict of interest of a PA bid prior to the tender being released. The PF team was assured by the Joint Funds Unit (JFU) that the existing conflict of interest mitigation measures were sufficient, and the process continued. Four of five submitted bids were deemed compliant for technical and commercial and underwent the full evaluation process using the Most Economically Advantageous Tender. After the scoring, the top three bidders were invited to present to the PT in late October 2018. PA Consulting emerged from the process with the top score.
[74] Business Environment, including Abt Britain, DAI (Europe) Ltd, McKinsey & Company, Adam Smith International, Deloitte LLP, Mott MacDonald, Atos IT Services Ltd, Ecorys UK Ltd, Oxford Policy Management, BDO LLP Ernst & Young LLP, Palladium International Ltd, Cardno Emerging Markets, IMC Worldwide Ltd, PricewaterhouseCoopers LLP, Coffey International Development, KPMG, PA Consulting, Crown Agents, and Maxwell Stamp.
PA Consulting affirmed in its bid that none of the CDU experts are involved in other PF activities in Mexico or elsewhere. However, it will utilise PA Consulting assets in London for its Operation Delivery Board, to support its inception phase back-office function and to develop its overall messaging planning[75]. There is no evidence of any conflicts of interest to date. There remains a remote risk when the strand supplier seeks final validation of its indicators and logframes from the M&R hub. Further discussion of this is found in Section 9.
[75] Bid documents 008 PF 18-018 PA Consulting 2.3, 007 PF 18-018 PA Consulting 2.2, 009 PF 18-018 PA Consulting 3.1
Environmental sustainability
The Call-Off Contract identifies operational methods for reducing environmental impacts. In addition to these, the ACROL strand programme team asked the strand supplier to utilise carbon offset options for travel. The strand supplier will include approaches to mitigate environmental impact in its delivery of strand activities in the Climate Resilience Strategy in June.
Intervention sustainability
There is good evidence that the ACROL strand supplier is considering an exit strategy during the inception phase. For example, four lines for sustainability were identified during KIIs:
1. Working with UK and Embassy. The Embassy has the capacity to continue to push for anti-corruption themes such as conflict of interest, which is now part of the 2015 Law; 3de3,[76] and the Embassy has ownership of mechanisms to combat corruption from UK best practices. The ACROL strand meets regularly with the Embassy anti-corruption team.
  [76] Ley 3 de 3 was a citizen-initiated law to prevent, detect and sanction corruption in the government. The initiative was signed by more than 634 million citizens and went into force on 18 July 2016. http://www.ley3de3.mx/es/
2. Civil society and think tanks within the ACROL resource pool. These individuals and institutions have a consistent focus and voice in these areas. They will be the ones that take these ideas and platforms and influence forward.
3. International synergies. The ACROL strand supplier sees potential in leveraging state level impact to attract other bilateral and multinational actors as other donors and development partners look to create ties to the new government. The Head of the Prosperity Fund in Mexico also included the PF Global Anti-Corruption Programme as an important mechanism to support international level coordination.
A comparative analysis of VfM for the Mexico Programme is in Section 6.2 and Annex 8.
Secondary Benefits
This section addresses the specific sub-questions for SBs set out in the Approach Paper:
- What factors were taken into account to make decisions on the balance and focus of the programme in terms of primary and secondary benefits?
- How has the PT incorporated SBs into programme and strand designs? Are these adequately defined in programme documentation, including in supplier designs?
- To what extent does the PT have the necessary capacity to monitor and measure SBs?
What factors were taken into account to make decisions on the balance and focus of the programme in terms of primary and secondary benefits?
The ACROL strand design identifies SBs in terms of general business environment improvements which would support increased levels of trade and investment with Mexico, as well as some specific opportunities for UK firms. To date these have primarily been identified as export wins – in the Business Case for instance these are described as including a range of cyber security services and general security and defence services. Although these are identified as areas where the UK has specialist skills, there is a less obvious correspondence with commercial opportunities than with Energy, Financial Services or Future Cities. The potential for a broader range of SBs may also emerge over time. For instance, emerging guidance on SBs (including issues such as soft power) may also help to identify further opportunities, which can be reflected in updated programme strategies.
What mechanisms within strand governance and management are in place to potentially identify and deliver SBs?
The strand logframe identifies two SB indicators: i) value of revenue lost by companies due to corruption and crime and ii) value of business opportunities identified. Although it is not clear how data for i) will be collected, this would provide a useful assessment of the contribution of the strand to improving the general business environment for UK firms.
In terms of ii), existing plans could be strengthened to maximise business opportunities. There is an ACROL VT, with an associated Prosperity Sector Plan and Impact Pie. This has planned activities and an allocation of resources for delivering a range of policy, programme and trade objectives, including SBs. This provides a good mechanism for information-sharing and coordination of work, and also allocates human resources including from DIT in Mexico.
The ACROL strand PT were able to generally articulate the potential for SBs (beyond the general improvement in the business environment mentioned in the BC). These will depend on the particular shape of the ACROL intervention and are likely to differ between the anti-corruption and rule-of-law elements. However, the ACROL strand PT mentioned as examples UK expertise in forensics, technology and training in relation to the likely focus of the rule-of-law intervention on homicide detection. It also identified technology solutions and services as significant for cyber-security interventions.
As with the other three strands however, plans for achieving SBs could be defined so that it is clearer
- Which SBs can realistically be delivered at different stages of strand implementation.
- Which activities DIT will carry out to deliver these specific SB opportunities.
- How the supplier can support delivering these opportunities, taking into account that this role can only be part of their work to deliver primary benefits.
- How achievement of SBs (or otherwise) will be monitored by DIT.
- How these things can be achieved through the course of the PF programme, not just during the forthcoming year – which is the timescale addressed by each Prosperity Sector Plan.
To what extent are suppliers’ emerging implementation plans aligned to the PF designs to deliver both primary and secondary benefits in a complementary way?
The strand supplier (PA Consulting) provided a very similar assessment to the strand PT in identifying the kinds of SB opportunities that might arise (e.g. exports of specialist cyber security services).
## Challenges and lessons
This section responds to the following EQs:
- EQ11. How is the Prosperity Fund learning and why is action on this learning happening more or less successfully?
- EQ12. Which Prosperity Fund lessons in translating outputs into intermediate outcomes are sufficiently robust for wider learning?
This section explores the challenges that the ACROL strand PT has faced and the lessons it has learned as it responded to those challenges. Some challenges also have recommendations from the evaluators associated with them. Recommendations are found in the following section.
Challenges internal to Prosperity Fund
The primary challenges within the PF relate to timely, fulsome guidance from the JFU and/or PFDU which are discussed in the main body of this report (see Section 7).
Challenges within the strand
The SoR ACROL design had focussed on crime and security which made it an outlier in the PF’s broader Transparency and Anti-Corruption (TAC) family. For this reason, it was omitted from the TAC sampling for this cycle. The current reframing is closer to other programmes in the family, but it remains distinctive. The ACROL strand PT is encouraged to engage the TAC through the PFLearning platform to share its lessons and to identify ways that other family-related programmes can inform the Mexico strand’s design before it transitions to implementation.
There are inherent challenges associated with the implementation of the strand, as it works with highly visible and contentious crimes, including homicide and the misuse of public funds. These challenges were assessed and factored into the prioritisation exercise conducted by the strand supplier and in subsequent stakeholder discussions with relevant authorities.
## Conclusions
The ongoing strand design and planning seeks to optimise the opportunities within the selected interventions and leverage the stakeholder engagement required to achieve the stated objectives. The political, social and security dimensions that the current design represents requires the ACROL strand PT and strand supplier to consider every nuance and potential barrier. The iterative, inclusive process being used to redesign and position the revised ACROL strand provides confidence in the resulting design. The selection of the final indicators will determine the strength and relevance of the overall ToC. These are expected by August 2019.
The alignment with the new administration, particularly framing corruption around impunity provides an indication of the strength of the support the ACROL strand may find in engaging federal officials. At the local level, equal care must be exercised to build strong, collaborative relationships with officials at that level of government. The ACROL strand PT already notes that it values the networks across Mexico that the strand supplier brings to the project, which should complement and extend the networks that the VT offers in maintaining channels into government and the private sector.
Thematically, the ACROL strand’s performance is mixed. It scores quite high against G&I metrics, but less well for VfM and SBs in its current design midway through inception. These lower scores are in part due to the unavailability of key reference documents to determine the relevant scores. Nevertheless, the guidance and additional suggestions from this evaluation should, if adopted, help to boost these scores in future evaluation cycles.
## Recommendations
Logframe and Theory of Change. The degree to which causal pathways will support promotion of inclusive economic growth directly and poverty reduction, albeit indirectly, depends on the final design of the ToC and the indicators, due in August 2019. The ACROL strand teams are advised to articulate the linkage to improving inclusive economic growth and to continue the clarity of the revision demonstrated since late March.
Align high-level indicators to government goals. The new administration has signalled a high priority to anti-corruption efforts. It has identified the World Justice Projects’ Rule of Law Index as its indicator, citing the 2017 score of 0.45 as a baseline and a 2024 goal of 0.6[77]. The July 2018 ACROL logframe also identified the ROL Index as a key indicator. It is recommended that the ACROL strand retain that metric to promote good communications and messaging with the new administration.
[77] National Development Plan, 27 April 2019. Page 75.
Maintain ethical walls with supplier. The ACROL strand PT notes that when the final logframes from strand suppliers are reviewed and validated by the M&R hub, PA Consulting will be on both sides of the table. The PF ACROL team has sought guidance from the Head of PF in Mexico that this does not present a conflict of interest and secure an alternative process if there are any concerns to the potential for risk. This due diligence should be captured in risk registers.
Strand management. The Social Inclusion and Gender Steering Committee may prove a useful addition to the sustained mainstreaming of G&I considerations within the ACROL strand. However, there are other coordination and oversight mechanisms within the existing PF/Mexico governance architecture which will press the time of both suppliers and stakeholders. Careful consideration should be given to the frequency of this steering committee as well as how it aligns and contributes to existing coordinating bodies.
Inter-strand Coordination. There is an opportunity during inception for PF strands to collaborate pro-actively to optimize interventions, intent and messaging. For ACROL and Energy this collaboration would focus on strategies and programming to engage rural communities around issues of energy development. For ACROL and Financial Services this would focus on cyber-security in financial transfers to women and other low-income financial service clients. The strand teams should meet to discuss regional strategies, stakeholder engagement strategies and shared messaging as soon as the strands define their draft approaches.
Exit and Sustainability Strategy. In its bid, the strand supplier described plans to launch a structured process to assess what is transferable and/or replicable in a planned closure phase (January-June 2023). Based on that assessment, a transference plan will be created. A more deliberative process of transferability would leverage the clarity offered in the KIIs. This approach would begin as early as the first year of implementation so that actors and institutions who show an interest and ability to incorporate those new practices and standards are supported within the strand context as soon as possible.
Improve assumptions within the Theory of Change. The assumptions in the emerging ToC[78] should be carefully considered to avoid gaps in the logical flow and realistic scope of the strand’s interventions. For example, in the SoR ToC, four assumptions fell out of alignment. These included:
[78] These recommendations may be offset by the changes to the final TOC and logframe of the ACROL strand.
- Assumption 4: “Authorities adopt and request scaling-up of successful pilot” is more logically placed between the intermediate outcome and the outcomes. However, the scaling-up of these pilots lies beyond PF resources, and is so noted in the ToC, although it is identified as an outcome.
- Assumption 5: Between the intermediate outcomes and a non-PF funded outcome reads “Programme intervention contributes to the improvement of capabilities of key actors of the criminal and anti-corruption systems at the national and local level that increases men and women’s trust in both systems.” It is unlikely that the capacity-building of selected individuals within an opaque investigative process will lead to an increase of trust locally and nationally within two complex systems. It is recommended that the team revise the language.
- Assumption 8: “Effective coordination among actors will lead to full implementation of the justice and anti-corruption systems”. This is more ambitious than the outcome to which it leads: “Improved coordination in the detection and investigation of serious crime and corruption.” It is recommended that the team revises the assumption to flow within the ToC and remove hyperbole.
- Assumption 9: Between the outcome and the impact is a summary of the strand’s role in “providing fair access to justice for men and women,” without any link to inclusive economic growth or poverty reduction. It is recommended that the team rearticulate the causal pathway of this high-level assumption to reflect inclusive economic growth or poverty reduction, as is logical.
Find a home in the Transparency and Anti-Corruption Family. The ACROL strand PT should maintain engagement in the TAC Family Reference Group, not only to inform the family of its challenges and progress, but to contribute to the peer-based platform to identify unexpected insights. Likewise, the TAC Family should reconsider sampling the ACROL strand into the next cycle of its family-level evaluation.

Annex 7: Thematic analysis: Gender & Inclusion Stocktake
This analysis was completed in February 2019 and shared at that point with the programme team. An updated score is included in the main body of this Cycle 1 evaluation report.
## Overall Score
Table 17: Mexico Programme overall score
Programme	Programme design	Internal capability & institutional incentives	Financial resources	Accountability mechanisms	Partnerships
Mexico

Programme design
Situational analysis: Both the old and updated versions of the BC contain a gender analysis which outlines gender gaps in employment, business leadership and education, as well as data regarding Mexico’s performance on gender equality and recent policy reforms. The updated BC uses data from 2017 about Global Gender Gap Index rankings, compared to 2013 levels used in the original BC. However, the BC does not mention that Mexico has fallen from 68th to 81st in that time or explore why this fall may have occurred.
Regarding other areas of inequality and exclusion, the paper mentions higher rates of poverty among indigenous people, a significant rural/urban divide, and high rates of old-age poverty, but does not respond to these issues in its interventions.
The updated BC also includes some gender analysis in each of the pillars of the project, outlining some of the key areas of inequality and potential opportunities for change. The gender analysis sections in some areas have been reduced in the updated BC.
The ‘Challenges to Mexico’s Future’ section does not mention G&I issues, even though these are listed in the preceding section as major challenges to Mexico. Mainstreaming the gender analysis throughout the BC would have strengthened the document.
Risk/harm: The Appraisal Case states that negative impacts on gender equality will be assessed and only then can work be taken forward. The updated BC includes more detail on how this will be assessed and monitored on a continuous basis, and what kind of risks and harm will be assessed. The updated BC also highlights that the UK will use its expertise on social and environmental risk management procedures, including consultations and conflict resolution, particularly with marginalised communities and women.
Objectives/outcomes: The BC states that the aim of the country project is "reducing poverty and gender inequality in Mexico". Each of the programme pillars has outcomes related to gender equality. For instance, one of the three key outcomes listed in the Financial Services project is “increased access to financial services for un(der)served populations", while the Energy pillar aims to “promote female empowerment” in the workforce. The section on what role the UK can play in Mexico’s development briefly mentions challenges related to access to credit and infrastructure for rural people living in extreme poverty, however, this does not explore G&I dimensions. It clearly states that “the entire programme is structured to ensure we drive and take advantage of secondary commercial benefits for UK companies”.
The BC includes a section on supporting the achievement of the Sustainable Development Goals, with more detailed descriptions of how the programme addresses them provided in each of the four pillars of the programme.
Interventions: There is a slight disconnect in the BC between analysis of issues and challenges and the ensuing programme interventions and activities. However, each of the projects identifies some gender-related response measures.
Future Cities
The Future Cities project notes that infrastructure will be improved for pedestrians including ramps, which support women and people with disabilities, as analysis shows that women tend to take shorter trips by foot in part because they cannot afford public transport. These measures address practical needs, but do not address the underlying gender inequality in access to public transport. The updated BC claims that “the programme will look to empower women by providing better and safe transport systems and by developing skills for Industry 4.0, providing access and inclusion to the digital economy”. Providing access and inclusion to the digital economy is not referenced elsewhere in the BC.
The updated BC states that “interventions will address poverty reduction and gender inequality on two fronts—via project design and project implementation”. The two paragraphs which detail project design and implementation state that delivery partners will ensure this happens in practice, but no further details are provided. The activities listed for this project do not detail G&I considerations.
Financial Services
The Financial Services project aims to empower women through increasing their financial independence by providing innovative financing tools and increased access to financial services. A more detailed separate ToC for the Financial Services project is gender-responsive, aiming to address specific aspects related to gender inequalities in the sector, related outcomes and gender-responsive activities, and is supported by a narrative, evidence and assumptions. The updated BC includes a clear pathway to assessing barriers to women in this sector and how they will be addressed, included targeted activities such as work through the national Prospera programme and on financial technology related to remittance payments. This pillar has the potential to lead to women’s economic empowerment.
Anti-Corruption and Rule of Law
The Anti-Corruption and Rule of Law project highlights the contribution of corruption to widespread discrimination and VAWG. Interventions include providing support and technical assistance to strengthen oversight and monitoring of how the justice system addresses gender issues and how gender justice reforms are implemented.
Energy
The Energy strand section states that the programme will have a focus on training women in service and maintenance roles within the energy sector and will support oil-dependent communities vulnerable to price fluctuations and economic shocks. It also repeats throughout a focus on supporting SMEs to integrate into the global supply chains of multi-national corporations and deliver services in the energy sector in Mexico, and states that “as three in five SMEs are run by women, this intervention will also have a positive impact on gender equality.” However, it later notes that most of these businesses are restaurants and laundrettes, operating within the informal economy. It is analysed that these businesses are affected by energy price fluctuations and have high energy demands. The BC could have provided more detail on how it intends to assist in integrating these businesses into the global supply chains and deliver energy access services in Mexico.
Appraisal case: Some aspects of G&I are included in the appraisal case, such as cost-benefit analysis relating to the financial services pillar’s activities focused on women’s financial inclusion.
GEA compliance: The updated BC has a specific GEA compliance section, with information about requirements for partners. The GEA compliance section also states that the programme "aims to increase the participation of women in decision-making processes in all levels of government. It seeks to foster dialogue among key actors, promote cultural change within political parties, carry out professional training and mentorships for public officers, and to increase knowledge of women’s rights."
SoRs also outline GEA compliance requirements for implementing partners, with inception report approval pending.
Internal capability
Team expertise: Responsibilities of programme and policy strand teams in relation to G&I are outlined. The appointment of a gender champion from within existing programme staff is also mentioned. The gender adviser role is not included in the management structure of the programme. The Mexico team has requested technical assistance from gender experts to develop their Fintech project. The GEA compliance section states a gender adviser will be involved at various stages in the programme.
Training: No information is currently available.
Financial resources
No information was available at this stage on budget lines for G&I-focused inputs or how G&I-related activities have been costed into budgets.
Accountability mechanisms
Governance: The BC could have provided more information about how G&I considerations will be governed and how risk and harm will be monitored and responded to. A gender expert will be involved at relevant points throughout the programme; their role in relation to governance structures could have been outlined in more detail.
MREL: The BC makes commitments to annually review programme impacts on gender equality.
Indicators: All project logframes in the BC have the same impact measure of inclusive economic growth—total GDP and FDI growth, which do not strictly measure the ‘inclusivity’ of growth. However, these indicators do not appear in project-level logframes, so they may have been changed for more relevant measures of impact. There are several indicators in logframes that are sex-disaggregated (please see below).
Reporting: Supplier requirements in terms of reporting about the impact of their work on gender equality as part of their annual reports to the Prosperity Fund Management Committee are noted.
Partnerships
Due diligence: The BC states that ‘gender equality’ is a qualifying condition for access to the fund. The supplier evaluation process detailed in the updated BC includes criteria relating to gender, poverty, and social inclusion, covering both the methodology of the bid, and the technical capacities of the bidder.
There are also some pillar-specific criteria, such as expertise in tackling energy access in poor communities, and experience in supporting female-owned SMEs. There is also a requirement to comply with the GEA. A social development expert was included in the review panel for the energy pillar, but not for other pillars.
The SoRs for the four pillars outline in detail gender equality–related outcomes and outputs, monitoring measures, GEA compliance requirements, supplier expertise and responsibilities on G&I. For instance, the Financial Services SoR specifies supplier capability requirements in ‘identifying, prioritising and benefiting groups with particular needs or terms of exclusion in a given context such as girls and women, the poorest, marginalised groups and adolescents/youth’.
Gender plan: The project-level ToC documents each state that a full gender and inclusion strategy, with an action plan, will be designed by the delivery partners during the inception and mobilisation phase.
Consultations: Supplier deliverables include community consultation plans and G&I mainstreaming and strategy action plans.
Documents reviewed:
- Business Case - ‘PF Mexico Business Case MASTER COPY to PFMO 6 June - UPDATED 060617’
- Business Case to IIOC 3 – December 2018 FINAL
- Statements of Requirements for Energy, Financial Service, Future Cities and Anti-Corruption and Rule of Law
- Appendix 3 – ToC documents for all 4 projects
- Appendix 4 – Logframe documents for all 4 projects

Annex 8: Thematic analysis: Value for Money Scorecard results
## Overview
This section presents a detailed analysis of the Value for Money (VfM) for the Mexico Programme, based on the Evaluation and Learning (E&L) VfM scorecards.
The process for this exercise was as follows. Scorecards and guidance were sent to each strand manager, who then scored eight VfM criteria separately, providing a summary explanation of their score and documentary evidence from programme documents to support it. These scores and the evidence were then reviewed by the evaluation team. Revised scores, and the rationale for these, are set out in this document.
The strand scores for each criterion were then averaged, to provide a programme score. The exception was criterion 6, which focuses on programme level arrangements (in this case the overall programme score was used to provide the same score for each strand).
## Summary of results
Overall, the programme is scored at 3.9 (out of 5), on the basis that there is good evidence the programme has put in place suitable arrangements likely to generate VfM over the course of implementation. Scores for individual strands are also indicated in the Table 18 below.
Table 18: Summary of Value for Money Criterion scores, for each strand and the programme as a whole
VfM Criterion	Energy	Future Cities	Financial Services	ACROL	Average programme score
1 – VfM indicators	3	3	3	3	3
2 – Procurement and cost containment	5	5	5	3	4.5
3 – Efficient use of resources	4	4	4	4	4
4 – Valid causal pathways	3	3	3	3	3
5 – Sustainability	3	4	3	4	3.5
6 - Governance	4	4	4	4	4
7 – Risk management	5	5	5	5	5
8 - Equity	4	4	5	4	4.25
Average Strand score	3.9	4.0	4.0	3.8	3.9

## Value for Money Criterion 1: Relevance and robustness of Value for Money measures
Summary
All strands are scored 3 out of 5, i.e. there is adequate evidence of relevant and robust measures in place at this moment in time. There is in fact considerable evidence that VfM indicators have been considered throughout the programme development process. However, the scoring approach is dependent on verifying documents, and as strand logframes have not yet been finalised it is not yet possible to score this criterion higher than 3 at this moment. There are strong indications from the available documentation (see below) to suggest the score will rise when the logframes are finalised.
Table 19: Relevance and robustness of Value for Money measures – scores
Strand	Strand manager self-assessed score	Evaluation team score
Energy	3	3
Future Cities	4	3
Financial Services	3	3
ACROL	3	3

Evidence
The December 2018 business case (BC) defines VfM, and sets out good programme-level VfM indicators for economy, effectiveness and efficiency (p.167).
Annex B to the SoRs (“Service levels and KPIs, Monitoring and Evaluation) provides detailed Delivery KPIs for assessing impact for each strand. These are the same as those provided in the March 2019 strand logframes. These indicators should provide good information to assess strand progress over time and therefore cover the effectiveness issue. The logframes have yet to be finalised however, so it has not been possible to assess how indicators will be measured and reported. If this is adequately addressed in finalised versions the overall score for VfM Criterion 1 should rise.
‘Service KPIs’ are also defined in Annex B, corresponding well with economy and efficiency considerations. The same document mentions the Gender Equality Act and women’s economic empowerment, and states that suppliers will be required to generate meaningful indicators for these. It also requires suppliers to provide data disaggregated by gender and socio-economic group. There is scope for equity indicators to be better defined in some areas.
If the finalised supplier implementation plans and logframes achieve this then the overall score for this VfM Criterion 1 should rise.
## Value for Money Criterion 2: Approach to procurement and cost containment
Summary
All strands are 5 out of 5, with the exception of ACROL which is scored 3. Scores for this criterion take into account both initial procurement and ongoing measures for cost containment during implementation.
Table 20: Approach to procurement and cost containment – scores
Strand	Strand manager self-assessed score	Evaluation team score
Energy	3	5
Future Cities	5	5
Financial Services	4	5
ACROL	2	3

Evidence
The BC provides a detailed assessment of different procurement options, and explains the approach ultimately adopted. Overall, the process that was actually implemented provides an example of good practice in procurement. Some of the features of the process that support this contention include the following.
- A strong supplier evaluation process (including separate review teams for commercial and technical bids, training for reviewers, moderation meetings to discuss scores, face-to-face interviews with bidders)
- A good explanation of the Most Advantageous Economic Tender, and clear rationale for the scoring system used
- Documentation of cost savings
- Consideration of drawbacks in the process (e.g. the fact that other PF programmes issued tenders at the same time, limiting the number of bids)
- Procurement using common SoRs across the programme, allowing comparison of costings and VfM across strands
The Prosperity Fund Framework Agreement was used, inviting bids from pre-qualified suppliers. This resulted in bids from three suppliers for the Financial Services and Future Cities strands, from five suppliers for ACROL, and six suppliers for the Energy strand. The number of bids, combined with the quality of bids (with very strong skills and experience within supplier teams and their resource pools) suggests that this was an effective approach in securing value for money.
## Value for Money Criterion 3: Efficient use of resources and inputs
Summary
There is good evidence that the programme has put appropriate monitoring tools and mechanisms in place to monitor the efficient use of resources over time. The overall score for this criterion is 4 out of 5. The score could be higher but at this early point in the programme it has not been possible to review in detail how tools are being used.
Table 21: Efficient use of resources and inputs by Prosperity Fund interventions – scores
Strand	Strand manager self-assessed score	Evaluation team score
Energy	4	4
Future Cities	5	4
Financial Services	4	4
ACROL	2	4

Evidence
- The PT receive a monthly budget monitor from each strand supplier, which summarises expenditure that month (including cumulative expenditure) and also explains any deviations from budget
- There is a monthly narrative commentary, with accompanying dashboard, risk register and lessons learned log
- Invoices are submitted per milestone, and detail the outputs delivered for the milestone.
Templates for all of the above were reviewed during Cycle 1 and correspond with good practice in programme and project management.
It is not clear why the ACROL strand team scored themselves 2 on this criterion. A score of 4 has been awarded because it appears the same processes are in place as for the other strands.
## Value for Money Criterion 4: Causal pathways for primary and secondary benefits
Summary
There is adequate evidence that the causal pathways for the Financial Services, Future Cities and ACROL strands will generate the desired primary and secondary benefits, but these could be better defined, as summarised below and explained in more detail in other sections of this report. Evidence is stronger for the causal pathways set out for the Energy strand however, both in relation to primary and secondary benefits.
Table 22: Validation of causal pathways for generating primary and secondary benefits – scores
Strand	Strand manager self-assessed score	Evaluation team score
Energy	4	3
Future Cities	4	3
Financial Services	4	3
ACROL	4	3

Evidence
In relation to the Fund’s primary purpose: all strands have clearly articulated detailed Theories of Change (ToCs) setting out pathways towards intermediate outcomes, outcomes and impacts. These specify the main assumptions underpinning each ToC. However, there is some variance in the link between strand activities and inclusive growth and reduced poverty.
- The Energy strand shows a clear link with inclusive growth, with four of the five main activities demonstrating this
- The broader evidence on financial inclusion supports the view that the Financial Services strand could lead to inclusive economic growth and lower inequality, by promoting inclusive financial services, better regulation and fintech activity oriented towards poorer people. However, positive impacts on inclusion are only likely to occur in the context of supporting conditions, which are not currently within the ambit of the strand. The strand ToC should therefore be clarified to include the assumption that these supporting conditions do in fact occur, and to highlight the risk that the strand may not achieve inclusive growth if they do not.
- There is also broad evidence for the Future Cities strand to improve urban planning processes and in doing so help promote inclusive growth and reduced poverty. However, until the particular focus of the pilots in each city had not been decided at the time of writing this report, it is not yet clear what the specific causal pathways underpinning the strand will be in practice.
- For ACROL, the evidence that greater cyber-security, improved homicide investigations, and better access to justice will reduce poverty is highly indirect. The logic that improved commercial, administrative and security dimensions at the state and federal level will improve economic growth is better substantiated. The final design of the ToC and the indicators selected for the strand should set out clearly the pathways for achieving these objectives.
In relation to Secondary Benefits (SBs), there is good evidence that all strands have good outline plans as well as appropriate assets (e.g. resources, skills & experience, networks) with which to achieve these. However, SB plans could be improved by providing more detail, as explained in the Secondary Benefits section in the main report (and the annex for each strand). This has contributed to scoring all strands 4 out of 5 for VfM Criterion 4.
## Value for Money Criterion 5: Sustainability of programme activities
Summary
Sustainability is considered here in terms of i) project sustainability – i.e. whether there are mechanisms to promote programme activities being sustained when funding ceases and ii) environmental sustainability. Scores vary between 3 – ‘adequate’ (Energy and Financial Services) and 4 – ‘good’ (Future Cities and ACROL). See Table 23 below.
Table 23: Sustainability of programme activities – scores
Strand	Strand manager self-assessed score	Evaluation team score
Energy	3	3
Future Cities	4 – 5	4
Financial Services	3	3
ACROL	2	4

Evidence
There is no overall programme sustainability strategy or framework, so the analysis has focused on arrangements for each strand.
There is adequate evidence that the Energy Centre is being established in a way that will promote its sustainability after funding ends. These include the planned funding mechanism (with large firms paying subscriptions to access the database on accredited firms and workers); the early investment in branding the Centre to establish an independent presence as a centre of expertise in the market; making permanent improvements in the capacities of regulators, and developing alliances between UK and Mexican organisations for skills training that hold the potential to outlast the programme.
The environmental sustainability of the Energy strand is attested to by the aim to support development of SMEs and workers with skills that are transferrable for work with ‘clean energy’. This is evidenced in the outline proposal for the Draft Climate and Resilience Strategy and Action Plan, which requires the supplier to “set out measures that will be taken to ensure that none of the activities associated to this programme will have a negative impact on climate change”. However, there is no evidence of formal measures to monitor the likelihood of project sustainability over time (in contrast e.g. to the logframe indicators for Future Cities – see below). Similarly, the Resilience Strategy is currently only an outline, rather than a detailed plan. As a result, the overall ranking for Energy on this criterion is 3 (‘adequate’ rather than ‘good’ or ‘strong’).
The Future Cities strand is closely focused on promoting more environmentally sustainable urban planning. There is also evidence of plans to ensure the pilot projects undertaken by the strand are mainstreamed afterwards, though this will remain dependent on factors beyond the programme’s control (i.e. the participating cities have the necessary technical, financial and human resources capabilities to do so). Examples of plans for mainstreaming include up-front commitments from city authorities to implement pilots, and plans to involve business and civil society organisations closely, such that momentum is maintained even with changes in political leadership in the cities involved. The revised draft logframe dated 9 May 2019 also includes indicators (e.g. Primary Indicators 1.1a and 1.1d) on project sustainability, which should help ensure the strand team continues to pay attention to this issue over time. The ranking for Future Cities is therefore 4 (‘good’).
The Financial Services strand is in the process of developing a Climate Resilience Strategy, but this could not be reviewed in this Cycle. There is potential for project sustainability, supported by DAI’s established ways of working, which seek to promote this. By supporting new fintech legislation, the regulation element of the strand should deliver this by definition. The financial education and fintech accelerator elements could also promote sustainability to the extent they help bring about a change in mindset, such that financial institutions and the accelerator itself focus to a greater extent on the ‘base of the pyramid’ in future. It is also possible that fintech start-ups supported by the accelerator will bring about systemic changes in financial services that promote greater financial inclusion. The score for this strand is however 3 for the same reasons as for Energy: the Resilience Strategy is not yet completed, and measures to promote project sustainability are not yet clear in the strand logframe.
The ACROL supplier team articulated a strong conception of project sustainability, highlighting measures and ways of working that could be promoted to encourage reforms to be continued after the end of the programme.
The draft (March 2019) logframe also includes a number of indicators assessing the uptake of reforms promoted through the strands (e.g. the primary indicators for intermediate outcomes 1 to 3). These should provide a good basis for assessing the likelihood of the strand’s work being mainstreamed and continued after the end of the programme. The ranking for ACROL on this criterion is therefore 4.

## Value for Money Criterion 6: Programme leadership, management and oversight
Summary
There is good evidence the programme has established strong governance structures. As it is not possible at this early stage to see how these are working in practice, this criterion has been scored 4 out of 5 (‘good’). When evidence (e.g. minutes of Strategy Board or Programme Management Committee (PMC) meetings, etc.) is available to demonstrate that these arrangements are working as intended the score could rise to 5. Although the strand managers have separately scored this criterion, the overall assessment is provided for the programme as a whole, because management and oversight arrangements are the same for each strand.
Table 24: Ability of leadership, management and oversight structure to support delivery – scores
Strand	Strand manager self-assessed score	Evaluation team score
Energy	3	4
Future Cities	4 – 5	4
Financial Services	4	4
ACROL	3	4

Evidence
The December 2018 Business Case discusses governance arrangements in detail and sets out strong leadership and oversight plans for the programme. Further documents providing details of how these plans will be put into practice include:
- Terms of Reference (ToRs) for the Strategy Board (meeting every four months, providing a strategic oversight role for the programme, and including Mexican officials from the highest levels of government (e.g. presidential advisers).
- ToRs for the PMC meeting monthly with management responsibilities including review of progress, spending, risks etc., and including representation from the respective embassy VT.
- ToRs for individual SGBs, creating spaces for involvement of key stakeholders (e.g. officials from relevant ministries).
There is also evidence of innovative practice in promoting learning (e.g. promoting a Mexico PF-wide Learning Lead for a 12-month period).
The evidence for other VfM criteria (e.g. 5 – efficient use of resources and 7 – risk management/delivery enhancement) also support the score for this criterion.
## Value for Money Criterion 7: Strategies to enhance delivery and mitigate risk
Summary
This criterion is scored as 5 out of 5, based on an assessment of programme level arrangements, but also the detailed description by each strand team of measures to reposition or adapt the programme in response to the election of the new federal government. The programme has good formal mechanisms to assess and mitigate risks, and to enhance delivery. Detailed evidence that these formal mechanisms are working well was not available to the evaluation team in Cycle 1. However, there is excellent evidence that the programme team has worked carefully in recent months to adapt the programme and its strands to fit the priorities of the new administration, and also to take account of potential changes in government at state and local level. This provides a good indication that future risk management will be robust.
Table 25: Strategies and measures adopted to enhance delivery and mitigate risk – scores
Strand	Strand manager self-assessed score	Evaluation team score
Energy	5	5
Future Cities	5	5
Financial Services	5	5
ACROL	5	5

Evidence
There are good mechanisms for assessing and mitigating risk, and for lessons learning including:
- Monthly strand reports (including risk registers)
- Monthly reviews of high-level risks by the PMC, using the programme risk register
- A lessons-learned log, reviewed monthly
- A regional strategy, designed in part to mitigate risks of changing political weather at the national level
- The Strategy Board and Strand Governance Boards, with links to a range of Mexican government and other stakeholders
- An active programme-wide approach to learning, for instance allocating a member of the PT as a learning coordinator on a rotating basis
## Value for Money Criterion 8: Equity of programme design and approach
Summary
The programme has made significant efforts to mainstream gender issues throughout the programme, and there is good evidence that this has been achieved successfully across all strands, which are therefore scored 4. Some elements of the Financial Services strand have the potential for a transformative impact on gender issues, so this is scored 5. There is also evidence that wider inclusiveness issues (i.e. beyond gender) have been considered, though with less focus than on gender.
Table 26: Relevance and robustness of Value for Money measures – scores
Strand	Strand manager self-assessed score	Evaluation team score
Energy	4	4
Future Cities	4	4
Financial Services	5	5
ACROL	3	4

Evidence
G&I issues were actively considered in programme design, as evidenced in the December 2018 BC. A separate E&L analysis of gender issues for the programme carried out in early 2019 also gave a green rating for the following issues: programme design; internal capability/institutional incentives; accountability mechanisms; and partnerships. An amber rating was given on the issue of financial resources, as no information was available at that moment on how G&I-related activities had been costed into budgets.
The PT has sought additional support to strengthen gender measures, including consulting DFID’s Work and Opportunities Help Desk, and commissioning a gender audit. It has continued this into the inception phase, for instance holding bi-monthly cross-programme gender meetings, to coordinate work between the different suppliers on this issue.
The bids for all strands illustrate that G&I issues were integrated into proposals rather than provided as stand-alone elements. Indicators in the March 2019 logframe for each of these are disaggregated by sex, and there are some specific G&I indicators. Several indicators in each logframe are disaggregated by income quintile. The suppliers are all required to deliver G&I strategies by the end of inception.

Annex 9: Theory of Change checklist criteria
The Theory of Change (ToC) checklist guides evaluators through specific questions to assess the strength of the ToC. The 14 criteria and their guiding questions are in Table 28 below.
Table 28: Theory of Change checklist
#	Criteria	Guiding Questions
1	Context	Is it clear that the ToC reflects the context in which the programme will be operating (political, social, economic, technological, legal and environmental)? / Is this context the same across the whole programme? Or does it differ by country or by intervention?
2	Beneficiaries	Is it clear what beneficiaries (direct and indirect) will benefit from the programme? Are they specified? / Is it clear what behavioural change(s) are sought in these beneficiaries?
3	Actors	Is it clear what other relevant actors (CSO, private sector, academic, government, or other donors) may be involved or impacted? / Is it clear how these actors interact to effect the change outlined in the theory of change?
4	Assumptions	Are clear assumptions made within the ToC? / Are these specified in terms of causality? Context? Beneficiaries or actors? / Are they meaningful and can be validated? / Are they linked to levels of the theory of change? / Do they set out the critical factors that can affect the success of work?
5	Causality/pathways	Is causality in the ToC shown? Is it clear how the interventions planned will lead to impacts? / Is it clear how a short-term outcome will lead to (or is necessary) to reach the one above it? / It is clear how these changes work with each other in a non-linear fashion?
6	Coherence	Is it clear how the programme will deliver change that is greater than the sum of its parts? / Is it clear who the interventions will occur alongside each other to realise this change?
7	Deliverability	Is the change exhibited in the ToC within the sphere of influence of the programme? How deliverable is the programme? / How realistic are the assumptions?
8	Gender & inclusion	Is it clear how the programme will realise benefits for women and socially excluded groups? / Is this made explicit in the ToC?
9	Value for Money	Is it clear how the programme will realise value for money?
10	Secondary benefits	Is it clear how the programme will realise both primary purpose and secondary benefits? / How do these benefits relate to one another? Is this clear and logical? / Is there the right balance between primary purpose and secondary benefit?
11	Sustainability	Is it clear how the change set out will be sustainable beyond the lifetime of the programme?
12	Additionality	Is it clear how the change set out is additional and additive to other activities planned or underway in part governments, other donors etc.? / Is there clear evidence that without this intervention(s) the change would not be realised or would not be fully optimised?
13	Fund ToC	Is it clear how the programme relates to the Prosperity Fund ToC? Is it made explicit? / Is there clear evidence of similar programming or activity by Prosperity Fund, the UK government, other governments, other donors that the programme has learnt from? Or is there evidence in the literature? / Is it clear what elements are shared and different?
14	Fund linkage	Is it clear how this programme crosses-over/is aligned with other programming being conducted across the PF? / Is it clear how these programmes will work together or deliver shared benefits?

 The ratings for these criteria are given according to this scoring:
- Weak – insufficient, superficial or uncritical
- Potential – some coverage, but gaps in important areas or in critical thinking
- Reasonable – fairly complete and critical thought in most areas, but some yet unclear
- Robust – clear, comprehensive, well-formulated, strong critical thinking

Annex 12: Bibliography
ACROL Crime Types—ToC (ppt), PA Consulting ACROL CDU. 25 April 2019
AMLO (Andres Manuel López Obrador) enjoys 86% approval rating, strong support for fuel theft strategy, Mexico Daily News 8 February 2019. https://mexiconewsdaily.com/news/amlo-enjoys-86-approval-rating/
Call Off Contract (ACROL) between The United Kingdom Secretary of State for the Foreign and Commonwealth Office and PA Consulting Services Limited in respect of the Mexico Programme – Anti-Corruption and Rule of Law. 12 February 2019
Call Off Contract (Energy) between The United Kingdom Secretary of State for the Foreign and Commonwealth Office and DAI (Europe) Limited in respect of the Mexico Programme – Energy. 6 February 2019
Call Off Contract (Financial Services) between The United Kingdom Secretary of State for the Foreign and Commonwealth Office and DAI (Europe) Limited in respect of the Mexico and British Embassy Prosperity Fund Financial Services. 18 February 2019
Call Off Contract (Future Cities) between The United Kingdom Secretary of State for the Foreign and Commonwealth Office and PricewaterhouseCoopers, LLC in respect of the Mexico and British Embassy Prosperity Fund Future Cities. 12 February 2019
Corruption Perception Index/Mexico, Transparency International. https://www.transparency.org/country/MEX
Cross-government Prosperity Fund programmes. https://www.gov.uk/government/collections/cross-government-prosperity-fund-programmes
Data Quality Briefing Note 1. 7 February 2019. https://www.pflearning.co.uk/x/D4a8
Data Quality Briefing Note 2. 2 April 2019. https://www.pflearning.co.uk/display/PSDQ/Data+Quality
Desarrollo orientado al transporte. Regenerar las ciudades mexicanas para mejorar la movilidad, ITDP México/Embajada Británica en México, Mexico 2013. http://mexico.itdp.org/wp-content/uploads/Desarrollo-Orientado-al-Transporte.pdf
Ease of Doing Business Index/Latin America, the World Bank. http://www.doingbusiness.org/en/rankings?region=latin-america-and-caribbean
Family Approach Paper: Energy and Low Carbon. PF Evaluation and Learning. April 2019
Family Approach Paper: Financial Services. PF Evaluation and Learning. January 2019
Family Approach Paper: Transparency and Anti-Corruption. PF Evaluation and Learning. May 2019.
Final Business Case, “Stimulating Opportunities for Productivity and Growth and Tackling Market Failures.” Mexico Prosperity Fund. Approved December 2018.
Financial Inclusion: New Measurement and Cross-Country Impact Assessment, Cyn-Young Park and Rogelio V. Mercado, Jr., ADB Economics Working Paper Series, No. 539, March 2018.
Financial Services – DAI Europe Ltd. ToC (word), April 2019.
Financial Services — DAI Europe Ltd. Logical Framework (excel), April 2019.
Future Cities— PwC Indicative Future Cities Logical Framework (excel), April 2019.
Future Cities— PwC Revised ToC (ppt), April 2019.
Future Cities— PwC 1.2 Delivery Plan - Inception (n.d).
Gender and Inclusion Approach Paper and Scorecard, Liisa Kytola, PF Evaluation and Learning. April 2019. https://www.pflearning.co.uk/x/5oOn
Invitation to Tender PF 18 015 (Statement of Requirements and annexes, Energy). Prosperity Fund. 30 July 2018.
Invitation to Tender PF 18 016 (Statement of Requirements and annexes, Financial Services). Prosperity Fund. 30 July 2018.
Invitation to Tender PF 18 017 (Statement of Requirements and annexes, Future Cities). Prosperity Fund. 30 July 2018.
Invitation to Tender PF 18 018 (Statement of Requirements and annexes, ACROL). Prosperity Fund 13 August 2018.
KII with PF ACROL team. Mexico City, 25 April 2019
KII with ACROL strand supplier. Mexico City, 26 April 2019
KII with PF Energy team. Mexico City, 24 April 2019
KII with Energy strand supplier. Mexico City, 25 April 2019
KII with PF Financial Services team. Mexico City, 24 April 2019
KII with Financial Services strand supplier. Mexico City, 25 April 2019
KII with PF Future Cities team. Mexico City, 24 April 2019
KII with Future Cities strand supplier. Mexico City, 25 April 2019
KII with Ambassador/Mexico. Mexico City 23 April 2019
KII with PM, PF/Mexico. Mexico City 23 April 2019
KII with Prosperity and Political Counsellor. Mexico City 23 April 2019
Milestone 1.1: Agreed Final Stakeholder and Community Engagement Plan for inception phase. DAI Mexico British Embassy Prosperity Fund Energy Strand Programme. 29 March 2019
Milestone 1.1: Agreed Final Stakeholder and Community Engagement Plan for inception phase. DAI Mexico British Embassy Prosperity Fund Financial Services Strand Programme. 17 April 2019
Milestone 1.3: Criteria of the Selection of States DAI Mexico UK Embassy Prosperity Fund Financial Services Strand Programme. April 17th, 2019
Milestone 1.4: Outline of Gender and Inclusion Mainstreaming Strategy and Action Plan. DAI Mexico British Embassy Prosperity Fund Energy Strand Programme. 8 March 2019
Milestone 2.1 Agreed plan for MREL engagement and compliance. DAI Mexico British Embassy Prosperity Fund Energy Strand Programme. 17 May 2019
Mexico Programme Cycle 1 Approach Paper, PF Evaluation and Learning. 1 April 2019
Mexico Prosperity Sector Plan – Energy. Mexico Virtual Energy Team. 3 May 2019
Mexico Prosperity Sector Plan – Financial Services. Mexico Virtual Financial Services Team. 21 September 2018
Narrative for Methodology for State Selection—final analysis, ACROL CDU. April 2019
National Development Plan 2019-2024. Office of the President. 27 April 2019
Oil and Gas Industrial Baseline Study Outline. DAI Mexico British Embassy Prosperity Fund Energy Strand Programme. 25 April 2019
Outline Business Case, “Stimulating Opportunities for Productivity and Growth and Tackling Market Failures.” Mexico Prosperity Fund. Approved March 2018.
Output 1.1: Stakeholder Engagement and Community Outreach Plan (draft for discussion). PwC for PF Mexico Future Cities Programme, March 2019.
Output 1.3: Proposed criteria for city selection (draft output). PwC for PF Mexico Future Cities Programme April 2019.
Output 1.4: Gender and Inclusion Strategy and Action Plan Outline. PwC for PF Mexico Future Cities Programme April 2019.
Proposal to PF/Mexico 18 015 Energy (technical bid and annexes; commercial bid and annexes), DAI Europe Ltd. 17 September 2018
Proposal to PF/Mexico 18 016 Financial Services (technical bid and annexes; commercial bid and annexes), DAI Europe Ltd. 17 September 2018
Proposal to PF/Mexico 18 017 Future Cities (technical bid and annexes; commercial bid and annexes), PwC. 27 September 2018
Proposal to PF/Mexico 18 018 ACROL (technical bid and annexes), PA Consulting. 26 September 2018
Prosperity Fund Monthly Progress Report (April 2019) - Financial Services Strand, DAI Europe Ltd. April 2019
Rule of Law Index, Mexico. World Justice Program. http://data.worldjusticeproject.org/#/groups/MEX
Secondary Benefits Cycle 1 Approach Paper, PF Evaluation and Learning. https://www.pflearning.co.uk/x/zgH8
Sistema Nacional Anticorrupcíon (National Anti-Corruption System). http://www.ley3de3.mx/es/
Strand Governance Board Terms of Reference (draft). ACROL Programme, PA Consulting. 5 March 2019.
Transformation Index, BTI. https://www.bti-project.org/en/key-findings/regional/latin-america-and-the-caribbean/
UN Sustainable Development Goals https://sustainabledevelopment.un.org/sdgs
VfM Scorecard Guidance, PF Evaluation and Learning. March 2019. https://www.pflearning.co.uk/x/e4K8

Annex 13: Cycle 1 and Cycle 2 timelines