Evaluation report title and date: Mexico Prosperity Fund Cycle 1 Evaluation Report / August 2019 / Link to evaluation publication on gov.uk:

Response to evaluation report (overarching narrative)
This Cycle 1 evaluation report for the Mexico programme covers the period from June 2017 through May 2019 (mid-point in the inception phase). The objectives for Cycle 1 are to: / Ensure the design and positioning of each strand and the programme as a whole are strong and align with overall Fund objectives. / Provide findings and insights to the programme team (PT), to enable adaptations necessary to achieve outcomes and goals. / Support the preparation of the programme’s first Annual Review. / Provide findings and insights on family and thematic issues. / Support adaptive programme management within PF Mexico. / The evaluation report showed that the programme’s design creates plausible causal pathways and this will ultimately lead to achieve the Mexico PF goal. Furthermore, the evaluation showed the effort the strands have made to mainstream G&I considerations into interventions, but with some areas to improve the scope. Additionally, the report shows that there is evidence the programme will represent VfM and will achieve SBs. Finally, the evaluation team provided 7 constructive recommendations and 9 strand specific recommendations. The programme has analysed and taken forward most of the recommendations.

Recommendation	Party that recommendation is directed to	Accept, partially accept or reject	If “accepted” or “partially accepted”, give action plan for implementation and if “rejected” or “partially accepted”, give reason for rejection / only partial acceptance
Programme Recommendations
Assess cross-cutting theme assignments within programme teams to mitigate soloing and to offer staff capacity building.	Head of PF/Mexico	Accept	The programme team has cross-cutting roles that cover different topics that go from G&I to regional engagement.
Define “poverty” to ensure common baselining and improve strategic communications with government stakeholders.	Head of PF/Mexico	Accept	This will be reviewed by each programme team with their implementing partners. Each programme will take as a baseline the definition from national sources such as CONEVAL and/or INEGI
Use Embassy’s Impact Bank assessments to provide basis for assessing SB network effects and soft power.	PMC	Accept	This will be revised with the SB lead, with the SB plans and seek further guidance from London
Account for gender and inclusion allocations in costed workplans to reflect fully the Financing dimension in the G&I scorecard.	Suppliers and Strand PMs	Accept	This will be reviewed within the programme teams and then discussed with each of the implementing partners.
Make strategic communications central to effort, backed up by verifiable actions, including message discipline within and across strands to build consistency and mitigate risks associated with inaccurate statements.	Head of PF/Mexico and Strand PMs	Accept	Governance and Communications Officer will be hired into PT
Prior to implementation, map all strands for regions, stakeholder, and interventions to identify all areas of synergy, overlap or gaps.	Head of PF/Mexico and Strand PMs	Accept	A Map where all strands are operating will be developed to identify synergies among the strands.
Strand Recommendations
Capture potential and mitigation efforts related to supplier in risk registry	ACROL PM	Accept	This will be discussed with the implementing partners so that the programme team receives monthly risk registries from suppliers and also for PT to identify and register risks and mitigation efforts. / The main programme-level risk register will be refreshed monthly by PTs; this register is not shared with suppliers. The PTs will be able to add sensitive risks there that would not be added to the strand register. The top risks from the main register will be presented at the monthly PMC.
Push for interventions that provide incentives for the use of financial services to increase income, productivity and education, rather than consumerism.	FS PM (all PMs should take note)	Accept	This will be reviewed and verified by the PT, to make sure that the interventions focus on education and productivity in the financial services sector.
Review indicators to ensure full reflection of gender and inclusion metrics	All Strand PMs	Accept	As part of the logframe, there will be indicators that will be disaggregated. So this will allow to know the impact of different interventions on different G&I aspects
Articulate the linkage to improving inclusive economic growth	ACROL PM (all PMs should take note	Accept	This will be discussed with the implementing partners, so that the programme reflects a clear causal pathway to the impact of the PF
Review assumptions within ToCs and logframes prior to inception phase sign-off to test rigour and causal pathways.	All Strand PMs	Accept	This will be reviewed by the MREL lead, to verify the causal pathways, assumptions, statements and narrative in the ToC and logframe
Prior to implementation, review strand level groups, boards and committees to ensure no duplication with other governance and management bodies.	All Strand PMs	Accept	Governance and Communications Officer will be hired into PT to follow-up to this recommendation