## Annual Review - Summary Sheet

Title: Monitoring, reporting, evaluation and learning in the Prosperity Fund
Programme Value: £37m		Review Date: Dec 2020
Programme Code: N/A	Start Date: September 2017	End Date: November 2021

Summary of Programme Performance
Year	2018/19	2019/20	2020/21	2021/22
Programme Score	N/A	B	A
Risk Rating	N/A	Major	Moderate

Summary of progress and lessons learnt since last review
The overarching objective of Monitoring, Reporting, Evaluation and Learning(MREL) in the Prosperity Fund (PF), as documented in the business case, is to provide insight and intelligence to drive innovation and improvement, to support the effective delivery of high-impact programmes and a high-impact fund. The service also contributes to the evidence base on mutual prosperity and contribute to accountability.
The delivery of the MREL programme was split into two contracts. A consortium led by PA Consulting were selected to deliver Monitoring and Reporting (MR) and a consortium led by TetraTech were selected to deliver Evaluation and Learning (EL) services. The contracts are managed by the Joint Funds Unit (JFU) MREL team and overseen by a Senior Responsible Owner (SRO), the Head of the JFU.
This is the second annual review of the PF’s MREL programme, covering the period from November 2019 to October 2020. The first annual review, completed last year, found that the decision to establish a MREL function was a sensible one and that the MREL programme was delivering against its core requirements. However, the programme scored a B as the annual review identified several practical and operational challenges hindering the delivery of a more efficient and effective MREL service and a number of recommendations were made to address these challenges.
This annual review has found that these recommendations have largely been implemented and that partners have delivered as expected against the majority of outputs over the last year. Considering the exceptional year, including changes to activities due to COVID-19 and the ODA prioritisation process, that partners have had to implement through shows the ability of both the programme’s management team and partners to adapt and continue to deliver under challenging circumstances.
The annual review concluded that the programme should score an A and be regarded as carrying moderate risk. Output 1 (monitoring and reporting) was scored a B; outputs 2 (evaluation) and 3 (learning) scored an A and output 4 (technical assistance) an A+.
Solid but at times mixed progress has been achieved through the programme and by the two different suppliers with an overall score of A reflecting this.
Highlights from the last year, include:
A common theme through almost all interviews was positive feedback on the both the MR and EL teams. Especially on their willingness to help, responsiveness and proactivity in reaching out to programme teams (PTs). Stronger relationships between PTs and programme evaluation leads (PELs) for example have helped encourage the uptake of learning.
Technically, delivery partners have delivered to a good standard with the Prospero sprint helping increase the amount of uploaded data on the MR system and EL evaluation products receiving consistently good scoring from the Evaluation Quality Assurance and Learning Service (EQUALS), an independent quality assurance mechanism. The PFLearning platform was viewed as a high quality, visually attractive and accessible product.
Management and delivery teams faced challenges with staffing issues, COVID-19 and the ODA reprioritisation process which they have managed well. An example was the EL team and the rapid deployment of a COVID-19 site on PFLearning.
Another highlight has been the technical support provided by EL to PTs through the use of flexible days. These were found to be very programme relevant, easy to access and covered a variety of uses including support on logframes, gender and inclusion (G&I) and secondary benefits (SB) and Theory of Change (ToC) strengthening.
Summary of recommendations for the next year (more detail in relevant sections below)
Number	Topic	Recommendation	Who
1	MR focus	JFU to review their expectations of the MR contract with the remaining time and resource left including which data are most needed so they can be prioritised.	JFU
2	Prospero user experience	MR Hub to continue to improve Prospero user experience within budget pressures – prioritising the themes of data uploading and editing to ensure as much data are on the system as possible.	MR team
3	Prospero learning	MR Hub to put processes in place to extract as much learning and use out of Prospero as possible	MR Team
4	Evaluation frequency	Continue to monitor and manage carefully the sequencing and timing of programme evaluations, moving away from an annual cycle, which would free up the EL to focus on more bespoke learning needs of programmes.	JFU
5	EL support to learning	The remaining focus of the EL contract should be on helping the PF document evidence for learning for programmes (including PCR) and on the PF approach itself.	JFU and EL team
6	Evaluation publication	The Foreign Commonwealth and Development Office (FCDO) need to put plans in place to adhere to the PF evaluation publication policy	FCDO
7	Evaluation evidence	Ensure evaluation evidence is highlighted to annual review teams, including G&I, VfM and SB analysis.	PTs
8	PFLearning	Maintained PFLearning and, as PF governance arrangements are confirmed, review this learning function in its new context.	JFU and EL team
9	Learning	Sustainability plan for learning to be considered for the period post contract (November 2021)	JFU
10	PFLearning induction	Produce a short recording for PFLearning induction	EL team
11	Learning products	Reflect on successful learning products/events and develop lessons for PELs and other thematic evaluators in developing their own learning products.	EL team
12	MREL collaborative working	EL and MR to continue to build on the progress they have made over the past year on collaborative working and ensure they are joined-up wherever possible.	EL and MR teams
13	Technical assistance expectations	JFU to review their expectations of MR and EL under Output 4 with the remaining time and resource left on contracts – and whether these differ for PTs based on their capacity.	JFU
14	VfM	MREL suppliers to provide regular updates on VfM achievements across contracts ensuring maximum cost efficiency.	MR and EL teams
15	VfM	In relation to costs the JFU MREL team should consider a more effective approach in understanding individual workstreams budgets for assurance and transparency	JFU MREL
16	Risk	The JFU MREL team to continue to regularly monitor their risk register and assess impact of the Spending and Integrated reviews.	JFU MREL

Summary response by the Programme Senior Responsible Owner (SRO) (Joelle Jenny – Director, Joint Funds Unit)
I agree with this overall assessment. I support the review team’s judgement that the MREL programme has broadly met its objectives for the period, via “solid but at times mixed progress”, and note that this is an improvement on performance compared to the last review.
I am particularly pleased that the programme’s responsiveness and proactivity has been recognised given this year’s exceptional circumstances that have meant pivoting several activities. I agree that highlights have included the Prospero ‘sprint’, the technical quality of evaluations, flexible technical support to programme teams, and COVID-19 mini-site on PFLearning.
I also acknowledge the feedback from stakeholders that not all parts of the MREL service are working perfectly for all, including user experience on Prospero and the workload required to engage in both annual reviews and annual evaluations. These issues will help guide workplans for next year.
The review’s recommendations are welcome and should help to drive delivery for the programme next year – as the Prosperity Funds moves onto the FCDO’s baseline. I would highlight the need for programme teams to continue to develop their own MREL capacity and capability as they mature, and for the MREL programme to adapt in parallel to focus more on cross-Fund learning and less on capacity support and development (as was appropriate earlier in the PF’s lifetime). In a very tight ODA context that will require difficult choices, flexibility will remain an important requirement.

List of Acronyms
AR = Annual review
Delivery partners = implementing partners (private companies, multilateral organisations or NGOs) hired by programme teams to implement PF programmes
EL = Evaluation and Learning contract
EQUALS = Evaluation Quality Assurance and Learning Service
FCDO = Foreign, Commonwealth and Development Office
G&I = Gender and Inclusion
GPST = FCO Global Programme Support Team
JFU = Joint Funds Unit
JFU Points of Contact = the individual contact person in the JFU. Each programme has one point of contact.
MR = Monitoring and Reporting contract
MREL = Monitoring, Reporting, Evaluation and Learning
ODA = Official Development Assistance
PF = Prosperity Fund
PFDU = FCO Prosperity Fund Delivery Unit
PEL = Programme Evaluation Leads
PTs = Programme Teams
SB = Secondary Benefits
SRO = Senior Responsble Owner
ToC = Theory of Change
VfM = Value for Money
## A. INTRODUCTION AND CONTEXT (1 page)

DevTracker Link to Business Case:	https://www.gov.uk/government/publications/prosperity-fund-monitoring-reporting-evaluation-and-learning

Outline of the programme
As part of its commitment to ensure the PF delivers good impact and value for money (VfM) across the Portfolio, the JFU manage a system to support, coordinate and partially deliver MREL across the Portfolio.
The programme’s impact objective is “A more effective Prosperity Fund – that is higher impact, better value for money and better managed – both in terms of the portfolio and individual programmes due to the availability and uptake of MREL recommendations and support”. In short, the programme is responsible for providing MREL support across the whole of the PF, through independent evaluation, providing technical advice on MREL to PTs and by aggregating and analysing information to provide a portfolio-level view for JFU and other parts of HMG. Key outcomes, intermediate outcomes and outputs are described in the programme ToC.
This MREL system is not a replacement for programme level monitoring functions but looks to provide a range of portfolio and programme level services. These services are designed to support management and accountability by enabling all three levels of the PF (Portfolio, Departments and Programmes) to access results, progress dashboards and independent assessment of contribution to outcomes. These services are also designed to improve practice across the PF network by surfacing, documenting and sharing the evidence-base and learning underpinning the design and delivery of what is a large scale and innovative fund to support adaptation, course corrections and future design.
The PF portfolio level MREL capability is split and outsourced into two synergistic components:
Component 1: Monitoring and Reporting (MR)
Monitoring and Reporting is delivered through a 4-year £13m contract (Sept 2017 – Nov 2021) with PA Consulting.
Programme ToC and logframes are central to measuring results and adapting to achieve high impact. The MR technical assistance work delivers demand-led support to assist programmes in refining ToC and developing logframes for their programmes to ensure they can link into the PF level ToC.
The MR supplier is also tasked to capture reporting from across the Portfolio and ensure it can be utilised at a project, programme and fund level to inform decisions. This is delivered through an internet-based platform called Prospero.
Component 2: Evaluation and Learning (EL)
Evaluation and Learning is delivered through a circa 4 year £24m contract (Sept 2017 – Nov 2021) with a TetraTech-led consortium including Integrity and LTS/Niras International.
EL are important functions to help ensure a focus on key objectives, maximise impact and VfM, and manage risk.
While supporting accountability, this is not the primary purposes of EL; instead, learning activities should help generate an evidence base (on primary purpose and SB), help improve the efficiency of PF programmes, support sharing of knowledge across the fund and inform communication of impact. EL should also address the needs of different stakeholders:
- At fund level it should assess the extent to which PF is contributing to inclusive economic growth and delivering SB while doing so and inform thinking on future, similar funds through synthesising lessons from programmes and cross fund evaluation of particular themes;
- At programme level it should test ToC and establish, while the programmes are running, whether they are delivering the outputs and outcomes that will likely lead to impact. Useful and usable learning will contribute to identifying programmes and projects not performing optimally and allowing corrective measure.

To deliver on this EL undertake independent evaluations across a variety of levels (programme, sector, theme, whole-fund); provide flexible evaluation support to programme teams and produce and disseminates a range of learning products. This work is supplemented by an MoU between JFU and FCDO to provide quality assurance of evaluations by their EQUALS programme.
An annual EL cycle will provide the basis for an evidence-based review of progress on what has been achieved, how and why, while enabling the sharing and use of evidence from evaluations to support decision making at project, programme and fund levels.
In turn, a cohesive picture of the programmes, projects / programmes in similar sectors or that target an intermediate outcome, cross-cutting themes and the fund itself will be generated over time. To support sharing of evidence and learning EL have designed and maintain the PFLearning platform, a curated web-based platform enabling sharing of information across the fund.
The programme has been successful in getting a large MREL system up-and-running effectively, for example the majority of PF programmes in delivery have up to date ToCs and logframes and are involved in peer learning across the PF. The two digital platforms (Prospero and PFLearning) are innovative in their ability to work cross-government, and a diverse range of information and data has been collected to help PTs to adapt and learn as well as for the fund to learn about its own progress.
The programme has faced some challenges since its inception. An ongoing challenge has been delays to the approval of PF delivery programmes or slow implementation leading to some MREL plans being disrupted and/or required to adapt. Over the last year several new challenges have arisen, including: the COVID-19 pandemic requiring suppliers to adapt their plans as well as impacting on PF delivery programmes’ ability to carry out theirs; this year’s ODA prioritisation process leading to delayed and reduced activities for both contractors; and staffing gaps in the JFU MREL team has meant a small number of staff have been responsible for managing and assuring a large amount of work.
Introduction to this Annual Review
This is the second annual review of the PF MREL programme work and covers the period from November 2019 to October 2020.
The annual review represents an opportunity to review the performance of the MREL contracts and consider whether the activities and outputs are of sufficient quality, timeliness and continued relevance – directly contributing to the effective delivery of the desired MREL objectives for which the suppliers are contracted. The annual review also captures some reflections on the design of the MREL service
The review was independently led by a FCDO Statistics and Evaluation Advisor who is familiar with ODA programming and is currently based in Nepal and has had no role in the PF. The review team also included two new starters in the JFU MREL team. One a Statistics Advisor the other a Commercial Advisor. The fourth member of the team is an Evaluation Advisor from the FCDO PFDU team.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)
Conclusions
The 2019 annual review was carried out without a logframe or Theory of Change (ToC) in place so progress was assessed against the ambitions set up in the Business Case. JFU, with partners, developed a logframe and ToC for the MREL programme prior to this review. The review team have reviewed supporting documentation and interviewed over 50 respondents to gather supporting evidence of progress of the MREL programme towards outcome delivery.
As discussed in the 2019 annual review the decision to set up a centralised MREL system for the PF when the fund began has proved to be effective in supporting accountability and the fund’s credibility, allowing effective working across multiple HMG departments, ensuring greater consistency and establishing the beginnings of a MREL culture amongst PTs. At the time the MREL programme was designed a central approach managed by JFU made sense as FCO and OGDs PTs did not have the capacity to commission MREL themselves. This centralised approach allowed greater consistency in approaches and the potential to aggregate results and learning at the portfolio level.
As outlined in the MREL programme ToC, robust and timely Monitoring, Reporting, Evaluation and Learning (MREL) helps ensure that programmes are held to account for performance and should support programmes and portfolios to improve design and delivery, thereby contributing to increased impact, sustainability and VfM.
Timely and relevant MREL data, combined with a culture of learning and reflection should generate evidence to inform decision-making and adaptive portfolio management, enabling donors to deliver policy objectives and meet partner country needs in a way that is suitable in the local context. By generating findings and recommendations for internal learning and improvements, evaluation can also contribute to the evidence base. MREL services will also support programmes to identify and share results stories with internal and external audiences and help to clearly show alignment with HMG priorities.
The ToC outlines how through 4 key outputs the MREL programmes aims to support delivery against key outcomes and ultimately contribute to a more effective PF – that is higher impact, better value for money and better managed - both in terms of the portfolio and individual programmes. The sections below summarise performance of each output for the programme and whether these indicate progress against outcomes as detailed in the ToC.
Output 1 aims to deliver timely and accurate information on programme and portfolio performance for PTs and JFU. Leading to an increased ability for PTs and JFU to identify and report on G&I, results, risks and VfM and communicate this to a wide range of stakeholders. Which in turn should increase the ability of JFU and PTs to apply best practice standards of transparency and accountability and for evidence-based decision making and adaptive programme and portfolio management.
The MR team received very positive feedback from interview respondents including about their willingness to help, responsiveness and proactiveness in reaching out to programme teams. Especially during the COVID-19 crisis, feedback was that MR staff “went out of their way to try and help and support programmes”.
Based on performance against logframe indicators the MR team moderately under delivered over the last year and scored a B for this output. The main reason for this being lower than expected levels of satisfaction and engagement with the Prospero platform and resulting products. Discussions with a wide variety of users corroborated this finding.
It was clear that Prospero was seen more as a portfolio tool than a tool for programme teams and that programme teams found it clunky and time consuming to upload data. These two issues we feel have led to a lack of data being loaded onto the system reducing the likelihood of delivery against outcomes as described in the ToC. It is worth noting that the Prospero Sprint successfully increased the amount of data on the system, but more are needed to enhance its utility. This should happen as the portfolio matures.
The MREL programme has done some important work in bringing together data and evidence from across several HMG departments. It is potentially too early to say whether this information is really being used for evidence-based decision making or adaptive management. There are signs that this is starting to happen at programme level (with closer ties between PEL and PTs, which is expanded on below under output 4) but it is not clear that Prospero is enabling evidence based decision making at programme level as PTs already have the data they need. At fund level the information is being used for background context in Board meetings but with concerns around quality and timeliness it is not key to decision making.
It is expected that this work should increase the ability of JFU and PTs to apply best practice standards of transparency and accountability but it is difficult to see this being achieved without a real drive across relevant HMG Departments to publish data and evaluation findings.
Under Output 2 the theory of changes states that the delivery of technically robust and independent evaluation products with clear recommendations for PTs and JFU should lead to an intermediate outcome of an improved evidence base on mutual prosperity, SB and X-HMG ODA delivery. This improved evidence base should then support the outcome of an increased ability of PTs and JFU to make more evidence-based decisions and adaptive programme and portfolio management.
The EL team delivered against planned activities - with any changes in delivery dates due to delays in feedback from an under resourced HMG team and rescheduling of annual reviews due to COVID-19 disruptions. The quality of products through these activities received consistently good scoring from EQUALS, an independent quality assurance function. On balance between the indicator scoring and feedback from interview respondents the review team agreed that delivery expectations against this output were met so a score of A was given.
Satisfaction with this service was high, especially from PTs who found working closely with Programme Evaluation Leads (PEL) a good way to maximise learning. Feedback from JFU, portfolio managers and HMG advisers was a little less positive and engagement from their side had not been as high, with the result that benefits of the MREL service not always fully understood or realised.
The ToC states that this output should lead to an improved evidence base on mutual prosperity, SB and X-HMG ODA delivery. This evidence base is emerging in line with the (delayed) delivery of the fund. Focussing EL efforts on further developing the evidence base and on learning and practical support to PTs to apply this learning could become a focus for the remainder of this contract. JFU should instruct the EL supplier to also focus on capturing learning around the strengths and weaknesses of the PF mechanism itself.
As this evidence base develops it is expected to support programme teams and JFU to make more evidence-based decisions and undertake adaptive programme and portfolio management. There is still a question over the capacity of PTs to effectively use this evidence and learning to influence decision making and adaptive management. There is some initial evidence of this happening from the ASEAN LCE, Mexico and ASEAN Economic reform for example but limited other evidence to support this. To make full use of this evidence base as it develops there will likely need to be an effort by relevant HMG Departments to build capacity of PF staff to understand how to use evidence in adaptive management and also evolve the PFs governance structure to ensure new evidence is used in strategic decision making.
The ToC states that the delivery of MREL resources, publications and events to support PF staff engagement with data, findings and learning under output 3, and access to expert technical assistance under output 4, aims to increase engagement with and understanding of MREL amongst PF staff. This increased understanding should then ensure that PF staff have the confidence and ability to deliver and oversee high-quality MREL.
Under output 3 delivery against the logframe met or moderately exceeded expectations and combined with feedback from users the review team agreed that this output met expectations so was scored as an A. The EL team, through the Knowledge Management Team provided a timely and accessible service through the PFLearning platform and an ability to adapt as shown through necessary changes following the onset of COVID-19 and the ODA budget re-prioritisation. The rapidly deployed COVID-19 site on PFLearning was a particular success.
EL produced good quality learning products, made them available in different formats and improved communication making learning more accessible. Although the PFLearning platform has been developed as designed and managed to a high quality a majority of interview respondents said they did not regularly use the site to access or share learning, and one of the most common uses of the PFLearning platform was as a document repository and to allow sharing of documents across HMG departments. A key feature of PFLearning is the network area and communities of practice enabling X-fund learning. The G&I CoP is the best example of this and is actively led by a group of HMG SDAs.
The MR teams delivery against logframe indicators for output 4 ranged from met expectations to substantially exceeding expectations. Combined with feedback from users an output score of A+ (moderately exceeded expectations) was agreed.
The majority of users were happy with the technical support received on ToC and logframe development. JFU took the decision to use the relative strengths of the MR and EL teams in a joined-up way to provide technical support to programme teams through flexible days. This was a recommendation from the previous annual review and aimed to address capacity issues within PTs while allowing EL technical experts to bolster MR resources. Flexible days were a big win and used for a variety of support including not just strengthening of ToC and logframes but also developing KPIs and support on G&I and SB.
The ToC states that both output 3 and 4 should lead to an intermediate outcome of increased engagement with and understanding of MREL amongst PF staff and that this would lead to an outcome that PF staff have the confidence and ability to deliver and oversee high-quality MREL.
Through the PFLearning platform and the provision of joined up technical assistance including flexible days there is good evidence that MREL support has helped increase the capacity of PTs to engage with and understand MREL. For example, flexible days have helped improve technical capacity of programme teams to strengthen for example ToC, logframes and VfM scorecards.
Although the quality of products being delivered by partners is not in question there are some doubts if enough fit for purpose monitoring and evaluation information for programme management is consistently available for programmes yet. Largely as it is still too early in most programmes life cycle and there’s not a lot of evidence of programme teams using the available evidence from this work to make major changes to programming, although operational changes are evident, informed by evaluations. Solid MREL foundations have been put in place which is a major achievement considering the cross HMG delivery approach and the lack of internal resources to support this work.
With the FCDO merger there potentially are more internal resources available for PTs to draw on through the professional cadres of sectoral and technical specialists so it will be important for JFU to consider this when making decisions around the final months of this contract and what it delivers and what MREL function is put in place following this.
Has the MREL work contributed to PF staff having the confidence and ability to deliver and oversee high-quality MREL themselves? Not consistently, although to be fair it is important to recognise that this capacity has improved. At PT level the capacity to engage and manage MREL clearly varies across teams and it is doubtful that most teams have the MREL expertise to do this completely on their own, nor should they be expected to. Some support will always be needed, the question is where is this support best to come from?
There have been several challenges over the lifetime of the PF and a significant change in context over the last year that must be taken into consideration when both reviewing performance and assessing recommendations for the next year. The challenges posed by COVID-19, ODA budget re-prioritisation and the FCDO merger raise a number of questions as to how best to take the MREL function forward. Without knowing the outcomes of the ODA spending review and its impact on the PF this review has focussed its recommendations on the expectations that the MREL contract will continue until its scheduled end on November 2021 with a similar operating budget as now. The review team do acknowledge that these circumstances may change and that the recommendations made here will need to be reviewed based on any these.
MREL support in the area of Gender and inclusion (G&I):
The MR team expressed that their role in G&I was to help programmes “understand legal and policy commitments/ensuring the minimum expectations of JFU (SDA advisory) are mainstreamed through ToC and LF”. These responsibilities included:
- Supporting the refinement of programme ToC that embed G&I
- Identify G&I fund level indicators
- Training on Prospero G&I dashboard
- Support teams to disaggregate indicators where possible
- Support the selection of programme specific G&I indicators.
SDA’s and PTs interviewed reported that most of the support the MR team provide is concerned with the disaggregation of indicators by age, sex, socio economic group, and ensuring this is set up on Prospero. Further, SDAs commented that MR supports logframe and indicator development - and the EL may be brought in to review G&I aspects. The output section of the review discusses the lack of specialised G&I technical capacity in the MR team.
The MREL/G&I quarterly forums, including JFU MREL, SDAs HMG departmental advisers (MREL and SDAs) are useful as good engagement between PF staff and the MR and EL contractors and provides opportunities for MR and EL to report back on progress and ensure the relevance of their G&I offer.
MR does provide an analysis on G&I indicators on Prospero shared with SDAs and other advisers at the quarterly MREL G&I forum which allows a cross portfolio view of trends, which programmes are reporting, what levels of disaggregation are on the system etc. 33% of indicators
The EL put in place measures to ensure improved consistency across evaluations and a minimum level of G&I analysis in each evaluation. Over this period G&I capacity was increased which enabled the provision of advice and support from the EL at the centre to programme level evaluation teams, i.e., improving guidance on the new G&I scorecard, enhanced training and more robust quality assurance. Other areas of improvement for G&I in evaluation included better mainstreaming G&I in evaluation questions; working with SDAs on a simplified G&I scorecard and beneficiary feedback guidance, better engagement and consultation with SDAs during evaluations, however it should be noted that some negative experiences were reported by SDAs unable to input to the evaluation appropriately, which led to several problems with the detailed G&I scorecard assessment and ultimate conclusions.
Summary of Responses to Issues Raised in Previous Annual Reviews
Recommendations relevant to specific outputs are discussed under the relevant detailed output scoring sections below. The recommendations below are for high level recommendations relevant across outputs

Recommendation 1: A logframe, based on a theory of change, should be created for the MREL programme to assess progress in future Annual Reviews by the JFU MREL team in conjunction with MR and EL suppliers. Achieved and used to assess progress in this annual review.

Recommendation 2: Within the next six months, the JFU MREL team should consider options for future MREL delivery models to cover the period 2021 to 2023. Options were developed and presented to the Board, but could not be acted on in light of the ODA cuts and FCDO merger.

Recommendation 3: JFU MREL team to clarify MREL roles and responsibilities between all key actors. Achieved including a MoU between contractors. Discussed in more detail through sections below.

Recommendation 4: PF HMG departments, in particular the FCO, need to consider how to fill programming and sector specialist capacity/capability gaps. FCO has progressively improved its capacity in programming management over the year, through experiential learning, fomal training (bespoke MREL capacity development) and recruitment of MREL facing personnel at Post. Specialist capacity has been drawn from strategic/ multilateral partners, as well as through links with X HMG technical specialists. FCO/DFID merger has facilitated some of these linkages.

Summary of changes to the logframe since the last annual review
As there was no logframe available for the last annual review a logframe based on a ToC was developed prior to this annual review. This was developed in consultation with delivery partners but with JFU MREL oversight and final say. The review team have made a few suggestions to improve the logframe, these are listed in the M&E section below.

## C: DETAILED OUTPUT SCORING (1-page narrative per output)

Output Title	Monitoring and Reporting: Timely and accurate information on Prosperity Fund programme and portfolio performance for programme teams and Joint Funds Unit
Output number per LF		1	Output Score	B
Risk:		Major	Impact weighting (%):	30%
Risk revised since last AR?		Y - new logframe	Impact weighting % revised since last AR?	Y - new logframe

Indicator(s)	Milestones	Progress
1.1. Prospero satisfaction. User satisfaction with the system, measured by % users rating it as 'good' or above	70%	Moderately did not meet expectation / 64% - this is the average score on the likert scale with 29 respondents. Of the 29, 14 (48%) of respondents agreed or strongly agreed with the statement ‘Prospero is friendly, intuitive and easy to navigate to the desired information’.
1.2. Prospero availability. Measured by: (i) site availability (24 hours/day, 7 days/wk); / (ii) time taken to resolve critical defects (P1), / and time taken to refresh: (iii) data page, and; (iv) dashboard page	i) 99% ii) 100% <1 working day iii) 100% <2 seconds iv) 100% <10 seconds	Met expectation / i) 100% (verified for Nov 19, Apr 20 – Oct 20) ii) 100% (3/3 priority 1 defects were fixed within the agreed KPI thresholds during the 12-month review period) iii) 100% (verified for Mar – Nov 20) iv) 100% (verified for Mar – Nov 20)
1.3. Prospero engagement. Measured by: (i) % active users (out of registered user); (ii) % logframes MR on-boarded to Prospero within agreed KPI timeframe	i) 70% ii) 100%	Moderately did not meet expectation / i) 60% (includes Nov ‘19 – Oct ‘20). If we only look at the proportion of active programme members, the result is 64%, though this only covers the period Dec ‘19 - Oct ‘20. ii) 100%
1.4. Reporting timeliness. % reporting processes run in line with agreed commissioning timetables, disaggregated by: / (i) quarterly reporting, and; (ii) Portfolio Board report templates	i) 100% ii) 100%	Met expectation / i) 100% ii) 100%
1.5. Commission and bespoke report usefulness. Measured by: (i) Portfolio/Programme Manager satisfaction with bespoke reports; (ii) satisfaction with commissions (both measured on a five-point scale; annual avg); / (iii) % bespoke reports delivered within agreed deadline, and; (iv) % commissions delivered to agreed workplan timeframe	i) 4.0 average (80%) ii) 4.0 average (80%) iii) 80% iv) 90%	Moderately did not meet expectation / i) 3.3 - 9 respondents; 37 bespoke reports ii) N/A iii) 100% iv) 100%

Key Points
Output 1 largely covers MR’s Prospero system and the products that come out of it, taking into account user satisfaction, timeliness and usefulness. The Output has scored a ‘B’ overall, meaning that expectations were moderately not met. Whilst Prospero availability and the timeliness of reports met expectations, user satisfaction with the overall system and some of the resulting products fell slightly short, based on stakeholder satisfaction survey scores and annual review interviews, thus contributing to the overall score. Prospero engagement was also not as high as was hoped.
In summary:
- Prospero is not seen as being particularly useful for programme teams (PTs). If this was addressed then PTs would likely engage better with the system, which in turn would result in them uploading more data on a regular basis, leading to Prospero becoming a more effective portfolio management tool
- Although the Prospero Sprint successfully increased the amount of data on the system, more are needed to enhance its utility – which should follow organically as the portfolio matures
- The Quarterly Reports and Good News Stories are largely well-liked across the board, with mixed feedback on the Portfolio Board templates and limited mention of the use of bespoke reports by interviewees
- Feedback on MR Hub staff was very positive across the range of interviewees
Prospero
Interviewees had mixed feelings about Prospero. It is largely seen as a portfolio management tool that has limited utility for PTs, with PTs mostly feeling that it does not directly benefit them aside from the quarterly reporting functionality. Indeed, a couple of PT respondents felt that Prospero didn’t give them any added insight to the results they fed in. This has resulted in the reluctance of some PTs to upload data to Prospero, which in turn puts other users off using the system because it doesn’t contain enough data (or didn’t in the past).

For portfolio management, Prospero is seen as an important tool for cross-government working in terms of collating information on what the fund is achieving as a whole, but again the general feeling is that it would be much more useful if it had more data. At the moment, the portfolio isn’t mature enough for Prospero to usefully extract certain information on the fund, and some respondents feel that the content is sometimes of limited use or they are unable to fully trust it due to the lack of up-to-date data. However, this has improved over the past year, with an acknowledgment from JFU colleagues and some PTs that the Prospero sprint in Spring/Summer 2020 was helpful and resulted in the system containing much more programme data than it did before. The Review Team (RT) expect that Prospero will be more able to provide more useful portfolio-level insights over coming months now that most programmes are fully up and running, as long as they continue to upload their data to the system.

From a PT perspective, Prospero is largely seen as a clunky and cumbersome system, with it being time-consuming to upload data. However, a small number of interviewees felt differently, saying that they found the system useful and user-friendly and data entry straightforward and manageable – notably, the more negative comments tended to come from legacy FCO staff. The RT also noted that the MR Hub are about to start work to improve the process of uploading data for PTs and that this would likely have been undertaken sooner if it wasn’t for the COVID-19 crisis and resulting JFU decisions on prioritisation of work. In addition to comments on data uploading, some interviewees felt that Prospero needs to more systematically represent qualitative data in order to fully capture the results of the PF, though it was noted that the Good News Stories try to tap into this – indeed, users can search the PF news archive applying a range of filters including by programme, media type, tag and date range. There was also a consensus that it would be easier if PTs were able to correct their own mistakes rather than having to go through MR.

The risk functionality of Prospero was raised as an issue, with some interviewees feeling that it would be more useful if they were able to upload all their risks to the system, and to view more detailed information on them that can be extrapolated and used for decision making. At present the system only shows the top 15 risks per programme, a conscious decision to keep portfolio level reporting manageable.

A final note is on data quality, with some respondents noting that if the quality of the data input to Prospero by PTs is poor, then Prospero will suffer. This is also true of the data uploaded to the system by MR, with a JFU user noting that the data on some basic things are incorrect, such as what stage a Business Case is at. It was unclear whether this issue could be rectified by more MR guidance or better PT capacity but is perhaps worth exploring with PTs.

Prospero Products
Most interviewees had not made use of the bespoke report functionality, with some saying they were unsure of the offer, though there were a few general comments that the reports are useful, albeit inflexible – and there was a glowing report of one interviewee getting all the information they needed from a bespoke report.

PTs largely praised the quarterly report functionality. Quarterly reports were said to be great visualisation tools and professional looking documents with suitable formatting, and useful for taking stock of the programme and informing seniors of progress. Respondents also like the pre-populated information on finances, staff etc, though some noted that these data are sometimes out-of-date or inconsistent – however, the RT do note that it would be difficult to get these data onto the cross-government system in real-time. Other interviewees would like the quarterly reports to do more than simply reflect the information they put into the system, and some aggregation of the information in the reports would also be useful to view the fund as a whole, as it is difficult to do this with the current system. Again, there were comments that the usefulness of the reports is dependent upon the amount of data put into Prospero by PTs.

Feedback was generally positive on the Good News Stories, with interviewees feeling that they were helpful, especially for annual reviews and to showcase work to seniors, and a good tool for taking stock of the programme. They were also noted as the only way to upload qualitative information onto Prospero. They were flagged as being useful for internal comms, but again it was noted that the usefulness of the system increases as PTs engage – and there has been a positive trajectory with this over time.

On the Portfolio Board Report template, feedback was mixed. Some interviewees said the report was useful, broad and good at presenting issues, with one JFU colleague taking it to x-WH meetings and another finding it useful in terms of giving strategic direction, feeding into decisions that are being made and informing the questions and choices that are being put to the Board as a whole. However, others felt that the report could be better utilised and is not particularly used for decision-making – and that PTs and the wider portfolio network likely refer to it more than Board members. Again though, there is the issue with out-of-date data – here because it comes from JFU to MR in the first instance and is often old by the time the Board meet, meaning that verbal updates have to be given alongside. This wasn’t a criticism of MR’s performance; it was noted that as a x-WH fund it is very difficult to get data onto the system in real time.

Commissions
Over the last year, MR delivered two commissions. For the staff heads commission, the team were very professional in their approach, setting up a clear timetable and plan of action. The commission process was very quick, and the result was exactly what JFU were looking for. The MR Hub also led on the SB attribution commission, in conjunction with the Economist Intelligence Unit (EIU). One JFU colleague felt that MR and EIU performed the task effectively, especially considering the challenges behind attributing SBs, and that engagement with EIU was positive. They were efficient with their timings, and flexible when programmes were unable to engage due to COVID-19. However, some advisers in JFU questioned the appropriateness of some of the models proposed and therefore the overall usefulness of the commission.

MR Hub Staff
Interviewees had many positive things to say about their interactions with MR Hub staff and their willingness to help, responsiveness and proactiveness in reaching out to teams. Especially during the COVID-19 crisis, feedback was that MR staff “went out of their way to try and help and support programmes”.

Summary of Responses to Issues Raised in Previous Annual Reviews
Recommendation 6. The JFU MREL team needs to monitor to what extent fund level ‘Portfolio KPIs’ are being used, whether they will be able to be reported, and whether they need to be refined at all now the JFU has a better understanding of final intervention designs.

The KPIs have largely been refreshed in consultation with PTs with around 30 programmes or projects now including the KPIs in their logframes. Some still don’t find the KPIs particularly useful. Some JFU staff questioned whether they are still too high-level for the level of maturity of the portfolio. JFU and MR have worked on basket indicators, a level down from the KPIs. Early feedback is that this has been quite useful.

Recommendations
- JFU to review their expectations of the MR contract under this output with the remaining time and resource left
  - Review which data are most needed from teams so they can be prioritised. For example, PTs could be instructed only to report against indicators that will be aggregated across the portfolio

- MR Hub to continue to improve Prospero user experience within budget pressures – prioritising the themes of data uploading and editing to ensure as much (high-quality) data are on the system as possible. For example:
  - Improve data uploading process and/or make Prospero more useful for PTs, to foster increased reporting in a timely manner
  - Consider enabling PTs to correct their mistakes within the system
  - [In slower time] Consult users on risk functionality within Prospero

- MR Hub to put processes in place to enable as much learning and use to be extracted out of Prospero as possible
  - Improve usefulness and visibility of Prospero products for programme teams
  - Ensure that data on Prospero are as correct as they can be, as far as MR’s influence allows

Output Title	Evaluation: Technically robust and independent evaluation products with clear recommendations for Programme Teams and JFU
Output number per LF		2	Output Score	A: met expectation
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		Y - new logframe	Impact weighting % revised since last AR?	Y - new logframe

Indicator(s)	Milestones	Progress Nov 19– Oct 20
2.1 Evaluation delivery: % and # of Approach Papers and Evaluation Reports accepted as 'delivery completed' by JFU (annual)	100% (# as per : workplan between Nov19 and Oct20) / Source: The revised EL workplan year 3 20/21 / 12 planned APs / 10 planned[1] / programme ERs / 2 fund level reports	Met expectation / Delivered between Nov19 and Oct20 / 11 Approach Papers including AP refresh / 1 fund level evaluation report “delivery completed” by Oct 20 / 1 fund Approach Paper / 6 evaluation reports “delivery completed” / 4 evaluation reports “delivery completed” slightly after Oct 20 period / The BHP evaluation report was planned to be delivered in Sept 20. However, this has been postponed until Mar 21. / Note the 1st fund level evaluation was completed in the previous period (Nov19) / The 2nd fund level evaluation Jul 20 - both accepted in sept 20
2.2 Evaluations quality: % of Approach Papers and Evaluation Reports rated by EQUALS as (i) 'fair', and (ii) 'good' or above (cumulative)	>Fair 80% / > good 70%	Exceeded expectation / 100% evaluation reports (10/10) scored > good / 91% approach papers (10/11) scored > good / 100% approach papers (11/11) scored > fair / The only AP that scored fair in this period was for Mexico cycle 2
2.3 Evaluations satisfaction: Satisfaction with Evaluation Reports from Programme Teams (measured on a five-point scale generated by composite questions agreed with JFU; annual avg)	3.5 (70%) annual ave	Moderately exceeded expectation / 4.6 point average (91%) from a 40% PT feedback response rate.
2.4 Evaluations satisfaction: Satisfaction with Evaluation Reports from Portfolio Managers e.g. JFU, dept advisers (measured on a five point scale generated by composite questions agreed with JFU; annual avg)	3.5 (70%)	Moderately did not meet expectation / Perception score not yet requested to date (Oct 2020) / 17 evaluation products completed in Q1 and Q2 / JFU/PFDU qualitative feedback (RAG self-rated by the EL) / 41% were good, clear, concise, well written / 41% included some info gaps, areas could be strengthened , several rounds taken to finalise, misunderstanding of brief, significant re-write / 6%[1] were of questionable usefulness / The remaining uncommented
[1] Note: the red rated report was interestingly scored a 5/5 by the PT illustrating the challenge of the difference in expectations between JFU and PTs in some cases

[1] Excluding GGEF (- not part of PF portfolio anymore)

Key Points
This output was concerned with evaluation delivery, quality and satisfaction with the evaluation products. Overall expectations were met with independently verified quality scoring highly, delivery and programme team satisfaction moderately exceeding their milestone expectations. Advisers, JFU and portfolio manager satisfaction on evaluation products was slightly less positive, based on triangulating the feedback collated plus interviews with stakeholders.

In summary:
- Evaluation approach papers (APs) and evaluation reports (ERs) were delivered as planned (following the ODA reprioritisation) in the revised EL workplan year 3 (20/21). Some delays were experienced on finalising products, resulting from delays in HMG feedback, in part due to staff shortages.
- Annual evaluations as envisioned in the design of the MREL service were found by all PT and HMG stakeholders consulted to be too frequent alongside an annual review. Flexible days to support annual reviews were highly valued.
- Evaluation quality as independently verified by EQUALS is consistently very good for both approach papers and evaluation reports.
- Differing expectations on the utility and quality of evaluation from PTs, JFU managers/ departmental advisers and EQUALS, has strong potential to be resolved as EL establishes appropriate products and feedback mechanisms for different audiences.
- Programme team satisfaction with APs and ERs was high, however from a low feedback response rate
- PTs are increasingly engaged on evaluation, working closely with their Programme Evaluation Leads (PEL) to maximise learning. There was limited evidence around the use of evaluation to influence decisions.
- JFU, portfolio managers and HMG advisers have provided less positive feedback on evaluations, and engagement has not been high.

Delivery of approach papers and evaluation reports
JFU MREL did not operate as a full capacity team (4 staff) until Sept 2020, inevitable delays were experienced by the EL service in receiving feedback on evaluation products.

Several approach papers were developed in the previous FY 19/20 but were not used at that time and underwent a refresh, pointing to evaluations being launched too early, and/or delays to delivery resulting in products that required re-working. The early APs usually formed the basis of any refresh, although in some cases changes in PT steer (due to staff turnover) led to a different emphasis placed on evaluation or learning needs. Learning from this experience the EL works closely with PTs to ensure there is less chance of evaluations being launched too early.

Programme evaluation frequency
In the design of the EL service the evaluation annual cycle was intended to support accountability and help programmes learn and adapt, as well as feed information needs of the fund level and thematic evaluations. Evaluations and PEL input have been useful for providing a stronger evidence base for the annual review. However, the frequency of having to conduct an annual evaluation was strongly challenged by PTs and even JFU respondents (including senior leadership). Key informant interviews relayed numerous comments along the lines of “conducting annual evaluations is not necessary for every year, this should be something done towards end of cycle” “having both is burdensome. The process is the same for both… TORs, team interviews, merging both feels like it would be obvious way to save resource?”

Alternative sources of input (via flexible days) to annual reviews could be just as effective i.e. EL’s readiness reviews, discrete workshops with the EL team (G&I, VfM, SB), the outputs could also inform fund and theme based needs.

The current revised EL workplan Y3 has set out a proposed Y4 evaluation delivery to Nov 21 when the EL contract ends. There are 2 evaluations planned in the period following the closure of the programme: The Global Infrastructure Programme and the Asian Infrastructure Investment Bank close in Mar and April 21 evaluations are planned for the autumn of 21. Given the likely challenges to conduct a post programme evaluation (with lack of key informants, priority to provide the necessary support and hard to ascertain buy in to the evaluation report/recommendations and findings) it would be more desirable for the EL to support a comprehensive programme completion exercise and lessons learned of sector importance, rather than conduct a standard AP and ER process. There are currently 5 programmes (Global Trade, Digital, ALCE, AER, Global Finance) finishing in Mar 22 with APs and ERs are planned for May or Jun 21, this will be too early for an end of programme evaluation. A delay of the evaluations into late summer/autumn would be preferable.

Evaluation Quality, independently verified
The technical quality of most APs and ERs were independently judged through EQUALS to be of consistent high quality. EQUALS raises its own challenges namely a mismatch concerning the technical detail and rigorous evaluation design required under EQUALS and the requirements JFU, or even PTs, have from evaluations for shorter reports with less methodological and contextual detail. To illustrate, one report scored excellent by EQUALS did not align with JFU feedback. This mismatch of evaluation audience expectations, around the technical detail they go into, is challenging for the EL to navigate. A review was undertaken in 2020 to determine the need for any systemic change required, resulted in evaluation quality not only being determined by EQUALS but important weighting placed on broader programme and advisory feedback on evaluations (as captured in the MREL results framework). As a result, EL is producing a range of different evaluation products to meet the needs of both EQUALS and PTs/JFU.

After April 2020 evaluations were conducted remotely, as part of the adaptation to working with COVID-19[1]. Remote evaluations do not appear to have detracted from the quality of the final APs or ERs. Between April 20 (during the height of COVID-19 (first lockdown) and following a travel embargo) and Nov 20 12 APs and evaluations have been completed (none with an EQUALS score below good)this compares favourably with evaluations that included travel.

Audience satisfaction with evaluation products
Evaluation products are scored on criteria including 1. Helpfulness of outputs to decision making 2. User friendly format 3. Appropriate team composition and engagement 4. Satisfaction scale. Of the 40% of PTs that provided feedback, the response was overwhelmingly positive 4.6/5. Given the low response rate to EL request for PT feedback, key informant interviews with PTs have provided some useful qualitative reflection. On the whole PTs found the recommendations useful – a positive shift from the previous attitude that they were simply used as evidence for annual reviews, to more about capturing early programme results, and learning for a broader user base, with a highly bespoke process. One PT member commented “Evaluation last year felt they (EL) were grading the programme rather than supporting collaboration and learning, but now there's a big improvement in this”. Efforts to improve PT feedback on evaluation could be to include a real time questionnaire applied as an interactive part of the presentation (i.e. mentimeter or similar) during the learning /feedback touch point with PTs and their partners.

Where evaluations have influenced decision making the response was mixed, with some very positive examples of the potential for this i.e. ASEAN LCE receiving overwhelmingly positive feedback during a call from Ambassadors in the region, whilst other PTs were less certain. Several PT/ bilateral PF staff commented that conclusions and recommendations were of matters that the programme already knew about, and stressed recommendations should be impactful, insightful and truly improve the impact of the programme. PELs as technical experts in their field would be best placed to bring in external sector insight and learning to inform programme impact and improvement.

Portfolio managers and JFU advisers did not prioritise providing feedback on evaluation products, suggesting limited bandwidth to engage due to competing priorities. Potentially there would be stronger interest if there were more emphasis on understanding what MREL can offer portfolio managers and advisers. There is clear evidence (in subsequent re-submissions of products, and the individual effort PELs put into soliciting feedback) that any feedback on evaluation reports is well received and PELs use this to improve the product. JFU feedback is carefully considered and tangible improvements include; strengthening of QA, introducing new templates/style guide, setting a page limit maximum, providing more support to writers and use of graphics. More broadly in the area of improvement, EL quarterly feedback reports clearly specify what they will do differently, although included in the next quarterly report should be actions taken to improve less satisfactory APs or ERs in addition to reporting on this at the monthly contract review meeting or weekly operational meeting.

JFU advisers commented that the EL could bring valuable insights to programmes concerning changes in the ODA environment, how to make a stronger VfM case, document better evidence and demonstrate results to Ministers (which is currently being piloted through development of three Stories of Change). Also, importantly, how to communicate what the PF has achieved to the public to gain support. Less positive comments related to the perceived lack of thought leadership, expected of EL support. “they're really comfortable doing routine VfM work, scorecard, but lack linking the programme-by-programme bigger picture –for example linking VfM assessments to an active approach to portfolio management”. In other words, missing the strategic link.

On G&I, one of the SDAs remarked that the EL capacity was now good, having improved significantly this year, with strong leadership and expertise. It was highlighted that it would be beneficial, during the evaluation process, to conduct joint interviews with the SDA and the programme G&I champion, to support ownership and PT understanding of when to draw on their SDA. In addition, it was important for evaluators to refer to the business case to understand and build into their assessment any commitments to G&I. Concerning annual reviews and their use of evaluation evidence, the G&I scorecard applied during the evaluation process should be a key source of evidence for the programme annual review, this was not always the case.

On the usefulness of thematic evaluations several key informants singled out the financial sector evaluation as being instrumental in bringing the network together to deliberate lessons learned. The fund level evaluation was also well received and disseminated to the network via webinar. There is no formal feedback rating sought for the thematic evaluation products, this will be sought in the future.

PF Publication of evaluations
The PF evaluation publication policy[2] states the publication of evaluations is the responsibility of the lead department, reviewing the first draft and (i) checking the evaluation report for sensitive information, (ii) drafting a management response, (iii) arranging publication of the report within a quarter of sign-off, and (iv) managing any risks that arise from publication e.g. through defensive press lines. To date no PF programme level evaluations have been published. HMG departments should endeavour to comply with the policy and implement a plan to do this.
[1] JFU PF GUIDANCE: Monitoring, Reporting, Evaluation and Learning during the COVID-19 crisis, updated guidance
[2] Evaluation publication policy Dec 19 JFU

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendation 7: EL supplier, JFU MREL team and JFU Points of Contact to further communicate with HMG programme teams on purpose and use of evaluation.
Achieved with EL team setting out roles and responsibilities at the PF away day in March 2020 with UK based FCO PTs and PFDU, and updated description on roles and responsibilities in place. PELs have forged stronger relationships with PTs through the flexible days scheme. Most programmes now at a point where early results are being achieved leading to good collaborative working around MREL.
Recommendation 8: JFU MREL team, POC and E&L should continue to highlight the intended differences between annual evaluations and annual reviews to programme teams, monitor how the processes are working together
Ongoing communications by the EL and JFU MREL on annual review and annual evaluation differences, and how the annual evaluations should feed into annual reviews. Programme teams have rescheduled some evaluation to take into account annual review deadlines, although not all annual reviews have made effective use of evaluation evidence. The two processes do still not appear to be working together effectively, as can be read in the review commentary and JFU should address this.
Recommendation 9: EL supplier needs to take a more proactive and individualised approach to sharing findings. EL supplier to make a stakeholder engagement plan for each evaluation and conduct targeted dissemination of findings using a range of products and approaches.
Achieved, there are now stakeholder engagement plans for each evaluation (and learning products) and targeted dissemination using a range of products and approaches.
Recommendation 10. JFU MREL to clarify the process for deciding scope method and timing for all evaluation types
Achieved: agreement between JFU and EL team on ownership, sign off of different products.
Recommendation 11: EL supplier to update the G&I scorecard, in consultation with JFU, and the G&I reference group.
The scorecard was updated and simplified. The JFU and FCO SDAs worked with the EL contractor to simplify the G&I scorecard to be used as a basis for the G&I evaluations.
Recommendations
- JFU MREL team to continue to monitor and manage carefully the sequencing and timing of programme evaluations, moving away from an annual cycle, which would free up the EL to focus on more bespoke learning needs of programmes (capturing stories of change, qualitative information, results, G&I).
- The remaining focus of the EL contract should be on helping the PF document evidence for learning for both programmes and on the PF approach itself. EL (with JFU MREL) can provide focused support to the programme on lessons learned as part of the programme completion review/report.
- FCDO must plan for adherence to the PF evaluation publication policy, setting out an approach to how this will be done
- PTs to ensure evaluation evidence is highlighted to annual review teams , including G&I, VfM and SBs analysis.

Output Title	Learning timely and relevant MREL resources, publications and events to support PF staff engagement with data, findings and learning
Output number per LF		3	Output Score	A: Met expectation
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		Y - new logframe	Impact weighting % revised since last AR?	Y - new logframe

Indicator(s)	Milestones	Progress
3.1 PFLearning content and support: PFL content and user support are made available in a timely fashion measured by: (i) time within which content is uploaded, (ii) time within which user profiles are set up, (iii) frequency of user training	(i) 2 working days, (ii) 5 working days; (iii) monthly	Met expectation / (i)average time to upload content / not been tracked to date, although rapid response to establishing a COVID-19 site on PFLearning is a good example / ii) time to set up user profiles / not been tracked to date / iii) frequency of user training - Prior to COVID-19 disruption user training was held 1 or 2 times a month. Nov 19 to Feb 20 Nov (1), Dec (2), Jan (1), Feb (2)
3.2 PFLearning availability: Measured by (i) site availability (24 hrs/day, 7 days/wk. excluding scheduled downtime), and time taken to respond to: (ii) blockers issues; and (iii) critical issues (during UK office hours)	(i) < 1% unscheduled down time (ii) 15 mins; (iii) 2 hours	Met expectation / (i)All applications 100% availability from Nov19 to Oct 20 except for Dec19 99.978% / (ii) blockers issues –none experienced during the reporting period / (iii) critical issues – defined as urgent priority – time taken to respond to 10 issues recorded on the managed services support portal 2 hours or less. none experienced during the reporting period
3.3. Learning products usefulness: learning inputs and products are deemed by Programme Teams to support engagement with findings, learning and recommendations. (measured on a five-point scale; annual avg)	3.5 (70%)	Met expectation / 4.24/5 (85%) and feedback from KIIs (note 3 events) / Triangulating from annual PF user survey / Output kpi3.2 and 3.3. qualitative feedback on learning support
3.4Learning products usefulness: learning inputs and products are deemed by Portfolio Managers e.g. JFU, dept advisers to support engagement with findings, learning and recommendations. (measured on a five-point scale) (annual avg)	3.5 (70%)	Met expectation / ( sample of feedback from surveys was too low to be representative, qualitative feedback from JFU/Managers and Advisers mixed. / How useful and appropriate do you find EL learning and support generally? / Data from 2 EL surveys, mixed respondents not exclusively Portfolio Mgs or advisers / FinSec event feedback (7 respondents) 4/5 / fund evaluation report feedback (31 respondents) 3.97/5

[1] Following the onset of the CV -19 reduction JFU request was to minimise non-essential activity between the EL and PTs, this activity was halted and then cut under the budget reductions.
Key Points
This output measured PFLearning (PFL) timeliness to upload content, availability, and perceived usefulness of learning products for PTs and JFU/Departmental Advisers and managers. Overall, this output has met expectations.
In summary:
- The ODA prioritisation exercise resulting from COVID-19 necessitated a change from 20 to 12 learning products but fund level deliverables remained the same. Support to Communities of Practice (CoP) was removed.
- The PFL platform was retained with a reduced level of effort to support moderation from the learning team; this did not affect the availability or functionality of the platform Induction and training on PFL stopped from March 20, but new users have continued to be added
- PFL support is timely and relevant. The rapidly deployed COVID-19 site on PFL is highlighted as a success. PFL has provided an uninterrupted service for the year, and service issues have been attended to on time.
- Feedback on learning products has been positive. EL have been responsive to suggested improvements and proactive in soliciting feedback. An example of this has been the introduction of different learning product for different audiences, which has been well received.
- PFL is viewed as a useful cross network platform with good quality content and an accessible attractive layout. Use of the platform (through number of views) decreased over the summer (20) but has increased in the autumn. Interviewed staff admit to not accessing the site often.

PFL timeliness of support
Time to upload content: A dedicated area to share information and knowledge on the impacts of COVID-19 was requested and approved by JFU in early April. Within 6 days the site was launched and is now established as one of the most frequently visited sections of the site, with 104 pieces of content uploaded (to Nov 20).

The PFLearning 2020 survey report (conducted in Feb 2020 by the EL team) found that 79% of responses reflect that PF staff either ‘agree’ or strongly agree’ that ‘The support team respond effectively and in good time’. The response rate for this survey was roughly 10% of 595 staff with PFL profiles at the time of the survey.

Training and induction of new users
User training for PFLearning was impacted by the onset of the CV-19 and budget cuts. From March onwards JFU requested the EL to minimise non-essential activity with PTs including training on PFLearning. Data provided from Nov to Feb, does indicate monthly training held, with 2 sessions conducted in some months. The reviewers feel it is likely that under normal circumstances this would have continued with the same frequency. Whilst the budget cuts resulted in the cessation of training, having no induction to new staff on PFLearning does not encourage uptake and use of the platform.

PFLearning availability and servicing
The EL provided a stable online platform for 704 users, with 12 months of near 100% availability. A table highlighting critical issues raised over the year and response times is available.

Learning products usefulness to Programme Teams
Learning products and events were designed to make key findings and learning from evaluation reports, using different formats/media, more accessible to different audiences. All products are made available on PFL and include Evaluation presentations (PPT webinars); case studies; webinars; video; reflective pieces; regional forums; lessons learned events. Over the period Nov 19 to end Oct 20 there were 16 different learning products or events.

Evidence against output indicator 3.3 is not yet collected systematically, due to the late agreement of the logframe. However, a few sources of evidence have been provided from feedback surveys conducted by the EL at the time of the event:

The PFLearning member survey report Mar20, completed by approximately 10% of staff with PFL profiles provides several useful proxy indicators demonstrating how useful members find PFLearning: 76% would recommend PFL to colleagues, 71% have used information from the platform in their work.

Interviews with PTs indicate that the diverse content and functionality of PFLearning is not always fully utilised, several teams stating they mainly used it as a document repository (for annual reviews). Almost all global and bilateral PTs consulted reported insufficient time to engage with PFLearning, despite acknowledgment that the quality of the site and content is very good, mentioning improved ability to find the latest (correct version of) guidelines on annual reviews, VfM, G&I and SB.

Several PTs mentioned the adoption of MS Teams as a day-to-day interactive platform for cross programme and team communication may have negatively affected the use of PFLearning for certain programmatic exchanges; this was also raised as a risk by EL. The March 20 PFLearning survey report recommended the EL should communicate what PFLearning does in comparison with other tools/functions … including MS Teams to both increase clarity about what is available and distinguish how PFLearning complements other offerings, however this was put on hold first due to COVID-19 reprioritisation and then due to budget changes as agreed with JFU in line with PF priorities.

DFID PTs praised PFLearning for helping the team gain better foundational understanding on SB, which led them to secure FCDO and DIT experts to provide support. The majority of PTs consulted reported they would encourage their country teams to use PFLearning more.

Fig: PFLearning staff views Nov19-Oct20

An Oct 20 snapshot of who is accessing PFL revealed that of the 458 views: PT 210: JFU 66: PFDU 73: DIT 69 and others 40. Interesting to note the relative frequency of access from DIT/others, indicating the expanded reach of PFL to other Gov Depts.

A key feature of PFL is the network area (containing Peer spaces or communities of practice), over this period there were 2,303 views from 148 individuals.

Communities of practice (COP) enable x-HMG learning and exchange around different theme-based areas of interest. The best example of a functioning CoP is the G&I champions (64 members). SDAs are the driving force behind this forum, having worked together last year with the EL team to make this a success. The platform facilitates the cross sharing of programme learning by periodically hosting relevant G&I thematic discussions. The EL no longer provides the same level of support as this was altered to improve VfM (facilitating and organising meetings, issuing invites, documenting learning), however, the group has strong HMG leadership and a critical mass of active champions to successfully continue. Other peer groups include: Communications Network members 34 Economists Network –members 28, SB Learning Network – 23 members, Global Business Environment 14 members.

Learning products usefulness to JFU and portfolio managers and advisers
Several JFU advisers interviewed suggested that the original design of MREL with its centralised, top-down, emphasis on quantitative analysis, through Prospero made it more difficult for programmes to fully-embed learning and continuous improvement. Qualitative data is generated by the EL team.

The need to strengthen capacity of PTs through learning products was felt important but there was also a recognition of the limit as to how much could be learned from reading reports. The EL team’s inventive and carefully considered approach to introducing new formats for learning products is a very positive development. Advisers interviewed found learning products generally useful, with at least 3 different individuals highlighted the financial services sector evaluation presentation as particularly impactful. Other advisers praised the video ppts – “the Postcard from DAP on a blended delivery model with both the SRO and the Kenya country lead presenting was a useful format” and the Mexico video on SB as this was a direct input from country-based teams that could be used for centrally based teams to use in reports and briefings.

DIT advisers reported finding the learning products and PFLearning “very useful in getting up to speed and building up (their internal) capacity relating to ODA programmes”. They reported accessing some of the forums to learn from other PF programmes with similar issues and to link with other analysts across the network. The economists COP group was mentioned as a helpful, practical forum, as well as the COVID-19 site and discussions on how to factor in how COVID-19 would affect programming.

A few JFU and departmental advisers reported their use of PFLearning has dropped this year, and senior leaders admitted they “hardly ever” use PFLearning due to competing priorities. Leaders do encourage staff to interact with thematic learning, strongly encouraging JFU advisors to build and launch thematic COPs, and for this to be included in their objectives. This has not been successful so far, due to other competing priorities.

It should be noted that PF senior leadership reported rarely using PFLearning other than occasional engagement with x-HMG network events

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendation 12: The JFU MREL team should carefully prioritise and set clear scope to maintain optimal efficiency of the learning resource (platform and EL supplier’s learning team). Consideration should be given as to how to align with JFUs capability strategy to be complimentary.
Support to PFL was reduced in light of the ODA prioritisation and reprioritised to maximise the value added of the learning team to focus on learning products, creation of the COVID-19 site and soliciting feedback for improvement.
Recommendations
- (MREL JFU) PFLearning to be maintained for now as a x-HMG learning platform for sharing of key publications, learning products and notification of learning events. As PFD structure and governance arrangements become clearer, revisit how the content/learning functions can be merged with broader FCDO /maintained/transferred or stored.
- (MREL JFU) Sustainability plan for learning to be considered for the period post contract (November 21)
- (Learning team) to produce a short recording of PFLearning induction that could be self-accessed, to show PFLearning highlights, how to navigate around the site, how to join COP and add comments for new staff, reference to and a link to this will be included in the PFD induction pack (PFDU FCDO)
- (Learning team) to reflect on the particularly successful learning products / events such as the fund level evaluation and the financial services thematic evaluation webinars, to develop top tips for PELs and other thematic evaluators in developing their own feedback and learning products. JFU to emphasise PTs should document and share learning

Output Title	Technical Assistance: Timely, expert MREL technical assistance provided to Prosperity Fund staff
Output number per LF		4	Output Score	A+
Risk:		Major	Impact weighting (%):	20%
Risk revised since last AR?		Y - new logframe	Impact weighting % revised since last AR?	Y - new logframe

Indicator(s)	Milestones	Progress
4.1. Tech Ops assistance satisfaction: Programme Team satisfaction with MR TA support, measured by: (i) general satisfaction (from bi-annual survey), and; (ii) immediate feedback from service users (both measured on a five-point scale; annual average)	i) 3.5 (70%) ii) 3.5 (70%)	Moderately exceeded expectation / i) 3.93 (78.6%) - average score to Stakeholder Satisfaction Survey question ‘The technical support I have received has benefitted me’ - 13/15 respondents (plus 8 who answered ‘N/A’) answered ‘agree’ or ‘strongly agree’. ii) N/A
4.2. Flexible evaluator days satisfaction: Programme Team satisfaction with flexible EL evaluator support (measured on a five-point scale; annual average)	3.5 (70%)	Substantially exceeded expectation
4.3. Joined-up assistance: Programme Team satisfaction with joint MR and EL support and the nature of collaboration between the two suppliers (measured on a five-point scale; annual average)	3.5 (70%)	Met expectation

Key Points
Output 4 details programme team satisfaction with the technical assistance provided by both MR and EL through the Technical Operations team, flexible days system and collaboration between the two contractors. The technical assistance provided was largely praised across the board, with flexible days especially receiving high praise, and collaboration between MR and EL improving over the period of the annual review. Thus, the Output is exceeding expectations and has scored an ‘A+’ overall.

In summary:
- MR’s Tech Ops assistance is well-received, and the team themselves received high praise
- The flexible days service offered by EL is very highly regarded, with programme teams using them to increase their internal capacity on a variety of topics
- Collaboration between MR and EL over the last year has certainly improved, though there is still a little work to be done.

MR Technical Operations Assistance
Feedback from PTs was generally very positive in terms of their satisfaction with MR technical assistance. The MR team are said to be very engaged, willing to help, professional, and always open to providing advice and support. They were also described as very organised and flexible. Support and expertise on logframes were noted as being good and very useful by a lot of interviewees, and MR were described as great facilitators and very technically competent, giving logical advice.

Other standout comments were that MR’s guidance on using Prospero has been useful, and that one PT benefitted from MR sharing lessons learned from other programmes when they were thinking about their own. MR were said to be very present and contributed at regular meetings, and one interviewee was pleased that MR knew when to step back and respect the knowledge of PT advisers.

However, there was also a small amount of negative feedback on the quality of the service received. One PT member felt that MR were focusing too much on perfecting a Theory of Change (ToC) when it was already good enough, another felt that MR’s feedback was a bit too general, as they already had enough expertise and wanted training on more specific themes, and a third wanted a little more structure on when to engage with the MR Hub as their interactions were rather ad hoc.

Other recipients of MR technical assistance were also overall rather pleased: specific feedback was that the MR team are very engaged, willing to help, professional and they “want to go the extra mile and do what they can for the PF”. They were said to be very organised and data savvy and have tried hard to get programmes to design their logframes and report results against them. The communications team were also flagged as performing well.

There were a couple of comments that the technical assistance is quite general though, and whilst this has been good – especially for teams that don’t have a solid background on the ToC and logframes – it may not be enough going forward if teams want more specialised advice in the context of international development. It was also noted that insights into the data would be very useful; flagging new ways of exploring the data or what more could be done with it.

On G&I, some of the Social Development Advisers (SDAs) said that they would like to be more sighted on revisions to programme logframes and ToCs and invited to key workshops, as this engagement has greatly reduced from the previous year. Additionally, some of the concerns they have flagged have not been actioned, which is frustrating. However, the SDAs noted that MR have engaged positively when requests have followed MR’s quarterly updates, and they are actively trying to increase their G&I offer.

EL Flexible Evaluator Days
The feedback from PTs on flexible days was overwhelmingly positive and the system has been described as “vastly improved” from the previous year. For PTs, flexible days have been helpful over the past year, working “incredibly well” and adding value. Some PT members would have liked to have had more flexible days, whilst others felt that theirs were sufficient – though the RT note that ODA budget pressures meant some PTs received fewer flexible days than initially planned. The way the days can be allocated through PFLearning was also praised, as well as the fact that days can be reallocated from one programme to another.

Flexible days have been used for a variety of things, though largely to help advise on recommendations coming from programme annual reviews, such as strengthening ToCs and logframes, developing KPIs and on G&I and SB. EL are able to provide valuable input because they have a wider perspective and know the programmes well. The support has also improved the technical capacity of PTs, with flexible days being used to help with the Value for Money scorecard on multiple programmes, as well as on G&I.

The EL PELs feel that the flexible days are very useful, especially for building relationships and trust with PTs. They have been well-used by PTs, are a good way to fill capacity gaps and allow the PT to be in control of what their technical support entails. There was some feedback that some PTs always wanted more flexible days when they could get them. The EL Central team did flag that the allocation of flexible days after the ODA reprioritisation exercise could have been better balanced, with half of teams that received 7 days asking for more, and four out of nine teams that received 25 days not using them all.

MR/EL Joined-up Assistance
Prior to the period of this annual review, EL were less involved in giving advice on ToCs and logframes, but this changed in December 2019 when they were given more of a mandate by JFU to do so.

Whilst some PT members felt that MR and EL work collaboratively, for example through holding joint workshops or having strong EL support at MR-led workshops, others didn’t feel they’d seen a difference in the level of collaboration between MR and EL over the past year, with some saying the two functions still feel separate. However, one noted that this isn’t a problem as they know which contractor to go to for what. One PT who are earlier on in their programme delivery cycle than the others were very positive about the joined-up service between MR and EL, with workshops playing an important role to the PT and them receiving direction and advice from both services on their ToC, logframes and Business Case, so this could perhaps be a legacy perception.

One MREL adviser noted that there has been a concerted effort by MR and EL teams to better define roles and responsibilities, and saw lots of evidence that the collaboration between MR and EL has improved over the past year as well as lots of good, joined-up work. JFU have also seen an improvement, and a resulting positive effect on some programmes. MR and EL now have an MoU between them, agreed ways of working and a shared menu of services – and gave combined presentations at the PFLearning event, which worked well. PTs have been given shared documentation so they can see when MR and EL will engage with them. However, because they are two separate contractors it’s not a completely smooth process and there are areas of overlap which isn’t ideal. They could also be more joined up, for example by producing a combined MREL satisfaction survey for service users – which the RT note is currently in development.

The contractors themselves feel that they have made good progress on improving collaboration over the past year. They reviewed their roles and responsibilities, clearly set out who did what, and have provided joint guidance and workshops. One benefit of being forced to work remotely since March due to the COVID-19 crisis is that this enabled better coordination between the two contractors on (virtual) country visits. They work together on comms to ensure that their separate services (Good News Stories and Stories of Change) don’t overlap and have weekly catch-up meetings between their counterparts to ensure that they are sharing information. However, they say that they could do more on this front, perhaps at a more senior level.

The PELs noted that EL and MR work together in a number of ways that work well, such as with weekly meetings on comms, discussions on Prospero’s Good News Stories, joint planning calls for PTs and on refining some of the KPIs. This has improved over the period of the annual review and has enabled PTs to receive better advice. Ad hoc pieces of work have also drawn the two contractors together, such as working on the templates for EL's Stories of Change, or on MR’s SB Attribution commission, and MR bring PELs into workshops using PTs’ flexible days. On an interpersonal level, the collaboration is said to be working well, with each team bringing in the other when needed.

On G&I, the two services have produced an information note for PTs on where they should go for information at different stages of the process, so it’s a lot clearer who does what, and MR sought out EL’s expertise on reviewing their G&I offer.

Summary of Responses to Issues Raised in Previous Annual Reviews
Recommendation 5. JFU MREL team to consider if the technical assistance provided by the MR supplier (through the MR Operations team) is the best way to reduce some programme team capacity gaps. In the meantime, two improvements to the current model:
- JFU MR Operations team should build a stronger internal quality assurance process. JFU should also consider how MR Operations work can be externally quality assured
- JFU MREL team to look at the feasibility of having MR Operations team to spend more time with programme teams, in particular FCO programme teams, in FCO London office.

The MR Hub have updated their internal quality assurance processes over the past year, creating a briefing note that details the measures they have put in place to quality assure the delivery of the MR service. These include training and inductions for MR Hub Technical Operations staff; training reviews; two layers of peer review and technical quality assurance; bi-annual internal reviews of MR technical support; gathering stakeholder feedback; and joint ways of working with EL. The note also details options for external quality assurance of the service, for JFU consideration. Additionally, EL were given more of a mandate in December 2019 to become more involved in giving advice on ToCs and logframes.

Recommendations
- EL and MR to continue to build on the progress they have made over the past year on collaborative working and ensure they are joined-up wherever possible
- JFU to review their expectations of MR and EL under Output 4 with the remaining time and resource left on contracts – and whether these differ for PTs based on their capacity:
  - MR to agree with JFU what their technical offer is to teams that have good MREL capacity and don’t need generic advice on ToCs and logframes
  - MR to ensure their advice is proportionate and they are not requiring programme teams to spend large amounts of time perfecting pieces of work that are already adequate.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (2 pages)

Programmes
The PF MREL Portfolio is delivered by two contracts, Monitoring and Reporting (PA Consulting) with a financial limit of £12,768,194 and the Evaluation and Learning contract (Tetra Tech and consortium partners Integrity and LTS International) with a financial limit of £23,957,497.
Financial Performance
Both MREL contracted services are paid monthly on INPUTS (that is time and materials) on an actual basis. The key cost drivers focus mainly on consultant time and fees. In addition, there are management charges and costs against travel, but due to the COVID-19 world pandemic travel costs have reduced significantly from the first quarter of the 2020/21 financial year.
During the review period there have been impacts on spend across programmes. The 3 key areas affecting budgets relate to:
1. Delay in programmes across PF starting and moving out of induction into implementation phase, thereby delaying evaluations
2. Readjustment of finances and resources impacted by the COVID-19 world pandemic from both the HMG and suppliers’ side.
3. The ODA prioritisation exercise which required budget reductions across the MR and EL contract spend profile.
Relating the actual spend to the revised budgets both contractors are running at a 2.5% - 3% underspend. Given this amount both suppliers have reacted and adjusted well to these difficult circumstances and have made considerable efforts to manage their contracts and work with the JFU MREL team to ensure service delivery continues.
Financial Reporting
Both MREL suppliers submit full breakdown of costs within their monthly invoicing process and explanations of variance to forecasted amounts which are challenged, clarified and agreed. Improvements have been made around the level of detail in providing assurance of costs. The monthly Contract Review Meetings provide the opportunity for the suppliers to discuss areas of work impacting on spend and potential impacts on forecasted values.
Financial Expenditure to end of 2020/21
	2017/18 Inception	2018/19 Implementation	2019/20 Implementation	Total to end of 2020/21
CONTRACT	Actual Spend £m	Actual Spend £m	Actual Spend £m	Forecast Spend £m
Monitoring and Reporting	2.91	2.87	2.2	1.77
Evaluation and Learning	0.90	4.32	4.83	4.68
TOTAL	3.81	7.19	7.03	6.45

Value for Money:
Economy (are we getting inputs at the right price?)
As above, both MREL contracts are paid on an INPUTS basis with the key cost drivers focused on fee rates and the number of days allocated to pieces of work. The EL contract was tendered through the DFID GEFA framework where rates are specified, and reductions agreed on a volume basis of 2.5%. The MR contract was tendered through OPEN OJEU competition with rates being benchmarked against rates held within the Crown Commercial Services Consultancy One framework with rates negotiated.
Across the MREL contracts, particularly with EL supplier, there is a large workforce delivering across multiple programmes. Both suppliers have processes in place for approval of new contractors and provide the JFU MREL team with evidence to justify recruitment for approval. There have been challenges during this review period with contract staff turnover with some vacancies remaining to be filled. The COVID-19 pandemic as well as the budget cuts arising from the ODA prioritisation exercise have impacted on confidence and created uncertainty. This should be monitored closely as the impact on PTs could be considerable and disrupt service delivery.
In relation to costs for individual pieces of work across PF teams, suppliers submit invoices for inputs on days and associated fee rates according to level of experience, qualifications and skills on an actual basis. The EL supplier allocates their budgets for workstreams internally which is flexible and can vary according to demand and engagement. The MREL team should consider fixing costs associated with workstreams to gain clarity on the variance of costs.
The flexible day offer was expanded in 2020 and feedback from Programme Teams has been positive for this resource with allocated days utilised by many programmes readily. The MREL team should consider the potential to reallocate unused days and prioritise to those programmes in need on a case by case basis.
Efficiency (how well is the programme converting inputs into outputs – Spending Well)
The JFU MREL team and suppliers have faced numerous challenges over the review period including the impact of COVID-19 global pandemic and the budget reductions emerging from the ODA prioritisation exercise. Despite these challenges both suppliers have managed to pivot and adapt services to deliver.
Feedback received from PTs has been in the main positive in relation to building capacity and understanding of the MREL function. The PFLearning Platform has provided useful learning particularly webinars and extracting lessons from evaluations. However, there is scope to refine the service, particularly in raising its profile across the JFU and usefulness to ensure that it’s the ‘go to’ place for information, support and learning. There was some feedback on the MR supplier over-delivering on some products which could be better utilised elsewhere. This is an area for the MREL to consider in refining inputs into outputs on a more cost effective basis maximising efficiency of effort
There has been complexity around the understanding and ease of interpreting invoices from the MREL suppliers to ensure clarity of spend. With payments made on an Inputs basis, the range of activities and deliverables is significant. During this review period both suppliers have provided increased clarity in relation to the breakdown of costs particularly on the main key cost driver of time and fee rates. However, there is an opportunity for MREL to seek definitive costings on individual workstreams which will provide increased assurance on spend.
During this period both the MREL suppliers have pivoted their services well according to the unprecedented conditions surrounding the COVID-19 global pandemic and the ODA prioritisation exercise. The requirement to reduce spend across both the EL and MR programmes provided an opportunity to re-focus priority work, reducing in other areas whilst maintaining meaningful service delivery.
Effectiveness (how well are our outputs delivering desired outcomes?)
Each of the MREL suppliers prepare and present monthly reports for the Contract Review Meetings to the JFU MREL team. Progress is monitored and reported, including weekly progress reports, allowing assessment of outcomes providing a ‘live’ position of the contract and stages of work and achievement of milestones.
The EL suppliers work on Approach Papers and Evaluations are quality assured through EQUALS (Evaluation and Quality Assurance and Learning Service) and for the review period has averaged 3.3 and 3.2 respectively ‘good’ performance with some pieces of work (5) rated excellent.
EQUALS Rating Scores.

Across the MREL Platforms offered to JFU and Programme Teams there has been substantial feedback on performance, accessibility and usability. Both the Prospero and PFLearning platforms have adjusted and adapted throughout the period of uncertainty with COVID-19 pandemic and ODA prioritisation funding adjustment. There has been positivity around the increase in MR’s Good News Stories from across the PF teams and the EL PFLearning increase in learning products. However, the feedback also highlighted frustration with ease of use with Prospero and lack of engagement. There was also concern over duplication of work with teams referring to internal data management as the main information source.
Detailed analysis of effectiveness on individual outputs is discussed earlier in the review (Outputs 1-4).
Equity (are benefits distributed in an even way that supports Inclusive Growth?)
The MREL contracts have supported the G&I agenda working with JFU advisers. The position is an improving landscape with more logframes including G&I indictors however there remains gaps in expertise across the portfolio.
MR contractors do not have specialist expertise in G&I, which has resulted in challenges in their ability to provide the necessary support as part of their agreed role. Attempts to recruit G&I expertise for the MR contractor were affected by the budget cuts. The MR contractor is required to work with programmes to:
- Support the refinement of Programme ToC that embed G&I
- Identify G&I fund level indicators
- Support the selection of programme specific G&I indicators
In recent months there have been improvements with strong collaboration between JFU, SDAs, MREL advisers and the contractors through the MREL G&I quarterly forum and feedback received to improve G&I related deliverables.
Demonstrable benefits of the EL service from an equity and inclusion lens that offer high value is the example of the most proactive use of the PFL platform by the network – i.e. gender as a CoP, which supported by a well-functioning and driven SDA + EL team, was able to share guidance and good practice examples used across the network. PFL was a great tool to share knowledge at scale across the network.
Overall VfM of the MREL Programme
The PF MREL programme has had to adapt its services and be flexible over the last 12 months. The COVID-19 global pandemic and the budgetary cuts emerging from the ODA prioritisation exercise as well as uncertainty around the Spending Review has provided a true test of endurance for the MREL team and suppliers.
Programming across the PF has increased, and results are emerging which merit acknowledgement with increasing capability and capacity. By emphasising communications and sharing of lessons, this will enhance the VfM contribution the MREL programme makes to the PF.
A key area of feedback from this review relates to evaluations and annual reviews taking place in the same year. Evidence provided from PTs suggests that this format has been particularly burdensome and resource intensive. Consideration should be given to assess and refine this process to explore alternative options to maximise effort and allocated funds.
Recommendations
- MREL suppliers to provide regular formal updates on VfM achievements across contracts ensuring maximum cost efficiency. Potentially using the 4E’s framework used in evaluation reports. In addition to provide a narrative on what did not provide VfM and how they would mitigate for this in future work.
- In relation to costs the JFU MREL team should consider a more effective approach in understanding individual workstreams budgets for assurance and transparency. An example of this could be the acceptance of pieces of work with defined budgets with payments or percentage of payments made on final approval of report or paper.

## E: RISK (1 page)

Risk Register in place: YES	Date of Last Review/Update: December 2020

Overall Risk Rating: Moderate
The overall risk rating for MREL has reduced from Major to Moderate during the timeframe under this annual review. In conjunction with the MREL risk register, 14 of the 22 identified risks were classed as moderate with 6 major and one severe. Regular updates provided by suppliers on risk also provide assurance on reducing impact on service delivery.
The MREL contracts cover a wide range of programmes across the PF with some still in their infancy. As noted within the last annual review, some programmes are still developing, and results have started to emerge, but the PF still has some time to mature.
Both the MR and EL contractors submit monthly risk registers as part of the Contract Review Management meetings and include Conflict of Interest registers and updates. In addition, both suppliers provide change control notices and staffing/resourcing reporting on issues impacting programme delivery.
There have been significant factors impacting the JFU MREL offer across Programme Teams over the last year.
1. The impact of the COVID-19 pandemic worldwide has reduced the capacity to travel for both JFU members of staff as well as suppliers. This has enforced suppliers to deliver remotely in most cases and reassess methods to engage teams.
2. The ODA prioritisation exercise required reductions in both EL and MR budgets necessitating reductions in programme deliverables and the need to re-focus priorities.
3. JFU MREL programme staffing resources were heavily impacted by a temporary hiring freeze at the outset of the COVID-19 pandemic with reduced capacity for the majority of the year.
4. During the lead up to the Government Spending Review and subsequent outcome along with the current Integrated Review, the uncertainty around future staffing and budgets has impacted on confidence across suppliers and the ability to plan ahead; there is also a risk this will affect staff retention going forward.

Overview of Programme Risk
The following represent PF MREL’s significant key risks:
Outcome of the Spending and Integrated Reviews (Strategic) – The continuing uncertainty in the short to medium term on potential impacts of the reviews, does not provide confidence or clarity on future work to the MREL suppliers and MREL Team and has been highlighted regularly. There have been considerable staff changes in both contracts which have a negative impact on business continuity and the ability to deliver VfM and react quickly to demand-led elements of the programme and support to Programme Teams.
Continuity Plan for the MR and EL Services (Strategic) – Both of the MREL contracts end on 30 November 2021 without a continuity plan in place to ensure ease of service transition. Uncertainty and lack of decision on the future of PF MREL continuity presents a key risk for PF teams to deliver, particularly with any break in service and access to expertise. There is also the risk of damage in relations with suppliers and disruption to the momentum of capability and capacity building.
Financial impact on MREL (Operational) - Both MR and EL suppliers had budgets in place to deliver outcomes for this year but due to the ODA prioritisation exercise in August 2020 these budgets were cut from Q1-Q3 and delays to spend in Q4. The reduction in spend and the required refocusing of business priorities across the PF programmes could result in a total underspend of the contracts and deliver less than anticipated, impacting on overall VfM.
Recommendations:
The MREL team to continue to regularly monitor their risk register and assess impact of the Spending and Integrated reviews.

## F: COMMERCIAL CONSIDERATIONS and WORKING PARTNERSHIPS (1 page)

Delivery against planned timeframe
The MR and EL contracts providing the MREL service to JFU PF continue to deliver and are due to complete in November 2021 (before the end of the anticipated life of the fund). Surrounding the COVID-19 pandemic and ODA prioritisation exercise including the reduction in budget, the suppliers have delivered and scaled up their service offer although some Programme Teams commented that they were unaware of the opportunity. Both suppliers had to quickly adapt and pivot their services with some commissions cancelled and re-alignment of priorities which were agreed with the JFU MREL Team.
Despite the delay in programmes starting across the PF fund there is evidence to suggest that they are progressing and catching up with the MREL contract and able to provide more detailed and useful evidence for the portfolio. This remains a risk to delivering VfM as the MREL service need the optimal number of PF programmes delivering their services to fully utilise the contract offer.

Performance of Partnerships
In general, the working relationships between the MR and EL suppliers across the JFU and other partner Government departments have been positive with feedback from the review interviews being constructive and collaborative in nature. There have been areas of concern relayed to the team on the level of communications surrounding products and services available and some PT’s highlighting minimal engagement with the MREL suppliers to date. A regular comment from JFU and PT’s has been the improvement in interactions after a slow start to engaging with MREL suppliers and the positive impact on service delivery.
The understanding of roles and responsibilities has remained an issue with PT’s when working with the service providers and this has led to confusion in some cases, understanding what the ‘offer’ was. However, progress has been made and clear communications should remain a priority.
There have been considerable external factors which have tested the relationship between the JFU MREL Team and the two contract providers. Specifically, with the COVID-19 world pandemic and the outcome of the ODA prioritisation exercise, but the evidence and feedback gathered suggests that there was a good understanding between them, demonstrating flexibility and adaptability to work with the conditions out of either party’s control.
Changes in the Delivery Plan
Over the review period there have been changes to the Delivery Plan. These relate to:
1. The significant impact of the COVID-19 world pandemic and the impact on contractual arrangements relating to service delivery and the reassessing and prioritising work across PF programmes.
2. The ODA prioritisation exercise conducted in July 2020 requiring programme budget reductions and movement of funds as a result of an expected economic downturn and reduction of GNI. The impact of the reductions affected deliverables / commissions, staffing and recruitment a well as travel.

## G: BUSINESS ENVIRONMENT (½ page)

This section was not completed by the review team as the MREL programme is internal facing and does not directly interact with the business community and environment.

## H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The JFU MREL team monitored the programme through participation in regular meetings with partners and users through the year. Over the last year a logframe based on a ToC was developed in consultation with delivery partners. JFU MREL maintained oversight and had final say in this development.
The review team found the logframe useful in framing our assessment but also recognised that this was not the only source of evidence to be taken into consideration. The review team interviewed over 50 people from a wide range of roles including, managers, users and delivery partners. We also reviewed relevant documentation and the Prospero and PFLearning web platforms. All these streams of evidence were used to make an assessment and score of performance at output level. They were also used to help assess progress towards outcomes as laid out in the ToC, but this assessment did not influence overall scoring.
Through this annual review the team identified several areas where the logframe could be strengthened:
Output 1: Monitoring and Reporting
It was difficult to independently corroborate MR’s self-assessment for output indicator 1.4. Although MR were reported as being faultless in terms of timings when running the quarterly reporting processes, being on time with all their correspondences, neither JFU nor MR recorded the dates that MR completed the Portfolio Board report template processes.
Additionally, ‘quarterly reporting processes could cover a number of things. Considering that: (a) “Portfolio Board reporting processes” is quite vague; (b) a lot of the timeliness of the Portfolio Board report depends on factors out with the MR Hub’s control; and (c) JFU don’t have any statistics on this indicator, it was difficult to disagree with MR’s self-assessment. However, JFU should look at refining this indicator to make it clearer what is being assessed and how.
- JFU to consider alternative ways to measure performance against outputs, given the low response rate to the Stakeholder Satisfaction Survey
  - MR and EL to produce a joint satisfaction survey for service users
- For indicator 1.4, JFU and MR Hub to work together to define exactly what “reporting processes” entails in the logframe, for both Quarterly Reports and Portfolio Board Reports, and to agree on how to track these robustly over the course of the next few months

Outputs 2: Evaluation and Output 3: Learning
- Indicator 2.1 “reports accepted as delivery completed” is not fully within EL control as it can only be met once JFU has signed off the report – following PT initial feedback, advisors feedback, JFU feedback. Should there be delays in the EL receiving feedback this would impact on the timeline to complete the report, change indicator to completion of “draft delivery”.
- Indicator 2.2 change milestone that rates AP and ER as percentage rated > good rather than have a fair category.
- EL (specifically PELs) to ensure an electronic evaluation satisfaction survey is applied during any interactive feedback session to ensure a higher and more representative response rate from PTs and partners.
- Indicator 3.1 on PFLearning content and support uses only time-based metrics i.e. time to upload content, time user profiles are set up and frequency of user training. It would be more useful to include a quality element as part of the performance measurement. Frequency and satisfaction with PFLearning, user profile setup and training (as measured in a quick live survey following PFLearning training sessions – scale.)
Output 4: Technical assistance
JFU to consider broadening the focus of Output 4, given that all indicators specify ‘programme team satisfaction’ but the overall output looks at the quality of technical assistance provided to all PF staff.