 Programme Completion Review – September 2020

Title: Monitoring, reporting, evaluation and learning in the Prosperity Fund
Final Programme Spend £ (full life): £27,266,468	Review Date:	June 2021
Programme Code: EL: CPG/1428/2016 / MR: CPG/1417/2016	Start Date: / September 2017	End Date: / April 2021

Summary of Programme Performance

Year	2018/19	2019/20	2020/21
Programme Score	N/A	B	A
Residual Risk Exposure Rating	N/A	Major	Moderate

DevTracker Link to Business Case (and any addendum):	https://www.gov.uk/government/publications/prosperity-fund-monitoring-reporting-evaluation-and-learning
DevTracker Links to all logframes used during programme lifetime:

List of Acronyms

AR = Annual review
Delivery partners = implementing partners (private companies, multilateral organisations or NGOs) hired by programme teams to implement PF programmes
EL = Evaluation and Learning contract
EQUALS = Evaluation Quality Assurance and Learning Service
FCDO = Foreign, Commonwealth and Development Office
G&I = Gender and Inclusion
GPST = FCO Global Programme Support Team
JFU = Joint Funds Unit
JFU Points of Contact = the individual contact person in the JFU. Each programme has one point of contact.
MR = Monitoring and Reporting contract
MREL = Monitoring, Reporting, Evaluation and Learning
ODA = Official Development Assistance
PF = Prosperity Fund
PFDU = FCO Prosperity Fund Delivery Unit
PEL = Programme Evaluation Leads
PTs = Programme Teams
SB = Secondary Benefits
SRO = Senior Responsible Owner
ToC = Theory of Change
VfM = Value for Money

A. Summary and Overview

Description of the programme and what it has achieved

The MREL programme sought to ensure “a more effective Prosperity Fund – that is higher impact, better value for money and better managed – both in terms of the portfolio and individual programmes due to the availability and uptake of MREL recommendations and support”. The programme was responsible for providing MREL support across the whole of the PF, through independent evaluation, providing technical advice on MREL to PF programme teams and by aggregating and analysing information to provide a portfolio-level view for JFU and other parts of HMG. Key outcomes, intermediate outcomes and outputs are described in the programme ToC.

This MREL programme was not intended a replacement for programme level monitoring functions but looked to provide a range of portfolio and programme level services. These services were designed to support management and accountability by enabling all three levels of the PF (Portfolio, Departments and Programmes) to access results, progress dashboards and independent evaluation of contribution to outcomes. These services were also designed to improve practice across the PF network by surfacing, documenting and sharing the evidence-base and learning underpinning the design and delivery of what is a large scale and innovative fund to support adaptation, course corrections and future design.

The PF portfolio level MREL capability was split and outsourced into two synergistic components:

Component 1: Monitoring and Reporting (MR)
Monitoring and Reporting was delivered through a 3.5-year contract (Sept 2017 – April 2021) with PA Consulting.

Programme ToC and logframes are central to measuring results and adapting to achieve high impact. The MR technical assistance work delivered demand-led support to assist programmes in refining ToC and developing logframes for their programmes to ensure they can link into the PF level ToC.

The MR supplier was also tasked with capturing reporting from across the Portfolio and ensure results could be used at a project, programme and fund level to inform decisions. This was delivered through an internet-based platform called Prospero.

Component 2: Evaluation and Learning (EL)
Evaluation and Learning is delivered through a circa 3.5 year contract (Sept 2017 – April 2021) with a TetraTech-led consortium including Integrity and LTS/Niras International.

EL are important functions to help ensure a focus on key objectives, maximise impact and VfM, and manage risk.
While supporting accountability, this was not the primary purposes of EL; instead, learning activities were intended to help generate an evidence base (on primary purpose and secondary benefits), help improve the effectiveness of PF programmes, support sharing of knowledge across the fund and inform communication of impact. It was also hoped that EL would address the needs of different stakeholders:
- At fund level EL would assess the extent to which PF is contributing to inclusive economic growth and delivering secondary benefits to businesses. EL was also expected to inform thinking on future, similar funds through synthesising lessons from programmes and cross fund evaluation of particular themes;
- At programme level it would test the theories of change and establish, while the programmes are running, whether they are delivering the outputs and outcomes that will likely lead to impact. Useful and usable learning should have contributed to identifying programmes and projects not performing optimally and allowing corrective measure.

The two MREL contracts were originally intended to run until Nov 2021 but, as a result of the closure of the Prosperity Fund on 31 March 2021, the MREL contracts were terminated early on 30 April 2021.A timeline of key moment is shown below.

Major lessons learned, evidence generated and recommendations

Below we have documented the major lessons learned which we hope will helpful to future FCDO teams working on similar MREL programmes.

Having a centralised MREL system proved to be effective, ensured consistency and established a MREL culture amongst PF programme teams working across several government departments, some of whom were new to ODA programming.

If FCDO wish to develop a portfolio management tool again, we recommend the terms of reference are structured such that FCDO is buying a product rather than a service so that FCDO still has access to the system after the contract ends. Alternatively, FCDO could consider developing it in house. The rationale for this suggestion is that, for this programme, at the end of the contract FCDO lost access to Prospero because it was built on PA Consulting’s systems and it was deemed too difficult and costly to transfer onto FCDO systems. This risk should have been clearly specified at the tendering stage.

There was a time-lag between data collection, data entry intro Prospero and portfolio-level report production. This meant the reports generated using Prospero data were not always able to include the most up to date results data and management information. A key lesson in this regard was the need to engage senior level stakeholders to ensure they understand the dependencies and time lag between data being entered to Prospero and ending up in reporting products like the monthly Portfolio Board report.

It was challenging to get programme teams to engage with Prospero because it was a portfolio management tool and wasn’t directly useful to them. In the future, any portfolio management tool, should be built so that it is also useful to the programme teams else low engagement is likely to be a problem.. Additionally, ensuring the ease of uploading information is critical to engagement and use. Finally, more clearly showing programme teams how Prospero data could be used for adaptive portfolio management decision-making may have helped increase programme user ‘buy in’.

The PF broke new ground in seeking to formally define and measure secondary benefits. The fund made significant progress in developing policy and guidance for measuring secondary benefits. However, the extent to which PF suppliers – with ODA-funded contracts – were able to commit resources to secondary benefit measurement varied.

The evaluation contractors had a associate based of 80-100 people. Over time they found it was more efficient and effective to draw on fewer people able to provide more time to the programme, rather than drawing on a large number of experts with limited inputs. This is because it is time-consuming to bring staff up to speed, and because an adaptive programme requires ongoing intense involvement to remain ‘up to date’.

Evaluation findings and recommendations should be packaged differently for different audiences. The evaluation contractors developed a suite of products to share learning with different audiences; this included workshops for programme teams, executive summaries for senior and managerial FCDO staff, detailed reports for technical staff, and multimedia learning products for the wider PF community.

Facilitating learning requires different expertise from that of conducting evaluations. Evaluators should be supported to develop learning products, and specialist skills (including storytelling, graphic artists, etc.) should be included in the team.

How this report was conducted

This PCR was intended to be a ‘light touch’ process given it was done only 5 months after a comprehensive annual review. It was prepared by the FCDO team who worked most closely with the contractors.

Actions following approval of this report

There are no outstanding actions on the programme. Final payments have been made, final financial statements have been received, and there were not any assets to dispose of. All data on Prospero and PF Learning have been transferred to the FCDO and deleted from contractors systems.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£37m	£27,266,468
Timeframe	September 2017 - November 2021	September 2017 - April 2021
Outcomes	Increased ability of JFU and Programme Teams to apply best practice standards of transparency and accountability. / Increased Programme Team and JFU ability for evidence-based decision-making and adaptive programme and portfolio management. / Increased PF staff confidence and ability to engage with, deliver and oversee MREL

Overall assessment of programme outcomes, sustainability and VfM

The decision to set up a centralised MREL system for the PF when the fund began has proved to be effective in supporting accountability and the fund’s credibility, allowing effective working across multiple HMG departments, ensuring greater consistency and establishing a MREL culture amongst PF programme teams. At the time the MREL programme was designed, a central approach managed by JFU made sense because FCO and programme teams from other government departments did not have the technical capacity or resources to commission MREL themselves. This centralised approach allowed greater consistency in approaches and the potential to aggregate results and learning at the portfolio level. The MREL programme undoubtedly increased programme teams’ confidence and ability to engage with, deliver and oversee MREL, especially for FCO teams who were new to ODA programming. This will likely have a lasting impact as many of these individuals continue to work in the newly created FCDO.

The MREL programme likely did increase the incidence of PF programme teams applying best practice standards of transparency and accountability. All programmes developed theories of change and logframes and these were regularly reviewed. Additionally, all programmes reported on their progress quarterly to the JFU and conducted their own Annual Reviews. Additionally almost all programmes were subject to at least one independent evaluation, though many of these are yet to publish them online. Given that many programme teams were not familiar with these ODA transparency and accountability concepts and processes at the inception of the PF, without this MREL programme it is quite likely that programme teams would have struggled with these aspects. Additionally the PF itself was subject to three fund-level independent evaluations.

The MREL programmes were only somewhat successful at enabling Programme Teams and the JFU to use evidence to improve the programmes. On the whole Programme Teams found the evaluation recommendations useful and there were some good examples of where evaluations influenced decision making. However, the initial delays in design, approvals, procurement and set-up of PF programmes in the first two-to-three years substantially reduced the time available for the MREL programme to influence programme teams. Even though the MREL programme ran for 3.5 years, it was only in the final year of the MREL programme that almost all PF programmes were in implementation[1] - so the time available to change and improve programmes was limited. In particular, these delays, and the required time to get data onto Prospero meant this tool was not used to its full potential. Should FCDO procure a portfolio management tool similar to Prospero again, we recommend the terms of reference are structured such that FCDO is buying a product rather than a service so that FCDO still has access to the system after the contract ends. Alternatively, FCDO could consider developing it in house. FCDO lost access to Prospero because it was built on PA Consulting’s systems and it was deemed too difficult and costly to transfer onto FCDO systems. The data on Prospero nevertheless continues to be available to the FCDO for programme management purposes, despite the Prospero system itself no longer being live.
[1] Two years before the end of the MREL contract only 6 out of 27 PF programmes were in the implementation phase

The total amount spent on the MREL contracts was approx. 4.5% of the amount spent by the PF. This is a reasonable proportion to spend on MREL with recommendations for M&E spend usually between 2% and 10%. For the PF, HMT had ring fenced 5% of the total PF allocation for MREL so the amount spent on MREL was in line with expectations at the outset.

## C: Detailed Output Assessment

Output Number and Title	Output 1: Monitoring and Reporting: Timely and accurate information on Prosperity Fund programme and portfolio performance for programme teams and Joint Funds Unit
Output Score	B
Impact weighting (%)	30%		Impact weighting revised since last AR?	No

Output Indicator		Starting Target for Nov 2021	Final Logframe Target for Apr 2021	Final Result Achieved
1.1. Prospero satisfaction. User satisfaction with the system, measured by % users rating it as 'good' or above		80%	75%	Moderately did not meet expectation / 64% - this is the average score on the Likert scale with 29 respondents. Of the 29, 14 (48%) of respondents agreed or strongly agreed with the statement ‘Prospero is friendly, intuitive and easy to navigate to the desired information’.
1.2. Prospero availability. Measured by: (i) site availability (24 hours/day, 7 days/wk); / (ii) time taken to resolve critical defects (P1), / and time taken to refresh: (iii) data page, and; (iv) dashboard page		(i)99%; (ii)100% <1 working day; (iii)100% < 2 seconds; and (iv)100% < 10 seconds	(i)99%; (ii)100% <1 working day; (iii)100% < 2 seconds; and (iv) 100% < 10 seconds	Met expectation / i) 100% ii) 100% iii) 100% iv) 100%
1.3. Prospero engagement. Measured by: (i) % active users (out of registered user); (ii) % logframes MR on-boarded to Prospero within agreed KPI timeframe		(i) 80%; (ii) 100%	(i) 75%; (ii) 100%	Moderately did not meet expectation / i) 61% ii) 100%
1.4. Reporting timeliness. % reporting processes run in line with agreed commissioning timetables, disaggregated by: / (i) quarterly reporting, and; (ii) Portfolio Board report templates		i) 100%; ii) 100%	i) 100%; ii) 100%	Met expectation / i) 100% ii) 100%
1.5. Commission and bespoke report usefulness. Measured by: (i) Portfolio/Programme Manager satisfaction with bespoke reports; (ii) satisfaction with commissions (both measured on a five-point scale; annual avg); / (iii) % bespoke reports delivered within agreed deadline, and; (iv) % commissions delivered to agreed workplan timeframe		(i), (ii) 4.0 average (=80%); (iii) 80%; (iv) 90%	(i), (ii) 4.25 average (=85%); (iii) 85%; (iv) 92.5%	Moderately did not meet expectation / i) last measured 3.3 in Nov 20 ii) N/A iii) 100% iv) 100%

The satisfaction and engagement with the Prospero platform and resulting products was lower than expected. Programme teams found it ‘clunky’ and time consuming to upload data, and didn’t find the tool directly useful for their own work because it was mainly a portfolio mamangement tool. These two issues have led to a lack of data being loaded onto the system. This, however, is not a reflection of the efforts or usefulness of the MR team who consistently received very positive feedback from interview respondents including about their willingness to help, responsiveness and pro-activeness in reaching out to programme teams. The information in Prospero was used for background context in Board meetings but with concerns around quality and timeliness it was not key to decision making.

Lessons learned through this output, and recommendations for future programming
1. If FCDO wish to develop a portfolio management tool again, we recommend the terms of reference are structured such that FCDO is buying a product rather than a service. Or alternatively, consider developing it in house. The rationale for this suggestion is that, for this programme, at the end of the contract FCDO lost access to the Prospero system software because it was built on PA Consulting’s systems and it was deemed too difficult and costly to transfer onto FCDO systems. FCDO does however continue to have access to the data that was loaded on to Prospero for future programme management purposes.
2. There was a time-lag between data collection, data entry into Prospero and portfolio-level report production. This meant the reports generated using Prospero data were not always able to include the most up to date results data and management information. A key lesson in this regard was the need to engage senior level stakeholders to ensure they understand the dependencies and time lag between data being entered to Prospero and ending up in reporting products like the monthly Portfolio Board report.
3. It was challenging to get programme teams to engage with Prospero because it was a portfolio management tool and wasn’t directly useful to them. Exploring how the tool could have been more useful to programme teams would have been useful early on. Additionally, ensuring the ease of uploading information is critical to engagement and use. Finally, more clearly showing programme teams how Prospero data was used PF adaptive portfolio management decision-making may have helped increase programme user ‘buy in’.

Output Number and Title	Output 2 Evaluation: Technically robust and independent evaluation products with clear recommendations for Programme Teams and JFU
Output Score	A
Impact weighting (%)	25%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target for Nov 2021	Final Logframe Target for Apr 2021	Final Result Achieved
2.1 Evaluation delivery: % and # of Approach Papers and Evaluation Reports accepted as 'delivery completed' by JFU (annual)	100%	100%	Met expectation
2.2 Evaluations quality: % of Approach Papers and Evaluation Reports rated by EQUALS as (i) 'fair', and (ii) 'good' or above (cumulative)	(i) >90% fair, (ii) >70% good	(i) >85% fair, (ii) >70% good	Exceeded expectation / 83% reports submitted to EQUALs scored good or above
2.3 Evaluations satisfaction: Satisfaction with Evaluation Reports from Programme Teams (measured on a five-point scale generated by composite questions agreed with JFU; annual avg)	4 (80%)	3.75 (75%)	Moderately exceeded expectation / 4.6 point average (91%) from a 40% PT feedback response rate. (last measured Nov 2020)
2.4 Evaluations satisfaction: Satisfaction with Evaluation Reports from Portfolio Managers e.g. JFU, dept advisers (measured on a five point scale generated by composite questions agreed with JFU; annual avg)	4 (80%)	3.75 (75%)	Moderately did not meet expectation / Perception score not requested / 41% were good, clear, concise, well written / 41% included some info gaps, areas could be strengthened , several rounds taken to finalise, misunderstanding of brief, significant re-write / 6%[2] were of questionable usefulness / The remaining uncommented / (last measured Nov 2020)
[2] Note: the red rated report was interestingly scored a 5/5 by the PT illustrating the challenge of the difference in expectations between JFU and PTs in some cases

The EL team delivered 19 programme evaluations, 1 sector level evaluation, 8 thematic evaluations and 3 fund-level evaluations . The delivery of technically robust and independent evaluation products with clear recommendations for programme teams and JFU lead to improved evidence base on mutual prosperity, secondary benefits and X-HMG ODA delivery. The quality of products through these activities received consistently good scoring from EQUALS, an independent quality assurance function. Satisfaction with this service was high, especially from programme teams who found working closely with Programme Evaluation Leads (PEL) a good way to maximise learning. There was some evidence of programme teams effectively using evaluation evidence and learning to influence decision making and adaptive management, for example in the ASEAN LCE, Mexico and ASEAN Economic reform programmes. Largely it is still too early in most programme life cycle and there’s not a lot of evidence of programme teams using the available evidence from this work to make major changes to programming, although operational changes are evident, informed by evaluations.

Lessons learned through this output, and recommendations for future programming:
1. The evaluation contractors found it more efficient and effective to draw on fewer people able to provide more time to the programme, rather than drawing on a large number of experts with limited inputs. This is because it is time-consuming to bring staff up to speed, and because an adaptive programme requires ongoing intense involvement to remain ‘up to date’.
2. Evaluation findings and recommendations should be packaged differently for different audiences. The evaluation contractors developed a suite of products to share learning with different audiences; this included workshops for programme teams, executive summaries for senior and managerial FCDO staff, detailed reports for technical staff, and multimedia learning products for the wider PF community.
3. Facilitating learning requires different expertise from that of conducting evaluations. Evaluators should be supported to develop learning products, and specialist skills (including storytelling, graphic artists, etc.) should be included in the team.

Output Number and Title	Output 3 Learning timely and relevant MREL resources, publications and events to support PF staff engagement with data, findings and learning
Output Score	A
Impact weighting (%)	25%		Impact weighting revised since last AR?	No

Output Indicator		Starting Target for Nov 2021	Final Logframe Target for Apr 2021	Final Result Achieved
3.1 PFLearning content and support: PFL content and user support are made available in a timely fashion measured by: (i) time within which content is uploaded, (ii) time within which user profiles are set up, (iii) frequency of user training		(i) 2 working days, (ii) 5 working days; (iii) monthly	(i) 2 working days, (ii) 5 working days; (iii) monthly	Met expectation
3.2 PFLearning availability: Measured by (i) site availability (24 hrs/day, 7 days/wk. excluding scheduled downtime), and time taken to respond to: (ii) blockers issues; and (iii) critical issues (during UK office hours)		(i) < 1% unscheduled down time (ii) 15 mins; (iii) 2 hours	(i) < 1% unscheduled down time (ii) 15 mins; (iii) 2 hours	Met expectation
3.3. Learning products usefulness: learning inputs and products are deemed by Programme Teams to support engagement with findings, learning and recommendations. (measured on a five-point scale; annual avg)		4 (80%)	3.75 (75%)	Met expectation / (last measured Nov 2020)
3.4Learning products usefulness: learning inputs and products are deemed by Portfolio Managers e.g. JFU, dept advisers to support engagement with findings, learning and recommendations. (measured on a five-point scale) (annual avg)		4 (80%)	3.75 (75%)	Met expectation / (last measured Nov 2020)

The EL team, provided a timely and accessible service through the PFLearning platform, which has 650 HMG users. The rapidly deployed COVID-19 site on PFLearning was a particular success. EL produced good quality learning products, made them available in different formats and improved communication making learning more accessible. This included 7 reflection pieces (case studies), 2 stories of change and 11 products summarising learning from evaluation reports. Although the PFLearning platform has been developed as designed and managed to a high quality a majority of interview respondents said they did not regularly use the site to access or share learning. A key feature of PFLearning is the network area and communities of practice enabling X-fund learning. The Gender & Inclusion Community of Practice is the best example of this and is actively led by a group of HMG Social Development Advisors.

Output Number and Title	Output 4: Technical Assistance: Timely, expert MREL technical assistance provided to Prosperity Fund staff
Output Score	A+
Impact weighting (%)	20%		Impact weighting revised since last AR?	No

Output Indicator		Starting Target for Nov 2021	Final Logframe Target for Apr 2021	Final Result Achieved
4.1. Tech Ops assistance satisfaction: Programme Team satisfaction with MR TA support, measured by: (i) general satisfaction (from bi-annual survey), and; (ii) immediate feedback from service users (both measured on a five-point scale; annual average)		i) 4 (80%) ii) 4 (80%)	i) 3.75 (75%) ii) 3.75 (75%)	Moderately exceeded expectation / i) 3.93 (78.6%) - average score to Stakeholder Satisfaction Survey question ‘The technical support I have received has benefitted me’ - 13/15 respondents (plus 8 who answered ‘N/A’) answered ‘agree’ or ‘strongly agree’. ii) N/A / (last measured Nov 2020)
4.2. Flexible evaluator days satisfaction: Programme Team satisfaction with flexible EL evaluator support (measured on a five-point scale; annual average)		4 (80%)	3.75 (75%)	Substantially exceeded expectation . (last measured Nov 2020)
4.3. Joined-up assistance: Programme Team satisfaction with joint MR and EL support and the nature of collaboration between the two suppliers (measured on a five-point scale; annual average)		4 (80%)	3.75 (75%)	Met expectation / (last measured Nov 2020)

The majority of programme teams were happy with the technical support received on ToC and logframe development. JFU’s decision to change the technical support offer from only being provided by MR to using both the relative strengths of MR and EL teams in a joined-up way to provide technical support to programme teams worked well. In addition to support from the full-time MR Hub team at PA consulting, programme teams were also supported by 572 days of support from the EL team. The days were used for a variety of support including not just strengthening of Theory of Change and logframes but also developing indicators and support on Gender & Inclusion and Secondary Benefits.

D: Risk

The Risk profile of the MREL contracts, both MR and EL, was reduced from Major to Moderate in the last Annual Review conducted in 2021. Over the contractual period there have been significant impacts affecting delivery including the early closure of both programmes.

Throughout the contract period both the MR and EL contractors submitted monthly risk registers as part of the Contract Review Management meeting process which included Conflict of Interest registers and mitigating actions to reduce potential delivery risks. In addition, both suppliers provided change control notices and staffing / resourcing reporting on issues impacting on the programmes. The supplier risks were monitored and cross-referenced with the internal JFU MREL risk register to ensure all aspects of risks were covered and a full assessment made including acceptance on level and impact of risks.

There were significant factors impacting the delivery MREL contracts:
1. The impact of the COVID-19 pandemic worldwide reduced the capacity to travel for both JFU members of staff as well as suppliers. Enforcing suppliers to deliver remotely in most cases and reassess methods to engage teams.
2. The ODA prioritisation exercise in 2020 required reductions in both EL and MR budgets necessitating reductions in programme deliverables and the need to re-focus priorities.
3. JFU MREL programme staffing resources were heavily impacted by a temporary hiring freeze at the outset of the COVID-19 pandemic reducing capacity for the majority of that year.
4. During the lead up to the Government Spending Review and subsequent outcome along with the current Integrated Review, the uncertainty around future staffing and budgets impacted on confidence across suppliers and the ability to plan ahead; affecting the risk of staff retention.

Early MREL Contract Closure
The decision to exit the MREL contracts early raised the potential for major delivery risk to the programme and support to PF teams. The risk was mitigated through continual dialogue with suppliers, strong relationships established and clear exit plans and deliverables drawn up with roles and responsibilities clearly understood between parties.

Data delivered by the suppliers on the Prospero and PF Learning systems was retained and secured to ensure evidence and lessons learned from the PF programme, providing a clear audit trail for future enquiries. The FCDO secured confirmation from suppliers that data and information held on their systems were safely and securely disposed of.

E: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

The MR and EL contracts were procured and commenced in 2017 utilising an open OJEU competition and the DFID GEFA framework respectively. Throughout the life of both contracts there were staffing changes on both sides which was controlled and managed to reduce the risk of disruption by clear communications and handover reports.

The MREL programme, over its lifetime, faced considerable challenges and changes having to adapt and be flexible with suppliers, having to upscale certain areas of work and some commissions were cancelled due to realignment of priorities. Highlighted areas of change included:

1. The significant impact of the COVID-19 world pandemic and the impact on contractual arrangements relating to service delivery and the reassessing and prioritising work across PF programmes.
2. The ODA prioritisation exercise conducted in July 2020 requiring programme budget reductions and movement of funds as a result of an expected economic downturn and reduction of GNI. The impact of the reductions affected deliverables / commissions, staffing and recruitment a well as travel .
3. The early closure of both MREL contracts and the impact of PF programmes. Significant pressure placed on working relationships and retaining key staff to maintain service delivery.

Supplier Performance and Partnerships
During the challenges faced by suppliers (as above) they performed well and continually adjusted to meet the needs of the programme and changing priorities. Through the monthly Contract Management Review meetings both suppliers separately reported back on key areas of their contracts and regularly faced scrutiny on deliverables, forecasted values v actual costs as well as risk and programme changes requests.

Some PF programme teams however, expressed concern over poor communications as to what the offer was with the suppliers and the definition and clarity surrounding roles and responsibilities. After the slow start up of a number of PF programmes progressing to mobilisation, the position improved with engagement increasing.

During the early closure phase of both contracts the established working relationships with the suppliers provided a solid platform to ensure an orderly exit and reduce the negative impact for PF programmes. With regular communication (often daily meetings), agreed exit plans and strategies were implemented and clear timelines communicated across programme teams and senior management.

Financial Performance.
Both MREL suppliers submitted full breakdown of costs within their monthly invoicing process and explanations of variance to forecasted amounts which were challenged, clarified and agreed. Improvements were made around the level of detail in providing assurance of costs. The monthly Contract Review Meetings provide the opportunity for the suppliers to discuss areas of work impacting on spend and potential impacts on forecasted values. Both suppliers ran at a slight underspend (approx. 3%)

Value For Money
Both MREL contracts were established on an inputs basis i.e time and materials with no financial Key Performance Indicators in place to improve quality and timeliness of deliverables. The key cost drivers were fee rates across input days and expenses (although due to the Covid pandemic these reduced significantly) and management fees. A key issue for consideration is that both MREL suppliers did not report on contractual VFM metrics which should have been identified during contract design and before sign off took place. By doing so and considering the basis of a hybrid payment model, additional benefit could have been secured offering increased VFM

Programme-level approach to monitoring and evaluation [1/2 page]

The MREL programmes were dictated by COVID restrictions dictating that field visits weren’t possible meaning it was mainly a desk based review, with semi-structured interviews among key stakeholders, which drew heavily from material in the Annual Report. With regard to monitoring and evaluation of the contracts, quarterly Contract Management Boards were held, led by the SRO to asses performance, impact and direction. In addition, monthly Contract Review Meetings were held with both suppliers reviewing performance, risk and outputs as well as financial performance.

Date of last narrative financial report	24 May 2021	Date of last audited annual statement	23 April 2021