­­
Colombia Programme
 Cycle 1 Evaluation Report
FINAL
Prosperity Fund Evaluation and Learning

October 2019

Table of Contents

List of Tables

List of Figures

List of Boxes

Table of Acronyms
Acronym
ANI	National Infrastructure Agency
BC	Business case
CAF	The Development Bank of Latin America
CBA	Cost-benefit analysis
Confecámaras	Colombian Confederation of Chambers of Commerce
CSSF	Conflict, Stability and Security Fund
DANE	National Agency of Statistics
DFID	Department for International Development
DIT	Department for International Trade
DNP	National Department of Planning of Colombia
E&L	Evaluation and Learning
EQ	Evaluation Question
FARC	Revolutionary Armed Forces of Colombia
FCO	Foreign and Commonwealth Office
FDI	Foreign direct investment
FDN	Financial Institution for National Development
Findeter	Financial Institution for Development of the Regions
GEA	Gender Equality Act
G&I	Gender and Inclusion
IDB	Inter-American Development Bank
IP	Implementing partner
IUK	Innovate UK
JFU	Joint Funds Unit
KII	Key informant interview
Logframe	Logical framework
MoU	Memorandum of Understanding
M&R	Monitoring and Reporting
NDP	National Development Plan
OCP	Open Contracting Partnership
ODA	Official development assistance
OECD	Organisation for Economic Co-operation and Development
PEL	Programme Evaluation Lead
PF	Prosperity Fund
PPP	Public-private partnership
PT	Programme team
SB	Secondary Benefit
SECOP	Electronic System for Public Procurement
SDA	Social Development Adviser
SIGRA	Risk Information System for the Agricultural Sector
SMART	Specific, Measurable, Achievable, Realistic and Timely
SME	Small and medium-sized enterprise
ToC	Theory of Change
ToRs	Terms of reference
VfM	Value for Money

Version History
D03_02	Colombia Programme Cycle 1 Evaluation Report
	Revision	1
Revision	Written By	Checked By	Approved By
Revision 0	xxxxxxxxxxxxxx, xxxxxxxxxxxxxxxxx, xxxxxxxxxxxxxxxx, xxxxxxxxxxxx, xxxxxxxxxxxxxxxx	xxxxxxxxxxxxx
Revision 1	xxxxxxxxxxxx, xxxxxxxxxxxxxxx	xxxxxxxxxxxxxx
Revision 2

# Executive summary
## Overview
This Cycle 1 report for the Colombia Prosperity Fund (PF) programme covers the early design phases through to implementation, from 2017 to July 2019. This annual evaluation will take place ahead of the internal Annual Reviews each year up to 2021 currently. The aim for this evaluation report is to provide the Colombia Programme Team (PT) and PF Joint Funds Unit (JFU) with programme insights, lessons learned to date and recommendations for adaptive decision-making.
The Colombia PF programme aims to support economic development, unlock economic opportunities and drive inclusive growth in post-conflict and conflict-affected regions. The £25.5 million programme is being implemented by the Foreign and Commonwealth Office (FCO) from 2018 to 2022 and focuses on three key sectors – infrastructure, agriculture and institutional strengthening – through seven projects or ‘activities’. The infrastructure strand includes activities relating to urban and rail infrastructure. Agriculture includes an activity on agri-insurance and the Agri-Tech Catalyst Challenge Fund, which comprises seven grants. Finally, three activities focus on institutional strengthening, including regional competitiveness, open public procurement and corporate governance reform of the National Infrastructure Agency (ANI). All activities have a Gender and Inclusion (G&I) focus, with the aim to include women and other disadvantaged groups in project design and ensure implementation responds to their particular priorities and needs. The three Colombia PF sectors and their seven respective activities were selected by the PT for their potential to deliver primary benefits (poverty reduction as a result of inclusive growth) and secondary benefits (SBs) (expanded trade and investment opportunities). It is estimated that the programme will deliver £2 billion of primary benefits and £265 million of SBs.
The selected evaluation methodology for this first Cycle was developed in consultation with the wider PF Evaluation and Learning (E&L) team as well as the Colombia PT. It applies the principles of theory-based methodologies to identify early indications of change, with a focus on initial programme activities and outputs, resulting in lessons learned and recommendations. This Cycle 1 evaluation will form the baseline for subsequent annual evaluations, which will use contribution analysis to review observable outcomes and assess progress towards them and impact in line with the Colombia PF’s umbrella (programme-level) Theory of Change (ToC).
The Cycle 1 evaluation relied predominantly on qualitative data generated from key informant interviews (KIIs) and a background document review. The independent E&L team carried out a field visit to Colombia during the data collection phase to engage directly with the PT, the main implementing partners (IPs) and the beneficiaries in four cities across Colombia.
This evaluation report includes findings organised by Evaluation Question (EQ), as well as lessons learned, and also puts forward practical recommendations for its primary audience, the Colombia PT. These are summarised in the next section.
## Key findings
### Evaluation Question 1: What evidence is there that the Prosperity Fund is likely to contribute to the intended outputs and outcomes in the Theory of Change, as well as any unintended or unexpected outputs?
It is too early to assess the likely contribution of the programme to intended outputs and outcomes in the ToC, as well as any unintended consequences. It is encouraging to see that primary and secondary benefits are central to the umbrella ToC, thus increasing the chance of the programme delivering inclusive growth. The coherence between the programme ToC and the PF ToC and the internal coherence between the programme ToC and the activities’ objectives also increase the chance of positive outcomes. There are indications that a number of activities undertaken are delivering on outputs.
### Evaluation Question 4: What evidence is there that the changes supported by the Prosperity Fund interventions will be sustainable and ensure environmental sustainability, will be self-financing and will lead to inclusive growth that reduces inequality?
The Colombia Programme has strategically positioned itself to ensure sustainability by choosing to work in sectors that are aligned with national and subnational plans. The terms of reference (ToRs) for PF-funded activities include conditions on financial and environmental sustainability.
### Evaluation Question 6: How has the balance and relationship between primary and secondary benefits across the portfolio influenced the achievement of results?
There is common understanding between the PT and IPs on who the primary and secondary beneficiaries of the programme are. The programme engages indirectly with primary beneficiaries via the IPs and directly by working with governments and individuals. The PT considered SBs in the programme design. When choosing which sectors to work on, the team chose sectors where the UK has comparative advantages. The promotion of SBs is led by the PF’s Commercial Adviser, who works closely with the Department for International Trade (DIT) in London in promoting the PF in the UK. There are mixed perceptions among implementers about the trade-offs and the Value for Money (VfM) of the benefits of using UK experience in Colombia, as local expertise is more economic. However, there is no evidence about other VfM variables to justify or deny this claim.
### Evaluation Question 7: Which assumptions and causal pathways outlined in the Theory of Change remain valid, which refinements have been made and what refinements need to be made?
No explicit assumptions were identified in the updated umbrella ToC, though activity ToCs have identified assumptions. Changes in the political context and risks of corruption were initially underestimated but are now taken into account. The assumption that UK firms would be interested in partnering in the programme has encountered hurdles such as limited contextual knowledge, language skills, cost differentials between UK and Colombian firms and the perception by UK firms that the PF budgets are low.
### Evaluation Question 8: To what extent is the institutional governance set-up of the Prosperity Fund more or less effective in achieving (i) primary benefits, (ii) secondary benefits and (iii) other results?
The lack of a formal inception phase was initially challenging for the PT as well as for the Development Bank of Latin America (CAF) and the Financial Institution for Development of the Regions (Findeter), particularly in terms of contracting arrangements, due to different ways of working, systems and processes. There was a steep learning curve in terms of relationship building and learning, although this has ultimately paid off with strong existing engagement with partners and positive working relationships. There is regular and clear communication between the PT and implementers, as well as beneficiaries, across the PF portfolio. Regular meetings are scheduled to ensure constructive engagement and a timely resolution of any emerging issues. While early agri-tech project results are promising, the PT’s relationship with Innovate UK is more challenging due to remote working, institutional set-up and a perceived departure from the original Memorandum of Understanding delivery expectations. Quarterly Reports are the main mechanism for IPs to share results with the PT, and for the PT to report to London. Quality and timeliness vary and reporting against logframe indicators is limited to date, partly due to the level of indicators. Reporting to Prospero has not started. The PT receives limited feedback on their regular reporting from the JFU in London. The various relationships are positive and constructive, however, so this is not necessarily a cause for concern.
### Evaluation Question 9: What type of programmes, approaches and governance and management arrangements have been more or less effective for achieving results and demonstrate good approaches to supporting inclusive growth and Value for Money?
VfM systems are in place across the PF, with a focus on economy and some evidence of considering effectiveness, efficiency and equity. VfM frameworks are not consistent across the programme. Rather, each implementer uses their own VfM assessment criteria, for example, when scoring bids. Understanding of the implications of contracting UK firms is focused on economy. There is an argument that UK firms may be more efficient (for example with better knowledge, skills etc) but there is no evidence to prove this. VfM is reported against in the Annual Review, not the regular quarterly reports, although the PT has agreed to introduce this following the evaluation findings workshop. CAF and Findeter were initially selected due in part to their competitive management costs, although other aspects were also considered, for example experience, networks and track record in Colombia.
### Evaluation Question 10: To what extent have the Prosperity Fund interventions contributed to results that support gender equality, women’s economic empowerment and social inclusion?
The programme sets out a clear commitment to addressing the needs and constraints of women living in poverty and providing economic opportunities for them. All the activities have objectives on G&I, particularly explicit in the agri-tech project documents. The PT has also worked actively to set G&I-related requirements for IPs and ensure these are understood. However, there seems to be a lack of G&I-related capacity in many of the partner organisations, and consequently a lack of clarity about the gender dimensions, objectives and actions of activities to address these. Each ToR includes a specific G&I deliverable, following on PF guidance and the G&I framework. All activities will have a G&I analysis based on targeted stakeholder consultations. However, there could be more clarity around the level of ambition of each of the strands and the ways in which they plan to tackle G&I considerations.
### Evaluation Question 11: How is the Prosperity Fund learning and why is action on this learning happening more or less successfully?
The Colombia PF programme’s learning processes are a mix between formal (contract management, VfM and G&I) and informal (on the job, job shadowing and mentoring), but the PT has a strong learning culture and adaptive management is encouraged. The PT promotes internal and external sharing of lessons and supports decision-making through a reflection and learning cycle, including with partners. The PT is open and responsive to learning and has previously made programme adaptations based on lessons learned. This includes the logframe and ToC revision process in April 2019, in collaboration with the Monitoring and Reporting (M&R) team and all core implementers. The PT engages in sharing lessons with other PF actors and wider stakeholders. This is particularly true across Latin America, especially with the Mexico and Brazil PF teams, for example in the context of the twice-yearly Americas Conference.
## Lessons and recommendations
An innovative and ambitious programme
The Colombia PF programme is an innovative, complex and ambitious programme within the wider context of the Fund. The Colombia PT is very capable and committed and dedicates substantial time and efforts to ensuring the programme’s technical delivery objectives are met by the IPs in country. As one of the earliest PF programmes, Colombia has a lot of lessons learned to share with similar programmes, particularly in Latin America (Mexico and Brazil) in terms of what works well and what has been challenging.
The Colombia PF Programme’s umbrella ToC and logframe reflect the PT’s ambitions and include high-level outcome and impact indicators that will be difficult to report results against until the latter years of the programme. This evaluation recommends the inclusion of intermediary indicators for partners to achieve before the next Cycle evaluation and Annual Review, as well as a supporting narrative that clearly outlines the logic behind each pathway of change and formalises assumptions.
Adaptive management
The complexity and ambitions of the Colombia PF require highly adaptive programme management, as well as close collaboration with the IPs. The Colombia PT learned a lot in the early stages of programming, working with completely new partner organisations in Colombia, with their own internal systems and processes. Positive and constructive engagement between the PT and their partners ensured that challenges were dealt with as they arose, as far as possible. One lesson from the Colombia Programme is that a six-month inception phase would have been beneficial in terms of establishing these relationships and learning how to work together before trying to launch the activities.
Inclusive change
The Colombia PF programme sets a clear commitment to addressing the needs and constraints of women living in poverty and working to provide economic opportunities for them through project design and delivery. The programme has taken substantial steps to mainstream Gender and Inclusion (G&I) issues to date and lay the groundwork to ensure all activities will be delivered inclusively. The PT has also worked actively to set clear and ambitious G&I-related requirements for implementing partners and ensure these are understood and achievable. All activities have specific objectives on G&I, to date most explicitly addressed and operationalised in the Agri-Tech projects. However, G&I-related capacity in many of the implementing partner organisations is still nascent, with ongoing questions around gender dimensions, objectives and resulting projects activities to address gender concerns. Continuous capacity building and support to implementing organisations is needed to enable plans to come to fruition.
Learning
The Colombia PT has a strong learning culture, which includes both formal and informal mechanisms to reflect on what works well and what could be improved and to capture this information for uptake and adaptive management. Relationships with the implementing partners, national counterparts (for example, regional government) and beneficiaries are positive and constructive, with a focus on regular communication, sharing learning and challenges as they emerge in order to find swift solutions. The Colombia PT’s culture of learning and sharing lessons extends to the wider PF, and particularly with relevant global programmes, as well as the other two Latin American PF programmes in Mexico and Brazil.
Monitoring, reporting, evaluation and learning
Robust monitoring, reporting, evaluation and learning systems, as well as strong communications, are important to capture and document emerging lessons and programme results. The Colombia PT has robust processes in place to track and measure change across the programme, although this report encourages further development and roll-out of high quality, user-friendly and sustainable MEL.

# Introduction
This evaluation report presents the main findings, lessons and recommendations from the PF E&L Cycle 1 independent evaluation of the Colombia Programme.
## The Colombia Prosperity Fund Programme
The PT prepared the Business Case (BC) for a programme in Colombia in 2016, with the aims of supporting economic development, unlocking economic opportunities and driving inclusive growth in post-conflict and conflict-affected regions. The £25.5 million programme is implemented by the FCO from 2018 to 2022, in partnership with the CAF, Findeter and Innovate UK (IUK)[1], as well as the Open Contracting Partnership (OCP), the Financial Institution for National Development (FDN) and the International Center for Tropical Agriculture (CIAT).
[1] IUK has been converted into a UK research council and no longer has the same mandate as when the MOU was signed.
The programme focuses on three key sectors – infrastructure, agriculture and institutional strengthening – and includes seven activities. The infrastructure strand includes activities relating to urban and rail infrastructure. Agriculture includes an activity on agri-insurance and the IUK Agri-Tech Catalyst Challenge Fund, which comprises seven grants. Finally, three activities focus on institutional strengthening, including regional competitiveness, open public procurement and corporate governance reform of the ANI. All activities have a G&I focus, with the aim to include women and other disadvantaged groups in project design and ensure they benefit from implementation.
The three Colombia PF sectors and their seven respective activities were selected by the PT for their potential to deliver primary benefits (poverty reduction as a result of inclusive growth) and SBs (expanded trade and investment opportunities). It is estimated that the programme will deliver £2 billion of primary benefits and £265 million of SBs. The Colombia PF activities are implemented in post-conflict and fragile and conflict-affected areas (FCAS) across the country. Figure 1 below illustrates the breadth and diversity of current activities.
Figure 1: Colombia Prosperity Fund activities
## Evaluation objectives and scope
The objectives of this Cycle 1 evaluation are set out in the Approach Paper[2] agreed with the Colombia PT in February 2019. The primary purpose of this evaluation is to generate learning for the Colombia PT on results (what has been or is likely to be achieved), factors that have supported/hindered success and what works well or less well in order to inform and improve ongoing and future programming, as well as cross-Fund learning. Each year, evaluation findings will be used to support and improve programming and, where necessary, to course-correct. As outlined in the Colombia Approach Paper, the objectives of the evaluation remain:
[2] Colombia Programme Approach Paper, Prosperity Fund Evaluation and Learning, February 2019, Page 4.
1. to understand and assess the programme’s design – its coherence and likelihood of success
2. to track and review the programme’s implementation and its ongoing results
3. to investigate the contexts in which the programme takes place to identify affective factors, as well as other non-PF-related factors which may be generating results observed.
Four themes of relevance frame the scope of this first annual evaluation:
1. Adaptability: assessing the programme’s adaptability and the suitability of its governance and structure to adjust to changing contexts and make timely strategic decisions, and whether the programme’s set-up is adequate to achieve its objectives.
2. Early results: focusing on the key output-level achievements and their potential contributions to the programme’s outcome-level results.
3. Evidence and assumptions: building on existing evidence and generating new evidence to support or challenge the Theory of Change’s (ToC) assumptions about the programme’s implementation contexts and its causal mechanisms for achieving desired outcomes.
4. PF alignment: assessing the likely contribution of the programme to PF thematic objectives and whether its current design is appropriate and adequate for doing so.
A strong emphasis on learning underlies these four themes. This Cycle 1 evaluation report presents findings, lessons and recommendations based on the programme’s work between November 2017 and July 2019.
A core programme independent E&L team of two, with support from a national consultant and two international thematic experts,[3] undertook this evaluation between February 2019 and August 2019 and drafted this report.
[3] See Annex 1 on Page 52 for the Programme Evaluation Team details.
The team considered the Colombia Programme’s institutional set-up, including the systems and processes in place, and identified emerging lessons learned related to the effectiveness of the set-up to drive and facilitate the programme’s objectives, as well as early results from initial project activities. The report puts forward practical recommendations for its primary audience: the Colombia PT, including the Senior Reporting Officer, Programme Manager and wider PT members; the FCO and DIT staff at the British Embassy in Bogota, and the PF Fund-level management and governance structures. The report will be made accessible to a wider secondary audience including the programmes’ implementing partners; the national, subnational and local level government officials involved in the projects; UK and international business working within the sectors addressed by the programme; other donors active in development within Colombia; and the beneficiaries of the programme, subject to the JFU’s publication policy.
## Structure of report
This section, Section 2, introduces the evaluation, including the objectives and scope set out in the Approach Paper. Section 3 on Page 10 presents contextual information relevant to the PF in Colombia. Section 4 on Page 15 provides a summary of the approach and methodology used, as well as departures from the original Approach Paper proposal. Section 5 on Page 19 analyses the most recent version of the Colombia Programme ToC. Section 6 on Page 24 presents the evaluation findings organised by Evaluation Question (EQ). Section 7 on Page 43 summarises the main findings. And finally, Section 8 on Page 45 outlines the lessons learned and Section 9 on Page 48 offers several recommendations.

# Context
This section provides a broad overview of the current Colombian context and situates the PF programme within the rapidly evolving political dynamics in Colombia.
## Overview
Colombia is the fourth largest economy in Latin America, achieving a four per cent yearly average growth for the last decade. However, Colombia remains the seventh-most unequal country in the world, where one in three households is considered poor, with poverty predominant in secondary cities and rural areas in conflict-affected regions (World Bank, 2015). The benefits of peace in Colombia are projected to increase growth by up to two per cent per year and triple foreign direct investment (FDI) from current levels within a decade (National Department of Planning (DNP), 2015), making Colombia a strong prospect for growth, including opportunities for international investment.[4]
[4] Colombia Bilateral Programme: Unlocking Economic Opportunities in Colombia’s Post-Conflict and Conflict-Affected Regions. Prosperity Fund Final Business Case, August 2018.
Colombia has had good diplomatic and economic ties with the UK for a long time. The UK was the second-biggest investor in Colombia between 2000 and 2017, accounting for US$19.7 billion or 12.1 per cent of FDI (ProColombia 2018).
It is in this context that the UK PF launched a programme in Colombia in 2017, with the aims of supporting economic development, unlocking economic opportunities and driving growth in post-conflict and conflict-affected regions. The £25.5 million programme is being implemented by the FCO from 2017 to 2022.[5]
[5] Colombia Programme Evaluation Approach Paper. Prosperity Fund Evaluation and Learning, February 2019.
On 15 May 2019, Colombia signed a trade agreement with the UK in order to preserve bilateral trade following Brexit. Both countries have expressed their interest in preserving their commercial relationships.[6]
[6] Ministry of Commerce, Industry and Tourism Press Note. 15 May 2019. http://www.tlc.gov.co/acuerdos/suscrito/reino-unido
## A new political context
The political context has changed since the UK PF launched the programme in Colombia. In August 2018 a new president was elected, which resulted in both the PT and the main IPs having to invest in building new relationships with ministers and senior government representatives to secure buy-in and support that would allow the Colombia PF investments to proceed.[7]
[7] Colombia Prosperity Fund Programme Annual Review, November 2018.
The new government’s interest in the PF Programme is enthusiastic, with several senior representatives requesting that implementation be brought forward where possible.
In addition, the new National Development Plan (NDP) for 2018-2022 remains aligned with the Colombia PF programme.[8] This NDP indicates that the government will:
[8] Colombia Prosperity Fund Programme Annual Review, November 2018.
- Prioritise national gender equality through improved investment in both infrastructure and social development. This includes an increased focus on women and rural communities, anti-corruption and reduced bureaucracy, while supporting private sector development formalisation and better public financial management.[9]
  [9] Prosperity Fund Quarterly Report October to December 2018, March 2019.
- Prioritise the reactivation and promotion of rail transport as part of the development of a national intermodal system, via the formulation and implementation of the Rail Master Plan, generating conditions that allow the railway to exploit its competitive advantage and promote its integration in the logistics and multi-model transport chains.[10]
  [10] Colombia Prosperity Fund Programme Annual Review, November 2018.
- Promote productive transformation, agricultural and agro-industrial competitiveness and rural development, creating conditions that stimulate the provision of goods and services, private investment, innovation and entrepreneurship to generate opportunities for growth and the well-being of the entire rural population.[11]
  [11] Colombia Prosperity Fund Programme Annual Review, November 2018.
- Implement strategies to guide the sustainable development of the agricultural sector, including the implementation of the Risk Information System for the Agricultural Sector (SIGRA) and risk management schemes and instruments.[12]
  [12] Colombia Prosperity Fund Programme Annual Review, November 2018.
## Gender inclusion
Over 51 per cent of the Colombian population is female. Despite women being more highly educated than men, they have higher unemployment (12.4 per cent compared to 7.4 per cent for men). Moreover, the new NDP recognised that Colombian poverty is gendered and violence against women is higher than the Latin American average (NDP, 2019).
The NDP for 2019-2022 includes a gender chapter. The PF Colombia Programme will adhere to this and help to realise its objectives.[13] It includes public policy proposals to improve gender institutions, strategies to improve labour conditions and diminish salary gaps, sexual and reproductive rights promotion, rural women population initiatives to promote rural economic growth, and specific initiatives to promote gender inclusion in conflict-affected areas.
[13] Colombia Prosperity Fund Programme Annual Review, November 2018.
## The Colombia PF programme
The Colombia PF programme is focused on three key sectors – institutional strengthening, infrastructure and agriculture – and is further divided into seven activities.
The three sectors and their respective activities were selected for their potential to deliver primary benefits (poverty reduction based on inclusive growth) and SBs to the UK (expanded trade and investment opportunities). It is estimated that the programme will deliver £2 billion of primary benefits and £265 million of SBs.[14]
[14] Colombia Programme Evaluation Approach Paper. Prosperity Fund Evaluation and Learning, February 2019.
The target departments and cities were chosen based on a study delivered by Ernst and Young, with specific criteria that included needs, institutional and financial capacity, agriculture potential, social impact and possible commercial benefits. The regions selected were Antioquia, Atlántico, Caldas, Cundinamarca, Magdalena, Meta, Santander and Valle del Cauca. The first six municipalities chosen were Cartagena, Ibagué, Manizales, Santa Marta, Valledupar and Villavicencio. However, since this selection, programme operations in both Cartagena and Villavicencio have been put on hold due to reports of electoral or financial irregularities. Until these are resolved, the programme will be concentrating on the other four municipalities.[15]
[15] Colombia Prosperity Fund Programme Annual Review, November 2018.
Programme implementation began on 1 April 2018.[16] The British ambassador in Bogotá is the programme’s Senior Responsible Officer, and delivery of the programme has been outsourced to IPs with strong track records in infrastructure, agriculture and institutional strengthening:
[16] Colombia Prosperity Fund Programme Annual Review, November 2018.
- CAF, which implements the Regional Competitiveness, ANI Reform and Agri-insurance activities;
- Findeter, which manages the Rail; Urban Development and Open Procurement activities, currently managed by OCP;
- Innovate UK, which implements the Agri-tech Catalyst Challenge Fund, with support from the International Center for Tropical Agriculture during the initial stages to recruit potential implementers; and
- FDN, which will be managing the rail activity.
In order to operate the programme and deliver the proposed outputs, the PT works with a variety of stakeholders, including national ministries and agencies, regional governors and their staff, mayor’s offices and urban secretaries, public-private entities like the regional competitiveness commissions, Colombian consultants, British firms currently located in Colombia, British firms and investors with the potential to be located there, and agriculture technology project beneficiaries. Table 1 provides an overview of the seven activities, their sector and activities to date.
In October 2019, Colombia will hold regional and municipal elections, which may affect the implementation of the Colombia PF programme (especially urban development, open procurement and competitiveness activities). The Colombia PT, Findeter and current local governments are already trying to mitigate this risk. They are working on obtaining pre-agreements on project concepts before the new local administration elections and are also trying to gain increased national government support.[17],[18] In addition to these activities, and ahead of the elections, the PT is setting up meetings with the candidates most likely to win in the cities with existing or planned projects, in order to ensure buy-in and inclusion of the projects in the next municipal and departmental development plans.
[17] Colombia Programme Evaluation Approach Paper. Prosperity Fund Evaluation and Learning, February 2019.
[18] Interviews with stakeholders during June 2019.
The current British ambassador in Colombia has played a very supportive role in the design and early implementation of the Colombia Programme. The PT is engaged and motivated to execute the programme and lead the implementation. They actively work to build and maintain relationships with the highest national and regional authorities. A new British ambassador will arrive in September 2019.
Table 1: Colombia Prosperity Fund activity overview
Sector	Activity	Specific activities receiving PF resources to date	Implementing partner
Institutional strengthening	Regional competitiveness	Update the social, financial, legal and technical studies, identifying the best management model for the Coffee Region airport – Aerocafé, Palestina, Caldas. / Sustainable and inclusive feasibility study for an Agro-logistics Centre in Atlántico. / Update the feasibility study for a sustainable and inclusive Transport Logistics Platform in Barrancabermeja (Santander). / Create a business model and sustainable production of tilapia in Magdalena.	CAF
	Open public procurement	Two subnational authorities (Caldas and Valle del Cauca) are receiving technical assistance on how to manage and publish big data and the use of platform SECOP 2 for their regional procurement processes.	OCP
	Corporate governance reform of Colombia’s National Infrastructure Agency (ANI)	Cooperation agreement between ANI and CAF ready and waiting for legal approval. / Drafting ToRs for the governance reform of ANI, with gender considerations.	CAF
Infrastructure	Urban development	Design the inclusive and sustainable intelligent public transport system in Manizales: first project to be contracted.[19] / Sustainable and inclusive water and sanitation systems in Ibagué (contract to be signed by the end of August); and Valledupar (project has to be re-tendered for the third time). / SMART City project in Santa Marta –ToRs are being designed.	Findeter
	Rail development	Feasibility study – technical, legal, financial and social structuring for Bogotá – Zipaquirá rail line (Findeter). / Feasibility study – legal, financial and social structuring for La Dorada-Chiriguaná rail line (FDN).	Findeter and FDN
[19] Colombia monthly report, May 2019.

Sector	Activity	Specific activities receiving PF resources to date	Implementing partner
Agriculture	Agri-insurance	New IT-based information system for Colombia’s agricultural sector (GEOAGRO and SIGRA) – ToRs are being designed. / Connect the national meteorological agency to the new risk system – nearly final ToRs to tender the information system’s design and implementation. / Design and implement an inclusive agri-insurance activity – UK insurance models in Colombia will be piloted in a first stage.	CAF
	Agri-Tech Catalyst Challenge Fund	Open competition resulted in seven projects between a lead UK group and a Colombian partner (businesses, non-governmental organisations and research groups).[20] All these projects are being implemented.	Innovate UK
[20] Colombia Prosperity Fund Programme. Presentation made by Martin Johnston, Director, Colombia Prosperity Fund Programme, London, 16 July 2019.

A number of other PF programmes are located in the country, including the Colombia elements of the Global Infrastructure Programme and the Global Anti-Corruption Programme. The PT was actively involved in the development of the ToC for the Global Infrastructure Programme, who visited Colombia in March 2019. In recent months, there has also been contact between the SROS for the Colombia Programme and the Centre for Disaster Protection with the aim to share knowledge related to the agri-insurance activity.

# Approach and methodology
This section presents a summary of the approach and methodology detailed in the Approach Paper.[21] It highlights the key changes the independent E&L team adopted to adapt to a dynamic operational context.
[21] Colombia Programme Approach Paper, Prosperity Fund Evaluation and Learning, February 2019.
## Questions
The PF EQs[22] framed the Colombia Programme evaluation design and methodology. Together with the PT and the wider independent E&L team, the E&L team initially prioritised 6 out of the 12 Fund-level EQs for Cycle 1. EQs 4 and 6 were later added to the Cycle 1 sample, following requests from the E&L Secondary Benefits lead. Following this selection, the E&L team specified sub-questions for each of the EQs to ensure their relevance to the Colombia PF and the primary audience’s needs. Table 2 outlines the full set of 12 EQs for the PF with the first year EQs for the Colombia evaluation highlighted in bold.
[22] Prosperity Fund Evaluation and Learning Inception Report, May 2018.
The Colombia Programme EQs link to the family- and Fund-level EQs. Evidence collected and analysed through the programme evaluation will feed the family, thematic and Fund evaluations.
As with all elements of the PF, this evaluation aligns to the International Development Act 2002, the International Development (Gender Equality) Act 2014, the Organisation for Economic Co-operation and Development (OECD) Development Assistance Committee criteria, and the UK government transparency commitments on Official Development Assistance (ODA) expenditure.
Table 2: Prosperity Fund-level Evaluation Questions relevant to Cycle 1
Evaluation questions
Cycle 1 evaluation priority EQs
What evidence is there that the PF is likely to contribute to the intended outputs and outcomes in the ToC, as well as any unintended or unexpected effects? (EQ 1)
What evidence is there that the changes supported by the PF will be sustainable (environmental sustainability, self-financing, inclusive growth that reduces inequality)? (EQ 4)
How has the balance and relationship between primary and secondary benefits across the portfolio influenced the achievement of results? (EQ 6)
Which assumptions and causal pathways outlined in the ToC remain valid, which have been adapted and what refinements need to be made? (EQ 7)
To what extent is the institutional governance set-up of the PF more or less effective in achieving i) primary benefits, ii) secondary benefits, iii) other results? (EQ 8)
What type of programmes, approaches and governance and management arrangements have been more or less effective for achieving results and demonstrate good approaches to supporting inclusive growth and VfM? (EQ 9)
To what extent have the PF interventions contributed to results that support gender equality, women’s economic empowerment and social inclusion? (EQ 10)
How is the PF learning and why is action on this learning happening more or less successfully? (EQ 11)
Other EQs identified in the Approach Paper that will be addressed in next evaluation cycles
Which types of interventions, sectors and country settings have been more or less successful in contributing to the achievement of primary benefits?
Which types of interventions, sectors and country settings have been more or less successful in contributing to the achievement of secondary benefits?
What factors have contributed to the achievement of primary and secondary benefits?
Which PF lessons in translating outputs into intermediate outcomes are sufficiently robust for wider learning?

## Methodology
The Colombia Evaluation Approach Paper proposed the application of theory-based methodologies to answer the EQs, aligned to the other levels of the evaluation (family, thematic and Fund). The Fund-level evaluation will use contribution analysis as its primary methodology, building a contribution story for observable outcomes during the evaluation’s implementation period. This evaluation examines the programme’s contributions, instead of attribution, given the implementation status of the Colombia Programme, the dynamic implementation context, and multiple contributing factors to outcomes and impacts, which make attribution impossible. In line with the objectives and themes identified in the Approach Paper, the focus of this evaluation cycle is on assessing progress made to date by the Colombia PF, early indications of change and the identification of lessons learned and recommendations.
## Theory-based design
The Colombia PF evaluation is theory-based. Given the early-stages implementation for most activities across the portfolio, including the umbrella-level ToC,[23] the E&L team focused in this first evaluation cycle on inputs and activities that have taken place. Subsequent evaluations will move from inputs and activities to outputs and outcomes. Since the approval of the Approach Paper, the Colombia PF ToC has undergone a revision, facilitated by the Monitoring and Reporting Hub (PA Consulting), in which the E&L team participated. Section 5 on Page 19 discusses these changes further and updates the Colombia PF evaluability assessment, originally undertaken in the Approach Paper.
[23] The Colombia PF umbrella-level ToC is based on the umbrella logframe and illustrates change at the country programme level. Thematic ToCs for each thematic area feed into this, as do the individual project logframes.
## Data collection sources and methods/tools
The evaluation approach originally proposed a mixed-method approach to data collection, using both qualitative and quantitative data and a mix of primary and secondary data, allowing for triangulation of findings in our analysis. For this first cycle, there was limited quantitative data and we relied largely on qualitative information generated through KIIs and reviewing secondary sources.[24] The E&L team reviewed all background documents relevant to this evaluation, shared by the PT and partners.
[24] The Colombia PT has not yet begun to report its results on Prospero. Limited logframe reporting is included in the partners’ quarterly reports to the PT.
To validate and corroborate findings, data was triangulated between and within data sources: between KIIs with various stakeholder categories, and between KIIs and secondary sources such as programme documents. While triangulation was limited by the sample of available background documents and interviews conducted, the team was rigorous in challenging findings during the data analysis and report drafting stages, following up with various stakeholders as required to request clarifications where needed.
The independent E&L team consulted the PT during the design of the Approach Paper and throughout the Cycle 1 evaluation, specifically in the following areas: (a) prioritisation of the EQs; (b) identification of key informants; (c) actual interviews; (d) validation of results; and (e) joint formulation of lessons and recommendations. This continued engagement allowed the independent E&L team to ensure relevance of its work to the PT stakeholders’ needs and strengthen collaboration with the primary users of this Cycle 1 report.
The preferred E&L methodology of contribution analysis was not feasible in the first cycle of this evaluation, as the team lacked the necessary programme data and a robust ToC to test contributions against. This is related for the most part to the programme’s early stages of implementation, as only a few activities had started during the evaluation cycle. The PT were not yet reporting against logframe indicators and using Prospero, although progress has been made since then, working closely with the M&E Hub. There is a risk that contribution analysis will remain a challenging methodology in the next cycle evaluation as the Colombia programme indicators are high-level and there may still not be sufficient data available. This is further explored in Section 6, in particular under EQ7.
## Ethical considerations
Recognising that the sample of respondents is small but representative, we have ensured that views are not directly attributable to individuals and have considered the appropriate weighting of different perspectives, according to relevance of the informants, consistency of messages and other criteria outlined in the “strength of evidence” table in Section 6 on Page 24 of this report. We also ensured explicit consent from all respondents prior to interviews. We always clearly outlined the evaluation aims and rationale before conducting KIIs and clarified how statements would be used. The evaluation adhered to consortium values, including a code of ethics that aligns with the UK Evaluation Society guidelines for good practice. The evaluation was undertaken without interference to ensure independence, although we followed a highly participatory approach during the consultation processes, in consultation with the PT and implementing partners.
## Sampling
The Cycle 1 Colombia Programme evaluation employed a purposive sampling approach that provides insights into the variety of implemented activities and the wide range of stakeholders involved. We used a set of selection criteria to initially select sampled activities under each of the three sectors and discussed this with the PT to finally agree on a sample. The criteria included selecting: (i) at least one activity per sector, (ii) a mix of activities perceived as successful and unsuccessful, (iii) activities with the potential for learning lessons, (iv) activities of strategic importance to FCO, (vi) activities and countries that are at a relatively advanced stage of implementation with supporting documentation to ensure evaluability, and (vii) activities relevant to other family and thematic evaluations’ sampling.
The independent E&L team undertook in-person and phone interviews with 40 respondents, including stakeholders in four cities in Colombia (Bogotá, Manizales, Pereira and Montería), from early June to late July. Informants predominantly consisted of PT representatives, partner focal points, beneficiaries and other representatives from across the UK government. This purposive sampling was necessary due to the Cycle 1 evaluation’s focus on learning, requiring internal perspectives to generate lessons learned on setting up the Colombia PF and develop a baseline for subsequent annual evaluations.
## Limitations
. We identified a few additional limitations, to the ones identified in the Approach Paper, related to the generalisability of findings from our evaluation sample, the application of a theory-based approach at this early stage of programme implementation, and the strength of evidence. The Cycle 1 evaluation of the Colombia PF programme faced a number of limitations, including:
- the early stage of implementation of the seven PF activities;
- the lack of early output monitoring data;
- a resulting inability to use contribution analysis as a methodology;
- a nascent umbrella ToC that is not yet widely used by the PT and implementers, and a lack of supporting narrative, assumptions and problem statements, which meant it was too early in the programme implementation to apply a full theory-based evaluation approach;
- a purposive sampling approach, dictated by the few activities that have already started implementation, accessibility and the PT’s support in facilitating interviews with stakeholders;
- limited background documentation beyond programme design documents such as the business case, annual and quarterly reports, MoUs, and a few more recent examples of ToRs and other partner documents;
- generalising findings based on limited data.
## Approach to ensuring the usefulness of this evaluation
The independent E&L team worked closely with the PT from the outset to ensure that this evaluation will be useful and practical for the primary audience and users. The selection and prioritisation of EQs and specification of sub-EQs was undertaken jointly with the PT to identify the most important learning areas for them at this stage of implementation. A workshop for lessons and recommendations was also held to ensure early buy-in and, consequently, uptake. The PT was also given the opportunity to provide feedback on an early version of the report. The E&L team discussed the findings of this evaluation with CAF and Findeter in a workshop in Bogotá, and in a phone interview with Innovate UK.
The findings of the evaluation and key learning points will inform the ongoing oversight and management of the programme and the decision-making process through reflection meetings where changes in programme design are discussed with the programme managers.
The timing of this evaluation was adjusted to align with that of the Colombia Programme Annual Review cycle, which takes place in November each year. Finalising this evaluation by early October will ensure that this report feeds into the Annual Review.
# Theory of Change
Our analysis below and in EQs 1 and 7 focuses on the Colombia Programme umbrella ToC and this section discusses two aspects: the extent to which the Colombia Programme ToC is aligned with the ToC for the entire Prosperity Fund, as well as its internal consistency. This section is an update to the original ToC evaluability assessment, included in an annex to the evaluation Approach Paper. This section includes our assessment of the Programme ToC rationale, while Section 6 (EQ1 and EQ7) further details the intended contribution towards programme outputs and outcomes, as well as the ToC pathways and assumptions.
## The Colombia Programme umbrella Theory of Change development
The Colombia Programme chose to present a lean ‘umbrella’ or programme-level ToC to map their pathways of change from output to impact level, revised from an initial version of the ToC included in the business case. The latest umbrella ToC represented below in Figure 2 is based on the umbrella logframe for the Colombia PF, which has undergone several iterations. The resulting ToC diagram was initially shared by the M&R team during a workshop in Bogotá in early April 2019 and discussed among the PT and IPs. The figure below is the outcome of this effort and will likely be revised again, in parallel to the umbrella logframe, before it is finalised.
Figure 2: Colombia Prosperity Fund umbrella Theory of Change

While the independent E&L team is closely involved in discussions and revisions to the Colombia PF ToC and logframes, this process is led by the M&R team. The M&R team has worked closely with the PT and IPs since the very early programme phase to design the umbrella and seven activity logframes. Following this, they have facilitated three rounds of revisions and are ultimately responsible for ensuring the tools are updated and fit for purpose. The E&L team supports this process in an advisory role but is not directly involved in revisions to the ToCs or logframes. For the purpose of this evaluation, and following wider E&L guidelines, our analysis is focused on the programme-level (umbrella) ToC, as dictated by our approach and methodology.
## Assessment of the internal Theory of Change consistency
A pilot evaluability assessment of the Colombia Programme was conducted in December 2017, based primarily on a review of programme documentation, and shared with the PT in February 2018. During a trip to Bogotá in February 2018, the E&L team issued some corrections and clarifications[25] to the evaluability assessment.
[25] The main clarification pertained to the initial evaluability assessment’s conclusion that “the causal pathways leading to growth being sustainable and being inclusive (i.e. benefitting poor people in Colombia) are not yet clear.” The Colombia PT asked what type of information the evaluators would expect to see to demonstrate such causal pathways and the evaluators gave the following clarification: clearer evidence of targeting within programme activities, identification of assumptions and risks, particularly to identify barriers to sustainability and inclusion and to identify enablers – in other words the people the programme needs to persuade to ensure sustainability and inclusion.
The current umbrella ToC mirrors the programme umbrella logframe and identifies expected results at output, outcome and impact levels. It includes the Colombia Programme’s seven activities and demonstrates how they are working towards common goals. It aims to identify synergies across the seven activities and also to aggregate results. Compared to the seven individual activity logframes, the umbrella logframe only articulates the most important outputs and outcomes from the seven activities, rather than presenting everything the partners are delivering, particularly for discrete ‘stand-alone’ outputs. Outputs included in the umbrella will be used for reporting purposes in the upcoming 2019 Annual Review, which highlights the importance of capturing all key programme outputs.
The overall Colombia Programme outputs and outcomes and the impact of the programme are explicitly identified in the BC and other programme documentation for the purpose of the logframe.[26] Expected secondary benefits are also defined clearly. They comprise procurement opportunities outside of PF funding for international and UK firms and improvements to the business environment in Colombia. The business case also identifies the primary benefits expected from the three strands. They comprise respectively increased agricultural productivity and better service provision, as well as economic development in second-tier cities and improved and more affordable transport links. The primary benefits of the institutional strengthening strand focus on improving competition within eight regions, reducing the risk of corruption within the ANI, and increasing access to public procurement by international business. The activities complement (and therefore arguably contribute to the achievement of) the infrastructure activities.
[26] According to the business case, at the impact level, the seven proposed activities will contribute to increased FDI and gross domestic product in selected regions. The expected outcomes include an increase in land used productively in agriculture, more economic development projects executed, and an increase in the value of international investment dedicated to such projects. In summary, these include increased poverty reduction investments in urban infrastructure, rail, agricultural innovation and technology, and institutional capacity building.
One identified shortcoming of the Colombia PF umbrella ToC is that it is currently a simple visual diagram. No narrative was produced to accompany it, outlining pathways of change, problem statements and assumptions beyond the programme’s control and related mitigation measures. The E&L team discussed this with the PT during the validation of findings workshop.
The ToC is a tool that can evolve and change over time as the activity needs to adapt to the context and as new assumptions emerge. It is generally considered more flexible and fluid than the umbrella or activity logframes, which are used to identify and inform indicators to monitor progress and are therefore static. The absence of a ToC narrative can be problematic because pathways of change may be more or less explicit and shared by all the partners, and open to wider interpretation. Assuming a shared understanding across a large programme with different IPs and many activities is potentially risky, particularly where the shared understanding has not been made explicit. On the other hand, reframing the logframe is more complicated and poses problems for monitoring activities and evaluation exercises in the long term. If some indicators are reformulated over the course of the programme, as has been suggested during some interviews as a possibility, this would compromise the opportunity of monitoring indicators over time, and the ability to undertake contribution analysis as the baseline for new indicators would not match the baseline data. However, contextual change is inevitable, and the PT is aiming to work in a flexible and adaptive manner.
## Programme Team and partners’ assessment of the Theory of Change
Interviews show that partners are aware of the umbrella logframe and related ToC and understand its pathways and assumptions. They define their activities in line with their individual (seven) activity logframes and do not use the umbrella ToC as a management tool in their day-to-day work. Partners’ and the PT’s perception of the umbrella ToC pathways and its validity are further explored in the findings sections on EQs 1 and 7 below.
Both primary and secondary benefits are visible throughout the various levels, which helps project partners understand, design and implement activities that aim to deliver these PF objectives. The programme is implemented through seven different activities, each of which has its own ToC, although day to day they use logframes to track activities and measure results rather than the ToCs.
## Alignment with the Prosperity Fund’s Theory of Change
Overall, the programme’s objectives are aligned with the Fund-level ToC. All the activities selected address issues that hinder development and growth in Colombia and relate to outcomes in the areas of rail rehabilitation, agri-insurance, improved governance, urban infrastructure development and a focus on regional competitiveness, which should contribute to growth. The programme’s three stated impacts below are all aligned with the PF’s goal of contributing to inclusive growth, not only economic growth:
- “sustainable inclusive rural and urban growth in target departments and municipalities”
- “sustainable inclusive investment into target departments and municipalities and sectors”
- “sustainable inclusive trade to and from target departments and municipalities and sectors”.
The choice of pathways to achieve the impact within the programme is also consistent with those promoted by the PF. They focus on infrastructure development, human capital and innovative technology development and ease of doing business (all reflected in the PF intermediate outcomes).
## Conclusions
The Colombia Programme’s ToC, though lean, is sufficiently clear and logical to enable programme partners to align their interventions to the programme: primary and secondary benefits are identified and the causal pathways between most are identified and plausible, although some would need further clarification as part of a ToC narrative.
The programme is well aligned to the wider PF, making it relevant for evaluation. Indeed, some potential areas of focus for different PF evaluations are covered in this report, for example G&I.
One concern for future evaluations is the availability of programme data, considering the high-level indicators in the programme and activity logframes. The E&L team is concerned that it will be challenging to demonstrate enough results in time for the Cycle 2 evaluation, as well as the upcoming Annual Review. Related to this, the PT has yet to finalise its logframes and start uploading monitoring data to Prospero, which would also feed into future assessments. This revision process should be completed ahead of the upcoming Annual Review in November 2019. The PT are interested in exploring the feasibility of linking logframe indicators to the Sustainable Development Goals (SDGs), in collaboration with the M&R Hub and E&L team.
The PT and IPs show a positive attitude towards this evaluation and the opportunities that it provides for learning and adaptive management.
Given these findings, it can be concluded that the Colombia Programme is highly evaluable, although the most appropriate approach and methodology may need to be adapted by the E&L team if contribution analysis is not feasible.

# Evaluation findings
Using the PF Strength of Data assessment tool, we have reviewed each EQ against five criteria: validity, reliability, completeness, precision and bias. For each criterion, we have attributed a score of 1 to 5 – 1 being ‘weak’ and 5 being ‘strong’ – and aggregated these scores for each EQ to derive an overall data quality score.
Table 3: Strength of Data Assessment by Evaluation Question
Evaluation Questions	Data quality score*
EQ1: What evidence is there that the Prosperity Fund is likely to contribute to the intended outputs and outcomes in the Theory of Change, as well as any unintended or unexpected effects?	12
EQ4: What evidence is there that the changes supported by the Prosperity Fund interventions will be sustainable and ensure environmental sustainability, will be self-financing and lead to inclusive growth that reduces inequality?	12
EQ6: How has the balance and relationship between primary and secondary benefits across the portfolio influenced the achievement of results?	15
EQ7: Which assumptions and causal pathways outlined in the ToC remain valid, which have been adapted and what refinements need to be made?	12
EQ8: To what extent is the institutional governance set-up of the Prosperity Fund more or less effective in achieving i) primary benefits, ii) secondary benefits, iii) other results?	15
EQ9: What type of programmes, approaches and governance and management arrangements have been more or less effective for achieving results and demonstrate good approaches to supporting inclusive growth and Value for Money?	15
EQ10: To what extent have the Prosperity Fund interventions contributed to results that support gender equality, women’s economic empowerment and social inclusion?	13
EQ11: How is the Prosperity Fund learning and why is action on this learning happening more or less successfully?	21
*The maximum data quality score for each EQ is 25 (up to 5 points can be allocated to each of the 5 criteria)

The following section outlines our findings against each of the selected EQs. These are summarised above in Table 3. Our stakeholder interview questionnaire, stems from the sub-EQs derived from the 12 high-level PF EQs.
In general, EQs related to the ToC such as EQs 1 and 7 scored lower in the strength of data assessment. This is because there was little evidence for the E&L team to consider on measuring and assessing results at this early stage of the implementation. We relied heavily on the accounts of the PT and partners who have been involved in the set-up and early implementation of the programme. EQ8, which focuses on management arrangements and processes, for example, relied heavily on KII accounts and experiences to generate lessons learned from the set-up of the Colombia PF.
The independent E&L team considers the level of data, evidence and findings generated from the Cycle 1 evaluation sufficient to draw the learnings and recommendations presented in Sections 8 and 9. It is likely that in subsequent annual evaluations, the strength of data assessment will improve, given that there will be more evidence to draw on.
## Evaluation Question 1
What evidence is there that the Prosperity Fund is likely to contribute to the intended outputs and outcomes in the ToC, as well as any unintended or unexpected effects?
This section examines the underlying logic of the Colombia PF programme umbrella ToC. It includes an assessment of pathways, assumptions and early activity results where these exist, and aims to provide an appraisal of the programme’s likely contribution to its intended results. This section also reviews the Colombia Programme ToC’s coherence with the higher-level Fund ToC, and the internal coherence between the umbrella ToC and seven activity ToCs.
Box 1: Evaluation Question 1 – main findings and conclusions
- Flexible and proactive management arrangements in place to steer and redirect activities in response to evolving context.
- It is too early to assess the likely contribution of the programme to intended outputs and outcomes in the ToC, as well as any unintended consequences, but there are indications that several activities are delivering on outputs.
- Primary and secondary benefits are central to the umbrella ToC, thus increasing the chance for the programme to deliver inclusive growth.
- The coherence between the Programme ToC and the PF ToC and the internal coherence between the Programme ToC and the activities’ objectives also increase the chance of positive outcomes.

All partners, as well as the PT, have a good understanding of PF objectives and the ToC, mapping out their activities from output to impact levels. This holds true for all PF stakeholders consulted, including project beneficiaries. The PT is composed of qualified technical advisers and managers, who understand the PF and Colombia Programme well and travel to the field regularly, working closely with IPs and beneficiaries.
It is too early to assess the programme’s likely contribution towards outcomes and impact, mainly due to the early implementation status of all activities apart from the agri-tech pilots and some delays in procurement.
However, there are encouraging outputs at project level. The palette of activities undertaken so far is coherent with the expected outputs as presented in the umbrella ToC and in the logframe, and there is evidence of the Colombia Programme’s focus on G&I considerations.[27] For example:
[27] The Colombia Programme has four outputs: 1. Increased technical capacity of producers and providers* in agricultural insurance and agricultural technology products and services, especially female and male smallholders and small companies (including cooperatives, associations and micro, small and medium enterprises. 2. UK-led innovations aimed at inclusive, sustainable development piloted and tested in agri-tech, agri-insurance, urban and regional competitiveness. 3. Increased capacity of public officials to design and structure inclusive and sustainable urban, rail, regional competitiveness and agri-insurance investments. 4. The fourth output is subdivided as shown below: 1. Urban, rail and regional competitiveness projects are designed, structured and ready for investment in an inclusive and sustainable way 2. All PF activities lead to public procurement that allows international business to participate and deliver 3. Implemented urban, rail and regional competitiveness projects are inclusive and sustainable.
Institutional strengthening
- Regional competitiveness: four inclusive competitiveness projects have been identified. ToRs are ongoing for Aerocafé, the Atlántico Agri-Logistics Hub, the Barrancabermeja Transport Logistics Hub and the Magdalena Tilapia Value Chain Project. All of them, including the social, financial and technical studies for Aerocafé have been strengthened from a G&I perspective (see Section 6.7).
- Open procurement: the first training sessions were delivered in Caldas and Valle del Cauca for civil servants on how to manage and publish big data and the use of platform SECOP 2 for regional procurement processes. Capacity development is an important aspect of the programme and in this case contributes to Output 3.
- Corporate governance reform of ANI: while the cooperation agreement between ANI and CAF is ready and waiting for legal approval, CAF is drafting TORs for ANI’s governance reform which include gender considerations.
Infrastructure
Under the urban development activity, feasibility studies were tendered for the intelligent public transport system in Manizales. The study has been awarded and the project is under way. Two water and sanitation systems have been tendered for Ibagué and Valledupar. Ibagué’s is soon to be awarded. The Valledupar water and sanitation tender was twice declared void and will be re-tendered for a wider set of companies outside of the PF Commercial Framework.[28] Santa Marta’s projects for SMART City and water and sanitation will be tendered between September and December 2019. Two rail feasibility studies have been identified: Bogotá-Zipaquirá with co-financing from the Cundinamarca department for £1.5 million and La Dorada-Chiriguaná, MOU signed on 22 August 2019. These two activities in urban development and rail rehabilitation will contribute towards achieving Outputs 2 and 4.
[28] The project was procured twice through the Commercial Framework. The PT now has an agreement to change the ToRs in two areas. First, 10 points out of 100 will be given to project proposals that include bringing innovation and new technologies to Colombia for the first time. Another 10 points will be given to proposals that include external expertise, in other words experts from outside Colombia. The PT believes these two additions will encourage Colombian companies to form consortia with external partners. At the same time, the PT is contacting UK water and sanitation companies not in the Commercial Framework to make them aware of this opportunity and to encourage the creation of consortia with Colombian companies.
Agriculture
- Agri-tech activities have also started. There are now seven agri-tech projects being jointly implemented between UK and Colombian partners that promote innovative technologies and support female smallholder farmers. These activities contribute towards Outputs 1 and 4.
- Progress is being made in developing an IT risk-based information system that will underpin the agri-insurance market and offer a number of opportunities, such as the development of a digital dashboard for Geoagro, a new agricultural weather forecasting system for the meteorological bureau, or the development of SIGRA, a full agri-risk information platform. These will contribute to Output 2.
## Evaluation Question 4
What evidence is there that the changes supported by the Prosperity Fund interventions will be sustainable and ensure environmental sustainability, will be self-financing and will lead to inclusive growth that reduces inequality?
Box 2: Evaluation Question 4 – main findings and conclusions
- The Colombia Programme aims to ensure sustainability by choosing to work in sectors that are aligned with national and subnational plans.
- The ToRs for PF-funded projects include conditions on G&I, and financial and environmental sustainability.
- The Colombia Programme will be the first programme to develop an outline for a climate and environmental strategy that will inform all PF and CSSF programmes.
There is evidence that the Colombia Programme is committed to a sustainable agenda. For example, it aims to ensure sustainability by aligning with national and subnational development plans. The specific sectors and projects chosen to be funded correspond with national and regional agendas (see Section 3 on Page 10 on the context). This was confirmed by the PT, who highlighted that this alignment ensures the commitment of public resources to future execution of feasibility studies and ToRs and the continuity of projects beyond a changing political context, as sectors and projects are part of government plans and budgets.
The PT supports regions to design sustainable projects. According to the PT, during the past year, the programme has offered training to subnational authorities, the private sector, civil society and academia to propose and design sustainable projects. As part of this, a G&I toolkit for mayors and governors is being developed and will be shared in November 2019 with 150 newly elected mayors and governors who will also be trained on project management and strategic design by the Universidad del Rosario.
The PT is supporting the national government in the implementation of the Public-Private Partnerships (PPP) law. According to NDP[29] Colombia ranks second for its ability to develop PPPs since the introduction of Law 1508 in 2012. The government has identified investment needs in transport, energy, telecommunications, housing and water and sanitation, among other infrastructure sectors. For example, PT is helping to design complementary regulations to facilitate the PPP law application in infrastructure projects, whether funded or not by the PF.
[29] Challenges towards a more competitive country. National Planning Department, June 2019.
In addition to choosing areas of work in line with government priorities, the PT and IPs include conditions in the ToRs for G&I and financial and environmental sustainability. For example, the ToRs ask projects to include social impact assessments that request stakeholder consultations with vulnerable groups during project design in order to inform the implementation. Financial studies are asked to provide recommendations on the best financial mechanisms and project management to ensure that projects are structured to be financially sustainable.
ToRs request projects to be in line with relevant environmental regulations. This request is particularly relevant for infrastructure projects. The PT will work with an environmental expert, funded by JFU, to assess and establish the baseline on climate change and the environment for each project and to identify strategies to align closer to international best practices.
The PT is also leading work to inform other PF programmes on climate and environment strategies. It will soon develop an outline climate and environment strategy with a light-touch baseline to inform the PF programme. The director of the JFU visited the PF and the Conflict, Stability and Security Fund (CSSF) in Colombia in January 2019. She recommended that both programmes do more to link up with the UK government’s wider climate and environment work. The UK has prioritised the integration of environmental protection and climate change mitigation and adaptation throughout all its policies and programmes as appropriate. The PT prepared the ToRs for an expert to come to Colombia and conduct an outline climate and environment strategy with a light-touch baseline for both the PF and CSSF. A visit from a senior policy adviser from Cross-Whitehall Funds in the UK’s National Security Secretariat will be conducted from 2 to 6 September 2019 to develop this work, which will form the basis for PF and CSSF action plans to improve climate and environmental impacts. The Colombia Programme is the first programme to carry out this work, which will also produce guidelines for all PF and CSSF programmes on how to conduct a climate and environment audit and produce strategies and action plans.
## Evaluation Question 6
### How has the balance and relationship between primary and secondary benefits across the portfolio influenced the achievement of results?
Box 3: Evaluation Question 6 – main findings and conclusions
- There is common understanding between the PT and IPs of intended primary and secondary beneficiaries.
- The Colombia Programme considered SBs in the programme design. When choosing which sectors to work on, the team chose sectors where the UK has comparative advantages.
- The promotion of SBs is led by the PF’s commercial adviser who works closely with DIT and the JFU in London in promoting the PF in the UK.
- There are mixed perceptions among implementers about the trade-offs and VfM of the benefits of using UK experience in Colombia. Local expertise is more economic, but there is no evidence on the effectiveness, efficiency and equity to compare both.
This EQ focuses on establishing clarity in the definitions of primary and secondary benefits and beneficiaries within the context of the Colombia PF programme to gain a better understanding of who it is working with and delivering for. We then explore the relationship between primary and secondary benefits, and whether there is any evidence around whether they are compatible or not in the context of the Colombia Programme.
There is some evidence that the PT and the IPs have a consistent and clear idea of the Colombia Programme’s beneficiaries. According to the BC, the Colombia Programme’s ambition is to achieve the primary objectives of inclusive growth, poverty reduction and gender equality. At this stage, the programme mainly engages indirectly with primary beneficiaries through its IPs. Recently, they have also started to engage directly. For example, the gender expert contracted by the PT visited all agri-tech projects to provide advice on their G&I Action Plans.[30]
[30] Colombia Monthly Report. May, 2019.
The Colombia Programme is clear that the primary focus of the programme is poverty reduction, which the IPs confirmed. For instance, small landowners are the primary beneficiaries of agri-tech and agri-insurance projects, and regional governments are the primary beneficiaries of the open procurement projects. Competitiveness projects have their individual primary beneficiaries (for example, women working in the Aerocafé project). The water and sanitation projects target the poorest areas of the cities in which they work. The social impact analysis that is done for each project will identify specific primary beneficiaries.
Secondary benefits are at the core of the programme since the development of the BC. The programme (as outlined in the BC) targets key sectors where UK companies have an established track record in Colombia (infrastructure and capacity building) or where the opening of new markets would attract UK companies (agri-tech and insurance). The BC estimated that the potential direct secondary benefit to the UK could be up to £265 million over 10 years. SBs are not explicitly mentioned in the umbrella ToC, but they are in the logframe.
The Colombia Programme expects that the involvement of PF Commercial Framework firms in earlier phases of project is designed following international standards. This would support international firms to compete in future stages for non-PF funding when the government releases the tenders. PF projects are tendered via CAF, Findeter and FDN for PF Commercial Framework companies[31] and aim to create opportunities for future business. The Colombia Programme is funding the design and development of pre-feasibility and feasibility studies (in infrastructure) and feasibility studies (in agri-tech) (see Section 3 on Page 10).
[31] The PF Commercial Framework is legally compliant with UK and EU procurement directives. It has two lots, enabling environment and specialist sectors. The Framework is used to procure PF programmes. Bidders are only able to bid for a requirement if it is for a lot that they have successfully being placed in.
The Colombia Programme has already brought new UK firms to work in Colombia. Foreign firms that are part of the Commercial Framework can partner with local and foreign firms to bid for PF projects. In the case of agri-tech, tendered via IUK, seven UK firms that had not previously worked in Colombia are implementing PF projects in partnership with local firms and non-governmental organisations. The agri-tech funding is for market feasibility studies that allow the exploration and development of new markets. Due to IUK norms, these projects require co-funding from the firms. It is of interest to the firms to use this opportunity to generate network effects and establish longer-term new business opportunities in Colombia, which would generate SBs in future phases of the business (exports, FDI and/or ODI).
The Colombia Programme has been proactive in establishing strong links with the private sector through several activities including the Colombia roadshows held in Manchester and Birmingham (February 2019) and London, Leeds and Edinburgh (June 2019) which aimed to promote PF opportunities to UK firms, early market engagements in Colombia and the UK, exhibition fairs, promotional activities at renowned Colombian sectorial events and conferences on specialised topics to show UK expertise.
These activities have been led by a commercial adviser, funded with non-ODA funds, who works closely with DIT on promoting both UK firms in Colombia and PF opportunities in Colombia to UK firms. The experience of the PT and DIT working together was viewed as a positive experience leading to good learnings by both parties. The PT proactively seeks the advice from the JFU in London in relation to SBs.
The Colombia Programme produced a cost-benefit analysis (CBA) of SBs for the fiscal year 2018-19.[32] The report documents SB-related activities, costs and outputs and describes how the overall non-ODA allocation has supported the promotion and preliminary achievements of SBs via the PF in Colombia. The CBA was developed to inform the strategy for the non-ODA allocation budget for 2019-20, which is worth £154,950. Based on the CBA, the PT recommended increasing non-ODA resources to deliver activities in the UK to raise awareness among UK companies of opportunities generated by the Colombia PF and increase the non-ODA budget for early market engagements in the UK and Colombia.
[32] Non-ODA Cost Benefit Analysis Report FY 2018/19. Colombia Prosperity Fund Programme.
The PT considers the alignment and balance between primary and secondary benefits when designing activities, and the evaluation of different proposals also considers the balance between these two activities. For example, some proposals to develop projects in Chocó were not considered by the PT in spite of their primary benefits because the difficulties of developing projects in this region could report minimal or no SBs.[33]
[33] Chocó is one of the poorest regions in Colombia (Pobreza monetaria y multidimensional en Colombia. DANE, 2018) and its levels of corruption are one of the highest in the country (Transparencia por Colombia, 2016).
It is early to assess the trade-offs and VfM of the benefits of using UK experience in Colombia. The PT and IPs agree that the Colombia Programme is creating opportunities for Commercial Framework firms in Colombia. But there is no agreement as to whether this is good VfM. According to IPs, there are similar projects successfully implemented by national or regional firms or consortia at lower costs. This finding is countered by the PT, which has received feedback from the local governments that their experience of working with local and regional firms is not always positive.
## Evaluation Question 7
Which assumptions and causal pathways outlined in the ToC remained valid, which refinements have been made and what refinements need to be made?
Box 4: Evaluation Question 7 – main findings and conclusions
- No explicit assumptions were identified in the updated umbrella ToC, though projects' ToCs have identified assumptions.
- Changes in the political context and risks of corruption were initially underestimated but are now taken into account.
- The assumption that UK firms would be interested in partnering in the programme have encountered hurdles such as limited contextual knowledge, language skills, cost differentials between UK and Colombian firms and the perception by UK firms that the PF budgets are low.

There are no explicit assumptions documented in the umbrella programme ToC. However, there is clarity among the PT that there are assumptions under which they are working. During a workshop led by the E&L team in June 2019, the following list was identified:
- The changes in the political context, with potential changes in local and regional governments, could influence implementation especially during the gap between the election results and the start of the new government. For example, the ANI project which had been pushed forward by CAF in 2018 was delayed by six months due to waiting for the new director to be appointed by the president. The PTs and their partners are now more aware of these risks and are actively engaging with local politicians to position the PF favourably and increase its visibility.
- The risks posed by corruption were not accounted for fully at the time of design, but these have since been considered more explicitly. Alleged cases of corruption delayed project implementation but the PT is actively monitoring the situation and seeking opportunities to work around this.
- One of the assumptions is that UK firms would be attracted by opportunities in Colombia. However, UK firms encounter hurdles:
  - There are perceptions by some firms in the PF Commercial Framework that PF budgets are low and inflexible and procurement procedures are laborious, which might reduce interest by UK firms. The PT spent over six months working with partners and companies to address these concerns.
  - UK firms tend to lack the appetite to work in Colombia, based on long-standing but out-of-date perceptions of the political and security climate. They also often lack Spanish language skills, which make it difficult at times to fulfil bid requirements. One of the embassy respondents indicated that attendance at commercial events had initially been lower than expected, although this is not unusual with Latin American events. The recruitment of the commercial adviser within the PT provided a welcome a boost in interest.
  - The cost differential between Colombian and UK firms remains an issue. One respondent explained that local firms cost on average three times less than British ones. UK companies are trying to mix international and national consultants, as well as partnering with Colombian firms. They also sometimes propose a reduced scope of work for the same price, which is problematic.
All the signs are that the PT and their partners are actively addressing procurement and contracting issues. One-to-one meetings took place with companies to hear their concerns, and some of these were taken into account by CAF and Findeter and amendments made in the ToRs. New procedures were also considered before opening a call: i) a market survey to test price tags, ii) a pre-hearing before ToRs are published, iii) all concerns raised are analysed and considered for action.
One concern consistently raised by participants in group discussions and interviews is that the programme is very ambitious and that the duration of the projects is too short to achieve the expected outcomes. This issue has two aspects: one is the level of ambition itself, although within the PF team this is intentional to maximise the chances of results. The other is linked to the indicators of success selected for the logframe, which are very high-level and unlikely to be achieved within a short timeframe. Although the programme is likely to make good progress, it may be difficult to show evidence to this effect. For example, sustainable behavioural change in the area of G&I is unlikely to be visible within two to three years. Exclusionary processes are culturally and historically embedded within social and political structures and will take a long time to change. Similarly, while economic progress is a necessity it will not necessarily remove social strictures to women’s empowerment within a short space of time.
## Evaluation Question 8
To what extent is the institutional governance set-up of the Prosperity Fund more or less effective in achieving (i) primary benefits, (iii) secondary benefits, and (iii) other results?
Box 5: Evaluation Question 8 – main findings and conclusions
- The lack of a formal inception phase was challenging for the PT as well as CAF and Findeter initially, particularly in terms of contracting arrangements, due to different ways of working, systems and processes. There was a steep learning curve in terms of relationship building and learning, although this has ultimately paid off with strong existing engagement with partners and positive working relationships.
- There is regular and clear communication between the PT and implementers, as well as beneficiaries, across the PF portfolio. Regular meetings are scheduled to ensure constructive engagement and a timely resolution of any emerging issues.
- While early agri-tech project results are promising, the PT’s relationship with IUK is more challenging, due to remote working, institutional set-up and a perceived departure from the original MoU delivery expectations. IUK was also converted into a UK Research Council with a mandate that is not compatible with the goals of the Colombia Programme.
- The PT contracted a national G&I specialist, initially working with the agri-tech projects on their G&I action plans and providing training sessions, which is well received.
- Quarterly Reports are the main mechanism for IPs to share results with the PT, and for the PT to report to London. Quality and timeliness vary and reporting against logframe indicators is limited to date, due in part to the level of indicators. Reporting to Prospero has not started.
- High levels of management of the Colombia PF projects are reported by all main IPs, as well as sometimes changing goalposts, which is highlighted as a challenge.
- The PT receives limited feedback on their regular reporting from the JFU in London. The various relationships are positive and constructive, however, so this is not necessarily a cause for concern.
- Financial management has proved challenging, in terms of reconciling diverging systems and procedures (PT and IPs).

This EQ focuses on the effectiveness of the Colombia PT’s governance set-up and engagement with partners. EQ1 discussed the PT’s progress across all three sectors in terms of achieving early results for beneficiaries, while EQ9 covers the governance and management arrangements from a VfM perspective.
In the early Colombia PF design phase, the PT established new relationships with two regional development banks, CAF and Findeter. The programme signed a contract with CAF and an MoU with Findeter to establish them as their core implementing partners in country. The decision to work with CAF and Findeter was based on an assessment of their strong contextual and thematic experience of working across Colombia in the areas of infrastructure, agriculture and competitiveness, as well as their wide networks and reach, thanks to existing partnerships with sub-contractors implementing similar past or ongoing projects. There was also a VfM argument, as Findeter in particular had lower management fees than some of the more obvious partners, such as private consultancies or the World Bank, for example. Despite unavoidable challenges of working with new partners, CAF and Findeter have proved to be strong implementers for the Colombia PF and enabled the programme to start delivering early results. Both the PT and implementers have learned a lot in the first few months of implementation and have worked through emerging issues in order to find creative solutions and avoid delaying delivery. The PT’s existing relationships with CAF and Findeter are strong and based on mutual trust and understanding.
The third core implementing partner is Innovate UK, the UK government’s innovation agency, based in London. The PT reached out to IUK to replicate a successful Challenge Catalyst Fund they were implementing for UK Department for International Development (DFID), and IUK agreed to lead the agri-tech project for the Colombia PF. IUK work differently to CAF and Findeter, in that they currently deliver the project through seven grants to UK tech firms, which work in consortium in Colombia in a range of sectors. The PT’s relationship with IUK is less straightforward than with CAF and Findeter, partly due to the remote working conditions, and also to IUK’s institutional set-up as a UK government agency, and its perceived changing delivery expectations, a departure from the original MoU signed with the PT. While the existing partnership with IUK has produced the Colombia PF’s earliest results and all seven agri-tech have projects started implementation, IUK decided to discontinue its involvement with the PF at the end of the initial 18-month contract.
Exacerbated by a lack of formal inception phase, governance arrangements and engagement with all three core implementing partners proved challenging for the PT initially, as each have individual institutional ways of working, processes and delivery requirements, which do not always comply with PF regulations. These challenges included contracting requirements for sub-contractors, the inclusion of G&I in each project, complying with the PF Commercial Framework, or internal financing mechanisms, for example. The PT dedicated a substantial amount of time and energy to working closely with CAF, Findeter and IUK from the early design phase to find solutions to emerging issues and resolve them before they impacted delivery. While the first six months of the programme were not considered a dedicated inception phase, in practice this time was taken up by the unavoidable tasks of building new relationships with the IPs and setting up ways of working together before launching projects.
There is regular and clear communication and coordination channels between the Colombia-based implementers and the PT. Current relationships are positive and constructive, and issues worked through as they emerge. Where there were challenges in the past, such as one of the partners’ inadequate project management team tasked with leading PF projects, solutions were found by working together with the PT and agreeing a way forward. The IPs appreciate the PT’s availability, commitment to the programme and technical expertise across thematic areas, such as agriculture, infrastructure, policy, SBs or G&I. Parallel to this, the Colombia-based PT has direct relationships with PF focal points in London for reporting purposes, technical direction and financial matters, for example. The IPs do not directly communicate with any FCO/DIT team members in London but their close relationships with the PT enable efficient coordination, for example on contracting matters.
All three of the main IPs initially reported high levels of management for the PF projects, compared to other contracts, as well as changing goalposts at times. This is to be expected with any new project, however, and is also related to the fact that Colombia started implementation earlier than other PF country programmes, while the Fund was still in its design phase, and evolved alongside the programme, which resulted in design adjustments, such as the introduction of the Commercial Framework. However, one of the more recent IPs, OCP, finds the contract management relatively straightforward in comparison to other projects it delivers. The learning curve was steep for all parties in the first few months, which had an impact on implementation rates. Changes to current contracting processes include the introduction of new rules: the requirement that early market engagement events take place before launching calls, as well as formal agreement on contract values according to completed market surveys.
Financial management has proved challenging in certain instances, trying to reconcile diverging systems and procedures. One high-value example includes the rail project, originally contracted to Findeter, with the initial payment up front. However, Findeter failed to launch the project (ToRs/market research) within the quarter and was required to reimburse all funds to the PT before they were returned to the project to launch. Another example involved a public institution in Colombia being unable to finance delivery for an agri-tech project, as implementers are required to pay in arrears, as per the PF contracting arrangements. Despite these challenges, the IPs have worked closely with the PT to try and find creative solutions to working more efficiently and avoiding protracted financial or contracting procedures. The PT is able to engage directly with partners’ senior management and, at times, develop simplified mechanisms to contract and deliver a project. The PT was recently successful in convincing one partner to significantly simplify its legal requirements for international firms’ bids, which encourages greater participation in calls for proposals.
Some of the contracted partners aren’t used to working so closely with the regions in Colombia, but this is something they value on this programme. The regions are where the greatest challenges exist for Colombians, and where the PF can have a higher impact, according to the majority of the implementers. Traditionally in Colombia, most interventions focus on main cities but haven’t had a chance to engage directly with the regions, particularly those post conflict or suffering ongoing conflict.
The PT contracted a national G&I specialist, who is initially working closely with all agri-tech projects to provide G&I support and training. This is crucial, as the IPs develop their G&I action plans and start testing these with beneficiaries. The advisor’s inputs are currently part time and focused on agri-tech, but they will increase once other projects start implementation. The PT also includes a G&I focal point, the Deputy Programme Manager. An increased focus on G&I for all PF projects in Colombia has resulted in an irreconcilable difference between the PF and IUK. G&I was mentioned in their original MoU as one of four areas of focus. However, once grants were in the final award stages, the PF requested that additional criteria be fulfilled, including G&I training. Once projects were under way, all IPs were required to develop G&I action plans, with support from the locally contracted gender adviser. According to IUK, this is not in line with its core mission and ways of working, as it was originally involved to pilot the Catalyst Fund, with a clear focus on innovation. The PT pushed IUK to ensure G&I compliance with ODA requirements on this programme.
Quarterly reporting is the main mechanism for IPs to share results with the PT, and for the PT to report to London. The quality and timeliness of these quarterly reports vary but to date, IPs have not reported against indicators beyond number of attendees at a workshop, for example, as the projects have not yet started producing results. Direct reporting to Prospero is not yet operational. The IPs complete a standard template outlining outputs in the previous quarter, plans for the next quarter, challenges, risks and lessons learned, as well as spend. They also report against the logframe as far as possible, although most indicators are at a higher level and the projects do not yet have data. In terms of indicator reporting and monitoring, the project logframes were all recently revised, following the M&R visit in April 2019. There is now a need to coordinate with CAF and Findeter to fill in the targets and milestones, as these are incomplete to date. The PT requires the implementers to fill in the nested logframes each quarter and submit these with the quarterly reporting, as a narrative. The PT also wants the partners to update their project risk matrices and reflect on recent changes to risks or mitigation measures. The focal points are enthusiastic but require some capacity building from the PT Reporting Officer initially.
The PT produces ‘impact stories’ to communicate project successes. These are good news pieces and mainly used in public messaging and for communications material. These stories are not yet evidenced by attributable results, but they provide timely and usable communications pieces to publicise the programme. These were requested by London. The PT also uses the Colombia Embassy’s Twitter and Facebook accounts to provide updates on the programme.
## Evaluation Question 9
What type of programmes, approaches and governance and management arrangements have been more or less effective for achieving results and demonstrate good approaches to supporting inclusive growth and Value for Money?
Box 6: Evaluation Question 9 – main findings and conclusions
- VfM systems are in place across the PF, with a focus on economy and some evidence of considering effectiveness, efficiency and equity.
- VfM frameworks are not consistent across the programme. Rather, each implementer uses their own VfM assessment criteria, for example when scoring bids.
- Understanding of the implications of contracting UK firms is focused on economy. There is an argument that UK firms may be more efficient (for example with better knowledge, skills etc.) but there is no evidence to prove this.
- VfM is reported against in the AR, not the regular quarterly reports, although the PT has agreed to introduce this following the evaluation findings workshop.
- CAF and Findeter were initially selected due in part to low management costs, although other aspects were also considered, for example experience, networks and track record in Colombia.
This EQ examines the Colombia PF’s progress in setting up governance and management arrangements that will facilitate the achievement of results and demonstrate good VfM.
In October 2016, during the Colombia PF design phase, CAF and Findeter were selected by the PT as IPs following an open call for expressions of interest, based on evaluation criteria that included VfM considerations. Findeter scored highly in technical expertise, thematic and contextual knowledge of working in Colombia, networks and existing partnerships and track record of delivering similar or relevant projects. They also had much lower management fees when compared to perhaps more obvious partners, such as private companies or the World Bank. Their assessment by the PT at the time considered all aspects of VfM, including the 4Es (economy, efficiency, effectiveness and equity), and did not simply equate to a review of their total estimated costs to deliver PF projects.
To date, VfM systems and frameworks are in place across the Colombia PF programme and within the IPs’ processes, with a clear focus on economy and some evidence of considering effectiveness, efficiency and equity. There is a good level of understanding of VfM principles across the PT and implementers, which was further increased by VfM training to the PT, CAF and Findeter, including by the JFU and by the E&L team in summer 2018. Each IP uses their own VfM assessment criteria, for example, when reviewing commercial tenders as part of proposals.
The requirement that implementers use the PF Commercial Framework for all programme tenders created tensions between the Colombian IPs (CAF and Findeter) and the PT when it was first introduced. This was compounded by the fact that this clause was not clear from the outset, when IPs signed MoUs with the PF, as it was before the Framework came into effect. Resulting protracted MoU amendment processes have impacted the achievement of PF benefits by delaying delivery across projects. However, the PT have worked closely with the IPs to alleviate concerns related to the Commercial Framework and it is now better understood, and programming has resumed.
CAF and Findeter highlighted the higher total cost of contracting UK firms through the PF Commercial Framework compared to working with Colombian implementers, which is their benchmark. The PT is sympathetic to this and has continuously attempted to work with the implementers to highlight broader VfM considerations, including specific technical expertise and added value these firms may contribute, beyond the total cost to deliver a ToR. While there is currently a lack of evidence to support this claim, the Commercial Framework is a contractual requirement, and the Colombian implementers need to be able to work within its parameters. The Programme Manager pushes implementers’ proposals to include ‘true’ VfM proposals that consider quality of delivery, innovation, inclusion etc, to illustrate added value. UK or international firms bidding to prime a project also have the opportunity to partner with Colombian implementers in a consortium, which provides the contextual understanding that may otherwise be lacking.
The PT has received feedback from Commercial Framework firms that the initial PF budgets are low. This is one reason why two tenders (for Valledupar and Ibagué) were abandoned. In order to minimise this risk, the PT is organising early market engagement events to test project ToRs and contract values before being tendered. The first event was held in December 2018.
VfM is reported against in the yearly Colombia PF Annual Review. In the 2018 Colombia PF Annual Review, a comprehensive VfM assessment outlines the programme’s adherence to considerations on key cost drivers and performance, staffing, departures from the original BC, and the 4Es: economy, efficiency, effectiveness and equity. There is also a review of whether the programme continues to represent VfM, after six months of implementation, and finally an update on the quality of the Colombia PF’s financial reporting. The Annual Review identifies the need for the PT to develop VfM indicators to track progress against the 4Es.
To date, VfM has not been reported against in the Quarterly Progress Reports. However, the PT agreed to include a new section on VfM based on discussions during the evaluation findings validation workshop. At present, the Quarterly Reports include updates on total spend and underspend only. The implementers are not required to submit VfM reporting following a mandated framework. In a few cases, the PT has pushed the Colombian implementers to consider VfM and go beyond their institutional processes and requirements. For example, daily subsistence rates for some partner staff travelling to the field for PF project delivery were assessed as unjustifiably high by the PT, even though they were in line with internal guidelines. The PT requested an amendment to the MoU to amend these rates and ensure increased VfM in PF delivery.
## Evaluation Question 10
To what extent have the Prosperity Fund interventions contributed to results that support gender equality, women’s economic empowerment and social inclusion?
Box 7: Evaluation Question 10 – main findings and conclusions
- The programme sets out a clear commitment to addressing the needs and constraints of women living in poverty and providing economic opportunities for them.
- All the project strands have objectives on G&I, most explicitly addressed in the agri-tech projects.
- The PT has also worked actively to set G&I-related requirements for IPs and ensure these are understood.
- There seems, however, to be a lack of G&I-related capacity in many of the partner organisations, and consequently a lack of clarity about the gender dimensions, objectives and actions of projects to address these.
- The conceptualisation of what G&I means in practice for each of the project strands could be further clarified and elaborated.
- There could be more clarity around the level of ambition of each of the project strands and the ways in which they plan to tackle G&I considerations.
This evaluation considers G&I progress from an organisational set-up point of view, focusing on the systems and mechanisms in place and early activities undertaken during the programme’s set-up phase, and reflecting on ambitions set out at programme design phase. The following discussion builds on the G&I Thematic Stocktake Review conducted in December 2018.
Overall, the programme sets a clear commitment to addressing the needs and constraints of women living in poverty and providing economic opportunities for them. The programme seems to be paving the way in uncharted territory in Colombia, given that, according to the PT, the agenda of women’s economic empowerment and mainstreaming G&I issues into infrastructure projects is relatively new. The PT describes its ambition as influencing institutional change among government agencies to influence the norms, systems/processes and practices related to the ways in which public agencies consult with stakeholders and communities on their needs and interests, and the ways in which they design, deliver and manage projects. The PT has also worked actively to set G&I-related requirements for IPs and ensure these are understood, including by strengthening their capacity.
The programme has taken substantial steps to mainstream G&I issues into its main body of work and is laying down the groundwork to enable projects to be designed and delivered so that G&I-related issues are adequately addressed and projects contribute to positive benefits for women. Continuous capacity building and support to implementing organisations is however needed to enable plans to come to fruition.
Promotion of gender equality, social inclusion and poverty reduction are explicitly stated to be the main objectives of the PF in Colombia, with interventions focusing on creating economic opportunities in areas of former conflict. All project strands have some level of objectives and activities related to G&I. All projects should reach at least level 1 on the PF’s G&I framework, with ambitions to reach level 2 ‘empowerment’.
The PT has also taken active steps to build the capacity both of IPs on G&I requirements and of the government ‘targets’ or beneficiary organisations it seeks to influence on how to ensure that G&I considerations are built into projects from the analysis and design stage through to delivery. However, the E&L team has not always been able to verify these claims in documentation.
At this stage of programme implementation, the specific G&I-related objectives and activities for all project strands are being worked out and, in many cases, strands are carrying out analysis and consultation with stakeholders and communities. The approach and activities are clearest for the agri-tech projects, possibly because these are furthest along in delivery (see Table 4 for further details on the G&I elements of PF activities).
Table 4: Summary of Gender and Inclusion objectives and elements per project
Sector	Activity	G&I objectives and elements
Institutional strengthening	Regional competitiveness	Projects aim to capacity-build officials in chambers of commerce to ensure that they take G&I issues into account in scoping, selecting and managing projects. / The Aerocafé project had to review its previous socio-economic analysis as the G&I-related issues were deemed weaker in the previous study. The Aerocafé Master Plan had to include G&I and poverty dimensions.
	Open public procurement	Considering the differences in fees that the government pays female- and male-owned businesses and considering and addressing the lack of sex-disaggregated data, which is currently not being collected.
	Corporate governance reform of Colombia’s National Infrastructure Agency (ANI)	A new governance structure model of ANI’s board will be designed and piloted with the aim of achieving gender balance and female representation.
Infrastructure	Urban development	The project focuses on influencing the working practices of officials to ensure that infrastructure projects deliver benefits for women. It aims to change mindsets and working practices in relation to the importance of continuing stakeholder and community engagement in infrastructure projects. / G&I issues that the integrated transport project seeks to address are being scoped out and the project is about to start stakeholder and community engagement and socio-economic analysis. Overall, investment in public transport is expected to benefit women, who tend to have less access to private vehicles than men.
	Rail development	This activity was not sampled in this cycle.
Agriculture	Agri-insurance	The project is supporting the design of agri-insurance products to take into account access issues faced, for instance, by female producers to ensure that female farmers can access loans and insurance products specifically design for female small holders.
	Agri-Tech Catalyst Challenge Fund	The Agri-tech project is considering G&I explicitly, with a clearly thought-through approach and activities, mainly focusing on targeting women smallholder farmers as well as people who do not own land or own or rent small pieces of land. The project aims to increase productivity and incomes for Colombia’s smallholders in cacao, banana, coffee and tilapia fish farming.

To operationalise these objectives and to ensure that all projects are designed and delivered according to the UK’s ODA requirements, the PT has set relevant G&I-related requirements and deliverables for partners. The PT has also actively worked to socialise these requirements and train partners to ensure that the requirements and their practical implications are understood, as well as facilitating the development of initial G&I action plans for the lead partners Findeter and CAF. Partners are required to carry out socio-economic impact assessments and feasibility studies to analyse G&I-related needs and constraints, as well as conducting an analysis of potential harm and risks and drafting G&I action plans that explain how projects address these.[34] In cases where the initial feasibility studies did not sufficiently consider socio-economic issues and G&I specifically (such as in the case of the Aerocafé study), partners have been requested to conduct an additional study following PF G&I standards and requirements. The PT has also trained partner organisations on PF G&I requirements. In some cases, IPs stated that G&I-related requirements have evolved after the projects started, and have therefore been more challenging to incorporate after the project parameters and design have already been set. These shifting requirements may have also meant that partners with the most relevant G&I capacity were not chosen at the outset.
[34] The E&L team has not had access to these studies or G&I action plans (apart from early versions drafted in 2018 with the support of the JFU Social Development Adviser), with the exception of a G&I Annex for CAF, which sets outs the G&I requirements and the PF’s G&I programming framework.
The programme also provides resources for G&I for training, secondments, policy work and communications. For instance, training on G&I will be provided to mayors of departments /municipalities to ensure that their strategic plans integrate G&I concerns and help them identify projects that would yield the most G&I-relevant benefits.
With the exception of the agri-tech project, project strands are still conducting analysis, scoping out their work and designing their G&I-related objectives, approaches and activities. Specific approaches/activities of G&I work are therefore still being worked out at this stage for most of the projects. This may be due to the ‘early’ stage of many of the projects, which are in the process of analysis and scoping.
The PT has taken active steps to build its own knowledge and capacity on G&I and has hired an external consultant with specific G&I responsibilities. The PT also has a G&I champion (the Deputy Programme Manager) who champions G&I within the PT, brings good practice from other PF programmes and participates actively in the central PF G&I champions learning network. Currently, the G&I specialist mainly advises on the agri-tech project because it is at a more advanced stage, but the aim is that the G&I specialist will work across all projects as these advance in their implementation. The PT has worked actively to capacity-build both IPs on G&I requirements and the government ‘targets’ or beneficiary organisations it seeks to influence on how to ensure that G&I considerations are built into projects from the analysis and design stage through to delivery.
The PT has influenced initial G&I-related organisational and process-related changes in IPs CAF and Findeter (as well as other sub-contractors/partners). Partners report having to do things differently as a result of PF requirements. Many of the IPs do not have a previous background or expertise in G&I and are considering G&I aspects explicitly in their work for the first time. Partners express awareness of commitment (at least on paper and verbally) to addressing G&I-related issues. This demonstrates the work and capacity building the PT has carried out to set G&I requirements and ensure these are understood. Many partners in interviews are also quite open about their lack of knowledge and understanding of the potential G&I issues in their thematic area of work and what to do about these. Interviews with partner organisations (for instance Findeter) reveal expectations for the PT to continue providing G&I training to help fill organisational capacity gaps.
PT staff report challenges in building partner G&I capacity from a low base and ensuring this capacity is sustained. Some of these challenges are compounded by staff turnover, with trained partner staff having left, and requirements for the PT to restart the process. Some PT staff report overestimating partner capacity and existing organisational processes at the outset not only to actively promote G&I issues, but also to meet minimum standard requirements in terms of environmental, social and gender considerations. To address these issues, the PT has actively taken steps to capacity-build partners on G&I.
All of the above raises the question of how to build capacity in a sustainable manner to ensure that all partner staff (and not just the G&I experts) are able to manage sub-contractors on G&I-related aspects to a sufficient degree of quality. Many of these concerns may be ‘teething issues’ that are resolved as projects progress. This suggests that the PT may be required to continue its active role in providing support to partners on G&I for some time.
Broadly, project logframes include relevant G&I-specific outcomes and sex-disaggregated indicators, though most are mainly focused on women and people living in poverty rather than other excluded groups. However (and this is also the view of some of the partner interviewees), some of the G&I-related objectives and indicators may be too ambitious and not realisable and ‘monitorable’ within the timeframe of projects. The PT and projects should further consider what is within a project’s sphere of control and influence and the likelihood of attaining this within the project’s timeframe. The PT and projects should also consider how feasible some of the indicators and their data collection will be within a project’s lifetime, and what this will look like in practice. The support of specific sector specialists may be helpful in this regard. The evaluation team has not been able to verify how partners report against these logframes. Most of the reporting from the PT to HQ is (due to the early stage of projects) mainly activity-based.

## Evaluation Question 11
How is the Prosperity Fund learning and why is action on this learning happening more or less successfully?
Box 8: Evaluation Question 11 – main findings and conclusions
- The Colombia PF programme’s learning processes are both formal and informal, and the PT has a strong learning culture and adaptive management is encouraged.
- The Colombia Programme BC did not include a formal learning framework.
- The Colombia PT promotes internal and external sharing of lessons and supports decision-making through a reflection and learning cycle, including with partners.
- The findings of this evaluation will be used by the PT, in conjunction with the recommendations from the upcoming AR.
- The PT is open and responsive to learning and has previously made programme adaptations based on lessons learned. This includes the logframe and ToC revision process in April 2019, in collaboration with the M&R team and all core implementers.
- The PT engages in sharing lessons with other PF actors and wider stakeholders. This is particularly true across Latin America, especially with the Mexico and Brazil PF teams, for example in the context of the twice-yearly Americas Conference.
This EQ examines how the Colombia PT is learning and what mechanisms are in place for this purpose. Early PF activities, including design and contracting of the main implementers, presented substantial learning for the PT. The programme is a departure from previous FCO and wider UK government implementation in Colombia and the team is learning on an ongoing basis.
From the programme’s inception, the Colombia PT developed an effective combination learning mechanism. Capturing and sharing lessons learned and working adaptively is encouraged by the PF Programme Manager and facilitated through regular meetings (internal to the PT, with the implementers, with London colleagues and with other embassy colleagues, such as DIT), as well as reporting structures. The monthly and quarterly reports include lessons learned that the implementers share with the PT, which then reports these to London. The team also produces impact stories for public dissemination. Most importantly, open and honest communication and feedback is encouraged, and the team reflects on what is working well and what could be improved in order to adapt their management of projects or other aspects of the Colombia Programme delivery. Formal governance structures include the PF Internal Progress Review Governance Board, the Stakeholder Group and Private Sector Advisory Group.
One example of supporting learning to inform decision-making includes the process of designing and delivering this Cycle 1 evaluation of the Colombia PF. The entire PT and partners were open to honest discussions and responsive to requests for information. Findings and recommendations were shared initially in early August 2019, ahead of the evaluation report finalisation, in order to sense-check statements and co-create lessons learned for future uptake. These findings and recommendations, along with the internal Annual Review lessons, will be taken on board by the PT to inform their decision-making and programming. The PT understands the value of yearly evaluations for improved delivery and played a proactive and supportive role throughout the evaluation process.
The Colombia PT are active users of the E&L online portal PFLearning. PFLearning was mentioned by more than one PT technical adviser as a useful learning resource and a space to engage with other teams and discuss relevant and shared topics and ideas. This engagement was initially encouraged by the Programme Manager and wider PT and is now one of the learning tools at the advisers’ disposal. As Colombia is one of the most advanced PF programmes, PFLearning presents an opportunity to share up-to-date best practice and lessons learned with other PF stakeholders, as well as discuss challenges in live conversations. For example, in August 2019, the Colombia PT participated in the SB workshop in London, using teleconference facilities.
All PT team members are entitled to a specific annual learning/training budget. This includes external courses and presents a significant opportunity to network as well as to deepen expertise in a specific area of knowledge. Examples of external training or courses attended include the PF management course, DFID ToC training, commercial training from DIT, the DFID livelihoods workshop and Making Markets Work for the Poor approaches. The Deputy Programme Manager is currently going through additional G&I training and was able to job-shadow with a social development direct adviser in London. Within the British Embassy in Bogotá, the PF team members are seen as leaders in certain thematic areas, such as G&I or SB. They support colleagues from DIT and CSSF, for example, to increase their expertise in these areas. They are able to provide concrete examples of lessons learned, engaging with these by sharing PF experience to date. This support across the embassy is not outlined as a formal requirement in the PT’s roles and responsibilities, but it is a proactive approach to sharing best practice and working collaboratively.
The Colombia PT is active in attending relevant events, including internationally. These present opportunities to share their work broadly, learn from other implementers or donors, network and engage on future opportunities. The SB Adviser recently participated in engagement events in the UK, in collaboration with DIT, to share updates from the Colombia PF projects and discuss opportunities for UK firms. The Colombia PT also attends the twice-yearly PF Americas Conference, which rotates between Mexico, Brazil and Colombia, and brings the three PTs together. This is a more structured opportunity to share lessons and challenges with colleagues working in sometimes similar contexts. However, the teams also engage informally on a more regular basis, particularly in the case of Mexico and Colombia. There is also a yearly PF conference in London that the Colombia team attends, although it did not take place in 2019.
# Summary of findings
Table 5 presents a summary of the key findings of this evaluation cycle.
Table 5: Fund-level Evaluation Questions relevant to Cycle 1
Evaluation Questions	Strength of evidence*	Summary of findings
EQ1: What evidence is there that the Prosperity Fund (PF) is likely to contribute to the intended outputs and outcomes in the Theory of Change (ToC), as well as any unintended or unexpected outputs?	12	It is too early to assess the likely contribution of the programme to intended outputs and outcomes in the ToC, as well as any unintended consequences. It is encouraging to see that primary and secondary benefits are central to the umbrella ToC, thus increasing the chance for the programme to deliver inclusive growth. The coherence between the Programme ToC and the PF ToC and the internal coherence between the Programme ToC and the projects’ objectives also increase the chance of positive outcomes. There are indications that a number of activities undertaken by projects are delivering on outputs.
EQ4 What evidence is there that the changes supported by the Prosperity Fund interventions will be sustainable and ensure environmental sustainability, will be self-financing and will lead to inclusive growth that reduces inequality?	12	The Colombia Programme has strategically positioned itself to ensure sustainability by choosing to work in sectors that are aligned with national and subnational plans. The terms of reference for PF-funded projects include conditions on financial and environmental sustainability. The Colombia Programme will be the first programme to develop an outline for a climate and environmental strategy that will inform all PF and CSSF programmes.
EQ6 How has the balance and relationship between primary and secondary benefits across the portfolio influenced the achievement of results?	15	There is common understanding between the PT and IPs on who the primary and secondary beneficiaries of the programme are. The programme engages indirectly with primary beneficiaries via the IPs and directly by working with governments and individuals. The PT considered SBs in the programme design. When choosing which sectors to work on, the team chose sectors where the UK has comparative advantages. The promotion of SBs is led by the PF’s commercial adviser, who works closely with DIT and London in promoting the PF in the UK. There are mixed perceptions among implementers about the trade-offs and VFM of the benefits of using UK experience in Colombia.
EQ7: Which assumptions and causal pathways outlined in the ToC remained valid, which refinements have been made and what refinements need to be made?	12	No explicit assumptions were identified in the updated umbrella ToC, though project ToCs have identified assumptions. Changes in the political context and risks of corruption were initially underestimated but are now taken into account. The assumption that UK firms would be interested in partnering in the programme has encountered hurdles such as limited contextual knowledge, language skills, cost differentials between UK and Colombian firms and the perception by UK Firms that the PF budgets are low.
EQ8: To what extent is the institutional governance set-up of the Prosperity Fund more or less effective in achieving (i) primary benefits, (iii) secondary benefits, and (iii) other results?	15	The lack of a formal inception phase was initially challenging for the PT as well as CAF and Findeter, particularly in terms of contracting arrangements, due to different ways of working, systems and processes. There was a steep learning curve in terms of relationship building and learning, although this has ultimately paid off with strong existing engagement with partners and positive working relationships. There is regular and clear communication between the PT and implementers, as well as beneficiaries, across the PF portfolio. Regular meetings are scheduled to ensure constructive engagement and a timely resolution of any emerging issues. While early agri-tech project results are promising, the PT’s relationship with IUK is more challenging, due to remote working, institutional set-up and a perceived departure from the original MoU delivery expectations. Quarterly Reports are the main mechanism for IPs to share results with the PT, and for the PT to report to London. Quality and timeliness vary and reporting against logframe indicators is limited to date, partly due to the level of indicators. Reporting to Prospero has not started. The PT receives limited feedback on their regular reporting from the JFU in London. The various relationships are positive and constructive, however, so this is not necessarily a cause for concern.
EQ9: What type of programmes, approaches and governance and management arrangements have been more or less effective for achieving results and demonstrate good approaches to supporting inclusive growth and VfM?	15	VfM systems are in place across the PF, with a focus on economy and some evidence of considering effectiveness, efficiency and equity. VfM frameworks are not consistent across the programme. Rather, each implementer uses their own VfM assessment criteria, for example, when scoring bids. Understanding of the implications of contracting UK firms is focused on economy. There is an argument that UK firms may be more efficient (for example with better knowledge, skills etc) but there is no evidence to prove this. VfM is reported against in the AR, not the regular quarterly reports, although the PT has agreed to introduce this following the evaluation findings workshop. CAF and Findeter were initially selected due in part to low management costs, although other aspects were also considered, for example experience, networks and track record in Colombia.
EQ10: To what extent have the Prosperity Fund interventions contributed to results that support gender equality, women’s economic empowerment and social inclusion?	13	The programme sets a clear commitment to addressing the needs and constraints of women living in poverty and providing economic opportunities for them. All the projects have objectives on G&I, most explicitly addressed in the agri-tech projects. The PT has also worked actively to set G&I-related requirements for IPs and ensure these are understood. However, there seems to be a lack of G&I-related capacity in many of the partner organisations, and consequently a lack of clarity about the gender dimensions, objectives and actions of projects to address these. The conceptualisation of what G&I means in practice for each of the project strands could be further clarified and elaborated. There could be more clarity around the level of ambition of each of the project strands and the ways in which they plan to tackle G&I considerations.
EQ11: How is the Prosperity Fund learning and why is action on this learning happening more or less successfully?	21	The Colombia PF programme’s learning processes are informal, but the PT has a strong learning culture and adaptive management is encouraged. The PT promotes internal and external sharing of lessons and supports decision-making through a reflection and learning cycle, including with partners. The PT is open and responsive to learning and has previously made programme adaptations based on lessons learned. This includes the logframe and ToC revision process in April 2019, in collaboration with the M&R team and all core implementers. The PT engages in sharing lessons with other PF actors and wider stakeholders. This is particularly true across Latin America, especially with the Mexico PF team, for example in the context of the twice-yearly Americas Conference.

*The maximum data quality score for each EQ is 25 (up to 5 points can be allocated to each of the 5 criterion)

# Lessons
The independent E&L team validated the preliminary Colombia PF Cycle 1 evaluation findings with the PT during a workshop at the British Embassy in Bogotá on 2 August 2019. This workshop was also used to discuss lessons learned and recommendations. Following this, a findings workshop also took place with the main implementers in Colombia, CAF and Findeter on 27 August 2019 to sense-check findings and lessons.
Lesson 1: New partnerships, such as those between the Colombia PT and their main implementing partners, CAF, Findeter and IUK, require a dedicated engagement or inception phase, which should last a minimum of six months.
In order to ensure productive, collaborative relationships with partners, it is necessary to have a clear understanding of their internal processes, systems and ways of working. This is true of any partnership, but particularly important when engaging with new organisations, as is the case for the Colombia PF. The PT and partners have dedicated substantial time and energy into building these relationships, and a steep early learning curve paid off. While current engagement is now solid, it would have been preferable to dedicate six months to an inception phase in order to work through challenges before trying to start implementing projects (see Section 6.5).
Lesson 2: IPs bring a wealth of networks, experience and expertise to the Colombia PF that is vital to the programme’s success. In terms of technical and management capacity, the IPs might not be up to expected standards in all areas.
The IPs bring a wealth of experience of working in Colombia. For example, Findeter has a proven track record working at local level in all locations where the programme is implemented, and CAF is a regional multilateral with unique experience in competitiveness. The PT has identified some gaps in the IPs’ technical capacity to draft high-quality ToRs, for example when incorporating G&I considerations (see Sections 6.7 and 6.5). In response to these challenges, the PT has focused its attention on strengthening IPs’ and beneficiaries’ specific capacities in areas such as procurement, VfM or G&I and the three programme sectors (infrastructure, competitiveness and agriculture).
Lesson 3: The success of the Colombia PF Programme is highly dependent on it aligning with rapidly evolving national and local contexts.
From early stages in the programme design (Business Case), the Colombia Programme has worked closely considering the country context. The programme was designed in close collaboration with the government and in line with national and local development plans (see Section 6.2). Since the programme was launched, the PT has continued to actively monitor how the context is rapidly evolving (see Sections 3 and 6.4) and engaging with the government in order to ensure that new people coming into power are aware of the PF and remain interested in the programme’s implementation. The PT has developed political economy analyses in two sectors, agriculture and rail. However, the context and assumptions are not part of the ToC for the Colombia Programme.
Lesson 4: Secondary Benefits need dedicated resources (people and budget).
The creation of new interest from international firms to work in a new country requires pro-active support. In the case of the Colombia Programme, the PT has worked with national agencies responsible for trade and investment (ProColombia, UK/Colombia Chambers of Commerce in Bogotá and London) and with DIT regional networks. There have been challenges in identifying the demand from international firms and in getting the contracting processes right (see Section 6.3). The PF has weak recognition levels by the private sector in the UK.
Lesson 5: VfM principles are well understood and the PT and partners consider VfM throughout their work, although their approaches would benefit from increased consistency (see Section 6.6).
The PT reports on VfM in detail in Annual Reviews but does not have a formal VfM framework that it uses in its project management with IPs. Each organisation considers VfM to varying degrees and uses its own institutional VfM criteria when evaluating competitive commercial proposals, for example. However, the Colombia PF would benefit from a more rigorous application of VfM principles across the programme, with a shared understanding of definitions and regular VfM reporting, which the PT recently decided to introduce into Quarterly Reports requests. To date, economy receives most attention from IPs, with increasing consideration of efficiency, effectiveness and equity.
Lesson 6: Raising awareness of G&I in Colombia has been challenging with all stakeholders (see Section 6.7).
The programme has invested dedicated resources (budget and people) and hired a local expert to work with projects. Many programme stakeholders (programme staff, IPs, beneficiaries, governments) have received G&I capacity building. Through starting early and regularly repeating key G&I messages, the programme is now recognised for its innovative work on putting G&I at the centre.
Lesson 7: An open and transparent approach to collaboration and learning within the Colombia PF PT is key to its early successes and presents ongoing opportunities for future programming improvements and scaling up.
The Colombia PT is a highly qualified and collaborative team of experts working across a range of sectors (see Section 6.8). They are open to learning from experience, as well as receiving external support where appropriate. They share learning internally and externally with partners on a regular basis. This approach was clear during the evaluation design phase, when the team provided as much support as possible, and was receptive to the benefits of conducting an initial evaluative exercise of the Colombia PF. Their positive attitude towards learning has also resulted in a strong focus on G&I, for example, and the programme is now a case study for the wider PF portfolio. While it is early to demonstrate results, benefits of this way of working should extend beyond the PF life cycle, particularly for partner organisations.
Lesson 8: Adaptive management requires both openness to learning and the flexibility to change course in response to a dynamic environment.
The Colombia PT is developing a culture that is open and keen on learning (see Section 6.8). This is an important element of adaptive programming. Early evidence suggests that from its initial stages, the Colombia PT has been flexible and adaptive while working with governments as they change and their “National Development Plans” are elaborated. The programme has also adapted to changes in the working relationships with the three main IPs.
Lesson 9: Regional learning opportunities exist within the wider PF programme portfolio, but especially across Latin America, in Mexico and Brazil.
As one of the most advanced PF programmes, Colombia is leading the way in several areas in terms of PF delivery and early lessons learned (see Section 6.8). Best practice is shared by the Colombia PT with counterparts in Mexico and Brazil on an ad hoc basis, but also more formally twice a year, during the Americas Conference. Similarly, there is a lot to learn from the other countries’ programmes, as some contextual similarities exist.
Lesson 10: Communications and coordination require dedicated resources (budget and people) within the PF team and with partners.
The programme has developed several tools for its promotion (see Section 6.5): videos of the programme (one introductory, one more detailed and one on doing business in your country/thematic area), and a commercial bulletin for SBs. The PT is actively involved in learning activities: the PT’s Programme Manager and G&I champion have contributed to PF learning events. The PT has played a leading role in sharing lessons learned with other regional country programmes through the PF Americas Conference.
Lesson 11: At the methodological level, the application of contribution analysis was not possible at this stage due to limited data.
As per the Approach Paper, the E&L team plans to use a theory-based approach (contribution analysis) during the evaluation of the Colombia Programme (and other PF programmes). However, this was not possible during this cycle due to limitations of available data.

# Recommendations
This section provides recommendations based on the lessons identified in Section 8. These recommendations (and the findings and lessons from this report) are currently being used by the Colombia PT in the initial stages of drafting their annual review. They are the primary audience for all recommendations, unless otherwise stated below. We suggest that a plan for the implementation and the prioritisation of these recommendations be carried out in the next months. The E&L team is available to support and facilitate this process with the PT.
Recommendation 1: The PF should include an inception phase of at least six months in the set-up of new programmes.
The lack of an inception phase for the Colombia Programme caused delays in its set up and generated unnecessary tensions in the relationships between the PT and IPs who had to work under unrealistic expectations during programme set up (see Section 6.5). The PF should include a six-month inception phase in all new programmes to allow stakeholders to better plan and agree on ways of working together.
Recommendation 2: The PT should continue to work towards strengthening their partnership with the IPs, and the capacity of their staff, the IPs and the beneficiaries.
Establishing a new relationship between the PT and IPs in Colombia has been challenging at times (see Section 6.8). All teams are working under pressure to achieve results under changing circumstances. The teams have also encountered gaps in the technical capacity of the PT staff, IPs and beneficiaries (see Sections 6.5 and 6.7). By continuing to strengthen the partnerships and to provide opportunities to strengthen the capacity around themes such as G&I (see Section 6.10) and VfM (see Section 6.6), the PT will increase the chances that the programme continues to contribute towards its desired impacts.
Recommendation 3: The PT should continue to closely monitor the national and local context in which the programme is operating.
The Colombia Programme was designed in line with national and local priorities (see Section 6.2). Since its launch, a new government is in place in Colombia and negotiations around Brexit are happening in the UK. A rapidly evolving context in both countries can affect planned activities, and for this reason the PT should continue to closely monitor the national and international context (see Sections 3 and 6.4). Assumptions should be developed for the ToC of the Colombia Programme.
Recommendation 4: Further work in the creation of new consortia could be done by the PT. In addition, other forms of SBs should be identified and forecasted.
As explained in Section 6.3, it has been challenging to bring new international firms to work in Colombia. In order to facilitate this, the PT could work supporting the promotion of consortia between Commercial Framework and local companies before launching projects by facilitating ways in which international firms can meet local institutions. This was done in the context of the agri-tech project (by IUK and CIAT) and resulted in new firms establishing relationships with local institutions that jointly bided and are not implementing the agri-tech projects.
Other forms of SBs can emerge before programme outcome success and should be formally considered, over shorter timeframes. For instance, soft power goals and network effects can be realised as PF spending takes place through the increased presence of UK activities in country and the resultant partnerships developed with national and regional governments. Partnerships between UK, local, and international firms may emerge early on through the activities conducted by the programme. A much broader knowledge campaign on the PF opportunities being created is needed with international firms.
Relatively rigorous SB forecasts could be honed in future years. The Business Case shows appropriate and detailed methodologies that were used to form strand-level SB forecasts. The programme may consider returning to the inputs used to represent the magnitude of the impact of the intervention for each forecast. These could be derived from external sources. Alternatively, as the programme develops, more information could be available that indicates the likelihood of intervention success or the intervention’s magnitude of impact, which could be inputted into SB forecast calculations. This may then temper or heighten SB expectations.
Considering SBs of different timeframes and different pathways. The numeric forecasts all take in to account the likelihood of intervention success. This is appropriate. These SBs will also take a long period of time to be realised. Appropriate long-term monitoring mechanisms and appropriate supporting activities will need to be put in place to facilitate their achievement. The programme could also consider other SBs that may be more immediately realisable. Such SBs may also be realisable through different pathways.
Recommendation 5: Design further VfM training for the PT and partners to increase understanding of VfM principles and capacity to use VfM frameworks.
The Colombia PF considers VfM and reports against it formally in Annual Reviews (see Section 6.6). However, the PT and partners would benefit from further capacity building from the E&L VfM Lead to design an overarching VfM framework for the programme. This would increase consistency in VfM assessments and reporting on a more regular basis (quarterly). The partners currently use their own individual VfM criteria, with a strong focus on economy, which is not a true reflection of VfM. Some of the resistance to complying with the Commercial Framework is related to this, and a better understanding of wider VfM considerations, such as efficiency, effectiveness and equity, would perhaps streamline the bidding and assessment process for UK and international firms.
Recommendation 6: Further conceptualise by the PT what G&I means in practice for each project and support partners to refine their action plans and build their capacity.
As outlined in Section 6.10, while G&I is clearly mainstreamed is all programme design documents (MoUs, ToRs, etc.), the conceptualisation of what G&I means in practice for each of the project strands could be further clarified and elaborated. Implementing partners require ongoing G&I capacity support to ensure they are able to operationalise their plans once the projects start implementation. While great progress has been made to date, the PT need to ensure that the projects’ aim is not simply to involve women but rather to work in a genuinely G&I-responsive way to address barriers felt by women and other excluded groups. This relates to the longer-term and ambitious aim or creating transformational change for women and other disadvantaged groups. For instance, on the infrastructure/transport-related projects in particular, the programme/projects should think through not only how to address the barriers and needs of women and other excluded groups through stakeholder engagement at the design stage, but also consider how to ensure that projects during their development/construction/operation and maintenance phases actively provide targeted opportunities to increase employment and training opportunities for women and other excluded groups of people and the businesses owned by them.
Recommendation 7: Further formalise learning mechanisms within the PT and in coordination with implementing partners, as well as the development of lessons learned and best practice.
While existing learning systems are strong across the Colombia PF and what works well or less well is regularly identified and actioned (see Section 6.8), we suggest the programme would benefit from a few structured reflection points. The Colombia PF has progressed quickly, especially in comparison with other PF programmes, and in parallel with the refinement of the wider Fund processes. As a result, adaptive management was inevitable, and this has resulted in ongoing learning that the PT and partners have taken on board. We suggest that both the Colombia PF and the wider portfolio of PF programmes would benefit from identifying and sharing important lessons from implementation. Learning could be captured in an annex to the regular quarterly reports and discussed during a dedicated quarterly meeting between the PT and partners, or piggyback on existing appropriate coordination mechanisms. The E&L learning team have a wealth of resources available to support this process.
Recommendation 8: While the PT’s reservations around drafting a comprehensive ToC narrative are understood, we recommend that the PT and partners develop at a minimum a document outlining key ToC assumptions and describing in a narrative form the pathways for change visually represented in the umbrella ToC.
The Colombia Programme ToC lacks a narrative about its assumptions and pathways of change, which is fundamental to track and assess the causality of changes that are happening and will continue to happen during the life of the programme (see Sections 6.1 and 6.2). The rationale behind formalising ToC pathways assumptions includes the fact that that these relate to programme risks and dynamics beyond the PF’s control. Currently, these assumptions are well understood and broadly shared across the PT and partners, but we suggest formalising a common understanding of these pathways and assumptions, as well as risks the Colombia PF faces and how implementers would mitigate these should they arise[35].
[35] The PT confirmed that they will be developing a narrative for the Colombia Programme umbrella ToC during the Findings Evaluation Workshop held in September 2019 in Bogota.
Recommendation 9: Making use of lessons learned and applying the PF E&L Learning Touchpoints
The lessons above should inform the Colombia Programme and the wider PF E&L Learning Strategy[36] which outlines specific methods of dissemination and approaches for how lessons from PF evaluations will be shared (see Section 6.8). This report will be made accessible to a wider secondary audience, subject to the JFU’s publication policy. The Colombia Programme has had staged opportunities to learn through participation within this evaluation process, known as ‘learning touchpoints’, which include (i) planning follow-up actions for the PT and IPs teams to take responsibility for action on learning gains as part of an adaptive management approach; and (ii) wider learning and enquiry to ensure that E&L plans for sharing externally valid lessons from the evaluation or for commissioning further evaluations to address gaps in knowledge are appropriate to PF stakeholders’ own learning needs and opportunities. The PT should keep actively working on the promotion of its activities and sharing lessons with other PF programmes.
[36] Prosperity Fund Evaluation and Learning, Annex 14: Learning Strategy and Plan, March 2018.
Recommendation 10: Ensure dedicated and ongoing support from the PT to the initial seven agri-tech projects.
The agri-tech projects are set apart from other Colombia PF projects as they were the first to start implementation, and they are showing promising early results (see Section 6.1). While they are lower in value than most of the other projects, and are all in their early pilot phases, we recommend the PT ensures appropriate technical and financial support to ensure cross-project learning, results and ultimately sustainability. With IUK’s facilitation role disappearing after the initial 18-month contract, follow-on funding sources will be required to support any scaling up of these first agri-tech projects. The PT is actively engaging with this already. In the meantime, we suggest a strong focus on supporting learning between agri-tech projects as they all have relevant early lessons from the design and early delivery phases of their work. The lack of targeted funding of internal G&I and M&E components of the agri-tech projects to date has caused some frustrations with IPs, who are used to collecting monitoring data and producing baselines and other evaluation products based on their analysis. We support this initiative and encourage the PT to enable partners to carry out their own data collection activities to strengthen overall Colombia PF evidence generation.
Recommendation 11: The E&L team should use contribution analysis in the next evaluation cycle if possible.
The E&L team will continue to monitor data generated by the Colombia Programme in the next months and if possible will use contribution analysis during the next cycle.