Evaluation report title and date: / COLOMBIA PROSPERITY FUND PROGRAMME EVALUATION REPORT 2021 / (CYCLE 2) / February 2021 / Link to evaluation publication on gov.uk: Not yet published

Response to evaluation report (overarching narrative)
The Cycle 2 Evaluation came at a very opportune time. As we enter the last year of implementation for the Colombia PF Programme, the insights provided by the EL Team give us a solid basis to progress with the Programme, making some important recommendations to ensure effective delivery of results. It is also a solid basis with moving forward with the design of a Country-Business Plan. / The report and its annexes are comprehensive in their scope to reflect the totality of the Programme, and the level of analysis is deep, demonstrating the detailed understanding that the EL Team has of the Programme. The recommendations made are accurate and will be helpful as the programme continues implementation. A highlight is that this evaluation developed the first contribution analysis in the entire Prosperity Fund, the collaborative approach that the EL Team has taken to ensure that the Colombia Programme’s results are well captured in this evaluation are also key to having recommendations for which the Programme can take concrete action during 2021-2022. / The evaluation period reflected a busy time for the Colombia Programme, as 23 projects started and/or continued implementation within this time (until early December 2020). The projects which were more advanced in implementation included the Agritech Catalyst Challenge (7 projects) and the “Open Contracting at the regional level in Colombia”. Selected results from both activities were further analysed through the contribution analysis section. The variations between strands are well captured in most sections, and especially in the G&I annex, the VfM Analysis and the ToC assessment.

Recommendation	Party that recommendation is directed to	Accept, partially accept or reject	If “accepted” or “partially accepted”, give action plan for implementation and if “rejected” or “partially accepted”, give reason for rejection / only partial acceptance
Ensure complete alignment across MoUs, contracts and reporting mechanisms by standardising reporting formats and including logframe and ToC-related information and analysis.	PT Advisors and IPs	Partially accepted	We have already worked towards standardising MoUs, for example in terms of G&I requirements, but it would be challenging administratively to modify existing MoUs and contracts (which in some cases are already closed). For new contracts or MoUs we will consider these. In addition we will work together with IPs (using this evaluation report) to standardise reporting, including logframe and ToC related information.
Review communication lines from the PT to IPs to suppliers to direct beneficiaries to ensure that the layers of programme management harmonise and reinforce desired messages and principles. This could be done by periodic virtual gatherings to a quarterly ‘themes and talking points’ memo to be shared among project principals.	Head of PF, PT Advisors	Partially accepted	We will introduce quarterly meetings between IPs and the PT to harmonise and reinforce desired messages and principles. We will initiate this in May (to share evaluation results and as an end of fiscal year balance).
Consider sharing lessons and insights with IPs and suppliers by periodically convening thematic sessions to explore lessons and best practices. Identify ways to apply these lessons to projects and account for their use. Ensure that all relevant IPs engage actively together for cross-learning opportunities.	PT Advisors and IPs	Accepted	We will introduce lesson-sharing sessions with IPs for strategic topics. Although periodicity will not be very frequent, we have identified common cross-cutting topics from which IPs can learn from each other, such as adaptation to virtual contexts, what works best on G&I, best practices on beneficiary engagement, what are SBs and how do we work towards them, good practices on climate and environment, etc.
Assess project status 6–12 months before conclusion to create project sustainability plans. This includes identifying and bringing to bear project principals as well as UK-related assets (such as DIT, UK supply chain, local beneficiaries and delivery partners). This may include assessing IP capacity and interest to take projects forward after PF.	Head of PF, PT Advisors, IPs	Accepted	With support of the EL Team, the PT started actioning this recommendation with a workshop to learn and apply a useful and structured methodology to advance sustainability plans and prioritised actions between projects close to an end. With this methodology, each advisor will contribute to create strategic sustainability plans and implement them at an adequate scale.
Review the ToC and logframes (intermediate outcomes, G&I level of ambitions, VfM indicators, nesting/structure, assumptions) to ensure that these frameworks are strong tools.	Head of PF and PT Advisors	Accepted	This is another recommendation towards which the PT has started to take action. A four-hour workshop was dedicated to revisit and adjust the Programme level ToC to make sure it better served the purpose of telling the programme story. The PT will continue working to simplify current logframes.
Evaluate the VfM scorecard to optimise all aspects of Colombia programming. Use the findings from the VfM scorecard and available EL support to identify and take action on identified weaknesses to move the Colombia programme into a uniformly ‘good’/‘green’ score in future evaluations.	Head of PF and PT Advisors	Accepted	The PT has already taken initial action towards this recommendation, together with the EL team, during the revision of the Umbrella ToC and Logframe session. The team also reviewed available and recommended VfM indicators to embed within logframes. The Head of the PF and the Advisors will identify and action further actions on specific findings on VfM that can contribute to improve our score from adequate to strong.
Undertake actions which will enable the PF to translate the positioning for SBs into actual wins. This includes learning from other PF teams, linking better with DIT, developing bespoke SB strategies within projects, and mapping the supply chains of project against DIT priorities.	Head of PF, PT Advisors, DIT, HMA/SRO	Accepted	The PT has also started to take action towards this recommendation. A workplan was agreed with DIT in December 2020, and committees on infrastructures and agriculture have been created to enhance the work between the PF and DIT in these areas. The PT will continue to strengthen collaboration with DIT to maximise its opportunities to secure SB wins during the last year of implementation.
Review the programme and strand/activity ToCs, including review of assumptions and revise causal pathways as needed in light of the events of 2020 – COVID-19 and the Spending Review.	PT and IPs	Accepted	This recommendation relates to a previous one and will be taken into account simultaneously. The PT received information on the results of the spending review and final allocation on 22nd April. Before this, in order to understand better the impact of Covid-19 in Colombia, the PT commissioned a research piece with K4D Facility. This will be considered, together with any further information available to date, to review activity level ToCs.
Review the ‘nesting’ of the strand/activity ToCs into the umbrella ToC and consider a more direct transfer of intermediate outcome to intermediate outcomes and so on to equalise results across the different frameworks.	PT	Accepted	As mentioned in a previous recommendation, the PT has started to take action on this. A four-hour workshop was dedicated to revisit and adjust the Programme level ToC to make sure it served the purpose of telling the programme story. One of the things achieved during the workshop was to decide a better way to represent the programme, without using the previous nested approach.
Enable indicator analysis over time. While active use of indicators is useful in VfM delivery, it should not come at the cost of losing the ability to compare across time. Continue reporting on the old indicator or explain the link to the new indicator to allow this type of comparison and analysis.	PT Advisors, IPs	Accepted	The PT will take into account this recommendation and will advance its review of the Programme level and activity level logframes to simplify without losing key information and without changing indicators (instead it will try to reduce its number and migrate some of the activity level indicators to the programme level). The PT will keep the programme’s Output level indicators to maintain analysis overtime.
Build a more systematic approach to SBs, including increasing collaboration across PF, DIT and other relevant departments.	PT, DIT and SRO	Accepted	For this recommendation, please see above a comment related to working closely with DIT. Work with other relevant teams is already taking place and will continue to, as opportunities emerge.
Create plans to ensure that any unanticipated absences can be covered with existing resources. Thin staffing margins in the PT risk delays or gaps in programme implementation.	PT	Rejected	The PT structure was created in a way which allowed for a lean team in Colombia, as IPs would have a strong role in implementation. Although some capacity building to fill gaps has been necessary, at this point IPs will be able to continue implementing ongoing projects even in the unanticipated absence of a Team member.
Catalogue the COVID-19-related adaptations and innovations generated by project delivery partners to incorporate explicitly the responses that yielded positive results and address those responses which detracted or delayed project progress.	PT, IPs and suppliers	Accepted	Although not in a systematic way, the PT has knowledge of the adaptations and innovations generated to adapt to Covid-19. In one project, a systematic documentation (by the EL Team) has already taken place to capture the experience of beneficiary engagement in times of Covid-19 using technologies and innovations. This case will be shared with other IPs and its format is a good starting point to advance with cataloguing other adaptations.
Request that meeting times are rotated to ensure direct participation of all programmes over time to strengthen the ability of PF Colombia to align itself with the overall PF network.	PT, PFDU and JFU	Partially accepted	Due to changes within FCDO, neither PFDU nor JFU will continue to exist. Nevertheless, the PT will try to action this recommendation under the new governance structure.
Request EL support to strengthen its connection to the PF network by organising informal sessions with sector experts, PELs from other bilateral or global programmes and other technical experts to exchange views and ideas on selected topics.	PT and EL	Partially accepted	Due to changes within FCDO, the contract on EL has been terminated. Nevertheless, the PT will try to action this recommendation under the new governance structure.
Prioritise learning by investing one day each quarter to explore current challenges, celebrate progress and exchange lessons across programme principals.	SRO and PT	Accepted	This will take place once a quarter within the already existing monthly meeting with the SRO, and as a stand-alone feature of the PT.
Extend learning sessions to include other embassy sections, perhaps through the new cross-post group that HMA is launching in December 2020.	SRO and PT	Accepted	The new Post Programme Board will play a key role on disseminating learning. Its roles and responsibilities are in a design process.
Consider building learning and reflection into job descriptions and make appropriate time allowance to meet those expectations.	SRO and Head of PT	Partially accepted	The Post Programme Management Board and the already existing L&D Committee will promote learning activities and make sure that all staff, including the PT can dedicate time to learning activities.