## Annual Review - Summary Sheet

Title: / Global Anti-Corruption Programme
Programme Value: £45million		Review Date: Nov 2020
Programme Code: / GB-GOV-50-PF-07-ACO (including GB-GOV-3-PF-ACO-921; GB-GOV-3-PF-ACO-912; GB-GOV-3-PF-ACO-913; GB-GOV-3-PF-ACO-911)	Start Date: Some project transitional activity started in April 2017 but the full programme started in December 2018 following Chief Secretary to the Treasury approval in October 2018	End Date: March 2022

Summary of Programme Performance
Year	2018[1]	2019	2020
Programme Score	U	A	A
Risk Rating	U	Moderate	Moderate
[1] A pre-programme annual review was undertaken of transitional project activity in August 2018, but the programme log frame was not reviewed as it was not fully developed at that point in time.

Summary of progress and lessons learnt since last review
The programme is now in is its second full year of delivery. Seven of the nine projects, originally in scope for the programmes are mobilised and delivering outputs. Following recommendations from the 2019 Annual Review the EITI project was removed. The behavioural sciences project was postponed owing to ODA cuts. One new project, ‘Transforming Procurement Systems’ was designed this year but will not deliver outputs until 2021.
The programme is delivering intermediate outcomes and outcomes, with outcomes 1 and 3 exceeding most milestones. These include several anti-corruption legislative reforms, grand corruption law enforcement actions, and stolen assets recovered. There remains no baseline outcome indicator to assess if the project is achieving its goals at outcome level in raising awareness. Delivery against the output targets is mixed. Most met or exceeded their goals, but some have not been met. Considering the impact of COVID and ODA reprioritisation, the programme did well to meet so many of its output targets.
The programme’s theory of change is valid, with the log frame and programme architecture aligned to it. Work has continued to develop the log frame, update milestone indicators and add data sources. Some of this work was delayed due to capacity issues in the programme team so work is planned to continue developing the log frame, especially in light of the new project planned to begin next year. It would be worthwhile to continue reviewing the theory of change as the log frame develops to ensure it remains valid.
Regarding the value for money (VfM) position, the programme is on track to deliver good value for money in line with the Business Case. Good performance at the outcome level, top-level adherence to budget limits in a turbulent year, and broad compliance with the Business Case delivery models, provide a strong VfM narrative. Opportunities for improving the programme’s VfM offer come down to demonstrating impact level results, thinking through sustainability, and improving coordination in its five priority countries. On Equity, attempts are being made across the programme components to integrate gender equality and social inclusion (GESI) issues in line with GACP’s G&I Approach paper and Business Case commitments. The programme log frame gives a basis for monitoring work on GESI. Output indicators 4.1 and 4.2 direct delivery on a number of new knowledge products (e.g. reports/workshop outputs) to build GESI awareness in relation to anti-corruption as well as a number of new actions to become more aligned with the Prosperity Fund’s G&I standards (e.g. workshops, collecting disaggregated data, plans etc.). The biggest risks to the programme’s VfM delivery are the continued dependence on strong political will, and the geographically disparate nature of the workstreams.
List of recommendations for the next year
- By the end of February 2021, the GACP programme team should re-examine the feasibility of creating a baseline awareness score for outcome 4 using the 'community of experts’ and review whether there will be sufficient funding available to create the data needed to review against the baseline in subsequent years. Alternative approaches to assessing outcome 4 should be considered.
- By the end of March 2021, the GACP programme team, should reconsult with strategic partners, and review log frame milestones for accuracy and ambition. Many targets were over achieved in both 2019 and 2020. GACP should re-consider the 2019 recommendation of using indicative ranges if uncertainty is too high on deliverables.
- By the end of March 2021, the GACP team, in working with delivery partners, should develop sustainability plans for each project, and table a paper to the GACP Strategic Board for consideration.
- FCDO SDA support should be retained and augmented. Consideration should be given to pooling G&I specialist expertise so that not all delivery partners and programme components need to hire their “own expert”.
- By June 2021 carry out the planned output-based cost analysis study to better benchmark costs.

SRO Commentary
I am happy to sign off this annual review which has been undertaken by an independent multi-disciplinary team who have taken considerable time and effort to understand this complex programme.  Like many programmes, GACP has had to remain flexible this year both to absorb in year budget cuts and to respond to the Covid-19 pandemic.  It has done that well and the programme is now better focused as a result.  I strongly support the annual review’s focus on sustainability of elements of the programme, as ODA resources will be spread considerably more thinly in the coming year.  I am supportive of the recommendations for the programme contained in this review but these should be taken forward in the light of likely reprioritisation due to constrained ODA resources.
JFU Commentary
We welcome the conclusion of this annual review and endorse its recommendations. We note the strong progress the programme has made in maintaining delivery in a challenging context. Particularly noteworthy is the continuing pace of work on beneficial ownership registers, broadening of IACCC partnerships and the mobilisation of new programming responding to corruption issues in C-19 related emergency procurements. The review also raises important areas for improvement that we fully support, including raising ambitions within the results framework to better capture quality of delivery and strategic intent. We note limited progress from the programme’s last annual review on the cultivation of synergies between GACP projects, and between GACP and the broader FCDO portfolio, and would urge the team to take forward this recommendation over the coming review period, particularly in the context of the merger and creation of FCDO.
List of Acronyms
AML	Anti-Money Laundering
ASEAN	Association of Southeast Asian Nations
BenOwn	Beneficial Ownership
BODS	Beneficial Ownership Data Standard
CTF	Counter-Terrorist Financing
DFID	Department for International Development
DIT	Department for International Trade
EA	East Africa
EU	European Union
EGPS	Extractives Global Programmatic Support
EITI	Extractives Industry Transparency Initiative
FATF	Financial Action Task Force
FCDO	Foreign , Commonwealth and Development Office
GACP	Global Anti-Corruption Programme
GDMP	Global Digital Marketplace Programme
GDS	Government Digital Service
GFAR	Global Forum on Asset Recovery
G&I	Gender and Inclusion
HMT	Her Majesty’s Treasury
HMG	Her Majesty’s Government
IACCC	International Anti-Corruption Coordination Centre
IFFs	Illicit finance flows
IRG	Implementation Review Group
JACU	Joint Ant-Corruption Unit
JFU	Joint Funds Unit
LF	Log Frame
MLA	Mutual legal Assistance
MoU	Memorandum of Understanding
MREL	Monitoring, reporting, evaluation and learning
M&E	Monitoring and evaluation
NCA	National Crime Agency
ODA	Official Development Assistance
OECD	Organisation for Economic Cooperation and Development
PF	Prosperity Fund
SAM	South America and Mexico
SEA	South East Asia
SOEs	State Owned Enterprises
SRO	Senior Responsible Owner
StAR	Stolen Asset Recovery Initiative
ToC	Theory of Change
UNCAC	United Nations Convention Against Corruption
UNODC	United Nations Office on Drugs and Crime
VFM	Value for Money
WB	World Bank
	Cross Whitehall

## A. INTRODUCTION AND CONTEXT

DevTracker Link to Business Case:	https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/854188/Global_Anti-Corruption_Programme_Business_Case.odt
DevTracker Link to Log frame:

Introduction
The FCDO-led Prosperity Fund Global Anti-Corruption Programme deploys £45m over 4 years to promote inclusive sustainable growth and increase global prosperity through tackling corruption. The programme consists of projects delivered bilaterally, regionally and globally. The programme prioritises activity in five out of the twelve Prosperity Fund priority Middle Income countries: Colombia, Indonesia, Malaysia, Mexico and South Africa. The programme directly delivers on UK commitments made at the London Anti-Corruption Summit in 2016 and supports the delivery of the UK’s Anti-Corruption Strategy.
The objectives of the programme are to:
- Invest in introducing new policies, laws and regulations as well as strengthen existing ones.
- Increase transparency across the public sector, on beneficial ownership and procurement systems.
- Strengthen the ability to investigate and recover stolen assets.
- Raise awareness of the causes and impacts of corruption, taking into account G&I considerations.
- Identify, apply and disseminate good practice approaches.

The Annual Review covers the period August 2019 to July 2020. The review team undertook interviews with the HMG programme management team, HMG project managers and advisers (DFID, FCO, GDS, HMT and NCA), delivery partners, HMG staff at Posts, and beneficiaries/stakeholders from partner governments.
Context
The outbreak of the COVID pandemic at the start of the financial year has brought significant challenges and opportunities for the Global Anti-Corruption Programme (GACP). COVID highlighted the increased importance of anti-corruption work, especially in relation to the vast and rapid procurement exercises undertaken by countries across the globe. The circumstances also created significant opportunities for the GACP to amplify its impact. The pandemic has brought with it a significant increase in demand for anticorruption activity and reforms across many countries, particularly within the 37 countries of the UNODC ‘fast-tracking UNCAC’ project. The GACP has been able to capitalise on some of this increase in political will.
The programme responded by designing new activity within the original scope of the programme that also reflected on the previous review recommendation to more effectively build strong synergies between projects that were already in place. The new project, titled ‘Transforming Procurement Systems (TPS)’, was designed to respond to the immediate needs of the pandemic and a ‘building back better’ approach for the medium term. The TPS project is a collaborative effort between the UNODC, Open Contracting Partnership, Open Ownership, and complemented by the GDS project. It is intended to make more ambitious reforms under UNCAC than before the pandemic, including beneficial ownership and open contracting. It will ensure the entire procurement process is fairer and more transparent. The project will work with Mexico, Indonesia, and South Africa as a pilot.
Covid19 meant a rapid adjustment for the programme team. Members of the programme team were temporarily redeployed for urgent COVID activity, meaning for part of the review period the programme team was operating at significant under capacity. This has had an impact on delivery of some of the more ambitious plans to develop the results framework and maintain consistent communication with some delivery partners and posts. The subsequent reduction in ODA budget led to the termination or deferral of several strands of activity.
Delivery partners were challenged to rapidly switch to a more virtual setting. Much of this was done efficiently and smoothly (for example the redesign by the OECD of the Integrity conference to a virtual format), but some activity including capacity building by IACCC and GDS scoping missions could not be conducted virtually. At the local level, COVID meant that some partners, at least in the short term, reprioritised their resources away from GACP projects. Despite some delays, it appears little momentum has been lost.
Overall, the programme demonstrated its dynamism in responding to COVID-19.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment (Primary Purpose)
With one exception the programme is on track for delivering against the existing indicators for the three defined outcomes. There have been delays in developing outcome level indicators for outcome 4 and a risk that the concept to develop a baseline is no longer viable. Interviews with government stakeholders confirm that tangible results are being delivered. It is likely that for some of the projects the most impressive results are likely to be seen outside of the delivery lifecycle. The programme’s theory of change (ToC), log frame (LF) and gender and inclusion (G&I) approach set out how inclusive growth, poverty reduction and gender equality are central to the programme. Each project delivers across the four outcomes to differing degrees and there is some risk that highly effective projects may prop up less effective projects at the outcome and output level.
Outcome One – improved policies, laws and regulations on anti-corruption (StAR, UNCAC, FATF projects): Of the three planned outcome milestones, two were met and one exceeded. Considering the disruption from COVID in the second half of the review period this is impressive. The current milestones for this outcome are focused on structural or legislative change. There is no indicator to measure the extent to which these structural changes are implemented, a factor necessary to have an impact on the levels of corruption. Now the programme is seeing a number of these changes, the programme should consider the viability of an additional outcome level indicator to measure implementation.
For the intermediate outcomes indicator (Number of countries with strategic documents in place to assist creation/improvement of AC policies, laws and regulations as a result of programme support), all three milestones were exceeded and one significantly. The updated IO indicator (countries demonstrating commitment to improve or adopt new anticorruption policies, laws and regulations) shows positive progress in developing clear measurable targets for the programme, moving away from more intangible measures such as ‘political commitment’.
Outcome Two – increased use of transparent systems (BenOwn, Extractives, GDMP projects): The one planned outcome milestone (2.2 - number of companies on the global register), was missed. The delivery partners and programme team are developing a new indicator for outcome 2.2. This is to reflect a change in strategic direction to focus on the quality of registers instead of the global register. The change was agreed in conjunction with the programme and that took place mid-way through the reporting period. The outcome milestones does not yet reflect this pivot.
For a second year there was no planned milestone for outcome indicator 2.1 (Number of openly competed procurements run on new or improved systems in priority countries). The programme is now mid-way through its funding cycle and from interviews with stakeholders it appears likely that measurable results will fall outside of the funding cycle. The programme should review the effectiveness of how GDS prioritises activity to deliver at the outcome level.
For the intermediate outcome (Number of countries which have established national company beneficial ownership registers and/or contributed to the global register, Number of countries with on-line systems for disclosure of EITI data, Number of procurement systems positively impacted), one was exceeded, and two missed. EITI was removed from the programme this year, so intermediate outcome 2.2 should be removed from the log frame. Further work should be done to define specific criteria for how IO 2.3 measures ‘positively impacted’ so IO 2.3 can be better differentiated from output 2.1.
Outcome Three – increased success of anti-corruption law enforcement action (StAR, IACCC projects): Of the three outcome milestones, two were significantly exceeded and one met. For the intermediate outcome (increased number of anti-corruption investigations), one target was achieved and two (both IACCC) were exceeded. Although direct attribution is difficult to determine (given the number of actors and factors outside of delivery partners control), there is currently no disaggregation between cases where StAR and IACCC played a minor versus significant role. It is recommended that the log frame is adapted to disaggregate cases with differing levels of contribution.
For the intermediate outcomes (Number of new cases opened with potentially recoverable and tangible stolen assets, Number of additional intelligence disseminations from the IACCC), the three milestones were exceeded, two by a significant amount. It is worth reflecting on whether the IO indicators for the IACCC are sufficiently challenging in the next review period.
Outcome Four – increased awareness of the causes and impacts of corruption including G&I; and knowledge and application of good practices/approaches to address corruption in priority countries (OECD, StAR, BenOwn, FATF, UNCAC projects): This was planned to be the first year the programmes would be assessed against outcome level indicators outcome 4. The planned creation of a baseline awareness score in 19/20 using a 'community of experts' was delayed in part due to staff redeployment on urgent COVID activity. It recommended that the work to develop outcome indicators and milestones is urgently undertaken by the programme. There would also be value in the programme developing a secondary outcome level indicator focusing on innovation.
The evidence base for ‘what works’ and how it can be measured on corruption is nascent - especially at the outcome and impact level. Measuring success against existing indicators such as the CPI, at least in the short term, could wrongly lead to certain activity being judged incorrectly –for example a fall in the CPI could mean increased awareness of corruption due to more cases coming to light instead of corruption getting worse.
Many of the projects in the GACP include a form of innovation in anti-corruption programming. Outcome 4 does not fully capture where successful innovative practices contribute towards the wider evidence base. More work could be done by the programme team to share best practice with the global anti-corruption community. An additional outcome indicator under outcome 4 to measure the success of the programme in driving innovation and best practice could be beneficial
For the intermediate outcome (increased understanding of the causes and impacts of corruption and good practice approaches), performance is mixed. For some projects evidence is not collected in a manner compatible with measuring against indicator milestones. This makes it difficult to judge if projects (especially the OECD) are delivering against targets. G&I is reviewed in detail in the main body of the text. However, it is recognised that the inclusion of a G&I metric as an intermediate outcome is an effective tool to create accountability
Annual outcome assessment (Secondary Purpose: new economic opportunities for international, including UK business, and mutually beneficial economic relationships)
There are early indications that some programme strands have been successful in generating soft power wins. In Malaysia, the UK was awarded an Anti-Corruption Award 2019, by the Malaysian Anti-Corruption Commission. This reflected the help the UK had provided particularly through the law enforcement, beneficial ownership and asset recovery programmes. In one state, following a successful case involving returning seized assets, the President saw the UK "as its most important international partner on anti-corruption". It also led to an increased potential for Overseas Direct Investment (ODI), with a couple of companies stepping up interest in investing in the country recently, which will in part be down to a more stable and transparent government. The IACCC has also been incorporated into UK plans and deliverables for G7 and G20, which show cases UK leadership in Anti-Corruption (and has been designated a distinct pathway to generating secondary benefits).
Out of all the strands the Beneficial Ownership and GDMP programmes have the greatest potential for significant secondary benefit wins and soft power impact. These strands have seen good early progress in Mexico and South Africa. In Mexico, the UK has been recognised for its support to Ministries of Public Administration and Finance. In South Africa the UK has been instrumental in helping the National Treasury establish a spend data and conflicts of interest dashboard, thus assisting their efforts in beneficial ownership.
Interviews with partners demonstrated a mixed level of awareness when assessing the potential for secondary benefits. The programme team were unable to implement the strong secondary benefit narrative, as plans to hold more thematic based workshops with partners were derailed because of the ODA review and pandemic. The IACCC have been quick to assess some of their more significant achievements as soft power wins and having the potential to improve the business environment, whereas other partners such as FATF and StAR displayed less awareness (with StAR not having the capacity to assess any impact on the business environment). It is recommended that work should continue with implementing partners to enable them to recognise secondary benefits in the next reporting cycle. However, the team implemented the recommendations of the December 2019 Readiness Report to include all six types of secondary benefits, including ODI (which is recognised above), in the Theory of Change.
Overall output score and description
The four outputs are examined in detail in the main body of the report. It has been a challenging year to deliver against the four outputs, not all output indicators milestones have been fully met. Nevertheless good overall progress has been made against the four outputs.
Key lessons and recommendations from the last review
Of the five programme level recommendations from the 2019 Annual Review, two have been fully met, two partially met, and one has not been met (but is planned and will start in 2021).
- Undertake detailed analysis, to further realise synergies within the programme – Review of synergies resulted in the design of the joint UNODC, GDS, OO and OCP ‘Transforming Procurement Systems’ project
- Review log frame milestones for accuracy and ambition – The programme team has put significant amount of resource into updating the log frame, but this is only partially complete.
- Facilitate a review of the comparative VfM – The VFM review is planned and will commence in 2021.
- Review whether the Extractives project would be better managed solely by DFID - EITI was removed from the programme in 2020
- All project leads and partners should ensure access to gender and inclusion expertise; and that G&I is fully embedded into reporting, project level implementation plans and delivery –Delivery partners have improved access to G&I expertise and strengthened reporting, with a new output indicator created in the log frame to incentivise projects’ G & I approach and delivery

Summary of changes to the log frame since the last annual review
The programme team has devoted significant resource to working with delivery partners and MREL experts to review the outcome and output level indicators and data sources within the review period. The work to review the log frame is still ongoing, due to slight delays created by the limited staffing capacity the programme team had in 2020.
At output level
- Output 2 changed the indicator from ‘no. of additional countries which have established national company beneficial ownership registers and/or contributed to the global register’ with ‘no. of government data publishers implementing BODS including DfID priority countries and EITI member countries’. It was agreed this milestone was not the best measure of OO's work; it mostly measures the overall implementation of BOT whether OO have been involved or not. It was also agreed that the indicator for outcome 2 should be updated, but an alternative was not agreed in the review timeframe.
- In output 2, following recommendations from the 2019 Annual Review StAR and IACCC increased their milestones.
- There was an agreement to increase the indicators for OECD under output 4, but this was delayed owing to COVID.
- New output indicator created in the log frame to incentivise projects’ G & I approach and delivery

## C: DETAILED OUTPUT SCORING (1 page narrative per output)

Output Title	Improved assessments of country level anti-corruption systems and associated provision of technical support
Output number per LF		1	Output Score	A
Risk:		Minor	Impact weighting (%):	15%
Risk revised since last AR?		N		N

	Indicator(s)	Milestones	Progress
1.1	Number of FATF regional bodies/ member supported to: / I) carry out quality AML/CTF assessments / II) improve knowledge of how to comply with FATF standards	25	37. Mozambique/ Egypt/ Tanzania/ St Lucia/ Sierra Leone/ Belarus/ Uruguay/ Mali/ Benin/ Serbia/ Albania/ Honduras/ Nicaragua/ Peru/ Tunisia/ Kyrgyzstan/ Jordan/Eswatini/ Paraguay/ South Africa/ Nigeria/ Georgia/ Tonga/ Congo/ Ethiopia/ Madagascar/ Uganda/ Mauritania/ Morocco/ Grenada/ Philippines/ Mongolia/ Pakistan/ Myanmar/ Ukraine / Cameroon/ Egypt.
1.2	Number of technical assistance packages delivered to countries/ regions.	24 / SEA – 4 / EA – 9 / SAM – 8	47 / SEA - 11: Beneficial ownership: 2 (Malaysia Myanmar); Procurement: 2 (Indonesia Vietnam); AC Law: 1 (Timor-Leste); AC Policy: 1 (Cambodia); Penal code guidelines for judges: 1 (Vietnam); Liability of legal persons: 1 (Indonesia), and, Regional events: 3 / EA – 12: Procurement: 3 (Rwanda, Tanzania Uganda); Whistleblowing: 4 (Burundi, Tanzania, Uganda Kenya); Financial Investigations: 2 (Tanzania Kenya); Regional events: 3 / SAM – 15: Mapping/baselining: 8; Public integrity: 2 (Bolivia Ecuador); Corporate compliance: 3 (Peru, Ecuador Colombia), and Whistleblowing: 2 (Mexico Colombia). / SAF – 9: Regional event:
1.3	Number of concrete inputs into key global asset recovery events.	10	20 / StAR day at the Conference of the States Parties to UNCAC; UNCAC Implementation Review Group (IRG); Annual General Meeting of AR Inter-Agency Network Pacific ARIN-AP; Regional workshop as part of the 15th principles of meeting of South East Asia parties against corruption (SEA-PAC); 29th Asia-Pacific Economic Cooperation (APEC) Anti-Corruption and Transparency Working Group; INTERPOL Anti-Corruption and Recovery Global Conference; International Law Institute Anti-Corruption Seminar; American Bar Association Section of International Law Annual Conference; Civil Society Forum for Asset Recovery; CARIN Annual Meeting; UN FACTI; UN Global Compact Leaders’ Summit; 11th Session of the Implementation Review Group (IRG) of UNCAC; Inter-sessional meetings in preparation of UNGASS; FATF Recommendation (24 Project); Continued Meetings on FATF Recommendations (24 Project); Transparency of Beneficial Ownership to support Business and Investment; Enlisting Gatekeepers in the Fight Against Corruption (PACI Spring Meeting); ARIN Network Meetings, and OAS Department Against Transnational Organized Crime - XLVIII Group of Experts for the Control of Money Laundering.

Key Points

This output is covered by three projects. Implementing the United Nations Convention against Corruption (UNCAC) (implemented by UNODC), Strengthening Anti-Money Laundering Systems (FATF) and Supporting the Global Recovery of Stolen Assets (StAR), all of which have significantly exceeded progress against the milestones. However, milestones were significantly exceeded in the last reporting period, yet have not been updated. This indicates that the target forecasting is too low so the overall performance of the programme against output 1 is A.

Strengthening Anti-Money Laundering Systems (FATF): The project has produced national assessments of anti-financial crime measures, including efforts to tackle corruption, has improved the quality of these assessments and their recommendations, helping reports to be completed and published on time. The 37 FATF assessments completed closely match the 39 delivered last year. Given this consistency, the Programme is encouraged to increase the target next year. Delivery primarily focussed funding FSRBs to provide quality assurance support to Mutual Evaluation Reports and Follow up Reports (FURs). The milestones (measuring quantity of assessments supported) may benefit from better reflecting the extent to which the project is successful in impacting the quality of assessments and knowledge sharing interventions (for example, the Egyptian training in February, or expansion of FATF’s mentoring programme to Central Africa [GABAC]). It is recommended that the FATF/AML project component establish mechanisms to track these additional metrics by June 2021.

The programme’s FATF work, itself focussed on domestic compliance with anti-financial crime standards, provides a clear diagnosis, and remedial action plan, which benefits other components of the GACP and the broader international effort. The programme effectively supported all FSRB Secretariats in their COVID-19 response, notably in planning for new and emerging risks and potential policy responses for concerned members.

Implementing the United Nations Convention against Corruption (UNCAC): This workstream enables UNODC to support member states’ to address actions required for UNCAC compliance, and this year focussed on South America, Eastern and South Africa and South-East Asia. Delivery out-stripped the intended result by two-fold, indicating that this year’s target was not sufficiently stretching. The geographical spread of the results are indicative of UNODC’s strong global reach, and the substantive focus of the support packages provided (whistleblowing, procurement reform, investigative capability etc.) demonstrate good progress towards UNCAC compliance in the concerned countries. However, the results recorded in the log frame do not clearly articulate the extent to which support genuinely helped states to progress on the policy/law under consideration. Although more detail on contribution is captured in change stories it is recommended that UNODC work with the programme team to establish a metric in the log frame to demonstrate the value added of their intervention to the Member States by June 2021.

Supporting the Global Recovery of Stolen Assets: This output concentrates on StAR’s work to make sure that asset recovery is an important consideration for global change-makers, generally at inter-country fora convened by the UN, and aligns well to StAR funding provided by DFID under its I-ACT programme. StAR’s input to regional and global events also helps to ensure that there is common understanding with regards to asset recovery, helping to make processes more compatible. The 20 results delivered are a reduction on last year’s 27, possibly explained by StAR’s re-definition of what constitutes a concrete input. Either way, delivery significantly out-strips the 8 results forecasted. Following last year’s AR recommendation, StAR requires a contribution to be substantive (leading/moderating a panel, contributing to preparatory documentation, or convening a side meeting), a welcome improvement. StAR’s inputs are intended to ensure that there is common understanding of asset recovery, but the indicator does not currently track improved understanding – for example, whether change makers leave StAR meetings more capable or not. As with indicator 1.2, there is concern that the indicator tracks an input, rather than the quality of the input (as measured by how it is received/understood), and it is recommended that the StAR project component amend its indicators/milestones by June 2021 to track improved understanding of asset recovery attributable to its interventions.

Summary of responses to issues raised in previous annual reviews (where relevant)
A FATF/AML recommendation that output/outcome indicators/milestones be revised was taken forward by the programme team in a workshop in March, but improved indicators/milestones were not forthcoming. This Annual Review is repeating this recommendation.
StAR was encouraged to better define ‘concrete inputs’ to guide levels of assistance. This recommendation was appropriately actioned. The programme team encourages enhanced collaboration between StAR and concerned HMG missions regarding the content of StAR’s interventions.
Recommendations
1. FATF/AML to establish mechanisms to track both the quality of assessments and of knowledge sharing interventions by June 2021, in addition to the quantity of interventions.
2. UNODC to establish a metric to demonstrate the value added of its interventions to Member States and the laws/policies under review, by June 2021.
3. StAR to amend its indicators/milestones by June 2021 to track improved understanding of asset recovery attributable to its interventions.

Output Title	Research undertaken and plans established to implement transparent systems.
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	40%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of new procurement system developmental phases completed in target countries, disaggregated by country and region.	Mexico – 5 / Indonesia – 5 / Malaysia - 5 / South Africa – 5 / Colombia – 3 / TOTAL = 23	Mexico: 3 / Indonesia: 2 / Malaysia: 4 / South Africa: 6 / Global: 1 / TOTAL = 16 / Mexico: Secretaría de Hacienda y Crédito Público (SHCP) 'Better procurement platforms' Project: / Mexico City State Government digital agency and finance secretariat (Agencia Digital de Innovación Pública - ADIP / Secretaría de Finanzas - SAF). Open contracting data'. Project / Jalisco State Government innovation team and public administration (Coordinación General de Innovación Gubernamental - CGIG) and Secretaría de Administración). A discovery in Jalisco produced a set of proposed projects to begin delivery / Indonesia: Jabar Digital Service (JDS). 'Building capability and capacity'. Project: / LKPP. 'Better procurement platforms'. Project: / Malaysia: Digital Penang (Penang State Government). A discovery in Penang produced a set of proposed projects, the highest priority of which have been selected to begin delivery / Smart Selangor Delivery Unit (SSDU). 'Building capability and capacity'. Project / SSDU and the Treasury Office of Selangor State Government: A discovery in Selangor produced a set of proposed project, which have been paused / South Africa: National Treasury - Office of the Chief Procurement Officer (OCPO ‘Digital Delivery in Government’ training workshop. / State Information Technology Agency (SITA). 'Better procurement platforms' knowledge sharing. / Gauteng Provincial Treasury. 'Better procurement platforms’ User journey mapping sessions for the platform. / Department of Public Service and Administration (DPSA). ‘Digital Delivery in Government’ training workshops. / National Treasury – OCPO. 'Open contracting: Spend data and conflicts of interest dashboards. / South African Local Government Association (SALGA). Project: COVID-19 Response and Recovery Hackathon; / Global: Value-chain mapping of procurement functions 'Wardley' maps of procurement functions across all GDMP countries, strategic recommendations for GDMP and stakeholders, and internal capability building
Number of countries receiving technical/ financial support for the development of EITI BO roadmaps, commodity trading approaches, and undertaking mainstreaming activities that go beyond the EITI minimum standard.	Cumulative: / BO – 11 / CT – 8 / Mainstreaming – 10 / TOTAL = 29	BO – 12 / CT – 15 / Mainstreaming – 21 / TOTAL = 48 / BO: 12 total (4 additional countries). support to Ghana, Liberia, Mexico, Zambia and further support Armenia, Kenya, Nigeria & Ukraine and light touch support to BO reforms in Canada, Chile & UK Overseas Territories ). They have also supported the Financial Intel Unit, National Bank, and civil society. BO - All countries have a road map, / CT- 15 cumulative total (8 additional) (Argentina, Indonesia, Iraq, Democratic Republic of Congo, Malaysia, Mozambique, Nigeria, Seychelles, Cameroon, Mongolia, Papua New Guinea, Tanzania, Ghana, Chad and the Republic of Congo ) / Mainstreaming -21 cumulative, 4 extra Mainstreaming feasibility studies have been completed in Ghana, Nigeria and Liberia. Studies are underway in Myanmar and Tanzania and more are planned in Ethiopia, Ghana, Malawi Mozambique, Sierra Leone and Zambia.
Number of additional countries assisted with high-intensity to open registers.	4	4: Ghana, Liberia, Mexico and Zambia

Key Points
There has been significant success against this output, however COVID has led to a disruption of work and some targets have not been achieved. Of the three output indicator milestones, one was met, one was exceeded and one missed. It is likely that COVID impacted on the output 2.1 milestone being missed (target was 23 and 16 delivered). The indicators of output 2 could better reflect work done in legislative developments and awareness building, currently not fully used as evidence of progress on transparency and where success appears considerable. The programme team have started to develop new indicators for output 2 to reflect this and the new transforming procurement systems project created as a response to the COVID pandemic in 2020. Following the recommendation from the 2019 Annual Review EITI stopped receiving GACP funding in 2020. Next year output indicator 2.2 will have zero milestones. We recommend Output indicator 2.2 is revised to create a new milestone that reflects the broader impact the programme and new ‘Transforming Procurement Systems’ project have on transparency.
Supporting Global Digital Marketplace Platforms (GDS)
GDS has learnt through the programme how it can develop an international presence. Its “discovery missions” have served well in understanding local context as well as the role that can be played by local counterpart agencies who know the local politics and sensitives in establishing open procurement platforms. Effective collaboration in Mexico and South Africa has benefited following the arrival of locally recruited programme staff who have worked well with FCDO staff to establish a beachhead on this agenda. In Mexico, both the Secretariat de Hacienda y Crédito Público (SHCP) and the Secretaría de Hacienda y Crédito Público (SHCP) have used journey mapping sessions and user-centred design (UCD) to support the team building the procurement platforms. Working directly with local and national government agencies fully taking into account the local context has resulted in UK being Mexico’s Development Partner of choice to work in the complex environment on this agenda—which is impressive.
In South Africa GDS work with the National Treasury - Office of the Chief Procurement Officer (OCPO) promises major advancement of open contracting on the African continent. Several interventions are already underway at the State Information Technology Agency (SITA), the Gauteng Provincial Treasury, the Department of Public Service and Administration (DPSA) which suggests that bringing them and others together (e.g. work being done by the International Budget Partnership) may allow for a greater push for country wide open procurement. The move to promote open contracting at the local government level through the South African Local Government Association (SALGA) is further evidence that multiple entry points opened by this work. We recommend further consolidation over the last two years of this programme to ensure their sustainability.
Open Ownership (OO)
Work on national registers for beneficial ownership has started in four countries of Ghana, Liberia, Mexico, Zambia and further support Armenia, Kenya, Nigeria and Ukraine. For the developing countries these undertakings are likely medium term to achieve fully established registers. It is heartening to hear that since Jan 2020, the EITI International Board has agreed to assess countries’ compliance with beneficial ownership disclosures requirement, as part of their validation process.
 However, the degree to open ownership are connected with wider efforts for open contracting is not yet fully clear. The new project concept ‘Transforming Procurement Services’ devised by the GACP in 2020 may provide this connectivity but it is recommended that this is reviewed by the GACP to establish whether further connectivity with open contracting is possible within this programme and bilaterally with FCDO country offices (at least in Ghana, Nigeria, Kenya and Zambia) and their wider PFM and/or governance programmes.
It is remarkable that even under the constraints of COVID crisis, the programme has been able to work to understand the mainstreaming possibilities for 4 additional countries, resulting in cumulative 21 countries already underway in mainstreaming beneficial ownership. We recommend that mainstreaming feasibility studies completed in Ghana, Nigeria and Liberia should be shared with FCDO country offices to explore wider support and disseminating progress. Collaboration with EITI in Ghana, DRC and Nigeria is commended (with some question as to why EITI has been discontinued as part of this programme given the natural degree of complementarity of respective work with studies already underway in Myanmar and Tanzania and more are planned in Ethiopia, Ghana, Malawi Mozambique, Sierra Leone and Zambia.
Summary of responses to issues raised in previous annual reviews (where relevant)
A G&I-sensitive understanding of the procurement space was needed by GDS who were recommended to develop a clear forward work plan and communications on visit plans and objectives. Following this, GDMP commissioned Oxford Insights to carry out research on mainstreaming gender and social inclusion in ICT procurement, but further information is needed on how this will be used
Following the recommendation for the GACP strategic board should consider if it would not be more effective and efficient for DfID alone to be the sole HMG partner for delivering in the extractives sector, EITI was removed from the programme before the start of FY 20-21.
On Beneficial Ownership, GACP were recommended to explore the scope for prioritising GACP countries, considering political will and commitment to action. In conjunction with DfID, JACU and OO, GACP were recommended to agree plans on how users can make best use of the database to ensure the transparency impact of registers is being realised. Following COVID-19, the Transforming Procurement Systems project was developed. OO will be working with Open Contracting Partnership and through UNODC’ platform framework to support the governments in Indonesia, Mexico and South Africa across the procurement process of medical equipment and services. These are three of the GACP priority countries.
Recommendations
1. Output indicator 2.2 should be revised to create a new milestone that reflects the broader impact the programme and new ‘Transforming Procurement Systems’ project have on transparency.
2. GDS need to develop sustainability plans in the five priority countries to ensure relationships and momentum are not lost at the end the last two years of this programme
3. GACP should review whether there is sufficient connectivity between beneficial ownership and open contracting within the GACP, bilaterally with FCDO country offices (in Ghana, Nigeria, Kenya and Zambia) and their wider governance programmes.
4. Open Ownership would benefit from conducting mainstreaming feasibility studies in Ghana, Nigeria and Liberia which should be shared with FCDO country offices to explore wider support and disseminate progress

Output Title	Increased international capacity to undertake AC investigations
Output number per LF		3	Output Score	A+
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
Number of IACCC deployments and case-specific partnerships with other anticorruption organisations and initiatives.	6 (by March 2020)	12 deployments to affected states
Number of new referrals into the IACCC	95 (cumulative)	103 referrals received
Number of delegations received by IACCC	90 cumulative	93 country delegations hosted
Number of IACCC members	10	17 (including Interpol and eight new associate members) Isle of Man, Jersey, Guernsey, Gibraltar, Cayman Islands, Turks & Caicos, Mauritius, Seychelles
Number of IACCC cases involving co-ordination of multiple jurisdictions	2	7 (cumulative)
Number of scoping visits carried out by StAR	2-3	2 = Zimbabwe and Sudan

Key Points
This output is covered by two projects: Supporting the Global Recovery of Stolen Assets (implemented by StAR) which has achieved its milestone, and Co-ordinating International Intelligence Sharing on Grand Corruption (IACCC), which has exceeded five milestones. IACCC and StAR are still over-achieving their milestones, despite setting higher targets for the review period (by up to 15 to 20%). The programme may need to come up with a new rationale for setting more realistic targets. However, challenges in doing so remain, due to the complex nature timescales for pipeline cases and sensitivities around the programme’s activities. As all three intermediate and outcome milestones have either been achieved or exceeded, this is scored as ‘A+’.
Co-ordinating International Intelligence Sharing on Grand Corruption (IACCC).
Between Aug 19-July 20 IACCC froze £65m of assets, supported a domestic restraint order in an affected state to the tune of $330m, and Evidence secured by IACCC was used to prosecute a former head of state and a criminal summons served by IACCC on Financial institution brought a $3.9billion settlement.
The IACCC also formally launched the ‘Women against Transnational Corruption Hub’ (WATCH) in February 2020, a network for female prosecutors, investigators and other women involved in anticorruption work. The WATCH network aims to strengthen anti-corruption responses by empowering women working in anticorruption across the world. The head of the NCA, Lynne Owens supported the launch. It also commenced a partnership with DFID funded UKCA MLA drafting project to align support with the judicial side of a corruption investigation not in the mandate of the IACCC.
In July 2020, the IACCC launched a new Associate Membership Scheme, allowing law enforcement agencies from smaller financial centres to join the IACCC as associate members. Associate members can exchange intelligence with the IACCC to assist with the development of the intelligence picture on grand corruption cases and help IACCC support partners across the world with grand corruption investigations, including the facilitation of mutual legal assistance requests (MLA’s). The launch of the scheme brings the number of members and associates members of IACCC to 17.
Some programme elements suffered because of the pandemic. Intelligence gathering continued, but IACCC benefit from delivering training and maintaining and developing close personal relationships with affected countries. Lack of activity risks slowing progress on cases and referrals. However, IACCC foreign law enforcement partners continue to show commitment to the centre. The travel ban has been particularly challenging in countries where there are no HMG funded in country advisers, and the team have cancelled three courses since February.
In terms of target countries, IACCC maintain strong links in Africa, and there is evidence of achieving objectives outside the traditional areas of the programme (e.g. soft power wins). They are working hard to expand their influence in South America and have signed an MOU with Interpol for the latter to join the IACCC, which should lead to better future engagement in the region. In one country, IACCC are negotiating two MOUs, so they can start to share information and are helping with further cases in 3 other countries. There are some indications the programme is achieving secondary benefits, including recognition by one state of the UK as the most trusted partner in anticorruption. IACCC work in another country also contributes significantly to the UK receiving an anticorruption award.
StAR Stolen Asset Recovery Initiative
StAR achieved their target on scoping visits (Sudan and Zimbabwe), but others were curtailed because of the pandemic. The team supported Zimbabwe to investigate and prosecute financial crime and corruption cases, through technical and virtual training session on asset recovery for officials from the Zimbabwe Anti-Corruption Commission in June. The team also reviewed Sudan’s daraft AC law and provided inputs on sections related to asset recovery. This supported an important priority of Sudan's transitional government of "fighting corruption and recovering stolen assets" (which is included in the country's new Constitutional document).

Summary of responses to issues raised in previous annual reviews
The previous annual review recommended the programme seek 'further integration’ to help maximise the overall impact of the programme', investigate future funding options for the IACCC to ensure the sustainability of their operations' and 'review future year targets to assess whether they are ambitious enough'. On the second point, the IACCC already receives a certain degree of funding by the members. Further options are being explored for external assistance, through the Riyadh initiative in Vienna, a G20 initiative which aims to create a global operational network of anti-corruption law enforcement authorities and further assistance through the US INL.
Output Three Recommendations
1. StAR/IACCC: to further investigate opportunities to work with StAR on programme synergies and avoid duplication to help maximise the overall impact of the programme.
2. IACCC: to pursue small, individual cases (e.g. property) with countries as a way of building relationships, where it has been traditionally hard to get a foothold.
3. StAR / IACCC: Continue to review future year targets to assess whether they are ambitious enough.

Output Title	Gathering and disseminating new evidence of anti-corruption good-practice.
Output number per LF		1	Output Score	A
Risk:		Minor	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
Number of new knowledge products (e.g. reports/ workshop outputs) created (including G&I and Behavioural Science).	49 / StAR – 2 / UNCAC – (SEA 1, EA 9, SAM 3, SAF 1) / OECD – (1 ACI forum, 1 Auditors Alliance, 1 SOE Governance conference, 1 regional workshop in SEA, 3 national workshops Indonesia, Malaysia, Vietnam, 3 national and 1 regional stocktake reports on AC compliance) / FATF – 15 evaluation reports completed / Open Ownership – 6	TOTAL = 53 / StAR: 1 Going for Broke: step by step guide on asset recovery practitioners on the use of insolvency proceedings in recovering corruption proceeds. / UNCAC: 10 / SEA: 3, review frameworks for transparency of Beneficial Ownership; analysis of oversight mechanisms for COVID expenses A; study on digital data and AI / EA: 4, Survey on COVID19 oversight ; regional handbook on anticorruption in public procurement; Library of best practices for whistle-blower protection ; report on regional workshop for financial investigations / SAM: 1, Survey of COVID19 oversight mechanisms / SAF: 2, Outcome document of the regional conference to launch the regional platform for Southern Africa. Survey of COVID19 oversight mechanisms / OECD: 4. / State Owned Enterprise meeting 2019. published a detailed summary record of the 2019 SOE Network meeting on OECD`s web site / OECD organised the 10th Asia-Pacific Anti-Corruption Regional Conference Combatting Corruption in Infrastructure projects. The event brought together 60 participants from 15 countries. / The Anti-Corruption and Integrity Forum 2020 held as webinars due to COVID-19. Registration for all webinars was 4,144 participants, from 120 countries. 64% of speakers were female / Drafted, consulted, and launched the Anticorruption and responsible business conduct survey for southeast Asia. 400 Southeast Asian companies/business entities were approached and 229 responses received. / FATF: the 26 evaluation reports completed this year are being counted here, plus nine other activities (reports and workshops) listed below. / Delivered one Joint Assessor Training workshop where 39 candidates were trained: / CFT training course for 38 trainees / CPF training course for 34 trainees, / 22 candidates of FSRBs were trained: / Two online seminars on newly revised FATF Standards on Virtual Assets. 66 trainees from all nine FSRBs Secretariats attended / FATF/FSRB workshop on common challenges in the ME process, / The FATF Secretariat published a paper on COVID-19 related ML and TF risks and Policy Responses members and hosted two follow-up webinars / online training course on the drafting and using of scoping notes for FSRB secretariat staff working 29 trainees from all 9 FSRBs
Number of instances when projects have taken steps to become more gender and inclusion aligned (e.g. workshops, collecting disaggregated data, plans etc.).	9	TOTAL = 22 / IACCC: 6 / 1. Workshop on interconnection between corruption and gender, director of University of Sussex Centre of Corruption / 2. Designed WATCH (Women Against Transnational Corruption Hub) a network aimed at strengthening anti-corruption response by empowering and enabling the women who are working in the field across the world. / 3. NCA DG launch WATCH at Women’s Criminal Justice conference / 4. Sent out a survey to WATCH in July 2020 to understand the challenges members faced. / 5. IACCC reviewed the M&E spreadsheet to disaggregate data on suspects by sex, age and geographical location, recording the no. of women in delegation, recording the no. of women attending their trainings, recording the no. of female investigators in partner agencies’ teams / 6. G&I action plan finalised. / GDMP: 7 / Research and report by Oxford Insights on GESI progress within partner countries. / Penang, Malaysia – discussions have led to Digital Penang actively working with them to encourage accessibility standards for different social groups. / Jabar Digital Service (JDS) - 3 workshops delivered to JDS colleagues on how to do user research. greater appreciation from JDS to engage different users and social groups for user research and improve service design. / JDS = had not previously heard of inclusive design. / South Africa – encouraged use of standards to encourage accessibility in ‘ICT clearing house’ design / Malaysia, Smart Selango Delivery Unit – following a senior delegation visit to the UK requested accessibility training afterwards. / Mexico ADIP Mexico City – introduced the Mexico City government to user centred design techniques / UNODC: 6 / Identified G&I entry points within each thematic area from all 4 regional outcome documents. This has helped to identify potential programmatic activities to target. / Gender desk review of countries that are a part of the Southeast Asian Regional platform. Examining ways to reflect gender elements in draft guidelines on “protecting WB in the health sector”. / Drafting TORs to hire an expert consultant for additional experience and gender expertise. / Delivered a presentation on the linkages between gender and corruption to participants of the Regional Conference for the launch of the Southern African Regional Platform / Commenced research to explore the gendered dimensions of corruption. Published “integrity and gender equality as agents for change – exploring the gender dimensions of corruption’. / OECD: 2 / Gender-related questions in SE Asia Anti-Corruption and Responsible Business Conduct Survey, May-July 2020. Survey found that nearly two thirds of respondents report that their business does not have a gender-focussed internal policy or gender-sensitive reporting mechanism. / Strong relationships with civil society regular info exchange, invitation to speak at the OECD GAC forum, Asia Pacific AC regional conference and circulation of the survey in civil society’s networks. / Behavioural Science: 1 the research grant call for bids specified the need to include an impact assessment on G&I. G&I expertise was assessed when evaluating the bids. / StAR and OO regularly involve civil society in meetings/ workshops.
Number of behavioural science phases	6	2 – The OECD were appointed to carry out research in Colombia and completed a preliminary report.

Key Points
This output is covered by OECD, FATF, StAR and UNODC. Of the 3 indicator milestones, two were exceeded and one was missed. A significant amount of work was put in in 2019 to carry out a commission for behavioural insight grants, however this funding was subsequently cut in the ODA prioritisation exercise. The milestone should be revised for the next reporting period to reflect this.
On output 4.1, whilst the overall target has been exceeded, this is largely due to FATF’s result. All others have under-achieved, this is primarily due to the implications of COVID-19 which meant a lot of OECD activity was postponed and travel by UNODC was unable to go ahead. StAR have been working on several knowledge products but only one was completed and published during this time period. In the next year Open Ownership will be added to the indicator for output 4.1. They did however complete knowledge products during the review period covering: Verification; Principles of Effective BO disclosure and a BO visualisation system. Overall this outcome achieves an A.
OECD
Output 4 is the only output which the OECD funded work streams contributes towards, despite the fact that the GACP funds four different projects in the OECD. The programme team have indicated an intention to explore the wider value of the OECD work to the broader outputs and this should be prioritised - for example how the auditor’s alliance could contribute to corruption casework. Further work could also be done on identifying synergies between the state owned enterprises and responsible business work streams with the newly created ‘Transforming Procurement Services’ Project.
Broadly, there is a sensible logic in the OECD focusing on raising awareness. The OECD has developed some impressive standards and guidelines for anti-corruption. However knowledge and implementation of these standards is often been limited to OECD countries, limiting their effectiveness in impacting global corruption. As such focusing on raising awareness of these products to a wider OECD audience instead of creating new frameworks is a sensible approach. The Asia-Pacific Anti-Corruption Regional Conference Combatting Corruption in Infrastructure projects organised by the OECD with the UNDP, ADB and Government Inspectorate of Vietnam is a good example of this. Outcomes of the event included setting up a permanent business integrity network under the Asia-Pacific Anti-Corruption Initiative.
COVID had a significant impact on both the logistics for the OECD activities and funding. the OECD rapidly adapted their programming. Pivoting some activity to a virtual setting has created opportunities as well as risks. The Anti-Corruption and Integrity Forum 2020 was postponed and held as webinars in which 120 countries were recorded as attending. This is a broader audience than would have been able to attend an in person event. In the future the OECD should consider how messages from in person events can be shared online to maintain this engagement from the broader audience.
The quality of data on how the activities contributes toward the outputs and outcomes is mixed. For the state owned enterprises workstream the OECD embedded feedback in their programming and produced an analysis of feedback on network member priorities in October 2019 that were used in preparations for the next SOE Network meeting. The data collected on the value of the integrity forum was more limited, with only a small number of responses to feedback surveys. The OECD should also consider how to collect feedback from their activities in a more strategic manner to ensure that success is recognised in the log frame and to assist in the prioritisation of future conference subjects and formats.
Some value was created through the funding of an online portal and communication exercise to bring together disparate parts of the OECD who worked on subjects linked to corruption. Although there is value in bringing a range of OECD experts together, there is some question of whether external funding should be used for what could be business as usual activity.
StAR – StAR missed its milestone for output 4.1 to deliver 2 knowledge products. Work has also been ongoing on the data collection for international asset recovery cases between 2010-2019 and research on the victims of corruption and social damages, and another on the enforcement of foreign confiscations but these are not complete yet so cannot be counted as results for last year. The annual review agrees with the findings of the evaluation on the reprioritisation of StAR’s activity in the next financial year.
On the Gender and Inclusion output indicator some projects have taken several actions which has meant the programme has exceeded its target of nine actions. However, some are business as usual and cannot be viewed as instances of the projects taking steps to integrate G&I considerations and respond to opportunities to support women’s economic empowerment and transformative change. Further detail on Gender and Inclusion is in the Equity sub section of Value for Money (VfM) assessment.
Summary of responses to issues raised in previous annual reviews (where relevant)
Project leads must embed project level G&I action plans into measurement of their delivery success: gender and inclusion are included as a section on flash reports and projects know that it is counted as an indicator in the programme log frame.
Ensure project leads and delivery partners have access to their own G&I expertise and arrange additional G&I workshops with project leads/ delivery partners: some projects have sought additional expertise where necessary i.e. IACCC, UNODC, GDMP, however additional workshops have not taken place, largely due to COVID-19 and disruptions to work and staff (crisis deployment).

Recommendations
- By May 2021, the programme team should undertake a review of OECD led projects to identify how they can prioritise activity to maximise how they contribute towards overall delivery and create synergies with other GACP projects.
- By March 2021 the programme team should work with OECD to identify measurement metrics feasible for the OECD to report against and determine if/how OECD activity contributes towards broader outputs than output 4
- By May 2021 the output statement is reframed to reflect G&I focus and output style language

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (2 pages)

Key cost drivers and performance

The programme is in full delivery and spend for 2019/20 was £12,429,005 against a budget of £13,059,410, resulting in an underspend of £630,494. The main cost drivers were project delivery costs (partner staffing, expert technical assistance and events), cost drivers which are unlikely to change. 95.2% of the budget was spent. GDS (issues with financial forecasting and reporting) and FATF (did not proceed with a voluntary contribution) underspent. The review team was reassured by the GDS corrective action agreed on. Overall, this variance is considered small, with most components spending close to their budgeted allocations. In FY 20/21, programme forecasts an overspend of approximately £350k which both PFDU and JFU are comfortable with, the more so given the team’s good work in locating savings as part of the re-profiling exercise. In order to achieve significant calendar year and financial year savings, funding to some projects has been cut completely, notably StAR and Behavioural Science.  Funding to other projects was reduced: to UNODC (absorbed the shortfall) and OECD (struggling to prioritise and cover the shortfall in funding against their commitments).  Two XWH projects achieved the savings required: IACCC (by scaling back) and GOSAC (DFID/FCDO, by absorbing the shortfall). Both HMT and GDS have been unable to make the full savings but have made significant cuts to spend.

Financial year 19/20 outturn

Project Name (FCO) /description	Lead Dept	Budget 19/20	Total actual spend 19/20	Variance £ 19/20	Variance % 19/20
UK Based staff costs	FCDO	254,252	241,034	13,217	94.8%
Business case development[2]	FCDO	200,000	182,030	17,970	91.0%
Non staff admin[3]	FCDO	48,848	33,813	16,715	65.8%
OECD Organised Events	FCDO	5,000	5,000	0	100.0%
OECD	FCDO	917,813	917,813	0	88.0%
UNODC	FCDO	2,909,387	2,909,382	5	100.0%
StAR	FCDO	1,400,000	1,400,000	0	100.0%
Behavioural Science	FCDO	10,000	16,538	-6,538	165.4%
EITI Secretariat	FCDO	500,000	500,000	0	100.0%
Open Ownership	FCDO	1,147,742	1,150,963	-3,221	103.0%
GDS	GDS/CO	3,384,594	2,952,597	431,997	87.2%
IACCC	NCA	1,400,000	1,387,915	12,085	99.1%
FATF	HMT	881,774	731,920	149,854	83.0%
TOTAL		13,059,410	12,429,005	630,404	95.2%
[2] Costs associated with external consultants supporting the development of the Business Case and mobilisation of the programme, taken as a platform rather than a staff cost.
[3] Costs associated with travel and ad-hoc costs.

Programme Financial Profile
FY 17/18	FY18/19	FY19/20	FY20/21	FY21/22
£4.8m	£8.8m	£13.1m	£8m	£4.9m

The financial profile shows a rising spend up until FY19/20, sustaining a £2m increase in FY19/20 in comparison to the Business Case proposition, followed by a £3m drop in FY20/21. The programme managed the mid-2020 re-profiling exercise adeptly, using processes it will replicate if required to do so due to top-level ODA reductions.

VfM performance

The Cycle 1 Evaluation revisited the VfM scorecard in November 2020 and concluded that the October 2019 assessment holds. The programme’s direction of travel is ‘good’ for 2 metrics (efficiency, risk), adequate for 5, and limited for 1 (sustainability).

Economy. Cuts to the Behavioural Science project removed the one component not set up in line with the Business Case. The nature of intended results directs the programme towards government and multilateral partners. Consequently, and given the programme’s necessary absence of competitive tendering, the programme planned a cost management/benchmarking study which was curtailed by COVID-19. It is recommended this VfM study be implemented by June 2021 according to the established Terms of Reference. The majority of core funding (bar StAR) is ‘earmarked’ against specific outputs, allowing for an output-based cost analysis which both the 2019 VfM Scorecard and the 2020 Cycle 1 evaluation recommend.

Total HMG programme admin costs were £502,474, representing 4% of total spend, within the PF’s 5% margin. The programme team expects HMG staff costs to average out slightly below the 4.6% estimated in the Business Case (this excludes other admin costs). All delivery partners disaggregated their financial reports by delivery versus administrative costs (varying between 5% and 17%)[4], but multilaterals include all staffing costs within delivery costs. It is recommended the programme team analyse total administrative costs, including multilaterals’ staffing costs, by March 2021.
[4] The Business Case does not project appropriate percentages for disaggregated delivery partner spend, so a comparison is not possible.

Efficiency. The programme is complex, with four HMG departments managing nine components, yet the management model works.  COVID-19 and associated cuts impacted GDS, OECD (compounded by delayed decision making) and Behavioural Science results, likely to affect outcome-level attainment on procurement and transparency. The programme has the right level and capability of staff in place, with the majority of positions in the original design filled. The programme’s Global Head of Anti-Corruption oversees the programme and provides a valuable link across HMG anti-corruption policy. The addition of a locally engaged C5 in South Africa has generated clear efficiencies, and it is recommended the programme propose options for generating enhanced country-level coordination in the other 4 priority countries by March 2021, mindful of top-level administrative/staffing costs. Following an efficiency recommendation last year, DFID/FCDO became the sole HMG department for delivering the EITI from April 2020; the programme team is encouraged to assess whether this has delivered the intended benefits.

Last year’s annual review highlighted inefficiencies arising from the lack of inter-project coordination, a challenge the programme team has, top-down, sought to remedy, but with limited returns. Coordination of multilateral activity, dispersed across the globe, remains hard to achieve but impacts on the programme efficiency. It is recommended that by June 2021 the programme team empower the five priority country HMG posts to coordinate design/knowledge sharing between delivery partners.

Effectiveness. Although the PF’s anti-corruption KPI is still being finalised, log frame changes (including upgrading targets) have enhanced the programme’s effectiveness. Some results continued to out-strip targets, suggesting ambition could still be upgraded. Changes to the Open Ownership indicator suggest the programme is appropriately re-appraising the ambition of indicators, and it is recommended that output indicators measuring inputs be replaced on the grounds of effectiveness by June 2021. It is unclear how COVID-19 – and the Programme’s reliance on electronic communication for meetings/workshops – has affected the effectiveness of delivery. The re-profiling exercise appropriately assessed projects based on both their cost and their value, ensuring that the more effective workstreams were preserved.

There are some strong signs of attributable attainment at the outcome level (asset recovery, law enforcement actions, for example), as well as a smaller number of outcome areas not delivered (awareness raising, for example), suggesting the current outputs are the right ones for delivering the outcomes, and that the ToC assumptions are holding. It is recommended that the programme identify impact level indicators by June 2021 to track the transformational consequence of its work. Outcome 2 remains too ambitious for GDS’s current activity, and will be addressed through the ongoing GDS deep dive. The risk register tracks ‘political will’ in one or two priority countries; it is recommended the programme team adjust the risk register by March 2021 to track political will in all priority countries.

The programme is delivering in line with the Business Case and is expected to deliver primary benefits of up to £212m. On secondary benefits, the Business Case estimated only £3m of commercial benefits, however interviews suggested considerable network benefits and political influence are being secured through the programme. It is recommended the programme team assess the impact of re-profiling exercises on expected benefits by June 2021.

GDS, Open Ownership, OECD, StAR and UNODC are active communicators of the programme, reinforcing the programme’s effectiveness. FATF and IACCC are less active in initiating outward facing comms, and appropriately so given the content of their work. The programme has been active via PFD’s LinkedIn pages (its core social media site) and Prospero.  Given the range of workstream interests, and in order to take full advantage of project effectiveness to date, it is recommended that the programme stand up a sustainability plan using VfM evidence to distinguish between work the UK should continue/discontinue beyond 2022, with contingency plans in place for exited work to ensure gains are not lost.

Equity
The PF Evaluation and Learning team’s G&I Scorecard, revisited in November 2020, scores the Programme ‘Amber’, consistent with this Review’s finding of adequate performance on VfM equity. On balance there is good evidence that the programme understands and tracks the equitable distribution of benefits, with scope to go further. It is assessed in the evaluation as meeting the minimum standard on G&I outlined in the PF G&I policy on two out of six dimensions – on Design and Results, highlighting areas for further attention.
Programme design	Internal capability/ institutional incentives	ACCOUNTABILITY MECHANISMS	FiNANCIAL RESOURCES	DELIVERY Partners	REsults	OVERALL Score
GREEN	AMBER	AMBER	AMBER	AMBER	GREEN	AMBER

Following the request by the SRO in the 2019 Annual Review, the 2020 Review looked at Gender and Inclusion with an increased level of scrutiny. Attempts are being made across the programme components and delivery partners to increase awareness of G&I and anticorruption linkages, and integrate good practice on gender equality and social inclusion (GESI). The original programme Business Case highlighted the need to consider the differential impacts of corruption and of programme interventions on men and women from different social groups, ensure ‘do no harm’, identify any risks and risk mitigation measures, as well as actively maximize opportunities to improve gender equality and women’s empowerment through proposed interventions. However despite FCDO-led G&I workshops, guidance shared and consultation with delivery partners on GACP’s early G&I Approach Paper in 2019, it was not sufficiently and systematically built into the detailed programme and project-level design, with some retrofitting taking place. Recent more in-depth evaluation of the programme underscores this even though adequate inputs are being made.
As highlighted in the Business Case, delivery partners are required to submit regular progress reports setting out progress against plans in relation to delivery on Gender Equality Act compliance and inclusion components. Delivery partners are encouraged by the programme team to provide regular reporting against G&I action plans, demonstrating efforts to hold projects to account on G&I. However the annual review agrees with the evaluation’s main recommendation calling for “review, update and agree G&I action plans to ensure that they reflect current project plans, particularly, with respect to any changes as a result of budget cuts or COVID-19 pivots”.
The programme log frame gives a basis for monitoring work on GESI. Outputs indicators 4.1 and 4.2 specifically direct delivery on a number of new knowledge products (e.g. reports/workshop outputs) to build GESI awareness and capacity (e.g. WATCH network) as well as number of new actions to Number of instances when projects have taken steps to build evidence and promote good practice on G&I and anticorruption for alignment with PF G&I minimum standards (e.g. G&I analysis and action plans, collecting disaggregated data, stakeholder consultation etc.). Progress against both output indicators have exceeded expectations—but it is the second that is more commendable and suggesting a springboard for more – with opportunity to integrate and mainstream these G&I activities across the related Log frame outputs (e.g. on international capacity building). In Indonesia the Jabar Digital Service (JDS) held 3 workshops on user research which resulted in greater appreciation from JDS to engage different users and social groups for more inclusive service design. In South Africa activities have encouraged consideration of standards to promote accessibility when designing their ‘ICT clearing house’ processes. Finally, the IACCC has designed the Women against Transnational Corruption Hub, aimed at empowering and enabling the women who are working in the field across the world. NCA DG helped to launch the network at the Women in Criminal Justice Conference in February 2020 in London which received positive feedback.

On wider stakeholder engagement, there is also significant evidence that partners are engaging more with civil society resulting in more shared analysis and inclusive participation across the board. For example Open Ownership has consulted civil society to interrogate data; OECD GAC regional conference forum has been used to exchange views with civil society including through more regular surveys (collaborating with networks like Transparency International, Indonesia Business Links in Indonesia, Coalition for business integrity in Malaysia and Coalition Against Corruption in Thailand).

Activities reported under output indicators 4.1 and 4.2 in the log frame show that the programme does in part meet the obligation highlighted in the original business case that “the programme’s indicators will include disaggregated results by gender, age and socio-economic group where relevant, in compliance with the Gender Equality Act (GEA)”. For example, IACCC reviewed the M&E spreadsheet to disaggregate data on suspects by sex, age and geographical location, recording the no. of women in delegation, attending their trainings, as well as the no. of female investigators in partner agencies’ teams. However, data disaggregation is required more consistently across the log frame for regular reporting.
The challenge for some partners, in part, is that the evidence base and expertise on GESI on Anti-Corruption work is still a developing field and this has been compounded by staff turnover (in part caused by COVID cuts). At the programme level, access to a Social Development Advisor to support on G&I was partly compromised by capacity constraints and redeployment on COVID-19 and ODA reprioritisation. We would therefore recommend that SDA support be retained and in fact augmented if this objective is to meet the expectations. There is considerable evidence that the programme teams have drawn on expertise from the FCDO SDA—whose various presentations at GACP and G&I Champions workshops has resulted in more attention being paid to GESI with improved monitoring frameworks and G&I Action plans being designed. The programme team, with support from the SDA, have commissioned additional specific evidence work via U4 on asset recovery/return and social inclusion.

However on delivery partner capacity, we concur with the evaluation that the delivery partners’ use of GESI experts is variable. Some like GDMP, IACCC, and UNODC are doing better than others like OO and OECD. This will be affected by the degree to which funding is prioritized amongst competing needs. Consideration should be given to pooling G&I expertise so that not all delivery partners and progamme components need to hire their “own expert”. Indeed, such pooling will create more opportunities for collaboration across teams capturing synergies. In some cases the decision to conduct more local research and thereby use of local expertise shows promise. For example the GDS decision to commission an extensive study on Gender Equality and Social Inclusion (GESI) in ICT public procurement with country cases in Indonesia, Malaysia, Mexico, Colombia, and South Africa assessing country-specific barriers and opportunities for greater inclusion. The discontinuation of the Behavioural Science project may have removed the programme’s main opportunity to fill evidence gaps on G&I, but other options seem to be emerging. The UNODC has commenced research and drafting of a dedicated publication - titled “Integrity and gender equality as agents for change – exploring the gender dimensions of corruption”.

It is not clear how the projects assess and track G&I sensitivity within the interventions and work products developed (for example laws/regulations [outcome 1), to show they are working with governments to pro-actively think through the disproportionate impacts of corruption and inequitable systems on excluded groups. OECD’s example is one method of how to do this; whereby an OECD survey shed light on the absence of gender-focused internal policies/reporting mechanisms within two-thirds of businesses surveyed, and OECD is developing programming which responds to this. This gender sensitive approach goes beyond efforts to ensure equitable representation at events, in order to seek longer-term transformative change. StAR’s proposed research on how returned assets benefit disadvantaged groups is also on point. Building on these good examples, it is recommended that delivery partners demonstrate assessment of G&I impacts and incorporate a more progressive and ambitious approach to G&I into their project design by June 2021.

Following last year’s review, delivery partners are tracking inclusive representation in meetings and events. OECD, TPS, StAR and UNODC are including civil society voice at events, UNODC and GDS are earmarking funds for G&I work, and UNODC, OECD, GDS and IACCC are engaging more G&I expertise to improve the equity of their offer. It is recommended the programme-level LF and programme-level G&I Approach paper/Action Plan better track the positive G&I narrative (beyond outcome 4 which is tracked) by March 2021.

Assessment of whether the programme continues to represent value for money

The programme is on track to deliver good value for money in line with the Business Case. Good performance at the outcome level, top-level adherence to budget limits in a turbulent year, and broad compliance with the Business Case delivery models, provide a strong VfM narrative. Opportunities for improving the programme’s VfM offer come down to demonstrating impact level results, thinking through sustainability, and improving coordination in its five priority countries. The biggest risks to the programme’s VfM delivery are the continued dependence on strong political will, and the geographically disparate nature of the workstreams.

Quality of financial management

The FCDO internal financial reporting tool OBIEE is used to scrutinise FCDO spend, and to report the monthly spend/forecasting to GPST, PFDU and the programme SRO. A more high-level RAG-rated financial breakdown of spend is provided to the Steering Group and Strategic Board.  The programme team receives quarterly financial reports from multilateral delivery partners and commissions and scrutinises monthly financial actuals and forecasting provided by XWH project leads. Some issues have arisen with XWH forecasting and the reporting of actual spend by GDS (see above).  The programme team continues to liaise closely with project leads to ensure high quality, accurate and timely reporting.  A comprehensive record of monthly expenditure by project is maintained by the programme team.  The Multilateral delivery partners are well established partners in the anticorruption field and pose low risk to delivery.  Invoices are checked against deliverables and audit arrangements are covered by standard internal FCDO audit mechanisms.

## E: RISK (1 page)

Overall risk rating: Moderate
Overview of programme risk
The overall risk rating for the programme as a whole is classed as ‘moderate’. Three risks are classed as ‘major’ in the risk register, but they appear to have thorough a comprehensive mitigations to manage the risk. Most outputs are in the control of the programme team and the delivery partners. There are more factors and interdependencies at the outcome level which are beyond the control of the programme.
The programme team maintain a risk spreadsheet covering both project and programme risks. All XWH project leads are required to formally report on risks in their monthly flash reports and a more detailed assessment quarterly which updates the programme spreadsheet and in turn Prospero. The risks are highlighted to the Steering group (at quarterly meetings) and to the Strategic Board (at bi-annual meetings). Overall a lot of thought has gone into examining the broad range of risk the programme faces. . Both programme and project risks are covered along 4 categories (operational, fiduciary, delivery, safeguarding). Risks are regularly reviewed and mitigations have been designed to consider multi-pronged approaches to improve the resilience of these mitigations. Where delivery is taking place at the local level there could be a benefit in increasing the involvement of post in overseeing and contributing towards the regular review of risks. For some country specific risks, it may be of benefit for posts to be the risk owner.
There are lower priority risks in the register related to political will in specific countries. Interviews with beneficiaries suggested that this was also a risk for countries not captured by the risk register. The risk register should expand this risk to cover all countries where bilateral delivery is taking place and update regularly
There are 19 risks in total. They are RAG rated according to severity and the top 7 are listed below:
Programme and Project team staff are deployed to Crises – mitigated by - Monitor the potential need for staff deployments, across Projects and Programme and communicate this to FCO team, along with an assessment of the impact of this on projects/programme work. Utilise temporary staff as needed

Project activity and expenditure over FY 2020-2021 affected by COVID-19 – mitigated by - Undertake a COVID-19 risk management exercise across all projects to determine impact of COVID-19 on project delivery this f/y and beyond. Review responses and extract financial data to support proposals to pivot funding and/or secure additional funding for new COVID-19 project.

OECD do not join up with the many active donors, Posts, institutions and partners working in business integrity in SEA – mitigated by - OECD are currently mapping the donor landscape before commencing local activity and provide introductions to know donors undertaking related activity. Facilitated increased contact between OECD, UNODC, and posts.

Inaccurate forecasting by XWH delivery teams - underspend ranging from £2k - £500k – mitigated by - Regular engagement with XWH project leads. GACP SRO write out to SRO counterparts in XWH project teams seeking their cooperation and high level overview of all monthly forecasting returns before submission to GACP and upwards.

XWH partners providing inaccurate spend figures that have NOT been extracted from Departmental management information systems – mitigated by - Flagged to portfolio manager and GACP SRO. Regular close engagement with XWH project leads, issue identified, and project colleagues advised to report GL figures. Further monitoring and escalation as necessary

Other donors withdraw their funding to StAR – mitigated by - We are currently the largest donor to StAR, however they had an external review conducted in 2019 which agreed that the managing committee should extend StAR for a term of ten years, including securing sufficient and sustainable levels of funding. Success regarding the recommendations will be measured by the review team but we will also closely follow their (and donors plans) to achieve this.

Due to the inherent nature of corruption which doesn't want to be measured, and the lack of publicly available evidence base; the programme is unable to robustly capture and demonstrate its impact – mitigated by - The programme is working with the FCO Economics Unit, PFDU/GPST and PF MREL contractors to create a robust monitoring and reporting a and VFM approach. Communities of experts will be created at Posts to help assess the impact of the programme and shape its evolution. The programme aims to inform the international evidence base on effective anti-corruption activities and measures. The programme has and will continue to access external experts (e.g. U4, OECD etc.) to inform and review our approach to data gathering and benefits.

Outstanding actions from the risk register
There are four outstanding actions from the risk register, three of which stem of Amber RAG rated actions. Two of these outstanding actions relate to the OECD run project. These outstanding actions should be prioritised as a matter of urgency.
- Regular check-ins to ensure that OECD are communicating with posts and other donors.
- Work on the OECD on financial reporting to ensure it is aligned with FCO requirements
- Check in with StAR progress on this during monthly calls and Review the situation prior to providing new funding in 2020
- Launch communities of experts in all priority countries

Recommendations

- The programme should look to increase the involvement of posts in priority countries to manage risks.
- The risk on political will should be broadened to cover all countries where changes in political will could impact delivery.
- The frequency of communication with the OECD on areas of risk should be increased to fulfil outstanding actions in the risk register

## F: COMMERCIAL CONSIDERATIONS (1 page)

Delivery Against Planned timeframe

The programme’s delivery has been significantly affected by the impact of the COVID-19 pandemic. Programme partners were also asked to make significant cuts as a result of the ODA reprioritisation exercise. All projects continued to deliver activity at a reduced pace. The programme team worked closely with project leads to explain the cuts and ensure reduced funding was targeted towards high priority activity.

The Evaluation noted progress against the GDMP programme as slow, but the main contributing factors to GDMP's success are related to government ownership and partners' capabilities. Progress would have been negatively affected by a re-orientation of procurement to the pandemic response in most countries. IACCC activities have been significantly reduced by the pandemic as the programme relies on delivery of training in person and developing close personal relationships, raising the risk of slowing progress on cases and referrals. Although work on programme synergy can be complex, there is scope for further work to reduce the risk of programme duplication, particularly between the IACCC and StAR.
PT communication with posts in priority countries are good, however it is not always consistent. It is recommended that GACP working closely with FCO posts and involving all delivery partners to ensure and/or demonstrate greater coherence and synergy across all GACP-funded activities.

Performance of partnership(s)
The key partnerships are between Whitehall partners (DFID, FCO, GDS, HMT and NCA), with individual delivery partners (e.g., OECD) and with partner governments.  The partnership between the programme team and partners is broadly effective, for example, through the Quarterly Steering Committee. The PT had planned to organised more standalone sessions with delivery departments on themes, such as including gender and inclusion and secondary benefits. However, a combination of the reprioritisation exercise and staff shortages as a result of the response to pandemic and limited staff resources and capacity reduced the ability to carry these out.
Change to Delivery
Following a broad PF steer, the programme was asked to re-orientate some of its activities to the COVID-19 response. This led to the launch of a new programme, Transforming Procurement Systems (TPS), which changed the scope of the Open Ownership strand. Due to the ODA reprioritisation, a decision was made to postpone the start of the Beneficial Ownership programme until FY 20/21. The 2019 review made a recommendation the GACP stop funding the EITI programme, and this was formally agreed by DFID and FCO in February 2020.

## G: BUSINESS ENVIRONMENT (½ page)

How has the business community and business environment responded to the programme?
There are early indications that the business environment is responding well to the programme. The OECD's Anti-Corruption and Integrity (ACI) programme has developed strong links with the business community by establishing a permanent business integrity work stream for SE Asia. In another state the business environment had improved to such an extent, that UK firms were in very preliminary discussions to re-enter the market, displaying the potential for significant ODI wins.

Out of all the strands the Beneficial Ownership and GDMP programmes has the greatest potential for impact with the business community. The latter also has political support (from No. 10’s Anti-Corruption Adviser). Open Ownership's work is increasingly recognised internationally and at least two large international business groups have openly recommended governments to adopt beneficial ownership registries. These include the B20, the official business community engagement forum for G20, which supported this initiative since 2013, and the World Economic Forum Partnership Anti-Corruption Initiative, who is the principal CEO-led platform in the global anti-corruption arena.

It has been challenging for the programme team implement recommendations to stimulate further response from the business community. This is mainly due to a re-prioritisation of activities to the COVID-19 response and staff shortage because of the pandemic. However, the team have advanced plans to generate business awareness through e.g. annual surveys involving business associations. The programme has made limited progress with its community of experts plan (group of experts, including local business representatives, to assess progress) plan because of the pandemic. However, an appropriate group of experts was identified and convened in Indonesia in Jan 2020.

The programme team has engaged with DIT and this is confined to DITs plan to establish a Business Integrity network, but at the time of writing the project is at concept stage. Over the next year, it is recommended the programme team can feed in information on activities, impact and development using the FCDO's Overseas Business Risk website, which includes information and advice associated with Anti-Corruption overseas for UK businesses. The team might also consider deepening synergies with relevant global programmes (i.e. Global Business Environment and Trade) in the relevant geographies, e.g. South Africa, Mexico and Indonesia.

(Where relevant) What role has non-ODA spending played in promoting programme objectives?
The programme has no non-ODA spend.
## H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
A comprehensive evaluation of the Programme is finalising its findings as of December 2020, covering the last two years since the Business Case was approved. The evaluation took a sample-based approach focusing on Eastern and Southern Africa and SE Asia, included interviews with 130+ stakeholders. The evaluation’s early drafts are generally positive about the Programme with solid pointers for next steps, future engagement and lessons learned.

During the period under review, the Theory of Change (ToC) was revised to more clearly reflect how G&I, secondary benefits and synergies are incorporated into the Programme; the Results Framework has been reviewed and revised accordingly.  Limited progress has been made in developing new evidence for the Programme due to the inherent difficulties in measuring anti-corruption activity and the impact of COVID-19. The Programme team began exploring a new streams of evidence through its Communities of Experts work, as outlined in section G, and the U4 Helpdesk. Though the inaugural meeting in Jakarta met with good engagement and optimism, further activity was put on hold due to COVID-19.  The programme team has worked closely with a Social and Diversity Adviser to ensure evidence and results are disaggregated to reflect G&I requirements aligned with the central MREL system, however as noted log frame reporting on G&I is restricted to Output 4.

Monitoring progress throughout the review period

Programme monitoring takes place through regular calls, monthly and quarterly reporting, and governance meetings. The programme continued to grapple with the challenge of measuring changes in corruption, particularly quantitatively. The optimism in last year’s review that the community of experts’ approach would help with these challenges was this year undermined by COVID-19 but remains a model worth pursuing in each of the programme’s key countries. Last year’s recommendation that key monitoring stakeholders across the programme/project team more regularly communicate has been actioned and has delivered some benefits, however, and as noted in the pending programme evaluation, it is recommended the programme team should stand up more frequent monitoring and GDS-type ‘show and tell’ calls with all stakeholders, including UK missions, in its priority countries, by March 2021.