## 2021_PNAs
Suggested indicative timeline for the development of the pharmaceutical needs assessment

Week		1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42	43	44	45	46	47	48	49	50	51	52	53	54	55
Governance	Invite stakeholders to join the steering group and set date of first meeting
	Steering group meetings to be scheduled in line with the group's wishes (suggested minimum meetings included)
	Timeline signed off at first steering group meeting.
	Board meetings (schedule board update reports as required)

Health needs and priorities	Obtain reference documentation eg needs assessments
	Obtain information on known housing development, regeneration projects or transport developments that are current or will occur within the lifetime of the pharmaceutical needs assessment
	Obtain any additional data
	Agree localities to be used at first steering group meeting
	Analyse data

Patient/public questionnaire	Agree patient/public questionnaire at first steering group meeting
	Upload questionnaire to online platform
	Promote questionnaire via the council's websites, communications channels and online presence, and via press release
	Questionnaire runs for four weeks
	Analysis of questionnaire responses

Current pharmaceutical services provision	Contractor questionnaires to be agreed at first steering group meeting
	Upload contractor questionnaires to online platform
	Contractor questionnaires open for four weeks
	Analyse responses
	Obtain dispensing data and advanced and enhanced services activity data
	Analyse and map service provision data

Synthesis and drafting	Draft overview, health needs, identified patient groups and patient/public engagement results sections of the pharmaceutical needs assessment
	Draft pharmaceutical services sections
	Undertake locality assessments
	Share first complete draft pharmaceutical needs assessment with the steering group
	Steering group to review the pharmaceutical needs assessment
	Steering group meeting to agree changes to the pharmaceutical needs assessment
	Incorporate comments from steering group
	Share final draft of consultation pharmaceutical needs assessment with steering group
	Submit consultation draft of PNAs to health and wellbeing board/committee/sub-committee for sign-off
	Pharmaceutical needs assessment signed off for consultation

Consultation	Consultation questions agreed
	Consultation documents drafted
	Liaision with council's communications teams
	Consultations run for 60 days
	Review consultation responses and produce first draft of consultation reports
	Consultation report shared with steering group
	Steering group to agree response to the consultations
	Pharmaceutical needs assessment finalised
	Final pharmaceutical needs assessment submitted to the health and wellbeing board
	Final pharmaceutical needs assessment signed off by health and wellbeing board
	Pharmaceutical needs assessment published by 1 October 2022