## Front_Sheet
Construction Framework 21 Handbook - Appendix A - Process Timelines

Process timelines for the framework procurement routes to support Framework Users and Contractors

## Document_Control
Construction Framework 21 Handbook - Appendix A - Process Timelines
Document Summary

Version History
Date	Editor	Version	Status	Reason for change
30-Nov-20	Ed Furse	v1.0	n/a	Updated to reflect changes to value band processes as set out in Framework ITT documents
09-Feb-21	Darren Kaley	v2.0	Draft	Further development to suit updated processes
19-Feb-21	Ed Furse	v3.0	Draft	To allign with changes to the Handbook
05-May-21	Ed Furse	v4.0	Final	Final issue for procurement
09-Nov-21	Ed Furse	v5.0	Final	Updates to the CEM process on Route A2, A3 Direct Award and Future School.

## HVB_-_ROUTE_A1
			Design and Build Competition Timeline

High Value Band Cost-Led D&B Competition / ROUTE A1 - HVB DEFAULT / (BATCHES AND SINGLE PROJECTS)		Approx. RIBA Stage	RIBA Stage 0 / (Strategic Definition)			RIBA 1 Preparation and Briefing (Feasibility Study)			RIBA 2 Concept Design					RIBA 2 Concept Design					RIBA Stage 3 Spatial Coordination					RIBA Stage 4 (Technical Design)					RIBA Stage 5 / (Construction)			RIBA Stage 6 / (Handover and Close Out)			RIBA Stage 7 / (In Use)
		Framework Stage				Feasibility Study (c16 Weeks)			Pipeline (4 Weeks minimum)					PITT to Contract Close: / 37 to 40 Weeks / Framework Users to draft realistic programmes based on project-specifics	Local Competition (c10 Weeks)					Design Development / (4 weeks)					Design Development Clarification Process / (2 Weeks)		Planning Submission / (3 Weeks)			Planning Determination (15 to 18 Weeks)					Contract Finalisation / (3 Weeks)				Construction			Handover and Defects Liability Period			In Use
								Preliminary Invitation to Tender (PITT) / (3 Weeks)				Invitation to Tender / (4 Weeks) / 2 BIDDERS					Evaluation and Appointment / (3 Weeks)					Contractor's Proposals (8 to 10 Weeks)					CPs Review (7 to 8 Weeks)
		Week				Week -22 to -6			Week -4	Week -3	Week -2	Week -1			Week 1	Week 2	Week 3		Week 4	Week 5	Week 6	Week 7		Week 8	Week 9	Week 10		Week 11	Week 12	Week 13	Week 14		Week 15	Week 16	Week 17	Week 18	Week 19	Week 20	Week 21	Week 22	Week 23	Week 24	Week 25	Week 26	Week 27	Week 28	Week 29	Week 30	Week 31	Week 32	Week 33	Week 34	Week 35	Week 36	Week 37		Week 38	Week 39	Week 40

		Stage Summary	Framework User agrees Business Case and Strategic Brief			Framework User prepares the Scheme to end of RIBA Stage 1 – including a Feasibility Study and costed control option / Indicative information will be published on the Pipeline			Framework User gives minimum of five weeks notice to DfE Framework Team who provide at least four weeks notice to Contractors / Framework User issues Feasibilty Study / design information via DfE Framework Team / Contractors return Expression of Interest feedback to DfE Framework Team					Bidders Day	Issue of PITT and response	PITT evaluation and shortlisting		CEM 1	CEM 2	CEM 3	Submission		Evaluation and Appointment of Selected Panel Member (SPM) under a PCSA		Sign PCSA		CEM 4	CEM 5	CEM 6	Submission		Framework User clarification process; review of Design Deliverables submission (including cost plan); leading to approval to proceed to planning submission		Preparation, submission and validation of Planning Application			Time allocation subject to expected planning determination period / As per Exchange Information Requirements / SPM sessions to continue to evolve decisions / design (includng resolving RDD matters)					CPs Submitted	Time allocation subject to expected planning determination period / Clarifications process run in parallel leading to approval of Contract CPs / GAPs calls to run in parallel leading to drafting of Contract Schedules / Update CPs to reflect planning decisions / Conclusion of Contract Schedules					Finalisation, agreement and signature of contract following planning permission

								Design Competition: Client Engagement Meetings (CEMs) leading to ITT submission of concept design strategies and responses to quality questions (expected to be 3 number CE meetings). / Tenders must be within the cost envelope set by the Framework User or the tender is non compliant.					Client Engagement Meetings (CEMs) leading to production of the Design Development Deliverables (circa 3 number further CE meetings) leading to approval to proceed to planning

								At least one week after Bidders Day, the Framework User invites Contractors to compete for the Scheme by issuing a Preliminary Invitation to Tender (PITT). / The PITT states the maximum number of Contractors be invited to the next stage – either one or two. / If part of a Batch, the PITT for the Sample Scheme will include named Future Schools.

		Key Documents (TO BE UPDATED ONCE DETAILED EIR IS FINALISED)				Feasibility Study (and associated appendices)			Scheme Notification Form					Information to be provided at PITT by Framework User / - PITT / - Qualitive Questions / - Pricing Questions / - Draft Invitation to Tender (ITT) / - Feasibility Study / Information to be submitted by Bidders / - Responses to Questions set / - Completed and signed Forms and Certificates				Information to be provided at ITT by Framework User / - ITT / - Qualititive Questions / - Pricing Questions / - PCSA / - Future Schools Notice and Agreement (if applicable) / Informaton to be submitted by Bidders / - Design and Construction Proposal / - Pricing Proposal / - Information required to complete the PCSA / - Completes Forms and Certificates					Information to be issued by Framework User / - Succesful Bidder Letter / - Unsuccesful Bidder Letter / - PCSA for execution / Information to be provided by SPM / - PCSA (signed)				Information to be provided by Framework User / - n/a / Information to be provided by SPM / - Design Development Deliverables					Information to be provided by Framework User / - Clarifications / Information to be provided by SPM / - Clarification responses		Information to be provided by Framework User / - n/a / Information to be provided by SPM / - Planning Submission			Information to be provided by Framework User / - n/a / Information to be provided by SPM / - Contractor's Proposals					Info to be provided by SPM / - Contractor's Proposals (final)	Information to be provided by Framework User / - Employer's Requirements / - Gaps List / - Draft Contract / - Contract Schedules / - Clarifications / Information to be provided by SPM / - Contractor's Proposals (final) / - Contract Schedules / - Clarification responses

		PCSA Payment Milestone						Payment Milestone 1 after CEM 4 (Week 11)					Payment Milestone 2 approval to proceed to planning (Week 17)					PCSA Milestone 3 at submission of CPs (Week 30) / PCSA Milestone 4 (Final for PCSA) at agreement of Contractor’s Proposals and Contract (Week 37)

## HVB_-_ROUTE_A2
			Design and Build Competition Timeline

High Value Band Cost Led Two Stage D&B / ROUTE A2 - HVB OPTION / (BATCHES AND SINGLE PROJECTS) / Two-Stage D&B		Approx. RIBA Stage	RIBA Stage 0 / (Strategic Definition)			RIBA 1 Preparation and Briefing (Feasibility Study)			RIBA 2 Concept Design					RIBA 2 Concept Design					RIBA Stage 3 Spatial Coordination					RIBA Stage 4 (Technical Design)					RIBA Stage 5 / (Construction)			RIBA Stage 6 / (Handover and Close Out)			RIBA Stage 7 / (In Use)

		Framework Stage				Feasibility Study (c16 Weeks)			Pipeline (4 Weeks minimum)					EOI to Contract Close: / 36 to 39 Weeks / Framework Users to draft realistic programmes based on project-specifics	Local Competition (6 Weeks)					Design Development / (c7 Weeks)					Design Development Clarification Process / (2 Weeks)		Planning Submission / (3 Weeks)			Planning Determination (15 to 18 Weeks)					Contract Finalisation (3 Weeks)				Construction			Handover and Rectification Period			In Use
								Invitation to Tender (ITT) / (3 Weeks)			Evaluation and Appointment (3 Weeks)					Contractor's Proposals (8 to 10 Weeks)					CPs Review (7 to 8 Weeks)
		Week				Week -22 to -6			Week -4	Week -3	Week -2	Week -1			Week 1	Week 2	Week 3	Week 4	Week 5	Week 6		Week 7	Week 8	Week 9	Week 10	Week 11	Week 12	Week 13		Week 14	Week 15	Week 16	Week 17	Week 18	Week 19	Week 20	Week 21	Week 22	Week 23	Week 24	Week 25	Week 26	Week 27	Week 28	Week 29	Week 30	Week 31	Week 32	Week 33	Week 34	Week 35	Week 36		Week 37	Week 38	Week 39

		Stage Summary	Framework User agrees Business Case and Strategic Brief			Framework User prepares the Scheme to end of RIBA Stage 1 – including a Feasibility Study and costed control option. / Indicative information may be published on the Pipeline / Alternate Option: Framework User has the option to develop the Scheme to end of RIBA Stage 2 or 3			Framework User gives minimum of five weeks notice to DfE Framework Team who provide at least four weeks notice to Contractors. / Framework User issues Feasibilty Study / design information via DfE Framework Team / Contractors return Expression of Interest feedback to DfE Framework Team.					Issue of ITT, Site Visit within one week and response / Alternate Option: This period may need to be extended to reflect the quanitity of design information Contractors must review / Tenders must be within the cost envelope set by the Framework User or the tender is non compliant.			Evaluation and Appointment of Selected Panel Member (SPM) under a PCSA.		Sign PCSA		CEM 1	CEM 2	CEM 3	CEM 4	CEM 5	CEM 6	Submission		Framework User clarification process; review of Design Deliverables submission (including cost plan); leading to approval to proceed to planning submission		Preparation, submission and validation of Planning Application / Alternate Option: If the Framework User has already completed RIBA Stage 3 and submitted a Planning Application, proceed to the next RIBA Stage			Time allocation subject to expected planning determination period / As per Exchange Information Requirements / SPM sessions to continue to evolve decision (includng resolving RDD matters)					CPs Submitted	Time allocation subject to expected planning determination period / Clarifications process run in parallel leading to approval of Contract CPs / GAPs calls to run in parallel leading to drafting of Contract Schedules / Update CPs to reflect planning decisions / Conclusion of Contract Schedules					Finalisation, agreement and signature of contract following planning permission

								Client Engagement Meetings (CEMs) leading to production of the Design Development Deliverables (circa 6 number CE meetings) leading to approval to proceed to planning

		Key Documents (TO BE UPDATED ONCE DETAILED EIR IS FINALISED)				Feasibility Study (and associated appendices)			Scheme Notification Form					Information to be provided at ITT by Framework User / - ITT / - Qualitive Questions / - Pricing Questions / - Feasibility Study / - PCSA / Information to be submitted by Bidders / - Responses to Questions set / - Completed and signed Forms and Certificates			Information to be provided by Framework User / - Succesful Bidder Letter / - Unsuccesful Bidder Letter / - PCSA for execution / Information to be provided by SPM / - PCSA (signed)					Information to be provided by Framework User / - n/a / Information to be provided by SPM / - Design Development Deliverables					Information to be provided by Framework User / - Clarifications / Information to be provided by SPM / - Clarification responses		Information to be provided by Framework User / - n/a / Information to be provided by SPM / - Planning Submission			Information to be provided by Framework User / - n/a / Information to be provided by SPM / - Contractor's Proposals					Info to be provided by SPM / - Contractor's Proposals (final)	Information to be provided by Framework User / - Employer's Requirements / - Gaps List / - Draft Contract / - Contract Schedules / - Clarifications / Information to be provided by SPM / - Contractor's Proposals (final) / - Contract Schedules / - Clarification responses

		PCSA Payment Milestone						PCSA Milestone 1 after CEM3 (week 9)					Payment Milestone 2 approval to proceed to planning (Week 16) / or approval to proceed with Contractor's Deliverables where no planning permission required					PCSA Milestone 3 at submission of CPs (Week 29) / PCSA Milestone 4 (Final for PCSA) at agreement of Contractor’s Proposals and Contract (Week 36)

## MVB_&_LVB_ITT_-_ROUTE_A3
			Design and Build Competition Timeline

Low + Medium Value Bands / Two-Stage D&B		Approx. RIBA Stage	RIBA Stage 0 / (Strategic Definition)			RIBA 1 Preparation and Briefing (Feasibility Study)				RIBA 2 Concept Design					RIBA 2 Concept Design					RIBA Stage 3 Spatial Coordination					RIBA Stage 4 (Technical Design)					RIBA Stage 5 / (Construction)			RIBA Stage 6 / (Handover and Close Out)			RIBA Stage 7 / (In Use)

		Framework Stage				Feasibility Study (c16 Weeks)				Pipeline (4 Weeks minimum)					EOI to Contract Close: / 36 to 39 Weeks / Framework Users to draft realistic programmes based on project-specifics	Local Competition (6 Weeks)					Design Development / (c7 Weeks)					Design Development Clarification Process / (2 Weeks)		Planning Submission / (3 Weeks)			Planning Determination (15 to 18 Weeks)					Contract Finalisation (3 Weeks)				Construction			Handover and Rectification Period			In Use
								Invitation to Tender (ITT) / (3 Weeks)			Evaluation and Appointment / (3 Weeks)					Contractor's Proposals (8 to 10 Weeks)					CPs Review (7 to 8 Weeks)
		Week				Week -22 to -6				Week -4	Week -3	Week -2	Week -1			Week 1	Week 2	Week 3	Week 4	Week 5	Week 6		Week 7	Week 8	Week 9	Week 10	Week 11	Week 12	Week 13		Week 14	Week 15	Week 16	Week 17	Week 18	Week 19	Week 20	Week 21	Week 22	Week 23	Week 24	Week 25	Week 26	Week 27	Week 28	Week 29	Week 30	Week 31	Week 32	Week 33	Week 34	Week 35	Week 36		Week 37	Week 38	Week 39

		Stage Summary	Framework User agrees Business Case and Strategic Brief			Framework User prepares the Scheme to end of RIBA Stage 1 – including a Feasibility Study and costed control option. / Indicative information may be published on the Pipeline / Alternate Option: Framework User has the option to develop the Scheme to end of RIBA Stage 2 or 3				Framework User gives minimum of five weeks notice to DfE Framework Team who provide at least four weeks notice to Contractors. / Framework User issues Feasibilty Study / design information via DfE Framework Team / Contractors return Expression of Interest feedback to DfE Framework Team.					Issue of ITT, Site Visit within one week and response / Alternate Option: This period may need to be extended to reflect the quanitity of design information Contractors must review			Evaluation and Appointment of Selected Panel Member (SPM) under a PCSA.		Sign PCSA		CEM 1	CEM 2	CEM 3	CEM 4	CEM 5	CEM 6	Submission		Framework User clarification process; review of Design Deliverables submission (including cost plan); leading to approval to proceed to planning submission		Preparation, submission and validation of Planning Application / Alternate Option: If the Framework User has already completed RIBA Stage 3 and submitted a Planning Application, proceed to the next RIBA Stage			Time allocation subject to expected planning determination period / As per Exchange Information Requirements / SPM sessions to continue to evolve decision (includng resolving RDD matters)					CPs Submitted	Time allocation subject to expected planning determination period / Clarifications process run in parallel leading to approval of Contract CPs / GAPs calls to run in parallel leading to drafting of Contract Schedules / Update CPs to reflect planning decisions / Conclusion of Contract Schedules					Finalisation, agreement and signature of contract following planning permission

								Client Engagement Meetings (CEMs) leading to production of the Design Development Deliverables (circa 6 number CE meetings) leading to approval to proceed to planning

		Key Documents (TO BE UPDATED ONCE DETAILED EIR IS FINALISED)				Feasibility Study (and associated appendices)				Scheme Notification Form					Information to be provided at ITT by Framework User / - ITT / - Qualitive Questions / - Pricing Questions / - Feasibility Study / - PCSA / Information to be submitted by Bidders / - Responses to Questions set / - Completed and signed Forms and Certificates			Information to be provided by Framework User / - Succesful Bidder Letter / - Unsuccesful Bidder Letter / - PCSA for execution / Information to be provided by SPM / - PCSA (signed)					Information to be provided / - n/a / Information to be provided by SPM / - Design Development Deliverables					Information to be provided by Framework User / - Clarifications / Information to be provided by SPM / - Clarification responses		Information to be provided by Framework User / - n/a / Information to be provided by SPM / - Planning Submission			Information to be provided by Framework User / - n/a / Information to be provided by SPM / - Contractor's Proposals					Info to be provided by SPM / - Contractor's Proposals (final)	Information to be provided by Framework User / - Employer's Requirements / - Gaps List / - Draft Contract / - Contract Schedules / - Clarifications / Information to be provided by SPM / - Contractor's Proposals (final) / - Contract Schedules / - Clarification responses

		PCSA Payment Milestone						PCSA Milestone 1 after CEM3 (week 9)					Payment Milestone 2 approval to proceed to planning (Week 16) / or approval to proceed with Contractor's Deliverables where no planning permission required					PCSA Milestone 3 at submission of CPs (Week 29) / PCSA Milestone 4 (Final for PCSA) at agreement of Contractor’s Proposals and Contract (Week 36)

## D&B_-_Direct_Award
			Design and Build Direct Award Timeline

High Value Band Cost Led Two Stage D&B / ROUTE A2 - HVB OPTION / (SINGLE PROJECTS) / & / Low + Medium Value Bands / Two-Stage D&B		Approx. RIBA Stage	RIBA Stage 0 / (Strategic Definition)			RIBA 1 Preparation and Briefing (Feasibility Study)			RIBA 2 Concept Design					RIBA 2 Concept Design					RIBA Stage 3 Spatial Coordination					RIBA Stage 4 (Technical Design)					RIBA Stage 5 / (Construction)			RIBA Stage 6 / (Handover and Close Out)			RIBA Stage 7 / (In Use)

		Framework Stage				Feasibility Study (c16 Weeks)			Pipeline (3 Weeks minimum)				EOI to Contract Close: / 36 to 39 Weeks / Framework Users to draft realistic programmes based on project-specifics	Direct Award Appointment (6 Weeks)					Design Development / (c7 Weeks)					Design Development Clarification Process / (2 Weeks)		Planning Submission / (3 Weeks)				Planning Determination (15 to 18 Weeks)					Contract Finalisation (3 Weeks)				Construction			Handover and Rectification Period			In Use
								Expression of Interest (EOI)	Invitation to Submit Proposal (ISP)		Evaluation and Appointment					Contractor's Proposals (8 to 10 Weeks)					CPs Review (7 to 8 Weeks)
		Week				Week -19 to -4			Week -3	Week -2	Week -1			Week 1	Week 2	Week 3	Week 4	Week 5	Week 6		Week 7	Week 8	Week 9	Week 10	Week 11	Week 12	Week 13		Week 14	Week 15	Week 16	Week 17	Week 18		Week 19	Week 20	Week 21	Week 22	Week 23	Week 24	Week 25	Week 26	Week 27	Week 28	Week 29	Week 30	Week 31	Week 32	Week 33	Week 34	Week 35	Week 36		Week 37	Week 38	Week 39

		Stage Summary	Framework User agrees Business Case and Strategic Brief			Framework User prepares the Scheme to end of RIBA Stage 1 – including a Feasibility Study and costed control option. / Indicative information may be published on the Pipeline / Alternate Option: Framework User has the option to develop the Scheme to end of RIBA Stage 2 or 3			Framework User gives minimum of three weeks notice to DfE framework team who provide at least two weeks notice to Contractors. / Framework User issues Feasibilty Study / design information via DfE Framework Team / Framework User may contact highest ranked Contractor in Lot to gauge interest.					Framework User issues a request for Expressions of Interest (EOI) to all Contractors. The Contractors must provide a response within five working days.	Issue of ISP and response / Alternate Option: This period may need to be extended to reflect the quanitity of design information Contractors must review		Evaluation and Appointment of Selected Panel Member (SPM) under a PCSA		Sign PCSA		CEM 1	CEM 2	CEM 3	CEM 4	CEM 5	CEM 6	Submission		Framework User clarification process; review of Design Deliverables submission (including cost plan); leading to approval to proceed to planning submission		Preparation, submission and validation of Planning Application / Alternate Option: If the Framework User has already completed RIBA Stage 3 and submitted a Planning Application, proceed to the next RIBA Stage				Time allocation subject to expected planning determination period / As per Exchange Information Requirements / SPM sessions to continue to evolve decision (includng resolving RDD matters)					CPs Submitted	Time allocation subject to expected planning determination period / Clarifications process run in parallel leading to approval of Contract CPs / GAPs calls to run in parallel leading to drafting of Contract Schedules / Update CPs to reflect planning decisions / Conclusion of Contract Schedules					Finalisation, agreement and signature of contract following planning permission

								Client Engagement Meetings (CEMs) leading to production of the Design Development Deliverables (circa 6 number CE meetings) leading to approval to proceed to planning

		Key Documents (TO BE UPDATED ONCE DETAILED EIR IS FINALISED)				Feasibility Study (and associated appendices)			Scheme Notification Form					Scheme Notification Form including Feasibility, programme and cost plan	Information to be provided at ITT / - ISP / - Qualitive Questions / - Pricing Questions / - Feasibility Study / - PCSA / Information to be provided by Bidders / - Responses to Questions set / - Completed and signed Forms and Certificates		Information to be provided by Framework User / - PCSA for execution / Information to be provided by SPM / - PCSA (signed)					Information to be provided / - n/a / Information to be provided by SPM / - Design Development Deliverables					Information to be provided by Framework User / - Clarifications / Information to be provided by SPM / - Clarification responses		Information to be provided by Framework User / - n/a / Information to be provided by SPM / - Planning Submission				Information to be provided by Framework User / - n/a / Information to be provided by SPM / - Contractor's Proposals					Info to be provided by SPM / - Contractor's Proposals (final)	Information to be provided by Framework User / - Employer's Requirements / - Gaps List / - Draft Contract / - Contract Schedules / - Clarifications / Information to be provided by SPM / - Contractor's Proposals (final) / - Contract Schedules / - Clarification responses

		PCSA Payment Milestone						PCSA Milestone 1 after CEM3 (week 9)					Payment Milestone 2 approval to proceed to planning (Week 16) / or approval to proceed with Contractor's Deliverables where no planning permission required					PCSA Milestone 3 at submission of CPs (Week 29) / PCSA Milestone 4 (Final for PCSA) at agreement of Contractor’s Proposals and Contract (Week 36)

## D&B_-_Future_School
				Design and Build Future School Timeline

High Value Band Cost Led Two Stage D&B / ROUTE A2 - HVB OPTION / (BATCHES AND SINGLE PROJECTS) / & / Low + Medium Value Bands / Two-Stage D&B		Approx. RIBA Stage					RIBA 1 Preparation and Briefing (Feasibility Study)			RIBA 2 Concept Design					RIBA 2 Concept Design					RIBA Stage 3 Spatial Coordination					RIBA Stage 4 (Technical Design)					RIBA Stage 5 / (Construction)			RIBA Stage 6 / (Handover and Close Out)			RIBA Stage 7 / (In Use)

		Framework Stage		Sample Scheme			Feasibility Study (c16 Weeks)			Contractor Consultation				ISP to Contract Close: / 35 to 38 Weeks / Framework Users to draft realistic programmes based on project-specifics	Future School Appointment (5 Weeks)					Design Development / (c7 Weeks)					Design Development Clarification Process / (2 Weeks)		Planning Submission / (3 Weeks)			Planning Determination (15 to 18 Weeks)					Contract Finalisation / (3 Weeks)				Construction			Handover and Rectification Period			In Use
									Invitation to Submit Proposal (ISP)		Evaluation and Appointment					Contractor's Proposals (8 to 10 Weeks)					CPs Review (7 to 8 Weeks)
		Week		Contractor is appointed under a PCSA and Future Schools Agreement signed, including named Future Schools.			Framework User prepares the Scheme to end of RIBA Stage 1 – including a Feasibility Study and costed control option. / Alternate Option: Framework User has the option to develop the Scheme to end of RIBA Stage 2 or 3			Framework User consults with the Contractor about the release of the Future Schools Notice / Invitation to Submit Proposal and return date for Proposal.					Week 1	Week 2	Week 3	Week 4	Week 5		Week 6	Week 7	Week 8	Week 9	Week 10	Week 11	Week 12		Week 13	Week 14	Week 15	Week 16	Week 17	Week 18	Week 19	Week 20	Week 21	Week 22	Week 23	Week 24	Week 25	Week 26	Week 27	Week 28	Week 29	Week 30	Week 31	Week 32	Week 33	Week 34	Week 35		Week 36	Week 37	Week 38

		Stage Summary							Issue of Future Schools Notice and Invitation to Submit Proposal (ISP) and response (two weeks, or as agreed with Contractor) / Alternate Option: This period may need to be extended to reflect the quanitity of design information Contractors must review / For HVB Future Schols the ISP response must be within the cost envelope set by the Framework User or it will be deemed non compliant.		Evaluation and Appointment of Selected Panel Member (SPM) under a PCSA		Sign PCSA		CEM 1	CEM 2	CEM 3	CEM 4	CEM 5	CEM 6	Submission		Framework User clarification process; review of Design Deliverables submission (including cost plan); leading to approval to proceed to planning submission		Preparation, submission and validation of Planning Application / Alternate Option: If the Framework User has already completed RIBA Stage 3 and submitted a Planning Application, proceed to the next RIBA Stage			Time allocation subject to expected planning determination period / As per Exchange Information Requirements / SPM sessions to continue to evolve decision (includng resolving RDD matters)					CPs Submitted	Time allocation subject to expected planning determination period / Clarifications process run in parallel leading to approval of Contract CPs / GAPs calls to run in parallel leading to drafting of Contract Schedules / Update CPs to reflect planning decisions / Conclusion of Contract Schedules					Finalisation, agreement and signature of contract following planning permission

									Client Engagement Meetings (CEMs) leading to production of the Design Development Deliverables (circa 6 number CE meetings) leading to approval to proceed to planning

		Key Documents (TO BE UPDATED ONCE DETAILED EIR IS FINALISED)					Feasibility Study (and associated appendices)			Scheme Notification Form					Information to be provided by Framework User / - ISP / - Feasibility Study / - PCSA / Information to be submitted by Bidders / - Responses to ISP Requirements / - Completed and signed Forms and Certificates		Information to be provided by Framework User / - PCSA for execution / Information to be provided by SPM / - PCSA (signed)					Information to be provided / - n/a / Information to be provided by SPM / - Design Development Deliverables					Information to be provided by Framework User / - Clarifications / Information to be provided by SPM / - Clarification responses		Information to be provided by Framework User / - n/a / Information to be provided by SPM / - Planning Submission			Information to be provided by Framework User / - n/a / Information to be provided by SPM / - Contractor's Proposals					Info to be provided by SPM / - Contractor's Proposals (final)	Information to be provided by Framework User / - Employer's Requirements / - Gaps List / - Draft Contract / - Contract Schedules / - Clarifications / Information to be provided by SPM / - Contractor's Proposals (final) / - Contract Schedules / - Clarification responses

		PCSA Payment Milestone							PCSA Milestone 1 after CEM3 (week 9)					Payment Milestone 2 approval to proceed to planning (Week 16) / or approval to proceed with Contractor's Deliverables where no planning permission required					PCSA Milestone 3 at submission of CPs (Week 29) / PCSA Milestone 4 (Final for PCSA)at agreement of Contractor’s Proposals and Contract (Week 36)

## Construct_Only_(HVB+MVB+LVB)
		Construct Only Timeline

All Value Bands / Construct Only		Complete RIBA Stages 0 to 4 (minus any contractor design pacakges)					RIBA Stage 5 / (Construction)			RIBA Stage 6 / (Handover and Close Out)			RIBA Stage 7 / (In Use)
		Client Design and Planning Permission: c33 weeks					Pipeline: 5 Weeks Minimum					Competition: c9 weeks					Contract Close: / 2 Weeks		Construction			Handover and Rectification Period			In Use
		c33 Weeks					Week 34	Week 35	Week 36	Week 37	Week 38	Week 39	Week 40	Week 41	Week 42	Week 43	Week 44	Week 45	Week 46	Week 47	Week 48	Week 49

		Framework User secures planning permission and produces Bill of Quantities or detailed Schedule of Works that can be priced. / Indicative information may be published on the Pipeline					Framework User gives minimum of five weeks notice to DfE framework team who provide at least four weeks notice to Contractors					ITT issue and response					Evaluation and Selection			Scheme Contract signed