March 2021
GLOBAL ANTI-CORRUPTION PROGRAMME
CYCLE 1 EVALUATION
Cover image designed by Evening Tao/ Freepik

Version history

D11_02	Global Anti-Corruption Programme Cycle 1 Evaluation
Revision	Written By	Checked By	Approved By
Revision 1	Charlotte Vaillant	Valerie McDonnell-Lenoach
Revision 2	Charlotte Vaillant	Dulce Pedroso

Table of acronyms

Abbreviation
ACI	Anti-corruption and Integrity
ADB	Asian Development Bank
AML/CFT	Anti-Money Laundering/Combating the Financing of Terrorism
BO	Beneficial Ownership
CPI	Corruption Perception Index
COVID-19	Coronavirus disease of 2019
CSO	Civil society organisation
DFID	Department for International Development
EACC	(Kenya) Ethics and Anti-Corruption Commission
EL	Evaluation and Learning
EQs	Evaluation Questions
ESAAMLG	Eastern & Southern Africa Anti-Money Laundering Group
FATF	Financial Action Task Force
FCDO	Foreign, Commonwealth and Development Office
FSRBs	FATF-Style Regional Bodies
GACP	Global Anti-Corruption Programme
GDMP	Global Digital Market Place
GESI	Gender Equality and Social Inclusion
GDS	Government Digital Service
G&I	Gender and inclusion
HMG	Her Majesty’s Government
HMT	Her Majesty’s Treasury
ICAR	International Centre for Asset Recovery
IACCC	International Anti-Corruption Coordination Centre
ICT	Information and Communication Technology
JACU	Home Office Joint Anti-Corruption Unit
JFU	Joint Funds Unit
GFAR	Global Forum on Asset Recovery
LKPP	National Public Procurement Agency (Indonesia)
MACC	Malaysian Anticorruption Commission
MER	(FATF) Mutual Evaluation Report
MLHR	Ministry of Law and Human Rights
MoU	Memorandum of Understanding
MREL	Monitoring, reporting, evaluation and learning
MLA	Mutual Legal Assistance
ODA	Official Development Assistance
OECD	Organisation for Economic Cooperation and Development
OCP	Open Contracting Partnership
PF	Prosperity Fund
PT	Programme Team
SBs	Secondary benefits
SDA	Social Development Adviser
SRO	Senior Responsible Owner
StAR	Stolen Asset Recovery Initiative
ToC	Theory of Change
UNCAC	United Nations Convention against Corruption
UNODC	UN Office on Drugs and Crime
VfM	Value for money
WATCH	Women Against Trans-national Corruption Hub

Contents

TABLES

Table 1: GACP Delivery partners	1
Table 2: Main data sources	9
Table 3: GACP’s geographical distribution	17
Table 4: Project’s contribution to GACP themes	18
Table 5: FATF’s and UNODC’s light-touch contribution analysis	26
Table 6: Open Ownership’s and GDMP’s light-touch contribution analysis	29
Table 7: IACCC’s and StAR’s light-touch contribution analysis	32
Table 8: Gender and Inclusion scorecard summary	40
Table 9: Value for money scorecard summary	41
Table 10: Conclusions, lessons and recommendations on programme design, management and portfolio coherence.	45
Table 11: Conclusions, lessons and recommendations for individual projects.	45
Table 12: Conclusions, lessons and recommendations on GACP’s overall achievement and cross-cutting themes.	46
Table 13: Detailed recommendations, lead, priority and timescale	47
Table 14: Cycle 1 evaluation matrix	54
Table 15: Major driving factors for corruption and organized crime in Eastern Africa	76

FIGURES

Figure 1: GACP’s projects, % total allocation	6
Figure 2: Revised GACP Theory of Change	7
Figure 3: GACP’s governance set-up	12
Figure 4: GACP’s yearly allocation	15
Figure 5: AC pathways to secondary benefits	43
Figure 6: World Bank’s Governance Indicators, Indonesia and Malaysia, 2019	65
Figure 7: World Bank’s Governance Indicators, Kenya and Botswana, 2019	68

BOXES

Box 1: The UK Anti-Corruption Strategy	5
Box 2: COVID-19 pilot: Transforming Procurement Systems	14
Box 3: Unpacking synergy across projects in South East Asia	19
Box 4: Use of communities of experts	20
Box 5: Focus on knowledge—Behavioural Science and OECD	23
Box 6: Focus on selected GACP knowledge products	34
Box 7: Commissioning new research in AC: Experience from GACP	34
Box 8: Focus on the OECD Anti-Corruption and Integrity Forum	35
Box 9: Focus on OECD Anti-Corruption and Integrity Hub	36
Box 10: OECD/Asian Development Bank anti-corruption initiative in South East Asia	36
Box 11: Key G&I results	38
Box 12: SB categories	42
Box 13: Open Ownership SB potential and relationship to UK Anti-Corruption Strategy	44
Box 14: Gender and inclusion priority actions	49
Box 15: 2019 law undermining the Indonesian Corruption Eradication Commission	66
Box 16: One Malaysia Development Berhad scandal	66
Box 17: Regional platform in practice: Focus on whistleblowing in East Africa	73
Box 18: UN coordination and the politics of AC reforms in South Sudan	75
Box 19: Beneficial ownership landscape in Indonesia	79
Box 20: Botswana’s progress in AML/CFT	83
Box 21: Emerging results from implementing the GFAR principles	94
Box 22: Timeline of key events and decisions related to BO in Kenya	96

ANNEXES

# Executive summary
Brief overview / The Global Anti-Corruption Programme was developed to support the UK’s anti-corruption strategy by contributing to a range of innovative projects and building on the UK’s reputation and expertise. / The programme is complex, with ten government departments and seven delivery partners involved. / While the programme has contributed to some big wins on asset recovery in the last two years, it risks falling behind in its ambition to strengthen transparency and e-procurement systems in partner countries. / However, the Global Anti-Corruption Programme’s contribution to improved anti-corruption policies, laws, regulations and practices is expected to accelerate in the next two years.[1]
[1] At the time of finalising this report, the programme was facing an uncertain future as a result of cuts in the UK government’s Official Development Assistance budget.

What is the Global Anti-Corruption programme?
The Prosperity Fund’s Global Anti-Corruption Programme (GACP) is designed to respond to the UK’s 2017–22 Anti-Corruption Strategy commitment to help countries combat corruption. Tackling corruption is key to promoting sustainable and inclusive economic growth, helping to bring the poorest citizens out of poverty. The programme’s primary purpose is to disincentivise and ‘design out’ opportunities for corruption, help end impunity and recover illegally gained assets. It is a cross-government initiative worth GBP 45.1 million, involving four departments: the Foreign, Commonwealth and Development Office, National Crime Agency, Government Digital Services (GDS) and Treasury. The four-year programme is supporting four multilateral and three UK-based delivery partners (see Table 1) and operates globally, regionally and in selected middle-income countries.
Table 1: GACP Delivery partners
Multilateral partners			UK-based partners
UN Office on Drugs and Crime / Financial Action Task Force / Stolen Asset Recovery Initiative / Organisation for Economic Cooperation and Development			Open Ownership / Government Digital Services / International Anti-Corruption Coordination Centre

## What did the evaluation look at?
The evaluation reviewed the entire programme portfolio:
- assessing the overall quality of design, relevance and coherence of the programme portfolio, taking the context into account
- identifying what works and does not and why
- contributing to the Prosperity Fund’s analysis for selected cross-cutting themes (gender and inclusion (G&I), value for money and secondary benefits)
- supporting learning and making recommendations for improved delivery
- contributing to the 2020 annual review, Prosperity Fund sector synthesis and Fund-level evaluations.
This evaluation, completed in December 2020, is the first independent assessment of GACP since the business case was approved in 2018. Data was collected over a three-month period, with the Evaluation and Learning team remotely consulting more than 100 stakeholders, including delivery departments and partners, direct beneficiaries, civil society organisations, other donors and experts.
The evaluation focused on two regions, South East Asia and East Africa, using a light-touch contribution analysis approach looking at actual and likely results, identifying contributing factors and analysing the assumptions that underpin the programme’s intended results.
## What did the evaluation find?
Progress: All GACP projects have achieved outputs, but some have fallen behind on outcome results. However, according to the programme’s original lifetime, they have another two years to achieve their expected results. Four projects started activities in 2017/18 with some transition funding. Programme expenditure amounted to GBP 13.2 million in 2019/20. The 2020/21 budget was reduced by 32 per cent to GBP 8.2 million, as a result of cuts in UK Official Development Assistance.
Performance: The programme got off to a slow start but has accelerated its delivery in the last two years. Activities and milestones have been achieved for the majority of the projects, with a few projects performing better than expected. The Programme Team responded to the budget cut in 2020/21 by putting on hold or abandoning activities that had not started or had recently started.
Projects have adjusted well to the travel restrictions during the pandemic by organising online meetings and seminars as short-term solutions. While projects have mostly stayed on track, delivery partners say face-to-face relationships remain key to their success in the long run. This is all the more crucial when dealing with highly sensitive corruption cases.
Results achieved: The regional platforms set up by the United Nations Office on Drugs and Crime (UNODC) with GACP support have contributed a few changes, but results were expected to accelerate. The two platforms launched in South East Asia and East Africa in 2017 have yet to show significant results. Results are expected to improve, however, as the platforms promote realistic and practical actions and are conducive to peer learning and developing anti-corruption champions.
GACP has fallen behind in its ambition to increase transparency and strengthen information management systems in partner countries. Many of the Global Digital Market Place (GDMP) projects are still at an early development stage, while Open Ownership has not met its ambition to support the establishment of public beneficial ownership registers in selected countries.
While information is sparse and sensitive, the International Anti-Corruption Coordination Centre (IACCC) and the Stolen Asset Recovery (StAR) Initiative have demonstrated a positive contribution to international anti-corruption sanctions, leading to some big wins. This includes stolen asset recovery in Malaysia following the alleged One Malaysia Development Berhad scandal.[2]
[2] www.justice.gov/opa/pr/us-seeks-recover-more-300-million-additional-assets-traceable-funds-allegedly-misappropriated
The programme’s contribution to raising public awareness remains unknown, while its plan to support innovative research has been put on hold. A large majority of GACP projects have contributed to key events and knowledge products for practitioners. The Organisation for Economic Cooperation and Development (OECD) in particular is well placed to disseminate knowledge through its new Anti-Corruption and Integrity Hub. However, there is currently little evidence of uptake in priority regions. In addition, the Behavioural Science project has been cancelled and, as a consequence, the programme has not supported innovative research to shift corrupt behaviours as intended.
Design: The four areas of support that underpin the GACP change process are recognised as the key foundations to fighting corruption globally and in partner countries. These are: 1) improved anti-corruption policies, laws, regulations and practices, reflecting international norms and standards; 2) access to open data and more efficient and transparent information management systems; 3) increased international success in anti-corruption law enforcement actions, and 4) increased public and government awareness of good and innovative practices.
The link in the change process between e-procurement and anti-corruption is the weakest among GACP’s areas of support. Promoting open access to procurement data constitutes GDMP’s main entry point to anti-corruption. E-procurement can also potentially be a mechanism to reduce corruption as it reduces human interaction and facilitates public access to information. In practice, however, while e-procurement exists in partner countries, it is often underutilised. Consequently, decisions are still prone to interference at every stage of procurement and opportunities for external scrutiny can be limited.
The programme’s choice of partners has been highly relevant, with all but one partner (GDMP) having anti-corruption at the core of their mandate. The multilaterals play a central role in shaping and implementing the global anti-corruption agenda, while fighting corruption is also core to UK-based IACCC and Open Ownership. GDMPhas a much broader mandate, which is to lead the UK’s digital transformation; as a result, its focus on anti-corruption has been more difficult to convey.
GACP is also designed to act as a catalyst for change for the work of multilateral organisations, so they can have more impact globally and in partner countries. Through its support, GACP intends to encourage cross-fertilisation across OECD’s relevant workstreams, help the FATF Secretariat strengthen its global network, and innovate with UNODC’s delivery model to fast track the implementation of the United Nations Convention against Corruption in partner countries.
While strong for some, the relevance and added value of GACP projects overall has varied. GACP projects have typically combined in-country diagnosis and/or broad stakeholder consultation with a demand-led approach to delivering technical assistance. However, their relevance has been undermined at times by a lack of country presence (Open Ownership), highly technical products (GDMP), and the risk of duplication with other initiatives (StAR, UNODC and OECD).
The programme’s rationale for working regionally is strong; its selection of priority countries less so. GACP’s rationale for supporting regions was driven partly by FATF’s global network of FATF-style regional bodies and partly by the establishment of UNODC regional platforms. Colombia, Mexico, Indonesia, Malaysia and South Africa are the priority countries for the programme. However, GACP’s partners do not have the same country presence, nor do they share the same approach to country prioritisation. As a result, GACP’s activities have remained scattered, including in priority countries.
The programme has increasingly encouraged synergy across its projects and partners. A new project, Transforming Procurement Systems, was launched in late 2020 to address corruption in procurement during and after the pandemic, encouragingGDMP, Open Ownership, UNODC and a new partner—Open Contracting Partnership—to join forces in selected countries.
Gender and inclusion: GACP is beginning to demonstrate its ability to achieve G&I results, but patchy application of Prosperity Fund minimum standards is undermining its ambitions. The team has made significant efforts to develop an approach and vision for G&I and share it with delivery partners, and G&I results are beginning to emerge for GDMP (engagement with end-beneficiaries) and StAR (asset recovery). However, not all delivery partners have the processes and capacity in place to underpin further progress.
Secondary benefits: More transparent and competitive procurement processes, and access to corporate (beneficial ownership) data, are expected to open up opportunities for international businesses; GACP has also been a useful platform for promoting the UK’s policy priorities. GACP has a clear potential to generate benefits for both domestic and international business. Its close link with the UK’s policy priorities is likely to generate some secondary benefits for UK companies, with partner countries demanding anti-corruption expertise from the UK.
Value for money: The programme scores ‘adequate’ in the Value for Money self-assessment, reflecting a mix of good practices and challenges related to the range of activities and partners, and the complexity of the programme. The programme encompasses complex financial arrangements, which the programme team has monitored and managed effectively. The GACP team has benefited from the convening power of multilaterals, supported innovative projects and claimed some big wins (asset recovery) for a minimum investment. However, some projects have lacked efficiency, and insufficient attention has been given to sustainability. Cost containment and the lack of a shared approach to Value for Money have also been problematic.
Governance and management: GACP’s governance and management set-up has worked relatively well, but opportunities for joint decision making remain limited. The first years of operation have been spent developing the programme’s systems and requirements. The Home Office Joint Anti-Corruption Unit’s involvement has ensured a close articulation with the UK’s policy priorities. While decisions are made centrally, the GACP team has also associated with FCDO posts in priority countries. The combined role of the programme team as GACP coordinator and FCDO lead has sometimes reduced its ability to follow up on agreed actions, however, owing to limited resources. The number of projects to cover in relatively short meetings has also left little time for joint decision making.
Learning: GACP’s more innovative projects have come with a strong learning element, but opportunities to take the long view and capitalise on cross-government learning have remained limited. Open Ownership, IACCC and GDMP(international) were established with GACP’s funding. They have grown as organisations over the review period. There is also strong evidence of learning what works and what does not among their staff. However, GACP’s governance (and reporting) mechanisms have not been well set up to support learning among partners.
Risks: The programme’s risk register is comprehensive and follows Joint Funds Unit guidance, but the risk of causing unintended effects is missing. More specifically, the risk of unforeseen harm to vulnerable groups is not monitored. There is also a risk that the introduction of public beneficial ownership registers, without proper regulation, verification and sanction, could prompt criminals to develop more sophisticated concealment techniques.
## What are the lessons for the Prosperity Fund as a whole?
- Influencing multilaterals can work. Global programmes, such as GACP, can influence and strengthen the work of multilaterals by proposing innovative solutions and/or allocating additional resources to maximise impact.
- Priority country earmarking is key. When working with a range of partners, prioritising countries within global programmes, such as GACP, requires more explicit earmarking in relation to both resources and results monitoring.
- Innovation comes with a strong delivery risk but potentially high returns. Most of GACP’s more innovative projects (UNODC, Open Ownership, GDMP) were found to be making slow progress, but IACCC’s experience shows this can lead to big returns.
## Recommendations
The following high-priority recommendations were identified:
- The programme team should consider allocating more time for the steering and strategic group meetings to support shared learning and decision making.
- The programme team, the delivery departments and their partners should allocate more time and resources (including from FCDO posts) to seeking new opportunities and monitoring progress in priority countries, including on gender and inclusion.
- With FDCO as lead, UNODC should start prioritising its technical assistance where it has a stronger chance of success and publicise the regional platforms’ outcome statements more widely to generate lasting buy-in.
The Prosperity Fund is a UK government initiative supporting inclusive economic growth in partner countries through a GBP 1.2 billion portfolio of programmes over seven years. The Fund’s activities will contribute to achieving the UN Sustainable Development Goals, while creating opportunities for international business as a secondary benefit. / Scrutiny of the Fund’s work is undertaken by an independent evaluation service, led by Tetra Tech International Development, in partnership with LTS/Niras and Integrity. Evaluations take place at programme and Fund levels, and aim to identify learning on programmes, thematic areas, and sectors.

- Open Ownership should step up advocacy on public beneficial ownership registers, while exploring new options for public scrutiny.
- The programme team should develop a dissemination and learning uptake strategy to ensure its contribution to knowledge products, global and regional events, and the OECD Anti-Corruption and Integrity Hub is monitored and evaluated for value to priority regions and countries.

# Introduction
This report presents the evaluation findings of the Global Anti-Corruption Programme (GACP)’s performance for Cycle 1, covering three to four years of operation. The Prosperity Fund (PF) puts particular emphasis on formative evaluation exercises in order to:
- generate learning on what works in the PF areas of programming,
- support adaptive programming at the programme level and adaptive management at the Fund level,
- contribute to the accountability mechanisms of the Fund and the departments that use PF funds, and
- generate evidence for external communication and outreach purposes at programme and Fund level.
## Overview of GACP
The GACP is a five-year, GBP 45.1 million programme funded through the PF. The programme was designed in response to the UK’s commitments to fight global corruption, as reflected in the UK Anti-Corruption (AC) Strategy (2017-22) following the 2016 London AC Summit (see Box 1).
Box 1: The UK Anti-Corruption Strategy[3]
[3] https://www.gov.uk/government/publications/uk-anti-corruption-strategy-2017-to-2022
The UK Anti-Corruption Strategy 2017-22 sets out a framework and a vision for UK efforts to tackle corruption at home and abroad. The strategy, building on the UK’s 2014 Anti-Corruption Plan and reflecting commitments made during the 2016 Anti-Corruption Summit in London, supports the UK’s work on counter-terrorism, serious and organised crime and anti-money laundering. / One of the six priorities of the strategy is to work with other countries to combat corruption. This is where the PF interventions, starting with GACP, can help. This priority encompasses the following goals: / enhanced international transparency, especially in beneficial ownership (BO), extractives, public finance and contracting; / reduced levels of corruption in partner countries; and / enhanced action to address corruption in fragile and conflict-affected states.

The programme’s strategic business case was first submitted for approval in January 2018, leading to a revised version in June 2018. The programme was formally signed off in October 2018 and has been in delivery since early 2019.
GACP’s primary purpose and overall objective is “to disincentivise corruption, design out opportunities for corruption, recover illegally gained assets and help end impunity.” GACP’s goal is to promote higher rates of inclusive sustainable growth, poverty reduction, increased investment and trade, and enhanced UK soft power.
The programme, which is led by the Foreign, Commonwealth, and Development Office (FCDO), is a cross-government initiative. The five lead government organisations—formerly Department for International Development (DFID), National Crime Agency, Cabinet Office/Government Digital Service (GDS), Her Majesty’s Treasury (HMT) and FCDO—share management responsibility and, together with the Home Office/Joint Anti-Corruption Unit (JACU), sit on the GACP Strategic Board.
The programme is currently implemented through eight integrated projects (one still at design stage, which was put on hold as a result of Official Development Assistance (ODA) reprioritisation), an approach intended to reflect the complex multifaceted nature of corruption. These projects operate globally, regionally and/or in selected middle-income countries. The priority countries for the programme are Colombia, Mexico, Indonesia, Malaysia and South Africa.

Figure 1: GACP’s projects, % total allocation

The implementing partners are as follows:[4]
[4] GACP also supported the Extractive Industry Transparency Initiative until 31 March 2019. Originally budgeted for GBP 3.2 million, formerly DFID took over this project from 1 April 2019, one year ahead of original project deadline, and refunded GBP 500 thousand to the PF Delivery Unit.
- UN Office on Drugs and Crime (UNODC) (GBP 8.0 million)
- Global Digital Market Place (GDMP)[5] (GBP 10.5 million)
  [5] Delivery of the Global Digital Marketplace Programme (GDMP) is led by the Government Digital Service (GDMP), which is part of the Cabinet Office. GDMP forms part of the GDMP portfolio of funded activities focussed on sharing internationally - a priority of the Government Transformation Strategy 2017 to 2020. GDMP is also a commitment in the UK Anti-Corruption Strategy 2017 to 2022 and Economic Crime Plan 2019 to 2022
- Organisation for Economic Cooperation and Development (OECD) (GBP 4.0 million)
- Financial Action Task Force (FATF) (GBP 3.4 million)
- International Anti-Corruption Coordination Centre (IACCC) (GBP 5.1 million)
- Stolen Asset Recovery Initiative (StAR) (GBP 2.0 million)
- Open Ownership (Open Ownership) (GBP 2.8 million)
- Behavioural Science (GBP 3.0 million)[6]
  [6] Project budgets started as of October 2018 (business case approval) and exclude programme administration charges, which total GBP 3.1 million overall.
Four projects—StAR, IACCC, Global Digital Market Place (GDMP) and Open Ownership—received some transition funding in 2017/18 before the business case was signed off
Figure 2 provides GACP’s revised Theory of Change (ToC). The full list of assumptions (including those more specific to projects) is given in Annex 1.
Figure 2: Revised GACP Theory of Change

Other PF programmes also have AC elements. With GACP, they contribute to the Fund’s intermediary outcome on ease of doing business. Fighting corruption can also be found as important components of the Colombia PF, Mexico PF, and ASEAN Economic Reform PF programmes.
## Cycle 1 Evaluation
### Primary audience
The FCDO Programme Team (PT), GACP’s delivery departments, FCDO posts in priority countries and Senior Responsible Owner (SRO) involved in the programme are the primary audience for this evaluation.
The Joint Funds Unit (JFU), FCDO PF Delivery Unit, PF Social Development Adviser and FCDO Global Programme Support Team also have a direct interest in this evaluation. Other key stakeholders likely to learn from this evaluation include JACU, GACP implementing partners and other PF programme teams, other donors and the global AC community.
Meetings with the PT were held at regular intervals throughout the evaluation to support data collection and for validation purposes. The EL team presented their preliminary findings to the PT in October 2020, followed by the lessons and recommendations, listed in Section 5.
### Objective and scope
The objectives of this evaluation are to:
- Assess the overall quality of design, relevance and coherence of the programme portfolio, taking the context into account.
- Identify what works and does not work and why, in view of results to date, taking the context into account.
- Contribute to the Fund’s analysis for selected cross-cutting themes (gender and inclusion (G&I), value for money (VfM) and secondary benefits (SB))[7].
  [7] Climate change, which is a new thematic developed by the PF, will not be covered in Cycle 1.
- Support learning and make recommendations for improved delivery.
- Contribute to the 2020 annual review (due in December), the PF sector synthesis and fund-level evaluations.
The evaluation period starts in October 2018, when the business case was approved, and covers programme developments up to October 2020.
The Evaluation and Learning (EL) team shared a first draft evaluation report and discussed selected findings with the annual review team in November 2020.
### Approach
The EL team co-developed the approach for this evaluation with the PT. Key elements of the approach, including the PT’s learning needs, choice of evaluation questions (EQs) and sampling were discussed in detail in the months leading to the approach paper’s finalisation. The link to the approach paper can be found in Annex 2. The EQs cover the OECD DAC criteria of relevance, coherence, effectiveness and efficiency. They also cover the Fund’s thematics.
This evaluation uses a theory-based approach as developed by the EL team and agreed with JFU in the PF EL Inception Report. Theory-based evaluation provides a useful framework to understand how and why change happens as a result of funding programme activities. It also interrogates the extent to which the causal pathways that explain change and impact in the ToC have been observed during the implementation of the project, and whether the assumptions about causality and context hold true.
The evaluation also emphasises learning through events at key evaluation stages[8] and a forward-looking focus on lessons and recommendations. In line with the EL methodology, the PT will develop a management response and action plans to address the evaluation’s recommendations and disseminate learning.
[8] Learning events were held with the programme team in September 2020 to capture their own views on the programme’s performance, using the EQs; in October to present the evaluation’s preliminary findings, with a particular emphasis on the selected regions and countries; and in December to discuss and validate the evaluation’s conclusions, lessons and recommendations. The Programme Evaluation Lead also presented the evaluation progress in GACP Strategic Board meeting in November.
Because of the complex nature of the programme, the evaluation in effect combines four different levels of inquiry when assessing the programme performance: (i) the programme/governance set-up; (ii) the programme’s project portfolio; (iii) individual projects; and (iv) the programme’s performance in target regions and countries.
A sampling approach is used to support data collection, covering all GACP projects in two selected regions: South East Asia and East Africa. All individual projects are examined, in recognition that they all have a role to play in making the programme a coherent whole.
South East Asia and East Africa were selected for the following reasons:
- South East Asia is where most partners (except for Open Ownership) have activities, whether at country or regional level. It also includes two of GACP’s priority countries: Malaysia and Indonesia.
- East Africa was selected as the second region so that Open Ownership’s work could be assessed along with other relevant activities by selected partners (FATF, UNODC). The choice of East Africa also enables testing the programme’s performance in regions where GACP and its UK delivery partners have a reduced presence.
The EQs and sampling approach reflect the PT’s particular interest in investigating how GACP’s specific characteristics can make a positive difference. These characteristics include cross-government collaboration; innovation and scaling up; a multi-level approach combining country, regional and global levels; and a focus on the evidence base.
### Data collection tools
A detailed matrix listing all evaluation questions, sub-questions, data sources and data collection methods can be found in Annex 3. This matrix was used to develop questionnaires and project evaluation templates, which the EL team tested and used to collect and analyse data.
The EL team generated its findings using a triangulated approach, consisting of mixed data sources and data collection tools. Particular care was given to interviewing a broad range of stakeholders, including independent organisations and experts. While most interviews were conducted on an individual basis, focus group discussions were also held with the PT. Independent studies were identified to assess and put in context all of GACP’s projects. This included recent evaluation exercises, notably the StAR 2019 external review. This approach has greatly reduced the risk of introducing opinion bias from direct stakeholders (delivery partners and direct beneficiaries).
The main data sources are given in Table 2.
Table 2: Main data sources
MAIN CATEGORIES
All GACP-related documentation, including memoranda of understanding (MoUs), key programme and project documents, and minutes from the Strategic Board and Steering Committee.
GACP’s monitoring and reporting data.
A review of key policy documents and associated research from think-tanks, academics and other donors.
A review of comparative programmes.
Views of the PT, all project leads and all delivery partners.
Views of GACP projects’ direct beneficiaries/recipients of technical assistance.
Views of experts, academics, thinks-tanks, business representatives, (non-beneficiary) anti-corruption organisations, and civil society organisations (CSOs) (external stakeholders).

A bibliography can be found in Annex 4. In total, the EL team conducted more than 100 stakeholder interviews at headquarters and in the selected regions (see Annex 5, disaggregated by gender). All triangulated sources are listed in the relevant footnoted and annexes. When evaluation findings are only according to the views of some stakeholders, this is clearly noted.
### Ethical considerations
With this evaluation, the EL team was able to work independently and without interference in their assessments; ensure the anonymity of beneficiaries and other stakeholders; and follow a broad-based participatory approach by consulting with a range of stakeholders, including public and private sectors and men and women. All team members are required to declare any actual or potential conflicts of interest with their work and respect the confidentiality and integrity of any information and data that they access.
### Variations from the approach paper
It was envisaged that the Cycle 2 Approach Paper would further develop EL’s approach to contribution analysis. Cycle 1 evaluation is only expected to build and (as possible) assess contribution stories in selected regions, using mixed quantitative and qualitative evidence. In addition, a full question (EQ6) was dedicated to assessing the factors linked to the context and the programme contributing to and/or hindering the achievement to date.
The contribution methodology, recently approved by JFU, was made available to the EL team at the time of writing this report. While the full methodology could not be used as a result, the team used the guidance to present the projects’ contribution to results (see Section 3). For each project, the team assessed its contribution against achieved outcomes, as well as the Stories of Change and/or results reported in the recent comprehensive spending review.
At the time of finalising this report, the programme was facing an uncertain future due to a reduction in the UK government’s ODA budget. The EL evaluation considers that these exceptional circumstances would call for an entirely different set of recommendations, should the programme be negatively affected. The recommendations listed in Section 5, which include recommended actions spanning over the next two years, have been kept unchanged and in line with the original lifetime of the programme.
### Limitations
This exercise comes with a number of limitations, which the EL team mitigated as follows:
- There is an important evidence gap related to effective AC measures and their impact in reducing corruption.[9] In addition, measuring the scale of corruption and change in corruption levels relies on proxy, perception-based data such as Transparency International’s Corruption Perception Index (CPI), which the PT has not retained as an impact indicator. In this evaluation, most projects focus on the OECD DAC criteria of effectiveness as a result, by looking at progress against intermediary and final outcomes (not impact).
  [9] DFID (January 2015), Why Corruption matters: understanding causes, effects and how to address them”, Evidence Paper on Corruption. https://www.gov.uk/government/publications/why-corruption-matters-understanding-causes-effects-and-how-to-address-them
- The programme’s geographical coverage (see Section 2.3) has led to some results, not only in middle-income countries, but also in low-income countries such as Timor Leste and South Sudan (see Annex 7). Because of limited time and resources, interviews with direct beneficiaries were only conducted in selected middle-income countries in the two sampled regions.
- This evaluation took place during the COVID-19 pandemic, which means that all data has been collected remotely. The EL team’s ability to understand the context in which the programme operates has remained limited as a result. As a mitigation measure, two national consultants (one Kenyan, one Malaysian) supported this evaluation and particular care was given to interviewing a range of stakeholders, including direct beneficiaries, CSOs, experts and other donors. The quality of stakeholder interviews was deemed good, despite using remote communication.
- While all AC commissions interviewed have benefited from the support of a range of GACP partners, notably the multilaterals, GACP’s specific contribution was unknown to them. In response, the EL team put particular care into framing their questions accordingly. It is also important to note that some stakeholders (notably FATF-Style Regional Bodies (FSRBs)) are both direct beneficiaries and delivery partners of the programme.
- There are still some gaps in the logframe (see Section 2.4). This includes the lack of technical definitions for each indicator and limited progress in developing more qualitative tools (including Stories of Change, communities of experts and surveys). These gaps have made it more difficult for the team to appreciate the programme performance as a whole. In response, the team spent more time discussing result measurement issues with the delivery departments and partners.
- Some information was deemed too sensitive to be shared. This most notably concerned ongoing investigation and asset recovery cases, which IACCC and/or StAR are supporting. On occasion, some stakeholders directly benefiting from their support could not be reached.
# Programme design, programme management, and portfolio coherence
## Governance set-up and programme management
### Governance set-up[10]
[10] Interviews with GACP PT, JACU, formerly DFID, HMT, FCDO posts; business case, Strategic Board and Steering Group minutes and action logs.
Figure 3: GACP’s governance set-up

The programme’s governance set-up has worked relatively well, with participation from all government departments and JACU involvement ensuring a close articulation with HMG policy priorities. The programme’s governance set-up has been closely aligned to that envisaged in the business case. It has worked well on a number of fronts:
- The Strategic Board, chaired by the programme SRO, has met as scheduled every six months, with participation from all delivery departments (formerly DFID, National Crime Agency, GDMP and HMT) and the Home Office/JACU. JACU’s participation has enabled a close articulation between GACP and UK policy priorities, with JACU playing an effective coordination and oversight role linking GACP with the UK’s AC Strategy. The PT has also produced comprehensive dashboards and regular papers[11] for the Strategic Board’s consideration over the review period.
  [11] These papers have included an approach paper on adaptive management, SBs, G&I and synergy.
- The Steering Group has also met as scheduled every quarter, with participation from all delivery departments; external speakers were at times invited. In addition, the PT has organised stand-alone sessions with delivery departments to focus on specific issues, notably G&I.
FCDO posts in priority countries have not been involved in the decisions made centrally. The PT has maintained a close partnership with them over the years, although none participated in the Strategic Board as observer as initially envisaged.[12] FCDO posts in Indonesia, Malaysia and South Africa confirmed that they have regular contact with the PT, although they do not take part in the decisions centrally. FCDO posts in priority countries have increasingly played an oversight and coordinating role, however, working closely with the PT. GDMP and National Crime Agency have staff deployed in a number of priority countries. In addition, the programme is also funding full-time or part-time equivalent positions in South Africa and Indonesia. In contrast, some FCDO posts in non-priority countries were found to have little familiarity with the programme.
[12] According to the business case, the programme is designed to “support channels that are best managed through a centrally-run programme for example due to their cross-border nature or where there is a lack of highly specialist expertise in new and emerging areas (such as beneficial ownership transparency) at country level”.
The large number of projects to cover and high frequency of relatively short meetings have left the Steering Group with little “stock-taking” time, involving more in-depth discussion on the programme’s performance as a whole. As a result, opportunities to take the long view and capitalise on cross-government learning (see Section 2.6) have remained limited. The time allocated for the Steering Group and Strategic Group meeting seems quite reduced, compared to other global, yet smaller, PF programmes, like the Global Business Environment Programme.[13] Staff shortage has also meant that the same people ended up representing their departments in the Steering Group and Strategic Board.
[13] GBEP’s Council meets every six months for half a day, after two days of preparation by the FCDO-GBEP programme teams (technical meeting).
### Programme management[14]
[14] Interview with GACP PT, GDMP; finances; quarterly reports; Prospero; risk register; MoU with cross-government partners and multilaterals; Strategic Board and Steering Group minutes and action logs; Transforming Procurement Systems submission; 2018 and 2019 Annual Reviews.
Three important programming decisions were made over the review period: (i) to stop funding the Extractive Transparency Industry Initiative in 2019, (ii) to defer the Behavioural Science project until the next financial year, and (iii) to launch a new GBP 1.1 million project, Transforming Procurement Systems, in response to COVID-19. The decision to stop funding the Extractive Transparency Industry Initiative came from a recommendation in the 2019 Annual Review, which questioned FCDO’s value-add vis-à-vis formerly DFID funding and the initiative’s focus on low- rather than middle-income countries. More recently, the PT was required to defer the Behavioural Science project (as the only project which was yet to begin) until next year as part of the ODA reprioritisation exercise, leaving an important gap (see Section 2.5, Box 6). Following the global COVID-19 pandemic and rising risk of corruption related to emergency procurement, the PT also encouraged its delivery partners to develop a new procurement project, Transforming Procurement Systems, which was approved in September 2020 (see Box 2).

Box 2: COVID-19 pilot: Transforming Procurement Systems
Transforming Procurement Systems was developed over a five-month period, from April until August. The aim of the project is to capitalise on the considerable shift in political will arising from COVID-19 risk, by (i) responding to the needs for thorough and timely data and greater capacity to support procurement decisions, notably in emergency and health care; and (ii) accelerating essential procurement reforms, while engaging with citizens and the private sector. / The project’s budget combines new funding and funding reallocated from other areas of the GACP budget. Three out of 15 countries (South Africa, Mexico, Indonesia) were short-listed, after a review of the partners’ ongoing activities, the political context and impact of COVID-19, and stakeholder mapping. Open Contracting Partnership (OCP) was also brought in as a new partner. / Each partner has put in place a range of mostly new activities, playing to their respective strengths. This includes linking BO and procurement data and leveraging BO transparency in procurement for Open Ownership; creating an enabling environment for open contracting, developing open contracting tools and empowering civil society for OCP; and providing training and guidelines on corruption risk management in emergency and health procurement for UNODC.

The first year of operation has otherwise been used to develop the “nuts and bolts” of the programme. Limited staff resources have at times reduced the PT’s ability to follow up on agreed actions, however. 2018/19 was spent negotiating and finalising MoUs with multilateral partners (completed in December 2018/March 2019) and HMG departments (completed in May 2019) and the reporting requirements; developing a risk register, the programme logframe and other MREL tools; and agreeing on approaches for G&I, SBs and VfM. The programme also regularly tracked its response to the recommendations made in the 2018 and 2019 Annual Reviews. Due to staff shortages (in part because of short-term redeployment), limited resources,[15] and its combined role as programme coordinator and FCDO lead, the PT has yet to follow up on some agreed actions and recommendations, however.[16]
[15] This is despite drawing additional resources from PFDU and MREL.
[16] These include notably the work that the PT initiated with delivery partners on G&I action plans after the 2019 recommendation on an in-depth VFM assessment; and consolidation work on the programme logframe and use of milestones.
Concerning risk management, the risks and risk mitigation measures listed in the risk register appear comprehensive, but context-related risks are not included. The risk register, which is centrally managed, includes the key programme and project risks in four categories (operational, fiduciary, delivery and safeguarding). This register, which is aligned with JFU guidance, is regularly updated and was used to inform the Steering Group discussion on risks associated with COVID-19. The main gap concerns the risks to individual projects related to the different contexts in which the programme is operating. The risk of unintended effects is notably missing, including the risk of causing unforeseen harm to vulnerable groups and the risk of uncoordinated actions when promoting BO transparency (see Section 3.2).
Concerning finances, the programme encompasses complex financial arrangements, which the PT has monitored closely and managed effectively.[17] The team has notably taken appropriate actions to mitigate the risk of inaccurate spend figures and forecasts with cross-government project leads by engaging regularly and requiring monthly updates.[18] The programme has also managed the risk of (mostly) under-spend well.[19]
[17] Complexity of arrangements includes use of different calendars; use of different payment mechanisms (cash/annual payment); frequency of reporting.
[18] All multilateral partners (but StAR) report on finances quarterly.
[19] This included, for example, a submission to JFU to bring forward GBP 700 thousand of OECD spend into FY 18/19.
Figure 4: GACP’s yearly allocation

The PT has followed a pragmatic approach to the ODA reprioritisation, which was used as an opportunity to further scrutinise the use (and VfM) of GACP’s funding by some delivery partners. In 2020, GACP’s budget was reduced by 32% as a result of ODA reprioritisation, with project cuts varying from 15% to 40%. This was done by pausing activities that had recently started and identifying areas where savings could be made. The reputational risk—and, more specifically, the risk of damaging relationships with key partners—was also taken on board.[20] Over the review period, the level of financial detail has varied significantly from one partner to another (from one to six budget lines). Although the PT has on occasion obtained more information on activity costing, visibility on where the money goes can remain somewhat limited.[21] This is further discussed in Section 4.2.
[20] For example, GDMP made a strong case for continuing its activities in South Africa. The PT (SRO) and HMT were still in discussion as to whether a cut in funding to the FATF Secretariat would be in breach of their MoUs.
[21] The OECD project was often cited as a project that had little visibility during the discussion.
## Choice of partners[22]
[22] Interviews with delivery department and partners; business case; delivery partners’ websites; stakeholders in selected countries and regions.
GACP’s decision to choose multilateral organisations as partners has been highly relevant. They are all important partners for the UK. The UK committed to continue its support to multilateral initiatives at the 2016 London Anti-Corruption summit. The multilateral partners, namely OECD, UNODC, FATF and the World Bank/UNODC StAR team, play a central role in shaping and implementing the global AC agenda.
- UNODC both hosts the Conference of the State Parties, the main policymaking body of the UNCAC, and supports the implementation of UNCAC in partner countries. UNODC (as well as having regional offices) can also draw from an extensive field presence from other UN agencies.
- OECD is best known for its convention on anti-bribery, its global forum on anti-corruption and integrity and working groups established to support the G20 AC agenda. Over the years, it has developed ‘internationally recognised’ standards on a range of AC-related issues, including anti-bribery, public procurement and public integrity. Key informants consistently perceived the OECD and its staff to possess high levels of expertise, and the organisation to possess considerable influence.
- StAR is internationally recognised as the lead technical agency on asset recovery and has the convening power of two global organisations, World Bank and UNODC, behind it. UNODC brings the global membership of the UN and UNCAC with an entire chapter (Chapter V) on asset recovery. The World Bank has financial muscle, a country network and a reputation for technical excellence and effective management of multi-donor trust funds.
- FATF is the international standard setter for combatting money laundering and counter-terrorism financing. In addition, its peer regional organisations, the FSRBs (two of which GACP supports), have an essential role in promoting the effective implementation of the FATF’s recommendations by their members.
GACP’s support to IACCC, GDMP and Open Ownership has also grown out of UK’s commitment made in the 2016 AC summit. Fighting corruption is core to IACCC and Open Ownership’s missions, but GDMPhas a much broader mandate, which is to lead the UK’s digital transformation. IACCC is hosted by the National Crime Agency, which leads the UK’s fight to cut serious and organised crime. Open Ownership’s Steering group is made of well-established AC civil society and private organisations.[23] In contrast,GDMP’s main raison d’etre as GACP partner is linked to the user-centred, digital approach that it has developed to support better-informed and more transparent public procurement decisions in the information and communication technology (ICT) sector. This is a narrow focus compared to GDMP’s international offer.
[23] Transparency International, One, Open Corporates, the Open Contracting Partnership, the B Team and Global Witness.
An important development underpinning the first two to three years of GACP’s implementation has been the rapid growth of its bilateral delivery partners, namely Open Ownership, IACCC andGDMP. Over the last three years, Open Ownership, which started as a project with seed funding from GACP, has now grown into a small yet fully-fledged non-profit organisation, with 10 staff[24] and new sources of funding. In recent years, GDMP has expanded its international offer. The launch of GDMP in 2017 coincided with the establishment of GDS’s first international team, with GDMP funding staff at HQ and in post. As foreseen in the MoU, more members have joined IACCC’s founder members, the Five Eyes (UK, USA, Canada, Australia, New Zealand) and Singapore, with INTERPOL joining in April 2019 and nine associate members[25] joining in in July 2020. Switzerland now has a dedicated liaison officer for IACCC.
[24] From an initial four. The team now includes a policy and programme team, technical lead, research lead, human resources and communication.
[25] Cayman Islands Anti-Corruption Commission, Gibraltar Financial Intelligence Unit, Guernsey Financial Intelligence Unit, Isle of Man Financial Intelligence Unit, Jersey Financial Intelligence Unit, Mauritius Independent Commission Against Corruption, Seychelles Anti-Corruption Commission, and Turks and Caicos Islands Integrity Commission.
## Geographical coverage[26]
[26] Interviews with GACP PT, FCDO posts, cross-government lead and delivery partners; business case; flash reports.
GACP’s design decision to work globally, regionally and in priority countries was in large part dictated by its range of partners (including multilaterals). The rationale for working regionally appears strong: GACP’s rationale for providing support to regions was in part driven by FATF’s “follow the money” approach[27] and in part by the establishment of the UNODC regional platforms. The rationale for setting up the regional platforms was the role that they could play in enabling knowledge sharing and consensus building, and creating momentum for change in each region.
[27] GACP business case.
GACP’s approach to working in priority countries has been less effective, however. The choice of priority countries in the business case was first driven by the list of Prosperity Fund priority countries. It also reflects initial interest from FCDO posts[28] and a metric, combining scores on corruption, poverty and UK trade using secondary data.[29] Although eight countries[30] came on top of the list, it was subsequently decided to start with five, including three where GDMP had already begun activities (see Section 2.3).
[28] GACP “engaged with the FCDO’s posts in 18 countries to determine the likely level of interest in participating in the GACP from posts and country governments.”
[29] Secondary data included the Corruption Perception Index (CPI); the World Bank voice and accountability index, poverty headcount ration and GDP per capita; UK export and Doing Business ranking. Countries with lower CPIs have been ranked higher, i.e. have a greater need to address corruption.
[30] Colombia, Indonesia, Kenya, Malaysia, Mexico, Nigeria, Pakistan and South Africa. Brazil was also included in the list in the non-published June 2018 version of the business case.
As shown in Table 3, in practice, however, GACP’s activities have been geographically dispersed, reducing opportunities for a “clustering” of activities in priority countries. As put by one stakeholder, even priority countries have only received “bits and pieces” of the programme, while in non-priority countries, FCDO posts had limited knowledge of the programme. A number of related factors explain this situation:
- The lack of a dedicated funding window for priority countries has come to undermine GACP’s plan to dedicate some of its support to a small number of priority countries. Instead, GACP’s adaptive management policy, as presented to the board in April 2019, mandates the Strategic Board to change budget allocations across projects, with each delivery partner in turn free to make “small changes” across their activities, including their geographical focus.
- GACP’s partners do not have the same country presence, nor do they share the same approach to country prioritisation. When selecting their partner countries, most delivery partners follow a demand-led approach (Open Ownership, UNODC, IACCC, StAR); some “follow the money” (IACCC, StAR,[31] FATF); and others prioritise in-country engagement according to a rolling calendar (FATF in the context of their mutual evaluation). As a result, the PT has had limited success in getting delivery departments and partners (notably HMT and FATF) to prioritise GACP’s priority countries.[32]
  [31] This includes, for example, GFAR focus countries (Ukraine, Tunisia, Sri Lanka, Nigeria).
  [32] The PT and HMT delivery team discussed at length HMT’s plans to complement its support to the FATF Secretariat with direct AML consultancy to Botswana and other countries that were not listed as GACP priority countries.
- The lack of bilateral programmes and limited staff resources in priority countries has also made it more difficult. Unlike formerly DFID’s international Action against Corruption, which was designed to complement DFID’s bilateral programmes by focusing on the “public good”, opportunities to build synergy with PF country programmes have been limited because of their out-of-sync programming calendars and lack of country overlap. While FCDO posts in priority countries have supported the programme, they have had limited resources to do so.[33]
  [33] For example, FCDO posts were expected to play a lead role in organising community of experts meetings and conducting public perception surveys to feed into the programme logframe. This has not been possible, in part owing to lack of capacity and in part owing to COVID-19.
Table 3: GACP’s geographical distribution[34]
[34] Flash reports for all projects.
Projects	Global *	Regional	Individual countries	Priority countries
OECD	✓	✓
StAR	✓		✓
UNODC		✓	✓
IACCC			✓
GDMP	✓			✓
Open Ownership	✓		✓
FATF	✓	✓	✓

*includes global products
## GACP Theory of Change, portfolio coherence, and result measurement
### Theory of Change[35]
[35] Interviews with GACP PT, EL Readiness Review.
Although there has been no significant change in strategic direction since the programme was approved, the ToC in the business case came with several limitations and needed revising. GACP’s primary objective has remained unchanged, as captured in the programme’s old and new ToC, and no project was found to have significantly departed from their MoU objectives. By capturing the programme’s primary objective as an intermediary outcome, and its sub-objectives as outputs, the ToC in the business case had set the bar too high, however, and left no room for the projects’ activities and outputs. In addition, the programme’s primary objective remains hard to define, let alone measure.
GACP’s ToC was revised in May 2020 to reflect the programme’s project portfolio and alignment with the newly developed logframe. While this retrofitting exercise is unusual,[36] it has contributed to making the programme look more coherent and realistic. The new ToC was developed during and after a Readiness Review conducted in 2019[37]using a participatory approach. As well as being aligned to the four logframe themes (see below), the ToC includes (i) three categories of shared activities/outputs (technical assistance, regional and international cooperation, and global knowledge); (ii) a list of assumptions along the result chain, focusing on actors, social norms and incentives,[38] and (iii) reference to the Sustainable Development Goal 16 targets, G&I and a list of SBs.
[36] A programme result logframe is usually developed after the theory of change is completed.
[37] The Readiness Review is available upon request.
[38] The list seeks to capture the main theories of what works and does not work in anti-corruption, from corruption being a principal-agent problem to corruption being a collective action problem. See for example https://www.u4.no/publications/corruption-and-collective-action.pdf
The four themes/intermediary outcomes that now underpin the GACP ToC are recognised as the key foundations to fighting corruption globally and in partner countries. As well as supporting changes in AC laws, policies and regulations that reflect international norms and standards (Theme 1), the programme builds on a growing body of evidence to show that open data, notably in relation to beneficial ownership and public procurement (Theme 2), enhanced international cooperation (Theme 3), and increased public awareness (Theme 4) can help prevent and combat corruption.
The validity of these causal links is explored further in Section 3 and Annex 7, based on the evaluation’s findings in the two selected regions.
The rationale and causal links between the programme’s overall objective and expected impacts are also strong: tackling corruption is key to promoting a sustainable global economy where businesses can compete fairly and the benefits of economic growth can be shared across society, helping to bring the poorest citizens out of poverty. Corruption has far-reaching consequences—prolonging extreme poverty, social and gender inequality; reducing economic activity, growth, trade and investment; and threatening international security.[39] Corruption also leads to wasteful and inefficient use of public resources. As a result of corruption, investments are not allocated to sectors and programmes that present the best VfM or where needs are highest, but to those which offer the best prospects for the personal enrichment of corrupt politicians. For the private sector, corruption increases the costs and risks associated with doing business.
[39] GACP Business Case.
An important causal link that underpins GACP’s design, but has remained more implicit, is GACP’s ambition to act as a catalyst for change for the work of multilateral organisations so they can have more impact globally and in partner countries. This is in part captured in the MoUs and/or project descriptions, and in part expressed by the PT during the interviews, as follows:
- GACP OECD’s support has been designed to encourage cross-fertilisation across OECD’s relevant departments and AC-related workstreams, allowing better dissemination, influence and impact.
- GACP UNODC’s regional platforms are intended not only as technical assistance delivery mechanisms but also as an innovative approach to supporting joint learning and peer-to-peer pressure to achieve results.
- GACP FATF’s main entry point to strengthening AML/CFT systems in ODA-eligible countries is to help the FATF Secretariat increase its engagement with—and support to—FSRBs. To do so, GACP FATF provides funding to the FATF Secretariat and two FSRBs, Eastern and Southern Africa Anti-Money Laundering Group (ESAAMLG) and Caribbean Financial Action Task Force.
The programme has also increasingly encouraged synergy across its projects and partners as a way to maximise results, as discussed in the next section.
### Portfolio coherence and synergy[40]
[40] Interviews with cross-government lead and delivery partners; GACP quarterly reports; flash reports.
Table 4 shows low, medium, and high opportunities of synergy, as recently identified by the PT in its synergy approach paper.
Table 4: Project’s contribution to GACP themes
Project 1	Project 2	Degree of synergy	Proposed actions
EITI	Open Ownership	Medium	x
GDMP	Behavioural Insights	High	x
OECD	Behavioural Insights	Medium	x
GDMP	OECD	Medium	x
StAR	IACCC	Medium	x
UNODC	IACCC	Medium	x
StAR	UNODC	High	x

In the two sampled regions, the evaluation has identified three types of partnerships in practice: (i) projects that offer complementary assistance to recipient countries, (ii) projects that operate in the same area but have yet to work more closely together, and (iii) projects that are at risk of duplicating. Examples of synergy are given in Box 3 for South East Asia.
Box 3: Unpacking synergy across projects in South East Asia
Financial investigation and asset recovery / UNODC and IACCC have cooperated well, and, from a beneficiary point of view, offer complementary assistance, as confirmed in Malaysia. UNODC and StAR are also well coordinated both within and outside the StAR partnership. StAR takes part in UNODC regional workshops (including on BO in Malaysia) and jointly delivers technical assistance. When StAR cannot meet demand, UNODC may pick up the excess capacity building work, usually badging it as delivered by or with StAR. / In principle, StAR’s country work occupies a “middle ground”[41] between the applied casework of IACCC and UNODC generalised technical assistance. The evaluation noted a risk of duplication between IACCC and StAR, however: both organisations facilitate the links between the affected country and other jurisdictions, including financial centres and offshore jurisdictions, and there seems to be a lack of awareness from both organisations on what the other is doing when working in the same country. / Public procurement and data transparency / In South East Asia, the UNODC regional platform has offered training on BO, with all participating countries agreeing to specific actions under an outcome statement. In the outcome statement, participating countries are encouraged to consider the “feasibility of making the registers of beneficial owners accessible to the public through online publication, including in open-data format” and “promote and support the use and monitoring of beneficial ownership data by the civil society and media”, hence providing a useful entry point to Open Ownership’s work. UNODC is also interested in exploring e-procurement work as an effective AC measure, and could benefit from GDMP/Open Ownership/OCP operational work. While UNCAC has an article on procurement and public finance management, e-procurement is currently not well covered in UNODC guidelines.[42] OCP has started collaborating with UNODC, including on developing an open contracting red flags prototype (leveraging its existing methodology) in Indonesia. / There is good complementarity and partnership betweenGDMP, Open Ownership and OCP. Typically, GDMPfocuses on developing new prototypes, which can then be taken up by Open Ownership and OCP. GDMP’s in-country presence has also opened doors for Open Ownership and OCP in partner countries. GDMPand OCP have been partners since signing a MoU in March 2019. The collaboration between Open Ownership and GDMP started in early 2020 when the Bluetail protocol was developed. The GDMPteam introduced Open Ownership to the Indonesian authorities at around the same time (see Annex 7). A BO workshop on potential areas of support—including beneficial ownership data standards—was held in August 2020. Concerning public procurement, GDMP and Open Contracting Partnership have recently presented the Silvereye protocol to the Malaysian authorities (See Annex 6). In Malaysia and Indonesia, there are still some hindrances to making BO and procurement data publicly available, however, and the information management tools proposed by GDMPare also perceived as quite “niche” (see Section 2.5).
[41] StAR 2019 External Review.
[42] UNODC (2013) Guidebook on anti-corruption in public procurement and the management of public finances. https://www.unodc.org/documents/corruption/Publications/2013/Guidebook_on_anti-corruption_in_public_procurement_and_the_management_of_public_finances.pdf

### Result measurement and reporting[43]
[43] Interviews with GACP PT, PA consulting; delivery partners; feedback forms received from cross-government lead and delivery partners; EL Readiness Review; GACP logframe; UNODC GLO logframe and annual report, StAR annual report.
The programme logframe is comprehensive and ambitious. The logframe, and its articulation around four main themes—namely AC policies, laws and regulations in place (Theme 1); transparency (Theme 2); cooperation on AC cases (Theme 3); and raised awareness (Theme 4)—capture GACP’s project portfolio relatively well. The choice of indicators is broadly adequate, with the logframe combining quantitative and qualitative indicators and drawing from primary and secondary data sources. There was also a good attempt to draw from already existing logframes from the delivery partners (namely StAR, UNODC, and, to a lesser extent, FATF).
At the time of writing this report, the programme still faced a number of challenges on result measurement, owing to a combination of factors, including the programme’s level of ambition, limited monitoring and reporting capacity (including from partners), and staff redeployment during COVID-19:
GACP’s plans to mix secondary with primary sources, by using communities of experts and conducting a survey in priority countries, have yet to materialise. A first community of experts consultation was held in Indonesia with a view of meeting every six months, but this was put on hold as a result of the pandemic. It was also assumed that FCDO posts (with support from the PT) would have sufficient resources and capacity to lead on the two exercises.
Box 4: Use of communities of experts[44]
[44] Interviews with FCDO Indonesia, community of experts members; community of experts minutes.
GACP plans to establish communities of experts in the five countries where it is working bilaterally. The communities comprise a range of stakeholders that have expertise and insight on AC in their country. The purpose of the communities of experts is to provide balanced, independent and expert opinion on the progress, achievements and barriers to tackling corruption through GACP’s four themes. The PT is responsible for coordinating the work, with a country-based FCDO lead in each post expected to provide administrative support, host the meetings, facilitate sessions, produce write-ups and communicate findings to the GACP team and broader community. The first community met in Indonesia in January 2020. The first meeting was mostly used to introduce GACP and briefly discuss the themes (including G&I) in the country context. The community was expected to meet every six months, but this was put on hold during the pandemic. Plans to start the community in Malaysia were also put on hold.

- Setting milestones has been a steep learning curve for some projects. The PT, with support from MREL services, started working on the project milestones/indicator targets after it became apparent that all milestones in Year 1 had been exceeded. This work was still ongoing when the COVID-19 pandemic started.
- Delivery partners have shown a strong appetite for using qualitative MREL tools, starting with Stories of Change, as first piloted in early 2020 with support from the MREL team. There has been slow progress since, although additional capacity and the recently launched JFU guidance should help.
- All delivery partners report against the logframe once a year, but this is not used as an opportunity to discuss, validate and communicate their achievements against the programme intermediary and final outcomes. For example, the outcome achievements in the logframe do not feature in the good news stories in the quarterly reports and dashboards.
- As discussed in greater length in Section 4.1, the G&I result measurement remains quite limited.
- More specific issues related to the logframe were identified as follows. These are discussed in more detail for each project in Annex 6:
- At an outcome level, under Theme 1, improved polices, laws and regulations are given prominence over improved practices, which GACP’s delivery partners also support.
- In the absence of complementary information, the shared outcome indicator developed for all multilaterals under Theme 1 in effect counts “apples and pears”—with each multilateral partner using different definitions and units of measurement to measure progress.
- Feedback from delivery partners collated as part of a recent consolidation exercise has yet to be taken on board.[45] StAR’s country engagement and policy influence is not well captured across all three themes.
  [45] This work was facilitated by PA consulting.
- The indicators used for FATF are not specific enough to GACP; all core FATF activities are reported and the link with GACP’s priority regions and countries is not made.
- The intermediary and final outcomes under Theme 2 on procurement are ill-fitted to GDMP’s agile approach, consisting of a scoping, discovery, alpha (piloting), beta (implementation) and live phase.
- Due to the logframe’s vertical structure, the link between UNODC technical assistance in public procurement, BO and investigations—all currently listed under Theme 1—and Theme 2 and 3 is not made.
## Relevance (and additionality) of GACP projects[46]
[46] Interviews with GACP PT, cross-government lead and delivery partners, and stakeholders in East Africa (ESAAMLG, Kenya); StAR 2019 External Review.
The relevance and additionality of GACP projects have overall been strong, yet varied. All projects (except Behavioural Science and OECD (see below)) have combined diagnosis work with a demand-led approach to deliver technical assistance that is relevant to partner countries. They have all considered coordination issues to avoid duplication and ensure they add real value. The evidence collected in the selected regions and elsewhere nonetheless points to mixed performance across GACP projects on this front:
- GACP UNODC’s regional platforms have been initiated by carrying out an extensive scoping, stakeholder consultation and needs assessment exercise in all participating countries. Particular emphasis has been put on getting member countries to sign up to a list of recommendations during the launch events. The regional focus is to a large extent justified by the many shared characteristics that regional member states are facing. Each country in East Africa and South East Asia is also uniquely different. This is where the rationale for using a regional approach stops and where UNODC starts implementing activities at a country level (also with GACP funding). GACP comes under UNODC’s multi-donor Global Programme,[47] hence ensuring close coordination with other donor-funded UNODC activities.
  [47] Other contributing donors include Australia and Norway.
- GDMP has endeavoured to make its products relevant to country needs and priorities and ensure strong ownership along the way. This has involved: (i) an extensive scoping and discovery phase to identify options for GDMPengagement in selected countries, involving broad consultations with key stakeholders, and (ii) an agile, user-centred approach to product development, allowing products to be piloted before being mainstreamed, and tailored to the needs of all product users (from government procurement units to private suppliers). In practice, this approach has faced some limitations, as shown in Malaysia and Indonesia for five main inter-related reasons:
1. The discovery phase was too broad in scope, and as a result many propositions stood outside the remit ofGDMP’s main counterparts. It was also carried out by external consultants, and hence did not supportGDMP’s relationship-building objectives.[48]
  [48] In Malaysia, the findings from the discovery phase were also badly received by the authorities.
2. As put by one stakeholder, there has been a tendency for GDMPto use the discovery phase to push its products rather than truly understand stakeholder needs.
3. As a rapidly increasing area of government spend and a sector with potential for new market entries (including from start-up companies), GDMP’s initial focus on procurement in the ICT sector seemed broadly relevant. In practice, GDMP’s main partners, namely the procurement agencies and peer digital companies, have found it relatively narrow in relation to their respective mandates.
4. GDMP’s agile, user-centred approach and its digital solutions—while well understood by peer digital services—has been difficult to apply in country contexts characterised by high levels of bureaucracy and complex decision making.
5. Language and cultural barriers were reported in South East Asia, although the role increasingly taken byGDMP’s in-country project managers has greatly helped.
- GACP FATF uses the additional resources for the FATF Secretariat to engage with some of the weakest and least well-resourced FSRBs and countries in the FATF global network. A decision was made in early 2019 not to fund the recently established FATF Training and Research Institute due to delivery concern. The choice of ESAAMLG seems largely justified: this FSRB was placed on a performance improvement plan before FATF’s second mutual evaluation round started in 2014, and, until recently, was faced with significant delays in membership payments. To a large extent, FATF and its global network create their own demand for technical assistance, as they rate member states’ compliance against the FATF recommendations, some ending up on the grey or black list.
- IACCC’s combined “follow the money” and demand-led approach was confirmed as highly relevant to country needs, as shown by the growing number of referrals to IACCC over the years. IACCC responds to requests from law enforcement agencies on a case-by-case basis. The Centre responds to new demands for assistance where the need for, and impact of, its assistance is likely to be the greatest for the affected state, after consultation with HMG in-country liaisons.[49] IACCC’s training and capacity building support focuses on the skills needed to progress a particular case instead, which means that its support can be put to immediate use.[50] This, combined with its direct delivery of financial intelligence packages and close coordination with other HMG-funded initiatives, has reduced the risk of duplication with other donor-funded initiatives, although this was less clear with StAR.
  [49] IACCC has developed a case prioritisation matrix, which takes into account requesting agency’s capacity and experience among other factors. This matrix was deemed too sensitive to be shared with the EL team.
  [50] When a new request for assistance comes in, a lead officer is assigned to extract as much detail as possible on the viability of the case and conduct due diligence around the referring agency and in-country landscape for acceptance. This will involve speaking to the referring agency, the law enforcement networks based in country and possibly FCDO post.
- StAR is demand driven and requires a request for assistance before it can assist a specific country. StAR, which has limited resources, selects the requests using a number of criteria, including the competitive advantage it has vis-à-vis other providers.[51] There are already quite a few other organisations, starting with UNODC, that provide capacity building assistance to partner countries on asset recovery, however. According to the 2019 external review,[52] StAR is best placed to re-focus on its main mission, which is to support global actions specifically to address the issue of safe havens—a recommendation that StAR has agreed to take forward in its 2021-24 work plan.
  [51] The criteria include alignment to the Partnership Charter and Operations Manual; possibility of successful asset recovery using the StAR results framework; available funding; link to World Bank and UNODC operations; StAR’s competitive advantage vis-à-vis other providers (e.g. ICAR); strategic importance to StAR goals, mandate and visibility; available staff time.
  [52] StAR external review 2019.
- Open Ownership provides integrated support on policy, legal, systems and technology issues related to establishing public BO registers.[53] Open Ownership considers government agencies as their main direct beneficiaries. As a new organisation, they have networked extensively to generate more demand for their work,[54] as well as continued to work with civil society to create public awareness on why open BO data is important. In Kenya, Open Ownership has not met its ambition to develop a more intensive, sustained partnership with the authorities (see Annex 7). Stakeholders interviewed in Kenya confirmed that Open Ownership’s work was relevant and useful, not just for the authorities but also for local CSOs working on BO advocacy, which are less familiar with technical issues. When working in specific countries, Open Ownership faces stiff competition, however: many other (technical or advocacy) organisations[55] with greater capacity, local presence and/or international stature also offer technical advice on BO.
  [53] This support consists of (i) a suite of implementation guides, templates and tools made available on their website, (ii) a help desk and associated website that contains the draft specification of the Beneficial Ownership Data Standard, (iii) enhanced or bespoke support for a limited number of countries.
  [54] The Open Government Partnership annual conferences in Tsibili, Georgia in 2018 and in Ottawa, Canada in 2020 were often cited as main events—where Open Ownership met its main counterparts.
  [55] This includes GIZ, the World Bank, FATF, StAR and UNODC.
Behavioural Science and OECD follow a different logic, focusing on knowledge. The choice and rationale for the Behavioural Science and OECD projects were sound, with the former filling an important knowledge gap and the latter aiming to promote better knowledge sharing, in large part drawing from OECD’s existing expertise.
Box 5: Focus on knowledge—Behavioural Science and OECD
The objectives of the Behavioural Science project were threefold: to build momentum in partner countries for the use of behavioural science as an effective tool to tackle corruption with a view to future scaling up; to strengthen the behavioural science evidence base to better establish an understanding of what works and does not work in anti-corruption; and to build synergy across the programme by aligning Behavioural Insights to areas where greater impact is most likely. This project potentially fills an important gap: the literature suggests that decisions to engage in corruption are not simply driven by cost-benefit calculations, but influenced by fast, intuitive thinking and social norms. However, there is still little empirical evidence on what behavioural approaches can effectively tackle corruption. Most experimentation to date has been carried out in labs, with this evaluation identifying only one other ongoing field-based pilot applying behavioural approaches to AC.[56] / GACP is supporting OECD’s existing anti-corruption streams and activities, with a focus on sharing best practice approaches to tackling corruption and enhancing business integrity. The business case points to the importance of global coordination on AC and the breadth of OECD’s related work, but also to deficits in “OECD’s ability to engage on anti-corruption issues in a comprehensive and coordinated manner”.[57] As such, the GACP OECD project supports, among others, the annual OECD Global Anti-Corruption and Integrity Forum; the development of a new online platform; and the sharing of lessons between OECD and non-OECD member countries.
[56] An intervention to tackle petty corruption in the Tanzanian health sector being implemented by the Basel Institute.
[57] GACP business case.

## Approach to learning
Most GACP projects consider their work on raising public awareness and/or knowledge sharing (in addition to their training activities) as part and parcel of what they do (see Section 3.4). For example, GDMP has a full component focusing on the development of global products. In addition to country engagement, StAR de facto acts as a global platform on asset recovery, through participation in global and regional events and hosting a resource library with StAR’s publications and selected external materials related to the asset recovery process on their website.[58] UNODC regional platforms also include some commitments to share best practices, both regionally and globally.
[58] https://star.worldbank.org/resources?f%5B0%5D=category%3A10
At an organisational level, the delivery departments and partners that have piloted new projects and/or approaches have gained significant experience and knowledge on what works. This experience has not been capitalised yet and is only partially integrated in their ways of working.
- Open Ownership was found to have a strong learning function embedded in its organisation, by learning what works and does not work, and, on the back of it, partially adjusting its approach;[59] developing key criteria to support success;[60] producing new policy briefs (for example, on data verification); and innovating with new products (for example, with the forthcoming data visualisation tools and a new disclosure framework).
  [59] For example, as pointed out by one stakeholder, Open Ownership initially withdrew from Ghana after the government decided not to make its BO register public; its position subsequently evolved in other countries, however, with the organisation softening its stance and instead preferring to remain engaged, while waiting for the right opportunity to push for a public BO register.
  [60] Open Ownership, EITI (2020) Catalysing transformative change in beneficial ownership transparency https://www.openownership.org/uploads/Opening%20Extractives%20Research%20Report.pdf
- GDMP has also used its first years of operations to learn and adjust, although this has yet to be fully capitalised upon. In Malaysia and Indonesia, GDMPstarted to work in provinces after its first developmental (discovery) phase, where it is deemed easier to engage and promote changes. GDMP’s scope also evolved after GDMPassociated with OCP from early 2019 to focus on open data, a main entry point to AC.[61] There was strong evidence of learning among individual GDMPstaff on what has worked and has not worked in a given context. The learning across all GDMPpriority countries, however, has yet to be capitalised in the draft regional strategies.[62]
  [61] Initial plans were to include four workstreams in each project: strategy and policy, products and platforms, practices and processes, and people and capability. In practice, GDMP’s strategic focus is better captured in its five pillars: assuring plans before money is spent, assuring service delivery, designing procurements and contracts, building institutional capabilities and capacities; and publishing open contracting data.
  [62] It is worth noting that GDMP’s regional teams were disbanded as a result of ODA prioritisation.
- Similarly, IACCC took an early decision to associate with small financial centres, after learning from its first years of operation, when supported investigations repeatedly encountered difficulties coordinating intelligence gathering from smaller financial centres. As these smaller centres cannot afford to deploy full-time representatives into IACCC, a new category of associate membership was created as a cost-effective way of bringing them in.
GACP’s governance (and reporting) mechanisms, however, are not sufficiently well set up to play more of a challenge and learning function. As discussed in 2.1, because of limited time and resources, opportunities to capitalise on cross-government learning have remained limited.
# GACP’s contribution to its primary objective
This section assesses GACP’s performance across all four themes, mostly focusing on the selected regions/countries. A brief context analysis for the two regions and countries is available in Annex 6. This context analysis, together with stakeholder interviews and a documentation review, was used as evidence to generate a detailed contribution analysis and test the validity of ToC assumptions for each individual project (except OECD and Behavioural Science). This detailed contribution is available in Annex 7. No unintended or unexpected results were identified for any of the eight projects.
## GACP’s progress under Theme 1 (AC policies, laws, regulations and practices)
### Overall performance
Over the review period, the programme contributed to the following changes in AC laws, policies and regulations:
- GACP FATF reports that 116 laws, policies and regulations (equivalent to the number of upgrades across all 40 FATF recommendations) were changed as a result of its support.
- GACP UNODC reports that four countries have improved their policy, law and/or regulation on matters related to whistleblowing, financial investigations and anti-corruption since the project started in 2017.
- StAR reports that three countries in Year 1 and another three in Year 2 have improved their legislative frameworks on asset recovery as a result of its support.
Much of UNODC, FATF and StAR’s support also aims to strengthen AC practices—from supporting inter-agency coordination on asset recovery (such as in Malaysia) and procurement (such as in Tanzania) to strengthening financial investigations standard operating procedures (such as in Kenya).
The stark difference in results reported across all three agencies is explained by the very different definitions that they use to measure and attribute results to GACP. In the case of FATF, as previously mentioned (see Section 2.4), the results obtained are not solely attributable to GACP.
The next two sub-sections focus on GACP FATF and GACP UNODC’s performances, with StAR’s performance discussed under Theme 3
### UNODC FATF’s performance in selected regions/countries
GACP FATF’s main objective is to strengthen AML/CFT systems in ODA-eligible countries. In recent years, member countries in East Africa have improved their compliance rating to FATF recommendations. More specifically, five out of nine ESAAMLG member countries who have completed Mutual Evaluation Reports (MERs) since 2014 (FATF’s second round) have been upgraded, with Botswana showing the greatest improvement with 31 upgrades.
These improvements can be attributed to a number of factors, mostly irrespective of GACP support:
- In Botswana, progress was down to a mix of high-level political commitment, inter-agency coordination and tightly targeted donor technical assistance. Botswana’s recent progress in strengthening their AML/CFT framework also confirms FATF as an effective international rating mechanism that incentivises poorly rated countries to push for essential reforms. This is particularly the case for countries, such as Botswana, which are put on FATF’s grey list—a decision that can have a negative repercussion on their relationship with international financial institutions and detract trading opportunities, and which commits them to work with FATF to address deficiencies quickly.
- Under IMF leadership, key donors, including the US Treasury and HMT, were invited to participate in an AML/CFT diagnostic scoping mission in February 2019. A technical assistance mission followed in May 2019 to help deliver the country’s action plan, including specifically a national risk assessment. GACP funding was used to cover HMT’s visit.
- It is likely that the high number of upgrades obtained in some countries is also partly explained by the more severe rating that the first countries undergoing the revised 2013 FATF methodology (including Botswana) received.
While not captured in the programme logframe, GACP FATF’s specific objective has been to provide additional resources to the FATF Secretariat to increase its engagement with—and support to—FSRBs. Stakeholder feedback reports some progress on this front, although confirming GACP’s contribution remains difficult in the absence of baseline indicators.[63] According to the FATF Secretariat and ESAAMLG assessors, the increased resources at the FATF Secretariat have helped strengthen FATF’s engagement with FSRBs, as follows:
[63] Most baseline values for FATF’s output indicators are zero, while FATF Secretariat already provided regular training to its FSRBs before the project started.
- The FATF Secretariat has recruited dedicated desk officers for each of its FSRBs to provide quality assistance and day-to-day guidance.
- GACP has also enabled FATF to help improve its training offer. Furthermore, ESAAMLG considers FATF’s approach to training to have become more strategic.
The main stumbling block for FATF and its global network remains the slow completion and mixed quality of the MERs. According to ESAAMLG,[64] GACP funding was specifically used to conduct two mutual evaluation reports (Zambia and Malawi). Both countries have been put on FATF’s enhanced follow-up process, which will lead to further technical assistance to address their AML/CFT deficiencies. While these two reviews would have been undertaken without any GACP funding,[65] the quality and timeliness of the two MERs were said to have improved, reflecting a better understanding of FATF methodology and more time given to preparation. Factors contributing to these improvements were linked to ESAAMLG’s improved membership funding and, with it, recruitment of additional experts; its own learning by doing; as well as dedicated support from FATF Secretariat. HMT’s contribution to this success is hence deemed moderate.
[64] ESAAMLG (July 2020), mid-term review of the UK support to ESAAMLG to strengthen AML/CTF.
[65] ESAAMLG completed seven MERs before or shortly after the MoU with HMT was signed in March 2018: one in 2015, two in 2016, one in 2017, and three in 2018.
### UNODC’s performance in selected regions/countries
The handful of outcome results reported by UNODC—in view of the maturity and size of the project—in large part reflects the project’s “cascading” multi-stakeholder approach and the time it took to implement all agreed steps, from scoping and the launch of the regional platforms to the delivery of technical assistance packages. Before COVID-19, the project seemed well positioned to accelerate the pace of delivery, while country-led reform processes were also expected to start generating results.
Looking more specifically at UNODC’s Action Plan in East Africa (whistleblowing) and South East Asia, the added value of the platforms was confirmed as follows:
- While the cascading approach has taken longer than expected to start implementation in some areas, the regional platforms have evidently allowed UNODC to scale up its technical assistance across the regions, notably in countries where its previous engagement was low. In South East Asia, UNODC used the opportunity of a regional event on whistleblowing in Cambodia (during the transition year) to start providing support to Timor Leste. This eventually led the country to revise its AC law, which UNODC reported as an outcome result that they contributed to in the GACP logframe.
- The platforms have closely matched technical assistance demand with supply. The UNODC has worked closely with relevant AC authorities to tailor its assistance to their needs, while retaining a regional dimension. In East Africa, for example, a follow-up regional event was used to unpack actionable measures that each participant country could take forward to respond to the high-level commitments made on whistleblowing during the launch of the platform.
- The platforms have generated new demands for technical assistance and made relevant authorities more aware of existing gaps, sometimes leading to immediate actions. In Uganda, for example, the authorities changed their whistleblowing regulations after they realised some misalignment to the law.
- Stakeholder feedback confirms that the platforms have leveraged regional capacities and knowledge through fostering peer-to-peer cooperation and sharing information and experience among participants. In East Africa, there was good evidence to show that bilateral discussions took place on the back of regional events, as some member countries showed interest in learning from others.
- Partnership with regional organisations, like EAAAC,[66] and CSO participation have given the regional platforms a stronger foothold and greater visibility in the regions.
  [66] https://eaaaca.com/about-eaaaca
- The regional platforms have leveraged the work of other technical assistance providers, although more coordination is needed. The regional advisers have played a key role in coordinating the work of other contributing partners with UNODC’s Global Programme, seeking complementary support from GIZ and Danida. In East Africa, UNODC to a large extent relies on the East African Association of Anti-Corruption Authorities (with the Asset Recovery Inter-Agency Network for Eastern Africa) to coordinate donor-funded initiatives
- The launch events were useful in terms of “putting the fundamentals in place” by building consensus on realistic and practical reforms. There is also some evidence to show that, by seeking early endorsement from senior policy makers, the platforms may have helped identify AC champions. For example, in Burundi (whistleblowing) and Rwanda (procurement), actions were taken swiftly taken after the authorities (who attended the regional events) agreed to it. While this may be coincidental, it shows at the very least good practices.
Ultimately, the ability to fast-track UNCAC implementation also depends on other contributing factors, including support from other UN agencies and donors, and political will, as recently shown in South Sudan where the government has committed to AC as part of its peace agreement. In South Sudan, the UNODC could use the regional platform as a springboard to step up its engagement.
### Progress towards GACP’s primary objective
FATF and UNODC’s achievement to date, their assessed or likely contribution to final outcomes, and the key assumptions likely to affect the achievement of the projects’ outcomes, are summarised in Table 5.
Table 5: FATF’s and UNODC’s light-touch contribution analysis
Projects	Achievement to date against the outcomes	Assessed contribution to already achieved and/or future outcomes	Factors likely to affect the achievement of future outcomes
UNODC	UNODC has only led to a handful of changes in policies, laws, regulations and practices since the two regional platforms were launched in 2017.	UNODC has focused on realistic and practical actions. / Regional platforms have shown to be conducive to peer learning and identifying AC champions.	UNODC’s combined focus on AC laws and regulations, institutional frameworks and capacity responds to country priorities and needs. / Where partner countries are ready to take concrete actions, impact may take time to materialise.
FATF	FATF/ESAAMLG have shown progress in (i) supporting changes in AML/CFT laws and practices and (ii) conducting MERs as scheduled.	Limited evidence of GACP additionality against outcomes. / Some evidence that GACP has helped the FATF Secretariat to strengthen its support to FSRBs. / MERs have improved in quality and timing, in large part as a result of learning by doing.	Poor FATF rating is likely to prompt countries to take action to improve AML systems, but access to accurate data and technical capacity remains a key constraint.

Key
Achievement against outcomes	Assessed or likely contribution to outcomes
On track	Moderate/strong
Off track	Weak/moderate

Looking ahead, the COVID-19 pandemic has evidently affected the UNODC and FATF projects, especially where progress is hinging on follow-up country visits, as is the case in Botswana (who had yet to be taken off the grey list at the time of writing this report) and in countries where UNODC has only just started delivering its technical assistance.
GACP’s claim for FATF successes mostly hinges on whether the programme can show stronger evidence that the additional resources that it has provided to the FATF Secretariat and two FSRBS have made a difference. According to ESAAMLG, the support that they have received from the Secretariat has improved, but more evidence is needed to show that this has led to faster and better MERs.
With the UNODC project amounting to a 20% share of GACP funds, despite a slow start, it is important that the reforms agreed in the regional outcome statements start materialising in the next two years. Until then, it will remain unclear whether GACP UNODC’s unique demand-led approach, combining high-level commitments, technical assistance and sharing of good practices, has been sufficient to create enough local capacity and momentum for the member states to accelerate their reforms. In addition, while some countries are well capacitated, others are not and are more in need of complementary capacity building assistance. The focus on realistic and practical actions should nonetheless help.
At a higher level of results, there is strong evidence to show that partner countries use FATF/UNODC international standards (and associated technical assistance) as key instruments to guide their reforms. As already widely acknowledged by the two multilateral agencies, while changes in AC laws and regulations will help, ultimately, much will depend on better AC practices. GACP is well placed to demonstrate support in this area, as much of the technical assistance delivered by UNODC, StAR, FATF and IACCC, under GACP funding, is already focused on strengthening the priority countries’ institutional framework and capacity.
## GACP’s progress under Theme 2 (transparency)
### Overall performance
GACP’s progress under Theme 2 has been slow:
- No country established a public BO register in Year 1, and only one (Armenia) did so in Year 2 (against a target of two). Open Ownership nonetheless still expects four new countries to open public BO registers (including South Africa, Indonesia, and Mexico) in Year 3. Its approach to measuring success is tightly framed around its main mission, which is to promote public, central BO registers. This explains why countries, such as Kenya, which have made some progress on BO transparency but not made the data public, are not listed as a result in the logframe.
- The number of entries on the Global Register has exceeded targets, with an additional 6 million entries in Year 1 and 6.7 million in Year 2. The number of countries that feed into the registry has remained unchanged, however, with the additional entries first and foremost reflecting greater compliance from private companies. As such, this indicator does not match with Open Ownership’s initial ambition, which was to set up a truly global register from multiple countries and sources.
- In Year 2, GDMPreports that 12 (procurement) systems have been positively impacted as a result of its support. As discussed with the GDMPteam, this indicator should be read as the number of systems and frameworks that are currently benefiting from GDMP support in the five priority countries. GDMP considers this to be a success in itself, as all projects have received strong stakeholder buy-in and are now in their alpha phase, following an extensive consultation and prioritisation process.
### Open Ownership in selected regions/countries
Stakeholders in Kenya agreed that Open Ownership’s influence on the BO agenda in Kenya has been positive, but relatively modest. While Open Ownership’s ambition is to support BO at all stages of the BO implementation journey[67] a lot of BO transparency success ultimately depends on country-led advocacy efforts and strong technical presence on the ground. The CSOs’ advocacy campaign to promote BO in Kenya started a few years before Open Ownership started its operation, under the Open Government Partnership.[68] Technical expertise has mostly been provided by GIZ, which helped the Office of the Attorney General and today remains Business Registration Services’ main technical partner.
[67] These stages are: consider, commit, legal, systems, data, and publish. https://www.openownership.org/guide/
[68] CSOs involved included Transparency International–Kenya, Humanistic Institute for Cooperation with Developing Countries East Africa, Article 19, Tax Justice Network, International Budget Partnership, and InfoNET Africa.
Open Ownership’s contribution in Kenya is therefore best appreciated through a multi-stakeholder lens: the newly established organisation joins forces to promote BO transparency with other advocacy organisations and technical partners, each bringing their own specialist knowledge. Key stakeholders interviewed in Kenya, for example, confirmed that some of Open Ownership’s inputs into the draft company regulations had been relevant and useful, with Open Ownership being valued for its technical expertise on what “good looks like” and for bringing in a global perspective.
The relatively successful advocacy campaign in Kenya was very much facilitated by a strong lead from the government side, under the leadership of the Office of the Attorney General and, on the more technical side, Business Registration Services. Kenya was one of the first countries in Africa to commit to develop an open BO register in 2015. This was not enough, however, to overcome resistance from within the government. Despite promising developments, the authorities eventually decided not to make the newly established BO register available to the public.
Three main factors can explain the government’s U-turn:
- The government’s desire to comply with FATF recommendations was confirmed as the main factor driving progress on BO in the country; however, FATF recommendations do not require BO information to be made public.[69]
  [69] FATF requirement is that “countries should ensure that there is adequate, accurate and timely information on the beneficial ownership and control of legal persons that can be obtained or accessed in a timely fashion by competent authorities.”
- Those pushing for the progressive legislation passed in 2017 and 2018 were not fully aware of the repercussions that open BO data could have on vested business interests involving politically exposed persons.
- Kenyan authorities were becoming increasingly concerned about the risks associated with data accuracy and data confidentiality.[70]
  [70] As shown in some rare cases, there is a risk that the release of private data could lead to a lawsuit being launched against the government.
Looking ahead, the opportunity for sustained technical engagement with Kenya appears limited, as directly confirmed by Business Registration Services and other stakeholders.[71] The bulk of the work has already been carried out on the BO register software, which is now up and running.[72] On an advocacy front, the prospects for getting the authorities to re-commit to a public BO register in the immediate future are low. This is despite Kenya’s unconfirmed membership to the HMG BO Leadership Group, [73] which requires all its members to sign up to best practice disclosure principles, including on BO data.
[71] In the scoping phase of Transforming Procurement Systems, Open Ownership had shared plans to develop and test their software to collect and store BO data. Open Ownership was also hoping that the Office of the Attorney General would sign a letter of intent to confirm its commitment to public BO register and in so doing seal its membership to the BO Leadership Group.
[72] While the BO register will not be public, the software has been developed to allow the public elements to be reintroduced at “the click of a button”, according to GIZ.
[73] The Leadership Group initiative was launched by John Penrose, Minister of State for Northern Ireland, United Kingdom at the Open Government Partnership Ottawa conference in 2019. This Group came together in 2019 to drive the global policy shift towards free open BO data. The group is comprised of Kenya (to be confirmed), Armenia, Latvia, Mexico, and the Slovak Republic.
### GDMP in selected regions/countries
All projects reviewed in Malaysia and Indonesia were ongoing at the time of this evaluation and had not led to outcome results yet. Because of the agile, flexible approach that GDMP is supporting, it was also difficult for stakeholders to come up with a timeframe for final approval and scaling up (corresponding to the “beta” phase in the GDMPapproach). At the time of finalising this report, the digital services in Penang (Malaysia) and the National Public Procurement Agency (LKPP) in Indonesia focused on their next milestone, namely, the successful design and finalisation of a prototype, using a user-centred approach.
The main contributing factors to GDMP’s success are related to leadership and capabilities. The Malaysia and Indonesia case study noted the following:
- GDMPhas built a strong partnership with the LKPP director who leads on the procurement simplification project. As this director is the main decision maker, the new procurement document, which has been specifically designed for the ICT sector, is likely to be approved. It could then be replicated for other sectors, if deemed suitable.
- Digital Penang values the peer-to-peer support that it has received from the programme. The pilot phase, involving an iterative process and a handful of government agencies, was well under way at the time of this evaluation. However, Digital Penang does not have the autonomy of decisions. Key challenges to a successful roll-out are related to change management and the provincial government’s decision-making and approval process, which, according to Digital Penang, could involve as many as 7 official approving authorities and 13 non-official approving authorities. In Malaysia, a similar project focusing on data sharing for procurement had to be put on hold because of new management.
- GDMP has also started discussing two new protocols Silvereye (with OCP) in Malaysia and Bluetail (with Open Ownership) in Indonesia. Stakeholder feedback was that that these two protocols have not yet convinced the decision makers, some lacking familiarity with ICT products, and that more advocacy will be needed to convince all concerned. The BO agenda in Indonesia is also quite complex, with decisions involving many different stakeholders (not just GDMP’s main counterpart).
### Progress towards GACP’s primary objective
Table 6 summarises Open Ownership’s and GDMP’s achievement to date, their assessed or likely contribution to final outcomes, and the key assumptions likely to affect the achievement of the projects’ outcomes.
Table 6: Open Ownership’s and GDMP’s light-touch contribution analysis
Projects	Achievement to date against the outcomes	Assessed contribution to already achieved and/or future outcomes	Factors likely to affect the achievement of future outcomes
Open Ownership	The number of entries on the global register has increased, but the number of countries with public beneficial ownership registers (including Kenya) has lagged behind.	There are reduced opportunities for sustained engagement, with many other stakeholders (with a country presence) involved. / Open Ownership’s main competitive advantage remains to promote public beneficial ownership registers.	There is strong evidence that BO transparency can help prevent, track and prosecute corruption. / Risks associated with making BO data public include lack of data verification and data accuracy. / Public BO registers are not a global norm yet.
GDMP	Most GDMP projects, including in Indonesia and Malaysia, are still at developmental/pilot phase. / Timescale for scaling-up remains uncertain.	Selected outcomes measure the systems, frameworks and regulations that GDMP has helped to developed.	The main entry point to AC is to promote open data. / GDMP’s supported improvements are mostly incremental and/or narrowly focused. / Evidence supporting the link between e-procurement and/or digital solutions and AC remains mixed.

Key
Achievement against outcomes	Assessed or likely contribution to outcomes
On track	Moderate/strong
Off track	Weak / moderate

Open Ownership’s success will very much depend on whether the UK government will be successful in making public register a global norm by 2023. Progress will remain slow in the interim: at present, the issues of data accuracy (which is mostly self-reported) and lack of verification (as recently shown in the UK[74]) do not make the rationale for open BO data totally convincing. Although Open Ownership argues that data quality problems can be resolved through third-party scrutiny, there is little evidence of this happening in practice.
[74] UK House of Commons (August 2019), Register of Beneficial Ownership , Briefing Paper https://commonslibrary.parliament.uk/research-briefings/cbp-8259/
At a higher level of results, the causal link between BO transparency and AC is relatively strong, yet not automatic:
- According to StAR[75], 70% of corruption cases include the use of anonymous companies. Having access to BO data can increase the ability of law enforcement agencies to investigate bribery and corruption, money laundering and tax evasion; and help government prevent corruption in public procurement, for example, by reducing the risk of conflict of interest. Promoting BO transparency is hence seen as an important solution to both preventing and combating corruption.
  [75] StAR (2011)The Puppet Masters How the Corrupt Use Legal Structures to Hide Stolen Assets and What to Do About It https://star.worldbank.org/publication/puppet-masters
- Open Ownership also argues that BO registers should be made available to the public, a recommendation that businesses agree with. In Saudi Arabia, the B-20 team have also stepped up their recommendations for G20 leaders to establish digital public BO registers.[76] This is because open BO data can help the private sector do their due diligence, identify and manage network and supply chain risks, and ultimately make investment decisions.[77],[78]
  [76] https://www.b20saudiarabia.org.sa/wp-content/uploads/2020/09/B20-Integrity-Compliance-Policy-Paper-30092020.pdf. Their previous recommendations only asked G20 to ensure easy access to, and efficient use of, beneficial ownership information by laying down clear rules governing access to information, and facilitating access for users through adequate measures and guidance.
  [77] B29, 2020, Integrity and Compliance, Policy Paper 2020 https://bteam.org/assets/reports/Beneficial-Ownership-Transparency-B20-Report.pdf
  [78] Open Ownership considers the benefit of public BO registers as four-fold: it helps improve the business environment as private sectors know who they are dealing with; it provides better quality BO data as a result of scrutiny from third parties; it reduces administrative barriers to sharing BO information; and it contributes to sharing best practices internationally.
- Open Ownership recognises that “data needs to be consistently high-quality and easy to search and cross-reference globally” to be useful. Without accurate data, as put forward by the World Bank[79] there are concerns that “the introduction of public registers without proper regulation, systematic verification mechanisms, and sanctions enforcement would simply prompt criminals to develop more sophisticated concealment techniques, or move their money elsewhere, thereby increasing the scale of the challenge that beneficial ownership transparency seeks to address.” At the same time, Open Ownership’s strong alignment to the UK AC agenda and its “follow the UK lead” approach to opening a public BO register remains the organisation’s main strength and raison d’etre.
  [79] World Bank (2020) “Enhancing Government Effectiveness and Transparency: The Fight Against Corruption”, World Bank, Washington, DC https://www.worldbank.org/en/topic/governance/publication/enhancing-government-effectiveness-and-transparency-the-fight-against-corruption
The extent to which GDMP will contribute to more transparent and effective information management systems will also depend on a number of factors. Because of a slow departure and complex phased approach (involving trial and error), it will be key for GDMP to start demonstrating a positive impact on the priority countries’ systems and frameworks that are currently benefiting from the project. More specifically, GDMP’s success—from an international development perspective—will in large part depend on the extent to which projects in their discovery or alpha phase are likely to be scaled up and move into full implementation (beta phase). Only then will GDMP be able to demonstrate that its innovative approach has been transformative and led to lasting improvements in information management systems and practices (including through the use of open data). While the ODA cut reduced staff resources, it has also provided an opportunity for GDMP to prioritise projects that are at a more advanced stage.
At a higher level of results, there is growing evidence from organisations, such as Open Contracting Partnership, that open data can improve public integrity by deterring fraud and corruption.[80] GACP’s decision to bring in OCP under Transforming Procurement Systems could help the programme increase its likelihood of success under this theme.
[80] https://www.open-contracting.org/impact/
Open data requires governments to publish information about what they do, creating data that can be freely used, modified and shared by anyone for any purpose. Digital and information technology can be used for this purpose: for example, digital procurement platforms can be used to make contracts and tenders public. Digital procurement platforms can also help streamline procurement processes. These are two key entry points to AC for GDMP.
Looking more broadly, according to the World Bank,[81] e-procurement can help lower the risk of fraud and corruption by limiting one-on-one interactions between buyers and sellers and, as such, is recognised as an effective tool in combating corruption. The link between e-procurement and AC is conditional on many factors, however. First, as shown in the Indonesia case study, e-procurement systems are often under-utilised or bypassed, which means that decisions can still be prone to interference at every stage of procurement. Secondly, as put by OECD, “there is a misconception that e-Procurement will automatically reduce corruption. E-Procurement, in itself, is not the panacea to correct all ills. Governance reforms are not generated by the technology, but rather by the institutional changes that arise out of them. However, e-Procurement can offer transparency and substantial improvement in process efficiencies and, by enabling truly competitive markets, can reduce prices”.[82]
[81] World Bank, Doing Business (incl. Annex - Selling to the Government: Why public procurement matters), 2017  https://blogs.worldbank.org/psd/voices/restrictive-regulation-is-positively-correlated- to-corruption
[82] OECD (2007) Snapshot Assessment Of Indonesia’s Public Procurement System As At June, 2007 Piloting OECD/ DAC Procurement Jv Baseline Indicator Benchmarking Methodology Version 4 http://www.oecd.org/development/effectiveness/39254688.pdf
## GACP’s progress under Theme 3 (international cooperation)
### Overall performance
GACP has performed well under Theme 3:
- In Year 1 (2018-19), IACCC performed better than expected throughout the result chain: The number of new referrals into the IACCC totalled 36 against a planned 16. IACCC also received more delegations than planned. This confirms that IACCC has successfully raised its international profile, compared to the initial years when it was mostly unknown to most partner countries. The number of new IACCC cases involving coordination of multiple jurisdictions was twice as high as expected.
- According to IACCC’s estimates, its support could potentially generate around GBP 200 million in recoverable and tangible stolen assets.
- In addition to providing support for improved asset recovery practices (see Theme 1), StAR has continued to facilitate international cooperation on asset recovery, as is reported in its annual plan.
### IACCC
Assessing IACCC’s level of contribution can be difficult in complex cases where there are many international players involved. In addition, IACCC utilises partnerships with other HMG-funded in-country advisers (International Centre for Asset Recovery (ICAR), criminal justice advisers, National Crime Agency International Liaison Officers) and the UK Central Authority, which means credit usually accrues to the UK rather than to the IACCC. IACCC’s contribution to Malaysia’s success in the 1MDB asset recovery case has nonetheless been publicly acknowledged by the US Department of Justice and MACC.[83] IACCC has also been involved in two criminal cases involving high-level officials in Kenya, as confirmed by the Kenyan EACC.
[83] ttps://www.justice.gov/opa/pr/us-seeks-recover-more-300-million-additional-assets-traceable-funds-allegedly-misappropriated
Stakeholder interviews at HQ and in Kenya and Malaysia confirm IACCC’s positive contribution and added value as follows:
- By bringing specialist law enforcement officers from multiple foreign jurisdictions into a single location to work on specific cases, IACCC’s model of delivery fills an important gap, which complements rather than duplicates other donor initiatives.
- By associating with smaller financial centres,[84] IACCC brings key players into an international network. The smaller financial centres have a significant role to play in the identification, seizure and recovery of assets related to grand corruption cases in affected states.[85]
  [84] When considering inviting smaller financial centres to join, each full time IACCC member jurisdiction identified the top five smaller financial centres encountered in its own domestic grand corruption investigations. These lists were then analysed against the IACCC caseloads to identify priority countries to be invited. In total, 16 were invited, 9 accepted.
  [85] See, for example, StAR external evaluation 2019.
- IACCC’s facilitation of Mutual Legal Assistance (MLA) requests to the UK and other jurisdictions has helped to expedite the process and increase the chance that a request will be accepted.[86]
  [86] For example, from the investigator who writes the request, to the prosecuting authority for issue, to the Director of Public Prosecutions for approval, to the interior ministry, to the foreign ministry and then submission to the UK. There is huge potential for delay or blockage because of a lack of knowledge of the process or for more nefarious reasons.
- IACCC has helped strengthen partner law enforcement agencies’ ability to frame and draft requests for assistance and intelligence, better understand and follow processes for international cooperation, turn intelligence into evidence to develop a case, and adopt improved investigation practices.
- Success achieved through IACCC’s (and others, notably StAR’s) support was also said to be instrumental in building the confidence of law enforcement partners as well as the confidence of the public and government in those partners that they can more successfully bring grand corruption cases to fruition.
The above successes first and foremost reflect the conducive political environment that has characterised Malaysia and Kenya over the review period. The growing capability of partner law enforcement agencies has also been an important contributing factor. The support that EACC has received from other donor agencies, in particular GIZ, has been an important contribution to its successes. The importance of regional networks in promoting cooperation should also not be underestimated.
### StAR
StAR’s long-term mandate and technical expertise have allowed the organisation to work on less controversial, more technical reforms while waiting to take advantage of a return to a positive environment when it occurs. For example, StAR’s main contribution (besides the publication of the updated Asset Recovery handbook[87]) to asset recovery in Malaysia was related to its support to the MACC’s asset recovery work plan and, with it, improved inter-agency cooperation. StAR’s assistance to Malaysia has also focused on linking Malaysia with other jurisdictions and facilitating agreements on cooperation on intelligence, including in relation to the 1MDB case.
[87] See box 6 below
StAR’s main added value is related to its convening power and policy influence. StAR has also helped develop and facilitate country-to-country links to support international cooperation on asset recovery. Numerous side meetings were held during the 2017 Global Forum on Asset Recovery (GFAR), which was funded by the GACP transition fund, allowing international cooperation on individual cases and requests for technical assistance to be taken forward in subsequent years. The forum notably helped facilitate the return of some of the Abacha II stolen fund, after the governments of Nigeria and Switzerland and the World Bank signed a tripartite agreement setting out arrangements for the return of USD 321 million of funds and the World Bank’s monitoring role. StAR has since continued to hold bilateral meetings including in the margins of the UNCAC Conference of the State Parties and as part of their country assistance.
The GFAR event was also used as an opportunity to launch the GFAR principles on monitoring asset recovery. The principles notably recommend the early involvement of civil society—from the drawing up of the agreement to monitoring the spend of returned funds—to ensure that funds will be used to benefit the populations of the affected states.
### Progress towards GACP’s primary objective
Table 7 summarises IACCC’s and StAR’s achievement to date, their assessed or likely contribution to final outcomes, and the key assumptions likely to affect the achievement of the projects’ outcomes.
Table 7: IACCC’s and StAR’s light-touch contribution analysis
Projects	Achievement to date against the outcomes	Assessed contribution to already achieved and/or future outcomes	Factors likely to affect the achievement of future outcomes
IACCC	IACCC has become well-established and faces a growing demand, including from Kenya and Malaysia. / IACCC has provided intelligence on the most high-profile investigations in over 33 countries. / IACCC has contributed to successful prosecutions (particularly the 1MDB case)/ asset recovery cases, including in Malaysia where IACCC helped to identify and freeze over USD300m in a so-called 1MDB scandal.	Many international players are involved, but IACCC’s model is innovative and adds value. / Partnership with other HMG-funded in-country experts is key.	Opportunities for high-level prosecutions vary with political context. / Success also requires sufficient capacity and goodwill at all stages of the criminal justice chain. / IACCC/StAR work points to the importance of working with smaller financial centres and asset recovery monitoring.
StAR	StAR has met its milestones.	StAR is financed through a multi-donor trust fund.	While more successes are expected, assets recovered are minor compared to the amounts stolen.

Key
Achievement against outcomes	Assessed or likely contribution to outcomes
On track	Moderate/strong
Off track	Weak/moderate

While the least impacted by the ODA reprioritisation, IACCC has had to cut down on its operations since the start of the pandemic. In contrast to other projects, IACCC outputs are slower to achieve remotely: its success largely depends on maintaining and developing close personal relationships with the affected countries. The travel ban has been particularly challenging in countries such as Angola, where there are no other HMG-funded in-country advisers. While StAR can to some extent rely on its INTERPOL/StAR focal point network, its HQ resources for delivery of technical assistance are also limited. IACCC is nonetheless well positioned to claim new successes in the near future, with StAR continuing to remain a trusted, authoritative technical and non-affiliated partner.
The rationale for GACP’s support to international cooperation on grand corruption cases is strong: a recent World Bank report[88] finds that “…in an increasingly interconnected world, mutual legal assistance and other forms of international cooperation between jurisdictions are crucial to effectively fight against cross-border corruption”[89] and that “grand corruption has proven to be a particularly challenging area for public officials and citizens to address, notwithstanding the progress made in confronting petty corruption”.[90]
[88] World Bank (2020) “Enhancing Government Effectiveness and Transparency: The Fight Against Corruption”, World Bank, Washington, DC. https://www.worldbank.org/en/topic/governance/publication/enhancing-government-effectiveness-and-transparency-the-fight-against-corruption
[89] Ibid page 322
[90] Ibid page 341
In the scale of things, however, the asset recovery cases, which IACCC and StAR have directly or indirectly supported, including through GACP, are only a drop in the ocean. According to Transparency International, “only a small percentage of the roughly estimated US$ 400 billion proceeds of corruption from developing countries has been recovered and returned in the last 10 years.”[91] Equally important, strategically and impact wise, is the work that the two organisations are doing to get small financial centres to cooperate while pushing for good international practices in this area (including through the GFAR principles).
[91] Transparency International and UNCAC Coalition Submission to the UNGASS against Corruption: Proposal for a Multilateral Agreement on Asset Recovery 12 June 2020
In addition, IACCC’s work is a useful reminder that identification and seizure of assets is not just the end point of a criminal prosecution for corruption but can, in parallel, inform an investigation and help build a criminal case, leading to more arrests.
## GACP’s progress under Theme 4 (awareness raising)
### Overall performance
Measuring public awareness (let alone its year-on-year change) remains challenging. The PT had plans to generate awareness scores, combining (i) annual surveys, involving business associations, CSOs and legal professionals, and (ii) analysis of media and specialist publications on key AC topics in all priority countries. This has proved over-ambitious, however, largely because of limited staff resources available at posts.
The GACP logframe produces some useful, yet partial, numbers on the extent to which some knowledge products are disseminated, as well as level of satisfaction among participants. This includes the number of visitors on the project’s website. For example, StAR and OECD report 117,000 and 150,000 visitors a year while Open Ownership reports 15,000 unique users. It also shows a high level of satisfaction among participants, although no distinction is made between participant feedback (at global advocacy events) and trainees’ feedback (at training events).
A list of selected knowledge products is given in Box 6. All products seem to fill a knowledge gap among AC practitioners (including CSOs). Their learning uptake remains unknown, however. In addition, the work that multilateral agencies are doing to keep AC high on the global agenda through leadership at events and use of knowledge products is not well captured. This includes, for example, StAR’s GFAR principles and its broader policy influence work.
Box 6: Focus on selected GACP knowledge products
Survey on anti-corruption and responsible business conduct in South East Asia: In 2020, OECD surveyed 229 businesses across Indonesia, Malaysia, Myanmar, Philippines, Thailand and Vietnam on these issues, with a well distributed sample across different types and sizes of business. / Overview and global directory for international partnerships on asset recovery: In 2019, StAR developed a directory which examines strategies for international cooperation through formal MLA requests or informal assistance; and lists asset recovery networks to enable specialists to cooperate. / The Asset Recovery Handbook: In December 2020, StAR launched an updated version of the Asset Recovery Handbook, which provides common approaches to recovering stolen assets located in foreign jurisdictions, identifies the challenges that practitioners are likely to encounter, and introduces good practices. / Policy brief on key steps and existing practices supporting data verification: In May 2020, Open Ownership published a step-by-step guide to data verification both at the point of and following submission. / Digital Buying Guide: Launched in October 2020,GDMP’s online guide presents digital approaches to public procurement that are open, transparent and focus on meeting users’ needs. It sets out practical steps as well as illustrative case studies. / Library of best practices and other handbooks: Part of the UNODC GACP project has been to produce regional handbooks and guidelines in various areas, such as financial investigations and corruption in procurement in East Africa; and MLA, BO and asset declaration, and international cooperation for investigation in South East Asia, with a view of publishing them all on partner websites. / Policy brief on COVID-19-related money laundering and terrorist financing risks and policy response: Published in May 2020, this FATF brief identified new threats stemming from COVID-19-related crime and proposes AML/CFT policy responses to these risks.

The difficulties in commissioning and launching the Behavioural Science project, which also grew out of UK’s commitment under its AC strategy, also shows the challenges of using highly relevant yet nascent, academic research to feed into AC practices. GACP’s experience is captured in Box 7.
Box 7: Commissioning new research in AC: Experience from GACP
With the application of behavioural insights to corruption problems a nascent field, it proved challenging for the PT to define the project scope and identify the right delivery partners. Over 1.5 years, the scope was refined from a general application to public services to a focus on public procurement systems to align with and complement existing GACP work being delivered byGDMP.[92] Some scoping activities failed to identify appropriate entry points. Pilots carried out previously had yielded limited directly applicable learning because piloted interventions did not have an anti-corruption focus. In a subsequent light-touch scoping exercise undertaken by the PT with posts, relatively few embassy staff were able to identify a problem which both related to anti-corruption and could be amenable to a behavioural insights approach. / Proposed delivery mechanisms also evolved through three iterations of the Behavioural Science delivery strategy: from OECD as sole delivery partner to a hybrid approach, combining the OECD as delivery partner in Colombia (where the organisation was best established) and a call for bids for a not-for-profit to undertake scoping and design work to produce a statement of requirements, followed by a competitive tender for implementation. / The GACP call for bids from the not-for-profit sector was well received, but ultimately cancelled as part of Outward Direct Investment reprioritisation in the context of reduced gross national income forecasts. The PT’s final plan for the project was to carry out experiments focusing on public procurement systems in five countries (Mexico, Colombia, South Africa, Malaysia and Indonesia), working in parallel with GDMP. A call for bids for the scoping and design work was issued, and well received by not-for-profits and academia. Twelve proposals were received and evaluated, and a decision made on award. However, ultimately no award was made due to the decision not to move forward with the Behavioural Science project (as the only project which was yet to begin) as part of the ODA reprioritisation exercise. / The project’s cancellation represents a significant lost opportunity to address an evidence gap on the application of innovative behavioural approaches to corruption problems.
[92] Prosperity Fund ​Global Anti-Corruption Programme:​ Summary​, presentation, January 2020

The next section provides an overview of the OECD project performance.
### OECD Anti-corruption and Integrity project
The OECD Anti-corruption and Integrity (ACI) project is contributing to multi-stakeholder dialogue by addressing gaps in the international AC architecture at both global and regional level. The strength of the Global ACI Forum is that it is multi-stakeholder; unlike other experience sharing conferences, it brings together government ministers and officials, civil society and the private sector (for more information on the Global ACI Forum, see Box 8). The ADB/OECD ACI Initiative for Asia Pacific has a more targeted AC focus than other regional networks, and its newly established Business Integrity Network draws private sector perspectives into regional dialogue, in a context of limited existing opportunities for the private sector to engage in relevant fora.[93]
[93] Findings of an independent evaluation of the ADB/OECD Anti-Corruption Initiative for Asia Pacific carried out in 2018 found that the initiative complements other anti-corruption initiatives and networks and is relevant to the AC priorities of member countries.
Box 8: Focus on the OECD Anti-Corruption and Integrity Forum
OECD Global ACI fora held in March 2018 and 2019 enabled exchange of good practice approaches to addressing corruption. Two thousand government, business and civil society participants from 120 countries attended in 2019.[94] / GACP funding has enabled the forum to increase, and promote diversity of, participation. There was a 45% increase in the number of registrations for 2020 compared to 2019. Speakers at the 2018 and 2019 fora included senior politicians and heads of various institutions from low- and middle-income countries in Latin America and sub-Saharan Africa. At least 50% of panellists are women. Over the past two years, the forum has also developed a focus on youth engagement, including inviting young researchers to present their work. / The March 2020 forum was replaced by a webinar series in the context of the COVID-19 pandemic. This has created an opportunity to attract participants who would have been unable to attend in person, however, it may be more challenging to bring together diverse experiences from OECD and non-OECD countries through webinars. In 2021, forum organisers are considering holding global virtual events alongside in-person meetings at regional hubs.
[94] KIIs; Project overview, dated 2019.

Good results have been achieved in relation to:
- Increased dialogue and exchange of good practice between developed and developing countries, with the reach of the OECD Global ACI Forum expanded as result of GACP support.
- Increased collaboration of business, civil society and government on issues of AC, through both the Global Forum and, at regional level, the establishment of a permanent Business Integrity Network as part of the ADB/OECD ACI Initiative for Asia Pacific.
- Greater access to knowledge and expertise on anti-corruption for developing countries through the development and launch of the online ACI Hub which serves as an open-source knowledge repository.
However, while GACP has supported the OECD to extend its reach, there is little evidence to show these efforts have translated into greater influence over and results in ACI-related policy and practice in developing countries.
Regarding knowledge sharing, the online ACI Hub addresses a gap in the international architecture as a repository of OECD knowledge products with the potential to improve access to knowledge on anti-corruption for developing countries. However, for this aspiration to be realised, some funding (in the context of a 55% reduction in the OECD ACI project budget) will be needed to continue to grow the repository and promote uptake among non-member countries. For more information on the Hub and its users, see Box 9.
More emphasis could also be placed on uptake of learning. For example, while there are plans to launch the recent OECD business integrity survey for South East Asia at the ASEAN Business and Investment Summit later this year, it is unclear what else will be done to promote uptake of findings.
Box 9: Focus on OECD Anti-Corruption and Integrity Hub
OECD’s online ACI Hub is intended to serve as a trusted point of reference for AC practitioners to access action-oriented content to support efforts to combat corruption and promote integrity. A beta version was launched in March 2019 and a revised version in March 2020. / Between April and October 2020, the Hub had 35,000 users. According to analytics data, users are mostly English-speaking and from Western countries or Brazil, Russia, India, and China.[95] No data has been processed on users in non-member countries specifically. Key informants interviewed as part of this evaluation, who have been engaged in different aspects of OECD’s work, had mostly not heard of the Hub. / By April 2020, an ACI newsletter was being sent regularly to 21,000 people in 120 countries. Since April 2020, the subscriber list has grown by nearly 18%. The majority of subscribers are European or North American, but there are a growing number from Asia and South America. The open and click rate of campaigns are above both industry and OECD averages.
[95] The top six countries are the US (12.1%), France (9.5%), the UK (5.1%), Brazil (4.6%), India (4%) and Mexico (3.8%).

OECD’s work in South East Asia is analysed in Box 10.
Box 10: OECD/Asian Development Bank anti-corruption initiative in South East Asia
The first regional business integrity meeting was organised as part of the 10th Regional Conference Preventing and Combating Corruption in Infrastructure Projects in Asia Pacific in December 2019, in collaboration with UNDP, ADB and the Government Inspectorate of Vietnam. The event brought together 60 participants from 15 countries. Outcomes of the event included setting up a permanent Business Integrity Network under the Asia-Pacific Anti-Corruption Initiative, of which all 10 South East Asia countries are members. / According to stakeholders, the establishment of a Business Integrity Network under the ADB/OECD ACI Initiative also addresses a gap in the international architecture. The stakeholders note that the ACI Asia Pacific has a more targeted AC focus than other regional networks (although the Asia-Pacific Economic Cooperation does have an AC and transparency working group.) There are also limited opportunities for the private sector to engage in international AC fora. Commissioned by ADB, independent evaluation of the ADB/OECD Anti-Corruption Initiative for Asia Pacific (2018)[96] confirmed that the initiative was relevant to the anti-corruption priorities of the member countries as well as regional and global anti-corruption efforts.
[96] Bhargava, V. (2018) Final Report on External evaluation of the Anti-Corruption Initiative for Asia and the Pacific. Commissioned by the Asian Development Bank. https://www.oecd.org/site/adboecdanti-corruptioninitiative/external-evaluation-final-report-27-december-2018.pdf

Finally, although good efforts have been made to improve internal coordination on ACI within OECD (an implicit objective of GACP funding), coordination deficits persist, with implications for external influencing. The GACP-funded 2018 OECD Strategic Approach to Combatting Corruption and Promoting Integrity responded directly to calls made at the 2016 London Anti-Corruption Summit to improve information sharing,[97] and identifies opportunities to improve coordination through each of the OECD Working Group on Bribery and G20 Working Group on Anti-Corruption. At present, OECD project activities in South East Asia appear to be quite scattered and thinly spread relative to levels of funding received, with recent contributions to the ADB/OECD network fairly minimal (both financially and in terms of staff time), restricting opportunities for cross-fertilisation.
[97] OECD Strategic Approach to Combatting Corruption and Promoting Integrity; https://www.oecd.org/corruption/oecd-strategic-approach-to-combating-corruption-and-promoting-integrity.htm FCDO/OECD MoU on Project Funding.
# Thematics
## Gender and inclusion[98]
[98] For a list of stakeholders and more detailed discussion of the scorecard assessment and individual project progress, see Annex 8.
### Gender and Inclusion assessment
Following minimal consideration of G&I in the initial business case, significant efforts were made by the PT with PFDU Global Social Development Adviser (SDA) support to update the business case and develop an approach paper and vision for G&I in GACP.[99] The approach paper sets out the key links between corruption and G&I and human rights, and their relevance to GACP projects. The evidence base is summarised and the high-level linkages between project areas of work and G&I are used to suggest entry points for addressing G&I. GACP was regarded as a trailblazer on G&I among PF global programmes.
[99] The Global Anti-Corruption Programme’s G&I Approach and Vision February 2019, updated August 2019.
G&I analysis specific enough to be useful across GACP’s areas of intervention has been difficult to commission or develop at the programme level but there has been some success at project level. At programme level, there is a lack of evidence on G&I and corruption in GACP’s focus areas and no common set of priority countries to enable context-specific analysis to inform programme design. A report commissioned from U4 was disappointing in its lack of direct relevance to GACP activities. The EL Topic Guide on G&I and Corruption was more relevant and, with the addition of PT and SDA research, informed development of the G&I approach and vision and identification of potential G&I activities. Some projects have drawn on more context-specific G&I analysis. GDMPcommissioned an extensive study on Gender Equality and Social Inclusion (GESI) in ICT public procurement,[100] with country cases in five countries.[101] The Behavioural Insights project pilots incorporated gender-specific data into design and, where possible, assessed gender differences in impact.
[100] Gender Equality and Social Inclusion in ICT Procurement, Oxford Insights, April 2020.
[101] Indonesia, Malaysia, Mexico, Colombia and South Africa.
Efforts to consult on and share GACP’s G&I vision and approach with delivery partners were partially successful. A presentation by the PT and SDA to UNODC in mid-2019 has proved to be catalytic to the integration of G&I into the GACP-supported project. A similar presentation to OECD has not brought the project team on board. In March 2019, the PT and SDA led a workshop with HMG-led projects that resulted in a mixture of detailed action plans and bulleted lists of actions. The PT drew up action plans for the multilateral-led projects but, although G&I was regularly raised in PT discussions with StAR, the action plan was not shared and the StAR team has indicated it would welcome more specific guidance. With exceptions (such as IACCC), action plans have been little used, even by projects that have taken G&I initiatives forward. This may be because action plans lost relevancy where not updated as implementation progressed.[102]
[102] Progress on action plans for each project is detailed in Annex 8.
Integration of G&I by the projects has been patchy as a result. Some projects have successfully identified ways to bring G&I into design and delivery, invested in G&I expertise and moved forward into implementation (GDMP, IACCC, UNODC), but others have not prioritised G&I in the light of competing priorities or perceived lack of relevance of G&I to their project (HMT, Open Ownership, OECD).
Earlier communication of expectations on G&I would have been helpful but for transition projects a degree of retrofitting was inevitable. Most projects were not designed with G&I considerations in mind and went into implementation before the G&I approach and vision was developed. MoUs did not specify a focus on G&I. This has resulted in some lost opportunities: UNODC, for example, did not integrate G&I into the first regional platforms established (East Africa) in the way it is now doing with later ones (Southern Africa and South America and Mexico). For transition projects, such as IACCC, that began before GACP business case approval, there was no alternative other than to fit G&I activities around the existing design.
G&I capacity and expertise vary across the programme. The PT has made effective use of SDA expertise, including to develop the programme’s G&I approach and vision and to help communicate it to programme partners.[103] However, the PT has struggled to manage delivery partners on G&I, including through follow-up advice and support[104] and monitoring of action plans, although G&I reporting has been encouraged in flash reports and some project-level accountability measures are in place. G&I is a specific agenda item at the OCED and UNCAC project boards, and the IACCC G&I action plan was presented to its Governance Board. The 2019 Annual Review recommended that the PT repeat the March 2019 workshop to ensure that delivery partners have access to G&I guidance and action planning support. This is now planned for early 2021. GACP delivery partners did not attend the PF G&I Champions sessions in 2020.[105]
[103] Interview with SDA, Presentation “Prosperity Fund – Approach to gender and inclusion.” Anti-Corruption Programme July 2019, AR 2019.
[104] Interview with project G&I leads.
[105] To ensure that wider PF delivery partners have access to new G&I guidance and support on action planning (sharing learning, good practice and templates).
Delivery partners vary in their use of or investment in internal G&I expertise. GDMP appointed two successive G&I champions—the first had regular interactions with the PF G&I champions network and his successor has significant experience in diversity and inclusion.[106] IACCC recruited a G&I lead into a permanent team position. HMT and Open Ownership, however, do not have active G&I champions. Multilaterals vary in the extent to which they draw on institutional G&I expertise. The UNODC gender team actively supports implementation of the GACP-funded project, whereas the OECD and StAR projects do not utilise the expertise available to them within their respective institutions.[107]
[106] The new G&I champion was previously with Exceptional Individuals, a charity that supports neurodiversity in the workplace.
[107] The PT has raised this issue with OECD on several occasions.
Support, management and monitoring of G&I was partially impacted in 2020 by staff re-deployments[108] and the ODA reprioritisation/spending review, and 2019 Annual Review recommendations remain relevant. External events reduced staff and SDA resources available for programme-specific G&I support and put some programmatic decisions on hold. G&I was not a high priority for the PT at this time, despite being a strong focus of the 2019 Annual Review recommendations, and projects received little support or incentives. In addition, the programme did not take up PF-wide G&I support opportunities available, for example through the G&I Champions network. G&I activity increased towards the end of 2020 once the PT and SDA team were back to full strength, including the commissioning of additional research from U4 (see below).
[108] Due to other government priorities, largely the COVID-19 pandemic and Brexit.
For the most part, however, project G&I activities already planned or under way were not delayed or reduced by COVID-19-related restrictions or budget cuts. IACCC launched its Women Against Transnational Corruption Hub (WATCH) initiative for women in law enforcement in February 2020 and has followed up with a survey to identify network priorities.[109] GDMP commissioned a report on GESI in ICT procurement[110] and has moved ahead with its user-centred design approach. The exception is UNODC, whose G&I pilots in some regional platform countries have been delayed, but appear to be in the planning phase now.
[109] Activities are currently confined to sub-Saharan Africa.
[110] Gender Equality and Social Inclusion in ICT Procurement, Oxford Insights, April 2020.
G&I results are beginning to emerge (see Box 11) but there is a risk that some will be missed or only partly captured. A G&I-specific output indicator captures the number of G&I activities carried out. It does not, however, allow for a qualitative value to be put on these activities and outcome-level G&I results may be missed where they fall outside the awareness-raising ambitions of Outcome 4. Although the logframe includes indicators disaggregated on gender and other dimensions such as age and ethnicity, there has to date been very little disaggregated data reported.
Box 11: Key G&I results
UNODC: The GACP-funded project provides a good entry point for influencing the wider UNODC global project (GLOZ99) and GACP has succeeded in influencing an increased integration of gender.[111] / StAR: The return of USD 321 million to Nigeria followed an agreement between Nigeria and Switzerland facilitated at the GACP-funded Global Forum on Asset Recovery. The return has been in accordance with the GFAR principles[112]—ensuring that the victims of grand corruption receive the benefits of returned assets and that civil society is involved at all stages. The distribution of returned funds has been through Nigeria’s existing social safety net system and has been tracked by CSOs with DFID Nigeria funding.[113] / OECD: OECD’s Global Anti-Corruption and Integrity Forum has had the most gender-balanced panels of all OECD conferences (with at least 50% women, often more). The forum has also developed a focus on youth engagement, including inviting young researchers to present their work. / IACCC: Launch of WATCH, aiming to strengthen the engagement of female prosecutors and investigators in global anti-corruption response through a peer-to-peer network for learning, support on career progression, sharing good practice, and enhancing operational capability.[114]
[111] Interviews with UNODC, GACP PT, FCO SDA.
[112] StAR (2017) GFAR Principles for Disposition and Transfer of Confiscated Stolen Assets in Corruption Cases https://star.worldbank.org/sites/star/files/the-gfar-principles.pdf#:~:text=GFAR%20Principles%20for%20Disposition%20and%20Transfer%20of%20Confiscated,receiving%20countries.%20Such%20partnership%20promotes%20trust%20and%20confidence.
[113] https://mantra-acorn.com/
[114] WATCH briefing document, IACCC.

Some projects lend themselves more easily than others to producing G&I results. The Readiness Review advised that G&I interventions do not need to be a prominent part of every programme in the PF, but G&I should be meaningfully considered through the design and implementation of all programmes and projects.[115] For most GACP projects there is a long causal chain to primary purpose—e.g. to more equitable growth through encouraging greater integrity in the public and private sectors, and to positive benefits for poor and vulnerable women and men through the return (or prevention of theft of) of stolen assets—although StAR has already shown the potential for this kind of result (if long term). The Open Ownership project, for example, sees limited opportunities for achieving G&I results. It has, however, begun early exploratory research work in South Africa, where the Black Economic Empowerment framework[116] could provide it with an entry point to G&I results. This highlights the usefulness of repeated scanning for G&I opportunities. Project scope can limit ability to achieve results: GDMP’s promotion of user-centred design may lead, in Indonesia for example, to supporting government to consult with a more diverse set of end users.[117] However, its engagement of governments on G&I aspects of public procurement more broadly is unlikely to lead to policy influencing, being outside its (largely technical) scope.
[115] GACP Readiness Review December 2019. Available upon request
[116] Broad-based black economic empowerment is a government policy to advance economic transformation and enhance the economic participation of Black people (African, Coloured and Indian people who are South African citizens) in the South African economy.
[117] Interviews with FCDO Jakarta and GDMP Indonesia and UK.
The discontinuation of the Behavioural Insights project may have removed the programme’s main opportunity to fill evidence gaps on G&I, but other options seem to be emerging. Initial hopes that Behavioural Insights would fill evidence gaps in relation to G&I were not fully developed and the project has now been discontinued. Alternative options may come from (i) the GDMP GESI analysis,[118] (ii) COVID-19 pivot projects, and/or (iii) the GACP research proposal accepted by U4 on social protection and corruption.[119]
[118] Gender Equality and Social Inclusion in ICT Procurement, Oxford Insights, April 2020.
[119] Interview with SDA and PT. Email from SDA.
Engagement with end beneficiaries[120] is not possible for most projects due to the long pathways from their activities to the end beneficiary. GDMP is an exception, with its user-centred approach allowing direct consultations with private sector suppliers, including small start-ups in the ICT sector. Elsewhere, involvement of CSOs as representatives of beneficiary groups is seen in some projects (UNODC, OECD, StAR). UNODC invites CSOs to the regional workshops to support their role in governments’ ongoing work to fast track UNCAC implementation. CSOs representing women’s interests are specifically invited and in South East Asia the private sector is increasingly represented. Consultation with CSOs on prioritisation of topics or on aspects of selected topics that particularly impact women and disadvantaged groups is not evident. In the OECD project, although there appears to have been relatively little consultation on the shape or content of global activities, there is evidence of stakeholder consultation in the context of redesign in response to the COVID-19 pandemic.
[120] End beneficiaries are defined as: male and female workers and entrepreneurs, the end users, and the women, girls, men and boys living in poverty that PF interventions aim to provide benefits for, such as access to services and resources, transport, employment and financial resources.
### Gender and inclusion scorecard (see Annex 8 for more detail)
GACP achieves an amber overall score (not clearly aligned with PF G&I policy minimum standards with areas for development or unable to provide evidence). It meets PF minimum standards on two dimensions (Design and Results). The amber score on the internal capability/incentives dimension is due to insufficient follow up with projects over the past year. The impact of the COVID-19 pandemic and ODA reprioritisation has been taken into account, nevertheless, more prioritisation of G&I would have been expected, particularly following the 2019 Annual Review recommendation to ensure that G&I is fully embedded into project-level implementation plans by end of May 2020. The Accountability dimension is rated Amber due to limited reporting on and monitoring of G&I action plans and G&I risks. The lack of a VfM strategy or equity indicators leads to an amber rating on financial resources.[121] The amber score on the Delivery Partners dimension reflects the varying level of G&I expertise across GACP’s partners. It does not apply to all projects, some of which (GDMP, IACCC, UNODC) would likely be rated green overall if assessed individually.
[121] Planned for 2020 but postponed due to COVID-19 pandemic.
Table 8: Gender and Inclusion scorecard summary
Overall score	Design	Internal capability /incentives	Accountability	Financial resources	Delivery partners	Results

Red	Fails to meet PF G&I policy minimum standards
Amber	Not clearly aligned with PF G&I policy minimum standards with areas for development OR unable to provide evidence
Green	Meets PF G&I policy minimum standards

## Value for money
The programme scores ‘adequate’ overall on the VfM self-assessment, the full details of which are found in Annex 9.[122] VfM touches all aspects of programme design, management and implementation. To reflect this, the VfM scorecard encompasses eight distinct criteria, each of which is scored on a five-point scale based on the quality of the evidence (‘no evidence’, ‘little’, ‘adequate’, ‘good’, and ‘strong’ evidence). Given the stage of programme implementation, the VfM assessment has considered primarily how the programme is set up to deliver VfM, and secondarily, how it is delivering VfM in practice. Evolution of VfM systems in the past year is assessed against the Readiness Review VfM scorecard and is reflected in the direction of travel scores.
[122] During the evaluation, the VfM scorecard was used in a self-assessment exercise by the FCDO programme team to stimulate self-reflection and identify areas for improvement. The evaluation team moderated the programme’s self-assessment based on the findings of the evaluation.
The programme comes with specific VfM-related features, as follows:
- GACP has demonstrated that investments in AC can be high value for money, but that it takes time—and/or a conducive environment—for results to emerge. As partly discussed in Section 3, IACCC was involved in two major asset recoveries in Malaysia and Angola for USD 3.9 billion and USD 2 billion, respectively.
- GACP is helping to strengthen the AC institutions that it supports. The programme has not only invested in young institutions, such as Open Ownership, but is also targeting specific improvements in the way multilateral partner organisations work, including UNODC, OECD and FATF.
- The convening power of multilaterals has allowed GACP and its partners to use existing networks and platforms to showcase their work. In the case of IACCC, the centre has also benefited from co-funding.
- GACP’s support to global events and knowledge products has made it well suited to online delivery. GACP’s partners make their knowledge products publicly available. The switch to online events during COVID-19 has allowed partners to attract more participants, while saving in transport costs.
Having appropriate VfM measures in place is made more difficult by the wide range of GACP partners and the programme’s geographical spread, however. GACP’s partners have different approaches to VfM and cost containment. Plans to introduce benchmarks for unit cost of activities is challenged by the wide spread of countries.
The issue of sustainability has not been sufficiently considered. Most projects have yet to think about sustainability mechanisms to ensure lasting benefits. This includes GACP’s contribution to public goods, notably the OECD ACI Hub and Open Ownership’s global register, which, once launched, need additional resources to be maintained and grow.
Table 9: Value for money scorecard summary
SCORECARD ELEMENT	QUALITY OF THE EVIDENCE	DIRECTION OF TRAVEL	COMMENTS
1. Relevance and robustness of VfM measures in place	Adequate	Adequate	The introduction of a programme-level results framework, with indicators that all projects feed into, has represented a step change to the programme systems. In the past year, the ToC was also updated to align with programming. However, delivery partners have different views about what constitutes VfM and have different standards of reporting.
2. Approach to procurement and cost containment	Adequate	Adequate	Actual and forecasted spend are regularly reported and scrutinised by the PT. Cost containment is difficult to measure, however, given the programme’s geographical spread and range of partners. Cost-saving measures were introduced on the back of the COVID-19 pandemic and ODA reprioritisation.
3. Efficient use of resources and inputs by Prosperity Fund interventions	Adequate	Adequate	FCDO is able to track progress with activities and outputs on a monthly or quarterly basis. The programme is benefiting from the convening power of multilaterals, whereas GACP funding in turn seeks to improve the latter’s performance. Some projects, notably UNODC and GDMP, have lacked efficiency, however, with staff turnover and capacity constraints also continuing to be a challenge for the programme.
4. Validation of PF ToC causal pathways (for primary purpose and SBs)	Adequate	Adequate	The revised ToC reflects the programme’s portfolio of activities and lists detailed assumptions. Risks include the wide geographic dispersion of activities which limits opportunities for activity synergies in priority countries.
5. Sustainability of programme activities	Little	Little	GACP and its projects have not developed comprehensive sustainability strategies. While GDMP’s staged approach (if successful) has good potential for sustainability, other GACP projects have yet to put in place sustainability measures. Where the programme focuses on public goods (such as open knowledge), this is not sufficient for sustainable results: Open Ownership’s global register and the OECD ACI Hub will, notably, need resources to grow and expand.
6. Ability of leadership, management and oversight structures to support programme delivery	Adequate	Adequate	GACP is a complex programme with seven different projects and implementers. Governance arrangements are clear and broadly right for the programme. The cross-government collaboration with JACU has been effective. The role of posts to provide context knowledge and open doors in-country for the technical support has been identified as a key enabler of programme success.
7. Strategies and measures adopted to enhance delivery and mitigate risk	Good	Good	Risk management systems are in place, and there is evidence that the top risks are escalated and discussed at Strategic Board meetings. The programme and its partners have shown good capacity to adapt and learn. Risks associated to individual projects in specific context(s) have not been developed, however, reducing the PT’s oversight.
8. Equity of programme design and approach	Adequate	Adequate	While equity was minimally considered in the GACP design phase, the programme has made significant progress by developing a vision and approach paper, action plans or actions for delivery partners (except StAR), and some logframe indicators tailored to G&I.
Overall VfM assessment	Adequate

## Secondary benefits
By reducing corruption and levelling the playing field for business, GACP has a clear potential to generate benefits for clean international business, including UK firms.[123] However, due to the upstream nature of the programme and its long impact pathways, it is too early for the programme to deliver significant SB wins. With some evidence emerging of the private sector responding positively to anti-corruption reform, the SB potential of the programme has started to develop but is still largely unexplored.
[123] The business case estimates GBP 2.7 million will be generated in terms of UK exports to partner countries. This estimate measures the long-term effect of inclusive growth in partner countries on UK exports and does not include additional income from outward direct investment. The benefits attributable to other mechanisms mentioned in this section are not quantified.
GACP has developed a SB Action Plan. Its revised ToC reflects an ambition to deliver all the six types of SBs, as listed in Box 12.
Box 12: SB categories

Exports: Increased export opportunities can arise from new markets in the partner country (market creation), a widening of the market (more of the same and more innovative goods and services in the same sector) or a deepening of the market (supplying the supply chain in the partner country).
Foreign direct investment: FDI from partner countries increases economic activity in the UK and other countries, competition and productivity and can lead to learning within sectors and along the supply chain.
Outward direct investment: UK and other international companies benefiting from being able to outsource production into the partner country. Repatriation of profits and improvements to the supply chain as well as upskilling (i.e. the focus on the higher skill end of the production process) in the UK—or other countries—benefit the UK or other countries’ economy (applies to manufacturing and private and public services). The economy of the partner country is not included. Improvements here are the primary purpose of PF intervention.
Soft power: Creating good will—an enabling SB. Soft power describes a nation’s ability to attract and persuade, rather than coerce or buy the outcomes it wants. Soft power is a country’s culture, political ideals and policies.
Market access (for UK and other international firms): Improved market access for British and other international companies can have a number of benefits by reducing import costs: consumers may benefit directly, UK and other international producers get better access to raw materials, intermediate goods and skilled labour.
Network effects: UK and other international businesses building partnerships and working successfully with companies from other third countries, gaining new opportunities in markets of third countries.
The evaluation team has identified five distinct channels or pathways through which GACP can generate SBs (see Figure 5). These pathways do not only feature different mechanisms by which SBs are realised, but also start operating at different levels of the ToC and display different relationships with the primary purpose. The pathways, ordered from the most to least proximate to programme outputs, are identified as follows:
1. UK global leadership in AC: With the delivery of activities and realisation of the outputs, GACP signals the UK’s commitment to tackle AC around the world; contributes to set international standards based on established UK best practice; builds reputation for UK businesses overseas; and strengthens the integrity of the UK as an international financial centre.[124] The involvement of HMG partners in the delivery of GACP, specifically the Home Office through JACU, HMT, National Crime Agency andGDMP, contributes to establishing UK institutions as the partner of choice for assistance in anti-corruption in partner countries. Through these efforts, GACP aligns with and contributes to the UK’s AC Strategy.
  [124] More specifically, the business case suggested that GACP’s support to anti-money laundering and illicit financial flows discovery capabilities in partner countries could “protect the UK financial services sector from being exploited by corrupt interests” (GACP business case, page 19). As a result, the integrity and reputation of the UK financial services sector could benefit. In the longer term, this might bolster investor confidence and attract new Foreign Direct Investment into the UK.
2. Partner countries’ demand for international professional services related to AC: Once GACP outputs are achieved, it is expected that beneficiary institutions in partner countries may require follow-up training and capacity building to further expand capabilities in specialist areas such as ICT for procurement.[125] These services (exports) could be offered by international (including UK) professional firms with the right expertise.[126]
  [125] It is worth noting that the UK was recently ranked second (after Korea) in the OECD Global Digital Index. https://www.oecd.org/gov/digital-government-index-4de9f5bb-en.htm
  [126] It should be noted that professional services procured with PF funding cannot be regarded as SBs.
3. Pro-competitive effect of AC policies: Lower corruption can foster greater competition and attract new entrants by making the regulatory environment more predictable and public procurement processes more transparent and competitive. Greater market access can also be achieved as more “transparent data and information encourages sourcing of intermediate and final goods and services from partner countries”.[127] New entries of international business in partner countries could move in tandem with GACP’s overall objective, which is to foster inclusive economic growth in partner countries, and play a reinforcing role through cheaper imports, integration in global value chains, and more and higher-quality capital.
  [127] GACP Theory of Change.
Figure 5: AC pathways to secondary benefits

1. Entry of international business incentive for AC: The entry of clean international business in partner countries could demonstrate the beneficial effect of AC to local stakeholders and incentivise domestic business to act with integrity. This could be especially important for domestic firms that engage with an international business value chain. This mechanism can also play an indirect role in disincentivising a return to ‘business as usual’. While programme documents do not refer to this mechanism explicitly, the GACP PT acknowledges this as a distinct possibility, because UK firms enjoy a reputation as clean and reliable partners internationally.
2. Long-term trade and investment through conducive business environment and inclusive growth: As the benefits of AC are felt in the broader domestic economy and economic growth is enhanced, new opportunities for bilateral investment and trade are expected to arise.[128] This mechanism is dependent on the programme achieving its impacts.
  [128] The business case refers to these as ‘indirect benefits’, while greater openness to trade in the third mechanism is a ‘direct benefit’ (see page 30).
While it is too early in the programme cycle to observe significant SB results, evidence exists of soft power being generated for the UK, globally and in selected countries. Interviews with JACU suggest that the UK is enhancing its reputation as AC champion through GACP. The programme has led to representation for UK government at multilaterals, such as UNODC, stronger relationships with international partners, and ability to influence and shape the discourse around anti-corruption. These benefits had not been expected by government stakeholders. IACCC’s work in Malaysia and also Angola[129] is supporting the UK’s reputation as a global leader in AC.
[129] The British Ambassador in Angola reported that the embassy has enjoyed greater access to Angolan government counterparts thanks to the success of the IACCC’s support to Angola investigators in relation to a sizeable illicit transfer involving the UK financial sector.
In practice, GACP faces several challenges that affect the governance of SB delivery:
- GACP is a varied programme and each project might contribute to SBs in different ways and at different levels of the ToC.
  Box 13: Open Ownership SB potential and relationship to UK Anti-Corruption Strategy
  Open Ownership presents unique opportunities for commercial SBs. Access to BO data can indeed help companies carry out their due diligence with third parties, and in so doing strengthen their supply chain. This in turn can help them inform their investment decisions abroad. Partner countries that Open Ownership helps to set up public BO could potentially generate new foreign investment, including from the UK.
  UK business groups supported the UK government plan for a public BO registry. Promoting the transparency of BO has also been a high priority for B20 (the official business community engagement forum for G20) since 2013. The UK was the first country in the world to launch a publicly available register.
  The prospects to generate SBs through Open Ownership come with challenges in terms of the reliability of BO information and gaps in information on the full ownership chain. In turn, unverified or incomplete BO data could potentially lead to the wrong decisions being made.
- Both delivery departments and partners have shown a lack of familiarity with PF’s approach to SBs. They are not confident about how SBs fit with their projects and perceive SBs to fall outside their remit.[130] Delivery partners also lack the tools to appreciate the causal linkages between what they deliver and the realisation of SBs.
  [130] It should also be noted that SBs were not mentioned in the MoUs governing the relationship between the implementers and GACP. As a result, implementers might be reluctant to actively pursue and report on SB results.
- Another challenge is the lack of FCDO posts’ awareness of GACP in non-priority countries, which reduces opportunities for soft power and networking. This might result in missed opportunities to track and maximise SBs from an early stage of delivery.
Finally, while the SB potential has been explored in theory, engagement with the international private sector has remained limited. OECD’s business integrity initiative in South East Asia has the potential to attract international players, although it is not directly targeted to them. Similarly, most UK and global corporate companies have long supported Open Ownership’s advocacy to establish public BO registers (see Box 13). These links are more the result of the natural positioning of GACP projects to SBs than of an intentional strategy. In fact, the delivery partners largely expect that it will be sufficient to reduce corruption across the economy in order to attract entry of international business. This is also reflected in the ToC, which does not include assumptions specific to SBs.

# Conclusions, lessons and recommendations
This section draws from the report’s main findings in Sections 2, 3 and 4 to identify key conclusions, lessons and recommendations. The priority of each recommendation (high, medium, low), the team or people responsible and the timescales for implementing them are also given. The lessons and recommendations were shared with and commented on by the PT, after validation of the report’s main findings in December 2020. An action planning workshop to take the lessons and recommendations forward was scheduled for March 2021.
As explained in Section 1.2.6, the recommendations are based on the assumption that GACP will continue until fiscal year (FY) 2021/22.
Table 10 provides the main conclusions, lessons and recommendations on programme design, programme management and portfolio coherence. The Fund-level lessons are highlighted in bold italic.
Table 10: Conclusions, lessons and recommendations on programme design, management and portfolio coherence.
CONCLUSIONS	LESSONS	RECOMMENDATIONS
The programme’s governance set-up, while operational, has not allowed sufficient time for in-depth discussion and/or learning.	With each serving a different purpose, projects are unlikely to learn from each other unless the discussion is structured around common issues, countries and/or themes.	Recommendation 1: Consider less regular but longer steering and strategic group meetings to support shared decision making and learning.
The programme has been consolidated around four themes, but MREL tools are not fully operational.	Monitoring GACP’s achievements across 7 to 8 projects, some multilateral, some bilateral, requires sustained efforts and extra resources.	Recommendation 2: Develop an MREL plan and address MREL issues identified in this evaluation.
The programme is geographically dispersed, with each project at present following a different approach to prioritisation.	When working with a range of partners, prioritising countries in global programmes requires an explicit earmarking strategy, both in relation to resources and result monitoring.	Recommendation 3: Allocate more time and resources to seeking opportunities, developing relationships, and capturing results in priority countries.
GACP’s combined support to priority countries (and synergy across its projects) is not well known or articulated.
Most GACP projects have adjusted well to travel restrictions under COVID-19, but the remedial measures need to remain temporary.	AC is a very sensitive field, which requires investing in personal relationships, formal and informal. Relationship building is also key to seizing new opportunities and promoting donor coordination.
UNODC regional platforms, GDMP, Open Ownership and IACCC have been confirmed as innovative.	n/a	Recommendation 4: Capitalise on learning for GACP’s innovative projects.

Table 11 provides the main conclusions, lessons and recommendations on GACP’s contribution to its primary objective for each individual project.
Table 11: Conclusions, lessons and recommendations for individual projects.
CONCLUSIONS	LESSONS	RECOMMENDATIONS
GACP UNODC has produced limited results, yet its combined support to concrete AC actions and regional cooperation is well placed to lead to a significant contribution.	Regional platforms have shown to be conducive to peer learning and identifying AC champions.	Recommendation 5: Start prioritising UNODC’s technical assistance where it has a stronger chance of success and publicise the regional platforms’ outcome statements more widely to generate more legacy and buy-in.
FATF has successfully helped to strengthen AML/CFT frameworks, although GACP contribution is likely to have been minimal.	Partner countries tend to step up their commitment to reforms ahead of FATF (and to a lesser extent UNODC) reviews.	Recommendation 6: Prioritise and more closely monitor GACP’s support to the countries that are next on the FATF/UNODC review calendars.
Open Ownership has not met its ambition to support the establishment of public BO registers, owing to the lack of global norms and standards and, with it, limited political buy-in.	Many countries that have committed to setting public BO registers have yet to be convinced this is the right step.	Recommendation 7: Step up global and country-led advocacy on public BO registers, while exploring other options for public scrutiny.
The timescale for scaling up GDMP’s projects remains uncertain.	GDMP’s agile delivery approach is only understood by a few. Its chance of success can be constrained by heavy bureaucracy and centralised decision making.	Recommendation 8: Ensure that the necessary conditions are in place for GDMP pilot projects to move on to full delivery.
International cooperation with StAR and IACCC has contributed to a small portion of stolen assets being recovered in affected countries, although measuring contribution remains difficult.	IACCC’s and StAR’s work point to the importance of building trust in affected countries, while associating with smaller financial centres.	Recommendation 9: Set up partnership principles between StAR and IACCC to ensure stronger coordinated efforts.

Table 12 provides the main conclusions, lessons and recommendations on GACP’s cross-cutting themes, including VfM, G&I, SBs and learning. The Fund-level lessons are highlighted in bold italic.
Table 12: Conclusions, lessons and recommendations on GACP’s overall achievement and cross-cutting themes.
CONCLUSIONS	LESSONS	RECOMMENDATIONS
GACP has generated relevant knowledge products but evidence of uptake remains limited.	Making knowledge products public is not sufficient and requires active dissemination.	Recommendation 10: Develop a dissemination and learning uptake strategy to ensure GACP’s contributions to knowledge products, global and regional events, and the OECD ACI Hub are shown to benefit selected regions and countries.
The programme has made good use of the multilaterals’ convening power and international presence, while acting as a catalyst for their work.	PF global programmes, such as GACP, can strengthen the work of multilaterals by proposing innovative solutions and/or allocating additional resources to strengthen their own ways of working to maximise impact.	n/a
Many of the GACP-funded innovative projects were found to be off track, but the experience of IACCC shows that this can lead to big returns.	Innovation comes with a strong delivery risk but potentially high returns	n/a
While accountability mechanisms and internal capability do not meet minimum standards, some projects have successfully carried out G&I-related activities and are beginning to achieve results.	The links between AC and G&I from a programmatic point of view can mostly be found at the two ends of the causal chain: activities (with female and CSO participation and, on occasions, end beneficiaries) and impact (inclusive growth). This makes it difficult to track the programme’s contribution to G&I results.	Recommendation 11: Consolidate GACP’s approach to G&I and ensure that G&I results are adequately captured (see Box 16).
ODA reprioritisation has resulted in closer scrutiny and cost savings, but VfM practices vary significantly across delivery partners.	Having appropriate VfM measures in place is made more difficult by the wide range of GACP partners and the programme’s geographical spread. GACP partners have different approaches to VfM and cost containment. Plans to introduce benchmarks for unit cost of activities is challenged by the wide spread of countries.	Recommendation 12: Map out the different approaches of GACP delivery partners to VfM and cost containment to inform good practices and comparability.
The issue of sustainability has not been sufficiently considered.	Most projects have yet to think about sustainability mechanisms to ensure lasting benefits. This includes GACP’s contribution to public goods, notably the OECD ACI Hub and Open Ownership’s global register, which, once launched, need additional resources to be maintained and grow.	Recommendation 13: Develop sustainability plans for each project.
GACP has clear potential to generate secondary benefits in the short, medium and long term. Its cross-government design has already helped to showcase UK global expertise and AC priorities.	Alignment to UK priorities is a useful mechanism for the realisation of SBs. Global programmes, like GACP, that are highly strategic and closely aligned to UK policy priorities can rapidly generate soft power across government.	Recommendation 14: Monitor the likely pathways of SBs and start engaging more actively with the international private sector on the likely benefits of the programme.

Table 13 provides more details on the recommendations, team or people responsible and level of priority.
Table 13: Detailed recommendations, lead, priority and timescale
DETAILED RECOMMENDATIONS	LEAD	PRIORITY	TIMESCALE
Consider less regular but longer steering and strategic group meetings to support shared decision making and learning.	PT / SRO	High	FY 2020/21
Develop a MREL plan and address MREL issues identified in this evaluation. / This MREL plan[131] will help to ensure closer links between result measurement, reporting and communication. It should include roles and responsibilities, data collection processes, data quality assurance, and internal and external learning.	PT / With support from MREL consultant/ consortium	Medium	Immediately
Allocate more time and resources to seeking opportunities, developing relationships and capturing results in priority countries. / Priority countries should feature more centrally in the programme’s approach to MREL. In the absence of joint programming, opportunities for synergy should be actively pursued. FCO posts have a strong role to play and will need more resources. The FCO-DFID merger could help optimise resources on this front.	PT / FCDO posts in priority countries	High	FY2020/21
Capitalise on learning for GACP’s innovative projects / UNODC, GDMP, Open Ownership and IACCC are now in their fourth year of delivery. A stock-taking exercise on what has worked or not appears timely to inform future directions.	PT / UNODC, GDMP, Open Ownership, IACCC	Medium	FY2020/21
Start prioritising UNODC’s technical assistance where it has a stronger chance of successes and publicise the regional platforms’ outcome statements more widely to generate more legacy and buy-in. / UNODC should identify areas of support where it is likely to make more progress in the next two years. Promoting the regional platforms’ outcome statements would allow all relevant stakeholders (including civil society) in country to refer to them and use them for monitoring and advocacy during and after GACP funding.	PT / UNODC	High	Immediately
Prioritise and more closely monitor GACP’s support to countries on the FATF/UNODC review calendars . / The programme should keep track of the list of countries who are next on the FATF/UNODC review calendars. Particular attention should be given to identifying GACP’s added value when supporting the multilateral review mechanisms.	PT / HMT, FCDO delivery departments	Medium	FY 2021/22
Step up global and country-led advocacy on public BO registers, while exploring other options for public scrutiny. / Open Ownership should use its close strategic fit with UK priorities to step up its global advocacy work on public BO registers, while exploring other options for public scrutiny and establishing more sustained partnerships with local advocacy organisations in partner countries.	Open Ownership / FCDO	High	FY 2021/22
Ensure that the necessary conditions are in place for GDMP’s pilot projects to move to full delivery. / GDMPshould articulate the main conditions—standing within and outside its control—that are necessary for GDMP projects to move on to their next phase. GDMPcould use an approach similar to that recently developed by Open Ownership consisting of identifying each project’s sphere of control, influence and interest as a way to explore main conditions for success and possible remedial actions.[132]	GDMP	Medium	FY 2021/22
Set up partnership principles between StAR and IACCC. / These partnerships should establish how their work in country and with smaller financial centres can be made more complementary.	StAR / IACCC	Medium	FY 2021/22
Develop a dissemination and learning uptake strategy to ensure GACP’s contributions to knowledge products, global and regional events, and the OECD ACI Hub are shown to benefit selected regions and countries.	PT / OECD / UNODC, StAR	High	FY 2021/22
Consolidate GACP’s approach to G&I and ensure that G&I results are adequately captured (see Box 16).	PT	High	FY 2021/22
Map out GACP delivery partners’ different approaches to VfM and cost containment to inform good practices and comparability.	PT / All delivery departments and partners	Medium	FY 2021/22
Develop sustainability plans for each project.	PT / All delivery departments and partners	Medium	FY 2021/22
Monitor SBs’ likely pathways and start engaging with the international private sector on the likely benefits of the programme.	PT	Medium	FY 2021/22
[131] See template.
[132] https://www.openownership.org/uploads/Opening%20Extractives%20Research%20Report.pdf. Op.cit

Box 14 suggests priority actions for recommendation 11.
Box 14: Gender and inclusion priority actions

With the PT’s G&I lead and SDA back in role there is now an opportunity to review and consolidate what has been achieved, re-engage with projects and address weaknesses as highlighted by the G&I assessment, the scorecard review and 2019 Annual Review. As the Readiness Review advised, G&I interventions do not need to be a prominent part of every programme in the PF, but G&I should be meaningfully considered through the design and implementation of all programmes and projects.
Priority actions to align the programme to PF minimum standards are:
- Jointly with the projects, review, update and agree G&I action plans to ensure that they reflect current project plans, particularly with respect to any changes as a result of budget cuts or COVID-19 pivots, and that they are realistic in terms of ambition and resources available for implementation. The PF template should be used. (Internal capability and incentives)
- Ensure that all delivery partners are aware of and know how to access and use PF G&I guidance, templates and policy. (Internal capability and incentives: Delivery partners)
- Put a system in place to hold projects to account on G&I, including regular reporting against action plans, and regular review of action plans. (Accountability)
- Delivery partners should ensure access to the level of G&I expertise and resources necessary to implement their G&I action plans and integrate G&I into delivery. (Delivery partners)
- Monitor risks of unintended harm. (Accountability)
- Review the disaggregation of indicators in the logframe to identify where disaggregated reporting is feasible and useful, bearing in mind the data that delivery partners are already collecting but may not be reporting. Clarify expectations with delivery partners on reporting of disaggregated data to ensure that it is reported on at least an annual basis to update the logframe. (Accountability)
- Integrate G&I into the programme’s approach to VfM, including equity indicators in any VfM strategy developed. (Financial resources)
Other recommendation:
Ensure that G&I results are captured in such as way so as to be able to distinguish the different qualities and kinds of results emerging. This is particularly important for outcome- and impact-level results, such as the return of stolen assets that are then used to benefit the poor and vulnerable, and GACP’s success in informing UNODC ways of working. Consider using soft earmarking of StAR funding to encourage more integration of G&I, perhaps with a focus on monitoring of returned stolen assets
.

Theory of change and list of assumptions

Programme-level list of assumptions
Type of assumptions	List of assumptions
Overarching assumptions	Strong political will and a shared commitment to fighting corruption exist globally and in middle-income countries.[133]
External assumptions	Macro-economic stability/absence of external shocks. / Government allocates sufficient resources to support the fight against corruption, including those forms of corruption most impacting the poor and vulnerable.
Behavioural assumptions	Change in social norms (including in public administration) leads to lower tolerance of corruption and levels of corruption. / Civil society and the population at large feel empowered and protected (e.g. whistleblower mechanism in place) to denounce acts of corruption, including through the use of open data.[134] / The banking sector and investors are aware, and respond positively, to improved country compliance to international rules and standards. / Corrupt companies and individuals have less place to hide and the risk of being caught deters them from corrupt actions. / Target groups[135] are independent and free of political interference. / Target groups get full support from government (including the Ministry of Justice) and parliament to adopt new policies, laws and regulations / Target groups have the right capacity, leadership and mandate in place to implement new policies, laws, regulations and practices. / Target groups cooperate well and respond well to peer pressure.
Programmatic assumptions	International norms and standards are effective solutions to strengthening AC policies, laws, regulations and practices, and are mutually enforcing. / Digital procurement platforms are effective solutions to strengthening procurement practices and reduce opportunities for non-compliant behaviour. / The data submitted to international standards agencies and open data systems is accurate. / Innovative data generates useful solutions to tackle and change corrupt behaviours.
[133] The overarching assumption (in the logframe) was concerned with the lack of dramatic political change in country. This assumption may need to be reconsidered: change in government can, on some occasions, bring new opportunities for AC and lead to renewed interest in fighting grand corruption (against former rulers)
[134] This assumption—focusing on actors—seeks to test the assumption that increased transparency will lead to reduced corruption.
[135] Target groups refer to all relevant AC institutions whether they directly benefit or not from GACP projects.

Corresponding assumptions for individual themes/projects[136]
[136] GACP programme logframe.
Themes	Assumptions
Theme 1: Improved AC policies, laws and regulations / (all projects)	There is sufficient available capability to develop fit for purpose policies, laws and regulations.
FATF	Higher quality MERs will lead to countries taking action to improve AML systems. / Technical assistance increases capability and capacity, and therefore leads to partner governments taking action to improve AML systems.
UNODC	As technical assistance is demand driven, it therefore leads to partner governments taking concrete steps towards new legislation.
Theme 2: Transparency (all projects)	There is money/necessity/appetite for procurements in those countries so the systems get used. / Accurate results of procurement exercises are regularly published to aid transparency. / Improved transparency will deter individuals from undertaking corrupt activities. / Increased fiscal transparency makes it easier to detect when corruption takes place.
Open Ownership	Countries will follow the BO Data Standards which will enable data to be shared with the global Open Ownership register. / BO data is accurate and the register is marketed to encourage usage, therefore improving transparency. / BO registers are either mandatory once created (and companies comply), or there is significant work alongside it to encourage companies to sign up. / Technical assistance increases capability and capacity, and therefore leads to partner governments taking action to establish BO registers.
GDMP	Systems are mandatory once created. / These [development] stages will lead to the establishment of open and inclusive digital procurement platforms.
Theme 3: (International cooperation)	The assumption is that a successful grand corruption case on average takes 7-10 years to complete. Therefore, there is a need to focus on the law enforcement actions that build up to asset forfeiture and return.
IACCC	It is challenging to predict the number of law enforcement actions that the IACCC should target, as this depends on the number of referrals and the stage of the investigation in each referral. / Intelligence collection and sharing is essential to identify stolen assets and take law enforcement action. / Police-to-police information sharing is the precursor to International Letters of Request/MLA requests. / Building trust between law enforcement agencies, often via personal relationships, is crucial to the intelligence-sharing process and progressing complex international investigations.
Theme 4: (Increased public awareness)	Improved AC awareness and knowledge enables individual countries to effectively implement anti-corruption measures.
(all projects)	The publications chosen are both reflective of the topical AC themes of key interest groups and important to them. / Improved AC awareness and knowledge leads to society rejecting corruption as an acceptable behaviour. / Increased reporting of corruption and demands for justice change the behaviour of those undertaking corruption. / Accessing new knowledge products improves awareness of the causes of corruption and best practices/approaches to addressing corruption. / Behavioural Insights projects successfully demonstrate that behavioural insight is an effective tool to address corruption.

Evaluation Approach Paper

Evaluation matrix for Cycle 1
Table 14: Cycle 1 evaluation matrix
FUND-LEVEL EVALUATION QUESTIONS	Programme QUESTIONS	programme sub-QUESTIONs	oecd dac criteria	DATA SOURCES	DATA COLLECTION METHODS
EQ 1: To what extent have the key changes made to GACP since it was approved contributed to a stronger likelihood of success? / EQ11: How is the Prosperity Fund learning and why is action on this learning happening more and less successfully?	EQ 1: To what extent have the key decisions and changes made to GACP since it was approved made it more relevant, coherent, and/or likely to succeed?	EQ1.1: Has GACP’s choice of partners and institutional governance set-up evolved since it was approved? Has this made GACP more relevant, coherent and/or likely to succeed, including for the poor and vulnerable? / EQ1.2: Has GACP’s design, including the ToC and result framework, evolved since it was approved? Has this made GACP more relevant, coherent and/or likely to succeed, including for the poor and vulnerable? / EQ1.3: How is GACP set up to learn and adapt, Including through monitoring and evaluation? / EQ1.4: Has GACP evolved to reflect new evidence, recommendations and/or contextual changes (including COVID-19)? Has this made GACP more relevant, coherent and/or likely to succeed, including for the poor and vulnerable?	Coherence / Relevance / Efficiency	GACP programme documentation / Prospero and other MREL tools / External documentation / Key informants / Direct beneficiaries / External stakeholders	Documentation review / Semi-structured interviews / Statistics and timeline
EQ2: To what extent is GACP’s evidence-based, innovative approach and its combined use of UK and multilateral expertise likely to contribute to its primary objective?	EQ2: To what extent is GACP’s evidence-based, innovative approach and its combined use of UK and multilateral expertise likely to contribute to its primary objective? Have any results been achieved to date? (focus on outcomes)	EQ2.1: To what extent are GACP’s innovative projects and/or those implemented by UK lead government organisations on track to achieve their expected results (from activities and outputs to intermediary and final outcomes) and likely to contribute to GACP’s primary objective? Have any results been achieved to date? / EQ2.2: To what extent is GACP’s support through multilateral partners on track to achieve expected results and likely contribute to GACP’s primary objective? Have any results been achieved to date? / EQ2.3: To what extent has GACP led to additional results (expected and unexpected), including through building synergy, in relation to primary purpose?	Effectiveness	GACP programme documentation / Prospero and other MREL tools / External documentation / Key informants / Direct beneficiaries / External stakeholders	Documentation review / Semi-structured interviews
EQ3: To what extent is GACP likely to contribute to results that support gender equality, women's economic empowerment and social inclusion?	EQ3: To what extent is GACP likely to contribute to results that support gender equality, women's economic empowerment and social inclusion?	EQ3.1: Is evidence on G&I being used to guide programming? Has this already resulted in gender-specific activities, outputs and/or outcomes? / EQ3.2: To what extent is GACP’s level of ambition on G&I appropriate and supported by the ToC, programme design and dedicated resources/capacity? / EQ3.3: To what extent is programme analysis, design, consultation, implementation and monitoring in line with PF G&I ToC, policy, framework and guidance (including G&I minimum standards)?	Relevance / Effectiveness	GACP programme documentation / Prospero and other MREL tools / External documentation / Key informants / Direct beneficiaries / External stakeholders / G&I scorecard	Documentation review / Semi-structured interviews / Scorecard analysis
EQ4: To what extent is GACP’s evidence-based, innovative approach and its use of UK and multilateral expertise contributing to learning, including through global knowledge?	EQ4: To what extent is GACP’s evidence-based, innovative approach and its use of UK and multilateral expertise contributing to learning, including through global knowledge?	EQ4.1: To what extent are GACP’s innovative projects and/or those implemented by UK lead government organisations contributing to learning, including through global knowledge? / EQ4.2: To what extent is GACP’s support through multilateral partners contributing to learning, including through global knowledge? / EQ4.3: To what extent has GACP contributed to learning, including through global knowledge, on thematic issues, including G&I? / EQ4.4: To what extent has GACP led to additional, unintended or unexpected results, including through building synergy, in relation to learning?	Effectiveness	GACP programme documentation / Prospero and other MREL tools / External documentation / Key informants / Direct beneficiaries / External stakeholders / G&I scorecard	Documentation review / Semi-structured interviews
EQ5: To what extent is GACP’s evidence-based, innovative approach and its use of UK and multilateral expertise likely to generate secondary benefits?	EQ5: To what extent is GACP’s evidence-based, innovative approach and its use of UK and multilateral expertise likely to generate secondary benefits?	EQ5.1: Does the GACP have a credible ToC for SBs or a well-argued strand in the overall programme ToC? / EQ5.2: Which SBs (of the six types) does the PT expect and what is the timeframe? How realistic are these? / EQ5.3: Have any SBs been achieved yet? / EQ5.4: Are there any constraints to the delivery of SBs? Which steps does the PT take to remove barriers and constraints? / EQ5.5: What processes, systems and management arrangements are in place to deliver and monitor the realisation of SBs?	Relevance / Coherence / Effectiveness	GACP programme documentation / Prospero and other MREL tools / External documentation / Key informants / Direct beneficiaries / External stakeholders	Documentation review / Semi-structured interviews
EQ6: What factors have contributed to or hindered achievements to date? Are the assumptions and causal pathways outlined in the ToC still valid?	EQ6: What factors have contributed to or hindered the programme’s achievements to date?	EQ6.1: What factors linked to GACP have contributed to or hindered achievements to date? / EQ6.2: What factors linked to the context have contributed to or hindered achievements to date? / EQ6.3: To what extent have GACP’s specific characteristics been verified and have contributed to achievements to date? / EQ6.4: Are the assumptions and causal pathways outlined in the ToC still valid?	Effectiveness	GACP programme documentation / Prospero and other MREL tools / External documentation / Key informants / Direct beneficiaries / External stakeholders / G&I scorecard	Documentation review / Semi-structured interviews
EQ7: To what extent is GACP built on systems, processes and management arrangements that provide good value for money?	EQ7: To what extent is GACP built on systems, processes and management arrangements that provide good value for money?	EQ7.1: How is the programme overall performing in relation to the four Es (economy, efficiency, effectiveness, and equity)? / EQ7.2: What is the direction of travel of all eight VfM scorecard elements since the last self-assessment exercise?	Relevance / Efficiency / Effectiveness	GACP programme documentation / Prospero and other MREL tools / External documentation / Key informants / Direct beneficiaries / External stakeholders / VfM scorecard	Documentation review / Semi-structured interviews / Scorecard analysis

Bibliography
BIBLIOGRAPHY
Programme-level documents and reports
GACP Business Case 2018
GACP Annual Review 2019
GACP Annual Review 2018
GACP Critical Friend Review 2019
GACP Logframe (updated in September 2020)
GACP programme, Revised Theory of Change
Comprehensive Spending Review (CSR) Programme Impact Examples version August 2020
GACP Steering Board Minutes & dashboards, 2018-20
GACP Steering Group action log, 2018-20
GACP Risk Register, updated 2020
GACP Adaptive Management Strategy, 2018
GACP synergies approach, 2019
GACP Secondary Benefit plan
GACP AC gender and human right approach paper, 2019
GACP Value for Money scorecard, 2019
GACP Readiness Review 2019
Prospero
Quarterly Report, GACP, Q1, Q2, Q3 and Q4 of 2018-19
Quarterly Report, GACP, Q1, Q2, Q3 and Q4 of 2019-20
Quarterly Report, GACP, Q1, Q2 of 2020-21
GACP COVID-19 Pivot: Approval of Transforming Procurement Systems, August 2020
Memorandum of Understanding, as approved and signed with HMT, DFID, OECD, UNODC, GDMP
Project Overviews, 2019
Monthly and Quarterly Flash Reports 2018-20
Additional internal project documents
UNODC
UNODC Regional Platforms – Launch events (Nairobi, Bangkok): Outcome Statement, Agenda, List of participants; CSO statements
UNODC Regional Platforms – follow-up workshop (Tanzania -whistleblowing) : agenda, list of participants, presentations, action plan
GACP monthly email updates
GDMP
GDMP Country Discovery reports (Caution your blast, Rainmaker, Spend Network, DXW, Development Gateway): Malaysia, Indonesia
GDMP Programme Roadmap, 2020
GDMP Vision, Strategy and Indicators
GDMP Stories of Change
GDMP, Gender Equality and Social Inclusion in ICT Procurement: Discovery Report, Oxford Insight 2020
GDMP portfolio database
GDMP South East Asia Strategy, 2021
GDMP various presentations in Indonesia and Malaysia
FATF
ESAAMLG (July 2020), mid-term review of the UK support to ESAAMLG to strengthen AML/CTF.
Overview of progress made by ESAAMLG members in implementing the FATF Recommendations
Botswana case analysis - FATF
Open Ownership
Notes for Open Ownership’s Impact https://www.open-contracting.org/impact/
Behavioural Science
Behavioural Insights Project Delivery Strategy versions 1, 2, 3
OECD, Project proposal: Mitigating corruption risks through behavioural insights, undated.
Global Anti-Corruption Programme Behavioural Science project: Problem statement for call for bids.
OECD
GACP OECD Results Framework, July 2020.
OECD (2019) Auditors Alliance: Annual Meeting Highlights.
OECD ACI project Results Framework, dated June 2020
Other relevant documents by selected delivery departments and partners
Formerly DFID
DFID International Action against Corruption, Business Case, Annual Reviews 2018-19 / https://devtracker.fcdo.gov.uk/projects/GB-1-205181
UNODC
UNODC Global Programme GLOZ99 Annual Report 2019
https://www.unodc.org/unodc/en/ft-uncac/platforms.html
https://www.unodc.org/unodc/en/ft-uncac/overview.html#steps
Mid-term Independent Project Evaluation of the Global Programme segment Asia-Pacific Joint Action Towards a Global Regime against Corruption (2016-2020) GLOZ99 (Component funded by DFAT) South and Southeast Asia, February 2019 . https://www.unodc.org/documents/evaluation/Independent_Project_Evaluations/2019/GLOZ99-segment_Mid-Term_IPE_Report_February_2019.pdf
Danida (2018) Anti-corruption programme, concept note (2019-20). www.umk.dk/Dania/Consultations/2018/AC programme
INTERPOL (2019) Corruption as a facilitator of organised crime in the East African Region, October 2019. https://enactafrica.org/research/interpol-reports/corruption-as-a-facilitator-for-organised-crime-in-the-eastern-african-region
https://www.unodc.org/southeastasiaandpacific/en/what-we-do/anti-corruption/topics/29-the-anti-corruption-commission-in-timor-leste-builds-its-capacities-to-investigate-corruption-and-financial-crimes.html
https://eaaaca.com/index.php/events/harmonization-of-anti-corruption-laws-in-eastern-africa
UNODC (2013) Guidebook on anti-corruption in public procurement and the management of public finances. https://www.unodc.org/documents/corruption/Publications/2013/Guidebook_on_anti-corruption_in_public_procurement_and_the_management_of_public_finances.pdf
FATF
http://www.fatf-gafi.org/publications/mutualevaluations/documents/assessment-ratings.html
http://www.fatf-gafi.org/publications/high-risk-and-other-monitored-jurisdictions/documents/increased-monitoring-october-2020.html
https://www.euractiv.com/section/botswana/news/countries-seek-removal-from-controversial-eu-tax-blacklists/
https://ec.europa.eu/info/business-economy-euro/banking-and-finance/financial-supervision-and-risk-management/anti-money-laundering-and-counter-terrorist-financing/eu-policy-high-risk-third-countries_en
IMF (April 2019) 2019 Article Iv Consultation – Press Release; staff report; and statement by the Executive Director For Botswana. https://www.imf.org/en/Publications/CR/Issues/2020/03/18/Botswana-2019-Article-IV-Consultation-Press-Release-Staff-Report-and-Statement-by-the-49276
STAR
STAR Annual Report 2019 https://star.worldbank.org/publication/star-annual-report-2019
External Review of the World Bank / UNODC Stolen Asset Recovery Initiative August 2019
StAR quarterly newsletters https://star.worldbank.org/content/star-quarterly
StAR (2011) The Puppet Masters How the Corrupt Use Legal Structures to Hide Stolen Assets and What to Do About It / https://star.worldbank.org/publication/puppet-masters
StAR (2017) GFAR Principles for Disposition and Transfer of Confiscated Stolen Assets in Corruption Cases https://star.worldbank.org/sites/star/files/the-gfar-principles.pdf#:~:text=GFAR%20Principles%20for%20Disposition%20and%20Transfer%20of%20Confiscated,receiving%20countries.%20Such%20partnership%20promotes%20trust%20and%20confidence.
Open Ownership
Open Ownership Verification of Beneficial Ownership Data, Policy Briefing, May 2020 https://www.openownership.org/uploads/OpenOwnership%20Verification%20Briefing.pdf
Open Ownership, EITI, 2020, Catalysing transformative change in beneficial ownership transparency https://www.openownership.org/uploads/Opening%20Extractives%20Research%20Report.pdf
OECD
https://anticorruption-integrity.oecd.org
Bhargava, V. (2018) Final Report on External evaluation of the Anti-Corruption Initiative for Asia and the Pacific. Commissioned by the Asian Development Bank. https://www.oecd.org/site/adboecdanti-corruptioninitiative/external-evaluation-final-report-27-december-2018.pdf
OECD Strategic Approach to Combatting Corruption and Promoting Integrity. https://www.oecd.org/corruption/oecd-strategic-approach-to-combating-corruption-and-promoting-integrity.htm
Literature
General
Claudia Baez Camargo. (May 2017). Can a Behavioural Approach Help Fight Corruption? Basel Institute on Governance Policy Brief No 1, 3. https://baselgovernance.org/publications/policy-brief-1-can-behavioural-approach-help-fight-corruption
DFID (January 2015), Why Corruption matters: understanding causes, effects and how to address them”, Evidence Paper on Corruption. https://www.gov.uk/government/publications/why-corruption-matters-understanding-causes-effects-and-how-to-address-them
Open Contracting Partnership (2016) Corruption in public contracting: change behaviour, not rules https://www.open-contracting.org/2016/06/22/corruption-public-contracting-change-behavior-not-rules/
U4 Issue 2019:12 Asset recovery and illicit financial flows from a developmental perspective: Concepts, scope, and potential https://www.u4.no/publications/asset-recovery-and-illicit-financial-flows-from-a-developmental-perspective-concepts-scope-and-potential
United Kingdom Anti-Corruption Strategy 2017 – 2022 https://www.gov.uk/government/publications/uk-anti-corruption-strategy-2017-to-2022
UK House of Commons (August 2019), Register of Beneficial Ownership , Briefing Paper, https://researchbriefings.files.parliament.uk/documents/CBP-8259/CBP-8259.pdf
World Bank (2020) “Enhancing Government Effectiveness and Transparency: The Fight Against Corruption”, World Bank, Washington, DC https://www.worldbank.org/en/topic/governance/publication/enhancing-government-effectiveness-and-transparency-the-fight-against-corruption
B20, 2015, Putting Beneficial Ownership Transparency into Practice / https://bteam.org/assets/reports/Beneficial-Ownership-Transparency-B20-Report.pdf
B29, 2020, Integrity and Compliance, Policy Paper 2020 https://www.b20saudiarabia.org.sa/wp-content/uploads/2020/09/B20-Integrity-Compliance-Policy-Paper-30092020.pdf
Country
UNODC UNCAC Implementation Review Mechanism Country Profiles: https://www.unodc.org/unodc/en/corruption/country-profile/index.html
FATF Mutual Evaluation Reports: http://www.fatf-gafi.org/publications/mutualevaluations/?hf=10&b=0&s=desc(fatf_releasedate)
World Bank Worldwide Governance Indicators https://info.worldbank.org/governance/wgi/
Transparency International Corruption Perception Index https://www.transparency.org/en/cpi#
Open Government Partnership https://www.opengovpartnership.org/our-members/
Public Expenditure and Financial Accountability reports www.pefa.org
OECD (2007) Snapshot Assessment of Indonesia’s Public Procurement System As At June, 2007 Piloting OECD/ DAC Procurement Jv Baseline Indicator Benchmarking Methodology Version 4 http://www.oecd.org/development/effectiveness/39254688.pdf
Rachmat Hidayat (2015) Local Government E-Procurement Practices in Indonesia: Accountability, Efficiency, and Barriers , Journal of US-China Public Administration https://www.researchgate.net/publication/285383748_Local_Government_E-Procurement_Practices_in_Indonesia_Accountability_Efficiency_and_Barriers
Aditya Pandu Wicaksono, Dekar Urumsah, and Faishal Asmui (2016)The Implementation of E-procurement System: Indonesia Evidence, SHS Web of Conferences https://www.researchgate.net/publication/313735505_The_Implementation_of_E-procurement_System_Indonesia_Evidence
Transparency International, 2019, People’s Experiences of Corruption: Implications for Business In South-East Asia / https://www.transparency.org/en/publications/peoples-experiences-corruption-implications-business-south-east-asia

List of stakeholders interviewed
Stakeholders interviewed at headquarters or in non-sampled regions.
ORGANISATION	ROLE	M/F
HMG
FCDO	Global Head of AC, GACP Programme Manager	F
FCDO	GACP Deputy Programme Manager	F
FCDO	AC Project Manager, GACP	M
FCDO	AC Project Manager, GACP	F
FCDO	MREL Adviser	F
FCDO	MREL Coordinator for Global Programmes & Deputy Head, Global Programme Support Team	F
FCDO	Social Development Adviser | Global Programmes Support Team	F
FCDO	Social Development Adviser | Global Programmes Support Team	F
FCDO	GACP SRO and Head of Global Economics Issues Department	F
Home Office	Deputy Director and Head of JACU	M
Home Office	Head of International Engagement, Joint Anti-Corruption Unit	M
Home Office	Head of Prosperity, Joint Anti-Corruption Unit	F
Formerly DFID	Governance Adviser, Anti-Corruption Team, Governance and Open Societies Department	F
HMT	Head of FATF and International Engagement	F
HMT	Head of AML/CFT capacity building, HMT; G&I lead	M
HMT	FATF TEAM	F
GDMP	Head of Operations, GDMP	M
GDMP	Programme Director, GDMP	M
GDMP	International Smart Adviser, GDMP	M
GDMP	G&I Lead GDMP	M
National Crime Agency	Manager, IACCC	M
National Crime Agency	Senior Officer, IACCC	M
British High Commission	Assistant Desk Officer, GACP, South Africa	M
British High Commission	British Ambassador, Angola	F
Delivery partners
Open Ownership	Executive Director	M
Open Ownership	Policy and Programmes Director	F
Open Ownership	Chair of Board, Open Ownership / Executive Director of OCP	M
UNODC	UNODC UNCAC Senior Adviser	M
UNODC	UNODC Global AC Programme Coordinator	F
UNODC	UNODC Project Financial Reporting	M
UNODC	UNODC Monitoring and Evaluation Lead	F
UNODC	UNODC G&I Lead	F
UNODC	UNODC Civil Society Lead	F
UNODC	UNODC Regional Adviser SA	M
UNODC	UNODC Whistleblower Protection Expert	F
UNODC	UNODC Financial Investigations Expert	M
UNODC	UNODC Public Procurement Expert	M
FATF	FATF Technical Director	F
FATF	FATF Training Manager	M
FATF	FATF Mentor	F
OECD	Anti-Corruption Analyst, Office of the Secretary-General	F
OECD	Adviser, Office of the Secretary-General	M
OECD	Events Coordinator (Global Anti-Corruption & Integrity Forum), OECD	M
OECD	Communications Officer (Global Anti-Corruption & Integrity Forum), OECD	M
OECD	Head of Division, Public Sector Integrity, Public Governance Directorate	M
StAR	UNODC StAR lead	M
StAR	Coordinator StAR Initiative	M
StAR	World Bank	F
External Stakeholders (CSOs, Experts, Private Sector)
Formerly U4, now TI Knowledge Hub	Research and Knowledge Coordinator	F
Basel Institute	Head of Public Governance	F
Centre for the Study of Corruption, University of Sussex	Director	F
ICAR	Operational director	M
ANEEJ; oversees MANTRA monitoring of returned stolen assets	Executive Director	M
World Economic Forum	Lead, PACI (Partnering Against Corruption Initiative)	F
ACC Seychelles	Executive Director	F

Stakeholders interviewed in the selected regions and countries
STAKEHOLDERS	ORGANISATION	ROLE	M/F
East Africa
CSO	Open Government Partnership	Open Government Partnership Regional Lead for East Africa	F
Delivery	ESAAMLG	ESAAMLG Mentor, FATF	M
Delivery	ESAAMLG	ESAAMLG Mentor, FATF	M
Delivery	ESAAMLG	Principal Expert, ESAAMLG	M
Delivery	StAR	Task Team Leader Ethiopia and Financial Sector Expert	F
Delivery	Open Ownership	Country Manager	F
Delivery	UNODC	Regional Adviser, East Africa	M
Others	UNODC	Regional Coordinator Container Control Programme, Eastern Africa, UNODC	M
Direct beneficiaries	East African Association of AC Authorities	Acting Chair	F
Donors	GIZ East Africa	Global Programme for Combating Illicit Financial Flows, Regional Coordinator Eastern & Southern Africa	F
HMG	National Crime Agency	National Crime Agency International Liaison	M
HMG	Formerly DFID	Governance Adviser, DFID South Sudan	M
HMG	FCDO	Economic Adviser, FCDO South Sudan, Juba	M
HMG	FCDO	Anti-Corruption Programme Adviser, Southern Africa, FCDO	M
Others	UNODC	Regional Coordinator Container Control Programme, Eastern Africa, UNODC	M
Others	UN Mission in South Sudan	Rule of Law Adviser, South Sudan	M
Kenya
CSO	TI Kenya	Head Policy, Legal and Institutional Frameworks Programme	F
Direct beneficiaries	Ethics and AC Commission	Deputy Director Legal Services	M
Direct beneficiaries	Office of the Attorney General	State Counsel, Business Registration Services at the Office of the Attorney General	F
Donors	GIZ	Global Programme for Combating Illicit Financial Flows, Programme Manager	M
Experts	ICAR	Embedded TA, EACC Kenya	M
HMG	Formerly DFID	Senior Governance Adviser, FCDO, Kenya	M
HMG	FCDI	Chair of cross-HMG AC board and IFF lead, FCDO Kenya	M
HMG	CSFF	Former Criminal Justice Adviser, Nairobi	M
HMG	CSFF	Criminal Justice Adviser, Nairobi	M
Others	Kenya Wildlife Service	Deputy Director	M
Others	Blue Company Kenya	Deputy Director	M
South East Asia
CSOs	Collective Actions Against Corruption	Project Director and CEO	F
CSOs	TI Malaysia	Secretary General	M
Delivery	UNODC	UNODC Regional Lead	M
Delivery	OECD	Lead, Business Integrity in South East Asia	F
Direct Beneficiaries	Office of the Public Sector Development Commission, Thailand	Public Sector Development Officer, Change Management and Innovation Development Directorate	F
Direct Beneficiaries	Government Inspectorate of Viet Nam	Deputy Director General, International Cooperation Department	F
Donors	UNDP Asia	Project Specialist, Transparency and Accountability, Governance Team	F
Donors	ADB	Senior Integrity Specialist, Office of ACI	F
Experts	n/a	Independent Consultant, AC	F
HMG	GDMP	Product Manager, SEA	M
Malaysia
CSOs	Coalition for Business Integrity, Malaysia	Executive Director	M
CSOs	Transparency International Malaysia	Manager	F
Direct beneficiaries	MACC Malaysia	International Relations Branch, Policy, Planning & Research Division	F
Direct beneficiaries	MACC Malaysia	Asset Recovery	M
Direct beneficiaries	Digital Penang	Senior Manager, Strategy and Communication	M
Direct beneficiaries	Malaysian Administrative Modernisation and Management Planning Unit (MAMPU)	Focal point	F
Direct beneficiaries	MAMPU	Focal point	F
Experts	Institute of Ethnic Studies, National University of Malaysia	Former (until August 2020) Deputy Director General of the National Centre for Governance, Integrity & Anti-Corruption, Malaysia; now, Principal Fellow	M
HMG	British High Commission	Counsellor, Head of Prosperity and Economics Team, British Embassy, Kuala Lumpur	M
HMG	British High Commission	HMRC Fiscal Crimes Liaison Officer British High Commission Malaysia	F
HMG	British High Commission	Delivery manager, GDMP	F
Indonesia
CSOs	Indonesia Business Link	Head	F
CSOs	Indonesia Corruption Watch	Coordinator	F
CSOs	SPAK	Adviser	F
Delivery partner	Ministry of Law and Human Rights	Company Registrar, AHU	M
Delivery partner	LKPP	Regulation team	F
Delivery partner	LKPP	Regulation team	F
Delivery partner	Corruption Eradication Commission International Division	Cooperation Specialist	F
Expert	Bibit Samad Rianto Centre	Deputy Director of Anti-Fraud Consultancy; former Deputy Chief of the Corruption Eradication Commission	F
HMG	British High Commission	Digital Access and Anti-Corruption Lead, British Embassy, Jakarta	M
HMG	British High Commission	GDMP Delivery Manager	M

Context analysis
The member countries of the two sampled regions, South East Asia and East Africa, both share commonalities and display differences. This was discussed with stakeholders in the regions and countries and is clearly evidenced in the various composite indices. As confirmed by the Basel Institute,[137] while each country has different risks, each region also displays particular trends and problem zones.
[137] https://baselgovernance.org/sites/default/files/2020-07/basel_aml_index_2020_web.pdf
South East Asia
Regional context
South East Asian countries present economic, cultural and political conditions that have varying effects on AC efforts and implementation of reforms. International indices point to the following:
- According to the Basel AML Index,[138] the most prominent weaknesses in South East Asia relate to the quality of the Anti-Money Laundering/Combating the Financing of Terrorism (AML/CFT) framework itself, and to underperformance with respect to public transparency and accountability. In both areas, technical and legal adjustments as well as effective implementation would need to be the focus of future reform.
  [138] The Basel AML Index measures the risk of money laundering/terrorism financing (money laundering/TF) in countries around the world. Risk is defined broadly as a country’s vulnerability to money laundering/TF and its capacity to counter it. It does not measure the actual amount of money laundering/TF activity in a country. Risk scores are based on data from publicly available sources such as the Financial Action Task Force (FATF), Transparency International, the World Bank and the World Economic Forum. They cover 16 indicators in five domains relevant to assessing money laundering/TF risk at the country level: 1. Quality of AML/CFT Framework, 2. Bribery and Corruption, 3. Financial Transparency and Standards, 4. Public Transparency and Accountability, 5. Legal and Political Risks.
- With regards to stakeholder perceptions, Transparency International’s CPI for 2019[139] presents an average score of 45 (out of 100) for the Asia Pacific region, only slightly above the global average of 43. According to CPI, after several years of stagnation, the region continues to make very little improvement in tackling corruption. According to a recent study,[140] also produced by Transparency International, people’s experience of corruption in South East Asia varies greatly. The largest percentage of respondents that believed that corruption had increased (as captured in 2016-17) were found in Indonesia (65%) and Malaysia (59%). This same study also shows a significant contrast between Indonesia and Malaysia, with 85% and 48% of the respondents respectively agreeing that it is socially acceptable to report on corruption.
  [139] https://www.transparency.org/en/cpi/2019
  [140] Transparency International, 2019, People’s Experiences of Corruption: Implications for Business In South-East Asia https://www.transparency.org/en/publications/peoples-experiences-corruption-implications-business-south-east-asia
- According to the World Bank’s Governance Indicators (Figure 6),[141] Malaysia scores better than Indonesia in all areas but voice and accountability. However, Malaysia’s ranking is expected to deteriorate in 2020 as result of recent political events.
  [141] The Worldwide Governance Indicators (WGI) project reports aggregate and individual governance indicators for over 200 countries and territories over the period 1996–2019, for six dimensions of governance: Voice and Accountability; Political Stability and Absence of Violence; Government Effectiveness; Regulatory Quality; Rule of Law; Control of Corruption. http://info.worldbank.org/governance/wgi/
Figure 6: World Bank’s Governance Indicators, Indonesia and Malaysia, 2019

Indonesia country context[142]
[142] Interviews with Indonesia Business Link, Indonesia Corruption Watch, SPAK, LKPP, MLHR. Indonesian Corruption Eradication Commission. Bibit Samary Tianto Centre, British High Commission, UNODC regional lead.
Transparency International’s CPI shows stakeholders’ perception of Indonesia as a country that is “moderately corrupt”, ranking as the 85th (out of 198) most corrupt country in the world in 2019.[143] Indonesia conducted its last FATF review in 2018 and UN Convention against Corruption (UNCAC) review in 2018.[144]
[143] https://www.transparency.org/en/cpi/2019
[144] https://www.unodc.org/documents/treaties/UNCAC/WorkingGroups/ImplementationReviewGroup/ExecutiveSummaries2/V1802700e.pdf
The 2019 general election was won by the incumbent president, Joko Widodo (known as Jokowi), with 55.5% of the vote.[145] The opposition accused the incumbent of vote-rigging and sought to challenge the outcome at the Constitutional Court (though the court rejected the challenge in June 2019 due to paucity of evidence). Protests by supporters of the opposition resulted in violent clashes with police and reduced access to social media.
[145] https://www.nytimes.com/2019/06/27/world/asia/indonesia-widodo-prabowo-election-fraud.html; https://theconversation.com/indonesias-presidential-election-dispute-prabowos-plan-to-challenge-election-result-may-be-in-vain-117663
The Jokowi administration has faced accusations of rolling back Indonesia’s AC efforts and progress towards democracy more broadly.[146] In October 2019, large student protests erupted across the country against new laws that weakened the Indonesian Corruption Eradication Commission and amendments to the criminal code that would have infringed on citizens’ rights and freedoms. The government’s plans were also criticised by the international community.[147] The government conceded to postpone the amendment of the criminal code but proceeded with the revision of the commission’s status (see Box 15).
[146] https://www.reuters.com/article/us-indonesia-politics-rights-student-ins/anger-on-campus-behind-the-student-protests-that-have-rocked-indonesia-idUSKBN1XH2XI; https://theaseanpost.com/article/indonesias-anti-corruption-bill-ushered; https://www.afr.com/world/asia/indonesia-guts-corruption-watchdog-with-a-new-dirty-law-20191031-p536bz; https://www.thejakartapost.com/news/2020/09/26/dozens-of-kpk-employees-resign-following-footsteps-of-ex-spokesperson.html
[147] https://www.europarl.europa.eu/doceo/document/TA-9-2019-0044_EN.html
Box 15: 2019 law undermining the Indonesian Corruption Eradication Commission
A law passed in October 2019 eroded the independence and effectiveness of the Indonesian Corruption Eradication Commission by imposing a new supervisory body over its commissioners. The members of the supervisory body will now be appointed by the president, and therefore seen as a political entity under the executive. The Jakarta Post reported in September 2020 that 31 commission employees submitted their resignation between January and September. The former spokesperson cited recent “changes in [the commission’s] political and legal state” as the primary reason for his resignation in September.[148] Stakeholders interviewed indicated that this change in the Corruption Eradication Commission’s status is likely to slow or even reverse earlier progress on AC, with the potential to scare off investors and slow economic growth.
[148] https://www.thejakartapost.com/news/2020/09/26/dozens-of-kpk-employees-resign-following-footsteps-of-ex-spokesperson.html

An estimated 83% of corruption cases are linked to public procurement.[149] While it is mandatory for all government agencies to conduct all their procurement through an e-procurement system, this system is only partially used. In practice, e-procurement is only used for 40 to 70% of government procurement, depending on estimates.[150] In its last review, the UNCAC recommended that steps be taken to develop a more comprehensive public procurement law.[151] Some academic research linking e-procurement with AC in Indonesia[152] concluded that, while empirical evidence shows that e-procurement can help prevent and reduce fraud, this cannot be verified in the case of Indonesia, where the e-procurement system is not fully implemented, and where there are issues related to fragmented regulations, human resources, and lack of internal control and auditing.
[149] https://www.unodc.org/southeastasiaandpacific/en/what-we-do/anti-corruption/topics/31-indonesia-shares-progress-towards-uncac-implementation.html
[150] https://openupcontracting.org/assets/2019/04/Indonesia-Brief-on-Public-Procurement.pdf; Indonesia Public Expenditure and Financial Accountability Assessment Report 2017 https://www.pefa.org/node/546
[151] op. cit
[152] https://www.researchgate.net/publication/313735505_The_Implementation_of_E-procurement_System_Indonesia_Evidence; https://www.researchgate.net/publication/285383748_Local_Government_E-Procurement_Practices_in_Indonesia_Accountability_Efficiency_and_Barriers
Malaysia country context[153]
[153] Interviews with British High Commission, Coalition for Business Integrity, Transparency International Malaysia.
Transparency International’s CPI captures stakeholder perceptions after a change in government in 2018 ended 60 years of ruling by United Malay’s National Organisation, leading to significant AC actions. As a result, Malaysia rose 10 places in the global CPI ranking between 2018 and 2019, improving its score from 47 to 53. In previous years, Malaysia’s CPI performance had been dragged down by the One Malaysia Development Berhad (1MDB) scandal (see Box 16), after “many of the institutions that were set up to detect and sanction corruption became gradually compromised, with increasing concentration of political power.”[154]
[154] World Bank (2020), Enhancing Government Effectiveness and Transparency The Fight Against Corruption, Malaysia case study.
Box 16: One Malaysia Development Berhad scandal
The 1MDB scandal broke out in 2015 when the then Prime Minister, Najib Razak, was accused of channelling funds from 1MDB, a multi-billion-dollar state investment fund, to his personal bank accounts. The fraud was an intricate one, involving assets in multiple jurisdictions stretching from South East Asia and The Gulf to New York and Hollywood. / Following electoral defeat in 2018, Najib’s properties were raided, his personal assets seized, and both he and his wife charged with a series of corruption offences linked to 1MDB.[155] / In July 2020, a Malaysian court found the former Prime Minister guilty in the first of a series of corruption trials. Najib has been sentenced to 12 years in prison for abuse of power and 60 additional years on six counts of money laundering and breach of trust.[156] He is the first Malaysian leader to be convicted of corruption.[157] / With support from international law enforcement agencies, including the US, Switzerland and the UK (see Section 3.3), the Malaysian Anti-Corruption Commission (MACC) recovered over USD 300 million worth of assets stolen from 1MDB[158] and reached a settlement with Goldman Sachs worth a further USD 3.9 billion.[159]
[155] https://www.bbc.com/news/world-asia-22338100
[156] https://foreignpolicy.com/2020/07/31/najib-razak-malaysia-guilty-corruption/
[157] https://www.csmonitor.com/Commentary/the-monitors-view/2020/0728/Malaysia-upends-its-malaise-on-corruption
[158] https://www.thestar.com.my/news/nation/2019/05/08/rm13bil-in-1mdb-assets-recouped/
[159] https://www.wsj.com/articles/malaysia-and-goldman-sachs-reach-3-9-billion-settlement-over-1mdb-dispute-11595589269

The historic win of the multi-party, multi-ethnic Pakatan Coalition in the 2018 elections was attributed to the population’s frustration with public sector corruption, abuses of power and economic mismanagement, which led to rising cost of living. However, as a result of political infighting, the coalition government was ousted after 21 months in March 2020, with the new government effectively reinstating the old ruling party.[160]
[160] https://www.bbc.com/news/world-asia-51716474
The key changes carried out under the Pakatan Coalition (some confirmed by the new regime) include:
- The launch of the National Anti-Corruption Plan (2019-2023) developed by the Governance, Integrity and Anti-Corruption Centre, the Prime Minister's Department, in collaboration with other government agencies. The plan sets a practical goal based on initiatives to be taken by every government and private agency to address corruption, integrity and governance issues for the next five years.[161]
  [161] https://www.sprm.gov.my/index.php/en/arkib-berita-sprm/3227-national-anti-corruption-plan-2019-2023-nacp-2019-2023
- Law amendments leading a number of key agencies originally under the Prime Minister's Department to report to Parliament instead. These entities include the MACC, Election Commission and National Audit Department.[162]
  [162] https://www.straitstimes.com/asia/se-asia/malaysia-rises-10-spots-to-improve-its-ranking-in-annual-global-corruption-index
- Strengthened anti-bribery provisions, after section 17A of the MACC Act 2009, which entered into force in June 2020.
- Guidelines by the Companies Commission of Malaysia in March 2020, making the disclosure of beneficial owners mandatory.
Importantly, progress was also made in the 1MDB scandal, leading to the conviction of the former prime minister and a recovery of a proportion of the stolen assets.
Increasing efficiency and transparency in public procurement is one of the six priorities identified in Malaysia’s national AC plan.[163] This includes actions to introduce a more transparent mechanism to prevent information leakages in procurement processes; establish procurement complaints mechanisms for aggrieved parties; and enhance the technology-based procurement system (e-perolehan) in order to reduce human intervention between parties. Malaysia has an e-procurement system in place, but this system is not used to support decisions. According to MACC, corruption cases resulting in leakage of government procurement involving civil servants are increasingly critical: "I can say that, based on the MACC analysis, such wastages are common in the public sector, where [the top leadership of government agencies] who are in power in deciding a matter (government procurement) are involved in misappropriation and abuse of power.”[164]
[163] https://www.pmo.gov.my/wp-content/uploads/2019/07/National-Anti-Corruption-Plan-2019-2023_.pdf
[164] https://www.nst.com.my/news/crime-courts/2020/10/628715/macc-rampant-corruption-govt-procurement-processes
It remains unclear if the momentum will be sustained under the new regime. Stakeholders interviewed notably shared their concerns about the risk of political interference in the country’s ongoing AC efforts. According to stakeholders, the country’s economic fabric, made of numerous government-linked companies, coupled with party financing, makes Malaysia particularly prone to nepotism.

East Africa
Regional context
In 2011, governments from the region launched the East African Association of Anti-Corruption Authorities to provide a platform for Eastern African countries to tackle corruption as well as reinforce and strengthen good governance across the continent.
Like South East Asia, East Africa is not homogenous in terms of scale of corruption or capacity to tackle it. No aggregate indices were available for this sub-region in Sub-Saharan Africa. The World Bank’s Governance Indicators (see Figure 7) illustrates well the commonalities and differences between Kenya and Botswana,[165] two non-priority countries for GACP. In 2019, the control of corruption in Botswana scored four times better than that in Kenya.
[165] Botswana was not selected in this evaluation’s sample; this country is used as an example of GACP FATF’s assessment.
Figure 7: World Bank’s Governance Indicators, Kenya and Botswana, 2019

Diagnoses also tend to vary from one source to another, reflecting data availability. According to the Basel AML index,[166] the risk of money laundering in Botswana (ranked as medium with a 5.06 score) is lower than that in Kenya (ranked as high with a 7.18 score). In contrast, Botswana was put on the grey list by FATF as a country facing strategic deficiencies in its regimes (see Annex 7 for more detailed analysis). Kenya had yet to be evaluated using FATF’s revised methodology.
[166] op. cit
Kenya country context[167]
[167] Interviews with Open Government Partnership, Open Ownership, Transparency International Kenya, Ethics and AC Commission, GIZ, ICAR and CSFF advisers, British High Commission, UNODC regional office.
While the stakeholders interviewed still consider Kenya highly corrupt, they agree that there have been some improvements over the last five years. Transparency International’s stakeholder perception index ranks the country as the 137th (out of 198) most corrupt country in the world in 2019 (against 144th in 2018). Kenya completed its last FATF review in 2017[168] and UNCAC peer reviews in 2015 [169] and 2019.[170]
[168] https://esaamlg.org/reports/Kenya_Mutual_Evaluation_Detail_Report(2).pdf
[169] Also in 2015, a task force chaired by the Attorney General was set up to review the legal, policy and institutional framework for fighting corruption in Kenya, leading to a final report with recommendations in November 2015.
[170] https://www.unodc.org/documents/treaties/UNCAC/CountryVisitFinalReports/2019_07_08_Kenya_Final_Country_Report_English.pdf
In March 2018, President Uhuru Kenyatta and main opposition leader, Raila Odinga, agreed to set aside differences and reconcile through a ‘handshake’. Their reconciliation brought to an end months of post-election violence that had followed the close results of the 2017 presidential election.
This reconciliation period coincided with the government taking steps to strengthen its AC architecture on a number of fronts:
- In 2018, the country adopted a National Ethics and Anti-Corruption Policy to mainstream ethics and integrity in the management of public affairs and coordinate AC efforts.
- In June 2018, the president announced a lifestyle audit to be conducted for all public servants. The lifestyle audit was, however, challenged by politicians for having no legal backing. The lifestyle audit bill has since been presented in both houses of parliament for enactment.[171]
  [171] https://nation.africa/kenya/blogs-opinion/letters/lifestyle-audit-bill-will-boost-war-against-corruption-215990
- In July 2018, an executive order set out disclosure requirements for government tenders, requiring all procuring agencies to maintain, update and publicise complete information on all tenders awarded, including full particulars on their suppliers. Since 2019, all public procurements are to be undertaken through the electronic public finance management platform.
There has also been a number of high-level arrests and prosecutions involving top government officials, including ministers, cabinet secretaries, heads of government parastatals, members of parliament and county governors,[172] with the office of Director of Public Prosecution and the multi-agency task team [173] being recognised driving forces behind this success. In addition, a court ruling has banned all elected and non-elected government officials charged with corruption from accessing office. According to the Ethics and Anti-Corruption Commission (EACC), in the past five years, the government was able to recover close to KSH 20 billion in stolen public funds and assets, and avert the possible loss of another KSH 100 billion shillings over the same period.[174]
[172] https://www.theafricareport.com/15545/kenya-finance-minister-arrest-shines-light-on-infrastructure-debt/; https://www.aljazeera.com/economy/2019/07/26/kenyas-corruption-crackdown-new-era-or-political-theatre/; https://www.aljazeera.com/news/2019/12/9/nairobi-governor-mike-sonko-denies-corruption-charges-in-court; https://www.nytimes.com/2019/12/06/world/africa/nairobi-governor-mike-mbuvi-sonko.html; https://www.capitalfm.co.ke/news/2020/08/governor-obado-his-4-children-to-face-sh73mn-graft-case-for-fleecing-migori-county/
[173] Multi-Agency Task Team, which was born out of a presidential directive in November 2015, includes the Ethics and Anti-Corruption Commission (EACC), Directorate of Criminal Investigations, National Intelligence Service and Financial Reporting Centre, Asset Recovery Agency, Kenya Revenue Authority and the Office of the President.
[174] https://nation.africa/kenya/news/sh20bn-recovered-in-graft-purge-2460062
In other areas, however, the government has been slow to meet its commitments. Some government critics have also criticised the recent prosecution cases for being politically motivated.[175] After being the first country to commit to open a public BO register, the company regulations, adopted in 2020, state that BO information will not be made available to the public (see Section 3.2 and Annex 7 for detailed analysis). There have also been continuous delays in adopting the Whistleblower Protection Bill (amendment) and Anti-Corruption Law Bill (amendments).[176] As put by one stakeholder, Kenya’s AC context is made of competing “push and pull” interests, with political factions repeatedly challenging the government’s push (and motivation) for AC.
[175] For example, the High Court stopped the Office of the Director of Public Prosecutions from prosecuting the Deputy Chief Justice and former Judicial Service Commission member and lawyer Prof. Tom Ojienda against grant. https://nation.africa/kenya/news/philomena-mwilu-survives-as-court-stops-prosecution-over-graft-172844 https://www.capitalfm.co.ke/news/2018/12/high-court-blocks-prosecution-of-lawyer-ojienda-over-mumias-sugar-payment/
[176] None of those bills are mentioned in the October 2020 Building Bridge report, which renews the government’s commitment to intensify the fight against corruption. https://www.bbi.go.ke/
Concerning procurement, the legal, institutional and regulatory framework has strengthened in the last five years. An e-procurement system is also in place. The majority of public corruption cases are still related to breaches in procurement regulations, however. Some government procurement entities have not rolled out e-procurement yet, whereas open access to procurement data remains scattered. In 2020, the misappropriation of COVID-19 funds, involving the procurement of personal protective equipment, was exposed by the media, prompting activists to organise protests across Kenya to demand accountability from the government.[177] Investigations by EACC subsequently confirmed the alleged misuse of USD 7.8 million involving officials from the Kenya Medical Supplies Authority and the Ministry of Health.
[177] https://www.washingtonpost.com/world/africa/kenyan-police-teargas-anti-corruption-protesters-in-nairobi/2020/08/21/bb4cd452-e3ab-11ea-82d8-5e55d47e90ca_story.html
Detailed project contribution analysis
GACP UNODC[178]
[178] List of stakeholders include GACP PT, UNODC delivery team (Programme Coordinator, Senior Advisor, Regional Advisors, M&E lead, Gender lead); UNODC technical experts (public procurement; financial investigations), Kenya EAACCA (acting chair, embedded advisor) UNMISS rule of law adviser (South Sudan), FCDO economics advisor and governance advisor (South Sudan).
Overall project performance
GACP UNODC’s performance is captured in the logframe under three outputs (two under Theme 4) and two (intermediary) outcome indicators. The outcome indicators can also be found in UNCAC’s global programme under Outcome 2 – states’ legal and policy frameworks. The logframe only captures GACP UNODC’s contribution to strengthening the member states’ institutional framework and capacity at an output level.[179]
[179] Capacity building indicators can be found under Outcome 3: States’ institutional frameworks address corruption risks in line with UNCAC, and Outcome 4: Anti-corruption practitioners and other stakeholders have and apply the capacity to prevent and combat corruption, in UNODC Global Programme
The logframe indicators for Years 1 and 2 show the following project performance:
- Activities started slowly in Year 0 (2017-18), when the first two regional platforms (East Africa, South East Asia) were launched in 2017.[180]
  [180] Some regional events in South East Asia in 2017/18, as reported by UNODC on its website, were evidently a follow-up from the platform. https://www.unodc.org/southeastasiaandpacific/en/what-we-do/anti-corruption/activities.html. Others are reported in GACP’s 2018 Annual Review.
- Activities picked up in Year 1 (2018-19) when UNODC delivered seven national and one regional technical assistance packages, as planned. In Year 2, UNODC met its initial targets by delivering eight country technical packages and three regional events in South East Asia, and nine country packages and one regional theme (covering three themes) in East Africa. Although the logframe targets have been met, as discussed during the interviews, staff constraints[181] have in practice reduced UNODC’s ability to deploy technical assistance rapidly, a situation made worse by COVID-19 (see below).
  [181] UNODC heavily relies on external consultants to carry out its work both in country and globally. In addition, the regional position for East Africa was vacant until late 2018, with much of the earlier regional work conducted from Vienna.
- Over the same period, UNODC has also performed well against its intermediary outcome and outcome targets and reported that one country in Year 1 and seven countries in Year 2 had adopted new strategies, while another four had made progress in changing laws and regulations in various areas in Year 2.
Looking into Year 3, COVID-19 has had a significant impact on the operations of the UNODC in all four regions. This has delayed planned regional workshops and country follow ups by thematic experts. There has nonetheless been some progress virtually, in terms of developing online tools, leading to recent delivery of webinars.[182]
[182] Whistleblower protection in Zambia and Indonesia and Beneficial Ownership in South East Asia.
Results in selected regions and countries
The outcome results reported by UNODC in the GACP logframe (Year 2) for East Africa were as follows:[183]
[183] The GLO annual report for calendar year 2019 reported the following results under Outcome 2, indicator 1 (number and type of adopted revised or new laws and regulations): “whistle-blowing protection systems” in Burundi, Tanzania and Uganda; and Outcome 3, indicator 2: “number of countries improving coordination of institutions at the national level”. UNODC provided support to the United Republic of Tanzania to improve coordination among national institutions on corruption in procurement.
- Kenya: The adoption of financial investigation policies and procedures on management of seized assets and ongoing vetting of employees.
- Uganda: Whistleblower protection policy amended.[184]
  [184] At an intermediary level, strategic documents were also adopted to (i) develop whistleblowing protection regulations in Tanzania and Uganda; (ii) strengthen anti-corruption in public procurement in Rwanda and Uganda; and (iii) draft financial investigations policies and procedures in Kenya and Tanzania.
In addition, GACP reported the following result in South Sudan: "South Sudan also recently approached UNODC seeking support on the implementation of their Peace Agreement. Thanks to the prior existence of the regional platform, South Sudan directly included the commitments on anti-corruption in their work plan established for the implementation of the Peace Agreement."
In South East Asia, it was reported that a new AC law had been adopted in Timor Leste[185] as a result of the programme support. Intermediary results were also reported in Year 2 (2019-20) across a wide range of areas.[186]
[185] http://timor-leste.gov.tl/?p=25518&lang=en
[186] At an intermediary level, results were reported as follows: Vietnam: Guidelines for inspection of procurement for the Ministry of Agriculture and rural development / guidelines for the implementation of new articles of the penal code for judges. Indonesia: Policy paper on procurement and contracting in the forestry sector / guidelines for investigators on conducting cases involving liability of legal persons. Cambodia: Anti-corruption policy drafted. Timor Leste: New anti-corruption Law (outcome 2, indicator 1).
The above shows relatively few results at outcome level, given the maturity of the project and size of funding. This reflects the protracted nature of reforms, as well as the time it took for the regional platforms to start implementing activities. The “cascading” consensus-building approach that characterises the regional platforms, coupled with the multi-stakeholder focus the UNODC uses in many of its technical assistance packages to push for reforms, has made the project quite process-heavy.[187] Before COVID-19, the project was well positioned to further accelerate the pace of delivery, while country-led processes were also expected to start generating outcome results. Based on selected stakeholder interviews, the evaluation team, for example, could find supplementary evidence[188] to confirm good progress in public procurement in Rwanda and Tanzania and whistleblowing in Burundi.
[187] In East Africa, for example, the main objective of the public procurement theme is to establish national coordination bodies to manage inter agency coordination to address procurement corruption. Technical assistance packages also typically involve using task forces to push through the recommended actions.
[188] GLOZ99 Annual Report; GACP logframe; interviews with UNODC regional advisers and technical experts.
Contributing factors
GACP UNODC’s activities
The UNODC regional platforms in East Africa and South East Asia were launched in Nairobi and in Bangkok in February 2017 in a first pilot phase funded by GACP transition funds. The same methodology was used in preparation of the regional platforms in Central America and Southern Africa (launched subsequently in May and October 2019).
The two regional platforms in East Africa[189] and South East Asia successfully followed all agreed steps,[190] with each platform sharing the following features as a result:
[189] Burundi, Djibouti, Kenya, Ethiopia, Rwanda, South Sudan, Tanzania, Uganda.
[190] The four steps can be found here: https://www.unodc.org/unodc/en/ft-uncac/overview.html#steps
- Scoping: The platform themes were selected through a desk-based review (including identified gaps in the UNCAC compliance reviews) and stakeholder consultations in all countries. In Eastern Africa, the selected themes were: whistleblower protection, financial investigations, public procurement and international cooperation. In South East Asia, the three selected themes were: (i) strengthen capacities for detecting, investigating and prosecuting corruption at the national and international level; (ii) prevent money laundering, prevent and detect the transfer of proceeds of crime and recover stolen assets; (iii) prevent corruption and enhance transparency and accountability of public services.
- Regional conference: The two launch events were attended by 67 (East Africa) and 180 (South East Asia) technical experts and policy makers drawn from relevant government departments, civil society, the private sector and development partners.
- Further mapping/baselining through in-country visits and follow-up events was carried out to understand the situation and needs of all countries with regard to thematic areas.
- Implementation: Activities ensued at a national and regional level, as listed in logframe and UNODC flash reports.
GACP UNODC’s contribution
Given the multi-donor support arrangements of the UNODC Global Programme, it is difficult to attribute results to a particular donor or agency. In some countries and areas UNODC started to deliver technical assistance before the start of the regional platforms. In East Africa, the evaluation nonetheless finds a close correspondence between the list of activities and the logframe results. In its annual report, UNODC also directly attributes some progress to the platform. In South East Asia, the platform and its action plan are very broad (and less specific) in scope, making contribution more difficult, especially in countries like Cambodia, Indonesia, Lao, Myanmar and Vietnam, where UNODC has a long-standing partnership.
Box 17: Regional platform in practice: Focus on whistleblowing in East Africa[191]
[191] Stakeholder interviews; UNODC 2019 GLO Annual Report; flash reports and logframe; outcome statement – regional launch event; presentation and workshop results (Tanzania 2019).
In the outcome statement endorsed at the launch of the regional platform in 2017, participating delegations recommended a few concrete and practical steps towards strengthening reporting systems and whistleblower protection, with nine proposed actions (legislations; policies and procedures; awareness raising; legal advice; streamlining; capacity building (regional); legislation and establishment of units; capacity building; regional and international cooperation) / A follow-up regional meeting on whistleblowing (and public procurement) in Tanzania followed in 2018, where CSOs were also invited and six member countries (Kenya, Uganda, Ethiopia, Burundi, Tanzania) agreed on next steps, with EACC acting as the focal point coordinator. During the workshop, Burundi, Ethiopia and Djibouti agreed to consider reviewing and revising their legislation, with support from the technical expert, while Tanzania and Uganda proposed to focus on implementation, while recognising gaps in their laws and regulations. Uganda also announced that they would coordinate with the ministry to amend the regulations to align with the law. In Kenya, the whistleblowing protection bill (developed in 2016) was still under adoption, making it more difficult to commit to next steps. This event discussion generated opportunities for promoting further cooperation (notably between Tanzania and Uganda), and evidently helped the participants improve their conceptual and practical knowledge about the important distinction between whistleblower protection and witness protection. / In 2019, the UNODC technical adviser conducted follow-up technical missions in Tanzania (April), Ethiopia (July), Uganda (October), and Burundi (November); needs assessment scoping visits were organised in South Sudan (March) and Rwanda, around the same time.[192] Also in 2019, UNODC shared good practices, international standards and national laws related to whistleblowing via the website of the East African Association of Anti-Corruption Authorities with countries in the region. Furthermore, translation of the Tanzanian Witness Protection and Whistleblower Protection Act (2015) as well as the East African Community Bill on whistleblower protection into French was facilitated to provide other francophone jurisdictions in the region with model law.[193] / In 2020, the UNODC followed up on progress in Tanzania, Uganda, and Rwanda and conducted further stakeholder consultation in Kenya to follow up on the adoption of the whistleblowing protection bill following UNODC comments provided in 2019. A process was initiated to recruit a consultant to provide in-country capacity building on whistleblower protection in Kenya and Rwanda.
[192] Uganda, 30-31 October 2019; United Republic of Tanzania, 23 April, 6 May, 24-25 October 2019.
[193] UNODC 2019 GLO Annual Report.

The work on whistleblower protection in East Africa and on capacity building (Theme 1) in South East Asia provide two contrasting examples of contribution. The thematic work on whistleblower protection in East Africa shows how the platforms have effectively combined high-level commitments, mapping/baselining, sharing of information and practice, and the deployment of UNODC technical expertise to push the AC agenda forward. In South East Asia, the regional platform was also used as an entry point to follow up on recommendations made in the UNODC Implementation Review Mechanism. In Timor Leste, for example, UNODC stepped up its capacity building support to anti-corruption on whistleblowing, financial investigation and revision to the legal framework, from 2018. This eventually led to the adoption of a new AC law, a recommendation that was already made in the country’s 2012 Implementation Review Mechanism.[194]
[194] https://www.unodc.org/southeastasiaandpacific/en/what-we-do/anti-corruption/topics/29-the-anti-corruption-commission-in-timor-leste-builds-its-capacities-to-investigate-corruption-and-financial-crimes.html
Based on the above, and supplementary stakeholder interviews, the added value of GACP UNODC’s project was confirmed as follows:
1) While the cascading approach has taken longer than expected to start implementation in some areas (notably investigations in East Africa), the regional platforms have evidently allowed scale up of UNODC’s technical assistance across the regions. The high-level commitments made by all participants during the regional platform events have provided UNODC with a useful mandate to work in member countries without (much) further negotiation.[195] This has both allowed the organisation to continue its work in some member states and, importantly, step up its engagement in others, such as Timor Leste.
[195] In Burundi, UNODC still needed to receive an agreement to provide in-depth legal advice on how to improve their legalisation on whistleblower protection.
2) The platforms have closely matched technical assistance demand with supply. UNODC has worked closely with relevant AC authorities to tailor assistance to their needs, while retaining a regional dimension. For example, under financial investigation, UNODC’s first task was to compile the standard operating procedures used by the AC agencies across the East Africa region.
3) The platforms have generated new demands for technical assistance on reforms and made relevant authorities more aware of existing gaps, sometimes leading to immediate actions. In East Africa, the platforms have evidently helped to put whistleblower protection back on the agenda (see Box 17). In Uganda, this led to immediate action, as the AC authorities took steps to revise their whistleblower protection regulations after being made aware of a gap. This was done with very little need for capacity building.
4) Stakeholder feedback confirms that the platforms have leveraged regional capacities and knowledge through fostering cooperation and sharing information and experience among participants. Stakeholder interviews confirmed the regional platform had generated further collaboration, as evidenced by peer-to-peer requests for sharing expertise on whistleblower legislation (Tanzania with Uganda); financial investigation policy and procedure (Tanzania with Ethiopia); and inter-agency coordination (Kenya with Uganda). The regional events were all facilitated by the UNODC experts, who continued to bring in international expertise and knowledge. In South East Asia, UNODC used the opportunity of a regional event on whistleblowing in Cambodia (during the transition year) to start providing support to Timor Leste.
5) Partnership with regional organisations, like EAAAC,[196] and CSO participation have given the regional platforms a stronger foothold and greater visibility in the regions. One hundred CSOs (23 in Latin America, 26 in Southern Africa, 35 in South East Asia and 25 in Eastern Africa)[197] contributed to the recommendations agreed in the four regional platforms. In Eastern Africa, CSOs had their own roundtables and also participated in the follow-up regional workshops in Tanzania (2018) and Uganda (2019).[198],[199] In East Africa, the partnership with EACC complimented UNODC’s own convening power well, with EACC acting both as focal point and repository of knowledge (see Box 17).
[196] https://eaaaca.com/about-eaaaca
[197] # https://www.unodc.org/unodc/en/frontpage/2020/January/unodc-uk-event-showcases-civil-society-initiatives-for-implementing-un-convention-against-corruption.html. CSO public statement during the launch of the South East Asia regional platform can be found here: https://uncaccoalition.org/files/Civil-Society-Statement-Bangkok-Meeting.pdf.
[198] https://www.unodc.org/unodc/en/ngos/steps-towards-a-regional-approach-to-prevent-corruption-in-procurement-and-whistleblower-protection-in-east-africa.html
[199] This included a civil society report in South East Asia in 2018/19 and an East Africa CSO roundtable on their role in fast tracking implementation in 2019/20.
6) The regional platforms have leveraged the work of other technical assistance providers, although more coordination efforts are needed. The regional advisers have played a key role in coordinating the work of other contributing partners to the UNODC’s Global Programme.[200] They have also worked closely with StAR and other UN agencies in country (see Box 18 on South Sudan). As of 2019, Danida was envisaging allocating some of its funds that “may further allow for the expansion of the regional platform approach to Central and Southern Africa”.[201] UNODC also worked closely with GIZ on their certified online training in relation to investigation. Both Danida and GIZ had participated in the launch event in East Africa. The risk of duplication between other donor-funded regional initiatives nonetheless remains high. In East Africa, the UNODC to a large extent relies on the East African Association of Anti-Corruption Authorities (with the Asset Recovery Inter-Agency Network for Eastern Africa) to coordinate donor-funded initiatives.[202],[203]
[200] In South East Asia, Australia, which is also supporting the UNODC regional programme, was reported as having co-funded the launch of the South East Asia platform. Mid-term Independent Project Evaluation of the Global Programme segment Asia-Pacific Joint Action Towards a Global Regime against Corruption (2016-2020) GLOZ99 (Component funded by DFAT) South and Southeast Asia, February 2019.
[201] Danida (2018) Anti-corruption programme, concept note (2019-20).
[202] In East Africa, GIZ is also supporting the East African Association of Anti-Corruption Authorities and Asset Recovery Inter-Agency Network for Eastern Africa to Harmonise Anti-Corruption Laws of Eastern Africa. https://eaaaca.com/index.php/events/harmonization-of-anti-corruption-laws-in-eastern-africa
[203] UNODC also has a Global AML programme, run from Vienna, working with Asset Recovery Inter-Agency Network for Eastern Africa.
7) The launch events were useful in terms of “putting the fundamentals in place” by building consensus on follow-up actions. There is also some evidence to show that, by seeking early endorsement from senior policy makers, the platforms have helped find AC champions. Great efforts were evidently put into bringing in technical experts and high-level government officials at the launch events, although success in doing so varied from one country to another. The evaluation team came across two examples where this approach may have fast-tracked decisions:
- In Rwanda, UNODC achieved some success by encouraging the deputy ombudsmen to put procurement on the agenda of the AC committee meetings. The permanent secretary of the office of the ombudsman (still in post as of writing) participated in the 2017 regional launch event.
- In Burundi, the decision to review and possibly revise the country’s whistleblower legislative framework with support from UNODC was formalised in May 2019, after the participants at the Arusha follow-up event made a request to their superiors. The permanent secretary of the Ministry of Justice (still in position as of writing) participated in the launch event.
Other contributing (and hindering) factors
In South Sudan, it was found that other contributing factors and actors have played a more significant role in getting the government to push the overall AC agenda forward[204] (see Box 18).
[204] The participants attending the regional launch event were mostly from the South Sudan AC Commission, although the deputy director for public prosecution and the legal counsel of the ministry of justice and constitutional affairs were also present.
Box 18: UN coordination and the politics of AC reforms in South Sudan
UNODC’s regional Financial Investigations Adviser for East Africa has recently begun to support South Sudan’s AC commission to develop a Financial Investigation Manual, part of South Sudan’s AC commission reform plans, associated with the refreshed peace agreement road map. The support was to some extent enabled by relations established earlier when South Sudanese officials attended a UNODC workshop in Tanzania (Arusha) and when officials from the AC authority participated in the UNCAC review mechanisms. At the time of completing this report, the UNODC was conducting work with South Sudan in all three thematic areas. / Taking forward the work has involved close collaboration with the UN Mission in South Sudan. The personal networks of mission staff have also played an important role (in terms of being able to draw down support from other parts of the UN system) and ensured broader UN coherence. For UNODC, financial investigation is a competitive thematic area in terms of the provision of technical assistance and, in the absence of a UNODC presence in South Sudan, the regional platform created an entry point for catalysing demand for UNODC’s technical offer at the country level. The UNODC regional financial investigations expert has been responsive to the request and progress is being made on the development of a Financial Investigation Manual. / The back story to this initiative is important. The Mission’s efforts to implement the peace agreement road map has to some extent been constrained by lack of funding. The UN Mission in South Sudan has political leverage but no technical assistance role. UNDP usually provides in-country governance technical assistance through its Rule of Law programme, but has little money (as donor funding moved to other regions, particularly in the Middle East, and there has been a general attrition of bi-lateral donor funding for governance programming).[205] / For the South Sudan government, it is important to be seen taking steps to reform the AC commission as such action will help trigger an IMF loan. According to DFID, the commitment to reform the AC authority was largely driven by the IMF, as part of a series of AFRITAC measures designed to improve economic stability and public financial management, including prevention of corruption, considered endemic in the country. / The hope of the international community is that such small steps will go some way towards slowly building the investigative capacity of the AC authority over the longer term. After years of conflict, South Sudan’s AC authority has remained an institution in name only. The AC bill is moribund, having sat in the Ministry of Justice for the past six years. The AC authority remains under-staffed and under-resourced, its mandate undermined by the more powerful Ministry of Justice and the police. It has yet to undertake any financial investigations.
[205] A coordination call was held on 21 September 2020 between UNODC, UN Mission in South Sudan Rule of Law, UN Procurement Division, International Organization of Supreme Audit Institutions, and World Bank on anti-corruption activities to be conducted in the country and the way to build partnerships.

East Africa and South East Asia are not homogenous regions in terms of scale of corruption or capacity to tackle it. While UNODC attempts to acknowledge these contextual differences in the way it categorises countries in the region, as high, medium or low capacity, many external factors—beyond capacity—will influence success. These include:
- The long-term support from other donors with a country presence, which can complement UNODC’s ‘fly in and fly out’ approach to technical assistance delivery.
- Political incentives, which UNODC has sought to influence with some success by identifying AC champions who can take the agreed actions forward.
- Windows of opportunity, which vary at different points in a country’s electoral cycles, as shown in Kenya.
Verification of GACP’s Theory of Change assumptions
The main assumption underpinning UNODC’s work is that international norms and standards are adapted to country needs. They are effective solutions to strengthening AC policies, laws, regulations and practices and are mutually reinforcing. It is important to note, however, that a weak legal framework and judicial system is just one of many factors driving corruption and organised crime in a region like Eastern Africa.
Table 15: Major driving factors for corruption and organized crime in Eastern Africa[206]
[206] INTERPOL (2019) Corruption as a facilitator of organised crime in the East African Region, October 2019.
Driving factors of corruption and organised crime in the Eastern Africa region
Economic profit
Challenges in evidence gathering
Weak legal framework and judicial system
Lack of specialised skills and experience in investigation and prosecution
Political will
Low wages of public servants
Political patronage
Poverty
Unemployment
Cultural practices

GDMP[207]
[207] Project documentation; stakeholders interviewed specifically on this project: GDMP HQ staff (management team, regional product manager), Indonesia post, Malaysia post, South Africa post, Indonesia (LKPP), Indonesian Corruption Eradication Commission, MLHR, Malaysian Administrative Modernisation and Management Planning Unit, Penang Digital, Open Ownership, OCP.
Overall project performance
- GDMP does not envisage making progress against the logframe’s outcome indicator—number of openly competed procurements run on new or improved systems in priority countries—until Year 3, because most systems that benefit from the project are still in development.
- In Year 2, GDMPreports 12 systems as being positively impacted as a result of its support. As discussed with the GDMPteam, this intermediary outcome indicator should be read as the number of systems, frameworks and/or processes that are currently benefiting from GDMP’s support in the five priority countries. While closer to an output definition, GDMP considers this to be a success in itself, as GDMP was able to build strong relationships with stakeholders and agree a set of prioritised propositions, which were then turned into proof of concepts/protocols, using GDMPexpertise. All projects in South East Asia were still in their alpha/pilot phase at the time of conducting this evaluation.
- At output level, GDMPreports that 14 developmental phases had been completed in Year 1 and 12 in Year 2. According to GDMP’s database, as of October 2020, GDMP had 11 projects in progress; 8 in scoping phase; and 8 on hold as a result of ODA prioritisation; as well as 21 projects listed as opportunities. The majority of these projects fall under three GDMPpillars:[208] designing procurements and contracts; publishing open contract data; and building institutional capabilities and capacities.
  [208] The other two pillars are assuring plans before money is spent; assuring service delivery.
In addition, GDMPshared with the EL team three stories of change, demonstrating the following achievements (those in South Africa demonstrating successful relationship building):[209]
[209] These projects are outside this evaluation’s sampling. GDMP South Africa projects were briefly discussed with GDMP HQ team and FCO in South Africa.
- In Mexico, GDMP’s support to Mexico City’s Digital Agency for Public Innovation helped the Agency to deploy their procurement platform better and faster, by focusing on specific modules (including open contracting modules).
- GDMP supported the Office of the Government Chief Information Officer in South Africa and successfully ran a webinar to help the Office strengthen ICT standards across government.
- GDMP supported the Office of the Chief Procurement Officer, a division of South Africa’s National Treasury, and presented two dashboards that integrate data from various existing systems (a spend data dashboard and a conflict of interest dashboard). The National Treasury has since asked GDMP to produce a dashboard on projects procured since COVID-19 (under special emergency provisions).
The team also shared positive feedback from the Executive Secretariat of the National AC System, in Mexico, where GDMP has supported the inter-connection of data systems between three pilot local AC systems with the National Data Platform, working in partnership with a local Mexican provider. The project’s next milestone, which is expected to be achieved by the end of 2020/21, is to replace dummy data with real data.
### Results in selected regions and countries
No outcome results were reported in South East Asia. The context analysis in Annex 6 of the main report analyses Malaysia and Indonesia’s main achievements in strengthening procurement, e-procurement and open data over the review period.
At the time of conducting this evaluation, all GDMP active projects in South East Asia were still in development and had yet to be rolled out by GDMP’s government counterparts.[210] This, combined with their focus on incremental changes, means that a contribution analysis to higher-level results is not yet possible. Instead, the following section focuses on the likelihood of results in Indonesia and Malaysia, looking at progress to date for selected projects and factors likely to contribute to and hinder their success.
[210] Corresponding to GDMP’s beta and transition phases.
Contributing factors
#### GACP activities in South East Asia
GDMP started its engagement in South East Asia with a scoping visit and discovery phase in late 2018. This work was overseen by the GDMP South East Asia multi-disciplinary regional team until it was disbanded as a result of ODA reprioritisation. The two GDMP delivery managers in Malaysia and Indonesia have also played an increasingly important role in building relationships with key stakeholders.
The first discovery phase, which was carried out by four different companies and completed in August 2019, produced extensive analysis on procurement systems, policy and regulations; digital capability; and open data, with good evidence of extensive consultations involving government, private sector and civil society representatives. The main shortcoming of this first discovery round was that it was too broad in scope, with many propositions falling outside GDMP’s and stakeholders’ remits. According to some stakeholders, this discovery phase was less about understanding stakeholders needs and more about testing the validity of GDMPprojects. Finally, because it was conducted by external consultants, it did not help GDMPstaff to build a relationship with stakeholders.
#### Indonesia
The GDMP database shows that, as of October 2020, the project had four active projects in Indonesia (one in scoping phase, three in progress), working with four main stakeholders.[211] One project with LKPP had been put on hold following ODA reprioritisation. Three projects[212] were completed and three others[213] were listed in the database under “opportunity”. In consultation with GDMP/FCDO, it was decided that this evaluation would focus on GDMP’s partnerships with LKPP and Ministry of Law and Human Rights (MLHR).
[211] National Public Procurement Agency (LKPP), Ministry of Law and Human Rights (MLHR), Ministry of State Secretariat, and Jabar Digital Service.
[212] Completed developmental phases included: the discovery phase; transition workshop; and a technical review of LKPP’s procurement system.
[213] # This includes a project with OCP and LKPP on OCDS implementation.
BO data transparency and BO groundwork, with LKPP and MLHR (scoping)
Progress to date: This work is part of the work that GDMP commissioned in early 2020 to explore and test the linkages between procurement system elements (such as supplier registration), open data and BO registers—leading to the development of the ‘Bluetail’ prototype, which uses a data interface to alert of potential conflict of interest during procurement.[214] In December 2019, a delegation from MLHR came to the UK to meet with GDMPand Open Ownership, which will be the technical partner for this project. A workshop was subsequently held in July 2020 to present the various tools and initial research conducted in Indonesia.[215] Next steps (including sharing of dummy data and translation of BO Data Standards) are being finalised with MLHR.
[214] Where beneficial owners of suppliers bidding for government contracts match cabinet ministers of that government and/or when multiple bidding companies are owned or controlled by the same beneficiaries.
[215] The work was won on a competitive tender by MySociety and SpendNetwork.
Likelihood of success: While the regulatory framework is in place and there is an online BO registry, progress in implementing the next steps (database strengthening, supervision, database utilisation) has been slow (see Box 19). There is also strong reticence from within the government to promote BO transparency. As such, top government officials were said to have been initially unhappy about theGDMP’s project proposal; this was discussed with the UK embassy.
Although MLHR has championed the project,[216] meeting with the Indonesia Financial Intelligence Unit and government planning agencies, promoting BO transparency was not proposed during the discovery phase, and, as such, did not stem from GDMP’s initial stakeholder consultations. In addition to the government’s ambivalent commitment to open BO (and procurement) data, stakeholders shared the following concerns about the project design and, with it, its chance of success:
[216] The Ministry’s engagement with the UK on BO started early in 2016-17 before the country enacted the act. MLHR also had the opportunity to meet with Open Ownership before the workshop.
- limited understanding of the country’s landscape, which is complex and opaque, and language barriers[217]
  [217] The presentation made in July 2020 on BO in Indonesia was described as very brief and succinct, and lacking an in-depth understanding of the country’s BO landscape. During the interview with the EL team, MLHR explained that what was presented during the workshop is not what is going on in practice—with a lot of discussion (some confidential) going on within the Indonesian government. Because of language barriers, the workshop was the only opportunity given to stakeholders to share their feedback (the research commissioned by GDMP was not translated). But participants felt uncomfortable sharing often sensitive information.
- a focus on IT solutions and insufficient attention given to building consensus.[218]
  [218] GDMP’s technical offer is mostly understood by the MLHR technical team. The policy team is, in contrast, less familiar with IT tools and solutions. In addition, the decision to go ahead will require approval from a variety of actors, starting with government planning agencies.
At the same time, the stakeholders agreed that the tools presented by GDMPpartners could be very useful and relevant to the country—the Panama paper identified 1,038 Indonesian businessmen as tax evaders that had shell companies overseas[219]—but that better strategic communication was needed to get all relevant stakeholders on board. When discussing this project with the EL team, GDMP staff also noted the potential legal and institutional blockages and the need for more advocacy.[220]
[219] Open Government Partnership National Action Plan 2018-20.
[220] At the time of finalising this report, Open Ownership was looking to recruit a national consultant to support further stakeholder mapping and engagement and policy mapping on BO in the country.
Box 19: Beneficial ownership landscape in Indonesia[221]
[221] Interviews with MLHR, Indonesian Corruption Eradication Commission; Indonesia Corruption Watch presentation on BO in National Strategy on Corruption Prevention; OPG Indonesia National Action Plan 2018-20; FATF Mutual Evaluation Report, September 2018.
Progress in pushing the BO transparency agenda in Indonesia has been mixed. Progress has been made on the following fronts: / BO regulations adopted 2018-19, with MLHR hosting the online BO/company registry. / BO is a component of the Indonesia National Strategy on Corruption Prevention, which is coordinated by five ministries and agencies (including the Corruption Eradication Commission) and comes under the presidency. / MoU and cooperation agreements have been in place with relevant ministries (including finance, mining, oil, land and spatial) to strengthen and utilise BO data.[222] / Promoting BO transparency in the extractive, forestry and plantation sectors is a government commitment in the 2018-20 Open Government Partnership. / Some CSO engagement (with Indonesia Corruption Watch). / There are also challenges, however: / Government commitment to BO transparency remains ambivalent. / There are no plans to make BO data publicly available, although this is mentioned in the ‘to do list’ of the National Strategy on Corruption Prevention. / Only a small percentage (less than 10%) of companies are currently compliant with BO regulations. [223] There is no effective sanction mechanism. / There are some issues around data accuracy and lack of data verification. / Data integration with relevant ministries is still at an early stage. Ministries tend not to share or request BO data.
[222] Financial Transaction Reports and Analysis Centre (Indonesian Financial Intelligence Unit); Minister of Energy and Mineral Resources; Minister of Finance; Minister of Agriculture; Minister of Cooperation and Micro, Small, and Medium Enterprises; and Minister of Agrarian Affairs and Spatial Planning (National Land Agency).
[223] BO self-declaration only became compulsory in January 2020.

Designing procurements and contracts, including simpler procurement documents, with LKPP (in progress)
Progress to date: This project aims to simplify the procurement documents for suppliers in the ICT sector, as suppliers in this sector are mostly small and medium enterprises with reduced capacity. LKPP’s main procurement documents are currently more than 100 pages long. It is hoped that these documents, once adopted, can be rolled out to other sectors.
This project uses a user-centred, participatory approach. LKPP also received some training, with support from a local supplier. This training was used to develop a prototype simplified template procurement document, which was still in development at the time of the interview. A follow-up workshop was planned to conduct a practice session, involving both federal and provincial procurement agencies[224] and regular suppliers and newcomers (mostly small and medium enterprises).
[224] Including West Java.
Likelihood of success: GDMPhas built a strong relationship with LKPP’s director in charge of regulations, who will ultimately make the decision. It should not take more than a couple of months for the procurement documents to be approved once finalised. As the agency overseeing procurement both at federal and provincial levels, and regulating more than 600 procurement agencies, LKPP is also well placed to roll out the simplified procurement documents across all government agencies. Change management remains complex, however, and careful navigation and stakeholder consultation will be needed to ensure the new documents do not circumvent established regulations and/or legal requirements and are used by all government procurement agencies.
At a higher level of results (impact), the key underpinning assumption is that the simplified documents will attract more start-up companies to compete for public contracts, hence making the ICT sector more inclusive and better value for money.
Co-design procurement systems, including technical support to e-procurement system, with LKPPP (On hold)
Progress to date: Following the alpha transition workshop, GDMP conducted a technical review of LKPP’s centralised digital procurement system to inform the new version that they are developing to replace the current one. This included mapping the user journey and highlighting inefficiencies in the system, such as in the way supplier data is being collected. In April 2020, the GDMP South East Asia team shared a proposal with LKPP regarding support for a centralised procurement platform (April 2020), but this was not pursued following the ODA cut.
Likelihood of success: This project has been put on hold as a result of ODA re-prioritisation. The project also faced a number of challenges, including a new director who came on board and seemed a bit more cautious. While the ongoing e-procurement revision was on paper an opportunity, in practice, it proved challenging to promote GDMP’s agile approach into an already-moving process and come up with the right propositions. At a higher level of results (impact), the key underpinning assumption is that the improved e-procurement system would be used, leading to increased efficiency and transparency. The linkage between e-procurement and AC is not straightforward in Indonesia, however, because the e-procurement system is used for less than half of the transactions; and most data is not made available to the public.[225]
[225] https://openupcontracting.org/assets/2019/04/Indonesia-Brief-on-Public-Procurement.pdf
#### Malaysia
GDMP’s engagement in Malaysia started shortly after the launch of the Malaysia National AC Plan in January 2019, in which the British high commission and GDMP leadership participated. The findings of the first batch of discovery reports were said to have been poorly received, however, in part reflecting poor communication and tone of language. It was subsequently decided to continue to work at federal level but start stepping up engagement with two provinces (Selangor, Penang), a decision that the change in regime only helped to reinforce.
The GDMP database shows that, as of October 2020, the project had five active projects in Malaysia (one in scoping phase, four in progress) working with three main stakeholders.[226] One project with the Selangor government[227] had been put on hold following ODA reprioritisation. Four projects[228] were completed. In consultation with GDMP/FCDO, it was decided that this evaluation would focus on GDMP’s partnerships with the Malaysian Administrative Modernisation and Management Planning Unit and Digital Penang Corporation (Penang State Government).
[226] Malaysian Administrative Modernisation and Management Planning Unit, Digital Penang Corporation (Penang State Government).
[227] Selangor State Treasury Office, Smart Selangor Delivery Unit.
[228] Completed developmental phases included: the discovery phase; transition workshop; and second phase discovery phase with Development Initiatives. Digital Delivery in Government in Selangor.
Designing procurements and contracts, with Digital Penang
Progress to date: GDMPengagement with Digital Penang started in late 2019, a few months after Digital Penang was established, as part of GDMP’s scoping phase. Digital Penang paid a visit to the UK in October 2019 and was then involved in facilitating the deep-dive discovery phase, which GDMP commissioned in the region. In March2020, GDMP conducted a two-day training on digital delivery. Propositions were discussed in May Areas of collaboration between GDMPand Penang State Government were then discussed in an Alpha Planning Workshop, also in June2020. Two projects were selected—one on data sharing standards and one on user research. Digital Penang was finalising a work plan at the time of conducting this evaluation.
Likelihood of success: The project was designed using a participatory process, combining high-level scoping visits (with British High Commission), technical meetings and training, and multi-stakeholder deep-dive diagnosis, whose findings and recommendations were well received. This approach has helped GDMPand its Penang partners to get to know each other and share the same understanding of the context. GDMP also received early approval from the Penang State Cabinet to begin the project. The project fits well with the state development vision of Penang 2030, which includes a pillar on digital transformation (infrastructure, economy, community and government). By partnering with a GDMP-like organisation, the project is expected to progress well during the alpha phase, when the new protocol standards will be developed and tested. The timeline for launching the new standards is harder to predict, however. UnlikeGDMP, Digital Penang does not have the autonomy of decisions. To get the State Cabinet on board, the offer will need to be non-technical and convincing. According to Digital Penang’s own estimates, operationalising the standards could require the approval of as many as 7 official approving authorities and 13 unofficial approving authorities. In addition, change management will also be needed: data is currently shared on a request basis and the government’s culture is quite procedural and bureaucratic.
Designing procurements and contracts, capacity building, and publishing open contracting data, with the Malaysian Administrative Modernisation and Management Planning Unit (and Ministry of Finance)
Progress to date and likelihood of success: The Malaysian Administrative Modernisation and Management Planning Unit is GDMP’s main federal partner. Following the alpha transition workshop in November 2019, GDMP’s support has focused on promoting data sharing policy and standards in ICT procurement, putting in place a framework contract for cloud services, and capacity development. The Planning Unit has received some training, but the projects have yet to start following a change in Unit management, although GDMP has since made good progress in re-engaging with the new management. GDMP also has plans to develop the Silver Eye prototype—focusing on open contracting data standards and use of red flags for anti-corruption—although it was reported that the Ministry of Finance (also part of the consultation) was not yet fully on board. At a technical level, the Planning Unit’s team also noted some early miscommunication and that it did not always feel involved in the decisions (notably with regards to capacity building and choice of training).
Verification of Theory of Change assumptions
The main assumption underpinning GDMP’s model is that the systems that it is supporting will be used.[229] GDMP is well placed to achieve this: its proof of concept and co-designing approach is deliberately designed both to secure commitment from partners and build their capacity to implement and use the systems. The projects in Malaysia and Indonesia were still in pilot phase when this evaluation was conducted, so there was no evidence to verify the success of the approach. What is apparent is that, while GDMP’s approach is well placed to generate lasting results, it also comes with a high delivery risk, as some pilot projects—but not others—are taken forward.
[229] GDMP assumptions in the logframe were listed as follows: Systems are mandatory once created; there is money/necessity/appetite for procurements in those countries so the systems get used; the process of developing new or improved procurement systems builds capacity and commitment to implement and use the systems; these [project phases] stages will lead to the establishment of open and inclusive digital procurement platforms.
Furthermore, the Indonesian and Malaysian contexts show that, even when systems are in place, they are not always used (in part owing to capacity) and/or can be bypassed to make decisions. While GDMP’s main partners directly benefited from GDMP’s training and were shown to have strong capacity, there were some concerns that other government departments likely to use the new systems remained poorly capacitated and that the incentives to use the digital systems (in particular when involving data sharing) were lacking. While some of these issues were highlighted in the first discovery reports, there is no evidence to show that they were used to informGDMP’s engagement in the form of external risks and possibly risk mitigations.
GDMP’s model is also based on demonstrating results through proof of concept, helping to push the AC and transparency agenda forward, even when the fundamentals are not in place. However, a key challenge—highlighted by both GDMPstaff and external stakeholders—is that GDMP products and solutions are only properly understood by a few. More convincing may be needed to get decision makers on board.GDMP’s technical solutions are also inherently political. In most cases, GDMPtechnical expertise will need to be supplemented by softer influencing skills and a good understanding of the context. The embassies and GDMP managers in Malaysia and Indonesia have increasingly played a key role in this regard, and other external partners with a stronger advocacy background, such as OCP, can help. The influence of the language barrier should also not be underestimated.
GACP Financial Action Task Force[230]
[230] Stakeholders interviewed include GACP PT, HMT, FATF HQ (technical director, training manager, mentor), ESAAMLG principal assessors, GIZ regional coordinator, GIZ programme manager.
Overall project performance
FATF has three outputs, one intermediary outcome and one outcome indicator in the GACP logframe. While useful, these indicators do not try to specifically capture GACP’s achievements against the three outputs selected in HMT’s MoU with FATF.[231] Instead, the logframe seeks to measure FATF’s overall performance and contribution to improving AC policies, laws and standards in its member countries—with no distinction being made between countries that are deemed eligible for GACP support and those that are not. As is the case for StAR and UNODC, the logframe’s alignment to FATF’s own approach to tracking results is not clearly articulated. As a result, the intermediary outcome and outcome indicators, which FATF shares with UNODC and StAR, are difficult to read. It is also worth noting that the logframe does not take advantage of FATF’s enhanced 2013 methodology, which, in addition to measuring compliance against the FATF recommendations, assesses the effectiveness of country AML/CFT systems across 11 immediate outcomes.
[231] Output 1: the FATF Secretariat increases its engagement with FSRBs to support a greater understanding of the FATF Standards within those organisations and among ODA-eligible members. Output 2: The FATF Secretariat supports FSRBs to improve their ability to conduct mutual evaluations of their ODA-eligible members. Output 3: The FATF Secretariat supports FSRBs to take a more active role in development assistance coordination and provisions (where relevant).
Main achievements—as reported in the logframe in Years 1 and 2—are understood by the EL team as follows:
- The first output[232] measures the number of MERs that FATF and its regional bodies have completed every year. According to the logframe results, FATF exceeded its 15 MERs per year target when it completed 39 reports in 2018-19 and 26 reports in 2019-20. These numbers largely correspond to FATF’s aggregate results, which show that a total of 41 and 36 MERs (all countries included) were produced in 2018-19 and 2019-20 respectively.[233] It is unclear if the 15 MERs per year target was drawn from the FATF and FSRBs’ MER calendars.
  [232] This output, which is core to FATF compliance mandate, can be found under Theme 4.
  [233] http://www.fatf-gafi.org/publications/mutualevaluations/documents/assessment-ratings.html
- The second output indicates that FATF Secretariat was able to support the review processes of 39 countries in 2017-18 and 37 countries in 2018-19. The FATF Secretariat also organised three training events in 2018-19 and nine in 2019-20. All countries and events are fully listed. However, according to output 3, FATF trained 259 people in Year 2 against a target of 450.
- GACP logframe’s intermediary and final outcome indicators under Theme 1 count the number of countries that have strategic documents in place to improve and/or adopt new AC policies, laws and regulations, and the number of AC policies, laws and regulations that were improved or adopted. The logic behind these two indicators mirrors FATF’s ‘increased monitoring’ mechanism, whereby countries that are put on a ‘grey list’ are actively working with FATF to address non-compliance strategic issues.[234] Countries not on the grey list that demonstrated progress against FATF recommendations in recent MERs or follow-up reports also seem to have been included. In 2019-20, 26 countries were reported as implementing reforms as a result of FATF’s increased scrutiny and/or guidance; with 116 changes to laws, policies and regulations (equivalent to the number of upgrades across all 40 FATF recommendations) being reported in the same year.[235]
  [234] “Jurisdictions under increased monitoring are actively working with the FATF to address strategic deficiencies in their regimes to counter money laundering, terrorist financing, and proliferation financing. When the FATF places a jurisdiction under increased monitoring, it means the country has committed to resolve swiftly the identified strategic deficiencies within agreed timeframes and is subject to increased monitoring”. www.fatf.org. Progress in these countries is monitored on a quarterly basis.
  [235] GACP’s level of contribution was evidently taken on board when setting targets (3 countries; 5-10 changes in laws, polices and regulations), but this was not followed through when reporting against them.
Looking into Year 3, COVID-19 has had a significant impact on the operations of FATF and the FSRBs. This has notably resulted in the ESAAMLG mutual evaluation round being delayed by more than one cycle (three months). While the disruption has also undermined ESAAMLG’s capacity to conduct its own regional trainings, FATF has stepped up its commitment to provide online centrally delivered training, with an exponential increase in reach and potential number of participants.
Results in selected regions and countries
Analysis of quantitative data sets undertaken by the FATF Secretariat suggests that five of the nine ESAAMLG member countries who had completed MERs since 2014 (as part of the second round) and have subsequently been reassessed in Follow-up Reports have shown improvements.[236] Those showing the greatest improvement were Botswana (31 upgrades) and Mauritius (26); those with only moderate improvements were Zimbabwe (14), Ethiopia (11) and Uganda (13). All countries but Uganda are listed in the GACP intermediary outcome indicator. Botswana is worthy of attention as it achieved the most post-MER reassessment upgrades and was also a recipient of the above mentioned direct technical assistance by HMT (see Box 20).
[236] FATF overview report.
Box 20: Botswana’s progress in AML/CFT
Botswana had been included among the jurisdictions with strategic AML/CFT deficiencies and subject to an ‘enforced monitoring and control mechanism’ due to the scope and extent of deficiencies reported in the 2017 MER. FATF grey-listed the country in October 2018, with the government and FATF concomitantly agreeing to an action plan.[237] Concrete steps were subsequently taken to rectify the deficiencies, with the country gaining 31 upgrades in the April 2019 Follow-Up Report, which the authorities requested.[238] The country was expected to be taken off FATF’s grey list by early 2021.[239] / The main improvements were noted as follows: / The national AML/CFT strategy, which includes specific actions on CTF, was adopted in November 2019 and is currently being implemented. Botswana has also recently staffed its Counter-Terrorism Analysis and Fusion Centre and has proposed amendments to its 2020 counter-terrorism regulations in order to implement targeted financial sanctions without delays. Botswana concluded its non-profit organisations’ risk assessment earlier in 2020. / Based on the National Risk Assessment findings, Botswana has started introducing some risk-based measures (such as enhanced due diligence for life insurance services, considered as high risk for money laundering). The country has also embarked on a modernisation project of its company registry to ensure it obtains and maintains basic information and information on ultimate beneficial ownership. / As a result of the above, the number of money laundering investigations is reported to have increased from 0 to 18 in less than two years. Of these investigations, 50% are reported to have been triggered by suspicious transaction reports sent by banks to the Financial Intelligence Unit. It is too early to determine the results of such investigations, but it is hoped that improvements in the country’s AML/CFT structures, systems and skills will reduce risk of money laundering and terrorism financing in the future.
[237] The action plan included: (1) assessing the risks associated with legal persons, legal arrangements, and non-profit organisations, and developing and implementing a risk-based comprehensive national AML/CFT strategy; (2) developing and implementing risk-based AML/CFT supervisory manuals; (3) improving analysis and dissemination of financial intelligence by the Financial Intelligence Unit, and enhancing the use of financial intelligence among the relevant law enforcement agencies; (4) developing and implementing CFT strategy, and ensuring the TF investigation capacity of the law enforcement agencies; (5) ensuring the implementation without delay of targeted financial sanctions measures related to terrorist financing and proliferation financing; and (6) applying a risk-based approach to monitoring non-profit organisations.
[238] The Follow-Up Report re-rates 6 recommendations as compliant; 12 recommendations as largely compliant; and 13 recommendations as partially compliant, while highlighting the need for further actions in some areas.
[239] http://www.fatf-gafi.org/publications/high-risk-and-other-monitored-jurisdictions/documents/increased-monitoring-october-2020.html; https://www.euractiv.com/section/botswana/news/countries-seek-removal-from-controversial-eu-tax-blacklists/ The Botswana government says it had submitted a report to FATF at the end of February 2020. However, an in-person review scheduled for March 2020 was cancelled due to the outbreak of the coronavirus pandemic and postponed to April 2021. Moreover, the Remedial Action Plan agreed by the two parties, valid up to the end of December 2020, was extended to April 2021.

As previously mentioned, GACP’s support to FATF and two FRSBs is more specifically intended to strengthen FATF’s partnership with—and support to—FSRBs.
There is good evidence to show that ESAAMLG’s performance has improved over the years. According to FATF, ESAAMLG had been placed on a performance improvement plan before the start of the second round in 2014, as the quality and timeliness of its MERs were deemed to be lower than necessary for the FATF process. A combination of financial and technical assistance was deployed to improve ESAAMLG performance to ensure that the second round of 18 MERs would be completed on time with commensurate quality improvements. After four years of assistance (e.g. training, mentoring, quality assurance), ESAAMLG has demonstrated sufficient improvements to come of the FATF watch list and a performance improvement plan is no longer in place.
Since the second round started, ESAAMLG has completed nine evaluations.[240] Five are still at different stages of assessment, including Mozambique. ESAAMLG expects to complete all second round MERs by the 2024 deadline. While the pace of conducting MERs has not accelerated, the quality and timeliness of the MERs was said to have improved over the years, in large part owing to a better understanding of FATF’s new methodology and more time given to preparation. For example, assessors believed that MERs for Mauritius and Botswana were poorly executed, compared to Malawi, which was better prepared.
[240] FATF reports that 7 MERs were completed before or shortly after the MoU was signed (March 2018), including Madagascar (April 2018), Seychelles (September 2018), Mauritius (September 2018), Botswana (2017), Zimbabwe (2016), Uganda (2016), Ethiopia (2015).
There is less evidence, however, to show that ESAAMLG has taken a more active role in development assistance coordination and provisions (output 3 in the FATF-HMT MoU).
Contributing factors
GACP FATF’s activities
The following activities were confirmed during the stakeholder interviews:
- FATF has heightened its quality assurance role through the appointment of dedicated desk officers for each of its nine FSRBs. In the ESAAMLG region, the FATF Secretariat reviewed scoping notes (Mozambique, Eswatini) and MER drafts in Tanzania.
- FATF provided training to individuals from ESAAMLG member countries to understand and implement the FATF standards into their domestic regime, and to act as high-quality assessors for countries in the region. In February 2017 (South Africa) and April 2019 (Tanzania), FATF organised regional trainings to train future ESAAMLG assessors. In addition, FATF organised its first online assessor training in September 2020. Botswana authorities participated in all three events. They also attended a 2018 regional course on FATF AML/CFT standards organised by the FATF in Zambia in December 2018, and other at the FATF’s training centre.
- Since COVID-19, there is evidence of more people accessing and interacting with new knowledge products, particularly through greater investment in online training initiatives.
GACP FATF’s contribution
In the absence of baseline values and more specific indicators[241], assessing GACP’s contribution to FATF’s strengthened partnership—and support to—FSRBs remains difficult. Training has been a core element of FATFs technical assistance to ESAAMLG and other FSRBs for many years. TREIN piloted its first training in 2018 (with some initial GACP seed funding).[242] Similarly, ESAAMLG had completed seven MERs before or shortly after GACP funding started—one in 2015, two in 2016, one in 2017 and two in 2018,[243] with another two produced with GACP funding.
[241] Most baseline values for FATF’s output indicators are zero, while FATF Secretariat already provided regular training to its FSRBs before the project started.
[242] http://fatf-trein.org/fatf-trein/about/fatf-trein.php
[243] Madagascar (April 2018), Seychelles (September 2018), Mauritius (September 2018), Botswana (2017), Zimbabwe (2016), Uganda (2016), Ethiopia (2015).
According to the FATF Secretariat, the increased resources at the Secretariat have helped strengthen FATF’s engagement with FSRBs, and, with this, increase its scrutiny of and guidance towards all member countries. In Botswana, the newly appointed FATF dedicated officer was able to provide day-to-day guidance and discuss challenges with ESAAMLG. GACP FATF was also said to have paid for the recruitment and training of country assessors conducted by ESAAMLG (normally five-person multi-disciplinary review teams).
GACP has also helped FATF to improve its training offer, aiming to consolidate improvements in ESAAMLG MER efficiencies. Furthermore, ESAAMLG considers FATF’s approach to training to have become more strategic. There is, for example, a greater attempt to ensure that those trained will participate in forthcoming assessments.[244],[245] There is also a greater focus on ensuring participants are representative of key institutions (e.g. financial intelligence units, banks and drug enforcement agencies) and from different professional disciplines (e.g. lawyers, forensic accountants, law enforcement officials, internal auditors).
[244] FSRB assessors argue that stakeholders they meet when conducting the MER assessments are often different to the ones that attended the pre-MEL awareness training sessions. Such issues are not always noted by those in the FATF Secretariat as they are often one step removed from the beneficiary relationship (yet such issues could be better picked up by those providing supporting technical assistance to the specific country).
[245] For instance, of the five ESSAMLG members trained in September, two will be on the Kenya assessment team, two on Namibia and one on Eswatini.
Finally, despite being unearmarked, some activities and outputs were directly attributed to GACP funding. This included HMT’s participation in Botswana’s donor consultation in early 2019, and, according to ESAAMLG,[246] the timely completion of the country assessment in Zambia (April 2019) and Malawi (September 2019). ESAAMLG expects to use the remaining funding to undertake assessments of Angola and Kenya.
[246] ESAAMLG (July 2020), mid-term review of the UK support to ESAAMLG to strengthen AML/CTF.
According to FATF, UK’s increased attendance at FATF meetings has also helped.
Other contributing factors
ESAAMLG considered Botswana’s success was down to a mix of high-level political commitment to authorising recommended actions, good inter-agency coordination led by the Financial Intelligence Unit and timely, tightly targeted donor technical assistance.
While not as serious as being black-listed, countries on the grey list are considered to have a much higher risk of money laundering and terrorism financing, which can in turn have a negative repercussion on their relationship with institutions like the IMF and the World Bank[247] and detract trading opportunities.
[247] Botswana was also put on the EU’s grey list in October 2020. https://ec.europa.eu/info/business-economy-euro/banking-and-finance/financial-supervision-and-risk-management/anti-money-laundering-and-counter-terrorist-financing/eu-policy-high-risk-third-countries_en
As such, getting off the grey list has remained the main driving factor behind Botswana’s high-level political commitment to work with the FATF and ESAAMLG to strengthen the effectiveness of its AML/CFT regime and address any related technical deficiencies. According to the IMF, while the health of the financial system in Botswana has not been impacted so far by the FATF decision, it has reportedly contributed to delays in outward investment by asset managers and shifts in the management strategy of assets abroad with attendant effects on costs.[248]
[248] IMF (April 2019) 2019 Article Iv Consultation – Press Release; staff report; and statement by the Executive Director For Botswana. https://www.imf.org/en/Publications/CR/Issues/2020/03/18/Botswana-2019-Article-IV-Consultation-Press-Release-Staff-Report-and-Statement-by-the-49276
With FATF involvement, Botswana’s Financial Intelligence Unit was able to coordinate the relevant agencies by rolling out UNODC’s Go-AML platform to financial institutions, notably banks and casinos. This support from FATF and UNODC was useful. As a regional body, ESAAMLG often lacks the convening power to undertake what is predominantly a country-based coordination role.
Finally, under IMF leadership, key donors, including the US Treasury and UK HMT, were invited to participate in an AML/CFT diagnostic scoping mission in February 2019, soon followed by a technical assistance mission in May 2019, to help deliver a post-MER Action Plan with clear measures and associated milestones and deadlines. It is in this context (and with limited GACP funding) that HMT provided advisory support to the country.[249]
[249] The ‘crisis management strategy’ approach and use of strategically targeted technical assistance from other public sector governance donors, including Germany (GIZ), IMF, World Bank and HMT, could also be found in other member countries. For instance, after Mauritius was put on the FATF list, GIZ aligned its resources to a rapid response initiative. GIZ is also supporting Kenya as it prepares for its (now delayed) MER next June.
It is also important to note that ESAAMLG staff believed Botswana had been ‘unlucky’ as one of the first countries to be subject to the more complex FATF assessment framework they had been poorly prepared for. According to some stakeholders, Botswana was hence probably closer to complying to FATF recommendations than was reported in its 2017 MER.[250] This in part explains the significant upgrade in Botswana’s 2019 Follow-Up Report.
[250] While Botswana is listed by both the FATF and is proposed as a country with strategic deficiencies by the EU on their ‘grey’ list (expected to take effect in October 2020), Botswana is not listed by the US as a ‘Country of Primary Concern’ in respects to money laundering and financial crime.
While FATF Secretariat’s support to FSRBs can help improve their ability to conduct timely and good quality mutual evaluation, many variables remain outside the Secretariat’s control. In particular, much of the MER success is contingent on the ability of ESAAMLG to ‘cascade’ training after ‘Training of Trainers’ events to country-based assessors. Furthermore, the ability of ESAAMLG assessors to collect data against 11 outcomes in addition to the 40 best practice standards is heavily dependent on the country capacity to pull together the data in advance of FATF country visit. Data was also often found patchy and inaccurate.
In the case of ESAAMLG, its improved performance reflects greater predictability of membership fee payments and ESAAMLG’s own learning by doing. Thanks to improved membership funding, ESAAMLG was able to increase the number of core experts and technical staff. This has contributed to ensuring consistency and continuity in the compositions of assessment teams, and helped improve the quality of coordination with those countries undergoing mutual evaluations. ESAAMLG has also learned from its first MER (including Botswana), by placing greater focus on preparing country teams in advance of the assessments. In Malawi, for example, an in-country training was conducted for the country-based assessors and all the people that needed to be involved in the process. HMT contribution to this success is hence deemed moderate.
Verification of Theory of Change assumptions
The key assumptions underpinning FATF’s work are directly related to the acceptance of FATF’s recommendations as international AML/CFT standards and effectiveness of its compliance rating reviews and mechanisms.
There is good evidence to show that governments take their rating against FATF recommendations seriously. As such, the process of preparing for and completing a MER and the subsequent engagement with the recommended MER action plan is likely to contribute to stronger systems in terms of laws, policies and procedures to counter money laundering and terrorist financing. Government incentives, however, are evidently higher when their country is put on FATF’s black or grey list. These countries also tend to receive more attention and support from international financial institutions. Much also depends on whether MERs are used to foster ownership and commitment in terms of the implementation of the MER recommendations, not just the MER.
The main stumbling block for FATF is the slow completion of MERs and challenges raised regarding the comparability of ratings. In the ESAAMLG region, all countries that have requested a follow-up report since their MERs were first conducted were significantly upgraded, in part because of progress in the countries in dealing with inefficiencies and in part because of the assessor bias that seems to characterise the first MERs conducted under the new FATF methodology. As put forward in the list of assumptions, timely quality completion of MER is also contingent on a balance of political will and technical capacity, supported by accessible and reliable data. In addition, the lack of in-country data collection mechanisms or demand for data other than during MERs remain a key challenge. There is also a general paucity of outcome data, particularly as it pertains to assessing functionality rather than form (e.g. analytical quality of suspicious transaction reports, number of money laundering investigations).
At a higher level of results, the main assumption is that action taken to improve compliance to standards and outcomes will reduce money laundering and terrorism financing risks. Findings from Botswana strongly validate this assumption, according to reports of money laundering investigations, but there was less evidence of progress in countries such as Zambia or Malawi, where risks are lower. In addition, stakeholder interviews pointed to the risk of political interference when dealing with suspicious transaction reports. According to GIZ and other technical assistance providers, the incentive for such behaviour can be to use suspicious transaction report information to target tax evaders in order to improve the domestic tax base in the context of growing debt burden and budget constraints. Conversely, it can also be used to target those investors unprotected by high-level patronage networks, reflecting collusion between the Financial Intelligence Unit and revenue authority staff for instance. Suspicious transaction report analysis can also be used to inhibit the funds being channelled to political opponents from diaspora groups in the lead up to elections.
IACCC[251]
[251] Stakeholders interviewed on IACCC were: (i) IACCC, ICAR, UK Central Authority at HQ; (ii) in Kenya: EACC (direct beneficiary), in-country ICAR adviser, National Crime Agency Independent Liaison Officer Nairobi, Criminal Justice Adviser Nairobi and former CJA Nairobi; (iii) in Malaysia; (iv) elsewhere.
Overview of project performance
IACCC’s indicators in the GACP logframe include four output indicators; two intermediary outcome indicators; and two outcome indicators. IACCC does not have a separate logframe. All indicators are relatively well defined and representative of IACCC’s modus operandi,[252] except for IACCC’s contribution to capacity building, which is not measured (See 4.1.2). Its target setting is also realistic: for example, the focus of its final outcome is on the value of potentially recoverable assets, rather than the value of assets returned, in recognition that it can take up to 10 years for assets to be returned once identified.
[252] To inform – which organisations and initiatives can offer assistance; to assist – with practical actions and advice; to collect – information to form a single picture of grand corruption; to coordinate – an effective global law enforcement response; and to collaborate – creating a constructive, cooperative and agreed approach.
In Year 1 (2018-19), IACCC performed better than expected throughout the result chain:
- The number of new referrals into the IACCC totalled 35 against a milestone of 16. IACCC also received more delegations than planned. This confirms that IACCC has successfully raised its international profile, compared to the initial years when it was mostly unknown to most partner countries. IACCC has also reached its Year 1 target, by bringing in nine participant agencies. There are also plans to build on a recent UK-Switzerland cooperation agreement to bring a UK-based Swiss officer into the IACCC on an observer basis. (outputs)
- IACCC also took on 11 new cases with potentially recoverable and tangible stolen assets, against a target of 6. The number of additional intelligence packages disseminated by IACCC totalled 19 against a target of 1. (intermediary outcomes)
- In Year 1, the IACCC identified GBP 55 million of potentially recoverable and tangible stolen assets between August 2018 and July 2019, against a target of GBP 51 million. (outcome)
Year 2 (2019-20) data was obtained late in the evaluation and has not been verified by the EL team. The data shows, however, that IACCC continued to exceed expectations albeit against relatively conservative milestones. Reported results include:
- Number of additional intelligence disseminations: 54 against a target of 5. (intermediate outcome)
- Value of potentially recoverable and tangible stolen assets identified (cumulative): around GBP 200 million[253] against a target of 75 million. (outcome)
  [253] GBP 212,207,213.20 to end July 2020.
Bringing the smaller financial centres into IACCC as associate members has, anecdotally,[254] already started to improve the speed and quality of the intelligence that IACCC offers to affected states. In Year 2, IACCC planned to take on 13 news cases with potentially recoverable and tangible stolen assets and disseminate 5 new intelligence packages which, together, would lead to a cumulative value of potentially recoverable and tangible stolen assets amounting to GBP 75 million, the arrest of six more senior public officials, and the submission of eight new MLA requests.
[254] Interview with IACCC
Looking further ahead, the COVID-19 pandemic has hindered IACCC’s performance in a number of ways:
- Although IACCC was the least impacted of all GACP projects by the ODA reprioritisation, resources are tight and it is close to operational capacity. For this reason and for fear of raising expectations that it cannot meet, IACCC is not currently focusing on attracting new referrals and cases.
- In contrast to other projects, the outputs of the IACCC are slower to achieve remotely.. Successful MLA procedures rely on “direct, working-level contacts between different authorities”.[255] With incoming delegations and outgoing deployments being put on hold, IACCC has found it difficult to maintain and develop its close personal relationships, especially in countries like Angola, where the National Crime Agency has no country presence. According to IACCC, this is beginning to slow progress on some cases.
  [255] U4 Issue 2019:12, Asset recovery and illicit financial flows from a developmental perspective: Concepts, scope, and potential.
According to IACCC, the logframe targets[256] have been raised to reflect better than planned performance, and while the impact of COVID-19 has reduced the number of inward delegations and deployments (with a potential impact on the longer-term pipeline of new work), IACCC remains on track to meet its case-related targets in Year 3.
[256] Almost all KPIs are reflected in the logframe. 3 of the 5 IACCC output indicators are also KPIs. Both of the IO indicators are very similar to two of the KPIs. Of the 2 output indicators that are not KPIs, one relates to cases involving multiple jurisdictions (3.5) and the other is “Number of IACCC deployments and case-specific partnerships with other anti-corruption organisations and initiatives” (3.1) – this combines two KPIs, if imperfectly – # of deployments and “Coordination with other initiatives (i.e. ICAR, STAR) to progress grand corruption investigations”.
Results achieved in selected regions and countries
IACCC’s contribution to the Malaysia Anti-Corruption Commission’s successes in the 1MDB asset recovery case was put forward as an example of GACP impact in the spending review. In addition, IACCC has recently developed two stories of change, which describe two results in Kenya, which it says it has contributed to:
- In Malaysia, the MACC froze over USD 300 million worth of assets connected to 1MDB, a state-owned fund, and a settlement with Goldman Sachs worth a further USD 3.9 billion. The scandal involved the former Malaysian Prime Minister Najib Razak who was convicted of corruption charges in July 2020. The fraud was an intricate one, involving assets in multiple jurisdictions stretching from South East Asia and The Gulf to New York and Hollywood.
- In Kenya, a criminal case has now been finalised, making its way through internal EACC processes. This case has now been forwarded to the Office of the Director for Public Prosecutions.[257]
  [257] https://www.capitalfm.co.ke/news/2020/08/governor-obado-his-4-children-to-face-sh73mn-graft-case-for-fleecing-migori-county/
- Also in Kenya, the identification of overseas assets and unexplained wealth belonging to a former public official is providing evidence to inform an ongoing investigation into allegations of corruption.
While many other factors and actors have contributed to the above successes, IACCC’s contribution was largely verified as both positive and unique, as discussed in the following sections.
Contributing factors
IACCC’s activities in Malaysia and Kenya
While some information was deemed too sensitive to be shared, stakeholders interviewed and available documentary evidence confirmed IACCC’s level of engagement as follows:
- IACCC’s partnership with the Malaysian authorities, specifically MACC, started in 2018. IACCC’s main activity was to package intelligence from multiple jurisdictions and help MACC strategize and coordinate its investigation, both with jurisdictions within IACCC such as the US and jurisdictions outside IACCC, to maximise assets recovered. IACCC also helped MACC draft and submit successful MLA requests to the UK.
- In Kenya, stakeholder interviews, including with beneficiaries, confirmed that for a specific criminal case IACCC has helped to facilitate and fast track the evidence collection for MLA requests from the EACC. This included facilitating MLA requests to the UK and coordinating MLAs from England, Scotland and Australia. In doing so, the Centre worked with the National Crime Agency International Liaison Officers and the ICAR[258] embedded adviser to support the EACC’s investigation and prepare the case for prosecution. Elsewhere, the National Crime Agency was asked to help the EACC because of the suspect’s regular travel to the UK and property that they allegedly owned in the United States.[259]
  [258] ICAR is funded by I-ACT to provide technical assistance in the investigation and prosecution of corruption, bribery and recovery of assets. Its core model is to work through embedded advisers, mostly in sub-Saharan Africa. ICAR technical assistants work with partner governments under case consultative agreements and, while that often gives them some of the status of a sworn officer of that jurisdiction, are more consultants than law enforcement officers.
  [259] In Kenya, the Criminal Justice Adviser is funded by CSSF, while the National Crime Agency Independent Liaison Officer and ICAR in-country adviser are funded through i-ACT.
IACCC’s contribution
Assessing IACCC’s level of contribution can be difficult in complex cases where there are many international players involved (see below). In addition, IACC utilises partnerships with other HMG-funded in-country advisers (ICAR, criminal justice advisers, National Crime Agency Independent Liaison Officers) and the UK Central Authority, which means credit usually accrues to the UK rather than to the IACCC.
Stakeholders at large confirmed IACCC’s positive contribution and added value as follows:
- By bringing specialist law enforcement officers from multiple foreign jurisdictions into a single location to work on specific cases, IACCC’s model of delivery fills an important gap, which complements rather than duplicates other donor initiatives (see below). More specifically, without the coordinated approach that IACCC offers, an affected state would likely have to progress through a chain of MLAs—each one giving it access to evidence that enables it to identify other jurisdictions that it needs to apply to for a MLA.
- By associating with smaller financial centres,[260] IACCC brings key players into an international network. The smaller financial centres have a significant role to play in the identification, seizure and recovery of assets related to grand corruption cases in affected states.[261] In its early years of operation, IACCC-supported investigations repeatedly encountered difficulties coordinating intelligence gathering with smaller financial centres. As these smaller centres do not have the resources to deploy full-time representatives into IACCC, a new category of associate membership was created as a cost-effective way of bringing them in.
  [260] When considering inviting smaller financial centres to join, each full time IACCC member jurisdiction identified the top five smaller financial centres encountered in its own domestic grand corruption investigations. These lists were then analysed against the IACCC caseloads to identify priority countries to be invited. In total, 16 were invited, 9 accepted.
  [261] See, for example, StAR External evaluation 2019.
- IACCC’s facilitation of MLA requests to the UK typically involves taking a referral by an informal route—often directly from the law enforcement agency in the affected country—and working with the UK Central Authority to review drafts prior to submitting a formal request. This has helped to expedite the process and ensure a better chance of success than a formal process from an inexperienced law enforcement agency developing country that may well have a long route to the UK.[262], Other IACCC members, the Australian Federal Police for example, work on MLAs in in a similar way with their respective Central Authority.[263]
  [262] For example, from the investigator who writes the request, to the prosecuting authority for issue, to the Director of Public Prosecutions for approval, to the interior ministry, to the foreign ministry and then submission to the UK. There is a huge potential for delay or blockage because of lack of knowledge of the process or for more nefarious reasons.
  [263] Interview, IACCC.
- Stakeholders also confirmed that IACCC has helped strengthen partner law enforcement agencies’ ability to frame and draft requests for assistance and intelligence, better understand and follow processes for international cooperation, turn intelligence into evidence to develop a case, and adopt improved investigation practices.
- Success achieved through IACCC’s (and others’) support was also said to be instrumental in building the confidence of law enforcement partners and the confidence of the public and government in those partners that they can more successfully bring grand corruption cases to fruition.
In Malaysia, the USA Department of Justice and Malaysia Anti-Corruption Commission have publicly acknowledged IACCC’s contribution.[264] MACC also recognised the British High Commission in December 2019 for its contribution to AC efforts, specifically citing IACCC’s contribution to the 1MDB investigation.[265]
[264] ttps://www.justice.gov/opa/pr/us-seeks-recover-more-300-million-additional-assets-traceable-funds-allegedly-misappropriated
[265] The UK received an Anti-Corruption Champion Award from MACC on Anti-Corruption Day, 9 December 2019.
Other contributing factors
The above achievements first and foremost reflect the conducive political environment that has characterised Malaysia and Kenya over the review period. In Malaysia, the regime change in 2018 saw a strong focus on prosecuting grand corruption and recovering assets, as the then-ruling multi-party coalition came with an AC drive led from the top. A key feature of this effort has been a successful attempt to investigate the old regime for grand corruption and to locate and return assets. Similarly, there is a currently a positive enabling environment in Kenya for the fight against corruption. This is led from the top—President Kenyatta has been vocal about his wish to create a legacy—and has international support (and pressure).
The growing capability of partner law enforcement agencies, some with support from other donors, has also been an important contributing factor: In Kenya, EACC, the lead agency on corruption investigations, has become more proactive and established an international team to undertake intelligence-led inquiries over the past seven years following a strengthening of its mandate in the 2010 constitution, a new CEO in 2013, and increased support from political leadership. The support that EACC has received from other donor agencies, in particular GIZ, has also been an important contribution to its successes. GIZ, in particular, supported the introduction of a multi-agency team, allowing EACC to strengthen its collaboration with other relevant agencies involved in combating corruption. [266],[267]
[266] Other agencies are: Kenya Revenue Authority; Ethics and Anti-corruption Commission (EACC); Office of the Director of Public Prosecutions; Directorate of Criminal Investigations; National Intelligence Service; Financial Reporting Centre; Asset Recovery Agency; and Office of the President.
[267] In Malaysia, other foreign agencies assisting MACC with the IMDB case include the Swiss Office of the Attorney General and the Singapore Police.
The importance of regional networks in promoting cooperation should not been underestimated either. Relevant organisations include The Asset Recovery Inter-Agency Network for East Africa and the Asset Recovery Inter-Agency Network for Asia Pacific in South East Asia.[268],[269]
[268] A mapping of asset recovery networks can be found here: https://star.worldbank.org/sites/star/files/networks-16-reduced-maps.pdf
[269] Malaysia also belongs to the Economic Crime Agency Network (ECAN), a formal network of law enforcement organisations involved primarily in the investigation and prosecution of economic crimes, which includes 12 law enforcement agencies including the European Union, Hong Kong, Indonesia, Malaysia, New Zealand, Nigeria, the United Kingdom and the United States.
Finally, other donor-funded initiatives also focusing on international cooperation, notably ICAR, UNODC, and StAR, have also contributed to the above successes.[270] While the evaluation noted a risk of overlap between IACCC and StAR when supporting the same countries and the need for more coordination, these initiatives were overall found to complement rather than duplicate each other.
[270] Another international initiative is Norway-funded Corruption Hunter Network, which since 2005, has provided an informal peer-to-peer network of individual investigators and prosecutors, mostly from Europe, sub-Saharan Africa and South America. https://norad.no/en/front/thematic-areas/democracy-and-good-governance/corruption-hunters/
IACCC has also learned that it is most successful where it has close in-country partners such as the National Crime Agency and ICAR to work with.
Verification of Theory of Change assumptions
The above findings both confirm and enrich GACP’s ToC assumptions on asset recovery (see Annex 1).
- Strong political will and a shared commitment to fighting corruption remains the main overarching assumption behind IACCC’s success. In the case of IACCC, shared commitment also requires goodwill at all stages of the criminal justice chain. Some cases supported by IACCC (including in Kenya and Malaysia) were said to experience delays or stalling due to lack of political will and/or inefficiencies in other agencies in the criminal justice chain, such as the courts. In Malaysia, the political upheaval in early 2020 has led to the old regime re-joining government, which has reduced the political appetite to fight against corruption and the ability of MACC to carry out its mandate.
- The long view needed for seeing through grand corruption cases and returning stolen assets is widely accepted—see StAR.[271] The above findings also show that identification and seizure of assets is not just the end point of a criminal prosecution for corruption but can, in parallel, inform an investigation and help build a criminal case, which is IACCC’s entry point.
  [271] https://star.worldbank.org/about-us/frequently-asked-questions (ii) Building trust between law enforcement agencies, often via personal relationships, is crucial to the intelligence sharing process and progressing complex international investigations. Police-to-police information sharing is the precursor to International Letters of Request/MLA requests.
- Malaysia and Kenya case studies also confirmed that building trust between law enforcement agencies, often via personal relationships, remains crucial to the intelligence sharing process and progressing complex international investigations. Successful MLA procedures rely on “direct, working-level contacts between different authorities”[272] In countries like Angola, where there are no in-country advisers from ICAR/NAC, IACCC has struggled to maintain momentum and establish the relationships and channels of communication necessary to progress an investigation quickly and efficiently. The ban on travel as result of the COVID-19 pandemic has made this even more striking.
  [272] U4 Issue 2019:12, Asset recovery and illicit financial flows from a developmental perspective: Concepts, scope, and potential.
- Finally, the two case studies show that IACCC’s success is also largely reliant on their main counterparts having the right capacity, leadership and mandate, as well as networking capacity. The long-term capacity building support that AC Commissions receive from other donors and organisations like UNODC—and ongoing partnership with other law enforcement agencies in the region—are also important factors to IACCC’s success.
StAR[273]
[273] Key stakeholders interviewed on StAR were StAR, UNODC, ICAR at HQ and in selected countries, including Nigeria, Malaysia, Ethiopia. Additional documents used included StAR external review 2019, StAR Annual Report 2019, StAR quarterly newsletters, StAR monthly calls with GACP. It was not possible to interview MACC on asset recovery efforts.
Overview of project performance
StAR’s contribution to GACP objectives, as represented in the logframe, broadly reflects its own description of how its work is organised: policy influence and partnerships, country engagement, and knowledge and innovation. The GACP logframe includes all five result indicators, which StAR is using to report to donors[274]—some more implicitly than others. There are also additional indicators that FCDO requests, which were not formally agreed as part of StAR reporting: scoping missions and metrics on knowledge products; and workshop participant satisfaction surveys. There are still some data measurement and alignment issues, however, some shared by StAR implementers.[275],[276]
[274] Number of countries improving legislative framework on asset recovery; number of asset recovery cases opened that include a proceeds of corruption component; number of countries with improved domestic coordination mechanisms adopted as asset recovery action plans; concrete inputs into key global asset recovery policy themes through leadership at events and through use of knowledge products; knowledge gaps and emerging trends identified and addressed in new knowledge products.
[275] StAR notably disagrees with outcome indicator under Theme 3, number of AC law enforcement actions through arrest, production orders and asset restrained (outcome indicator 2). At the same time, the work that StAR is doing in facilitating international cooperation between requesting and requested countries (as reported in their Annual Reports) is not captured.
[276] The EL team also notes that StAR’s main indicator on policy influence, namely concrete inputs into key global asset recovery policy events is listed under Theme 1. This classification means that StAR’s more global ambition to participate in global events to keep asset recovery high on the global policy agenda and influence international standards is not adequately captured.
Main achievements—as reported in the logframe and complemented by the StAR Annual Report in Year 1—are understood by the EL team as follows:
- Under Theme 1, StAR reports that three countries (Moldova, Tunisia and Mongolia) have improved their legislative framework on asset recovery in Year 1, followed by another three (Ukraine, Uzbekistan and Armenia) in Year 2. Under intermediary outcome 1, StAR reports Macedonia, Moldova and Malaysia have improved domestic coordination mechanisms adopted as asset recovery action plans, followed by another five countries (Sri Lanka, Ecuador, Armenia, Ethiopia and Colombia) in Year 2. In addition, according to StAR’s annual report, in 2019, StAR conducted 21 national capacity building exercises and contributed to two regional workshops, training a total of 670 people.
- Under Theme 3, scoping visits were reported in Ecuador, Pakistan, Colombia and Malaysia in Year 1, followed by another two (Zimbabwe and Sudan) in Year 2. In addition, StAR helped develop and facilitate country-to-country links to support international cooperation on asset recovery. In 2019, StAR held 35 such bilateral meetings, 23 of them in the margins of the UNCAC Conference of the State Parties.
- Also under Theme 1 (but relevant to Theme 4 and StAR’s work on policy influence), StAR largely exceeded its target by making 25 and 23 concrete inputs into key global asset recovery events in Year 1 and 2 respectively (output 1.3). The breadth of events, which are all listed, demonstrates StAR’s international standing and influence on the global agenda. Over the year, the “StAR Day” has become a key element of the Conference of the State Parties in which StAR coordinates a day of sessions and dialogue on asset recovery.
The impact of the COVID-19 pandemic on StAR’s work this year has been to postpone scoping visits and some other country engagement where relationships had not yet developed sufficiently to be able to be sustained remotely. Close support on specific cases has also proved difficult to deliver remotely.[277] In some countries, notably Ethiopia, StAR was nonetheless able to innovate, by organising weekly two-hour trainings with the Directorate for Asset Recovery within the Attorney General’s office. Global and regional events have either been cancelled, postponed or conducted remotely.
[277] Interviews with StAR.
Complementing the results in the logframe, StAR has developed a story of change on the success of the 2017 GFAR, which GACP supported with transition funds. This story of change was then used as example of GACP impact for the comprehensive spending review. It is explored in more detail in the following section:
“StAR—played integral role in conceptualising and support the convening of the first ever GFAR in December 2017, co-hosted by UK and US with four focus countries (Nigeria, Sri Lanka, Tunisia, Ukraine). The event brought together over 300 participants representing 26 jurisdictions as well as international organisations, civil society, and media to recommit to the global asset recovery agenda outlined in UNCAC. Through the GFAR platform, new agreements were signed between countries, such as an MOU between Nigeria, Switzerland and the World Bank. Recent returns of stolen assets have referenced the importance of GFAR principles, as evidenced in the case of over USD 300 million being repatriated from Switzerland to Nigeria.”
Results in selected regions and countries
Success stories associated with StAR are related to:
- Malaysia’s successful asset recovery efforts. StAR reports that Malaysia has improved domestic coordination mechanisms following the adoption of an asset recovery action plan, as a result of its support.
- Nigeria, which is one of the four GFAR countries, where some progress has been made in returning some of the Abacha II stolen fund, with Switzerland returning USD 300 million to the Nigerian government in 2017 and USD 267 million being seized from a Jersey account in 2019. As put by the BBC, however, “the money is just a fraction of the billions of dollars that were allegedly stolen and laundered during the presidency of Mr Abacha”.[278]
  [278] https://www.bbc.co.uk/news/world-europe-jersey-48509274?intlink_from_url=&link_location=live-reporting-story
StAR’s activities and (direct and indirect) contribution are assessed in the following section.
Contributing factors
StAR’s activities
The sensitive nature of much of StAR’s work makes reporting and assessing contribution difficult. StAR’s facilitation of inter-country cooperation and direct case-related support is, by its nature, silent diplomacy and behind the scenes. Despite limited access to key stakeholders, the EL team was able to verify the following activities:
According to the information available, StAR’s main contribution to asset recovery in Malaysia was related to supportingMACC’s international cooperation efforts and providing trainings on the use of open source investigation for asset tracing. StAR’s assistance to Malaysia has also focused on linking Malaysia with other jurisdictions and facilitating agreements on cooperation on intelligence in relation to the 1MDB case. The start of StAR’s support to Malaysia was in 2019 at an event hosted by the UN Resident Coordinator’s Office in Malaysia and attended by national stakeholders, UNODC, UNDP and UK FCO. StAR went on to assist MACC with facilitation of contacts with foreign jurisdictions that were particularly difficult for Malaysia to access. These resulted in cooperation on information and intelligence in relation to the ongoing 1MDB case (see below). There has been little activity in 2020 due to the change in government in Malaysia and the impact on travel of COVID-19.
During the 2017 GFAR and in subsequent years, StAR stepped up its engagement in four focus countries, including Nigeria. GFAR was a successful event supported by GACP transition funds, and was attended by over 300 participants representing 26 jurisdictions as well as international organisations, civil society and media.[279] The event was hosted by the US and the UK, and supported by the G7, Switzerland, UNODC and the World Bank.
[279] GFAR Communique December 2017
StAR’s contribution to asset recovery
The above findings, combined with those on IACCC and the 2019 StAR External Review, confirm StAR’s contribution and main added value in supporting partner countries’ asset recovery efforts, as follows:
StAR’s facilitation of inter-country cooperation has positively contributed to addressing individual asset recovery cases in affected countries. At the same time, while StAR can facilitate inter-agency cooperation through its INTERPOL/StAR global focal point network on asset recovery, its own staff resources are very limited, which means that they mostly rely on consultants to support their capacity building work.[280]
[280] The StAR secretariat is staffed by World Bank and 1-2 UNODC secondees who are full-time assigned to StAR. Most technical staff work on other projects in addition to StAR.
StAR’s main added value is related to its convening power and policy influence. As shown with GFAR, this can in turn contribute to results in affected countries. The event, which focused on progressing the recovery of assets stolen from Nigeria, Sri Lanka, Tunisia and Ukraine, enabled numerous other side meetings that advanced international cooperation on individual cases of return of stolen assets and requests for technical assistance that StAR has taken forward... A few days after the event, on 4th December 2017, the governments of Nigeria and Switzerland and the World Bank signed a tripartite agreement setting out arrangements for the return of USD 321 million of funds and the World Bank’s monitoring role.
The GFAR event was also used as an opportunity to launch the GFAR principles on monitoring asset recovery (see below). Monitoring of returns is an expectation of the MoU between FCO and the National Crime Agency.[281]
[281] April 2019
Box 21: Emerging results from implementing the GFAR principles
The GFAR Principles for Disposition and Transfer of Confiscated Stolen Assets in Corruption Cases[282] set out standards to govern returned funds and “address approaches and mechanisms for enhancing coordination and cooperation, and for strengthening transparency and accountability of the processes involved”. The principles aim to address the concerns of affected countries in relation to infringement of sovereignty (where return agreements direct how the funds should be spent) and the concerns of countries returning the funds that these funds will not be re-corrupted. The principles notably recommend the early involvement of civil society– from the drawing up of the agreement to the monitoring of spend of returned funds—to ensure that funds will be used to benefit the populations of the affected states. The return of the Abacha II stolen funds to Nigeria from Switzerland that was agreed at GFAR is an example of the GFAR principles in action: civil society was involved in the drawing up of the agreement and in monitoring the spend of returned funds.[283] The GFAR principles have since informed future legal and policy work in this area including an asset forfeiture bill in France[284] and calls by civil society for a multilateral agreement on asset recovery[285] and a set of Civil Society Principles for Accountable Asset Return.[286]
[282] https://star.worldbank.org/sites/star/files/the-gfar-principles.pdf
[283] Conducted through Africa Network for Environment and Economic Justice (ANEEJ) funded by DFID Nigeria.
[284] https://www.u4.no/the-obiang-case-how-will-france-return-stolen-assets
[285] Transparency International and UNCAC Coalition Submission to the UNGASS against Corruption: Proposal for a Multilateral Agreement on Asset Recovery 12 June 2020.
[286] Joint submission to the UNGASS against corruption of: Africa Network for Environment and Economic Justice (ANEEJ), CiFAR – Civil Forum for Asset Recovery e.V., Civil Society Legislative Advocacy Centre, CISLAC Nigeria, Human Rights Watch, I Watch (Tunisia), The International State Crime Initiative, Transparency International EU, Transparency International France.

StAR’s long-term mandate (recently renewed for a further ten years) and modality of funding gives StAR the ability to take a long-term view. StAR also has a unique offer and is viewed as authoritative technically and non-affiliated.[287] These findings are in line with the 2019 External Review,[288] which finds that StAR’s uniqueness lies in its knowledge products, its ability to broker between countries (particularly in the case of certain jurisdictions) and, StAR has continued to hold bilateral meetings in the margin of the UNCAC Conference of the State Parties.
[287] Results of research to inform StAR website redesign; Discovery Findings presentation 28 September 2020; interviews with in-country stakeholders including CSOs and Anti-Corruption Commissions; interview with StAR.
[288] StAR external review 2019 https://star.worldbank.org/governance
Other contributing factors
The contributing factors related to the context are analysed under IACCC (See preceding section)
Verification of the Theory of Change assumptions
IACCC and StAR share many implicit and explicit assumptions. In addition to those already discussed under IACCC, the above findings lead to the following conclusions:
Some of the assumptions identified by StAR in the GACP logframe are delivery risks, for example, the risk of dramatic political changes where the projects are active, which would prevent them from implementing planned legal/policy or regulatory reforms. However, StAR’s experience shows that, in order to be successful, asset recovery efforts require careful balancing between seizing political opportunities and sustaining long-term engagement. StAR is usually invited by a country to assist only when there has been a regime change or similar political upheaval that has triggered a commitment to prosecuting grand corruption and recovering stolen assets. Conversely, political upheavals can slow the rate at which reforms will be achieved or halt them completely. StAR has shown, however, that its engagement can and should be sustained by working on less controversial, more technical reforms, while waiting to take advantage of a return to a positive environment when it occurs.
According to Transparency International, only a small percentage of the roughly estimated USD 400 billion proceeds of corruption from developing countries has been recovered and returned in the last 10 years.[289],[290] IACCC’s association with smaller financial centres and StAR’s strategic re-focusing on its original mission to deny safe havens for stolen assets will help. Improved legal frameworks and greater capability make taking criminal and civil proceedings against individuals easier and more likely to succeed. It appears that these successful actions are only a drop in the ocean, however: StAR’s experience with the return of the Abacha II funds to Nigeria shows that this is a long-term exercise (it took eight years from confiscation to return), was complex (involved a coalition of 134 CSOs), required agreement between the states involved, and required funding (DFID Nigeria funded the CSO monitoring).
[289] Transparency International and UNCAC Coalition Submission to the UNGASS against Corruption: Proposal for a Multilateral Agreement on Asset Recovery 12 June 2020.
[290] StAR is currently undertaking a data collection exercise to try to put up-to-date numbers on the value of assets recovered worldwide.
In addition, as pointed out by the 2019 External Review, there has been a proliferation of safe havens over the years, which has made asset recovery efforts even more challenging. Monitoring of returns is an expectation of the MoU between FCDO and the National Crime Agency.[291]
[291] April 2019
Open Ownership[292]
[292] Stakeholders interviewed on Open Ownership were (i) at HQ, Open Ownership, OCP, DFID (ii) in Kenya, FCO post, TI-Kenya, Business Registration Services, GIZ, and Open Government Partnership.
Overview of project performance
Open Ownership’s indicators in the GACP logframe are tightly framed around Open Ownership’s mission to promote public BO registers. They include two output indicators; one intermediary outcome indicator; and two outcome indicators. Open Ownership does not have a more detailed logframe for its project. While it recognises that some countries—including those that committed to a public register during the 2016 UK AC summit—may choose to set up a non-public BO register first, Open Ownership is reluctant to consider this intermediate step as an indicator of success. It is with this in mind that the project performance against the logframe should be interpreted:
- At an output level, the organisation has increased the number of countries it provides tailored assistance to faster than planned, with five new countries in Year 1 (against a target of two) and another four in Year 2 (against a target of four). As discussed in Section 2.5, while Open Ownership may characterise its tailored assistance to these countries as ‘sustained’ or ‘significant’, in some countries, like Kenya, Open Ownership remains a relatively small player when compared with the work of other donor-funded organisations.
- At an intermediary outcome level, no additional country established a public BO register in Year 1, and one (Armenia) did so in Year 2 (against a target of two). Open Ownership is confident that its target in Year 3 will be met, however, when four new countries are expected to open public BO registers (including South Africa, Indonesia, and Mexico).
- At an outcome level, the number of entries on the global register exceeded its target by 1 million in Year 1, before increasing in Year 2 from 6 million to 6.7 million (against a target of 7 million). As discussed with Open Ownership, this indicator is not as representative and/or specific as it should be: the number of countries that feed into the registry has remained unchanged, which means the additional entries first and foremost reflect greater compliance from private companies. This indicator hence does not match Open Ownership’s initial ambition, which was to set up a truly global register from multiple countries and sources.
In the spending review, Open Ownership’s success is reported as follows: “Open Ownership has become the preeminent global organisation with deep policy and implementation expertise on what is required for delivering BO to effectively support anti-corruption goals and improve the business environment. They have built key technical tools to support the implementation and use of linkable beneficial ownership data around the world. This includes developing the first open-source standard for company ownership information, the BO Data Standards, and working with 30+ countries (including UK Overseas Territories) to implement it. Open Ownership also developed the global Open Ownership Register—an open-access portal for linking and searching company ownership data from around the world—which currently holds 22.7m records (including 6.5m companies).”
This claim was partially verified, as follows:
- Open Ownership’s website has hit an increasingly large number of users, from 9,800 in Year 1 to 15,000 unique users in Year 2; corresponding to 150,000 visitors per year. By offering free access to its guides, templates and tools made available on their website, Open Ownership does not know who its primary users are and where they come from, however. This means its engagement in 30+ countries can only be measured through specific requests made through its help desk or through its participation in events.
- The BO Data Standards have recently been referenced in two flagship publications by the World Bank[293] and OECD as a useful framework for representing BO information.[294] At the moment, however, there is no verifiable information on the extent to which the standards are known and used in partner countries. In Kenya, some key stakeholders did not seem to be familiar with the BO Data Standards, while Open Ownership could not verify the extent to which the new registry was aligned to the standards.[295]
  [293] https://www.worldbank.org/en/topic/governance/publication/enhancing-government-effectiveness-and-transparency-the-fight-against-corruption
  [294] BO Data Standards can in principle be used for both public and non-public beneficial ownership.
  [295] A comparison between Open Ownership’s draft note and the Company regulation shows that Open Ownership’ recommendations on the BO forms were not taken forward.
Results achieved in selected regions and countries
This section focuses on achievements in Kenya. Kenya was one of the first countries in Africa to commit to develop an open BO register in 2015. Despite promising developments up until 2018-19, the authorities eventually decided not to make the newly established BO register available to the public. A timeline of key decisions and events related to the BO agenda in Kenya is given in Box 22.
Open Ownership has also provided tailored support to Nigeria and Ghana. While these three countries have made good progress with setting up their BO registers, at the time of writing this report, none of them had made it available to the public, despite previous commitment to do so. There are many factors, outside Open Ownership’s control, that explain this mixed success story.
Box 22: Timeline of key events and decisions related to BO in Kenya
2015: The Kenyan government commits to “create an open, usable and publicly accessible BO register” as part of its Open Government Partnership Action Plan (2016-18) under the leadership of the Office of the Attorney General. The first multi-stakeholder consultation is organised in 2015, with TI-Kenya co-hosting the event. / 2016: During the 2016 UK AC summit, Kenya committed to “take measures in line with her new Companies regulatory framework to establish public central registers of company beneficial ownership information” and ensure “that international and domestic law enforcement agencies have full and effective access to beneficial ownership information for companies and other legal entities registered within their jurisdiction”. / 2017: President Kenyatta signs the Companies Act amendment, which defines BO and requires companies to disclose information about their beneficial owners to the Registrar of Companies. Initial plans to set up a BO register, involving the e-citizen platform and InfoNET Africa, are discussed. / 2018: An Executive Order (effective 1 July 2018) sets out disclosure requirements for government tenders, requiring all procuring entities to maintain, update and publicise complete information on all tenders awarded, including ‘full particulars’ (including beneficial ownership) of their suppliers. According to the Executive Order, this information must be publicised, including through the website of the Procuring Entity, e-Citizen, and Public Procurement Information Portal. / 2018-20: Office of the Attorney General holds consultations with key stakeholders on the drafting of the new Company Regulations. / 2020: The Company Regulations are passed by parliament, requiring companies to register BO with the Registrar of Companies. The regulations state that “beneficial ownership information shall not be made available to the public”.

In Kenya, NGOs and Open Ownership have decided to wait until more progress has been made with the BO registry before advocating for open BO data again. Open Ownership was nonetheless hopeful that Ghana and Nigeria would open their registers in the forthcoming year(s).
Contributing factors
Open Ownership’s activities in Kenya
The campaign to promote BO in Kenya started a few years before Open Ownership began operation. Open Ownership started to provide support to Kenya in 2018, when it was invited to make recommendations on the draft company regulations, as part of broader stakeholder consultations (see below).[296] In its draft note prepared in mid-2018, Open Ownership recommended that Kenya’s BO register be made free and accessible to the public—arguing that, in its current form, the register “will limit the effectiveness of the register for businesses and civil society as a due diligence and anti-corruption tool. It also means that data quality problems may be slower to surface, as the data lacks external scrutiny”.[297]
[296] In Kenya, it was said that the Kenyan authorities had reached out to Open Ownership through their help desk; and also that Open Ownership had offered to help them during the 5th Open Government Partnership Global Summit in Tbilisi, Georgia, on 17-19 July 2018.
[297] Other recommendations included a call for clarifications on exemption to reporting requirement and sanctions; some modifications on the BO form; and the need for more guidance to report changes to BO interests.
In 2019, Open Ownership, with Open Government Partnership, discussed with the Deputy President/Attorney General’s Office Kenya’s membership to the HMG BO Leadership Group. [298] At the time of writing this report, Kenya’s membership to the group had yet to be confirmed; however, this group in effect requires all its members to sign up to best practice disclosure principles, including on BO data.
[298] The Leadership Group initiative was launched by John Penrose, Minister of State for Northern Ireland, United Kingdom at the Open Government Partnership Ottawa conference in 2019. This Group came together in 2019 to drive the global policy shift towards free open BO data. The group is comprised of Kenya (tbc), Armenia, Latvia, Mexico, and the Slovak Republic.
In early 2020, Open Ownership visited Kenya to participate in an event hosted by TI-Kenya[299] and meet with the authorities, with a view of providing continued support to the Kenya Business Registration Services and continue lobbying for open BO data. There was no further country visit because of the COVID-19 pandemic.[300]
[299] This multi-stakeholder event focused on open contracting for health. http://ti-health.org/content/health-systems-transparency/
[300] Business Registration Services was said to have participated in one of the Open Ownership webinars organised in 2020. https://www.openownership.org/events/openownership-tech-showcase-webinar/
Open Ownership’s contribution
Stakeholders in Kenya agreed that Open Ownership’s influence on the BO agenda in Kenya has been positive, but relatively modest, in part because its efforts to push for a more public element to the Kenyan BO register have largely failed, and in part because many other organisations and actors have also played a role in pushing the BO agenda forward.
- In countries like Kenya, Open Ownership faces stiff competition: many other organisations, with greater capacity, local presence and/or international stature,[301] offer technical advice on BO (albeit with a lesser focus on open data); while advocacy NGOs, like TI-Kenya, are better placed to maintain a sustained relationship with key government counterparts.
  [301] This includes FATF, the World Bank, StAR and GIZ.
- Open Ownership’s contribution in Kenya is hence best appreciated through a multi-stakeholder lens, where it joins other advocacy organisations and technical partners, each bringing their own specialist knowledge, to promote BO agenda. While Open Ownership’s ambition is to support BO at all stages of the BO implementation journey, a lot of BO transparency success will ultimately rely on country-led advocacy efforts and strong technical presence on the ground.
- Open Ownership was notably valued for its technical expertise on what “good looks like” and for bringing in a global perspective. Key stakeholders interviewed in Kenya confirmed that some of Open Ownership’s inputs into the draft company regulations had been relevant and useful.
Looking ahead, the opportunity for sustained technical engagement with Kenya appears limited, however, as directly confirmed by Business Registration Services and other stakeholders.[302] The bulk of the work has already been carried out on the BO register software, which is now up and running.[303] At present, the main priority for the Kenya Business Registration Services is to get companies to comply with the new 2020 Company Regulations, with support from GIZ (see below). On an advocacy front, the prospects for getting the authorities to re-commit to a public BO register in the immediate future are considered low.
[302] In the scoping phase of Transforming Procurement Systems, Open Ownership had shared plans to develop and test their software to collect and store BO data. Open Ownership was also hoping that the Office of the Attorney General would sign a letter of intent to confirm its commitment to a public BO register and, in so doing, seal its membership to the BO Leadership Group.
[303] While the BO register will not be public, the software has been developed to allow the public elements to be reintroduced at “the click of a button”, according to GIZ.
Other contributing (and hindering) factors
The government’s desire to comply to FATF recommendations was confirmed as the main factor driving progress on BO in the country. The government’s main priority is to improve its rating on the FTAF recommendation on BO by the time its next review is conducted in 2020-21.[304] At the same time, FATF recommendations do not go so far as requiring BO information to be made public.[305] This constitutes a major hindrance to pushing Open Ownership’s transparency agenda forward.
[304] In its 2011 MER, ESAAMLG had rated Kenya as largely ‘non-compliant’ with the FATF recommendation on BO. Despite recognising progress with the new Company Law, FATF ESAAMLG 2018 post-evaluation report available still considered Kenya non-compliant. https://esaamlg.org/reports/Progress%20Report%20Kenya-2018.pdf
[305] FATF’s requirement is that “countries should ensure that there is adequate, accurate and timely information on the beneficial ownership and control of legal persons that can be obtained or accessed in a timely fashion by competent authorities.”
Because the government first committed to BO as part of its Open Government Partnership National Action Plan (2016-18), the advocacy agenda around BO has also been highly participatory.
- CSOs—some local, some regional[306]—have been involved in monitoring the government’s commitment to beneficial ownership since 2015. Their engagement with the Attorney General’s Office deepened in 2017, when TI-Kenya (with UK aid support through Transparency International-UK), assessed the BO transparency legal framework against the ten G20 BO transparency principles.[307]
  [306] Transparency International (K) and Humanistic Institute for Cooperation with Developing Countries East Africa, Article 19, Tax Justice Network, International Budget Partnership InfoNET Africa Ushahidi.
  [307] TI-Kenya, (September 2017), Towards Beneficial Ownership Transparency In Kenya: An Assessment Of The Legal Framework.
- In 2018, with GIZ’s assistance, the Office of the Attorney General developed the companies (BO information) regulations and a first prototype for the Beneficial Ownership e-Register, which were both subjected to stakeholders’ consultations from within government and with key external stakeholders, including CSOs. This is when Open Ownership was also invited to send its observations. GIZ has since continued to remain Business Registration Services’ main technical partner.[308]
  [308] Another relevant initiative includes InfoNET‘s development of an open BO Registry Portal in the infrastructure sector. http://usajili.ke. This portal holds data on past and existing tenders awarded for infrastructure development in select counties in Kenya while linking it to the respective company awarded whose ownership/directorship is made open to public scrutiny.
The relatively successful advocacy campaign was very much facilitated by a strong lead from the government side, as represented by the Office of the Attorney General and, on the more technical side, Business Registration Services. This was not enough, however, to overcome resistance further down the path. While the draft company regulations included a regulation to make the BO register public,[309],[310] the Department of Justice asked it to be removed before the regulations could be tabled before parliament.
[309] The draft regulations did not go so far as providing free access to BO data.
[310] As explained by Open Ownership, advocating for small legal changes, such as lowering the threshold for disclosure requirement—while small on paper—can have significant repercussions. This disclosure requirement was successfully lowered in Kenya to 10%, a decision that was already reflected in the draft company regulations and pre-dated Open Ownership’s first inputs but reflected strong advocacy from NGOs and other partners in preceding years.
According to the stakeholders interviewed, two main factors could explain the government’s U-turn away from making its BO register public:
- Some stakeholders argue that the very progressive legislation passed in 2017 and 2018 were a bit of a “stroke of the luck”, as those making the decision were not fully aware of the repercussions that open BO data would have on vested business interests involving politically exposed persons.[311]
  [311] In addition, neither the 2017 Company Act amendment nor 2018 Executive Order needed parliament approval.
- Kenyan authorities were becoming increasingly concerned about the risks associated with data accuracy and data confidentiality.[312] Under the current regulations, only the AC commission and law enforcement agencies will have access to BO data.
  [312] As shown in rare occasions, there is a risk that the release of private data could lead to a lawsuit being launched against government.
Kenya’s AC context was described by one stakeholder as made of competing “push and pull” interests, with the “against” camp eventually winning over the “pro” camp. For similar reasons, stakeholders noted that—while in itself a significant advancement—the 2019 Executive Order linking BO with public procurement would not be sufficient to ensure open procurement (and with it BO) data. Some stakeholders also shared concerns that the use of BO data by law enforcement agencies would come with a high risk of political interference.
Verification of Theory of Change assumptions
The above assessment both confirms and enriches Open Ownership’s and related GACP’s ToC assumptions.[313] It shows that two assumptions underpinning Open Ownership’s model have not been met yet—namely, that countries will follow the BO Data Standards which will enable data to be shared with the global register and data will be accurate, high quality and comprehensive. The lack of international standards requiring BO to be made public (with FATF preferring a risk-based approach); issues around data verification and accuracy; and the limited evidence of BO Data Standards being used as a global framework, explain this situation. At a global level, Open Ownership’s success depends on whether the UK government will be successful in making public register a global norm by 2023.
[313] Open Ownership’s main external assumptions listed in the logframe are: (i) countries will follow the BO Data Standards which will enable data to be shared with the global register; (ii) data will be accurate, high quality and comprehensive. In the GACP ToC, main assumptions are the overarching assumption on strong political will; target groups being independent and free of political interference; getting full support from government and parliament; and having the right capability; and open data systems are accurate.
The case study in Kenya also confirms that Open Ownership’s main counterparts indeed need full support from government (including Department of Justice) and parliament to implement the BO agenda. A key assumption underpinning Open Ownership’s model, which has remained implicit, is the importance of a multi-stakeholder, coalition-building approach to push for the BO agenda, which Open Ownership has actively supported through its Open Government Partnership, and was said to have worked well in Kenya.
At the same time, Open Ownership’s strong alignment to the UK AC agenda and its “follow the UK lead” approach to opening a public BO register remains the organisation’s main strength and raison d’etre. Open Ownership has notably maintained a close partnership with the Home Office JACU over the years. Open Ownership’s strong leadership team is also well placed to address some of the above challenges and steer the organisation in the right direction.
Gender and inclusion: Approach and detailed analysis
Introduction
In Cycle 1, the GACP programme evaluation has sought to understand the ability of the programme design to deliver G&I results, and how feasible and achievable GACP’s level of G&I ambition is in relation to its design, strategies, activities and resources. The approach used is set out in the EL Year 3 Thematic G&I Approach Paper and comprises the answering of evaluation questions (EQs) and a scorecard assessment:
- The G&I scorecard[314] has been used to assess whether GACP meets PF minimum standards on G&I. The scorecard provides a framework to interrogate six programme dimensions (programme design, internal capability and incentives, accountability, financial resources, delivery partners and results) on a rating scale of 1 to 3 (red, amber, green). Green indicates that the programme meets the associated PF minimum standard on G&I, amber score indicates not clearly aligned with PF G&I policy minimum standard, with areas for development OR unable to provide evidence.
  [314] As revised in November 2020.
- All EQs have a G&I element and G&I aspects will be probed to answer them.
- In addition, EQ3 specifically addresses G&I considerations: “To what extent is GACP likely to contribute to results that support gender equality, women's economic empowerment and social inclusion?”
This annex provides an overall assessment of G&I-related issues in the design and implementation of GACP, followed by action plan updates for each project.
Programme G&I Scorecard
SCORECARD DIMENSION (AND pf MINIMUM REQUIREMENTS )	RAG RATING	FINDINGS
Design		Headline findings / G&I analysis in the initial business case was weak and the PT (supported by the SDA) made significant efforts in the first year of the programme to flesh out the G&I approach and the evidence that underpins it and revise the business case for publication. This initial work helped to inform delivery partner G&I action planning (see next section), but has not, overall, been specific enough to inform their detailed design and delivery. This is partly due to the programme’s focus on corruption, a difficult area in which to identify entry points for G&I-focused results, but also due to its institutional, thematic and geographic spread, and the fact that detailed social assessments were not carried out at an early enough stage to inform design. / Focused and more context-specific assessments are beginning to be seen in places at the project level, but more could have been done to encourage or require these earlier in order to better inform design and delivery. / G&I action plans have not been fully completed across the board and are not being used or ‘owned’ by most of the projects. / G&I approach and analysis / assessment / Business case: The main way in which the business case addresses gender issues is through arguing that the prevention of corruption can ensure governments channel increased levels of funding into public services such as healthcare and education (and women disproportionately tend to benefit from these services).[315] / The PT drew on advice and expertise from the PF SDA to develop a G&I Vision and Approach for GACP (February 2019, updated August 2019). This goes some way to filling gaps in the business case, feeding ideas for relevant activities into action plans, and for disseminating PF G&I guidance to projects. Analysis is still relatively high level, however, with no context-specific analysis—partly due to the spread of the programme, thematically and geographically. / The PT identified a need for further research and analysis to help GACP identify “What evidence currently exists on the links between corruption and gender and inclusion and what are the evidence gaps?”[316] A request in August 2019 to U4 for research on G&I and corruption resulted in a Help Desk answer in October 2019. The research was disappointing in that it focused on gender rather than gender and inclusion and did not take the PF (or GACP) context into account. A request to the WoW helpdesk to help add further detail to the U4 research and identify more programme-specific evidence gaps the programme could fill[317]was considered in January 2020 but was not followed up—initially due to COVID-19 related pressures on PT and SDA time/redeployments and, latterly due to lack of budget to commission from WoW.[318] In November 2020, the PT developed proposals to U4 on specific research topics relevant to GACP (with support from the SDA). Its proposal on Social Protection and Corruption has been accepted. It hopes that this will both inform delivery and enable the programme to have contributed to filling evidence gaps in what is known about G&I and corruption.[319] / Context-specific programme-level analysis has been difficult without GACP priority countries—interventions are widespread and disparate in technical focus as well as geographic focus. However, some projects have conducted or plan to conduct G&I analysis relating to their area of operation and country context. / GDMP commissioned a report[320] that included detailed G&I country assessments in five focus countries.[321] / UNODC: Appreciation of the PF’s focus on G&I came too late for integration into the earlier regional platforms (South East Asia and East Africa) but is more evident in the newer platforms (Southern Africa, and South America and Mexico).[322] / IACCC: The design of the WATCH network is currently being informed by a survey of women in law enforcement in sub-Saharan Africa.[323] / Meaningful G&I integration into project design includes: / UNODC: The PT and SDA’s engagement with UNODC delivery team in mid-2019 is credited with gender becoming more central to UNODC’s delivery work within the GACP-funded project and more broadly. A member of the gender team supports implementation of the project. / IACCC: Greater disaggregation of statistics in relation to officers received in delegations and trained; setting up of the WATCH network for women involved in the investigation of corruption. / GDMP: G&I considerations are integrated throughout the ToC, and a user-centred design that is inclusive of women and disadvantaged groups is central to the project’s approach. / The OECD project documents suggest a general aspiration to ensure that the benefits of globalisation are well distributed[324] and some OECD staff report that G&I considerations formed an inherent part of project design (and OECD’s work more broadly), referencing the need for vulnerability to be considered in policy development and research. However, there appears to have been some resistance to further integration of G&I when requested by the FCDO (following the PF’s development of GACP’s approach). This is common to both GACP and the ASEAN Economic Reform programme. / Although the Open Ownership project has not seen the relevance in integrating G&I into project delivery, it has paid particular attention to gender and diversity when recruiting new staff, developing a gender and inclusive policy to cover hiring and other key functions. In the last year, they recruited their new staff using a “blind” approach, selecting candidates on the basis of written submissions, rather than on CVs. / G&I action plans (see individual project action plans in main body of Annex) / The PT (with SDA support) held a workshop with project leads (March 2019) to identify entry points for specific G&I work, appoint G&I champions and support drafting of action plans. / All projects apart from StAR developed (or the PT developed for them) either full G&I action plans or a list of planned actions. However, the plans have been little used. The only projects that appear to be monitoring progress against their action plan are IACCC and GDMP. Others have achieved some key actions (e.g. GDMP), but the majority have not used it to guide delivery, updated it or reported against it. / The Open Ownership project has struggled with understanding the relevance of the PF G&I approach to the project. This is in response to what the project sees are limited opportunities for achieving G&I results. It has not achieved any of the actions in its G&I action plan and has not used it to inform delivery. / The HMT AML (FATF) project has also not used the G&I action plan to guide delivery. / StAR does not have a G&I action plan, it having been viewed as inconsistent with the multi-donor trust fund modality by the PT. / Action plans are over 18 months old, so a review as the projects progress into implementation would have been good practice. In addition, context changes (e.g. COVID-19 pivots and ODA reprioritisation) would have been expected to prompt a review of G&I action plans. A workshop is now planned for early 2021 to support strengthening of G&I action plans (with timeframes/ milestones, responsibility, resources etc) and refresh of delivery partner actions.
Internal capability and incentives / (Good use of HMG social development expertise in place, along with active capability building on part of programme team. / Active G&I champion.)		Headline findings / There has been good use of HMG SDA expertise at strategic points—including in developing the programme’s G&I Vision and Approach, supporting early action planning, and engaging HMG and multilateral partners on the PF G&I approach. / The PT has a strong G&I lead who has been the first global PF programme champion, proactive in the G&I champions network and has taken the programme forward on G&I. His short-term redeployment to other teams over the past few months has reduced PT resources available for G&I. / There have been some clear efforts to hold delivery partners to account on G&I, particularly in the first year of the programme. However, the stresses put on PT resources by COVID-19 pandemic redeployment, the ODA reprioritisation exercise, and the uncertainty as to future programme plans resulted in reduced monitoring of G&I to both support and hold delivery partners to account. As a consequence, there is unevenness across the programme portfolio on G&I. / The uptick in capacity towards the end of 2020 once the PT and the SDA team were back to full strength indicates an intention to reprioritise G&I. / Use of HMG SDA expertise / The SDA’s involvement in GACP came early on and her expertise was used by the PT to inform the GACP G&I approach and vision paper and to support a PT workshop in March 2019 to engage cross-government delivery partners on the PF G&I approach and action planning. The SDA went on, in July and August 2019, to lead or support presentations and discussions at OECD and UNODC headquarters on the PF G&I approach and potential entry points for the projects concerned. The PT also drew on the SDA at the end of 2019 to further strengthen the business case for publication. Other occasions where SDA assistance was sought include: wording on GDMP's procurement and research (ICT Commissioning), assessment of UNODC's proposal, grant competition for Behavioural Insights, and research proposals to U4. / It appears that opportunities for delivery partners to attend G&I champions sessions offered by SDAs in 2020 were not taken up by projects or disseminated to GACP delivery partners by the GACP G&I champion. These sessions were on updated PF G&I guidance, and action planning templates and guidance. / PT capability and incentives / GACP was one of the first global PF programmes to be proactive on G&I. It was viewed as somewhat of a trailblazer as a result.[325] This early progress was due to the efforts of the PT (particularly, the G&I lead) and to strategic use of SDA expertise. / Initial engagement with delivery partners on the PF G&I approach and possible entry points for the programme to achieve G&I results took place March to August 2019. Cross-government delivery partners were assisted with action planning and introduced to PF G&I guidance, policy and tools. The PF G&I agenda was shared with multilateral delivery partners too, with formal requests of OECD and UNODC to consider how G&I could be further embedded in G&I activities and to draw on their internal gender expertise. / This work has not been sustained, however, with systematic follow up and monitoring of agreed action points. / The 2019 Annual Review had a focus on G&I and recommended that “by the end of May 2020, ALL project leads should ensure that G&I is fully embedded into project-level implementation plans”. This has not happened. Most additional recommendations on G&I remain valid and require PT and project lead urgent attention: / Project Leads: Embed the project-level G&I actions plan into measurement of implementers’ delivery success. Where possible, share lessons across the programme on actions that are having an effect. / Project Leads: Ensure delivery partners have access to their own requisite G&I expertise to further build awareness; and develop, implement and monitor their G&I action plans. / GACP programme team: Arrange additional G&I workshops with project leads/delivery partners to help share experience, good practice and learning; and further adapt and implement G&I-sensitive project activities.
Accountability / (G&I integrated into monitoring, reporting and evaluation, with disaggregated data and indicators. / Active stakeholder and beneficiary engagement (including women and excluded groups))		Headline findings / There is disaggregation of some indicators in the logframe but no related disaggregated targets and almost no[326] disaggregated reporting to date. / Some projects are collecting gender disaggregated data related to participation, e.g. IACCC on incoming delegations and training participants, but this is not captured by the programme logframe. / Capture of G&I results is mainly at output level as number of G&I activities, although outcome 4 shows consideration of G&I, aiming to increase awareness of the causes and impacts of corruption, including on G&I. / Reporting templates suggest but do not require G&I reporting, and there is no robust system in current use for reporting against G&I action plans. / Beneficiary engagement is limited for many projects by the nature of their design. Some projects, however, have integrated it into ways of working. / Monitoring G&I results through the logframe / Indicators with G&I disaggregation are: / Output indicator 4.1: New knowledge products disaggregated by how many include G&I. There are two recorded as achieved (OECD ACI forum had an equal gender balance between speakers in Years 1 and 2). In addition, GDMP’s products this year are either G&I focused (Oxford Insights report, April 2020) or have G&I integrated (Digital Buying Guide October 2020) and will contribute to this indicator. / Output indicator 4.3: Number of behavioural insights phases carried out. Disaggregated by how many include G&I and by project. Zero disaggregated results. Preliminary design only—project discontinued. / Intermediate outcome indicator 4.1: Number of people accessing and interacting with new knowledge products. Disaggregated by age, socio-economic group, ethnicity, and gender where available and applicable. Disaggregated results from OECD are recorded. / Intermediate outcome indicator 4.3: Participant understanding and satisfaction ratings with workshops/products. Disaggregated by project and by age, profession, ethnicity, gender where available and applicable. No disaggregated results. / Some projects are collecting gender-disaggregated data that is not reflected in the programme logframe (e.g. GDMP, IACCC). / Outcome 4 has considered gender and inclusion. / Increased awareness of the causes and impacts of corruption including G&I; and knowledge and application of best practices/approaches (e.g. behavioural insights) to address corruption in priority countries. To be measured through surveys, focus groups and media analysis in priority countries. / Output indicator 4.2 is a specific indicator to capture project G&I actions at output level, capturing a mix of activities, some focused internally to the programme and some external. / Number of new instances when projects have taken actions to become more gender and inclusion aligned (e.g. workshops, collecting disaggregated data, plans etc.). Target for 2019 = 9, achieved. / There is no distinction of type or quality of G&I activities captured under output indicator 4.2. There is a risk that good G&I results will not be adequately captured, either at output or outcome level, unless captured by outcome 4 indicators in relation to raised awareness. / There is no facility to capture benefits to poor and vulnerable women and men flowing from returned stolen assets. There is already, however, one such result, with statistics available, and the potential for more. As a result of an agreement reached at GFAR that was partly funded by GACP transition funds, stolen assets have been returned from Switzerland to Nigeria where their distribution to the poor through the country’s existing social safety net system has been monitored by NGOs[327] (see also beneficiary engagement section below). The monitoring of the return of stolen assets is foreseen in the IACCC MoU.[328] / Reporting and governance / G&I is a specific agenda item at the OCED and UNCAC project boards.[329] The IACCC G&I action plan was presented to its Governance Board in December 2019.[330] / G&I has been discussed at the GACP steering group and board on several occasions but does not appear to be a standing item. / There is no required G&I reporting. The quarterly flash report template used by the projects contains a section for reporting on “Key primary benefits / results delivered (e.g. gender, poverty, human rights, prosperity)”. Projects report G&I results here. Although not specifically directed, some projects (UNODC and IACCC for example) also provide updates on G&I activities in the section for key achievements in the last period. / There is no systematic monitoring of G&I action plans or a requirement to report against them on a regular basis. / Risks / Risk of unforeseen harm is not monitored in the programme and project risks register. / Beneficiary engagement: / Due to the nature of the programme, there is little engagement with end beneficiaries. An exception is GDMP. / GDMP’s approach promotes user-centred design in procurement and the project engages with government counterparts in its five focus countries to raise awareness of ways in which procurement policy and processes can be more inclusive—including through consultation of a wider and more diverse group of potential suppliers. In this way, the project is aiming to help government partners engage more equitably and inclusively with its citizens. In Indonesia, for example, it is supporting the national procurement authority to user-test revised procurement documentation on a diverse group of businesses identified through another PF programme, the Digital Access Programme’s Digital Hub. / There is, however, engagement with CSOs as proxies for the interests of end beneficiaries. Examples include; / OECD: One of the three mechanisms that the OECD project uses to achieve its objectives is increased collaboration of business, civil society and academia on issues of anti-corruption.[331] Although not well covered in the GACP logframe, the project’s results framework has an outcome that captures “Enhanced collaboration of multi-stakeholder anti-corruption and integrity policy communities”. The Global Forum’s unique selling point is that it is multi-stakeholder; by convening government ministers and officials, civil society and private sector, it fills a gap in the international architecture that does not usually bring all three groups together. / UNODC: Participation of CSOs in regional conferences is improving, but involvement of private sector associations and federations is limited to South East Asia. The rationale is to ensure that CSOs are fully engaged in the work UNODC does with governments to fast track the uptake of UNCAC commitments. CSOs are invited to the project’s regional meetings where they are assisted to better understand UNCAC, and what the entry points are for working with government. Convening government and CSOs builds an understanding of how to work together. These CSO roundtables began with the kick off of the regional meetings in February 2017. At subsequent roundtables the project created an e-network to strengthen the regional civil society network. CSOs can bid for grants to take forward work on one of the regional themes (including whistleblower protection and procurement). Pilot projects are currently being scoped and identified in the South America and Mexico region. / StAR: The GFAR Principles for Disposition and Transfer of Confiscated Stolen Assets in Corruption Cases set out standards to govern returned funds and “address approaches and mechanisms for enhancing coordination and cooperation, and for strengthening transparency and accountability of the processes involved”. The principles aim to address the concerns of affected countries in relation to infringement of sovereignty (where return agreements direct how the funds should be spent) and the concerns of countries returning the funds that they funds will not be re-corrupted. The early involvement of civil society is recommended—from the drawing up of the agreement to the monitoring of spend of returned funds—to ensure that funds will be used to benefit the populations of the affected states. The return of the Abacha II stolen funds to Nigeria from Switzerland that was agreed at GFAR is an example of the principles in action. On 4th December 2017 the governments of Nigeria and Switzerland and the World Bank signed a tripartite agreement setting out arrangements for the return of $321m of funds and the World Bank’s monitoring role. Civil society was involved in the drawing up of the agreement and in monitoring spend of returned funds. The GFAR Principles have informed future legal and policy work in this area, including an asset forfeiture bill in France and calls by civil society for a multilateral agreement on asset recovery and a set of Civil Society Principles for Accountable Asset Return.
Financial resources / (VFM strategy with G&I mainstreamed and clear equity indicators.)		VfM strategy / There is no VfM strategy, so there is no opportunity to mainstream G&I or have equity indicators. / Impact of COVID-19 pivot on resources available for G&I / OECD’s increasing digitalisation of webinars has brought mixed results in terms of participation and access. Panellists for the 2020 webinars were less diverse than those for in-person Fora in the preceding two years, but this is at least partly due to the speed with which these needed to be organised and technological challenges. Nevertheless, it is worth noting that it may be more challenging to bring together and present diverse experiences from OECD and non-OECD countries through online webinars—which will be an ongoing challenge in the COVID context. / UNODC: COVID-19 has had a significant impact on UNODC operations in all four regions. This has delayed planned regional workshops and country follow ups by thematic experts. / Impact of ODA reprioritisation / With the exception of the discontinued Behavioural Science project, budget cuts to projects as a result of ODA reprioritisation have not impacted G&I activities. / Behavioural Insights: With the decision not to continue with the Behavioural Science project, opportunities to achieve G&I results and to fill evidence gaps on G&I have been lost. FCDO expected that the full Behavioural Science project would have a strong G&I focus and, accordingly, offer more potential for G&I results than most GACP projects. Although specific G&I entry points were not identified, it was expected that fairer procurement processes which level the playing field would open up and diversify markets—including for small and medium enterprises and women-owned and -run businesses. It was envisaged that project monitoring and evaluation would include an impact assessment on inclusive procurement. / OECD: The budget cut as a result of the ODA reprioritisation has negatively impacted hub development. It has not affected delivery of the Forum and South East Asia Business Integrity work that have had the best results in engaging civil society to date. / IACCC: The budget cut resulting from the ODA reprioritisation has not so far impacted the implementation of G&I aspects of the work. / GDMP: While the GDMP core team remains multi-disciplinary, the staff redeployment as a result of ODA reprioritisation has made the management team less gender balanced. Spend on G&I has not been affected, however.
Delivery Partners / (Procurement of high-quality, relevant and sufficient G&I expertise.)		Headline findings / There is a great deal of variability across cross-government projects in terms of G&I expertise, with two (Open Ownership, HMT/FATF) out of the four ongoing projects currently without sufficient G&I expertise. / Multilaterals also vary in the extent to which they draw on institutional G&I expertise. Only one (UNODC) out of the three multilateral partners is accessing sufficient G&I expertise from internal resources. / Strategies that projects have used to boost G&I expertise include: recruitment, commissioning research and expert advice, arranging workshops, and better integrating in-house G&I expertise into project delivery. / Procurement by the programme shows some integration of G&I considerations. / Cross-government delivery partners / Both GDMP and IACCC have recruited gender leads with G&I expertise. / IACCC held a workshop for its team on gender and corruption.[332] / GDMP commissioned a study from Oxford Insights on GESI in ICT public procurement to inform its work.[333] / Open Ownership does not have G&I expertise on the team and has not drawn on wider FCDO G&I expertise. / The HMT AML team does not have G&I expertise and has not sought to fill that gap through recruitment or capacity building. / Multilateral delivery partners / UNODC: The partnership with GACP has resulted in UNODC better integrating G&I into its work on corruption, and a member of the UNODC gender unit is part of the implementing team for the GACP-funded project. Despite this move towards better integration, the gender and CSO teams remain siloed within UNODC to some extent. / OECD: Staff reported that G&I, as it relates specifically to AC, is not a core area of expertise for their teams, and did not appear to be drawing on relevant, wider OECD expertise. This was identified as an issue by the PT in 2019[334] but no action appears to have followed. / StAR: StAR does not draw on World Bank or UNODC gender and inclusion expertise. The team has expressed an interest in receiving more G&I guidance from the GACP PT, however.[335] / The Behavioural Science project integrated G&I considerations into its procurement documentation and presentation to potential suppliers: it referenced inequalities, including gender inequalities, in the ‘summary of context for work’, set out Gender Equality Act requirements, included G&I expertise as a criterion to be scored during the evaluation process, and was explicit about expectations of suppliers on G&I. It is not clear whether further G&I guidance was provided to bidders, and if so, how this informed the content of bids.
Results / (Good G&I results. / Active G&I/do no harm risk monitoring and mitigation.)		OECD: / GACP funding has enabled OECD to strongly emphasise diversity of voices at and expanding access to its Global Anti-Corruption and Integrity Forum. In recent years, OECD’s Global Anti-Corruption and Integrity Forum has had the most gender equitable participation on panels of all OECD conferences (with at least 50% women, often more). Over the past two years, the Forum has also developed a focus on youth engagement, including inviting young researchers to present their work. / UNODC / The GACP-funded project provides a good entry point for influencing the wider UNODC global project (GLOZ99). GACP has helped to influence an increased integration of gender into UNODC’s AC work more broadly as well as within the GACP-funded project since mid-2019. A GACP PT and FCO SDA visit to Vienna to discuss the PF G&I approach and explore entry points for the UNODC-led project was instrumental in this change.[336] The increased focus on gender within the GACP-funded project was notable during the Southern Africa regional workshop in Zambia that has been described by UNODC and others[337] as a watershed moment for the articulation of issues around gender and corruption within the project. / The level of representation and participation of civil society groups at regional meetings improved from East Africa (Arusha) to subsequent meetings in Southern Africa (Livingstone, Zambia) and South America (Cartagena, Columbia), due in part to GACP influence. / IACCC / Launch of the WATCH (Women Against Trans-national Corruption Hub): network for female prosecutors, investigators and other women involved in anti-corruption work in February 2020. The objective is to strengthen the global anti-corruption response by empowering and enabling the women who are working in the field of anti-corruption across the world[338] through a peer-to-peer network for learning, support on career progression, sharing good practice, and enhancing operational capability. A common resource library is planned alongside information about AC news and events. Membership will be regional, at least initially, starting with sub-Saharan Africa and links will be established with other networks, helping to reduce potential overlap. A survey of the membership is being conducted to determine priority focus areas. / GDMP: / GDMP has high ambitions in terms of results. It aims to achieve G&I results on both (demand and supply) sides of government contracting in its partner countries, aiming for: / Greater access to public contracts. / Greater access to government run services. / Greater/more balanced involvement in standards setting and enforcement (governance) which influences the whole public spending lifecycle (planning, procuring and implementing). / Building institutional capability and capacity to empower women and underrepresented groups in digital, data and technology, and commercial roles.[339] / GDMP is currently at an early stage in terms of results. It has engaged delivery partners in Mexico, Colombia, South Africa, Malaysia and Indonesia on G&I aspects of procurement policy and practice and, in places, is beginning to stimulate demand from government partners for more information and training on how to make procurement more inclusive. Whether these translate into outcome-level changes in the relevant government counterparts’ systems and processes is to be seen and is largely out of GDMP’s (more technically focused) sphere of control. / StAR / World Bank in Nigeria has monitored the return of $321m to Nigeria following agreement between Nigeria and Switzerland signedat the GACP-funded Global Forum on Asset Recovery.[340] The return has been in accordance with the GFAR principles,[341] ensuring that the victims of grand corruption receive the benefits of returned assets and that civil society is involved at all stages to make sure that happens. The return has been tracked through the MANTRA Project with formerly DFID Nigeria[342] funding and is monitored by the WB country office in Nigeria.[343]
Overall	Not clearly aligned with PF G&I policy minimum standards with areas for development OR unable to provide evidence
[315] GACP readiness report December 2019.
[316] Request to U4, 22 August 2019.
[317] “entry-points and opportunities to build the evidence base in relation to [G&I aspects of] asset recovery, financial investigators, greater transparency through both procurement systems and beneficial ownership registers” email 20 December 2020.
[318] Advice from the DFID helpdesks was no longer free to programmes following the ODA re-prioritisation in mid-2020.
[319] Interview with PT.
[320] Gender Equality and Social Inclusion in ICT Procurement: Discovery Report, Oxford Insights April 2020.
[321] Colombia, Mexico, Indonesia, Malaysia, South Africa.
[322] Interview UNODC, GACP PT, SDA.
[323] Interview IACCC and WATCH documentation.
[324] FCDO / OECD Memorandum of Understanding on Project Funding.
[325] Interview with SDA.
[326] Save OECD reporting in Year 2 under Output 4.1.
[327] https://mantra-acorn.com/
[328] National Crime Agency and FCO MoU, April 2019.
[329] Annual Review 2019 (VFM equity assessment).
[330] IACCC G&I report.
[331] GACP business case.
[332] March 2020. Workshop led by Liz David Barret, Director, Centre for the Study of Corruption, University of Sussex.
[333] https://www.oxfordinsights.com/gender-equality-and-social-inclusion-in-public-procurement Note that country case study annexes are not published.
[334] GACP G&I work and planned actions (undated).
[335] StAR interviews.
[336] Interviews with UNODC, GACP PT, FCO SDA.
[337] Interviews with UNODC, PT and SDA.
[338] WATCH core script FINAL.
[339] Written response from GDMP to evaluation questions.
[340] GFAR 2017.
[341] https://star.worldbank.org/sites/star/files/the-gfar-principles.pdf#:~:text=GFAR%20Principles%20for%20Disposition%20and%20Transfer%20of%20Confiscated,receiving%20countries.%20Such%20partnership%20promotes%20trust%20and%20confidence.
[342] https://mantra-acorn.com/
[343] https://www.unodc.org/documents/corruption/AddisEGM2019/Presentations/3._WB_Indira_Presentation_May_8_2019.pdf

Key
Red	Fails to meet PF G&I policy minimum standards
Amber	Not clearly aligned with PF G&I policy minimum standards with areas for development OR unable to provide evidence
Green	Meets PF G&I policy minimum standards

Individual project G&I action plan updates
G&I action planning – status by project
Project	Action plan	Planned actions (bullet list)
HMT/FATF	Y	N
UNODC UNCAC	N	Y
StAR	N	N
IACCC	Y	Y
Open Ownership	N	Y
OECD	N	Y
GDMP	Y	N
Behavioural Insights	N	Y

HMT/FATF
There has been no or little progress on G&I or use of the G&I action plan due to HMT’s lack of time and resources. Integrating G&I into the project has not been a priority for the delivery partner.[344]
[344] Interview with HMT.
Planned action	Progress
Advocating greater focus on gender and inclusion in FATF reports and publications/ESAAMLG work / G&I champion to raise need for focus on G&I with FATF contact points in context of funded activity. / G&I champion to use role of donor and role of UK delegate to (i) FATF and (ii) ESAAMLG to lobby more widely on G&I to build awareness, buy-in and understanding of need for G&I policy.	HMT’s implementing partners (FATF/ESAAMLG) have not been encouraged to report against G&I progress in their reports. / A requirement to prioritise/focus on G&I is not included in implementing partner MoUs, although they do focus on other cross-cutting themes such as 1) safeguarding, 2) management of cost drivers and value for money, 3) ODA eligibility.
Caribbean Financial Action Task Force: Advocating greater focus on G&I in region / Explore funding regional analysis of de-risking on financial inclusion, exploring whether impact is gender-biased, with recommendations for addressing and follow-up work by the task force and members. / Explore delivery of a financial inclusion workshop.	CTAF was not sampled by the evaluation.
At overall project level / Advocate greater focus and discussion of specific impact on women and protected groups in FATF/FSRB reports. / Fund training with substantial percentage of women attendees, and from countries facing significant G&I challenges. / Advocate horizontal analysis of money laundering and its predicates on women and protected groups. / Where external expertise is hired, require gender-balanced interviewee/final bidding round. / Require follow-up actions by implementing partners responding to G&I impacts of money laundering and its predicates identified in reports, e.g. raising awareness among membership through workshops, plenary discussions.	FATF does not have any specific policy on ensuring a gender balance in terms of training participants or MER assessors, but women are selected on courses and subsequently contracted as assessors. / Discussion of impact on women and disadvantaged groups is not evidenced in reports or training. For example, FATF produced guidelines on financial inclusion (with World Bank support) in 2013 and revised them in 2017. These were produced with a view to mitigating the unintended consequences of tighter banking controls on consumers, ensuring access financial services is not reduced, particularly for the marginalised. However: / ESAAMLG assessors interviewed had not noted this as a priority for assessment and did not provide an answer when asked if financial inclusion was included as a module in FATF training of trainers courses. / There is no mention of financial inclusion in the recently published MERs for Malawi and Zambia. / Civil society is a focus of MERs but only in the context of mitigating risks associated with terrorist financing through non-profit organisation. Insufficient attention is given to the unintended consequences of introducing tighter financing rules.
Monitoring and evaluation / Gender and inclusion indicators to be built into all results frameworks and logframes. / Project reports and annual reviews to: / note number of FATF reports where corruption, human trafficking and drug trafficking are recognised as primary threats for money laundering and mitigating actions taken by countries. / cover follow-up actions by implementing partners responding to G&I impacts of money laundering and its predicates, e.g. raising awareness among membership through workshops, plenary discussion.	G&I is not built into the HMT/FATF project monitoring and evaluation. / No disaggregated data is collected. / FATF noted that women attended their training events but they did not provide participant lists or disaggregate according to gender of participants. / ESAAMLG noted that they recruit female assessors, but this is not part of any affirmative action or other gender policy. Disaggregated data on gender of assessors is not available.
Project procurement / 1. Ensure G&I is integrated into terms of reference and project descriptions, where feasible, following the FCDO PF guidance. / 2. Ensure G&I components are properly weighted and scored as part of the bid assessment (see FCDO PF guidance). This should be clearly signalled in the terms of reference. / 3. Build G&I into early market engagement—make sure it is included in slides, info and presentations.	No procurement documentation was seen by evaluators.

UNODC
UNODC’s integration of gender, in particular into project delivery, has significantly increased due to GACP. It is beginning to make progress against its action plan.
Planned action	Progress
Build on the outputs from the G&I workshop held in Bangkok in September 2018 at the request of the PT, covering mainstreaming gender consideration into anti-corruption programming.	UNODC gender team reports that interest within UNODC on gender and corruption is at “an all-time high”.[345] It partly attributes this interest to GACP’s focus on G&I. / This year should have identified countries in the regions to pilot G&I activities. The COVID-19 pandemic has delayed this but recent reports to PT[346] indicate that work has begun on identifying pilots in some regions (South Africa and South America/Mexico).
Incorporate G&I into civil society engagement.	Women-focused/women-run CSOs are encouraged to join the regional platforms and, where corruption is not a core expertise, capacity building takes place.
Encourage women to train as financial investigators.	Not evidenced. However, UNODC’s work on financial investigation is gender neutral in its documentation and commentary. The sample scenarios used in workshops attempt to strike an even-handed tone; both males and females can be depicted equally as higher/lower ranking, effective/ineffective, acting with/without integrity, etc.
Consider G&I elements of whistleblowing protection.	UNODC’s approach to whistleblower protection is gender blind, to guard anonymity.
Ensure equal representation of women at all project events.	No information.
Ensure project results are disaggregated by G&I where possible.	Participant feedback forms are designed to capture disaggregated data.
[345] Interview with UNODC.
[346] Logframe update.

StAR
The StAR G&I action plan was developed by the PT but not shared. The GACP PT raises G&I frequently with the StAR team. There is also no soft earmarking of GACP’s contribution to StAR in relation to achieving a G&I focus or disaggregated data collection although StAR report participant information dissagregated by gender is collected where possible at workshops and trainings they organise.
IACCC
IACCC has made good progress on its G&I action plan, has set goals and is actively tracking progress despite disruptions due to COVID-19 and a reduction in budget to the project overall.
Planned action	Progress
Review results framework and consider a milestone for working with female investigators.	See disaggregated data capture below.
Ensure data capture for technical assistance project includes gender data	IACCC reviewed its monitoring and evaluation data collection to disaggregate data on suspects by sex, age and geographical location. It is recording; / the number of women in delegations (engagement tracker spreadsheet) / the number of women attending IACCC training (investigations & intelligence teams – Gender ratio spreadsheet) / the number of female investigators in partner agencies’ teams (investigations & intelligence teams – Gender ratio spreadsheet).
Create G&I approach paper/statement for the project.	Not yet developed.
Ensure G&I considerations/awareness are mandatory when planning capacity building or training. / All training provided by IACCC will raise awareness about different impacts of corruption upon men/women and disadvantaged groups. Transparency International I will supply slides for use in all IACCC-funded/delivered training courses.	IACCC actively encourages women’s participation. The IACCC requests in advance that women and other minority groups are equally represented when candidates are chosen to participate in training. The list of participants is always reviewed by trainers. / All trainers are familiar with their respective agency’s G&I and anti-bullying policies. / G&I and human resources awareness is promoted on each IACCC training course.
Recruitment of a G&I expert planned for May 2019.	Recruitment completed May 2019.
G&I human resources policy/plan being drafted.	Not yet developed.
Consider G&I budget if network of external stakeholder champions could be encouraged/supported.	WATCH network launched February 2020.
All staff to receive G&I awareness training.	Liz David Barret, Professor of Governance and Integrity at the University of Sussex, delivered a workshop on gender and corruption to the IACCC team. Follow-up with team to provide G&I literature and other relevant documents. / Planned Transparency International training has not yet taken place.
Capture intended purpose of looted funds i.e. if diverted from Aids fund this could adversely disadvantage women and poor.	Monitoring is currently not taking place.
All delivery partners will be provided with PF G&I policy guidance to capture evidence of compliance by delivery partners.	IACCC plans to provide all external trainers with a copy of the IACCC G&I policy once drafted.

Open Ownership
DFID participated in the brainstorming session, organised by the GACP PT and SDA in 2019, when plans for developing G&I action plans were first introduced. A list of planned actions was developed at some point but, as neither formerly DFID staff nor the team interviewed for this evaluation and the Readiness Review last year have knowledge of it, progress against it is not reviewed here.

OECD
Most OECD staff were either not familiar with the project gender action plan or had seen it without necessarily keeping its commitments in mind in their day-to-day work. G&I is integrated in the project’s work in two main ways: an emphasis on diversity of participation and, to a more limited extent, consideration of G&I-related issues in the development of knowledge products.
Planned action	Progress
Ensure equal representation of women at all project events.	OECD staff stressed that the organisation requires gender parity in attendance and on panels throughout all events. However, it is not clear whether or how this is monitored beyond the Global Anti-corruption and Integrity Forum. / As regards demographics, in recent years the Forum has had the most gender equitable participation on panels of all OECD conferences (with at least 50% women, often more). Over the past two years, the Forum has also developed a focus on youth engagement, including inviting young researchers to present their work.
Ensure G&I topics are included for discussing, debate and policy development within the Anti-Corruption and Integrity Forum.	A 2020 session is planned with colleagues in development centre on corruption and developing countries. / There is a willingness to bring in knowledge partners where OECD has a gap: ‘OECD don’t do much work on these aspects. Hence trying to bring in others’ research on women, vulnerable groups.’ / In 2019, there was a specific session on corruption and gender, including sextortion as a corruption crime. / Indicators on the impact of corruption on women and vulnerable groups will be included in a new project on developing public integrity indicators, as communicated at the 2019 Forum session on measurement of corruption. This will be a priority for G20 in 2021 with OECD support (outside of GACP), including through surveys. / Corruption, gender and sports were on the agenda for 2020 forum (which was ultimately cancelled).
Develop, publish and share leading practice G&I content on the Hub.	Relevant word searches (e.g. for ‘gender’, ‘women’, ‘race’ and ‘age’) on the Hub turn up relatively little. The most interesting exception is a 2020 publication on ‘Foreign Bribery and the Role of Intermediaries, Managers and Gender’[347] which explores the merits of applying a gender lens to the collection of data relating to cases of foreign bribery.
Address gender and diversity aspects of the fight against corruption and the promotion of business integrity in South East Asia. / Additionally, the project MoU states that: / In this Output area [output 4], the OECD aims to leverage its existing OECD engagement with Southeast Asian countries, in order to increase private sector engagement on anti-corruption and integrity issues. The OECD views this engagement, with a focus on gender and inclusiveness and the gender impacts of corruption, as important to its relationship with the region and vital to sustainable and inclusive growth.	G&I has been considered in research carried out under output 4. For example, the recent survey in business integrity across South East Asia included questions on gender aspects of business integrity (e.g. do reporting frameworks take into account gender sensitivities, were behavioural insights frameworks developed with gender considerations in mind?). Efforts were also made to ensure that the sample included a reasonable number of responses from small and medium enterprises. / However, G&I does not appear to be the focus of output 4 activities, as suggested by the project MoU.
Ensure project results are disaggregated by G&I where possible.	Reporting is not gender-disaggregated across workstreams. However, consideration is given to diversity of participation in reporting against output 1.
[347] https://www.oecd.org/corruption/Foreign-bribery-and-the-role-of-intermediaries-managers-and-gender.pdf

GDMP
GDMP’s user-centred approach to ICT products and services makes it well placed to promote and champion G&I. Guided by country-specific G&I assessments, it is adapting an approach to procurement and service delivery used in the UK which is a tried and tested approach to improve the accessibility of digital services and government contracts. GDMP developed a detailed and ambitious G&I action plan, with clear responsibilities and timelines, dated April 2019.
Planned action	Progress
Appoint an interim G&I champion until a permanent civil servant is appointed to the role of Capability Lead.	GDMP appointed two successive G&I champions (the first one was redeployed because of ODA reprioritisation; his successor became champion in October 2020).
Ensure clear and consistent messaging on the importance of G&I from the GDMP Director.	Given the level of G&I activity over the past year, strong leadership on G&I seems to be present.
Arrange workshops and training on G&I for GDMP programme team members.	It is not clear how much training has taken place, although the wider team was involved in the development of the Oxford Insights report.
Include G&I initiatives as an independent section of the programme budget.	A research and tools study that specifically focused on G&I has been budgeted for and commissioned: / In 2020, GDMPcommissioned a study on GESI in ICT public procurement (the Oxford Insights report),[348] with country cases in Indonesia, Malaysia, Mexico, Colombia and South Africa assessing country-specific barriers and opportunities for greater inclusion. This study produced a set of general and specific recommendations (some addressed to the government and its procurement agencies) to mainstream G&I into ICT procurement policies, standards and practices. The report provides useful tools to help GDMPpromote G&I when engaging with their government counterparts, and/or developing their knowledge products. / The latest knowledge product also has a key focus on G&I: / The Digital Buying Guide[349] makes useful reference to G&I at various stages of ICT procurement, from recruiting the procurement team and writing requirements to defining broader social outcomes through to evaluating suppliers and simplifying contracts. Illustrative case studies are included.
Set G&I targets that can be monitored and measured.	Until recently, GDMP used an adaptation of the PF G&I framework to monitor progress. It now has a tailored monitoring, evaluation and learning framework developed as part of the Oxford Insights report. This allows GDMP to assess its progress on G&I in procurement in each of the partner countries. GDMP plans to establish baselines in each partner country over the next three months and report against the framework every quarter. / The framework will also be used to monitor risks. / GDMP collects gender disaggregated data on event and workshop participants in partner countries.
Ensure G&I initiatives are mainstreamed through all stages of the programme delivery (discovery, alpha/beta).	G&I is integrated into the project’s ToC through user-centred design, supplier inclusion, inclusive procurement processes and more opportunities for marginalised groups. / The first series of discovery reports produced by GDMP(involving four firms—Rainmaker, Caution your blast, Spend network, DXW digital) for each priority country were gender blind. GDMPhas since given more attention to GESI issues. In Malaysia, the second round of diagnosis, which focuses on procurement in 3 provinces and was completed in mid-2020, did include GESI considerations. In practice, however, broadening the consultation process to companies led by marginalised or disadvantaged groups has proved difficult / GDMP have translated the Digital Buying Guide and the UK digital and technology standards into Bahasa Indonesia and Latin American Spanish languages.[350] These mandate accessibility standards in procurement of UK technology and delivery of services and are being used to help government counterparts who are considering creating their own standards and designing assurance processes. / In Indonesia, plans are being finalised on selecting end users to pilot the new simplified procurement document on ICT. A key challenge to doing so is the narrow range of established government suppliers in this sector. At the time of writing this report, the UK was exploring options to widen the net (using the UK-Indonesia TechHub which is part of the PF’s Digital Access Programme)[351] to bring in a diverse range of participants, e.g. small and medium enterprises, people with accessibility needs, a range of genders, and digital literacy.
[348] https://www.oxfordinsights.com/gender-equality-and-social-inclusion-in-public-procurement Note that country case study annexes are not published.
[349] https://www.digitalbuyingguide.org/en/
[350] https://alphagov.github.io/gdmp-translated-standards/
[351] Interview with FDCO and GDMP.

Behavioural Science
The Behavioural Insights project had a more developed list of planned G&I actions than some of GACP’s other projects but, as it did not progress past the procurement stage, only actions related to that stage are reported on here.
Planned action	Progress
G&I to be considered from the beginning of testing the market so it is included in ideas and bids by companies—the bidders will also be provided with G&I guidance.	Call for bids references: / Inequalities, including gender inequalities, in the ‘summary of context for work’ / Sets out Gender Equality Act requirements / Includes expertise in G&I in evaluation process and scoring. / Gender Equality Act requirements are similarly referenced in the presentation for potential suppliers, i.e. that projects must: / consider gender issues in their interventions​ / not exacerbate gender inequality​ / report annually on performance​ / Identify poor and excluded groups / Aspire to be ambitious by promoting empowerment and transformation. / It is not clear whether further G&I guidance was provided to bidders, and, if so, how this informed the content of bids.
Due diligence on each of the bidding companies’ experience of G&I and evaluation of this as part of the formal assessment.	Not able to verify (bid evaluation documents not shared).

GACP – Value for Money Scorecard, November 2020
Scorecard element	Quality of evidence	Direction of travel	Comments
Relevance and robustness of value for money (VfM) measures in place	Adequate	Adequate	Overall / The programme has a logframe with SMART indicators consolidating results from the seven projects, and the ToC was revised in May 2020 to align with the logframe. The programme does not have a MREL plan detailing purposes of MREL, roles and responsibilities, implementation, quality assurance, etc; however, the reporting systems have been operational and the logframe has been updated at least once a year. Delivery partners are monitored through flash reports provided monthly or quarterly, depending on the implementer. The relationships with the cross-HMG partners and multilateral institutions are governed by MoUs while the non-profit organisation (Open Ownership) has an accountable grant agreement with FCDO. / The programme has not yet developed VfM indicators to track costs of inputs, activities, outputs or outcomes. Interviews with implementers suggest that delivery partners’ understanding of VfM is skewed towards economy (e.g. on cost savings, budget forecasts reporting), which is only one element of the VfM framework. / Economy The PT tracks the costs of inputs and activities of delivery partners on a monthly basis for cross-HMG delivery partners and quarterly for multilaterals. The level of financial detail varies significantly across projects (from one to seven lines). The payment structures also vary across projects, with some projects receiving annual cash advance payments based on the calendar year and others based on the financial year. The PT scrutinises costs regularly. So far, activity costing has remained limited and benchmarking of unit costs across delivery partners has not been introduced. Efficiency / Delivery partners have work plans in place with deliverables defined quarterly. The PT tracks and scrutinises implementation progress through monthly flash reports and quarterly reports form the delivery partners. The results framework/logframe is updated annually. The PT has found the quality of reporting to vary significantly across delivery partners and is considering aligning financial reporting with activities and delivery. / Processes to track the quality of outputs also vary across delivery partners and activities, with OECD, StAR and UNODC using built-in mechanism and metrics (such as attendance records and feedback forms for workshops, events and reports). The PT also receives feedback from FCDO posts about quality of support delivered in-country. / Effectiveness / Following the review of the ToC in 2020, the delivery partners’ milestones are better aligned to the ToC. Assessing the impact of GACP is challenging due to a) long impact chains between GACP investments in institutional development, b) attribution challenges related to multiple sources of funding to the multilateral organisations, and c) the hidden nature of corruption which means changes are not easy to observe. The team has developed an approach to assess progress at the impact level in each country using communities of AC experts. This is because available measures of corruption, e.g. the CPI, can be tracked but it will not be possible to attribute changes in these measures to the programme’s activities. Effectiveness metrics (e.g. updated Return on Investment) are not available. / Equity / The programme has reviewed its logframe and disaggregated output, outcome and impact indicators by gender where appropriate, e.g. gender splits for trainees. Action plans or planned actions in a bullet list are available for all projects except StAR. / Lessons learned / The programme is not tracking the unit cost of activities/inputs or outputs for benchmarking with other programmes, overtime comparison, or standalone analysis. VfM indicators should be developed to a) assist in decision making and optimise VfM and b) support the programme VfM offer and demonstrate VfM externally. See note developed by JFU. / The programme is looking to update its quarterly reporting templates. The mechanisms to monitor the quality of outputs should also be reviewed and used in a more systematic manner (e.g. evidence of the quality of outputs could be stored centrally). / The seven delivery partners have different views about what constitutes value for money and have different standards of reporting. The programme should provide the delivery partners guidance on definitions and tools and ask for greater transparency. It is expected that multilaterals in particular will have set standards in place, otherwise they should be supported with developing these. / Definitions of some logframe indicators could be tightened to ensure shared understanding of what the indicators mean, particularly at outcome level where achievements are harder to define properly in advance, e.g. with GDMP.
Approach to procurement and cost containment	Adequate	Adequate	Cost containment (no need to review Procurement again) / GACP chose an option combining UK government, multilaterals and one non-profit organisation as implementers of the programme (see business case). This option reflects strengths in terms of multilateral credibility, global reach of FCDO and multilaterals and multilateral/other government department experience on anti-corruption reforms. In parallel, the programme also understands there are weaknesses with this approach: cost (multilateral management fees between 5% and 17%), SBs (multilaterals won’t focus on UK interests), and capacity. / The delivery partners submit spend forecasts on a monthly basis for cross-HMG partners and quarterly for multilaterals. These are scrutinised for accuracy against prior months’ data and milestones/activity delivery, and reported to PDFU/JFU. The level of justification for variances is high. / However, VfM practices vary significantly across delivery partners, which makes it more challenging for the PT to understand and manage different decisions. For example, it was found that UNODC relies extensively on international consultants to carry out the work, which could be more expensive than other approaches, and also pays per-diems to participants in their events. / During the current financial year, COVID-19 impacted spending in Q1 and travel was put on hold in Q2 which meant that a lot of in-person activities were delivered virtually. For most projects, remote working during COVID has resulted in some cost savings from missed travels without a loss of effectiveness of the activities. The programme was also impacted by significant budget cuts across projects as part of the ODA reprioritisation, and budget allocations have been revised. This allowed the PT to further scrutinise the funding and better understand what the funding pays for, but visibility of programme spend could still improve to see how this achieves value for money. Currently the programme has been able to reforecast and is tracking spend against new allocations. / Prior to COVID, in March 2020 (2019-20) the programme was on track to achieve full spend across all projects, except for an underspend of £400k with GDMP. / Lessons learned / There is a general assumption that the day-to-day finances of the multilaterals are managed to multilaterals’ standards and subject to internal VfM check and balances. / The PT is considering introducing benchmarking for unit costs of activities or outputs across the delivery partners. Given the wide spread of activities and countries where the projects operate, this may not result in like-for-like comparisons, but should be interesting to compare projects and query costs. / In the past year, work plans have been revised significantly to accommodate challenges with remote working (due to COVID-19). All projects identified areas to prioritise and have been able to reprogram. Some have found that remote working can be an efficient mode of delivery. Yet many GACP projects still rely on a country presence for their success.
Efficient use of resources and inputs by Prosperity Fund (PF) interventions	Adequate	Adequate	At central level, the PT has tracked delivery through monthly and quarterly reports. Funding to delivery partners is agreed annually, against a set of milestones and based on performance over the previous year. Also, all the projects have been reporting on the results framework/logframe, which provides a good picture of what the projects are delivering. The PT, however, has experienced staff turnover and redeployment and capacity constraints, particularly with MREL. Where the programme has accessed specialist support it has been very useful, for example MREL support from JFU or EL support with the ToC. / The choice of partners, co-funding and selected design features have all contributed to using GACP resources efficiently: / The multilateral delivery partners have leveraged their own networks and resources to back up the activities of the programme. In addition, IACCC has also attracted investment from other donors (UK’s £1.4m investment has leveraged a further £1.3m of co-financing from partner law enforcement institutions in USA, Canada, Australia, NZ, and Singapore). / OECD, StAR and UNODC are trusted partners in the anti-corruption sector, bring excellent expertise and are likely to have positive spill-over effects. The multilateral convening power is working as a platform to showcase GACP’s work. / The IACCC model provides an effective and streamlined method of pooling the intelligence from multiple jurisdictions, helping to avoid duplicative and parallel efforts and reducing the time taken by affected states to progress grand corruption investigations. In addition, IACCC has established effective working relationships with other HMG-funded AC programmes, such as I-ACT and CSSF. This has resulted in efficiency in the deployment of technical assistance in-country (particularly IACCC). / Open Ownership takes a graded approach to technical assistance, providing desk-based, medium- and/or high-intensity assistance which allows it to deploy its relatively limited resources nimbly and efficiently. / Elsewhere, UNODC has been conscious of maximising efficiency of activities delivered in country; for example, it has convened dual thematic workshops (rather than single) in Uganda and Tanzania. / By funding multilateral institutions, non-profits and cross-HMG partners, GACP also seeks to strengthen their performance and notably improve their efficiency. / UNODC regional platforms are expected to fast track the implementation of UNCAC in partner countries. / GACP’s additional resources are helping FATF and FSRBs to improve their organisational structures and learning capabilities. / OECD is making some progress in linking up its various AC workstreams under the 2018 Strategic Approach to Combatting Corruption and Promoting Integrity, which was funded by GACP. / Some projects have been slow to deliver, however, which has affected their efficiency: / It has taken time for UNODC to set up regional platforms and start activities; for example, in East Africa the platform was launched in 2017 but activities started a year later. The 2019 UNODC Multilateral Organisation Performance Assessment Network reports some “inefficiencies in co-ordination, procurement, and budget allocation, which affect timeliness and efficiency”. It also mentions, however, UNODC’s ongoing efforts to strengthen its operational performance, setting UNODC on the right path. / GDMP’s staged approach—while suitable to single product development—has been very resource intensive and taken too much time to supportGDMP’s country engagement. GDMP’s scoping and discovery phases were much more time consuming than anticipated, which may be explained by the too-broad scope of the discovery phase and by the decision to use four different firms to cover aspects of the procurement landscape in selected countries. These lengthy processes impact negatively on VfM given the shorter time left to implement. / Lessons learned: / The programme has benefited from the convening power of the multilaterals, while seeking to strengthen their performance
Validation of PF ToC causal pathways (for primary purpose and secondary benefits)	Adequate	Adequate	The programme revised its ToC in May 2020 to reflect its project portfolio of activities, align with the newly developed logframe, and include secondary benefits. The ToC has four key themes/intermediary outcomes. This evaluation found that there is a strong fit of programming for Themes 1 and 3, but less so for Themes 2 and 4: / UNODC and FATF align well with Theme 1 (i.e. improving anti-corruption laws, regulations and policies) / IACCC and StAR promote international cooperation and align with Theme 3 / GDMPis unlikely to support digital transformation of government procurement services in focus countries (Theme 2) / The lack of traction for Behavioural Insights projects leaves important gaps under Theme 4 (awareness raising). / The ToC themes and impact pathways suggest some potentially high rewards from GACP investments against also high-risk factors, such as the required political commitment to pursue anti-corruption in partner countries (ToC assumptions). For example, by investing in Behavioural Insights, GACP supports actionable research on policies that improve VfM of service delivery by changing corruption behaviours. Some early results, for example IACCC’s contribution to investigate a corruption case and return a very large asset to a country government, have started to emerge. The causal pathways are long and the impacts have not been tested before, therefore, it is critical that the programme continues to review and test the ToC assumptions. / In addition, this evaluation found that GACP aligns closely with UK government priorities in anti-corruption, particularly with the cross-government strategy. The UK’s reputation as a global leader in anti-corruption is growing through GACP, and coordination with the Home Office JACU has been built into the programme to maximise these benefits. / This evaluation also evidenced that GACP’s activities have been geographically dispersed, with the result that opportunities for synergies of activities in priority countries are reduced and effectiveness might suffer in the longer term. / Lessons learned / The previous VfM scorecard suggested that project-level ToCs could be introduced, as the seven projects are sufficiently different to identify and follow different causal pathways. These ToCs have not been developed but could still be useful in the next year.
Sustainability of programme activities	Little	Little	The programme has not yet developed a comprehensive sustainability strategy, and programme documents (e.g. Strategic Board meeting minutes) do not suggest that sustainability has been a priority so far. / The PT recognises that several aspects of the programme promote sustainability, but these largely remain untested: / The programme plugs gaps in the global anti-corruption architecture and contributes to global institutional reform efforts, which (while implicit), should last beyond the programme’s lifetime. IACCC and Open Ownership, in particular, are innovative organisations in the early years of delivery and are set to grow more in the future and expand their reach. / The programme also invests in international public goods, such as open knowledge, although sustainability is not necessarily guaranteed. / Both Open Ownership and OECD, however, have explained the cost of maintaining and expanding the global register and the ACI hub respectively. For example, Open Ownership is currently predicting that the level of effort required to consolidate beneficiary owner data could grow exponentially as more and more countries and sectors generate open data; as a non-profit organisation, Open Ownership does not have the right business model to manage the global register. / Looking at individual projects, the business case argued that the projects would become self-sustaining by building capacity ‘locally’. However, to date there is insufficient evidence that this growth is happening. / GDMP’s agile approach, focusing on building ownership and learning by doing, if successful, has good potential for sustainability. Stakeholders have raised concerns, however, that the delivery of technical assistance, notably via the UNODC regional platforms, may not lead to sustained results. / Lessons learned / The previous VfM scorecard noted the need to develop and document the programme’s sustainability strategy as a recommendation. While the programme has been impacted significantly by COVID-19 and ODA reprioritisation in the past year, sustainability should gradually be re-introduced into the programme agenda. / As noted by the previous scorecard, the strategy should identify what the options are to support sustainability for each of the seven projects and which should be pursued, as well as what costs are likely to be involved in promoting sustainability and potential sources to fund this (HMG, partner governments, multilaterals, etc.). Whether actions could cut across multiple or all projects (to ensure these are joined up) should also be considered.
Ability of leadership, management and oversight structures to support Programme delivery	Adequate	Adequate	GACP is a complex programme with seven different projects and implementers that come with set ways of working. However, the programme has made good progress exploiting some synergies between the projects at a global, regional, and country level, for example, through a consolidated ToC and results framework; opportunities to showcase each other’s work during events (e.g. UNODC with IACCC; OECD-GACP launch event) and open doors for others (GDMPwith Open Ownership, UNODC with IACCC); and some joint thinking in procurement. / The relationships with multilaterals are governed by MoUs while Open Ownership has an accountable grant agreement with FCDO. The level of oversight has varied from one project to another, reflecting the different partners’ ways of working and geographical/activity spread. / The business case sets out clear governance arrangements: role of SRO, Strategic Board, Steering Group; relationships between and responsibilities of FCDO and other government organisations. The Strategic Board and Steering Group have Terms of Reference in place and meeting minutes are documented. The sequencing of meetings has allowed good preparation, joint working, and adequate knowledge and information flows in advance of the Strategic Board. JACU staff regularly attend both the Steering Group and Strategic Board, which has supported good alignment and coordination with the broader UK anti-corruption strategy. However, a review of Strategic Board and Steering Group meeting minutes has shown that most of the time is spent discussing projects updates, which is needed to cover all the projects, so lesser time is devoted to programme performance and issues and solutions common to the seven projects. In addition, FCDO posts have not been involved in decisions made centrally and have not participated in the Strategic Board meeting as envisaged by the business case. As a result, cross-government learning has been limited. While some synergies have been realised (see above), the projects are not able to support truly joint programming. / All partners except GDMPhave well-established anti-corruption mandates which is helpful for setting expectations and overseeing delivery. / Lessons learned / The role of posts to provide context knowledge and open doors in-country for the technical support has been identified as a key enabler of programme success. The programme has strong relationships with posts, but could involve them more systematically (e.g. in decision making). / Getting systems in place (Strategic Board terms of reference, risk register, reporting requirements, result framework, responding to JFU requirements, approaches to G&I, SB and VfM) has been onerous and time consuming; however, these are now in place and working well.
Strategies and measures adopted to enhance delivery and mitigate risk	Good	Good	To identify and mitigate risks, the programme employs risk registers at the Strategic Programme Board level, Programme Management Committee level, and delivery partner level. Risks are identified and escalated through risk registers detailing risk owners, risk category and type, RAYG (red, amber, yellow, green) ratings, and mitigating actions. There is evidence that the top risks are discussed at Strategic Board meetings. / Because the programme is centrally managed and geographically diverse, there is a gap when dealing with the risks associated with individual projects in specific country contexts. The risks of causing unintended effects (including in relation to vulnerable populations) are also missing. / At programme level, in the past two years GACP has tried to act on all Annual Review recommendations and taken important decisions that demonstrate adaptive management (stopped funding the Extractive Transparency Industry Initiative, deferred the Behavioural Science project, launched the new Transforming Procurement Systems project in response to COVID-19). The programme’s response to COVID-19 has also been swift, with activities being reprogrammed to allow for remote interactions with in-country partners, where possible / Lessons learned / The PT uses a strategic and prioritised approach to risk management to inform centrally made decisions. / Because GACP is broad and complex in design, this strategy does not—and cannot—cover all aspects to risks associated with individual projects and the various country contexts in which they operate. This in turn reduces the PT’s ability to oversee delivery.
Equity of programme design and approach	Adequate	Adequate	While the business case gave minimal consideration to equity, the programme has since developed an approach and vision for G&I in GACP with the support of the PF SDA. The PT shared this vision and approach with the delivery partners and supported them in developing action plans or planned action bullet lists that they could take forward. However, in practice, integration of G&I has been patchy: GDMP, IACCC and UNODC have moved forward into implementation while HMT, Open Ownership, and OECD have not prioritised G&I. / In terms of results measurement, the programme has disaggregated logframe indicators on gender and other dimensions; however, there have not been results reported against them to date. In addition, the indicators currently focus on the volume of activities targeted to G&I rather than the quality or depth of change these activities make. Despite this, some relevant results have started to emerge. / Finally, in terms of capacity and expertise, this evaluation found that PF SDA support has been used effectively—however capacity to take forward actions has been limited and inconsistent across the projects. All projects have appointed G&I champions within their teams. The PT has continued to raise G&I with the delivery partners to ensure G&I is mainstreamed into their activities. / Lessons learned / An earlier, clear communication of expectations on G&I from JFU would have been helpful; but for several transition projects, a degree of retrofitting was inevitable. / Some delivery partners perceive their projects to lack relevance to G&I. This is partly due to lack of evidence on G&I and corruption in the areas GACP works across. Additional investments in studies and analyses, such as the one commissioned by GDMPin 2020, could help improve delivery partners’ understanding of their G&I relevance.
Overall VfM assessment	Adequate