PSD RB/December 2021/Paper 2

Public Service Delivery Review Board
minutes of meeting

Meeting date: 14 September 2021, 15:00 - 17:00, hosted remotely via Google Meet.
Attended: Sue Bateman (CDDO), Heather Neate (CDDO), Patrick Kiernan (CDDO), Ebru Yilmaz (CDDO), Kathleen Caper (CDDO, observer), Albert King (Scottish Government), Jack Ramsden (BEIS), Mark Brewin (HMRC), Glyn Jones (Welsh Government), Ross Young (UKSA), Stephen Mak (MHCLG), Tom Griffiths (MHCLG), Edgar Whitley (PCAG), Debra Heaton (ICO), Andy Gregory (Home Office), Louise Benett (PCAG), Helen Walker (DWP), Hugh Tohill (Northern Ireland Government)
Speakers: Patrick Kiernan (CDDO), Tom Griffiths (MHCLG)
Apologies: Tim Adams (LGA), Harry Lee (DCMS), Emma Wharram (DfE), Vicky Chico (NDG), Jennifer Boon (NHSX)

1	Welcome and introduction from the Chair
1.1	The Chair welcomed Members to the meeting, introduced new members Vicky Chico (NDG), and Jennifer Boon (NHSX) to the Review Board, and Ebru Yilmaz to the secretariat.
2	Conflicts of interest, minutes, and actions brought forward from 11 May
2.1	Louise Bennett wished to mention her membership of PCAG. Minutes from the last meeting on 11 May 2021 were approved. / Action point 37 - secretariat to publish the minutes from 11 May 2021 on gov.uk / Actions: 28, 29, 30, 31, 32, 33, 34, and 35. / Actions 26, 27, 36 remain open.
3	Paper 4 - Work programme update
3.1	Members heard an update on the progress of the Scottish ELC objective and the plans to proceed with a public consultation towards the end of the year.
3.2	Members discussed the feedback provided on the identity verification services proposal submitted by GDS. Members agreed that they were content that the proposal should be taken forward, but wished for their comments to be addressed. It was agreed that GDS would consider the comments made by members, and the secretariat will reissue the proposal to the Review Board. / Action Point 38: secretariat to liaise with GDS to address comments on the identity verification services proposal and will reissue the proposal after 24 September 2021.
3.3	Progress with the emergency planning and early help and prevention sub groups is progressing well, with multiple work streams underway. / Action Point 39: Secretariat to explore definition of emergency planning.
3.4	Members approved the revised process review. / Action Point 40: Secretariat to introduce Data Sharing Playbook team to devolved administrations with a view to a similar escalation process being established. / Action Point 41: Secretariat to include a list of specific bodies that would need to be consulted. / Action Point 42: Secretariat to upload a text version of the process review to gov.uk
3.5	Members discussed the proposed glossary of terms, and agreed on further consultation with the NDG on the definition of adult health and social care bodies. / Action Point 43: Secretariat to consult with NDG on definition of adult health and social care bodies and report back to members in December 2021.
3.6	Members reviewed the revised proposal form. / Action Point 44: Members to provide feedback to the Secretariat on the proposal form by 30 September 2021.
3.7	Members heard of the plans to expand s35 of the Digital EconomyAct 2017 to include businesses, so that businesses, too, may benefit from joined-up government services. Members discussed the importance of definition to capture businesses of all types and size. / Action point 45: Members to provide views on expanding the scope of public service delivery powers include businesses to the secretariat by 30 September 2021.
4	Presentation: register
4.1	Members heard an update on the public register of data shares, together with an analysis of the use of the powers up to the end of Q1 2021. Members suggested additional breakdown of the data to include more information on the specific powers being used. In response to a point raised about transparency, the Chair reiterated that the public register is the mechanism for having all data shares under the powers in one place and is one of the ways public authorities can meet their commitments to transparency as set out in the Code of Practice, but that other actions should be considered by public authorities eg engagement and consultation to support transparency / Action Point 46: Secretariat to include additional information for the next Review meeting in December 2021 and report quarterly thereafter.
5	Verbal update: ICO
5.1	The ICO updated members on progress with the ICO’s review of use of Digital Economy Act 2017 data sharing powers. . Initial audit findings are still being assessed, and the ICO anticipates providing an update to the participants and the Cabinet Office in a few weeks.
6	Data accelerator fund update
6.1	Members heard an update on the Data Accelerator Fund, and the proposals which will receive funding. The Chair reiterated that as a starting point the existing Data Ethics Framework and standards introduced by the Data Standards Authority should be used and supplemented as necessary. / Action point 47: Secretariat to liaise with MHCLG to explore gaps in legal gateways to help deliver the projects.
7	New objective - dormant assets
7.1	The secretariat advised members of the potential for a new objective to reunite individuals with dormant financial assets. / Action Point 48: The secretariat will keep members informed as the dormant assets policy is developed. / Action point 49: Members to advise the secretariat of any other dormant assets that government departments may hold by 30 September 2021.
8	Risk register
8.1	Members reviewed the updated risk register. It was agreed that the risk register will be reviewed quarterly. / Action point 50: secretariat to add a new risk to recognise how well public authorities are forecasting the metrics of data sharing activity.
4	AOB
4.1	None raised. The Chair ended the meeting reflecting on the progress the Review Board has made in the year since the transfer of functions to the Cabinet Office.
5	DONM: 07 December 2021