# Outline Business Case Template for non EA Risk Management Authorities
External form: LIT 55372	Published: [Publish date]

Audience: Local Authorities, Internal Drainage Boards and other risk management authorities

! Important The text in square brackets explains how to complete the template. [Please read and delete text in square brackets, using the space to write your own text].
This template is published on the GOV.UK website: Flood and coastal defence: develop a project business case. If the cost is likely to exceed £50 million, speak to your local Environment Agency contact before proceeding. There is now a single template for all RMA business cases, whatever the value.
For a flood and erosion risk scheme, send us your business case with a completed form FCERM 2: Flood Defence Schemes: application for grant. Please refer to Guidance note 1: Approval of flood risk management and coastal erosion studies, strategies and projects.
For a coastal erosion scheme, send us your business case with a completed CPA1: Certificate of statutory consultations and responses to them. Following the receipt of tenders, provide a completed CPA2: Application for formal approval of coast protection project, with an updated business case.
The Grant Memorandum explains what you must do to apply for grant. Once the application is approved you may then claim the cost of preparing your business case. Include this sum in your application. Please do not include costs already claimed under an FCERM7. Please note that the whole life cost includes all development and study costs.
The business case describes your application for Flood and Coastal Erosion Risk Grant in Aid (FCERMGiA). Include evidence (technical, environmental and economic) to demonstrate that the investment proposed is eligible for public investment.
Completion should comply with the Public Sector Web Site Regulations 2018. Simplified advice on what to include is provided in each section. This template uses pre-set heading and font styles. Headings comprise Section, Topic and Block in descending order. For example, the strategic case is a section heading; the introduction is a topic heading; the block heading is a further heading layer such as background.
The text styles can be seen in the Style drop down menu. Section headings describe the 5 cases. Do not add further section headings. Rename, add or remove Topic and Block headings so the content is in proportion to the value. Use tables to present numeric information but not text.
Contact your local Environment Agency Area Flood and Coastal Risk Manager and Partnership and Strategic Overview teams. They can advise you how to prepare your business case.
Update the contents field by clicking next to the contents heading and then on the update field option. Delete the lines down as far as project summary.]
# [Write the Lead Authority name here]

## [Write the name of your the Outline Business Case here.]
[You can insert a photograph with a description of what is in the picture.]

Recommendation
[Include here a brief description of the selected option, the benefits and the approval cost.]

Version Control
[Record here the version number, purpose, date and main changes]

Version History
[Record here previous versions, their purpose, date and main changes]

# Assurance and Approval Record
RMA reference number:
EA reference number:
Date of submission to EA:
## Assurance from Risk Management Authority
I confirm that this Outline Business Case meets our guidelines, quality assurance requirements, environmental obligations and Defra investment appraisal conditions. All internal approvals, including member approval, have been completed. I apply to the Environment Agency for capital grant and local levy in the sum of £_________(Grant Claim Value).
Name of RMA Project Executive:
[For administrative use only]

## Approval from Risk Management Authority Council

Version approved:
Date:

## Endorsement from Environment Agency Area Flood and Coastal Risk Manager
I confirm that the Outline Business Case is ready for assurance.
Applications less than £1million - I have consulted with the Area Director and Senior Finance Business Partner External Funding & Grants.
Applications up to £10million - I have consulted with the Director of Operations and the Deputy Director of Finance.
Applications up to £20million - I have consulted with the Executive Director of Operations and the Director of Finance.
Applications over £20million - I have consulted with the Executive Director of Operations, the Executive Director of FCRM and the Director of Finance.
Name of Area Flood and Coastal Risk Manager:
Date:
[For administrative use only]

# Environment Agency Assurance and Technical Approval
I recommend that the application is granted technical approval. The record of assurance is appended to the business case.
Name of AFCRM or Lead Assurance Reviewer:
Date:
[For administrative use only]

# Financial Approval
[See Section A4 of the Financial Scheme of Delegation.]
Name of Approving Officer:
Date:
Name of Approving Officer:
Date:
Name of Approving Officer:
Date:
FSoD reference:
Date:

# Financial Scheme of Delegation Co-ordinator
Notes
[Write your block here]

Contents

# 1.0 Project Summary
[This section is a summary of the reasons for the project, the justification for the investment and benefits expected.]
Total Value of Project £

Flood risk type: [Choose from Fluvial / Coastal / Pluvial / Groundwater]
Numbers of households at flood and/or erosion risk
- Households at very significant risk now -
- Households at significant risk now -
- Households at intermediate risk now -
- Households at moderate risk now -
- Households at very significant risk in 21XX -
- Households at significant risk in 21XX -
- Households at intermediate risk in 21XX -
- Households at moderate risk in 21XX -
Critical Infrastructure at risk now and in 21XX
[List critical infrastructure here]
Type, condition and residual life of existing defences
[State defence type, condition grade and residual life, specifically where the money needs spending.]
Environmental designations?
[State here the names of any designations affected by the project. Has the effect been authorised?]
How is flood and erosion risk managed?
[State the maintenance regime here]
Summarise the case for change
[State the implication of continuing with the status quo.]

Selected option
[Give a brief description of the selected option, the benefits and local choice where applicable.]

Economic cost and benefit of selected option
- Present Value Benefit - £
- Present Value Cost - £
- Net Present Value - £
- Benefit to Cost Ratio
- Incremental Benefit to Cost Ratio
- Whole Life Cash Cost - £

Affordability of selected option
- Raw Partnership Funding score is _%
- Adjusted Partnership Funding score is _%
- Funding from Environment Agency (grant) is £
- Funding from the Regional Flood and Coastal Committee is £
- Funding from [state the name of the funding partner and the status of the Agreement] is £

Risk
The total contingency amount is £
Top three residual risks are:
- [Describe the risk]
- [Add lines as needed]

Permissions and consents
- [State permission or consent and whether secured]
- [Add lines as needed]

Outcomes
- OM2 - [State number of claimed by the project]
- OM3 - [State number of claimed by the project]
- OM4a - [State number of Ha claimed by the project]
- OM4b - [State number of Km claimed by the project]

Schedule of critical milestone dates.
[Remember to include external funding approval dates and when you need the Environment Agency to approve the application.]

# 2.0 Strategic Case

## 2.1 Introduction
[Brief background to the project.]

## 2.2 Strategic context
[Refer to relevant Local Flood Risk Management Strategy and any Section19 investigations, Surface Water Management Plans, Environment Agency Flood Risk Management Plans or strategies and summarise what they say concerning this specific problem. Refer also to the relevant River Basin Management Plan and summarise any ways the proposal may help to support the achievement of Water Framework Directive objectives. Depending on the project it may also be useful to highlight links to other local plans/strategies such as Local Development Plans, economic regeneration strategies or green infrastructure plans.]

#### 2.2.1 [Write the name of your block heading here]
[Write your block here]

## 2.3 Environmental and other considerations
[Environmental issues, regulatory requirements, legal and other obligations affecting the project]

#### 2.3.1 [Write the name of your block heading here]
[Write your block here]

## 2.4 The case for change
[Explain the current problem and the impact of climate change. Define the households and infrastructure at risk and split into risk bands. (Flood risk bands are: very significant, significant, intermediate, moderate and low. Erosion risk bands are: short or medium term erosion loss.) Support this with specific evidence of flooding and/or erosion in the recent past. Include dates, photographs, news cuttings and plans of flooded areas or loss of coastline, and note the importance of assessing the flood depth, not just extent.
Describe the implications of doing nothing. Append an annotated map showing the baseline flood risk (extent and depth, where available) or erosion lines. Describe existing defences or other assets and refer to the standard of protection (bands of probability), residual life, environmental designation, access issues, maintenance arrangements and any other criteria that you consider material to the investment decision.]

#### 2.4.1 [Write the name of your block heading here]
[Write your block here]

## 2.5 Objectives
[Set out the objectives of the project, which should be SMART (specific, measurable, achievable, realistic and time bound). Explain the potential constraints on your scheme. Examples are environmental risks (biodiversity, historic environment, landscape, amenity), planning restrictions, land owner stipulations, working windows, access, ground conditions, contamination and available funding. Consider any opportunities for integrating wider social and or environmental benefits as part of your scheme (including the Environment Agency environmental outcome measures).
Think about any assumptions you make and the impact of error. Resist the temptation to state the solution at the start. Please be aware that any project, however small, must comply with environmental and other legislation, so if you are unclear about what this means for your project, please seek advice from your Area Flood and Coastal Risk Manager.]

#### 2.5.1 [Write the name of your block heading here]
[Write your block here]

## 2.6 Current arrangements
[Describe the existing situation, organisational approach, activities and the associated current investment or revenue costs]

#### 2.6.1 [Write the name of your block heading here]
[Write your block here]

## 2.7 Main benefits
[Identify the high level strategic and operational benefits that will accrue as a result of the investment.]

#### 2.7.1 [Write the name of your block heading here]
[Write your block here]

## 2.8 Strategic risks, assumptions, constraints and dependencies
[Provide a summary of the risks, constraints and dependencies highlighted in the Risk Potential Assessment, which should also be appended.]

#### 2.8.1 [Write the name of your block heading here]
[Write your block here]

# 3.0 Economic Case
[This section is where to explain the appraisal of the options that address the problem described in the strategic case. For all options, consider the technical issues, the environmental risk and opportunities, sustainability such as carbon use and the economic cost and benefit. Consider opportunities to work with natural processes.
Always include the option to do nothing to maintain or improve the situation. Always include the option to do the minimum necessary to maintain the situation. Start with a long list of all possible options and then dismiss those that do not warrant further investigation. If you reject individual options such as Sustainable Urban Drainage, they should be considered in combination with other options.
Assess the short list of options to demonstrate their hydraulic adequacy. The assessment of projects should be proportional to the investment. You may have the capability to undertake project assessment. If not, seek advice from an engineering consultant or collaborate with another Authority with expertise. Further advice is given below.
## Projects value less than £150,000
Manual calculations are acceptable, with appropriate sensitivity tests. Describe the method you use including assumptions. Use the flood maps to count the number of residential and non-residential properties affected today and in the future with climate impacts. Validate the numbers with historic evidence of flooding.
Assess the economic damages from flooding using the Multi-coloured Handbook. Estimate the number of residential properties before and after the implementation of the selected option. Separate these into the flood risk bands in the Partnership Funding calculator.
## Project value £150,000 to £500,000
Use industry standard surface water drainage design software. Consider how changes in surface water storage and flow rates associated with each option will reduce flood risk damages.
## Project value more than £500,000
This scale of project justifies the investment in an integrated 1D-2D hydraulic model. The model takes account of residential and commercial property threshold levels. The model is used to predict damages arising from the application of each option. Provide details of the model and the results.
Complete the economic appraisal spreadsheet provided in the Flood and coastal erosion risk management: Appraisal Guidance.

#### Climate Change
Measures that reduce flood risk today will become less effective over time due to climate effects that are predicted to increase rainfall intensity and sea level. The Partnership Funding calculator assesses the amount of grant available. It compares the number of properties before the project is implemented with the number at the end of the duration of benefit period. This accounts for climate effects that reduce the number of outcomes. The calculator now makes allowance for the number of OM2B additional households. This is the number of households that are at risk from the impacts of climate change before 2040. For example, a project will avoid flooding in a 3.33% annual event probability (AEP) rainfall event by the end of a benefit period of 50 years. In this case, the project may have to be designed to a 1.33% AEP today to allow for climate effects. This has significant cost implications.

#### Cost Estimation
The cost of the options can be derived from a plan of the works and a bill of quantities priced using industry standard estimating data. It should be benchmarked against the cost of other similar work. Consider the constraints for example access to land. Allow for risk using Optimism Bias or other method. The Supplementary appraisal guidance explains how to apply Optimism Bias. Alternatively identify the various risks, estimate the most likely and maximum impact on time and cost and then apply a root mean square approach. See the example in the template further below.
Tabulate the benefits and the costs of each option. Note that the costs and benefits in table 1 are discounted, not cash values. The discount period is your assessment of the lifetime of the assets. A benefit is a damage avoided. Rank the options in ascending order of benefit. The benefit cost ratio is an expression of value for money.
The incremental BCR column compares two options to assess the additional value provided by additional cost, and which should always be greater than unity. Identify the 2 options in the “option for incremental calculation” column. The incremental value is the benefit difference divided by the cost difference of the two options. Example values are included in table 1 to demonstrate the calculation. A worked example is shown in the Supporting Information.
Table 1 – Option Choice from Economic Appraisal Summary (example values shown to aid understanding)
Option Nr	Option name	PV cost £k	PV damage £k	PV benefit £k	Average BCR	Incremental BCR	Option for iBCR calculation
1	Do nothing	0	500	0	n/a	n/a	n/a
2	Do minimum	2	480	20	10	n/a	n/a
3	Do something 1 (5%)	100	200	300	3	2.85	2
4	Do something 2 (3.3%)	200	100	400	2	1	3

#### Option Selection
Choose the option in accordance with section 8 of the appraisal guidance. Describe how you have done this with reference to economic, environmental, risk and sustainability criteria. Some of these are non-financial benefits. Consider if the selected option is sensitive to variations in the assumptions.]
#### 3.0.1 Introduction
[Write your block here]

## 3.1 Critical success factors (CSF)
[List the attributes essential to the successful delivery of the scheme against which the available options can be assessed, for example availability of funding or resources.]
#### 3.1.1 Define the critical success factor here
[Expand here on how the success factor is measured and the weighting or priority of this success factor over others.]

## 3.2 Long List of Options
[Describe the long list of options. Identify the options from the long list carried forward for further appraisal and evaluation and say why the other options have been rejected.]
#### 3.2.1 Option Do Nothing. Shortlisted
[Describe the option and the reasons for shortlisting or rejecting it.]
#### 3.2.2 Option Do Minimum. Shortlisted
[Describe the option and the reasons for shortlisting or rejecting it.]
#### 3.2.3 Option Do Something 1. Shortlisted/Rejected. [Delete as appropriate]
[Describe the option and the reasons for shortlisting or rejecting it.]
#### 3.2.4 Option Do Something 2. Shortlisted/Rejected. [Delete as appropriate]
[Describe the option and the reasons for shortlisting or rejecting it.]
#### 3.2.5 Short listed options
[Option 1, Do Nothing, brief description.]
[Option 2, Do Minimum, brief description.]
[Option 3, name and brief description.]

## 3.3 Technical appraisal
#### 3.3.1 Option 1 - Do Nothing
[Provide a brief technical description of each option, how technical risk and residual uncertainty is addressed. Refer to technical opportunities or innovations.]
#### 3.3.2 Option 2 - Do Minimum
[Write your block here]
#### 3.3.3 Option 3 - Do Something 1
[Write your block here]

## 3.4 Environmental appraisal
[Detail the environmental impact or benefit of each of the options to enable these to be ranked for option selection. This could include routine environmental assessments but also any effects on the local community or other stakeholders.]

#### 3.4.1 Option 1 - Do Nothing
[Positive impacts: describe them here. Negative impacts: describe them here. Mitigation or enhancement opportunity: describe them here.]

#### 3.4.2 Option 2 - Do Minimum
[Positive impacts: describe them here. Negative impacts: describe them here. Mitigation or enhancement opportunity: describe them here.]
#### 3.4.3 Option 3 - Do Something 1
[Positive impacts: describe them here. Negative impacts: describe them here. Mitigation or enhancement opportunity: describe them here.]

## 3.5 Economic appraisal
#### 3.5.1 Assessment of benefits
[Summarise the main aspects of the benefits assessment from the Economics Appendix. There is no need to replicate tables of benefits and other detail here.]
#### 3.5.2 Assessment of costs
[Summarise the main aspects of the costs appendix, and how risk and uncertainty is valued. Present the economic appraisal in a table showing the benefit to cost ratio and the incremental benefit to cost ratio. Explain what the table tells us.]
Table 2 showing the results of the economic appraisal
Option	PVc / £k	PVb / £k	BCR	iBCR	Rank
1 - Do Nothing
2 - Do Minimum
3
4

#### 3.5.3 Economic sensitivity
[Explain the results of sensitivity testing.]

## 3.6 Carbon appraisal
[Summarise the main aspects of the carbon appraisal appendix. Explain what the table tells us.]
Table 3 showing the results of the carbon appraisal
Option	Capital Carbon / Tonnes CO2	Operation Carbon / Tonnes of CO2	Net Carbon (incl. sinks) / Tonnes of CO2	Rank
1 - Do Nothing
2 - Do Minimum
3
4

## 3.7 Other appraisal(s)
[Other appraisals may include non-financial benefits, matters of safety and operation and the preferences of local stakeholders and those part funding the project. Summarise the main aspects of the appraisals with reference to the appendices but do not duplicate their content.]
#### 3.7.1 [Write the name of the appraisal here.]
[Write your block here. Tabulate results where the table will contain numeric values only and explain what the table tells us.]

## 3.8 Option Selection
[Bring together the results of the various subject appraisals in the table below, showing the ranking of each option or stating Y or N to the question. Explain what the table tells us and how you have drawn the overall conclusion. Consider how sensitive the selected option is to changes in the cost, benefits, risk and other external factors]
Table 4 showing how well each option meets the appraisal criteria and the derivation of the selected option.
Criteria	Do Nothing	Do Minimum	Option 3	Option 4
Question: Meets the Objectives?
Question: Meets critical success factors?
Technical
Environmental
Economic
Carbon
Other appraisal
Operational
Local preference
Conclusion and selection

# 4.0 Commercial Case

## 4.1 Procurement strategy and timescales
[Explain the approach to procurement and how it demonstrates value for money and the benefits over the alternatives considered. Describe the form of contract proposed and how contractual risk will be shared. Confirm compliance with the Public Contract Regulations (if they apply to this procurement) and confirm compliance with your organisations procurement procedures. Provide the completion date for specific events in the schedule. Refer to the appendices for the main schedule chart. ]
#### 4.1.1 [Write the name of your block heading here]
[Write your block here]

## 4.2 Efficiencies and commercial arrangements
[All schemes spending grant are expected to demonstrate potential efficiency savings over the initial budget estimate and will be collected by the Environment Agency national programming team. Summarise the plan for delivering value for money, what has been done to date and future expectation. Refer to the appendix for the project efficiency register.]

# 5.0 Financial Case

## 5.1 Summary of financial appraisal
[Summarise the project costs. Explain how the costs have been derived and how the risk contingency has been calculated.]
Table 5 showing the Whole Life Cash Cost.
Cost Heading	Whole-life / cash cost / See note 1
Cost up to OBC. See note 3
Salary costs
Cost of Professional Advice
Site investigation and survey
Construction
Supervision
Environmental mitigation. See note 4
Land purchase & compensation
Other. See note 5
Risk or Optimism Bias. See note 6
Future cost (construction + maintenance)
Optimism Bias on future cost. See note 7
Total

Table 6 showing the Total Value of the Project.
Cost Heading	Total value of project / See note 2 / (For approval)
Cost up to OBC. See note 3	Exclude previous applications
Salary costs
Cost of Professional Advice
Site investigation and survey
Construction
Supervision
Environmental mitigation. See note 4
Land purchase & compensation
Other. See note 5
Risk or Optimism Bias. See note 6
Total	See note 8

[Notes]
1. This column shows the cash, i.e., undiscounted, values and includes all future costs over the design life including study costs approved under an FCERM7.
2. The costs in this column are cash values.
3. The whole life cash cost includes any study costs approved under an FCERM7 and the development cost of the OBC. The Total value of project does not include study costs as these have already been approved under an FCERM7. It does include the OBC development cost.
4. The cost of environmental enhancement is contained within the other cost elements and not shown separately.
5. Add further rows as necessary for individual headings. A cumulative miscellaneous cost should not be more than 5% of the total.
6. Note that the allowance for risk and/or optimism bias is part of the project approval but must be claimed separately when needed using the FCERM4 application. See supporting information for further explanation and refer to section 12 of the Grant Memorandum found on Gov.uk page: Flood and coastal defence: develop a project business case.
7. The allowance for risk and optimism bias applicable to future construction and maintenance is shown separately from current risk and optimism bias to account for uncertainty.
8. This is the total estimated costs shown in section A6 of the FCERM2. It is also the Total value of project referred to in section A4 of the Financial Scheme of Delegation.]

## 5.2 Funding sources
[State the partnership funding score and how the total project cost is to be funded. Specify the source of all contributions and any conditions and risks attached. Append the partnership funding calculator and letters of agreement. In the event that the cost of the completed project exceeds the approval, state who will underwrite the full cost.]
Table 7, Sources of Funding.
Source of Funding	£k
EA contribution (Grant in Aid)	£……….k
Local Levy	£……….k
Contributions 1 [add more lines as needed]	£……….k
Total funding	£……….k

Table 8, Partnership Funding Score
Source of Funding	%
Raw Partnership Funding score
Adjusted Partnership Funding score

## 5.3 Expenditure and income profile
[Continue writing your content here]
Table 9, Income and Expenditure Profile
Income and Expenditure streams £m	20/21	21/22	22/23	23/24	24/25	Total
Cost less contingency
Contingency
Total cost
Grant in aid
Contribution
Total income

# 6.0 Management Case

## 6.1 Project management
[Explain how you will manage the design and construction stages. Define the governance arrangements illustrated with an organisation structure chart and define the roles and responsibilities of key officers.]

## 6.2 Schedule
[Provide a schedule of events that demonstrates the main activities and the associated timescales. This can be a table or a chart that is in proportion to the scale of the project.]
Table 10, Main Event Dates.
Event [examples only included below]	Date
[Planning permission received]
[Work to be started on site]
[Work substantially completed by]

## 6.3 Outcomes
[Summarise the benefits and explain how they will be monitored and reported and when they will be realised. Consider recording the numbers of households that benefit from the project, even if they do not qualify under OM2/3. Add additional sections to the table to record other benefits, e.g., ecosystems services, natural flood management. Guidance references are taken from “Calculate Grant-in-aid funding for flood and coastal erosion risk management projects; April 2020”. Confirm who will own and maintain any assets built.]
Table 11, Outcome Measures delivered by the project
Guidance Ref	Outcome Measures	Value
4.1	OM 1 - Ratio of whole-life benefits to whole life costs over the duration of benefits period.
4.2	OM 1A – Qualifying benefits over the appraisal period (PVb taken from table 2)
4.4	OM 1B - benefits to people that are not associated with avoiding household damages, eg, less stress/risk to life.
4.5	Duration of benefit period (not the appraisal period)
5.2	OM 2A – Households at risk of flooding before the investment and which are going to benefit from a reduction in flood risk at the end of the duration of benefits period (households at risk today)
5.3	OM2B – Additional households that are at risk from the impacts of climate change before 2040
6.1.1	OM 3 – Households at risk of loss in the medium term
6.1.1	OM 3 – Households at risk of loss in the longer term
7.2	OM 4A – Habitat created or improved (ha)
7.3	OM 4B – Rivers enhanced – river habitats and natural processes restored and enhanced (km)

## 6.4 Risk, assumptions, issues and dependencies management
[State the main risks, assumptions, issues and dependencies. Tabulate the risks to the project and append a register of risks. Explain how you calculated the contingency.]
#### 6.4.1 Risks
[Risk name; risk owner; proposed mitigation]
#### 6.4.2 Assumptions
[Assumption name; proposed management action]
#### 6.4.3 Issues
[Issue name; proposed action]
#### 6.4.4 Dependencies
[Dependency name; impact on this project]

## 6.5 Assurance
[Explain the checks you have applied, for example a peer review, and the outcome. State the approval given by your organisation. Refer to any external approvals needed such as planning permission, licences and consents.]

## 6.6 Engagement with Stakeholders and compliance with the Equality Act 2010
[Summarise the process adopted to communicate the scheme to affected stakeholders and note risks and issues, for example opposition to the proposal. List out the roles within the RMA and other organisations who have been asked to comment on the proposals and provide a summary of the responses.
Describe the steps taken to meet the statutory requirements of the Equality Act 2010 that includes a duty for public sector organisations to show due regard to eliminate unlawful discrimination, advance equality of opportunity and to foster good relations between people who share a protected characteristic and those who do not.]

# 7. List of Appendices.
[Delete those not needed]
A	List of reports produced
B	Integrated Assurance and Approvals Plan
C	Benefits Realisation Plan
D	Partnership Funding Calculator
E	Photographs
F	Figures
G	Details of proposed works
H	Modelling
I	Economic appraisal and sensitivity analysis
J	Cost breakdown
K	Expenditure profile
L	Project Schedule
M	Technical reports
N	Risk, Assumptions, Issues and Dependencies register
O	Communications Plan
P	Environmental reports
Q	Natural England letter of support
R	Procurement strategy
S	Efficiency
T	Carbon Calculator
U	Equality Analysis
V	Appraisal Summary Tables
W	Information Delivery Plan

# 8.0 Supporting Information
[Please delete all supporting information from business case before submission for approval]

Introduction
Our experience shows that some aspects of the business case will benefit from further explanation. In the sections that follow we provide additional advice and links to sources of more detailed information that you may find helpful.

Selecting the Optimum Economic Option
A small village has suffered flooding on a number of occasions and the source of the flooding is both fluvial and surface water. Modelling indicates that flooding can occur from events with an annual event probability (AEP) as high as 10% from the surface water system but a little lower, at an AEP of 5% from a small watercourse.

Assessing the BCR
There are limited options to address the risk due to various constraints as follows:
Option 1 – Do Nothing
Option 2 – Do Minimum
Option 3 – a combined surface water / fluvial scheme with an AEP of 2%;
Option 4 – a surface water only scheme that provides protection from the 5% AEP event;
Option 5 – a fluvial only scheme that provides protection from the 3.3% AEP event;
Option 6 – a combined solution that provides protection from the 1% AEP event.
Table 8.1, assessing the BCR for each option
Option	Damage £	Damage avoided £	Cost £	BCR
Option 1 DN	500,000	0	N/A	N/A
Option 2 DM	480,000	20,000	2,000	10.0
Option 3 (2%)	50,000	450,000	170,000	2.6
Option 4 (5%)	200,000	300,000	50,000	4.0
Option 5 (3.3%)	100,000	400,000	150,000	2.7
Option 6 (1%)	0	500,000	220,000	2.3

It appears that the ‘Do Minimum’ (DM) option, which involves maintaining the current level of risk and preventing the situation deteriorating, is the leading economic option with the highest BCR. However, it delivers very little benefit and doesn’t achieve the objective of protecting the properties. This does not mean the DM is the optimum economic option. The other options are all cost beneficial and deliver far more benefit. To assess the additional benefits of the other options, we calculate the incremental benefit cost ratio.
Calculating the iBCRs
By comparing the iBCR between two options with an incremental increase in benefit, we can determine which option provides the optimum value for money. The options are placed in order of ascending benefit or damage avoided.
Table 8.2, ordering the options by increasing benefit.
Option	Damage £	Damage avoided £	Cost £	BCR
Option 1 DN	500,000	0	N/A	N/A
Option 2 DM	480,000	20,000	2,000	10.0
Option 4 (5%)	300,000	200,000	50,000	4.0
Option 5 (3.3%)	100,000	400,000	150,000	2.7
Option 3 (2%)	50,000	450,000	170,000	2.6
Option 6 (1%)	0	500,000	220,000	2.3

Looking at the iBCR of Option 4 i.e. the difference in costs and benefits between it and DM (the option preceding it in the list) gives:
iBCR = [PVb Option 4 – PVb DM] / [PVc Option 4 – PVc DM]
iBCR =[£200,000 - £20,000] / [£50,000 - £2,000] =	£180,000/ £48,000 = 3.75
Following this through for each pair of options i.e. comparing Option 5 to Option 4, Option 3 to Option 5 and Option 6 to Option 3 gives the following.
Table 8.3, calculating the iBCR
Option	Damage £	Damage avoided £	Cost £	BCR	iBCR
Option 1 DN	500,000	0	N/A	N/A	N/A
Option 2 DM	480,000	20,000	2,000	10.0	N/A
Option 4 (5%)	300,000	200,000	50,000	4.0	3.75
Option 5 (3.3%)	100,000	400,000	150,000	2.7	1.33
Option 3 (2%)	50,000	450,000	170,000	2.6	2.50
Option 6 (1%)	0	500,000	220,000	2.3	1.00

This shows that, in each case, the iBCR is greater than 1.0 indicating that the additional economic benefits provided by the next option in the list, outweigh the costs of providing these benefits and appear therefore to be justified. It could be argued that Option 6 should therefore be progressed. However, in order to ensure that too much investment is not directed at a single scheme, potentially at the expense of other schemes, iBCR thresholds are used particularly targeting solutions that deliver a high level of protection. In effect, this is aimed at controlling investment in solutions that may increase the level of protection from very rare events.
Rather than using the investment to achieve a very high SoP, it may be more appropriate to protect a number of communities to a lower standard, spreading the funding available more widely to benefit more people.
The thresholds used are:
Options delivering protection from floods with an AEP greater than 1.3%, must have an iBCR >1
Options delivering protection from floods with an AEP between 1.3% and 0.5%, must have an iBCR >3
Options delivering protection from floods with an AEP less than 0.5% must have an iBCR >5
This shows how it becomes increasingly difficult to justify providing very high SoP. An option that would provide protection against a flood with an AEP less than 0.5% would need to demonstrate that it was delivering 5 times more benefit than the associated increase in costs. This is one of the reasons why schemes tend to be targeted at achieving protection from events with an AEP of 1% or greater. Applying the thresholds to the options in our example gives the following.
Table 8.4, applying the probability thresholds
Option	BCR	iBCR	Threshold iBCR	Over threshold?
Option 1 DN
Option 2 DM	10.0
Option 4 (5%)	4.0	3.75	1	Yes
Option 5 (3.3%)	2.7	1.33	1	Yes
Option 3 (2%)	2.6	2.50	1	Yes
Option 6 (1%)	2.3	1.00	3	No

This changes the optimum economic option to Option 3. This is because the increased cost of delivering a scheme to protect from an event with an AEP of 1%, compared to one protecting from an event with an AEP of 2% cannot be justified i.e. the iBCR is less than 3, the threshold to justify the higher standard of protection. There is a useful flow-chart, on page 273 of the Flood and coastal erosion risk management: Appraisal Guidance which shows this process.
At this point in the process, we check how sensitive the optimum economic option is to various criteria that could affect the cost and benefit values. So for example, were the costs of option 3 to increase by £40,000 or 23%, the iBCR in relation to option 5 will fall from 2.5 to 0.8, which is below unity. Therefore the optimum economic option is more likely to be option 5.

Selecting the option
The methodology explained above describes how to use iBCR to identify the optimum economic option. The choice of option will be influenced by the environmentally preferred option and local choices (external contributions). In simple terms, option 6 can become a local choice if a local financial contribution of £50,000 is made towards the cost of the scheme. This is in addition to any external contributions needed under the partnership funding policy.

Treatment of Project Risk - Contingency and Optimism Bias.
The OBC includes a contingency to allow for underestimation of cost, time and scope, and for unplanned events that also increases cost. Guidance is provided in the ‘Defra Supplementary Note to Operating Authorities March 2003 Revisions to Economic Appraisal Procedures Arising from the New HM Treasury “Green Book”.
The supplementary note addresses the risk that the assessment of cost, time and benefits are overly optimistic and proposes the application of an Optimism Bias uplift. It is important to note that the Optimum Bias uplift is applied to the “best estimate”.
The “best estimate” is the appraiser’s assessment of the most likely outturn costs of the project. Cost includes labour, materials, supervision, land purchase, compensation, access costs and contractors’ overheads associated with both temporary and permanent works. Whole life cost includes operation and maintenance costs. Where the judgement of the estimator is that additional sums are likely to be required for particular areas of work, for example dealing with poor ground conditions, these should be included but general contingencies should be estimated as part of the process of deriving the optimism bias adjustment.
The supplementary note provides an alternative approach in the Environment Agency where the equivalent Optimism Bias uplift factor can be derived from an Environment Agency recommended Monte Carlo type risk valuation approach with 95%ile confidence.
This advice offers an alternative approach to the Monte Carlo type risk valuation technique that does not need specialist software to calculate. The following is an example of using the Root Mean Square to calculate the residual risks, for which a cost is not included in the best estimate. This is valuable as it gives a better idea of the maximum likely project cost.

Example of Root Mean Square calculation in Risk Management
Tabulate the residual risks for which a cost is not included in the best estimate and calculate their most likely and maximum cost. The statistical root mean square approach is applied to the difference between the most likely and maximum values in recognition that not all maximum values will occur at the same time.
Table 8.5, example of the application of the root mean square calculation.
Risk	Most Likely Additional Cost	Maximum Likely Additional Cost	Difference	Difference squared
Unexpected services	£500	£1100	£600	360 x 103
Weather delay	£700	£2000	£1300	1690 x 103
Sum	£1200			2050 x 103
Risk Allowance				Square root of 2050000= / £1430

Project best estimate is £30,000
Most likely additional cost is £1,200
Maximum likely additional risk is £1,430
Maximum likely project cost is £32,630
Optimism Bias uplift is £1430/£31,200=4.6%]