Business Case Summary

Portfolio/ Business/Country Plan Summary: / The Humanitarian and Migration Directorate (HMD) leads on the ODA thematic priority on Humanitarian Preparedness and Response. The HMD Business Plan objective is to prepare and respond to humanitarian crises, and help position the UK at the heart of an unrivalled global network of economic, diplomatic and security partnerships, by driving more effective collective approaches to crises, through prioritising people with the most severe needs, protecting civilians and access, and preventing future crises.

Title: Emergency Deployment Teams Programme (EDT2)
Programme summary (100 words maximum): / During humanitarian crises, local emergency responders and systems can be overwhelmed, risking injury, loss of life and secondary crises e.g. disease outbreak. The Emergency Deployments Team 2 (EDT2) programme enables the UK to offer assistance to countries in need of emergency medical assistance and international search and rescue. The programme will also support local emergency preparedness and response planning in partnered countries through training, mentoring and knowledge exchange with emergency responders and national response teams. EDT2 is the successor to the EDT programme (EDT1), due to conclude in June 2022, and forms an essential part of the UK’s emergency response toolkit.
What is the rationale for UK Aid spending? (200 words maximum): / UKAid has supported previous iterations of UK International Search and Rescue (UKISAR) for 25+ years and UK Emergency Medical Team (UKEMT) for 10+ years, showcasing the UK as a global humanitarian response leader. UK teams have responded to earthquakes, cyclones, diphtheria and measles outbreaks, and the UKEMT deployed over 130 medical experts to 18 countries in response to Covid-19. / The EDT2 programme will build on this legacy as part of FCDO’s humanitarian rapid response toolkit. It delivers on the Integrated Review’s strategic priority to prepare for and respond to humanitarian crises and continues to demonstrate that the UK is a principled humanitarian donor providing world class rapid response, drawing on the best of British expertise and capabilities; saving lives, alleviating suffering and protecting the dignity of affected people. EDT2 is positioned within FCDO’s Humanitarian Framework as specifically contributing to more prioritised and effective humanitarian responses. It will do this by responding to countries affected by major disasters and supporting and complementing local emergency responders. / Through EDT2, the UK will help implement and strengthen international emergency response standards and coordination through participation in UN fora and exchange of learning with other national and international teams. By enhancing the skills and expertise of UK personnel, including National Health Service (NHS) and Fire and Rescue Service (FRS), the programme will also contribute to building stronger resilience at home. Provision of humanitarian aid is in line with the International Development Act.

Strategic Case

Summary of the proposed programme:

1. The Emergency Deployment Teams 2 (EDT2) programme forms a key part of HMG’s emergency response toolkit. It enables the UK to offer support to countries in need of emergency medical assistance and international search and rescue in the event of a rapid onset emergency, in accordance with international standards. From year 2 of the programme, EDT2 will also deliver targeted partnership projects with selected countries to build capacity amongst first responders and national teams in line with international best practice, encourage knowledge exchange and build relationships ahead of any response needs.
2. Through EDT2, the UK will also help to strengthen international emergency health, and search and rescue response standards and capability. This will be achieved through participation in UN fora, partnerships with other international teams and through sharing learning from monitoring and evaluation. As a result, countries will be supported by rapid, coordinated and appropriate medical and search and rescue capabilities in the immediate aftermath of humanitarian disasters, which will ultimately save lives, alleviate suffering and protect dignity. The programme also raises the UK’s domestic profile and resilience by using “Best of British” expertise, including volunteers from the NHS and Fire and Rescue Service (FRS).

EDT2 will build on the EDT1 programme, due to conclude in June 2022, using an improved delivery model and drawing on previous successes and UK comparative advantage in these fields. The design of the programme will ensure that EDT2 is more efficient to manage than EDT1.

  Overall context:

1. Major disasters are increasing. A United Nations Office for Disaster Risk Reduction report highlights that in the period 2000 to 2019, there were 7,348 major recorded disaster events claiming 1.23 million lives, affecting 4.2 billion people – a sharp increase from the previous twenty years.
2. Much of the difference is explained by a rise in climate-related disasters including extreme weather events: from 3,656 climate-related events (1980-1999) to 6,681 climate-related disasters in the period 2000-2019[1]. 2020 was dominated by climate-related disasters. It rivalled 2016 as the world’s hottest recorded year despite the absence of a strong El Niño effect. Climate-related disasters were largely responsible for the 389 recorded events which resulted in 15,080 deaths, 98.4 million people affected, and economic losses of at least US$ 171.3 billion. In comparison to the previous two decades (2000-2019), 2020 was higher than the annual average in terms of number of recorded events and the annual average of economic losses, which is US$ 151.6 billion.[2]
  [1] https://reliefweb.int/report/world/human-cost-disasters-overview-last-20-years-2000-2019
  [2] 2020 The non-COVID year in disasters, UNDRR
3. The world is also experiencing more disease outbreaks. The Covid-19 pandemic is the most significant example. However, nearly 1,500 epidemic events have been recorded by the World Health Organization (WHO) during 2011-19.[3] Various factors including globalisation, urbanisation and climate change have increased the possibility of transmission of viruses from one place to another, overcrowding, animal-human interaction, antimicrobial resistance and other risk factors may also contribute to the emergence and spread of infectious disease outbreaks.[4] Almost half of all deaths in low-income countries are caused by communicable diseases, and maternal, perinatal and nutritional conditions. Respiratory infections, diarrhoea, malaria, tuberculosis and HIV/AIDS are the top 10 causes of death[5]. Covid-19, conflict, and reduced antenatal and vaccine coverage amongst children pose a high risk of increased disease in poorer countries as health systems decline, heightening exposure to disease epidemics and the need for more frequent rapid response as prevention systems falter.
  [3] WHO (2019) A world at risk: annual report on global preparedness for health emergencies; Geneva: Global Preparedness Monitoring Board, World Health Organization.
  [4] WHO (2018) Managing epidemics: key facts about major deadly diseases; Geneva: World Health Organization.
  [5] Global Humanitarian Overview, OCHA 2022
4. When disasters (e.g. earthquakes, tsunamis, cyclones, industrial accidents, disease outbreaks or any combination of these) are of such impact in terms of scale, scope or complexity that they overwhelm national capacity to respond effectively, international humanitarian response is required to save lives and alleviate suffering. Whilst all countries experience some level of vulnerability to sudden onset disasters, irrespective of their economic development or risk reduction efforts, it is in those countries with high vulnerability and low resilience that rapid onset emergencies are likely to have the most impact.
5. The UK has been a long-time investor, through bilateral and multilateral support, to build resilience in local systems, services and capacity for the most vulnerable countries to better prevent, prepare, detect and respond to crises. The UK also maintains a suite of rapid humanitarian response mechanisms that can be offered to countries in need of assistance when capabilities are overwhelmed. The Emergency Deployments Team 1 (EDT1) programme was a key part of this response toolkit to maintain and deploy world-class international search and rescue and emergency medical teams in response to international disasters. UK teams have developed alongside and in support of the global International Search and Rescue Advisory Group (INSARAG) and Emergency Medical Team (EMT) initiatives, reaching full accreditation under the current scope of standards.
6. INSARAG celebrated its 30th anniversary in 2021. It is a global network of more than 90 Member States and organisations under the United Nations umbrella. The work of INSARAG is focused on saving lives by promoting efficiency, enhanced quality and coordination amongst national and international Urban Search and Rescue (USAR) teams based on adherence to common guidelines and methodologies. INSARAG prepares for, mobilises and coordinates effective, principled and flexible international USAR assistance to countries affected by collapsed-structure emergencies. Since the INSARAG External Classification (IEC) system was introduced in 2005, 57 teams have been classified from 43 countries as meeting the necessary skills, equipment and resources to provide international assistance. The UK was accredited in 2006.
7. The EMT initiative, coordinated by the WHO, is in its 10th year and includes 32 accredited teams. EMTs are groups of health professionals (doctors, nurses, paramedics etc.) that treat patients affected by an emergency or disaster. They work to meet minimum standards set by WHO and its partners, and come trained and self-sufficient to avoid burdening the countries, communities and health services they are assisting. EMTs are designed to respond quickly - deploying to an impacted area within days or hours to treat immediate needs following a disaster or emergency. The EMT initiative also enables countries to improve their own national capacity, which they are then able to use to assist other countries in emergencies. It enables affected countries to accept and use international EMTs in a timely and coordinated manner. Host governments and affected populations can depend on EMTs from WHO’s global list to arrive trained, equipped and capable of providing the interventions promised. The Covid-19 pandemic has reinforced the importance of the EMT initiative as a flexible health response option as well as encouraged new innovations within the mechanism.
EDT2 point of entry:

1. EDT2 will build on the successes of, and learning from, EDT1. It will address lessons from 25+ years of UKISAR and 10+ years of UKEMT delivery experience. It will also adapt to new and changing response needs.
2. Under EDT1, the UKISAR maintains INSARAG accredited ‘medium’ and ‘heavy’ response teams comprising volunteers and equipment (e.g. search dogs, medics, engineers and veterinary personnel) who are on standby 24/7/365 to deploy and rescue people affected by disasters. This includes helping support local search and rescue efforts, provide coordination, command, and logistical support. In recent years, UKISAR have developed a structural engineering response capability and flood rescue response options drawing on available national resources.
3. The UKEMT provides world class, WHO accredited, medical, surgical, rehabilitation, disease outbreak and public health experts, from NHS and international rosters, that are ready to deploy at 24-48 hours’ notice to bolster the local health workforce or provide just-in-time training and supportive supervision and/or other niche expertise as required. Although the UKEMT was originally designed for trauma care following major earthquakes, it has evolved during EDT1 to also provide response to infectious disease outbreaks. This has been consolidated within a dedicated outbreak specialised team, which has been used extensively during the Covid-19 pandemic.
4. Outside of response, the UK has helped shape international standards and approaches in both these fields. For example, the UK has been an instrumental influencer through its engagement in WHO EMT technical working groups including setting the benchmarks on safeguarding and protection. UKISAR is also active at the global level in shaping and influencing ISAR policy and standards.
Key shifts in emergency deployments:

Need for flexible response options:
The increased frequency of extreme weather-related disasters carry new types of response needs, with implications for both UKISAR and UKEMT capabilities which need to develop more ‘flexible response’ options. This is recognised in one of INSARAG’s four strategic objectives for 2021-26, which focusses on the need for ‘flexible response’ teams that expand beyond urban search and rescue in order to address emerging climate related response needs e.g. flood response.[6] The WHO has also reflected on the need for more flexible response in order to accommodate more specific health requirements or other types of health emergencies beyond sudden onset disasters. A recent WHO EMT lessons learnt paper (December 2021) highlights that the varied requests over the past few years for EMT deployments demonstrate the wide range of needs they can fill.[7] In particular Covid-19 has forced an evolution in what EMTs can do and how they deploy internationally. For example, across the responses from the UKEMT to Covid-19 there was a strong focus on providing more technical support e.g. on Infection Prevention Control (IPC) and how to set up severe acute respiratory infection (SARI) treatment centres as well as supporting national and local strategies in responding to Covid-19.
[6] https://www.insarag.org/about/strategy/
[7] WHO EMT Secretariat: Emergency Medical Teams: Reflections and Opportunities, December 2021

More national teams and more competition:
Since EDT1 there has been a significant increase in the number of ISAR and EMT teams that have been developed, accredited and deployed to overseas disasters. Many countries frequently affected by disasters are also establishing their own national capabilities. There were 7 EMTs accredited in 2016 (including the UK) by WHO and there are now 32 WHO accredited EMTs (9 of which are classified as a ‘type 2’[8] EMT)[9] with more teams in the pipeline for accreditation. There are 57 ISAR teams now accredited and with new ‘light’ team accreditations starting in 2021 there is the potential for many more teams, including from lower income countries, to join the global ISAR family. This is testament to the success of the WHO and INSARAG initiatives and investments made to date in mentoring, training and building capacity of new teams and wider investments in disaster preparedness and resilience. However, stronger national capacity is changing the types of requests being made for international assistance e.g. for specialised health care teams who can work with existing national health facilities. More teams offer more choice for governments requesting assistance following a disaster but also risks competition between teams and too many teams risk hindering rather than helping rescue efforts.
[8] A type 2 includes hospital inpatient surgical emergency care and specialist cells, can be set up within 72 hours of arrival and operate 24/7 for up to 3 months. It can treat up to 100 out-patients, provide 7 major or 15 minor operations daily, accept up to 40 in-patients and provide maternal healthcare.
[9] WHO list of accredited field hospitals by country owned listed here

Capacity development of local and national response teams:
Regardless of the scale of international surge, the initial weight of a response always falls on national teams and local first responders. Investing in capacity building and relationships between international surge, national teams and local responders for future emergencies is an essential step in improving response efforts. This features prominently in UN strategic objectives for ISAR and EMT initiatives[10]. For example, one of INSARAG’s four strategic objectives for 2021-2026 is to ‘boost localisation’. This makes the case for capacity building in countries most at risk, to strengthen disaster preparedness and response at a more local level. Equally, capacity building features prominently in the recently revised WHO ‘Blue Book’ (published January 2021), and a WHO Executive Board Resolution calls upon Member States, donors and partners to strengthen the role of the local health workforce, and the development of effective and high-performing, national, subnational and regional Emergency Medical Teams[11].
[10] INSARAG strategic plan: https://www.insarag.org/wp-content/uploads/2021/07/INSARAG-Strategic-Plan-2021-2026_Endorsed-27-Jan-2021-V2-.pdf and WHO Blue book: https://extranet.who.int/emt/guidelines-and-publications
[11] https://apps.who.int/gb/ebwha/pdf_files/EB146/B146_CONF17-en.pdf
EDT1 lessons:

1. As part of this Business Case design, interviews were conducted with a range of EDT1 stakeholders including current partners, the Department for Health and Social Care (DHSC), Home Office, WHO and the United Nations Office for the Coordination of Humanitarian Affairs (OCHA) to understand what has worked well and what could be improved. Key limitations from EDT1 are summarised here.
2. Limited opportunities to deploy the largest EDT1 capabilities:
There have been no deployments of the UKEMT Field Hospital (since its accreditation in 2016), as the right combination of conditions (relating to scale and severity of disaster, need for a hospital facility, ask from host government/WHO) has not been met. In addition, due to the high cost of deploying the UKEMT Field Hospital, it will only be possible to deploy it in response to the largest of humanitarian disasters. Even in these contexts 9 other countries hold type 2 hospital facilities, many of which linked to national civil protection organisations and the military which have the capacity to deploy much faster than the UK. Instead, the UKEMT real value added during EDT1 has been in smaller personnel focused deployments, sending medics who have embedded with existing hospital infrastructure or other EMTs to provide clinical care and training tailored to the specific needs of each country. EDT2 presents an opportunity to rethink the level of hospital infrastructure required by UKEMT and types of teams the UK should develop, maintain and deploy.

Similarly, whilst UKISAR ‘heavy’[12] teams have deployed numerous times, including the Nepal earthquake in 2015 and flooding in Bosnia/Serbia in 2014, there has been limited deployment of UKISAR during the lifetime of EDT1. UKISAR was made available and in a state of readiness following the Beirut explosion (August 2020) and for the Haiti earthquake (August 2021) but was stood down when the offer of assistance was not taken up by the authorities. There have been small personnel deployments of UKISAR including to Bangladesh, the Caribbean (to conduct hurricane assessment) and to assist with wildfires in Greece. Not all of these deployments have been done under the EDT1 programme (e.g. deployment to Greece in 2021 utilised UKISAR personnel and processes but was coordinated by the Home Office), but this also demonstrates that there is a requirement for a wider range of UKISAR capabilities, including smaller specialised and ‘light team’ configurations in addition to the ‘heavy’ capability.
[12] A ‘heavy’ team has the capacity to support 24-hour search and rescue operations, at two independent locations, during a disaster.

Improvements needed to UKEMT governance and efficiency:
Delivery of the UKEMT under EDT1 was through three accountable grant partners and one commercial arrangement, all with accountability to FCDO but no arrangements (which the exception of
Field Hospital deployments) for collaborative working between them. This was due in part to the organic way that the programme developed over time. This gave rise to duplication among providers, blurred lines of accountability (particularly challenging in fast-paced humanitarian response) and required greater FCDO programme management oversight. The UKEMT mid-term evaluation highlighted these challenges and recommended establishing a dedicated Project Director and Governance Team which helped link the partners and FCDO together. Whilst this was an effective solution under EDT1, having a lead partner with oversight of all aspects of the UKEMT would ensure much clearer structures for delivery and accountability, with potential time and cost savings.

Need for dedicated UKISAR equipment cache:
UKISAR draws from UK domestic search and rescue teams for some of its recruitment, training and equipment. This has generated great efficiencies for the programme in being able to build on (and contribute back to) national resilience expertise. However, not having a dedicated UKISAR equipment cache has risked slowing down response times as kit cannot be packed and transportation paperwork prepared in advance. It also presents risks to UKISAR’s capacity and accreditation, should there be any changes to how national resilience capabilities are structured.

Opportunities to further expand coordination and alignment with wider health security activity:
Across UK Government, EDT1 engages in the Epithreats coordination forum which carries out horizon scanning of epidemics around the world. It also coordinates with the DHSC Public Health Rapid Support Team (PHRST) which supports low- and middle-income countries in investigating and responding to disease outbreaks. There is scope for further collaboration between these initiatives as well as the Global Outbreak Alert and Response Network (GOARN), which is a WHO hosted global network of public health institutes, including the new UK Health Security Agency (UKHSA).

Importance of having contingency budget and clear processes for smaller responses:
EDT1 has been primarily a programme for managing the UKISAR and UKEMT capabilities, rather than a programme that delivers deployments. For large responses this has worked well, with the capabilities used under a dedicated response programme and using funding from central crisis reserves. However, for smaller responses, where these wider systems have not activated, the lack of dedicated budget and processes hindered quick deployments. In the latter years of EDT1 addendums to the business case were made to enable smaller-scale response activity and build in contingency funding. This has proved instrumental in not only activating small-scale responses quickly but also initiating preparatory activity e.g. covering mobilisation costs or deploying assessment teams for larger responses.

Monitoring and evaluation should be built into new programme from outset:
The EDT1 programme evolved considerably over its lifetime, responding to changing context, demands and governance structures as noted above. Lessons from EDT1 have demonstrated the value of improved monitoring tools and systems to consistently, and more accurately, measure the timeliness, speed, effectiveness and efficiency of deployments, ensuring lessons are learnt and incorporated into future planning.

What does this mean for the EDT2 programme?

This is detailed in the appraisal case. In summary, to address these lessons and new emerging response needs, the preferred option for the EDT2 programme will:
  1. Introduce new flexible and specialised response teams. UKISAR and UKEMT capabilities will be expanded in response to changing needs and areas where the UK can demonstrate comparative advantage and fill critical gaps in the wider response system.

  1. Introduce a partnerships component for first responders and national response teams. EDT2 will make better use of available capabilities outside of response through the introduction of partnerships with local and national first responders in priority countries. These partnerships may involve delivery of targeted capacity building to help teams better prepare and respond to disasters. It may also involve knowledge exchange or joint exercising to improve the capacity of both UK and national responders, and build familiarity with working together. Partnerships will be identified in consultation with FCDO post and regional advisers to ensure they align with national strategies and assessments of gaps and needs and existing programming.
  2. No longer include a dedicated UK Field Hospital asset. The UKEMT field hospital asset has never been deployed and in November 2021 the FCDO made the decision that it should be decommissioned. This was a balanced judgement comparing the value of retaining a UK asset, useful only for very rare large-scale emergencies, against the high costs of maintaining and deploying the asset. It also considered the number of other countries who maintain Field Hospital capabilities. The savings can be redirected to more effective emergency response needs.
  3. Capitalise on evidence and learning generated during deployments and partnerships work, and through a more structured approach to inform and influence global policy and guidelines on EMTs and ISARs.
  4. Revise the programme’s governance structure to build in more efficiencies. EDT 2 will have a single lead partner for each of the UKISAR and UKEMT components. This will allow each component to be more effective and efficient. Two programme funded FCDO Implementation Roles will also be included to facilitate delivery against the programme’s outputs – including technical input and coordination across key stakeholders. Building in flexibility on how much we want to scale up capability and partnership building will manage resource and overstretch.
  5. Revise deployment process and include contingency budget for smaller deployments. EDT2 will include a small level of contingency funding and decision-making processes for small-scale responses that may not be appropriate for the Crisis Reserve.

Expected outcome and impact:

1. Outcome: Countries are supported by rapid, coordinated and appropriate medical and search and rescue capabilities in the immediate aftermath of humanitarian disasters and spikes in need during protracted humanitarian crises.
2. Impact: Lives are saved, suffering is alleviated and dignity is maintained for people affected by disasters and spikes in need during protracted humanitarian crises.

How does this meet the UK political commitments?

1. Provision of humanitarian aid through EDT2 is in line with the International Development Act. The 2021 Integrated Review (IR) of Security, Defence, Development and Foreign Policy marked a shift in UK priorities. EDT2 is aligned with the IR’s reaffirmation that the UK will provide humanitarian assistance at moments of crisis.[13] By responding to sudden onset disasters and disease outbreaks overseas, EDT2 will contribute to global health security objectives within the IR and will contribute to the priority of “building stronger resilience at home”.
  [13] Integrated Review of Security, Defence, Development and Foreign Policy: Global Britain in a Competitive Age.
2. In relation to Humanitarian Preparedness and Response, EDT2 will provide a key response capability for the UK to assist people in event of humanitarian disaster. In relation to Building Stronger Resilience at Home, EDT2 will, enhance the skills and expertise of UK personnel, specifically public bodies including NHS and FRS.
3. EDT2 is positioned within the FCDO’s new Humanitarian Framework as specifically contributing to more prioritised and effective humanitarian responses.  It will do this by responding to countries affected by disasters and supporting and complementing national and local responders. Through building capacity for national EMTs, EDT2 will also contribute to FCDO priorities around Health System Strengthening[14]. It also aligns with the UK’s 2017 Humanitarian Reform Policy[15] and principles around delivering better humanitarian responses in line with outcomes of the humanitarian “Grand Bargain”, such as localisation.
  [14] https://www.gov.uk/government/publications/health-systems-strengthening-for-global-health-security-and-universal-health-coverage/health-systems-strengthening-for-global-health-security-and-universal-health-coverage-fcdo-position-paper
  [15] https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/659965/UK-Humanitarian-Reform-Policy1.pdf

Assurances:

Gender Equality Act: Assistance will be given on the basis of need. Partners will ensure that treatment is gender appropriate and with special consideration given to women and girls. Deployable expertise will include specialists in maternal healthcare, meeting Sexual Reproductive Health and Rights requirements as appropriate. The programme will ensure that it adheres to the International Development (Gender Equality) Act 2014 by insisting upon disaggregated reporting during emergency responses, ensuring that any delivery partners are aware of the requirements and reflect that within their processes and policies, and that capacity building work engages a diverse training audience and that the curriculum reflects the differing needs of men, women, girls, and boys.

Disability: Partners will be required to provide disaggregated data on disability as part of their reporting commitments and efforts have been made to ensure a holistic approach to protection issues by integrating concerns for people with disabilities and older people. The programme will seek to maintain experts on the database who specialise in spinal injury and rehabilitation, which will target those newly living with disabilities as a result of a disaster.

Counter-Terrorism Act: There are no foreseen risks related to terrorism activities or funds being diverted to terrorist organisations for this programme. Strong financial controls and risk management guidance will be implemented within every deployment according to country contexts.  FCDO will carry out due diligence assessments of providers, who will cascade this to downstream partners.  This includes a delivery chain mapping which will be updated throughout implementation. This will also include checks to ensure providers’ systems and procedures provide adequate protection against the risk of terrorist financing. FCDO will jointly agree with partners on mitigation measures for all identified risks. FCDO will remain aware and vigilant of the terror threat in-country throughout the lifetime of this programme.

Climate and Environment: The EDT2 programme does not include a significant environmental objective or budget line for it to be eligible to be categorised as International Climate Change Financing. As a programme that addresses rapid onset humanitarian crises there is an exception to PROF rule 5 that “all new programmes (and the projects, interventions or events within them) must align with the Paris Agreement”. However, for the rapid onset element of EDT2 we will seek to reduce carbon emissions during the life of the programme.  The capability building and partnership building elements of the programme will not come under the exemption. For these, climate risk and adaptation assessments will be conducted when the specific projects are developed.

Partnership Principles: Partnership Principles will be held by the FCDO country desk for countries which require them. We will assess partnership principles in the context of management and monitoring of capacity building work alongside FCDO country desks.

Safeguarding: The programme will adopt a comprehensive approach to due diligence in line with FCDO programme management procedures. All partners of the work-strands will be required to have safeguarding policies in place and complete due diligence that, along with safeguarding and equality, also covers areas of financial management and reporting, past performance, professional and technical capacity and legislative compliance. Lead partners will be expected to perform due diligence on any other organisations that they partner with, ensuring that safeguarding requirements are passed down the supply chain. All partners will be expected to identify how they will ensure safeguarding of vulnerable persons throughout the programme, how they will ensure standards are maintained during responses, and to include training on it as an integral part of any capacity building activities that they perform.

Risk: The overall risk rating for the programme is moderate.  However, each deployment will carry its own level of risk, which could vary from minor to severe depending on the response context. FCDO will work with partners to establish each deployment risk, including: HEROS programme, country desks, OCHA and WHO. Wider risks and mitigation measures are detailed in the Management Case and Risk Register (Annex A).

Trained personnel for emergency response in specialist areas.

End to end management and transportation of supplies required for agreed menu of response capabilities.

Institutional, operational systems and supporting functions to deploy capabilities rapidly and safely.

New capabilities brought online, informed by learning, directed by advisor (Implementation Role)
Impact Statement
Lives are saved, suffering is alleviated and dignity is maintained for people affected by disasters and spikes in need during protracted humanitarian crises.
Countries are supported by rapid, coordinated and appropriate medical and search and rescue capabilities in the immediate aftermath of disasters and spikes in need during protracted humanitarian crises.

Outcome Statement
Theory of Change – Emergency Deployments Team Programme II
Outcomes
UK has internationally recognised rapid response capability to support countries in need of emergency medical and search and rescue support.
Stronger resilience is built for partnered countries to respond to disasters.
The global emergency response system is improved, based on evidence from learning and UK’s international engagement
Outputs
UK maintains highly effective emergency response capabilities, relevant to humanitarian needs, drawing on British skills and expertise, which are readily deployable in response to disasters.
First responders in priority countries have greater knowledge and capacity to provide coordinated and timely response following disasters.
Evidence is generated to improve the international emergency deployments system, enabling the UK to play a significant role, and maximise leverage, when engaging internationally in working groups to set standards and best practice
Activities
EMT and ISAR exercises alongside local and national counterparts

Targeted technical assistance to strengthen emergency preparedness capacities and systems

Exercises and technical assistance informed by learning

Advisor and coordinator (Implementation Roles) work with FCDO desks and wider HMG to raise awareness of partnership activities and ensure alignment with existing work

Active participation in INSARAG, WHO EMT forums and working groups, training, mentoring and knowledge exchange with other teams.

After action reviews from each emergency and capacity building deployment, with key learning shared.

Programme evaluation commissioned.
Implementation Roles provide advice on development /use of capabilities for the programme and connect with wider policy and programmes

Underlying principles
UK is leader in EMT and ISAR with experience and influence, adding value through flexible, proportionate response, working within international guidelines and with national systems and responders. UK does not duplicate or compete with other teams . As such the UK is well positioned through this programme to respond when required, mentor others and influence the system.

Strengthening emergency resilience in prioritised vulnerable countries through capacity building with local and regional responders is best to prevent suffering and loss of life in the aftermath of disasters.

Continued learning from responses, adapting programming to changing needs, and working within the international community to improve emergency response standards and coordination will lead to better future responses
.
Problem and barriers to resolution
Disasters cause suffering, morbidity and mortality. During a disaster local and regional response systems may be unable to respond because they are overwhelmed or because they lack capability. Support needs constant improvement and refinement to: set international standards for response, meet emerging needs, ensure efforts are not duplicated, ensure that those in need are targeted, and ensure they ultimately save lives and alleviate suffering of affected populations.
Main Programme Assumptions
That built capacity in country is retained so that it can be effectively used in the event of a disaster.

That evidence which can be generated through the programme is able to meaningfully shift the international system towards programme outcome and impact.

The UK is able to retain a menu of deployable medical and search and rescue teams held at a high level of readiness.

The UK is able to provide targeted technical assistance alongside maintaining response capabilities.

The UKEMT and UK ISAR teams’ expertise is requested for direct response and capacity building.

The UK is able to maintain an influential presence in international fora.

Quality feedback on deployment success / failure is able to be collated and reported.