## Sheet1
Statutory Homelessness Statistics - assessment requirements
The action plan for meeting the requirements set out in the recent Office for Statistics Regulation (the regulatory arm of the UK Statistics Authority) Assessment of the Statutory Homelessness Statistics. Details of each requirement, along propsed actions we intend to carry out are included below, as well as a target completion date for meeting each requirement. This will be updated with progress at each publication.

Public Value	Proposed actions	Target completion	Status
Requirement 1: To ensure that the statistics are useful, easy to access and support understanding of important issues, DLUHC should improve the clarity of the statistics’ main messages to help illustrate what the statistics show in terms of their value for answering key questions on homelessness, as well as their main strengths and limitations. DLUHC should also improve the accessibility of the current statistics package and website to aid navigation by a broader range of users, and so that the statistics can be appropriately accessed and interpreted.	We will review our current outputs, particularly the report to ensure key messages are presented more clearly, with a potential use of infographics to quickly glance at the key trends. We will also ensure clearer navigation between/within products. / We have drafted a 'How can it be used' and 'Things you need to know' section to be published as part of the publication in Summer 2022, similar to the Rough Sleeping Snapshot, which provides a clear steer on what questions can be answered through the H-CLIC statistics.	For the January to March 2022 publication in Summer 2022	In progress

Requirement 2: To ensure that users’ needs are fully understood, and their use of the statistics is supported, DLUHC should engage with a greater number and broader range of homelessness statistics users on an ongoing basis. DLUHC should review and update its user engagement strategy and set this out publicly, drawing on the updated GSS user engagement strategy. It would also be helpful for the team to update the GSS user forum web pages to include information of interest to a broad range of users of the statistics, beyond LA users.	We are developing a strategic user engagement plan to ensure ongoing contact/feedback from a broader range of users. We will engage with the GSS Good Practice Team in May 2022 to ensure our plan aligns with the GSS user engagement strategy. / We will review content on the GSS user forum to make it more accessible for a wider range of users.	Ongoing	In progess

Requirement 3: To realise the public value of the statistics and support the information needs of a broad range of users, DLUHC should ensure that users have opportunities to contribute to development planning; are aware in advance of developments being launched; and have opportunities to contribute their views on new developments once published. DLUHC should be clear and transparent in its communications about which user requests for further developments it plans to address, and those it does not, and the rationale for its decisions.	We will produce a development plan ahead of the upcoming 2021-22 annual release, with a view to publish and share this with our users. We will engage with the GSS Good Practice Team for advice on how best to engage with users and request feedback. / We will seek to get feedback from users ahead of upcoming developments, and publish responses to those we can/cannot address alongside a following publication	For the January to March 2022 publication in Summer 2022	In progress

Quality
Requirement 4: To enable all LAs to return data through H-CLIC, and to help drive improvements in the quality of the data returned, DLUHC should:
1. work with LAs that are unable to provide accurate H-CLIC data, including those not currently engaging with the team, to gain a better understanding of the specific barriers that they face, and overcome outstanding issues	We are working closely with DLUHC's Homelessness Advisory Service Team (HAST) and have developed a plan for engaging with LAs who have been unable to consistently submit H-CLIC data. We will ensure tailored approaches for specific barriers faced by LAs.	Ongoing	In progress
2. facilitate the sharing of best practice between LAs in terms of successful approaches to submitting data for those with similar IT systems, or those considering alternative systems, so that lessons can be shared more widely	We will engage with LAs to ask if they would be willing to be put in touch with others who use a similar IT system or one they may be interested in. We will manage this list internally, so that we can facilitate discussions between LAs using similar systems.	Summer 2022	Not yet started
3. review its assurances around the quality of data collected from LAs, including variability in quality across different variables, informed by engagement with LAs about their data quality management approaches, and the practice areas within the QAAD toolkit	We will review our quality assurance as a whole from the data collection to publication, looking at specific priority variables to have a more formal sense of variability in quality. We will engage with the GSS Data Quality Hub and reference the QAAD toolkit to ensure we are following best practices.	Summer 2022	In progress
4. publish a plan setting out its proposals and timelines for addressing 1), 2) and 3).	We will update this document at each publication to provide progress updates.	Ongoing	In progress

Requirement 5: To enhance user understanding on the quality of the statistics, DLUHC should expand the published information on data quality, in line with broader quality measures covered in the DLUHC quality strategy, and its learning from applying the QAAD toolkit, to include:
1. further information, in line with what was previously published on comparability between P1E and H-CLIC data, and the impact that removing P1E has had on data quality and the levels of imputation used, including on temporary accommodation figures	We will include information on the comparability of H-CLIC and the old P1E form and impacts of switching data collections.	Spring 2022	Completed
2. clarity around any limitations or quality issues identified through further engagement with LAs and from applying the QAAD toolkit, and how these have, or will be, addressed or mitigated	We will engage with the GSS Data Quality Hub for guidance on effective communication of limitations and quality issues. / We will complete a self assessment against the QAAD and resulting action plan for areas that need to be addressed/mitigated	Summer 2022	Not yet started
3. clear communication around the extent of uncertainty for different H-CLIC variables, and how these relate to the red, amber, and green dashboard quality indicators, to help to ensure appropriate interpretation and use.	We will ensure more coherent communication on quality in the technical note, linking to the quality measures in the performance dashboard.	Summer 2022	Not yet started

Requirement 6: To support users in the appropriate interpretation of the statistics, the team should provide:
1. clarity on when revisions are counted as scheduled or non-scheduled in line with what happens in practice	We will update technical note from the October to December 2021 publication to be clearer on scheduled/non-scheduled revisions	Spring 2022	Completed
2. clear information on how far back revisions are made, and the nature and extent of revisions, for example by providing a revisions table.	We will update technical note from the October to December 2021 publication to be clearer on exactly what revisions are made, how far back they go, and the average impact on the numbers.	Spring 2022	Completed