## Sheet1
Appendix A: Routemap - Complexity Assessments “We found striking patterns in the reasons for projects failing, which all related to the importance of understanding the delivery environment and complexity of the project when making a decision whether to proceed. Organisations which really understood the inherent challenges of their project were able to create an environment for success at the earliest stages of its design, while those which did not set themselves up for failure at a later stage.” The DECA: Understanding challenges in delivering project objectives - National Audit Office 2013 The complexity of your project may be assessed using the UK National Audit Office (NAO) Delivery Environment Complexity Analytic (DECA), which is set out below. The tool was written for public sector projects but is equally applicable to private sector projects. Helpful tips based on the most recent update of the Routemap modules have been added to the factor descriptions in italics. Most of these tips relate to sustainability (one of the cross-cutting themes running through all the Routemap modules) and systems integration (the topic of the new Routemap module published in 2021).
Number | Reference | Impact Statement Level 1 Complexity | 1 Low | 2 Med | 3 High | Impact statement Level 3 Complexity | Comments
1 | Strategic importance The extent to which the project supports delivery of the department’s objectives, the level of ministerial and wider public interest. Tip: You should consider whether the project supports delivery of national or regional policies, strategies and plans. For example, the UK’s National Infrastructure Strategy, UN Sustainable Development Goals and nationally determined contributions to the Paris Agreement. | ● Low Priority operational level project/programme. ● Expected benefits are necessary but low in value relative to organisation's/government's overall ambitions. ● Externally there is little political, media or public interest and failure would not have significant impact outside the organisation. |  |  |  | ● Critical to delivery of key strategy objectives or legal obligations, with very high expectation of benefits. ● High level political or public interest with strong media attention. ● Failure would have major impacts and consequences outside the organisation.
2 | Stakeholders/influencers The groups or individuals with an interest in the project and the level of influence they have on it. Tip: This may include project affected communities to be consulted on project design and development. | ● Low number of stakeholders or level of influence. ● Stakeholders are aligned with the business objectives, supporting the project and agreeing on the expected outcomes. ● Key stakeholders and influencers are unlikely to change. |  |  |  | ● Significant number of stakeholders with high levels of influence and differing or misaligned objectives/expectations. ● Stakeholders/influencers may change.
3 | Requirements and benefits articulation Are the sponsoring body and delivery team clear about their requirements and how these requirements will lead to the objectives being met? Tip: This should include the intended economic, environmental and social benefits and how these will be realised. | ● Requirements and expected benefits are clear and linked to business policy. ● Key performance measurements linked to goals, vision and values. |  |  |  | ● Ambiguity around requirements and how the expected benefits contribute to the realisation of the goals, vision and values. ● High uncertainty on project impact.
4 | Stability of overall context Will the requirements and environment remain stable for the foreseeable future? Tip: This may include the direction of public policy, for example relating to climate change, and its impacts on the target operating model. | ● Requirements, governance and delivery modes are clear and unlikely to change. ● No significant risk of change in scope, structure, external requirements or economic/political landscapes. ● High degree of confidence in planning, estimates and/or governance. ● Necessary approvals/investments already received or guaranteed. |  |  |  | ● High risk of scope, structure, external requirements or economic/political landscapes changing. ● Low level of certainty within key estimates, planning and/or governance. ● Uncertainty over whether necessary authorisations will be received.
5 | Financial impact and value for money How significant is the project financially to the sponsoring body/supplier and are the expected benefits proportional to the projected costs? Tip: This should include the economic, environmental and social benefits (including disbenefits) that may be realised beyond the scope of the project. | ● Investment is not significant relative to sponsoring body's capital expenditure, or comparable investments. ● Project/programme not material to key suppliers. ● Anticipated revenues, efficiencies or returns on investment are not fundamental to the business. ● High level of assurance over key estimates. |  |  |  | ● Investment is significant for the sponsoring body. ● Investment expected to deliver significant value for money, efficiencies or returns. ● Highly involved type/source of investment anticipated. Low level of assurance over key estimates.
6 | Execution complexity (including technology) How complex are the objectives to deliver, due to factors including technology, approach and tight timescales? How difficult is the project to deliver? Tip: Another important factor is the need to integrate multiple (new and existing) systems, and don’t forget that new technologies may emerge during the life of the project or the resulting asset. | ● No new or untested business practices or technologies form part of the scope. ● There is from end loading for phased implementation and piloting if required. ● Organisation or its partners has experience of all practices, key technologies and methods used. |  |  |  | ● New/untested business practices or technology required. ● Wide scope and challenging objectives with limited scope for risk management such as phased implementation or piloting due to immovable deadlines and demanding targets.
7 | Interfaces/relationships How many different bodies are involved in delivery? Tip: Don’t forget the bodies responsible for systems outside of the project control (for example transport systems, power systems, local natural habitats etc), but with which the project must interface effectively to successfully deliver. | ● Project/programme spans few boundaries (organisational, political and regional) and success is not dependent on relationships. ● Governance is not complex and supports decision-making and reporting. |  |  |  | ● Project/programme spans many boundaries with internal and external partners. ● Success is dependent on factors mainly outside control of the organisation and is dependent on relationship management. ● Governance is complex.
8 | Range of disciplines and skills Are specialist skills required for delivery, and are these available within the organisation? Tip: Examples might include ecological experts for sites of special scientific interest or social advisors for economic regeneration. | ● Delivery involves few specialist disciplines or skill requirements. ● Acquiring the skills for implementation is straightforward and readily available in the market. |  |  |  | ● Large number of disciplines and skills and/or potential for strain on the supply chain capability.
9 | Dependencies Is the work critical to the delivery of objectives elsewhere or dependent upon other projects for its own success? Tip: You should also consider whether the project is expected to contribute to shared outcomes and benefits, perhaps as part of a wider portfolio or system. For example, regional development goals. | ● Project/programme is not critical to delivery of other projects. |  |  |  | ● Project/programme is critical to the delivery of other projects.
10 | Extent of change Does the project/work involve a significant change in the way the organisation conducts its work, or is it business as usual? Tip: You may also need to consider the impact of change beyond the project organisation. | ● Business as usual. |  |  |  | ● Large amount of organisational change required to deliver desired outcomes and benefits. ● Delivery represents a fundamental change to the organisation.
11 | Organisational capability: performance to date Has the organisation demonstrated the capability and capacity to deliver its objectives? Has it learnt lessons from the past? Tip: Remember this includes success in realising the intended benefits, including economic, environmental and social benefits. | ● Demonstrated capability to deliver project/programme through delivery of similar successful projects/programmes. ● Culture promotes 'intelligent client' attributes. |  |  |  | ● Has not demonstrated key capabilities in delivering major projects/programmes and/or has not delivered under similar arrangements in the past.
12 | Interconnectedness How well does the organisation understand the links between the elements in its external environment, the complexity and its own capability? Tip: Don’t forget about the relationships between new and pre-existing built and digital systems, the natural environment, and the critical role of people in making these interactions work. | ● Consideration of the required alignment and relationships between policy, culture, practices, technology, people, processes and procedures. ● Interrelationships inform decision-making and risk management. |  |  |  | ● Consideration of the required alignment and relationships between policy, culture, practices, technology, people, processes and procedures has not been investigated, captured or communicated.