Levelling Up Fund – Round Two
Monitoring & Evaluation Teach-In

---
Agenda
Changes from LUF Round 1
What is Monitoring & Evaluation (M&E)?
Understanding the Intervention Being Evaluated
Establishing Your M&E Objectives
Evaluation Types, Approaches and Methods
Data
Governance and Resourcing
Use and Dissemination of Findings
Useful Links

---
1. Changes from LUF Round 1
There have been no substantial changes to the M&E section in the application form for LUF Round 2 – we still want applicants to set out what their plans are for monitoring and evaluation in relation to their interventions.
However, compared to Round 1, we have provided expanded M&E guidance for Round 2 which can be found in the LUF Round 2 Application Guidance and in the new Annex E in the LUF Round 2 Technical Note.

---
2. What is Monitoring & Evaluation (M&E)?
Monitoring is the systematic process of collecting, analysing and using information to track an intervention’s progress toward reaching its objectives1. It is an important part of effective management because it can provide early and ongoing information to help shape implementation in advance of evaluations2.
Evaluation is a systematic assessment of the design, implementation and outcomes of an intervention. There are three main types of evaluation: process, impact and value-for-money evaluations; each focused on answering different types of questions. For a full understanding of whether an intervention worked, how, why and for whom, and at what cost, all three types of evaluation are required3.
Monitoring and evaluation together can provide you with the necessary data to guide your strategic planning, to design and implement programmes and projects, and to allocate, and re-allocate your resources in better ways4.
A Monitoring and Evaluation (M&E) Plan is a guide as to what you should evaluate, what information you need, and who you are evaluating for. Depending on the detail of the M&E plan, you can identify the people responsible for different tasks, as well as timelines5.
1 UN
2 Better Evaluation
3 HMT Magenta Book
4 UN
5 Evaluation Toolbox

---
3. Understanding the Intervention Being Evaluated
The first step in any evaluation is defining and understanding the intervention, which should involve identifying and synthesising existing evidence and developing a Theory of Change.
Theory of Change
A Theory of Change should explain how the intervention is expected to work, the assumptions made, the quality and strength of the evidence supporting them, and wider contextual factors. An example Theory of Change can be seen on page 25 of HMT’s Magenta Book.
A key part of producing a Theory of Change is the synthesis of existing evidence. By bringing together and assessing the strength of existing evidence about the intervention, evaluators can begin to see where evidence is weaker. This can help to identify key questions the evaluation will need to answer.
Theories of Change can range from simple descriptions to more complex analyses. More sophisticated exercises produce a more detailed and rigorous assessment of the intervention and its underlying assumptions.
At a minimum, what we’re looking for in LUF Round 2 applications:
A well-evidenced Theory of Change, aligned with the intervention’s objectives, that sets out why the bid is likely to produce the expected outcomes and impacts
Source: HMT Magenta Book

---
4. Establishing Your M&E Objectives
The LUF M&E Strategy and Annex E in the LUF Round 2 Technical Note set out the UK Government’s approach to the national monitoring and evaluation of LUF, which has been shaped by a specific set of M&E objectives for the programme overall.
As the Technical Note states, LUF grant recipients will be responsible for their own local monitoring and evaluation. LUF interventions provide a unique opportunity for grant recipients to better understand what works in their local areas – it should not simply be seen as a tick box exercise. Applicants should carefully consider – and define – what they want to achieve from their monitoring and evaluation activities.
As the M&E objectives, and the overall M&E plan, should be proportionate and realistic, it is important for grant recipients to prioritise evaluation/learning/research questions that will provide the most value to them and their local area. Local M&E objectives need to take account of the requirements dictated by the national M&E – however, they may go beyond these requirements depending on what the grant recipient wants to achieve:
Grant recipients’ responsibilities as part of the national M&E
Grant recipients’ responsibilities as part of their local M&E
Clearly-defined M&E objectives, and evaluation/learning/research questions that you want to answer, with explanations for why these have been chosen

---
5. Evaluation Types, Approaches and Methods
Given your M&E objectives, you should identify the evaluation types, approach(es) and methods that will help meet these.
Evaluation Types
Process evaluation seeks to identify lessons from how the intervention was delivered.
Impact evaluation seeks to determine whether the intervention made a difference to outcomes/impacts.
Value-for-money evaluation seeks to determine whether the intervention was a good use of resources.
Evaluation Approaches and Methods
The most suitable evaluation approach(es) must consider the type of evaluation and question(s) to be answered, alongside an understanding of the intervention itself, the context in which it is being implemented and information/data available. For impact evaluation, typical approaches include experimental, quasi-experimental and theory-based approaches.
The methods for undertaking your evaluation must be considered in terms of their feasibility and appropriateness. For process evaluations, an example method is interviews and focus groups; for impact evaluation, an example of a quasi-experimental method is difference-in-difference analysis; for value-for-money evaluation, an example method is social cost-benefit analysis.
Further information on evaluation types, approaches and methods can be found in the Magenta Book.
An overview of the evaluation types and approaches that you have identified as being most appropriate for your evaluation, along with an explanation for why that is.
Source: HMT Magenta Book

---
6. Data
Data collection is an essential component of any evaluation and needs to be planned in advance. Without appropriate planning of data collection or data access an evaluation may be impossible, severely limited, or unnecessarily expensive.
The Theory of Change should, at the very least, identify the intervention’s inputs, activities, outputs, outcomes and impacts – and mapping these out will help identify what data needs to be collected. Applicants should refer to Annex B in the LUF Round 2 Technical Note for help in framing their outputs, outcomes and impacts.
Existing data from administrative and monitoring systems, or large-scale (long-term) surveys, are important sources for evaluation. Typically, new data collection and research is also required (and this should be budgeted for accordingly). It is important to note that baseline data – data collected before the intervention – will need to be collected early; and that comparison data – data from groups unaffected by the intervention – will also need to be collected.
Processes should be designed to maximise data quality and, wherever possible, evidence should be obtained to support the data.
The intervention’s inputs, activities, outputs, outcomes and impacts – identified in your Theory of Change
Potential sources of data for tracking these – with consideration shown for feasibility of collection, accuracy, etc.
Your strategy for collecting the data (e.g., who will collect it? When will it be collected? What supporting evidence is required?)
Source: HMT Magenta Book

---
7. Governance and Resourcing
It is crucial to set up effective governance structures at the beginning of an evaluation to ensure the evaluation is fit-for-purpose, can adapt to changing situations, has quality assurance and stakeholder buy-in, and can influence decision-making.
Resource requirements, both financial and human, need to be carefully considered and should not be under-estimated. Managing an evaluation requires both specialist evaluation skills and general project-management skills.
Different routes to conducting an evaluation are available: external, in-house or a combination of the two.
Regardless of the route chosen, you should ensure you clearly specify what is required of the evaluation to ensure its usefulness and quality.
Flexibility in the evaluation is often required and must be built into the specification and management processes.
Ethical issues need to be considered throughout.
A description of your governance arrangements and an explanation as to why these ensure accountability
A description of the resources (financial and human) that you have committed to your M&E
Your proposed route to conducting your evaluation, e.g., in-house or external, including timings
Source: HMT Magenta Book

---
8. Use and Dissemination of Findings
The value of an evaluation comes through its use and influence. Planning for this in advance will enhance the usability and use of evaluation outputs.
An explicit use and dissemination plan will ensure that all users and uses are captured, and that the outputs will be framed to maximise impact with these groups.
Monitoring and regular reporting can ensure that evidence is available to use in decision-making throughout the delivery of an intervention.
We expect all grant recipients to be open and transparent with their evaluation findings and materials to maximise the benefits to all. This includes underlying data and research instruments where appropriate.
The ROAMEF Policy Development Cycle – which shows how monitoring and evaluation play an important role before, during and after implementation
A description of your intended M&E deliverables and an explanation of why you have identified these as being most appropriate
An explanation of how you intend to use and disseminate your findings/outputs
A description of timings, including when findings will be available
Source: HMT Magenta Book

---
9. Useful Links
Magenta Book
HM Treasury guidance on what to consider when designing an evaluation.
Better Evaluation
A global collaboration aimed at improving evaluation practice and theory through co-creation, curation, and sharing information.
What Works Centre for Local Economic Growth
Has published evidence reviews and toolkits on impact of local economic growth policies, and can provide support to local policymakers undertaking impact evaluations.
LUF M&E Strategy
The Government’s high-level approach to monitoring and evaluating the Levelling Up Fund.
LUF Round 2 Technical Note – Annex E
Levelling Up Fund monitoring and evaluation guidance.
LUF Round 2 Application Guidance
Supports applicants from across the UK to complete their application.