Levelling Up Fund – Round Two
Project Deliverability
Funding and Government Commercial, Department for Levelling Up, Housing and Communities

---
Content
What has changed from round one?
.
2. What is the purpose of the deliverability assessment?
.
3. Financial case
.
4. Commercial Strategy
.
5. Management
.
6. Useful Links

---
Introduction
This presentation will explain the deliverability section of the application form and provide some helpful points to consider when completing this section. There are four key areas within the deliverability section that applicants are required to cover:
Financial case
.
Commercial approach
.
Management (Including governance and risk)
.
Monitoring & Evaluation
Please note: this presentation will focus specifically on 1 to 3 only, Monitoring & Evaluation will be covered in a separate presentation. Hyperlink access to this presentation can be found on the final slide below.

---
What has changed from round one?
We have made some minor changes to some of the questions within the application with the aim of encouraging applicants to provide more detailed information on how projects will be delivered.
We are keen to gain a better understanding of:
Who will lead on key activities, for example procurement, project management, etc within your team.
What role project partners will take in the project.
How funds will be structured and governed, where there are other beneficiaries involved in its implementation or the project involves complex structures amongst multiple partners.
We have also created new Excel Workbook Templates and guidance for fund profiling, project costings, and project plans.
Please note; there are now two Excel Workbooks:
     (1) for single site projects
     (2) package bids covering multiple site locations
WORKBOOK PAGE EXAMPLE

---
Purposes of deliverability assessment
The deliverability section focuses on all the key aspects of how you intend to deliver and implement your project including:
Project budget and costings – what the grant will fund?
.
Sources of other funding required to complete the project
.
Your approach to procuring and managing key supplier contracts.
.
Project activity and delivery plan, setting out key activities such as design, construction & build, and your timescales for completing your projects.
.
Your resource capability and project management including skills & experience in delivering large capital projects of this scale and nature.
.
Governance and risk.
PLEASE READ
>Application Guidance
>Technical Note
>Project Workbooks
Team
Risk
Budget
Plan

---
Purpose of deliverability assessment
How deliverable is this project?
A strong procurement strategy included – The bid clearly sets out sourcing options
Have all project risks been considered?
Project Partners are involved but it is unclear what role they are each taking in the project
Can this project be built and delivered by the required timeframe?
A descriptive budget has been included, it is clear how costs have been determined
Assessors
Some examples of what assessors are looking for

---
FINANCIAL

---
Financial
Match funding
Applicants are encouraged to contribute a minimum of 10% match funding. You are required to state how you intend to match fund the project in your response to Question 6.1.3 and with Table B of the Excel workbook. You are required to state the sources of your match funding and confirm the status in terms of it being fully committed or still to be secured. You are then required to profile the funding for each year. Your funding profile should correspond with your expenditure profile in Table C (Columns K to O). Assessors will be looking to see how you have profiled your funding to check it corresponds with information in your application and supporting information.
Evidence of match funding
Applications that provide evidence of match funding in the form of a commitment letter from other funders are considered stronger proposals. If you are intending to match fund using your own organisation funds, a commitment letter approved by your board, committee or equivalent will suffice. If there any funding conditions related to other sources of funding, please make these clear in your commitment letter. Match funding must be a new financial / monetary commitment associated with the build and construction of the project.
Funding gaps
Where you have yet to secure funding for your project, please make this clear in your application and outline what plans you will put in place to secure this, and state the timescales you anticipate that this match funding will be confirmed. Assessors are likely to score applications lower where funding gaps or timescales for securing funding have not been addressed.
Private sector project beneficiary
Should any private sector stakeholders (such as developers) stand to benefit from the project it is expected that a financial contribution should be made by this beneficiary towards the project costs.
Provision of land as match funding
Where the value of land is being contributed as match funding, applicants are required to confirm that an independent valuation of the land has been undertaken to verify the true market value of the land, and this must be confirmed in writing. The current ownership of the land and any restrictions on its use should also be set out in this letter.

---
Financial
Project costings
Applicants are required to provide a project budget in Table C of the Excel workbook. If you are submitting a package bid covering multiple sites, you will be required to provide a project budget for each project location.
Your overall budget should list all capital costs associated with the build and implementation of your project, clearly setting out what the grant will fund and what will be covered by any match funding. Stronger applications provide descriptive budgets making very it clear to assessors what is involved and how this corresponds with the rest of your application. Please remember that monitoring and evaluating how successful your project is will be a requirement, so please ensure you set aside a sufficient budget allocation to complete this activity.
Determining your project costs
Applicants that provide supporting comments or details of any market research or benchmarking activity you have undertaken to help determine project costs are likely to be considered stronger by assessors. You may have compared costs to existing projects or contracts you currently have in place or gathered recent market data or intelligence. If so, make this clear in your application. This demonstrates to assessors you have really thought through your budget and it has been developed specifically for need and requirements for each project that you are proposing. Where you have made assumptions please state this in your application. Your response to question 6.1.17 should correspond with your project budget/s. Please check that the accuracy of your budget, especially where you have inserted additional rows or columns.
What are ‘other or miscellaneous costs’ and why is the budget set so high?

---
Financial
Confidence of funding timeframe
We would expect all funding provided from the Fund to be spent by 31 March 2025, and by 2025-26 on an exceptional basis. Applicants are required to provide an expenditure profile in Columns K to O in Table C of the Excel Workbook. Assessors will consider the likelihood of grant funds being expended on time, and how you have profiled your funding commitment to the project.
Financial risks to the project
Stronger applications outline what potential financial risks there are to the project, setting out what mitigation measures will be in place to manage these risks. For example; how the likes of cost overruns will be managed or any external factors such as potential changes to price in materials or labour markets.
It is recommended that a risk register is provided with your bid that should set out the financial risks and how these will be managed across all projects. Consider how these risks could impact the delivery of your project/s.
.
“ Does your budget and plan allow for any potential financial risks, and these financial risks shared amongst all sources of funding? “
Quality
Cost £
Time
Scope

---
Financial
Project Partners and other grant beneficiaries
For projects that involve the disbursement of grant funds to other project partners (not supplier or contractors), applicants are required to declare this in Table G of the Excel workbooks. You should:
Include the name and address of all partners
State the role partners will take in the project and what the grant will fund or advise any benefit they are likely to gain from the project
Provide assurance that a robust legal structure will be in place amongst key partners, and where applicable, funding terms & conditions that will be/are agreed. (You may need to seek legal advice)
Consider Subsidy Control rules and ensure requirements are fully met.
Demonstrate that an adequate governance structure and financial due diligence is in place.
Show that robust budgeting and financial controls will be place – including traceability of grant funds.
Ensure that project funded assets are protected
Other complex structures such as joint ventures should be outlined clearly in your application and delivery plan.
Example: Sub-Granting Structure:
Sub-grant
Delivery Partner 2
Is the partnership structure clear?
Lead Grant Recipient
Sub-grant
Delivery Partner 1
Levelling Up Fund
£ grant disbursement
£ sub-grant disbursement

---
COMMERCIAL

---
Commercial
Procurement Strategy
Applicants are required to provide a procurement strategy supported by a project delivery plan that sets out the specifics for how you will research and engage with the supply markets and effectively award and manage any contracts for goods, works or
services to be funded by the grant.
What sourcing approaches have been considered and discounted?
What measures will be in place to implement and manage effective contracts with suppliers, to ensure that quality is delivered?
What approaches have been considered to minimise costs?
How will any potential supplier or supply chain risks be managed and mitigated?
How you will the market be tested to gain value for money?

---
Commercial
Things to consider:
Delivery
Pre-Market Engagement
Procurement
Scope and better understand your requirements
Research and gather information to know the current status and capability of the market/s
Engage with key stakeholders to support strategy and procurement plans
Warm up the market, give suppliers a better understanding of your needs
Help to understand how much it is likely to cost. Benchmark past/similar projects.
Stimulate innovative and sustainable solutions
Help inform and design specifications
Establish how long it may take and know potential lead times / potential tenders
Plan additional resource that may be required
How will you ensure value for money is obtained?
Choose the right sourcing approach proportionate for the value, complexity and level of risk
Open or restricted procedures
Consider use of frameworks
Who will lead on procurement?
Invite supplier submissions
Receive and evaluate
Award contract
Follow Public Procurement regulations
Ensure fair and transparent process
Record keeping of selection process
Governance & due diligence
Consider procurement timescales in project plan
How will you work and manage relationships with selected suppliers?
Who will lead and manage your key contracts?
Agree contractual terms & conditions – Will you need to seek legal support?
How will you mitigate and monitor supplier or supply chain risks?
Evaluate supplier performance.
Quality assurance measures.
Consider use of KPI’s
Risk Management
Ethical and Professional Standards
Compliance with applicable laws and regulations. (e.g. Modern Day Slavery).
Sustainability and Net Zero.

---
PROJECT MANAGEMENT

---
Project Management
Project Delivery Plan
Applicants are encouraged to submit a detailed Project Delivery Plan with their application. Under question 6.3.1 you are required to provide a summary of the your delivery plan. Assessors will want to see you have considered all major project activities in your plans, and it provides confidence that you will have the resource skills and capabilities to deliver the project and your timescales are made clear, and plans for each project have been well thought through.
Some things to consider when developing your delivery plan
Do you have communication plans for how will engage with project teams, partners, developers communities/residents etc.
What consultation have you completed or are you planning undertake with key stakeholders
Are key the phases or milestones of your project/s clearly set out in your plan and are your timescales realistic
How will manage and monitor the progress of your project
Provide details of your project team explaining roles and responsibilities – consider pen profiles for your core project team.
Have you set out your planning strategy confirming of any statutory approvals e.g. planning permission required or
      ownership or agreements for the land / assets involved in the project.
Have you included drawings, diagrams, designs for your project
See technical note for further guidance.

---
Project Management
Project Team
Applications that provide descriptive information about the core project teams delivering the project/s are considered stronger. You should make it clear what resource, skills & experience, and capabilities you have in place and what experience you (or project partners) have in delivering large scale capital projects of this nature.
Use of sub-contractors
If you have plan to use sub-contractors such as specialist support to lead on aspects of your project delivery please provide detail this in your response to question 6.3.4.
Capacity or skill gaps.
If you have any capacity or resource gaps, please explain how you intend to address these gaps in your application. Please ensure this activity is reflected in your project delivery plan and activity schedule. (for example recruitment process).
Leadership Team
Project Management
Procurement
Legal
Finance & Economists
Architects & Surveyors, Consultants
Have you addressed any skill or resourcing gaps?

---
Project Management
Project Activity Plan.
Applicants are required to provide Project Activity Plan. A simple template has been provided in Table D in the Excel Workbook. You can adapt or modify the template provided or you may insert your own plan or Gantt chart.
Assessors will be looking to see how descriptive your project plan is, and how this corresponds with the information provided in your delivery plan and
online application form.
Some points to consider:
Have you included all key project activities. Can the activities be packaged into project milestones?
Have you included enough time for design & planning?
Does your plan include sufficient time to sought approvals or sign off from internal, stakeholders, boards or committees?
Have you considered all RIBA construction phases?
Are your timescales realistic, have you built in any contingency?
Have you built in regular progress reviews including budget and risk reviews
WORKBOOK EXAMPLE
Will it meet the funding timescales?

---
Project Management
Project Governance
Stronger applications outline what governance frameworks will be put in place to govern the successful delivery of the project. This is strongly recommended where projects are following complex structures involving multiple partners, stakeholders, site locations. Consider:
Reporting and management structure with what oversight and involvement senior leaders will have.
Delegated authority procedures – for approvals, sign offs.
How will you ensure ethical and professional standards are followed by all parties involved
How will public funds and assets be protected
Record keeping for audit purposes and traceability of all funds
Quality control measures such as site inspections at key stages.
Policy and procedures – e.g. avoiding Conflict of Interests, fraud prevention, etc.
Project Risk Analysis and Risk Register
Assessors will be look to see if you have considered risk throughout the commercial and project lifecycle and if this has is supported by detailed risk register. NB: You are required to provide our own risk register. No template has been provided.
Stronger proposals demonstrate they have carefully considered all potential project related risks, not just risks that are associated with construction and build activities. Your risk register should correspond and compliment your governance framework and reporting structure. The responsibility of managing and monitoring risk should be shared and allocated appropriately.
Some example of other types risks to consider:
Staffing and resourcing,
Financial risks including fraud or financial error.
Environmental,
Health & Safety, including Covid.
Site access and security
Data management
All of the risks listed seem to be owned by Project Manager alone?

---
Useful Links
LUF Monitoring and Evaluation
Final presentation covering Deliverability Section.
Insert Link Here.
Construction Playbook
The Construction Playbook is a helpful guidance document aimed at public contracting authorities that applicants may find helpful in developing sourcing and contracting plans. https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/941536/The_Construction_Playbook.pdf
Sourcing and Consultancy Playbooks
Key policies and guidance for making sourcing decisions for the delivery of public services, including specific guidance on sourcing consultancy services.
https://www.gov.uk/government/publications/the-sourcing-and-consultancy-playbooks
Crown Commercial Services
CCS can offer help to public contracting authorities on sourcing construction contract, including helpful resource and access to procurement frameworks: https://www.crowncommercial.gov.uk/products-and-services/buildings/construction