## Mexico Third Annual Review

Title: Mexico Bilateral Prosperity Fund / Period of review: August 2020 – July 2021
Original Programme Value: £60 million		Review date: 20-25 September 2021
Programme Code: [AMP ID#] n/a	AMP start date: April 2017	New AMP end date: March 2022

Summary of Programme Performance
Year	2019	2020	2021
Overall Output Score	A	A	B
Risk Rating	Moderate	Moderate	Major

DevTracker Link to Business Case:	www.gov.uk/government/publications/prosperity-fund-mexico-programme
DevTracker Link to results framework:	TBC

## Women cycling in the newly installed cycle lane on Insurgentes Avenue, Mexico City. The temporary bicycle lane was made permanent following recommendations from the Future Cities Programme, supporting safe and sustainable economic recovery in the city (see para 46 on p 19 for more information). Credit: SEMOVI, Mobility Ministry, Mexico City

Following technical support and recommendations from the Future Cities Programme, 11,500 women were incorporated into Guadalajara’s city’s social fare scheme which included two free journeys on public transport daily and access to the bike sharing network. Credit: Future Cities Mexico Prosperity Programme

A. SUMMARY AND OVERVIEW

Description of Programme

The seismic impact of the pandemic on the UK economy resulted in the Government taking tough, but necessary spending decisions. As announced in 2020, the UK has moved to an Official Development Assistance (ODA) target of 0.5% of GNI. This has had an impact on UK international development programmes globally.

For the Mexico Prosperity Programme, that change led to an 85% budget reduction and an extensive review of priorities, contracts and activities between February and June 2021. Funding levels for each strand and for non-ODA work was only finalised in July. This Annual Review (AR) is based, therefore, on revised results targets and budget. The findings of this AR reflect a Programme in transition.

The Programme continues to focus on delivery of inclusive economic growth and poverty reduction in Mexico and on increased bilateral trade and investment between Mexico and the UK. It works in four areas or strands: Clean Energy, Future Cities, Financial Services, and Anti-Corruption and the Rule of Law (ACROL). The Programme was launched by the Foreign Secretary, Dominic Raab in August 2019, and was a central element of the UK-Mexico Partnership for Sustainable & Inclusive Growth (PSIG).

Summary supporting narrative for the overall score in this review

Since the last AR, two main contextual changes have taken place:

COVID-19.  This had an almost immediate impact on Programme outputs. There were delays in activities due to travel and other restrictions, and constraints on the abilities of Programme partners. It also affected a number of assumptions within the Theory of Change (ToC) given the changing the nature of poverty in Mexico.

Spending Review (SR).  The one-year SR announced in late 2020 came into effect in April 2021. COVID-19 deeply affected our resources for development work in Mexico resulting in reduced Programme activities. ACROL, for example, closed during the third quarter of the financial year (FY) while the other strands of the Programme will close in March 2022. The original end date was March 2023.

These changes continue to take place at the time of writing this AR. On balance, all strands were on their way to achieving 2021 milestones later this year, based on the updates made after the results of the SR were known.

The Programme’s overall score is B. This is based on taking the score for each strand and applying a weighting to it derived from the financial value of the strand compared to the total value of the Programme. Employing the figures below, 45% of Programme weighting is A; 19% is a B; and 36% is a C. Overall, this averages out to a B score where outputs moderately did not meet expectations.

Clean Energy score C – financial value of strand is 36% of total Programme budget
Future Cities score A – financial value of strand is 29% of total Programme budget
Financial Services score B – financial value of strand is 19% of total Programme budget
ACROL score A – financial value of strand is 16% of total Programme budget

Major lessons and recommendations for the year ahead

We have captured the results achieved between August 2020 and July 2021 and summarised a set of lessons and recommendations for future development work in Mexico.

Key lessons	Recommendations
Supplier contractual negotiations	Consider escalation with supplier’s FCDO Senior Relationship Manager to accelerate contractual negotiations. / Be agile – informal workplan approvals can be made to implement activity whilst contractual negotiations are ongoing. / Be ambitious yet realistic about timelines. / Seek contractual sign-off from London Commercial to speed-up process (typically, workplans for each new year of implementation are signed-off by Programme SRO).
Co-funding from other donors	In a reduced ODA context, seek-out co-funding opportunities to carry out key activity. / Where possible, continue engaging with other donors on a regular basis to help secure buy-in for potential collaborations.
Stakeholder engagement	Keep stakeholders up-to-date on changes and context via letters, emails, formal meetings or one-to-one conversations. / Highlight successes achieved to date and commitment to continue engagement via policy support and dialogue.
Resource capacity	Understand resource capacity constraints and prioritise accordingly. / Have a clear list of priorities going forward. / Be agile within the team to be able to provide support where needed, regularly or on an ad-hoc basis.
Secondary benefits (SBs)	Providing training and having secondary benefits-specific workshops ensured Embassy teams and implementing partners had an improved understanding of secondary benefits definitions and of how to help trigger them within each of the interventions. / Having a country-wide SB strategy leads to greater effectiveness. Define roles and responsibilities as part of that strategy. Include meaningful SB indicators in the Programme Theory of Change and logframe. / Incorporate UK expertise and speak to DIT colleagues when designing interventions. / Having the buy-in from management so teams in commercial and non-commercial teams work towards a common goal.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the Programme’s Theory of Change (ToC), including any changes to outcome and impact indicators from the original Business Case (BC).

The Programme Team (PT) updated the ToC in November 2020 as part of the Mexico Cycle 2 Evaluation. Though the updated version was prepared prior to the SR, it does take into account impacts from the pandemic and the evolving political economy in Mexico.

While the ToC impact statement has not changed, the PT did update both the outcome and intermediate outcome statements. These statements identify common outcomes between the four bilateral strands. The Programme was on track to meet the overarching impact (greater inclusive growth and reduced levels of poverty in Mexico), but given the SR budget reductions, the level of anticipated impact has also diminished.

The PT refined the ToC two times in 2021. The first time was in March prior to the cycle 3 evaluation. However, on instruction from London, that evaluation was cancelled. The second time was in July 2021 as a result of the SR.

The PT updated the Programme umbrella logframe in the autumn of 2020 to reflect the ToC amendments. It incorporates indicators from the individual strand logframes. All documents, at Programme and strand level, have undergone considerable updates over the last year (and since the development of the Business Case). However, this review did not consider the programme logframe for two reasons. First, the updated programme logframe fed from the strand logframes (updated in February/March 2021), which incorporated the recommendations from the Evaluation Cycle 2 and the previous Annual Review but did not consider the Spending Review outcome. Therefore, the programme logframe showed an outlook no longer true for the Programme. Second, the aim of the current draft of the Programme logframe was to gather feedback from the Evaluation Cycle 3 and the wider team in order to finalise it before the current Annual Review. This was not possible because Evaluation Cycle 3 did not take place due to the Spending Review outcome. The Programme logframe/ToC therefore remained as a draft version. For these reasons the review team considered that the strand logframes (updated in July 2021) were more suitable for this review.

During the second year of implementation, the Programme met many output and outcome level targets. Furthermore, several milestones (for all strands) were met or exceeded. All of the strands were on track to deliver their milestones for this year until the SR. As part of the budget reductions, milestones were amended in June 2021 to reflect reduced priorities.

Secondary Benefits (SBs)

The PT has addressed all seven SB recommendations made during the Cycle 2 Evaluation. Specific actions taken can be found in the following document: Addressing Cycle 2 Recommendations. These include: 1) trainings and workshops on secondary benefits, 2) creation of opportunities and impact trackers, 3) language usage reviews, 4) developing a strategic approach, 5) defining roles and responsibilities.

In addition, the Embassy recruited a SB Adviser in August 2020 to support implementers and Embassy teams on securing commercial wins. Led by the new SB Adviser, the Programme developed a Mexico-wide Secondary Benefits Strategy, Theory of Change and Logframe. Despite this progress, the SR resulted in an 85% reduction of non-ODA resources and the corresponding ability to pursue commercial opportunities.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The original outcomes and impacts at Programme and strand-level will not be achieved due to the SR reductions and, as the Programme closes in March 2022, no new action is planned. However, each of the strands did achieve several intermediate outcomes and the paragraphs below give a flavour of what our partners think.

Financial Services

The Platform for the National Inclusion Policy (PNIF) was launched at the last Strand Governance Board (SGB) meeting. A representative from Mexico’s Central Bank, commented that “this platform is innovative and dynamic, the population will benefit from it as this is a great example of financial inclusion for individuals”.

ACROL

ACROL helped improve the way crimes are investigated in Mexico. During the last SGB meeting, a representative from the Attorney-General’s Office of the state of Tabasco highlighted that thanks to the ACROL programme, “Tabasco state now has a more efficient law enforcement institution”.

Future Cities

Stakeholders from different cities recognised that the Future Cities strand "is highly relevant given the technical support it has provided to local institutions to develop high-impact strategic projects to reform city management”. Our Programme partners consider that the added value of our interventions are the “innovative solutions to complex problems, for example the data management to promote inter-institutional coordination that facilitates decision-making, in addition to being able to offer a public information platform to anyone who requires it in terms of mobility”.

Clean Energy

Key stakeholders from the strand have defined our collaboration as a key tool to learn how to improve the processes of the security, energy and environment authorities (ASEA by its acronym in Spanish). From their perspective, “the Clean Energy activities will allow ASEA staff to get an international certification and contribute to the development of the Agency in a safe environment, whilst performing their responsibilities in conditions that allow them to face current challenges and achieve Mexico’s goals to reduce carbon emissions”.

Secondary Benefits

In 2020/21, Prosperity export wins totaled £12.7m. Future SBs are difficult to calculate at this stage though we continue to pursue several promising areas where UK companies should benefit in the medium to long term. However, due to the pandemic and SR funding delays, we are likely to see limited commercial benefits in the remainder of the 2021/22 FY.

Our non-commercial SB work, such as soft power and network effects, should lead to commercial impacts in the medium to long term. For example, the support we have provided in modernizing regulations is opening new markets and strengthening strategic commercial relationships.

The Prosperity Programme has helped make the UK a Partner of Choice for Mexico in many instances. Some examples include one of the largest banks in Mexico enquiring about the UK offer in Open Banking; CFE expressing their interest in mini-hydro models; and the Ministry of Public Function (SFP) requesting support with drafting a Whistleblower Protection Act for corruption cases.

There are many cases demonstrating the value of partnership with the UK as fostered by the Prosperity Programme. Some of these include i) Puebla Energy Agency requesting technical information on our Waste to Energy projects and ii) CNBV writing to thank us for support on the fintech law, their anticorruption and cyber-security work, development of their SupTech projects, and support with their Inclusive Finance Policy.

Our relationship building work has also been beneficial to other Embassy teams. The COP26 team, for example, has obtained access to decision makers in many high level institutions, including the renewables section at CFE, ASEA, the CNBV, Banxico, Fiscalias and SEMOVI, as well as to numerous state-level governments, municipalities and cities across Mexico thanks to the Prosperity Programme.

The above are clear examples of soft power where Prosperity-funded work created positive perceptions of the UK. They open the door for future, mutually beneficial collaborations in the political, economic and commercial spheres.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The Programme closes on 31 March 2022.

## C. DETAILED OUTPUT SCORING

Clean Energy

Output Title	Establishment of 3 primary interventions to increase the skills of male and female workers to meet industry demand
Output number:			1a	Output Score:				C
Impact weighting (%):			45%	Weighting revised since last AR?				Same

Indicator(s)		Milestone for this review / (Y2 -2020) / (Sept 2020-Aug 2021)			Achieved against Milestone		Cumulative Results		Progress
Number of women and men taking a training course		250			127		218 / 610		53% of target met. Off Track. During 2021 the strand has implemented nine activities with 127 participants have taken a training course. The target for women’s participation 188 participants, but only 65 had been trained by this milestone.
Number of courses taken per person (average)		1.2			1.7		1.45 / (average)		Exceeded. 96% of the participants considered the training courses met their expectations and took more than one course to expand their professional knowledge.
Number of training programmes provided on-site and online		13			9		13/16		Off Track The strand scheduled 17 online iterations in 2021. To date, nine online courses had been successfully delivered.
Number of women taking mentorships		20			11		22/31		Off Track. The supplier is developing different mentorship formats. For 2021, the strand has established three iterations with this purpose: two iterations for the Access to finance and Procurement, and the Linking SMEs with financial services event.

Output Title	Establishment of the SMEs primary intervention to increase their capabilities to meet industry demand
Output number:			2a		Output Score:					C
Impact weighting (%):			45%		Weighting revised since last AR?					Same

Indicator(s)		Milestone for this review (Y2 -2020) / (Sept 2020-Aug 2021)					Achieved against milestone			Cumulative Results		Progress
Number of SMEs trained		45					34			60/65		Off Track. The strand scheduled eight courses to support SMEs and help them improve their skills. To date, six iterations have been delivered.
Number of SMEs registered in the Centre Systems (SRP)		40					0			6/60		Off Track. The strand will promote the supplier Registration Portal in the courses to create business linkages between local suppliers and buyers (operators and primary contractors).
Number of SMEs participating in mentorships		40					6			12/40		Off Track. In 2021, the strand scheduled three mentorships for SMEs. The “Linking SMEs with Financial Services” event delivered in April had the participation of six SMEs, the Energy Efficiency and Access to finance course is scheduled for July-September and October, respectively

Output Title	Establishment of partnerships within relevant government institutions that promote continuous improvement
Output number:		3a	Output Score:	B
Impact weighting (%):		10%	Weighting revised since last AR?	Same

Indicator(s)	Milestone for this review / (Y2 -2020) / (Sept 2020-Aug 2021)	Achieved against milestone	Aggregated target	Progress
Number of government officials that receive training (tailored training)	20 / (new 2021 indicators)	0	0 / 20	Delayed but on track. In the last quarter of 2021, the strand will deliver a government official tailored course. The course aims to certify Energy and Environment Agency regulators in the global certifications on Health, Security & Environment ISO 14001 and ISO 45001. Also, the strand is planning to provide a training course to the Federal Electricity Commission on mini-hydro technologies.
New 2021 indicator - Number of government officials that receive training (EPI course)	15	26	26 / 15	Exceeded. Government officials have shown interest in EPI courses. So far this year, 26 regulators had participated in five out of nine courses delivered.
New 2021 indicator - Number of different government institutions that receive training (tailored training)	1	0	0 / 1	Delayed but on track.. In the last quarter of 2021, the strand will be delivering a government official tailored course.
New 2021 indicator - Number of different government institutions that receive training (EPI course)	3	9	9 / 3	Exceeded. 26 regulators from nine, national and local, institutions had participated in at least one course.
New 2021 indicator - Number of tailored courses delivered to government institutions	1	0	0 / 1	Delayed but on track.. In the last quarter of 2021, the strand will be delivering a government official tailored course

Output Title	Secondary Benefits - New 2021 output
Output number:		4	Output Score:	C
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone for this review(Y2 -2020) / (Sept 2020-Aug 2021)	Achieved against milestone	Aggregated target	Progress
New 2021 indicator - Number of UK technical and vocational institutions (UK experts) consulted in course design and/or implementation	2	0	0 / 2	Delayed but on track. For the 2021 last quarter implementation, two UK companies are considered to participate as speakers in the Energy Efficiency basics and the Energy Efficiency advanced course.

This strand is off track and has been impacted by a multitude of changes forced on the Programme relating to the external environment. The first of these was that during inception this output needed to shift to supporting clean / renewable energy markets due to a UK policy change on fossil fuels. The second change forced on this output was the need to adapt the Programme to the global pandemic – altering the method of delivery of training courses to online only, but also adapting the training modules to build SME resilience. The latest change has been a budget reduction for this output, but it is important here to note that a linked impact is the time taken to reach a decision on UK budget resource available which has delayed the start of several activities in this reporting period.

During the period of August 2020 to July 2021, due to COVID-19 the strand adapted all the curricula to online delivery, which resulted in expanding the geographical scope to 16 states. The strand also went through the SR process from February to July 2021. This required the development and approval of two costed work plans and budget scenarios to adapt the strand while maintaining the core objectives with a VfM perspective. It also required the redefinition of the strand’s outreach strategy. The strategy now consists in reaching participants through internal communication means and external stakeholders’ collaborations. This strategy is being used to promote different EPI courses and, through stakeholder engagement, reach more beneficiaries.

The workforce intervention (intervention 1) trained 223 energy sector professionals through eight EPI courses. In addition, EPI has been working on creating a Big-Data analysis of the labour market in renewable and clean energy jobs in Mexico.

The SMEs intervention (intervention 2) provided training to 34 SMES in business skill-up by the New Business Opportunities and Supply Chain Development Colloquium and the Access to Finance and Procurement course. The strand developed two courses specifically designed for SMEs aiming to identify new business opportunities and increase their resilience. Furthermore, this intervention developed specific mentorships for some of the trainings for SMEs and workforce. These mentorships aim to provide advice to workforce and SMEs on specific topics on their professional careers or business.

For the Regulators intervention (intervention 3), EPI has been designing a training proposal, based on the gaps identified, in Health, Safety and Environment with a complement of soft skills for the Safety, Energy and Environment Agency (ASEA). Moreover, the strand promoted and coordinated a Memorandum of Understanding (MoU) signature between the British Embassy and Jalisco's Energy Agency (AEEJ, by its acronym in Spanish).

The strand also developed a new strategy for SBs (February 2021). The new strategy considers establishing new indicators and causal pathways (ToC), which focus in the engagement of UK companies with local SMEs and local stakeholders. For example, for the ASEA course a UK firm is considered as the potential supplier. This activity could strengthen the links between British and local companies in the energy industry.

In terms of gender and inclusion (G&I), 54% of the workforce participants are women and 48% of the regulator's participants are women. Furthermore, 30% of the participants earn less than 14 GBP per day. The strand has a clear definition of the vulnerable populations it aims to target, which has helped to focus certain activities on women. Thus, in terms of equity the benefits are being fairly distributed.

The strand started implementing five[1] activities (March 2021) related to the COVID-19 response. The aim is to provide support on the recovery of SMEs under critical topics (industry identified). Some activities have already had first iterations, which have benefited around 150 participants. Each activity seeks to benefit on average around 35 SMEs (~450 participants) in further iterations.
[1] COVID-19 activities: 1. Linking SMEs with financial services in response to COVID-19 pandemic, 2. E-commerce and digital marketing, 3. Crisis management for SMEs, 4. Digital tools to provide SMEs with mental health support in the context of COVID-19, and 5. Energy Efficiency awareness workshop for SMEs in response to the COVID-19.

Finally, the strand’s activities evolved and were adapted to align with the Paris Agreement and support the International Climate Fund (ICF) and COP26 activities. The strand has activities and results specific to clean energy and transition to low carbon economy. For instance, 91 participants (from all interventions) learned how to reduce fossil fuels and foster renewable energy and energy transition projects.

Although this strand of the Prosperity Programme has significant potential to bolster the clean energy market in Mexico by directly supporting the emerging SME industry, workforce and regulatory supervision by the Government, it is unlikely to achieve its desired outcome unless funding is increased for its final year. Given the number of changes forced on this strand and the delay in results as a consequence, there is a need to reassess whether it is value for money to continue with this strand in this Programme.

The inclusion of a separate secondary benefit output for this Programme was a great step forward in this year and represents a better articulation of the business case objectives. Whilst secondary benefits indicators are included in the outputs of other strands, it may be better to bring these out as separate outputs for the next review.

Future Cities

Output Title	Develop and deliver recommendations that aim to improve the governance and management of mobility in Mexican cities, including recommendations that address the basic and practical needs of vulnerable groups, including (but not limited to) women and girls
Output number:		1	Output Score:				A+
Impact weighting (%):		50	Weighting revised since last AR?				Same

Indicator(s)	Milestone for this review / (Y2 -2020) / (Sept 2020-Aug 2021)			Achieved against milestone		Aggregated target		Progress
Number of recommendations (strategies or agreements) that aim to improve transport governance and management prepared for consideration by the relevant Authority	3			42		45/3		Exceeded. Intervention 1 projects delivered multiple recommendations for integrated transport strategies: 9 in Mexico City, 7 in Monterrey, and 5 in Querétaro.
Number of stakeholders consulted regarding recommendations	9			188		296/9		Exceeded. Project teams continued interacting with external stakeholders through technical meetings. So far the strand has interacted with 188 stakeholders through technical meetings and interviews with diverse stakeholders, including academia, intergovernmental organisations, civil society organisations, federal, state and municipal authorities and transport authorities.
Number of deliverables (e.g. knowledge products, training, events) that support the capacity of authorities and others to improve mobility governance and management with respect to inclusivity	2			3		19/2		Exceeded. In October 2020, the strand delivered a short business case regarding gender parity in the public transport workforce. / In addition, the strand organised a roundtable with city stakeholders specifically focused on metropolitan coordination of gender policies with a focus on mobility.
Number of deliverables (e.g. knowledge products, training, events) that support the capacity of authorities and others to improve mobility governance and management with respect to climate mainstreaming	1			0		12/1		Exceeded. The strand delivered 3 deliverables. It organised a training workshop called “Deep Dive: Green Bonds for Cities”, also organised a roundtable with local stakeholders specifically focused on metropolitan coordination of environmental policies and facilitated a meeting between the Nottingham City Council and SEMOVI to discuss benefits and opportunities of introducing a workspace parking levy.
Number of recommendations (strategies or agreements) that aim to improve transport governance and management prepared for consideration by the relevant Authority that have considered climate mainstreaming	1			0		13/1		Exceeded. The strand delivered 4 recommendations. First, it provided Mexico city with indicators to recognise performance and cost differences based on the type of fuel and emission standards that public transport buses use, the city of Monterrey received a conceptual design for the Mobility Management Centre (CGM in Spanish) and a list of implementation strategies that incorporate a comprehensive C&R approach in their components and delivered a list of suggested sub-commissions, including one on metropolitan environmental policies,

Output Title	Identify and develop delivery plans* for practical mobility solutions in pilot cities, prioritising those that support inclusive, safe and sustainable mobility, particularly for vulnerable groups, including (but not limited to) women and girls
Output number:			2	Output Score:				C
Impact weighting (%):			40	Weighting revised since last AR?				Up

Indicator(s)		Milestone for this review / (Y2 -2020) / (Sept 2020-Aug 2021)			Achieved against milestone		Aggregated target		Progress
Number of potential pilots identified that have a particular impact on women, girls and other vulnerable populations		0			1		6/5		Met expectation. A new target has been established to be achieved by the end of March 2022. The Women in Mobility project is currently working to identify potential pilots focusing on micro-mobility targeted at women.
Number of stakeholder groups engaged during pilot identification		0			0		15/15		Met Expectation. A new target has been established to be achieved by the end of March 2022. It will be reviewed in September 2021 against the new work plans and updated accordingly. The Women in Mobility project is currently working to identify potential pilots focusing on micro-mobility.
Number of delivery plans delivered to city authorities for practical mobility solutions.		1			0		16/4		Exceeded. The strand delivered 7 plans. During the first year of implementation, 5 pre-feasibility studies were delivered for Mexico City, Guadalajara and Hermosillo. Then shortlisted to 3 pilots to take on to the next stage. The final deliverable for the feasibility phase was delivered in / December 2020. / In September 2020, a diagnostic to serve as a basis to study and design a social fare policy for public transport was delivered to Guadalajara.
Number of delivery plans delivered to city authorities which meaningfully incorporate disadvantaged groups’ views into the consultation and design		1			0		1/2		Delayed so not met. The Women in Mobility project is currently working to identify potential pilots focusing on micro-mobility targeted at women.
Number of stakeholders engaged during mobility solution development		30			0		42/60		Delayed / substantially did not meet expectation. As the Finebus (BANOBRAS), Green Bus Stops and Women in Mobility projects begin implementation, they will start engaging with authorities and other stakeholders to develop solutions and recommendations. This target is to be achieved by the end of March 2022. It will be reviewed in September 2021 against the new work plans and updated accordingly.
Number of deliverables (e.g. knowledge products, training, events) that support the capacity of authorities and others to improve mobility solutions with respect to inclusivity		1			0		7/1		Delayed so not met in this year. This target is to be achieved by the end of March 2022. It will be reviewed in September 2021 against the new work plans and updated accordingly.
Number of deliverables (e.g. knowledge products, training, events) that support the capacity of authorities and others to improve mobility solutions with respect to climate mainstreaming		1			0		2/1		Delayed so not met. This target is to be achieved by the end of March 2022. It will be reviewed in September 2021 against the new work plans and updated accordingly. The Green Bus Stops and Finebus (BANOBRAS) projects will likely be able to advance this indicator throughout delivery.
Number of delivery plans delivered to city authorities that have considered climate mainstreaming		1 / (new indicator)			0		13 / 1		Delayed so not met. This target is to be achieved by the end of March 2022. It will be reviewed in September 2021 against the new work plans and updated accordingly. The Green Bus Stops and Finebus (BANOBRAS) projects will likely be able to advance this indicator throughout delivery.

Output Title	Raising awareness of potential export opportunities linked to the programme for UK and international companies
Output number:		Secondary Benefits			Output Score:				B
Impact weighting (%):		10			Weighting revised since last AR?				Same

Indicator(s)				Milestone for this review / (Y2 -2020) / (Sept 2020-Aug 2021)		Achieved against milestone		Aggregated target		Progress
Number of showcases or events (e.g. trade presentation, video demonstration, company roundtables, communication materials) or reports to raise awareness of potential export opportunities organised with non-ODA funds				3		3		7/7		Met. 2 events held and 1 report submitted
The number of engaged participants in activities delivered for knowledge exchange between UK organisations / experts and Mexican authorities				10		0		44/40		Delayed so not met. This target is to be achieved by the end of March 2022. It will be reviewed in September 2021 against the new work plans and updated accordingly. For example, the UK Behavioural Insights Team is currently supporting the implementation of the Women in Mobility Project. The Project 5 team is planning on organising a virtual event in QR-9 on market participation with national and international companies that can provide relevant technological solutions to the pilot. The participation of companies with establishment or financing in the United Kingdom will be sought.

On the whole this has been an impressive strand of the Prosperity Programme realising innovative urban planning projects in Mexico City, Monterrey and Queretaro, with project preparation in the form of feasibility studies completed in Mexico City, Guadalajara and Hermosillo. Engagement with local authorities in each of these locals has been impressive. As impressive has been the level of involvement in transferring knowledge and expertise from UK institutions and local authorities – for example from Glasgow City Council, Nottingham City Council, Transport for London and Transport for Greater Manchester.

The Future Cities strand is in its second year of implementation. The strand continued to operate across five cities with two intervention areas. As with the other Prosperity Programmes, the Future Cities strand underwent an SR process in March 2021. This resulted in pausing most of the project activity and developing updated work plans (agreed at the end of July 2021). Project activities recommenced in August 2021, with two areas: responsible closure activities and the launch of three new activities. Due to the pause on project activities until final decision on budget allocation was made, a number of output indicators were delayed and agreed to be realised by the end of March 2022.

Intervention 1 projects delivered the first recommendations to the cities since the start of implementation. Intervention 1 projects delivered multiple recommendations for integrated transport strategies: nine in Mexico City, seven in Monterrey, and five in Querétaro. This intervention has engaged with different stakeholders such as academia, intergovernmental organisations, civil society organisations, federal, state and municipal authorities and transport authorities, to get their feedback and recommendations and find potential synergies to collaborate.

Furthermore, Queretaro Intervention 1 has worked to support the capacity of authorities to improve mobility governance and management with respect to inclusivity. In Monterrey, the city received a conceptual design for the Mobility Management Centre and a list of implementation strategies that incorporate a comprehensive C&R approach in their components.

Intervention 2 delivered five pre-feasibility studies (for Mexico City, Guadalajara and Hermosillo). The strand delivered a diagnostic to the Guadalajara authorities, which served as a basis to study and design a social fare policy for public transport. The intervention is currently working on the conceptual design for the technology and infrastructure components of the safe bus stops in Guadalajara.

Some of the Intervention 2 activities were paused as a result of the pandemic (some at request from cities) and will no longer continue under the new work plans. Some other activities have not had progress as the strand was still in an early stage of implementation. However, the strand has been engaging with authorities and stakeholders to start developing tailored solutions and recommendations and to gather feedback.

In terms of SBs, in June 2020, the strand facilitated a knowledge-sharing workshop between SEMOVI and Nottingham City Council on the implementation of a workplace parking levy. Connections were made between the Nuevo León state government with Transport for London (TfL), Glasgow City Council, Ascendal and Citymapper to exchange lessons on the implementation and operation of mobility data management. Moreover, the strand facilitated a city-to-city experience (to share good practices, recommendations and lessons learned) between teams from Transport for Greater Manchester and the Transport Institute in Queretaro.

Through the Agile Programming Fund (APF), the strand conducted several activities in each intervention. Those activities considered providing technical support to facilitate mobility while containing the pandemic. Furthermore, it considered mainstreaming G&I strategies and briefing on the impact of Covid-19 on the mobility of women and vulnerable groups. APF Covid projects also incorporated Climate and Resilience (C&R) considerations and green financing opportunities for the development/expansion of public transport.

The strand continued with its G&I mainstreaming strategy (up to March 2021). Examples include webinars highlighting impacts of Covid-19 on women’s mobility, writing a business case for gender parity in the public transportation workforce and creating a survey to understand end-users needs and perspectives in Mexico City. The strand has also strengthened considerations of G&I in the design of Monterrey’s new Mobility Data Management Centre, engaged civil society organisations for Queretaro’s new municipal governance structure, supported the design of a gender and mobility event in Guadalajara and mainstreamed gender indicators across SEDATU’s (Secretariat of Agrarian, Land, and Urban Development) new regional impact evaluation tool. These activities show the strategy the strand has followed to maintain equity in the work that has been done.

Finally, the C&R vision of the strand has been updated this year. This new vision focuses on contributing to decarbonising the transport system in Mexico whilst building the resilience of the system to future changes in climate. The new workplans strengthen this with three new projects. Furthermore, there are key project where climate has been mainstreamed. For instance, the Monterrey Mobility Data Centre sustainability strategy was reviewed in order to include climate and sustainability requirements into the infrastructure policy.

Going forward the Programme needs to take stock of its unexpected success in addressing strong demand from Mexican local authorities for UK expertise, and adjust logframe indicators to be more stretching. However with the budget cuts to this Programme in play this may be simply have to be recorded as no longer feasible.

Financial Services

Output Title	An HCD financial education programme to build financial capabilities in vulnerable and poor young adults for the foundations of provisional savings
Output number:		1	Output Score:	C
Impact weighting (%):		30	Weighting revised since last AR?	Down

Indicator(s)	Milestone for this review (Y2 -2020) / (Sept 2020-Aug 2021)	Achieved against milestone	Aggregated target	Progress / *In progress Intervention 1 activities have been transferred to Amafore and these indicators could be updated depending on the information sharing agreement
Number of institutions receiving HCD financial education	2	1	1/2	Delayed so not met. In April 2021 the first train of trainees workshop began with CONALEP. As a result of the Spending Review this intervention was closed and transferred to AMAFORE.
Level of satisfaction from training programmes	3.4	0	0/3.4	Delayed so not met. It is expected that AMAFORE ask about the level of satisfaction at the end of the educational circuit of AhorrandoAndo. This activity will depend on the agreement signed between AMAFORE and the BE.
Number of male and female receiving behavioural design financial education interactions	1200	119	119 / 1200	Delayed so not met. In April 2021, 119 vulnerable young adults, CONALEP students, received the first virtual module of HCD financial education interactions.
Number of international (including UK) experts engaged in supporting HCD methodologies for strengthening financial inclusion and safeguarding users' transactions	6	6	12 / 8	Met before transferring I1 implementation to AMAFORE, relationships were initiated with international stakeholders related to HCD financial education. (42, BFA, IDB Invest, IFC-WB, CGAP and UK Public Health Rapid Support Team).
Number of associations and institutions that will establish relationships with the British Embassy as a result of the intervention	4	4	8 / 6	Met. During the first quarter of 2021. CONDUSEF and the General Direction of Access to Financial Services of the CNBV also established a relationship with the programme and the BE, participating in some of I1 activities.

Output Title	Rollout of regulated open API standards for data sharing within the Mexican Financial Services Sector that empower consumer choice for men and women.
Output number:		2a	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	Same

Indicator(s)	Milestone for this review (Y2 -2020) / (Sept 2020-Aug 2021)	Achieved against milestone	Aggregated target	Progress
% of standards in the secondary regulation issued influenced by international best practice	100%	100%	100% / (average)	Met. No standards will be published in 2021. However, during 2019 and 2020, Open Data secondary regulation and ATM API standards (data dictionary, architecture, and security guidelines) were published.
Number of international (including UK) experts engaged in the provision of professional services for Open Finance	4	4	7 / 7	Moderately did not meet expectation. In 2021, Open Banking Delivery (UK) expert has being engaged in the provision of professional services for Open Finance. This engagement came from the partnership between IDB and the FSP. However, the partnership has not being signed yet due to slow progress with the regulators.

Output Title	A fintech-focused supervisory technology solution for regulators (SupTech/RegTech) to enable efficient reporting and reduced compliance costs.
Output number:		2b	Output Score:				C
Impact weighting (%):		15	Weighting revised since last AR?				Same

Indicator(s)	Milestone for this review (Y2 -2020) / (Sept 2020-Aug 2021)			Achieved against milestone		Aggregated target		Progress
Percentage of fintechs and banks submitting regulatory reports based on suptech/regtech solutions	30%			0		0% vs 30% / (average)		Off track. The platform for submitting regulatory reports is not ready yet. (the development of it is responsibility of CNBV). It is expected to be completed in March 2022, so results would be available until then.
Degree of progress of Fintech basic analytics capabilities of the SupTech platform	80%			35%		35% vs 80%		Off track. The progress made by July 2021 corresponds to efforts in developing the method and the information security controls. The project is expected to reach the milestone in December 2021.
Number of international (including UK) companies engaged in providing SupTech/RegTech solutions for automated reporting and compliance	1			1		1		Met. A UK company, worked to diagnose the SupTech platform.

Output Title	A functional regulatory sandbox environment for innovative Fintechs to safely test their products and services.
Output number:		2c	Output Score:				C
Impact weighting (%):		10	Weighting revised since last AR?				Same

Indicator(s)	Milestone for this review (Y2 -2020) / (Sept 2020-Aug 2021)			Achieved against milestone		Aggregated target		Progress
Number of projects submitted to the National Securities and Banking Commission seeking to test their products and services through the sandbox	5			3		4 / 11		Off Track. The companies that presented their project to the CNBV as of July 2021 are three
Number of innovative models receiving technical assistance to participate in the regulatory sandbox	14 / (new indicator)			6		12 / 20		Off Track. There were six Fintechs that received technical assistance. In 2021, the FSP was unable to continue many of these activities as a result of the SR and the pending approval of the Costed WP Y3. For this reason, the implementation of SBCH 2.0 was postponed until 2022. The results of the 8 potential winners (6 will seek entry to the CNBV Sandbox and 2 to the CONSAR Sandbox) will be known in the last quarter of 2021.
Level of satisfaction of Fintechs that received technical assistance in the process for applying to the Mexican regulatory sandbox	3.3			0		3.4 (average)		Off track. In 2021, this indicator cannot be reported on due to the budget cuts derived from the SR.
Number of international (including UK) start-ups engaged in the authorisation process through the Mexican regulatory sandbox	2			1		1 / 2		Not Met. The first international start up, a UK company, has being working on its authorisation file as July 2021. A second one decided not to continue with the development of its file.

Output Title	A programme for Fintech companies to support deployment of different solutions that empower MSMEs and vulnerable male and female individuals.
Output number:		3	Output Score:	A
Impact weighting (%):		35	Weighting revised since last AR?	Same

Indicator(s)	Milestone for this review (Y2 -2020) / (Sept 2020-Aug 2021)	Achieved against milestone	Aggregated target	Progress
Number of states participating in the Fintech Caravan (CF)	5	2	4/7	Off Track. In 2021 there were approaches with the government and the private sector of Jalisco, but it has not been possible to implement activities as a result of ODA cuts to this programme. With potential collaboration with GIZ, 2 other states may be selected where face-to-face activities will be carried out.
Number of Fintechs participating in the CF activities	5	5	8 / 8	Met. A total of 5 Fintechs will participate in the national CF activities during the life of the programme.
Number of CF activities	50	44	52 / 74	Moderately did not meet expectation. Adoption and socialisation activities will be an in-depth and integrated work of information and interaction activities that help facilitate the link between the supply (FinTech solutions) and the demand sides (MSMEs and vulnerable male and female users).
Number of MSMEs participating in the CF activities	300	264	478 / 400	Exceeded. Much stronger than expected demand from Mexican MSMEs wanting to grow this market over the last two years.
Number of male and female individuals participating in the CF activities	1400	2800	3570 / 1700	Exceeded. Much stronger demand than expected from Mexicans wanting improved financial services.
Number of international (including UK) companies engaged with CF activities (benefit partners and advisors)	2	16	17/3	Exceeded. Much stronger demand than expected from International Companies to participate in our programme to grow the Mexican financial services market. 16 companies have stayed engaged on Caravana Fintech into the second year with an additional business coming on board in the second year.
Number of associations and institutions at national and state level that will establish relationships with the British Embassy as a result of the intervention	6	7	7 / 6	Exceeded. Our expansion to Campeche brought on board three further institutions to the programme and all remaining institutions from Queretaro stayed on board. Institutions of Queretaro that established relationships with the BE were: SEDESU, SEJUVE, COPARMEX and TD2035. In 2021 institutions were from Campeche: SEDECO, CCE, and BANCAMPECHE.

Overall the financial services strand has proven that there is high demand across the country for improved financial services. There has been strong take up from local Mexican Fintech SMEs in the Programme. Equally there has been very impressive involvement from UK Fintech firms in exploring this market. The Central Bank in Mexico and the regulators have engaged well with the Programme and although there have been some delays with progressing support to the regulatory framework this is in most cases understandable. A key success this past year has been the adoption of the financial education element of the Programme wholeheartedly by the Mexican Institution AMAFORE as well as partnerships with other like-minded donors to support greater penetration of new financial services at the local level and support work on the regulatory framework to sandbox innovations.

The Financial Services strand is under its second year of implementation. Due to the pandemic, the strand moved from in-person to virtual activities. The strand achieved its output indicators, particularly for Intervention 2 and 3. After the SR, the strand had significant changes in all of its interventions. The strand developed new work plans and updated the logframe and ToC to reflect the SR outcome.

Intervention 1 (I1) focused on the development and implementation of the Financial Education Initiative for the Inclusion of Young Adults into Provisional Saving System. The initiative provided content through a Circuit of Digital Educative Interactions hosted in a microsite called “AhorrandoAndo”. A pilot project started with CONALEP Merida and Tizimin, Yucatan during March and April 2021 reaching 119 students. However, as a result of the SR, the Financial Education Initiative was closed down and transferred to AMAFORE. The BE signed a MoU with AMAFORE which considers information sharing (e.g., results). For this review, the team focused on the available documents and thus the score is based on those. This score does not reflect the latest results that could have been achieved by the intervention. It is important to mention the review team did not interview external stakeholders as this exceeds the scope (ToRs) of the review.

Most of the outputs for Intervention 2 (I2) are still on track for delivering the milestones and targets. This intervention concluded its first edition of the Sandbox Challenge, which had 166 FinTech participants and awarded six winners. The winners received legal and business support to prepare their applications for the CNBV Regulatory Sandbox, three of them have already submitted and the rest are expected to do so in the coming months. Phase II of Open Finance (OF) regarding the development of debit accounts and client consent transactional API Standards was completed. I2 completed the SupTech platform analysis and secured APF funding to develop the Phase I. By the end of June 2021, I2 submitted eight dashboards and the security functionality of the administrative module.

Intervention 3 (I3) made progress through virtual activities for Caravana FinTech (CF) in Queretaro and Campeche. It conducted the segmentation analysis and launched the Call for FinTechs event in Queretaro in August 2020 that attracted 116 applications and Call for FinTechs awards in Queretaro in October from which three FinTechs were selected. It also conducted a demand analysis in Campeche and also in October launched CF in Campeche and Open Call for FinTechs launching event in January 2021. Socialisation activities reached +1,000 attendees in Queretaro and +600 people in Campeche, whereas +200 attendees were registered for adoption activities in Queretaro. These activities enabled I3 to facilitate a wider, supportive and gender sensitive range of FinTech products and services available to MSMEs, and vulnerable male and female individuals. Following the SR outcome, the CF model was updated with a view of expanding activities with a national scope through a 100% virtual model.

Secondary Benefits indicators have been well woven into the Programme logframe for financial services and captures the articulation of the original business case. As a result we have seen some fruitful engagement with UK best practices on regulation of the market and with UK Fintech companies, Intervention 1 focused on soft power through events such as National Financial Education Week (SNEF), which concentrated in sharing knowledge and experiences in the financial sector. I2 continued focusing on building strong relationships with strategic allies such as the National Banking and Securities Commission (CNBV) to increase the influence of UK best practices in financial regulation. Finally, Intervention 3 continued promoting the participation of UK and international Fintechs in CF activities.

The G&I strategy of the Financial Services strand focused on internal training to show how gender roles and conditions of vulnerabilities impact financial and social inclusion. It focused on safeguarding training and review of materials or activities to integrate client protection principles. I1 concluded the design of archetypes that support the deployment of educative materials to consider a human-centred design. I2 continued prioritising the participation of female leading voices in sector activities for the events regarding the Sandbox Challenge. I3 had regular meetings with the GESI adviser to reinforce the strategy by reviewing materials and activities for Caravana FinTech to raise awareness between MSMEs and FinTechs. The equity component of VfM of the strand shows a clear definition of vulnerability and how it aims to target, specifically, vulnerable women.

The Programme has been forced to make sensible adjustments to the scope of the activities in line with budget cuts but had made enough of an impact at this point to illustrate strong interest and demand for further evolution of the financial services market in Mexico.
 ACROL

Output Title	Standards, processes, guidelines and/or policies for investigation of serious crime (homicides), corruption and cyber-crime
Output number:		1a,b,c	Output Score:	A+
Impact weighting (%):		15	Weighting revised since last AR?	Up

Indicator(s)	Milestone for this review / March 2021	Achieved against milestone	Aggregated target	Progress
Number of formal collaboration agreements in place with relevant institutions	6	5	5/6	Met. ACROL signed Memoranda of Understanding with 5 institutions in: Tabasco (1), Jalisco (2) and CDMX (2). The implementer signed 1 DA with CNBV. A sixth planned agreement was abandoned after cuts were made to the budget.

Output Title	Detailed outline of case building procedures for the detection and investigation of selected crimes
Output number:		1,d,e,f	Output Score:	B
Impact weighting (%):		10	Weighting revised since last AR?	Down / *Due to the decision to close early from the supplier. Detail below.

Indicator(s)	Milestone for this review / March 2021	Achieved against milestone	Aggregated target	Progress
Number of sets of recommend-ations provided which incorporate UK or international best practice	3	2	5 / 6	Partially met. Final sets of recommendations to improve investigations have been created for Tabasco and Jalisco authorities. Recommendations for CDMX are pending due to impacts of CV-19 and SR results. The strand also started an analysis on financial cyber fraud.

Output Title	Mapping of handover points between agencies working on selected crimes
Output number:		3,a,b,c	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	Same

Indicator(s)	Milestone for this review / March 2021	Achieved against milestone	Aggregated target	Progress
Number of recommendations provided to improve inter-agency coordination	2	2	3/3	Met. Final sets of recommendations to improve inter-agency coordination were delivered in November 2020 for Tabasco (1) and Jalisco (1). From February to July, the strand carried out activities to define recommendations to the cybercrime component.

Output Title	Multi-agency working groups for detection and investigation of selected crimes involving multiple hand offs
Output number:		3, d,e,f,i	Output Score:				A
Impact weighting (%):		15	Weighting revised since last AR?				New indicator

Indicator(s)	Milestone for this review / 2020			Achieved against milestone		Aggregated target		Progress
Number of community of practice meetings held	4			4		8 / 8		Met. Two inaugural meetings were held in 2020 (Homicide and Cyber fraud), and the remaining two took place in January 2021

Output Title	Annual workshop for judges in selected states to socialise new standards and processes and share international best practice, learning events and SGB meetings.
Output number:		3,g,j,k,l,m	Output Score:				A
Impact weighting (%):		20	Weighting revised since last AR?				Same

Indicator(s)	Milestone for this review / March 2021			Achieved against milestone		Aggregated target		Progress
Number of learning events held	Work was brought forward as part of the exit strategy			4		1		Met. 4 event were held. Virtual learning events on Cybersecurity, Homicide (2), and Embezzlement were held
Number of beneficiaries and public agencies attending knowledge sharing events aiming to showcase UK and international best practices, approaches and methods.	Work was brought forward as part of the exit strategy			21		21 / 21		Met. All learning events held during 2020 shared UK best practices with Mexico public agency servants.

Output Title	Diagnosis and support to implement non-discrimination practices, policies and/or complaint procedures within beneficiary institutions
Output number:		3h	Output Score:				A
Impact weighting (%):		20	Weighting revised since last AR?				Same

Indicator(s)	Milestone for this review / March 2021			Achieved against milestone		Aggregated target		Progress
Number of G&I diagnosis delivered	0 work was brought forward as part of the exit strategy			5		5		Met. 5 G&I diagnosis were delivered

Following the Spending Review, the ACROL supplier concluded that it was no longer possible to meet the strand objectives and agreed with the Embassy team to prepare a handover plan to minimise reputational impact while delivering VfM. The Exit plan covers the transition period from May to November 2021. Thus, the logframe results showed are up to the latest Supplier Report (March 2021). The logframe was no longer updated, but it was agreed that the implementer would provide results up to November 2021.

In its second year of implementation, the ACROL strand moved to fully virtual working. This shift increased the strand’s interactions and strengthened the strand’s relationships with Jalisco, Tabasco and Mexico City. Intervention 1 developed the new investigation model for homicides and embezzlement (Jalisco and Tabasco), released the first standards and processes and provided specific recommendations (including UK/international best practices and G&I considerations). As a result, the intervention obtained an initial commitment to implement the recommendations and the new model in these regions. In Mexico City, the intervention finalised a diagnostic work on homicides and gathered evidence from real cases to issue specific recommendations and tailor the new investigation model. Additionally, the strand started the financial cyber fraud criminal phenomenon's analysis based on a prosecution approach with the CNBV’s leadership. The final report is expected to be delivered at the exit plan conclusion.

ACROL’s intervention 2 finished analysing the training needs to implement the new investigation model (for Tabasco and Jalisco). Furthermore, it developed a capacity building strategy, which would include interactive training sessions and materials with practical hands-on implementation of the new investigation model through pilots in real (homicide and embezzlement) cases.

Intervention 3 established four communities of practice, which operated with high-level stakeholders (one for each crime - homicides, embezzlement and cyber-fraud and one focused on gender and inclusion). The intervention had several knowledge sharing events with high attendance rates (100 + attendees). This intervention created networks and relationships between Mexican agencies and its UK/international counterparts.

The main progress on SBs was on showcasing UK expertise. The strand shared during virtual activities the UK best practices in the investigation and detection of selected crimes. The strand’s work was supported by the Chief Constable, who also participated in a homicide learning event.

ACROL has embedded a G&I approach in the findings, recommendations and diagnoses. Furthermore, the strand launched the Gender and Inclusion Community of Practice to improve coordination across authorities and government levels. The strand participated in the diagnostic work to assure that G&I was embedded into future models of criminal investigation (homicide and embezzlement). All of these actions, show a strong perspective of equity of the strand (especially towards the gender aspect of it).

Despite the impact of the budget cuts on this programme a very sensible and sensitive exit plan had been agreed which met initial demand from Mexican Institutions for support on Anti-Corruption and left in most circumstances a platform or diagnostic on which these institutions and also other donors and stakeholders can build.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

2020 Annual Review recommendations	Accept, partially accept or reject	Actions/activities
Refresh cost-benefit analysis in autumn 2020	Partially accept	The approach taken was to conduct a pre- Political Economy Analysis (PEA). This document analysed weather or not the economic and political environment/priorities changed and from there decide if a cost-benefit analysis was needed. The programme team decided not to refresh the cost-benefit analysis.
Set target of Paris compliance by mid-2021	Accept	All programmes are Paris compliant. The Clean Energy programme has been re-designed to ensure full adherence to Paris compliance.
Consider reallocation of £6m between strands	Partially accept	This recommendation was considered by the PT and conducted a pre- PEA. The analysis sought to provide information around the changes in the economic/political orientation of the Mexican Government and its implications for each of the Prosperity Programmes. Given the SR outcome, funding for all strands had to be updated and so this is no longer an applicable recommendation.
Develop strategic approach to secondary benefits	Accept	A strategic approach to SBs was developed by ensuring SBs are not just identified in the logframes at the beginning of each project but that their progress is monitored and necessary follow ups are carried out. The tracker was created for this purpose. / The SB approach will ensure the tracker is updated regularly and it will serve as a place where all information can be recorded and necessary actions identified. / SBs will be categorised in terms of type and impact.
Encourage roll-out of successes to Southern States	Partially accept	After the pandemic, the Programme switched its delivery to on-line activities, which contributed to increase the number of states the programmes operated (e.g. Campeche on Financial Services). Through GIZ co-funding discussions (ongoing), the Financial Services Programme will also expand to cover Yucatán and Oaxaca.
Strengthen non-gender aspects of G&I in programme	Accept	As part of the ToC/logframe workshops, the PT sought to strengthen definitions for vulnerable population. These definitions not only cover income, but wider sides of vulnerability (e.g., access to health services). Around gender, the Clean Energy and Financial Services agreed to prioritise women participation for some of its interventions.
Strengthen strategic communications back to the UK	Accept	A communications strategy was developed which included as a key objective the strengthening of strategic comms to the UK. Numerous examples include our feedback to the Prosperity Programme Annual Report, ministerial briefings, etc.
Improve financial management/performance	Accept	An independent financial audit was carried in 2021 and recommendations that followed to improve financial management and performance have been implemented.
Retain Deputy Head but consider using natural attrition if Programme funding is reduced	Accept	Recommendation was taken forward but team size and structure has been affected by the SR outcome.
Hold back (or seek extra) evaluation support for the autumn	Accept	The Programme (as a whole) and each of the four strands reviewed the ToC/logframe during a workshop (Nov-2020) facilitated by the MR Hub and with the participation of the E&L team. The workshop helped to address the recommendations from the Cycle 2 Evaluation and the second Annual Review. The programmes finalised updating the ToC and logframe in March 2021.

D: RISK [½ to 1 page]

Overview of risk management

The main programme risks are in the delivery, reputational and operational categories, stemming largely from the impact Covid-19 has had in both the Mexican and the UK economies.

The UK’s target spend of 0.5% of GNI as Official Development Assistance in 2021 has had in impact in the funding for the Mexico programme and the original targets set in the log-frames have had to be updated, affecting original planned delivery. The programme has responded well to risks posed by Covid-19 which were properly addressed at the beginning of the pandemic and continue to be managed through existing structures. Workplans have been adapted to the current context and adaptability of the programmes has been key to ensure delivery.

Reputational risks have also suffered a large amount of pressure. Funding support has significantly reduced and will most likely end for key areas of our bilateral cooperation. Relationships at both local and federal levels have been significantly strengthened (and in some cases created) through our ODA programming and discourse on mutual prosperity. Stakeholder handling has been managed carefully to inform programme reductions to date but will need to continue to announce full closure in most cases.

Operational risks have also materialised in terms of team capacity in managing the programmes. The team has been reduced in size due to natural attrition, but staff funding decisions will continue to affect the overall team structure and its capacity to deliver.

Fiduciary and safeguarding risks have had no significant impact and we expect the same trend until the end of the programme in March 2022.

The Programme has strong management systems and practices in place to manage risk, as concluded in previous Annual Reviews and independent evaluations. Risks are reviewed and discussed monthly at our Programme Management Committee, with SRO oversight.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

Quality and timeliness of narrative and financial reporting:

Monthly narrative and financial reporting have been received on time for all four strands. Given how we have had to re-prioritise resources due to the Covid-19 context, a revision was made to all our reporting requirements and changes were proposed and implemented to ensure the information received was relevant for our own internal reporting processes. Quality of narrative reporting has been strong.

In some cases, the quality of the financial reporting has not been satisfactory. One Partner in particular, has not complied with the format requirements of the financial reporting and has either not updated it accurately or has submitted a proposed new version which does not include the level of detail required in forecasting. This has caused substantial back and forth with the Partner, which has been an ongoing issue now since the last AR.

Audits:

The Call Off Contracts do not stipulate that audited financial statements are required. The Call Off Contracts do however state that the Partners must submit an annual self-audit certificate signed by a director of the Partner which confirms all Call Off Contracts have been correctly calculated and charged to the Customer, and that the call of contract charges have been appropriately accounted for to enable the appropriate taxes to be paid to the Partner. We received these annual self-audit certificates for the four contracts in February and March of 2021, but no further action has arisen upon receiving these statements.

An external financial and supply chain rights audit was commissioned on the Mexico programme by the previous Head of Prosperity in Mexico with funds from the programme budget. The audit was conducted from January – March 2021. There were no major findings.

A recommendation here would be for the contract to stipulate that audited financial statements are required annually. This would ensure that the information is reviewed by an independent body for a fair and true opinion. It could be a way for the programme team to lessen financial monitoring on a detailed level on a monthly basis (which has been time consuming reporting for both the FCDO and one Partner).

Risks and issues reporting:

The monthly risks and issues register has been supplied by all Partners on a monthly basis. Sometime the register has not been updated by the Partners. On balance there is strong risk and issues reporting from Partners with risk reporting featuring in all weekly or monthly meetings with the embassy teams.

Delivery chain maps:

These have been updated annually when the embassy team have reminded the Partners to submit alongside new yearly costed work plans. Overall, these have complied with the FCDO requirements to ensure a clear flow of funding to all delivery chain partners.

Financial management (e.g. accuracy of forecasting):

As above, quality of financial management including on forecasting has been particularly challenging with one supplier. Milestone values have been changed without prior approval, which reflects an issue with forecasting. This has materialised in the failing of a KPI for the supplier with a value of £10,000 of service credit to the customer. Limited resource on the Embassy side has had to be used to compensate for the quality of financial reporting, resulting in having to de-prioritise oversight in programme delivery in favour of oversight of financial management.

Delivery against contract KPIs, and Terms and Conditions:

In terms of Service KPIs, the four strands have continued the quarterly performance review meetings where the quarterly performance report is assessed. The Service KPIs for three strands have remained the same for implementation, while the KPIs for ACROL were reduced for the period of Exit. For the other three strands, the embassy team have worked on new sets of KPIs making them more relevant. These new proposed KPIs have not been shared with Partners as the embassy team was waiting for clarity on the programme staff capacity.

Only one KPI has been failed by one Partner, this was in the last quarter of FY 20-21. The resulting Service Credit to the Customer is to the value of almost £10,000. The agreement is that the Partner will allocate this Credit to new work (additional to what has been agreed in the annual work plan) within the FY 21-22. A variation form is being drafted to ensure this Credit is assigned by December 2021.

On the contract Terms and conditions, the Partners have complied almost completely apart from Schedule 3 Call Off Contract Charges, Payments and Invoicing part 7 “Partner Periodic Assessment of Call Off Contract Charges”. This has not been followed by any of the Partners but as part of the closure, profit margins will be revised to ensure they are in line with the stipulation of the Framework Agreement.

Performance of Partners, including summary of the SRM scorecard assessment for each delivery partner:

Performance by suppliers in this year needs to be set against the changing environment affecting their delivery due to cuts and then early closure of the Programme.

Overall the performance of our commercial suppliers for this Programme has been exceptional. They have worked collaboratively and patiently with the Embassy in Mexico to realise new adjustments to the Programme in line with cuts. They have had to downsize teams and manage change processes whilst also achieving results. Many of the results targets missed in this review are a result of an initial delay by the FCDO in being able to confirm budget allocations for FY 2021/22 and so the scoring of this Programme does not reflect poor performance by suppliers.

Contract KPIs have been impacted twice in this year, variations were required each time and some are still to reach resolution. Terms and Conditions have stayed the same throughout and as defined in the original contracts tendered.

Suppliers have worked tirelessly and with professionalism in the face of these changes. The last SRM scorecard exercise was carried out in June 2021, just before a decision to close the programme was communicated to suppliers. Note that the SRM scorecard only applies to two of our three suppliers.

- Future Cities – 70
- Financial Services – 52
- Clean Energy – 58
- ACROL – does not have a scorecard

The SRM process in June really reflects the performance of suppliers in handling the cuts made to the Programme:

  1. The supplier for the Future Cities contract swiftly agreed an exit strategy for the Programme and has implemented it very efficiently with its alliance partners.
  2. The supplier for the Clean Energy and Financial Services contracts worked effectively to support prioritisation of interventions that were sensitive in that they had the buy-in of important stakeholders for other teams within the British Embassy or had the most potential for residual impact in spite of cuts to resources. However, these contract variations have taken the most time to renegotiate. Cuts have also resulted in the commercial supplier having to declare a position of excess profit as a result of payments made against the initial milestone schedule before changes to the contract needed to be made to reflect the future scope and time remaining of the deliverables. This has led to more work for the Team in terms of considering how to best reinvest that excess profit.
  3. The supplier for the ACROL strand agreed to work to a longer and more responsible exit strategy to which the British Embassy and Mexican stakeholders to the Programme were very grateful.
Review of the original Value for Money (VfM) assessment:

#### Cost drivers and performance

The 85% cuts to this Programme have had the largest detrimental impact on the VfM proposition as outlined in the business case and therefore represent a key cost driver this year. The result of the cuts has been that the Programme will have to write off substantial investments in activities that were geared up that will now not reach fruition. For example, the amount of investment initially made in the creation of EPI Energía will be lost as the timeframes and amount of investment available for the future are not enough to see this initiative through to become the sustainable business model that was planned. The initial investment in ACROL on balance is much weaker VfM as the interventions completed have only been preliminary diagnostics and investigation models for the Government to take forward under their own steam. The original plan was to work with them to support deep implementation of those models in partnership with UK expertise. Financial Services and Future Cities Programmes have better VfM elements. Some activities were delivered online which reduced cost inputs for those activities and the Future Cities design lent itself to selecting less, but higher impact pilots and ultimately still enabling overachievement on its results.

Another cost driver has been the amount of time taken to adjust work plans that still represent valuable impact for primary and secondary benefits, negotiate and issue contract variations, and then hold discussions with stakeholders about changes to or exit of interventions. All processes had to be repeated twice within the year to reflect the new decision to close the Programme early. Moreover, a lot of activity has been spent on readjusting and handling fallout rather than on driving impact and deepening collaboration with partners and stakeholders to improve outcomes.

An additional cost driver has been the interplay between the bilateral Mexico Programme and the Global Prosperity Programmes in Trade, Health, Skills, Anti-Corruption and Infrastructure. The early closure of these Programmes has also limited the overall strategic cohesion of UK ODA investments in Mexico and their collective impact for the UK Government.

A valuable reinforcement mechanism which has helped reduce the impact of some of these cost drivers has been the British Embassy’s use of virtual teams comprising representatives from climate change, trade, economic, defense, development and political teams. These teams have been extraordinarily effective in coordinating handling of the impact of cuts with external stakeholders as well as supporting reprioritisation processes for each Programme strand.
#### Economy

The Business Case considered that the Programme would be delivered through four contracts to enable a strategic approach across the interventions for each strand. The experience and expertise of the delivery partners has promoted economy and efficiency and has improved commercial skills in the Programme Team also. There have been some good attempts at promoting cross-strand working that took place in the first year of implementation, however the second year of implementation has seen fragmentation as strands focused down on more limited scope and retreated inwards to negotiate new contract variations with FCDO. One supplier, responsible for the work most focused on tackling the overarching business environment in Mexico by tackling corruption, decided to exit the programme early.

The core Programme Team created effective procedures to monitor spending and improve forecasting and financial management. At full resourcing, this comprised the Head and Deputy Head of the PF, 4 Programme Managers, 4 Programme Officers, 3 Finance Officers, and MREL lead, a Stakeholder and Governance lead, and the Contract Management lead. Some work had been undertaken earlier on in this review year on improving scrutiny of financial information submitted by delivery partners, building on the recommendation from the previous AR that suppliers needed to provide an increased level of detail in order to correctly forecast activities and identify savings. This enabled better decision-making processes and ensured greater control over costs and more proactive identification of savings.

#### Efficiency

There have been considerable delays to implementation in this year due to the need for suppliers to freeze implementation plans until FCDO had established a budget for FY21/22; although the initial plan was to unfreeze quickly in June with a new budget, the scale of the cuts meant that the programmes suffered a 3-4 month delay in implementation as new work plans were agreed and new contract variations signed off. At this point all but one of the suppliers planned to continue into the final year of 22/23 with activity. However a further decision to cut the Programme meant that the original impact had to be adjusted to meet new realities and planned work with stakeholders in some cases has lost momentum.
We judge that the Programme will achieve most of its newly agreed output indicators by the end of March 2022 and that changes and adaptation has been managed as best as it could in the context of a series of decisions forced onto it. More than this the programme in all strands will have exited responsibly and efficiently with stakeholders whilst minimising reputational damage to the UK.

#### Effectiveness

In order to strengthen effectiveness, logframes have been reviewed and updated throughout the project cycle. The first update occurred before the cycle 2 evaluation started (February 2020) and the Programme logframe was fed from the strand logframes’ indicators and uploaded to Prospero in July 2020. A second review exercise occurred in November 2020 to improve coherence between the four strand logframes and the overarching Programme logframe. The latter one became irrelevant once the cuts were announced. In July 2021, workshops with suppliers about what to close responsibly and what to retain resulted in the strand logframes being updated. These are the logframes being used now for the purposes of Programme monitoring and evaluation.

The Business Case originally estimated a central scenario of £886m primary benefits and £462m secondary benefits (see table below) generated by the Programme after it had completed 3 years of full implementation following its inception year. The combined impacts of COVID-19, changes in government priorities and the eventual cuts have changed these scenarios substantially. The Programme has only completed 1 full year of implementation against its original plan. Its second year of implementation has seen a budget cut of 85% and the third year of implementation (although this was planned to taper down) will now not take place. This means that around 2/3rd of planned activities will not happen.
Original Business Case calculation of Primary/Secondary Benefits per Strand
Strand	Primary Benefit (£m)			Secondary Benefit (£m)
	High	Central	Low	High	Central	Low
Anti-Corruption and Rule of Law	809	219	24	234	153	72
Financial Services	421	221	80	52	28	4
Energy	320	215	129	376	254	139
Future Cities	684	231	53	35	27	20
Total	2,234	886	286	697	462	235

#### Equity

The Programme underwent a light G&I review in its cycle 2 evaluation. The April 2020 scores were 4/5 for three of the categories (programme design, internal capability and partnerships) and 3/5 for two of the categories (financial resources and accountability mechanisms). As a result, new G&I leads were appointed within the Programme Team, who have held regular meetings with delivery partner G&I leads. Strand and programme-level logframe information was disaggregated for some indicators for income, vulnerable groups and gender categories.

Further G&I adaptations became unfeasible due to the need to adapt the programme to focus on C19, and then cut and close the programme responsibly. However, previous G&I strengthening has been protected within all interventions that continued through 2021.

Date of last narrative financial report	September 2021 for each supplier for this Annual Review.	Date of last audited annual statement	Future Cities: February 2021 / ACROL: February 2021 / Clean Energy & Financial Services: March 2021