Overview of the Performance of the Prosperity Fund Portfolio IN 2020/21
Fund-Level Evaluation Cycle 3
March 2021
Version History
Revision	Written By	Checked By	Approved By
1	Valerie McDonnell-Lenoach, Fionn O’Sullivan, Claire Howard, Neil Pogorelsky	Elbereth Donovan, Paddy Abbot

Table of Acronyms
Abbreviation
ASEAN	Association of Southeast Asian Nations
COP26	The 26th UN Framework Convention on Climate Change Conference of the Parties
DAC	OECD Development Assistance Criteria
DCMS	Department for Digital, Culture, Media and Sport
DFID	Department for International Development
DIT	Department for International Trade
EL	Evaluation and Learning
EQ	Evaluation Question
EQuALS	Evaluation Quality Assurance and Learning Services
FCDO	Foreign, Commonwealth and Development Office
FCO	Foreign and Commonwealth Office
FDI	Foreign direct investment
G&I	Gender and inclusion
GNI	Gross National Income
IO	Intermediate Outcome
JFU	Joint Funds Unit
K4D	Knowledge, Evidence and Learning for Development
MR	Monitoring and Results
MREL	Monitoring, reporting, evaluation and learning
NHS	National Health Service
ODA	Official Development Assistance
ODI	Overseas direct investment
OECD	Organisation for Economic Co-operation and Development
PF	Prosperity Fund
PPPs	Public–private partnerships
SB	Secondary benefit
SDA	Social Development Adviser
SDGs	Sustainable Development Goals
SR	Spending Review
ToC	Theory of change
UN	United Nations
UNDP	United Nations Development Programme
VfM	Value for Money

Contents

Tables
Table 1: Illustrative examples of results at intermediate outcome level	8
Table 2: Annual Review scores for programmes 2018–2020	12
Table 3: Advantages by programme type	24
Table 4: Opportunities and realisation of secondary benefits by programme type	24
Table 5: Recommendations	26

Figures
Figure 1: Prosperity Fund intermediate outcomes	4
Figure 2: Official Development Assistance country/region and sector focus 2017–2023	5
Figure 3: Actual vs planned PF programme spend as at Dec 2020	7
Figure 4: Number of reported results at intermediate outcome or higher level, by the five intermediate outcomes	9
Figure 5: Percentage of programmes reaching minimum standards, by G&I scorecard dimension	11
Figure 6: Estimated commercial secondary benefits realised to date, by type	14
Figure 7: Number of programmes realised and potential secondary benefit opportunities	15
Figure 8: The Prosperity Fund's alignment with the Sustainable Development Goals	16
Figure 9: The range of factors identified by programmes that hinder delivery of results	22
Figure 10: Results achieved by programme type	23

Boxes
Box 1: How the Fund is supporting better lives for women and excluded groups	10
Box 2: Examples of commercial secondary benefits	13
Box 3: Examples of soft power created by the Prosperity Fund	15
Box 4: Evaluation and Learning value for money scorecard dimensions	18
Box 5: Examples of PF programme adaptations to the COVID-19 pandemic	19

Annexes
Annex 1. JFU management response to the 2019/20 Fund Report
Annex 2. Evaluation purpose, methodology and approach
Annex 3. Context to and background of Prosperity Fund
Annex 4. Documents reviewed
Annex 5. Stakeholders interviewed
Annex 6. Findings on Value for Money
Annex 7. Detailed findings
Annex 8. Approach Paper - Scope of PF Year 3 Evaluation

# Executive summary
The Prosperity Fund has made notable strides forward over the past year. Most of the programmes are now in implementation, although a few are not yet up and running and some programmes have only been in delivery for a short time. During 2020/21, the Fund has acted in a flexible and adaptive manner as demonstrated by its proactive response to the challenges of the COVID-19 pandemic. Based on the evidence available, the Fund has started to deliver results at intermediate outcome level. Notable results achieved in 2020/21 include the following: / The Fund has made progress towards delivering the primary purpose of poverty alleviation through inclusive economic growth. Intermediate outcome results were reported across all five sectors in which the Fund works; the area that performed the strongest was ‘Ease of Doing Business’. / The Fund has delivered benefits for women and excluded groups. It is likely that such benefits will continue to increase in future as the impacts of reforms supported by the Fund take effect. However, the Fund could have delivered more results for these beneficiaries in the time available if there been greater capacity and a better understanding of gender & inclusion considerations at an earlier stage and if gender & inclusion had been better embedded into programme designs. / The Fund has already contributed to delivering commercial secondary benefits (exports and investment) for business (including UK firms) to the value of GBP 1.62 billion. There are also documented opportunities to deliver substantial additional secondary benefits in future. Although secondary benefits are not yet at the originally anticipated levels, results in this area exceed the planned value of the Fund and are considerably more than the GBP 518 million spent to date. / The Fund generated soft power, including supporting access and influence over development outcomes for the UK; it has been viewed as a useful tool for economic diplomacy and engagement with government partners in the middle-income countries in which it operates. / The Fund has potential to help achieve Sustainable Development Goals and is already doing so in areas such as health, industry, innovation and infrastructure, clean energy and climate change. / Moreover, the Fund has shown that the concept of a cross-government Official Development Assistance (ODA) programme, based on the principle of mutual prosperity, is sound and can be successfully put into practice. The Fund has supported an extension to cross-government capacity to deliver ODA programmes, with departments such as the Department for International Trade and the Department for Digital, Culture, Media and Sport increasing their ODA experience as a result of engagement with the Fund. The value of the Fund as a successful testing ground for innovative, new or high-risk approaches was noted by stakeholders consulted for this Fund evaluation. / The Fund has continued to improve its programme level governance and management processes, including value for money systems and processes. Learning and knowledge sharing have continued to take place at programme level and across programmes but the COVID-19 pandemic and ODA reprioritisation exercise reduced the time available for these activities. / The Fund has significantly underspent over its lifetime. Initial delays in design, approvals, procurement and set-up in the first two-to-three years substantially reduced the time available for implementation. This was recognised early on by the Fund managers and a two-year extension has been requested, although not yet secured. / While good progress in implementation was made during 2020/21, the hoped for acceleration of the pace of implementation has been negatively affected by the COVID-19 pandemic and the ODA reprioritisation exercise. As a result of these delays, the Fund is not currently on track to achieve its objectives or to deliver value for money in accordance with the timescale originally set out in the business cases and implied in initial funding allocations. / Despite delays in the achievement of results, the Fund has shown that an innovative cross-government ODA-Fund operating in middle-income countries with the dual purpose of supporting poverty alleviation through economic growth while generating business opportunities can be made to work. In particular: / Given enough time it is possible for an ODA programme to deliver a primary purpose of inclusive growth to reduce poverty, while also creating substantial secondary benefits for businesses, including UK firms, (and, in many cases, with modest non-ODA accompanying resources to help achieve these). / Cross-government delivery of ODA programmes can be successful, allowing programmes to harness the specialist technical and sectoral expertise of different government departments. / Similar to the experience of other ODA programmes, aligning programme priorities with partner government priorities, tailoring governance arrangements to local partner needs and involving partners in decisions around adaptation is a key factor to success. / The experience of the Prosperity Fund shows that realistic targets, ambitions and timeframes for delivery are essential. The Fund’s original time scale was over ambitious given that some sponsoring departments and programme staff had limited experience of ODA programming or of creating secondary benefits. In practice, it took substantially longer than anticipated and up to three years for some programmes to complete set-up, design and procurement activities. This also highlights the need to ensure efficiency in the management of procurement and contracting and programme set-up arrangements so there is enough time for programme implementation.

# What this review is about
## Aim of the evaluation
The independent Evaluation and Learning (EL) provider, Tetra Tech International Development, in partnership with Niras-LTS and Integrity, is responsible for evaluating the Prosperity Fund (PF)’s progress and performance in annual cycles. Developed in January–February 2021, this Fund-level evaluation summarises the progress and performance of the PF during the 2020/21 financial year.
The evaluation captures evidence to respond to three overarching evaluation questions (EQs) set out in the EL business case:
- EQ1: What has been or is likely to be achieved as a result of the PF?
- EQ2: What factors have contributed to or hindered these achievements?
- EQ3: What can be learned from the Fund’s experience to date to improve ongoing and future programming?
The evaluation ensures independent scrutiny of the Fund’s performance for accountability purposes, considers if the Fund is on track to meet its aims, and contributes to capturing learning. It also considers whether programmes are set up to deliver good value for money (VfM) and what effect contextual changes in the past 12 months, specifically the COVID-19 crisis and resulting ODA reprioritisation, had on delivery of results.
While the future of the PF is unclear at the time of writing, this report makes recommendations for future improvements to delivery. It also shares some broader reflections on a fund of this nature to inform the design and delivery of other, similar funds.
## Target audience
The key audiences for this report are the Joint Funds Unit (JFU) and Foreign, Commonwealth and Development Office (FCDO) PF Leadership teams. PF programme teams and implementing partners and other government departments delivering or planning to deliver large cross-sectoral funds will also be interested in the findings.
## Evaluation approach and evidence base
This third Fund-level evaluation focuses predominantly on the results of and learning from the more mature Fund; it builds on the previous two evaluation cycles, which assessed Fund progress and dealt mainly with the set-up, leadership, management and governance of the Fund.
The overarching methodology is research synthesis. The evaluation draws on available programme-level information generated over the past year through analysing 79 documents, including external evaluation reports, internally led Annual Reviews, risk registers, quarterly management reports and Prospero[1] data provided by programme teams and managed by the Monitoring and Research Hub. The evaluation also considers Fund-level information such as PF Portfolio Board reports and EL sector and thematic level synthesis products. Key informant interviews were conducted with a small sample of 20 stakeholders (6 Fund level decision makers and 14 from programme teams) purposively selected in partnership with the JFU to address evidence gaps in relation to the strategy, focus and performance of the portfolio.
[1] Prospero is the PF’s bespoke online performance monitoring and reporting system.
## Limitations
The key limitation of the evaluation approach is the limited evidence base: while most programmes received Annual Reviews a number of programmes did not receive an independent evaluation as planned in 2020/21 due to the COVID-19 pandemic and ODA reprioritisation. As a result, not all programmes have had an independent evaluation over the life of the Fund to date. Combined with delays in PF delivery, which reduced the speed with which results emerged, there have been limited opportunities to independently verify the PF’s contribution to results as originally anticipated in the design of the independent evaluation service.
Details of secondary benefit opportunities recorded by the JFU[2] could not be shared with the evaluation team for commercial and confidentiality reasons. The evaluation of secondary benefit results has therefore been limited to reviewing the government’s approach to calculating the value of secondary benefits. There are also notable gaps in the monitoring data on the performance of all PF programmes uploaded by programme teams on to Prospero despite central support in this area.
[2] The Joint Funds Unit is the central Cabinet Office unit that manages the Prosperity Fund
Additional details on the methodology, limitations and evidence base for the Year 3 Fund evaluation are set out in Annex 2.
# Overview of the Prosperity Fund
What is the Fund trying to achieve and where?
At the time of writing, the PF remains a cross-government fund worth GBP 1.2 billion over 7 years aiming to reduce poverty by supporting inclusive economic growth in partner countries[3] while creating opportunities for business. The Fund began operation in 2016/17 and was planned to run until at least 2022/ 23, subject to subsequent Spending Review outcomes.
[3] www.gov.uk/government/publications/cross-government-prosperity-fund-programme/prosperity-fund-map.
The Fund delivers programmes in a range of sectors in which the UK is a leader or has a competitive edge and where there is a high potential for inclusive growth. It works across five key themes or sectors which are essential to improve the conditions for inclusive growth and poverty reduction: the Fund’s primary purpose. These sectors are: Investment in Infrastructure; Human Capital, Innovation and Technology; Trade; Financial and Economic Reform; and Ease of Doing Business (collectively the Fund’s intermediate outcomes, as shown in Figure 1).

Figure 1: Prosperity Fund intermediate outcomes

Source: Prosperity Fund Annual Report 2019/20, October 2020
The Fund’s focus is on middle-income countries that are eligible for ODA. Around 60 per cent of the world’s poor live in MICs and 60 per cent of global growth is expected to come from these countries by 2030.[4] Figure 2 on the next page presents the geographical and sectoral coverage of the Fund. Annex 3 provides more background information on the Fund.
[4] www.oecd.org/dev/pgd/economydevelopingcountriessettoaccountfornearly60ofworldgdpby2030accordingtonewestimates.htm.

Figure 2: Official Development Assistance country/region and sector focus 2017–2023

Source: Prosperity Fund Annual Report 2019/20, October 2020

Overall, 46 countries are reached by PF programmes, although the spend in many of these countries is small. There are only seven countries in which PF spending is more than GBP 5 million[5], accounting for over 61 per cent of all PF spend that can be tracked to specific countries. Some countries that do not have bilateral programmes still have significant spend from a range of global programmes (for example, Kenya, South Africa, Nigeria and Vietnam).
[5] The countries are: Brazil, China, Colombia, India, Mexico, Nigeria and South Africa
Overview of activities supported by the Fund
The MR Hub[6] has identified key outputs delivered by PF programmes covering the period October 2018-February 2021; examples are set out in Box 1.
[6] MR Hub, Aggregated Output Results, February 2021
Box 1: Overview of activities and outputs
Ease of doing business: over 23,000 stakeholders have been engaged in capacity building activities and over 328,000 stakeholders have accessed and interacted with Prosperity Fund knowledge products and platforms as a result of the work of the Global Anti-corruption and Business Environment programmes to date. / Investment in infrastructure: 142 project concepts and pilot projects have been developed, often using UK best practice methodologies in project planning, preparation and delivery. / Human capital, innovation and technology: over 27,000 people to date have participated in PF capacity building activities related to human capital, innovation and technology, and 153 commercial opportunities for UK and international business have arisen as a result of the Fund’s activities in these areas. / Financial and Economic reform: 56 policies and practices have been reformed towards deeper and more stable, inclusive and innovative financial systems. / Trade: 400 stakeholders have been trained and 26 learning and resource platforms and tools have been developed as a result of the work of the Global IPP programme to attract foreign trade and investment.

Management and delivery status of the Fund
The Fund is overseen by the JFU. Four government departments (the FCDO, the Department for Digital, Culture, Media and Sport (DCMS), the Department for International Trade (DIT) and HM Treasury) lead the delivery of PF programmes, supported by other government departments and agencies.
The majority of the Fund’s portfolio of 26 remaining programmes[7] are now in implementation; as of December 2020, three programmes[8] have not been finally approved and have not yet started full delivery. In others (eg India Economic Reform and Prosperity Programme, Investment Promotion Programme) some components were active, others had not been fully approved.
[7] To date, two programmes have exited the Fund: Caribbean Marine Economies, which transferred to the Conflict, Stability and Security Fund in 2018, and the UK-India Green Growth Equity Fund, which transferred to DFID (now the FDCO) in 2020.
[8] China Phase 2 and 3; Turkeyl.
Delivery of the Prosperity Fund has been significantly slower than originally intended due to a lengthy design, procurement and start-up phase[9], which is reflected in the level of spend to date. Figure 3 sets out the total value of spend to the end of the 2020/21 financial year, compared to what was forecast at the start of the 2017/18 financial year.
[9] See Fund-level Evaluation cycle 1 and Evaluation cycle 2 reports.
The Independent Commission on Aid Impact[10] noted that the design and implementation of the Fund over a five-year period was an overly ambitious timescale. The JFU recognised the need for more time, requesting a two-year time extension; this is subject to confirmation through the Spending Review process underway during this evaluation.
[10] Independent Commission on Aid Impact, The cross government Prosperity Fund – a rapid review, February 2017.
Figure 3: Actual vs planned PF programme spend as at Dec 2020

Source: Generated in February 2021 using data on PF spend recorded in the Prospero database
In April 2018, it was anticipated that the Fund would have spent GBP 906 million by March 2021. The actual spend to date is GBP 518 million, representing an underspend of GBP 388 million, or 43 per cent of the intended total.
In the 2020/21 financial year, Fund programmes are forecast to spend GBP 221 million against an allocation of GBP 240.5 million. This is a 28 per cent increase on the GBP 172.6 million spent in the previous financial year. Annex 3 (Background on Prosperity Fund) provides details on the overall budget allocation per programme for the 2020/21 financial year, with the actual and forecasted spent as at the end of December 2020.
# Prosperity Fund results in 2020/21
## Primary purpose
The Fund’s results in 2020/21 demonstrate progress towards achieving its primary purpose. At least 12 PF programmes are now delivering results at the intermediate outcome level[11]. This contrasts significantly with the situation at the end of 2019/20, when not all programmes had started implementation and there were only isolated examples of programmes achieving intermediate outcome results.
[11] Progress towards its objectives is assessed here in terms of the achievement of intermediate outcomes at programme level, rather than for the Fund as a whole.
Intermediate outcome-level results are results that fall outside the Fund’s direct control. They are significant, therefore, because they demonstrate that partner governments and agencies are involved in working towards programme objectives. The achievement of intermediate outcome-level results represents progress on the pathways towards delivering overall objectives, and as such, demonstrate that programmes are working as intended. Although the strength of evidence for the Fund’s contribution to these results varies (see Annex 7, Section 7.2) there is good reason to judge that the Fund is making progress towards its goals of supporting reforms in partner countries that will promote inclusive growth.
Illustrative examples of some intermediate outcome-level results are provided in Table 1[12].
[12] See Table 6 in Annex 7 for summary descriptions of all results at intermediate outcome level or above identified for this study.
Table 1: Illustrative examples of results at intermediate outcome level
PF programme	Example of results
ASEAN Economic Reform	Vietnam and Myanmar integrated international standards and good practice into judicial mechanisms for reducing corruption, using advice from programme-funded experts.
ASEAN Low Carbon Energy	In Thailand, a bank and a renewable energy generator each issued green bonds after the programme raised awareness of green bonds and provided technical support. Worth GBP 270 million in total, the green bonds are an important step in developing markets for green finance in South East Asia.
Centre for Disaster Protection	Malawi, Pakistan, the Philippines and St. Lucia developed or strengthened their disaster risk financing policies with technical assistance from the programme.
China Phase 1	Three business environment reforms were adopted in China with advice from the programme. These include the country’s Foreign Investment Law, the revision of its Anti-Monopoly Law and the Chinese Supreme Court’s judicial interpretation of force majeure clauses in contracts – the latter responding directly to the COVID-19 crisis.
Colombia	The programme supported the development of a digital marketplace app (Listo), giving 1,980 farmers in the pilot phase access to wider networks to buy and sell products. Participating farmers have seen prices for their produce rise by up to 23 per cent.
Digital Access	Nigeria developed its National Broadband Plan 2020–25 with programme support. By implementing its National Plan, Nigeria will expand connectivity and achieve 70 per cent broadband penetration by 2025.
Global Anti-Corruption	The International Anti-Corruption Coordination Centre, funded by the programme, contributed to the Malaysia Anti-Corruption Commission recovering USD 300 million of assets in the 1MDB case.
Global Finance	The Bank of Bangladesh and Ministry of Finance established a Regulatory Sandbox based on advice provided by the programme, enabling fintech start-ups to develop, test and launch products.
Global Infrastructure	The UK’s Five Case Model for infrastructure planning was adopted for 41 major projects in Indonesia and two projects in Colombia, and Five Case Model principles were integrated into national guidance in both countries through programme support.
Mexico	The programme financed a pilot scheme in the city of Guadalajara extending a fare subsidy system in peripheral areas to promote low-carbon transport benefitting poorer people.

As illustrated in Figure 4, some sectors are out-performing others in the realisation of results.
Figure 4 shows that the greatest proportion of intermediate outcome results occurred in the Ease of Doing Business sector (14 results) and Investment in Infrastructure sector (10 results). The proportion for other sectors is lower – Financial and Economic Reform accounts for eight results and the Human Capital, Innovation & Technology and the Trade sectors each account for three results. The range of factors that have supported the achievement of results are explored in Annex 7.10.

Figure 4: Number of reported results at intermediate outcome or higher level, by the five intermediate outcomes

Source: Analysis of results from document review
Within the Ease of Doing Business sector, a notable high performing programme is the Global Business Environment Programme. Some of the significant reforms which the programme contributed to are set out in Box 2.
Box 2: Global Business Environment Programme results
Nigeria improved its business regulations framework by reducing the time and cost to start and operate a business. As a result, the time to start a business was reduced from 14 to 8 days in Kano and from 10 to 7 days in Lagos. These figures represent a more than 30 percent reduction in the time to start a business in Nigeria, which positioned Nigeria among the top 10 improvers in the Doing Business 2020 report. / Brazil streamlined its Anti-Dumping Framework by adopting regulatory reforms. Between April 2019 and July 2020, the Ministry of Economy already issued 22 public interest reports in antidumping investigations based on the reformed framework, and seven of them led to either the reduction, suspension or elimination of antidumping measures due to public interest reasons. / Brazil has also established a Direct Investment Ombudsman (DIO) and introduced an online DIO portal enabling officials to receive, track and follow up on investors’ grievances. Between its inception in April 2019 and October 2020, the cases that have been solved through the DIO amount to USD 830 million in FDI and expect to create approximately 4,100 new jobs. / The Philippines strengthened the regulatory framework around the 2018 Ease of Doing Business Act, enabling the full implementation of this foundational law. As a result, the Anti-Red Tape Authority issued notices to automatically approve more than 7,000 pending permit applications across different government entities. This reform is expected to reduce firms’ compliance costs through a reduction in the time and number of procedures to obtain required permits and licences.

Source: Improving Business Environment for Prosperity, Reform Stories, World Bank
## Gender and inclusion
Progress has been made by programmes across the Fund towards delivering positive results for women and excluded groups. In a few programmes, change has already been achieved for some groups of end beneficiaries: this includes increasing incomes and access to markets for women farmers in Colombia, enabling poor farmers and women farmers in China to claim insurance pay-outs for weather-related crop damage and helping women on low incomes in peripheral urban areas in Mexico access public transport at lower cost.
However, most gender and inclusion (G&I) results delivered so far are at the level of activities or outputs, not outcomes. Examples of outputs achieved include:
- developing tools to help policy makers better target reforms and avoid negative impacts of regulation, policies and laws on women and excluded groups (Global Business Environment and Global Trade)
- raising public and private sector awareness on employment equality issues (Future Cities, Global Business Environment, ASEAN Economic Reform)
- delivering skills, knowledge and networking opportunities targeted at women or excluded groups (Colombia, Global Business Environment, Global Anti-Corruption)
- more equitable participation and representation in meetings and training (ASEAN Low Carbon Energy, ASEAN Economic Reform, Colombia, Global Infrastructure and Global Anti-Corruption)
- filling G&I data and knowledge gaps (ASEAN Economic Reform, Global Business Environment, Global Trade).
These outputs have the potential to improve the lives of target beneficiary groups, albeit over time (as anticipated when programmes were designed). The Fund mainly seeks to make an impact by promoting institutional and policy reform rather than delivering benefits directly to beneficiaries. While this approach has the potential to achieve systemic change, it also means that positive impact for most ultimate beneficiaries will mostly emerge over the longer term and beyond the lifetime of PF programmes.
The fact that most results are outputs at this stage is therefore not a criticism. Indeed, there are signs that the PF is beginning to influence partners’ institutional ways of working. This includes revising planning, policy making, funding, employment and contracting processes so they are more responsive to the needs of women and excluded groups. Some regulatory and legal reforms supported by the Fund also have the potential to benefit women and excluded groups. Examples where this has occurred include the Centre for Global Disaster Protection, Global Anti-Corruption, Colombia, Global Future Cities, Brazil and ASEAN Low Carbon Energy and Global Business Environment programmes.
Examples of how programmes are likely to benefit women and other excluded groups are indicated in Box 3.
Box 3: How the Fund is contributing to changes that should make lives better for women and excluded groups
- The Five Case Model promoted by the Global Infrastructure Programme mandates preparation of an economic case considering social and environmental impact in detail. For the first time in Colombia and Indonesia, social impact is being formally and fully considered in infrastructure decisions.
- Green bonds supported by the ASEAN Low Carbon Energy Programme will have a long-term positive impact on poor women and socially excluded people – groups disproportionately affected by climate change. Financing from the bonds will be used for forestry and environmental conservation projects, expected to benefit 10,000 farming communities, and reforest up to 80,000 hectares of land.
- The Global Business Environment Programme is supporting regulatory reforms in a number of countries to make doing business easier for small or medium enterprises. Given that the majority of female-owned businesses are small, women entrepreneurs are likely to benefit from these reforms.
However, despite good progress this year, the Fund’s G&I impact is unlikely to match original aspirations as embodied in the Fund’s own minimum standards for G&I. There are still weaknesses in the way G&I issues are addressed across the portfolio, despite significant improvements in the last year and the strong performance of some programmes. The legacy impact of a slow start in embedding G&I in programme design has also hampered performance across the portfolio.
Figure 5 below presents the aggregate results for 17 PF programmes assessed using EL’s G&I Scorecard, which measures G&I programme performance against the minimum-level G&I standards set by the Fund[13]. Year-on-year improvements are evident in each of the scorecard’s dimensions, which cover delivery partners, accountability, capability and incentives, and programme design.
[13] Although only five dimensions feature in Figure 5, the G&I scorecard has six dimensions. The dimension on results was not assessed in 2020/21; a sixth dimension assessing if programmes had equity indicators in their VfM strategies has also been excluded as insufficient evidence was available for many programmes.

Figure 5: Percentage of programmes reaching minimum standards, by G&I scorecard dimension

Source: E&L G&I scorecard ratings for programmes assessed in 2019/20 and 2020/21
Despite the progress made by programmes in G&I this year there are still significant weaknesses. An internal PF assessment found that some programmes are unable to fully articulate their approach or contribution on G&I, and that G&I considerations needed to be ‘reprioritised’ in delivery of the Fund.[14] Of the 17 PF programmes reviewed using the Scorecard in Year 3:
[14] Minutes of the October 2020 PF Portfolio Board meeting.
- Three programmes do not yet meet the Fund’s minimum standards in terms of design (Centre for Disaster Protection, ASEAN Economic Reform and some components of China Phase 1) or capability (Centre for Disaster Protection, Brazil and Global Anti-Corruption).
- Only 11 programmes meet PF standards in terms of having delivery partners with sufficient and high-quality G&I expertise (Centre for Disaster Protection, ASEAN Economic Reform, Brazil, China Phase 1, Global Finance and Global Anti-Corruption do not).
- Only ten programmes achieve minimum standards in accountability for G&I progress (Centre for Disaster Protection, ASEAN Economic Reform, Brazil, China Phase 1, Global Finance, Global Anti-Corruption and Global Infrastructure do not).
Annex 7.4 and the separate G&I thematic synthesis report provides more detailed analysis of the Fund’s G&I performance.
## Is the Prosperity Fund on track?
The Fund has underspent by 43 per cent against the total budget over its lifetime, as indicated in Figure 3. Given the scale of this underspend, the Fund is not on track to deliver its objectives within the timescale originally anticipated[15], even though it is now starting to deliver results at intermediate outcome level. As reported by senior stakeholders, more progress was anticipated at this point in time than has been achieved. Spending by the Fund in 2020/21 should also have been at its peak given its projected close in 2022. While the Fund’s trajectory is positive and output performance according to the majority of Annual Reviews in 2020/21 is strong (see below), the key finding from last year’s Fund level evaluation still holds true: the Fund’s impact will be substantially lower than expected, unless programme timelines are confirmed up to 2023 and in some cases extended beyond this date.
[15] The evaluation team acknowledged that Fund has a 10-year timeframe for delivery of impact as set out in the business cases. While only four of the 10 years has lapsed and there is time left to deliver impact, due to the slow initial start, the significant underspend to date and the compressed timeframe for implementation left, it is highly unlikely the Fund will deliver the impact desired in the time remaining; not enough has been done to date to establish the trajectory that will allow the anticipated results in the timeframe set in the business cases.
There are several reasons for the delays. Analysis in the 2019/20 Fund evaluation report identified that, in the early stages, progress was impeded by cumbersome decision-making structures and processes, as well as the challenges faced by other government departments, which were not experienced in ODA programming. These issues negatively impacted on the time taken by programme design, procurement and set up.
Despite hard work by the PF programmes over the past 12 months, delays have been compounded by other factors. These include the severe disruption caused by the COVID-19 pandemic, delayed approvals of some programmes, delays caused by the impact of a UK General Election in late 2019, the demands of the ODA reprioritisation on staff time and the resulting uncertainty, as well as the merger of the Department for International Development (DFID) and the Foreign and Commonwealth Office (FCO) in September 2020.
Despite this programme Annual Review[16] scores provide a positive trajectory: these indicate that the majority of programmes are meeting expectations, in terms of delivering their current planned outputs. Table 2 below presents scores for 2020 for those programmes whose Annual Reviews could be obtained, with the scores for 2019 and 2018 for comparison.
[16] As with most ODA programmes, Annual Reviews are undertaken internally by the programme. Annual Review teams may also include staff external to programme delivery and/or external reviewers from the EL service.
Table 2: Annual Review scores for programmes 2018–2020
Annual Review Scores	2018		2019		2020
	No.	%	No.	%	No.	%
A / A+ (outputs met/exceeded expectations)	3	60%	19	83%	13	81%
B (outputs moderately did not meet expectations)	1	20%	4	17%	2	13%
C (outputs substantially did not meet expectations)					1	6%
U (unrated)	1	20%
Total	5	100%	23	100%	16	100%

Source: Annual Review reports for PF programmes
Table 2 illustrates that in 2020/21:
- Thirteen programmes (81 per cent) were rated A (meeting expectations) or A+ (exceeding expectations).
- Two programmes were rated B (moderately not meeting expectations).
- One (Global Trade) was assigned a C rating (substantially not meeting expectations).
Annual Review scores for 2020/21 provide a useful snapshot of performance at a specific point in time and demonstrate that valuable results are starting to be achieved. However, they do not contradict the broader point made above, that initial delays in procurement and set-up, slower than hoped for implementation and the substantial underspend means the Fund is not on track to achieve its ambitions in the timeframe set out.
Annual Review scores suggest a positive story – that programmes are generally delivering intended outputs. With sufficient time and budget, programme level outputs should contribute to intermediate outcomes and outcomes at Fund level. However, while Annual Reviews are a useful management tool (for example allowing the Fund’s Portfolio Board to identify areas of poor performance and ensure these are acted on), the scores in them should be interpreted with caution. Annual Reviews for UK aid projects have been shown to tend towards over-optimism[17]. They also track logframe results, which may change (increase ambition up or down) over the course of the programme, and focus on delivery of outputs, rather than higher levels of the results chain.
[17] . See for instance https://aidleap.org/2016/03/14/i-analysed-600-of-dfids-annual-reviews-heres-what-i-found/.
## Secondary benefit achievements
Secondary benefits are commercial benefits for business, including UK firms, generated as a result of PF programmes (but not from programme delivery contracts). These include exports, market access (including imports), overseas direct investment by UK firms, foreign direct investment into the UK by foreign firms and development of networks. Secondary benefits also include soft power, which mainly benefits the UK government and its institutions[18].
[18] ‘Soft power’ is described as a nation’s ability to attract and persuade, rather than coerce or buy the outcome it wants. Secondary benefits can enable each other – in particular, soft power and network effects can facilitate commercial wins such as overseas direct investment or exports. The experience of the PF shows secondary benefits can be delivered before, after, and in parallel with working towards the primary purpose.
To date the Fund has contributed to GBP 1.62 billion of exports and investment. This illustrates that the PF has been able to create benefits for international business, including UK firms, in addition to working towards its primary purpose of promoting inclusive economic growth and alleviating poverty. Inclusion of secondary benefits in the Fund’s objectives was innovative, and while implementation required experimentation and learning, the PF has been able to deliver notable opportunities for the private sector, including UK firms (see Box 4 below).
Box 4: Examples of commercial secondary benefits
- The Brazil Programme has supported two export wins worth GBP 22 million in the Energy sector.
- The Mexico Programme has contributed to export wins worth GBP 41 million in water, infrastructure, fraud detection and financial payments.
- In Colombia, the PF programme has led three UK companies in setting up in the country and creating six partnerships, including UK firms and universities.
- The Global Infrastructure Programme has promoted UK-developed programme management techniques, placing UK companies in a good position to support partner countries with advisory services. The programme team also strengthened the UK’s commercial offer embodied in a UK technical assistance agreement with the Government of Peru’s Reconstruction Authority, estimating UK firms will ultimately derive benefits worth GBP 100 million from this.
The PF has been successful in creating opportunities for SBs and contributing to their delivery, including by identifying barriers and overcoming them. Programmes have developed strategies to address barriers to commercial activity and SBs. These barriers can include:
- Lack of awareness in the business community of the opportunities generated by the PF: PF programmes have developed strategies to overcome this issue. For instance, the Smart Cities Programme of the India Economic Reform and Prosperity Programme has raised awareness of opportunities among potential suppliers, as well as showcasing UK supplier expertise to partner governments.
- Initial lack of knowledge about economic sectors and their supply chains within programme teams: Non-ODA support from DIT sectoral experts has been successful in addressing this knowledge gap in PF teams, for example in the case of the India Economic Reform and Brazil programmes.
- Perceptions and lack of knowledge by UK companies about the partner country, in particular among UK companies new to international trade: The evaluation of the Colombia Programme identified a lack of knowledge of the local legal system as a barrier to engaging in the country.
- Regulatory barriers in partner countries, which cannot be overcome in the short term: For example, foreign architects are not able to work in India, meaning that there is no opportunity for UK registered architects to take up and benefit from SBs.
As illustrated in Figure 6 below, the SBs that the PF has created primarily represent export wins and overseas direct investment by UK firms.[19] For reasons of confidentiality, the evaluation team have not been able to assess the details of this estimate made by the JFU. However, the methodology used by the government is judged to be robust and appropriate. Evaluation reports and Annual Reviews also record some commercial SB wins, providing additional partial evidence supporting reported claims. Overall, the evaluation team’s assessment is that there is reason to accept these figures with a moderate degree of confidence.
[19] The definition of secondary benefits includes those accruing to all international companies, not just those from the UK. However, assessment of secondary benefits in this report focuses on those realised by the UK because of data availability. In many cases benefits have been recorded by secondary benefit advisors – as these were funded from non-ODA Opportunities Fund in doing so the advisers focused solely on UK companies.
Figure 6: Estimated commercial secondary benefits realised to date, by type

Source: JFU Secondary Benefits database
The value of SBs already realised is more than the anticipated spend of the Prosperity Fund budget to date. The Fund’s original ambition for SBs, as set out in programmes’ business cases, was GBP 10.7 billion over a period of 20 years.[20] The total Fund budget is GBP 1.2 billion, of which GBP 518 million has been spent to date. While SB results may not reach the totals forecasted in programmes’ business cases, realisation of secondary benefits looks likely to be a substantial and lasting achievement of the PF.
[20] The business case total of GBP 10.7 billion represents the total present value of SBs forecast over 20 years; the time period for achievement of the GBP 1.62 billion of commercial benefits is not indicated but has not been discounted to provide a present value.
The Fund has the potential to realise further SBs, on the basis of opportunities already developed. There are a number of programmes which have identified potential opportunities[21], (see Figure 7 below). Further SB opportunities are likely to be created in the future. This indicates that there is potential for the value of SBs generated from the PF’s work to grow significantly in the months and years ahead as long as the private sector is able to realise the opportunities developed by the PF. In some cases, for instance where firms from the UK or elsewhere are unaware of the opportunities created, realising these potential benefits is only likely to happen by continuing measures of the type hitherto undertaken with non-ODA funding.
[21] Several programmes have identified more than one opportunity in each category. The chart includes programmes which have reported at least one opportunity and / or one realisation of the SBs by type. Note that not all programmes reporting a realisation also have reported an opportunity, however some have. For example, eight programmes reported only at least one opportunity for Soft power. Another 8 reported only at least one realisation. One programme reported both.
Annex 7.3 provides further analysis of the types of SB opportunities reported by programmes and the number of opportunities that have been realised in practice.
Source: Evaluation Reports and Annual Reviews
Figure 7: Number of programmes realised and potential secondary benefit opportunities
Anecdotal accounts indicate that the Fund is viewed as contributing to soft power benefits in several of the countries in which it is operating. The evaluation team have evidence from evaluations on 30 instances of soft power created through the Fund’s work, a few of which are detailed in Box 5.[22], [23]
“All the ambassadors or trade commissioners I’ve spoken to have said the Prosperity Fund has been critical in terms of access and influence”
Interview with senior HMG stakeholder
[22] The JFU has accounted for 157 such instances of soft power. However, these are based on diplomatically sensitive information and because details cannot be shared by PF they could not be validated by the evaluation team, and as such are not included here.
[23] Reporting is not uniform across programmes: some programmes have only reported opportunities for secondary benefits, others only those SBs that have been realised, and some both.
Box 5: Examples of soft power created by the Prosperity Fund
- In June 2020, the ASEAN Low Carbon Energy Programme held a round table between Mark Carney, the UK Prime Minister’s Finance Adviser for COP26 and central bank governors of ten ASEAN member states to discuss greening the financial system. The programme’s SB Advisers continue to identify SB opportunities alongside initiatives of this kind.
- The Bank of England is working with central banks in Ghana, Sierra Leone and South Africa (through the Global Finance Programme), providing access at the highest institutional levels in these countries.
- In Malaysia, the UK received an award from the Malaysian Anti-Corruption Commission, reflecting UK help on law enforcement, beneficial ownership and its support in recovering assets in the country’s 1MDB scandal.
PF has also helped promote UK values, for example helping institutions in Colombia to understand issues of gender and social inclusion and how these can be integrated, for example, into infrastructure planning.
### Wider Prosperity Fund achievements
A number of wider achievements are also evident in addition to the progress towards primary purpose and SBs already described.
The Fund has shown that the concept of a cross-government ODA programme, based on the principle of mutual prosperity, is sound and can be successfully put into practice. Interviews with senior stakeholders from four government departments represented on the Fund’s Portfolio Board – the FCDO, the Cabinet Office, DIT and DCMS – highlighted different ways in which the Fund’s cross-government mutual prosperity concept has been validated in 2020/21. These include:
- demonstrating that it is possible for an ODA programme to promote the primary purpose of inclusive growth and poverty reduction, as well as delivering SBs
- engaging core government expertise in the delivery of development programmes, for example through the involvement of the Government Communication Service and DIT in delivering the Investment Promotion Programme, the Government Actuary Department in the Centre for Disaster Protection, or the Infrastructure and Projects Authority in the Global Infrastructure Programme
- extending cross-government capacity to deliver ODA programmes – several embassies and high commissions have implemented large bilateral programmes for the first time and other departments such as DIT and DCMS have extended their ODA experience.
The Portfolio Board cites the value of the PF as a successful testing ground for innovative, new or high-risk approaches. Examples that are considered unlikely without the Fund include:
- testing new initiatives, such as the Centre for Disaster Protection and the India Green Growth Equity Fund (both of these programmes have proven successful and have moved into FCDO core baseline funding)
- taking higher levels of risk than would normally be tolerated, for example in the Horn of Africa Programme, which is helping to connect the expanded port at Berbera in Somaliland with Ethiopia, currently a high-conflict region
- promoting collaboration between UK technology firms and partners in developing countries and showcasing UK digital skills through the Digital Access programme.
### Contributing to global public goods
The Fund is aligned to several of the UN’s Sustainable Development Goals (SDGs), as set out in Figure 8. The SDGs are 17 global public goods aimed at ending poverty and hunger and ensuring access to adequate services and building strong and stable institutions.
Figure 8: The Prosperity Fund's alignment with the Sustainable Development Goals
Source: PF Annual Report 2019/20, October 2020.
Given that programmes have only recently begun to deliver results at intermediate outcome level, alignment with the SDGs largely represents the potential for the Fund to contribute to these goals over time. Examples of the ways in which this is likely to be achieved include:
- addressing climate change – an internal review in May 2020 found 99 per cent of PF activities to be aligned with UK commitments under the Paris Agreement; the other 1 percent have since been modified, to ensure alignment. Box 6 below provides an illustrative example of the Fund’s work to address climate change.
- promoting improved global financial stability through improved regulatory environments and reducing exchange rate risk by supporting development of local currency finance (Global Finance)
- supporting international institutions such as the UN Office on Drugs and Crime, International Anti-Corruption Coordination Centre, or Extractive Industries Transparency Initiative (Global Anti-Corruption) which work more broadly at a global level
- pivoting by PF programmes to support the response by the UK and partner countries to the COVID-19 pandemic, contributing to SDG 3 on health and wellbeing.
Box 6: Examples of the range of climate change programming across PF
ASEAN Low Carbon - Facilitating green finance and improving the regulatory and policy conditions for energy efficiency / Brazil: Green finance – advising two Brazilian development banks on adoption of Environment, Social and Governance standards and providing a platform for matching international investors interested in investing in sustainable infrastructure / Centre for Global Disaster Protection Supporting countries to insure against the risks of natural disasters, many of which are linked to climate change / China - Energy and Low Carbon Strand supporting clean energy, green goods and services. Financial Services strand developing weather index insurance for poor farmers to mitigate climate change risks / Indonesia Renewable Energy - advising on policy, regulation and financial instruments; brokering investment; financing demonstration projects; and networking and collaboration between domestic and international renewable energy sectors / Mexico - supporting integrated urban transport. / Source: PF EL

## Do Prosperity Fund programmes deliver good value for money?
There are two dimensions to the assessment of VfM:[24] Delivery of VfM by PF programmes, which is evidenced by Annual Review assessments; and management of VfM, which is based on findings of EL VfM scorecard assessments. These scorecards evaluate programme performance annually against the dimensions listed in Box 7.
[24] Value for money (VfM) is defined as the optimal use of resources to achieve the intended outcomes; that is, using resources in the most desirable way given expressed or implied restrictions or constraints. VfM is not about securing the lowest initial price; instead, it is about delivering the greatest impact in the circumstances by using the resources available (time, money, expertise) in the most appropriate and cost-effective manner.

Box 7: Evaluation and Learning value for money scorecard dimensions
1. Relevance and robustness of VfM measures in place
2. Approach to procurement and cost containment
3. Efficient use of resources and inputs by PF interventions
4. Validation of PF Theory of Change causal pathways (for primary purpose and SBs)
5. Sustainability of programme activities
6. Ability of leadership, management and oversight structures to support programme teams
7. Strategies and measures adopted to enhance delivery and mitigate risk
8. Equity of programme design and approach
Source: PF EL
Based on the EL review of qualitative evidence in 16 Annual Reviews, all but one of the PF programmes (the Global Trade Programme) have the potential to deliver VfM given enough time. More detail on the analysis is in Annex 6. Eight programmes are viewed as on track to deliver VfM without notable risks, and seven programmes are expected to deliver VfM, assuming some specific risks are addressed.
Progress on management of VfM has also been made over the past 12 months. The seven programmes for which an assessment of the direction of travel could be made (those programmes with a second cycle of evaluations in 2020) all demonstrate an improvement to VfM systems and processes over time. Specifically, governance and management systems have improved, and programmes with complex partnership networks, for example, have taken time to establish effective systems. These improvements have helped address the challenges of working with multilateral partners that have their own structures in place, which can limit PF oversight of delivery.
However, performance against VfM dimensions varies across the portfolio. Programmes that are on track against the VfM scorecard have cost containment measures or mechanisms for monitoring and managing VfM in delivery in place. They are delivering activities and outputs on time and have good systems to manage the work of their implementing partners.
Challenges to VfM are operational risks in many cases, such as implementation delays or staff shortages. Many programmes still lack well-developed VfM indicators focused on the key dimensions of VfM (namely economy, efficiency, effectiveness and equity). The absence of VfM indicators reduces the programme’s ability to track VfM and mitigate any shortcomings. A lack of overall programme VfM frameworks and management tools also makes it more difficult to spot when corrective actions need to be taken to deliver VfM.
To ensure the ability to deliver VfM PF programmes will need to revisit plans to deliver envisaged results. COVID-19 and ODA reprioritisation resulted in adaptations and delays during this financial year. As such programmes should ensure that programme outputs and intermediate outcomes are still contributing to the achievement of intended outcomes and impact as set out in original programme designs.
The biggest VfM risk to the PF is the time available to the end of programmes. Due to the slow start to delivery and the contextual challenges this year, which hampered quicker progress, the timeframe remaining to achieve impact is compressed. As a result, the PF is unlikely to deliver to the level initially envisaged in the programmes’ business cases, and for which it had potential.
## Is the Prosperity Fund learning?
The PF is actively engaged in capturing and using learning to improve delivery at programme level. There are increasingly successful mechanisms for review, feedback on and analysis of programme performance in place. These processes have been effective in helping to generate learning, which has been used to support programme improvement.
There are opportunities for cross-Fund learning. Stakeholders interviewed suggested that one of the key benefits of managing the PF as a portfolio had been the scope for learning lessons, using communities of practice, thematic evaluations, the PFLearning website and conferences and regional meetings as platforms for sharing learning across programmes.
At a programme level, there is clear evidence of active learning within programmes, both in country and across programmes. Global programmes have been particularly successful in sharing learning, likely due to their inherent ability to more easily engage across different countries and teams.
However, the capacity to generate and engage with learning was somewhat disrupted this year due to the pressures that COVID-19 and ODA reprioritisation placed on PF programme teams and resources. Programme teams had other pressing priorities, and faced challenges due to restrictions on travel and engagement across multiple time zones, in addition to reduced EL learning resources.
A more detailed discussion of learning across the Fund is provided in Annexes 7.12.
# The impact of challenges faced in 2020/21
The Prosperity Fund faced a number of challenges the past year; while the Fund adapted well to the COVID-19 crises, the ODA reprioritisation process was challenging. Challenges faced are likely to have a permanent impact on the ability of the Fund to deliver the results desired in the time available.
The Fund helped deliver the government response by deliberately retargeting work to respond to the COVID-19 crisis. Early in the pandemic, the government identified the Fund as well placed[25] to support the third of four priority responses to the crisis: “Economic Response: Keep Trade Flowing and Supply Chains Open”. The JFU set out plans for 15 PF programmes to provide either a direct response to the COVID-19 pandemic or provide support to partner countries to cope with its secondary impacts. Evidence from interviews and document review verified that 12 of the 15 programmes that planned in April 2020 to directly respond to the pandemic had executed these plans (there was insufficient evidence to assess if the other three programmes achieved this). Box 8 presents some examples if PF programme adaptations to support the response to the COVID-19 pandemic.
[25] JFU, Information Note on PF engagement in HMG’s international C-19 response, March 2020.
Box 8: Examples of PF programme adaptations to the COVID-19 pandemic
- The India’s Skills Programme worked with the WHO to support training and capacity building for over 200,000 front-line health workers and 200 lab technicians.
- The China Business Environment Programme influenced the China Supreme People’s Court guiding opinions on handling civil cases involving the COVID-19 pandemic by providing examples of best practice in addressing force majeure.
- The Digital Access Programme provided support on telemedicine and affordable connectivity for health centres in remote locations.
- Programmes also responded well to the realities of the pandemic, and not only identified new - mostly successful – ways of working, but also adapted programming in the light of PF priorities in a number of cases. Programmes that could, pivoted to remote delivery, demonstrating both flexibility and capacity to manage a broad number of delivery partners and approaches remotely. Although most programmes were able to move delivery online, this was not always possible, particularly where relations with counterparts were not yet fully developed or where it was simply not possible to use online tools. While programming adaptations are evident across the portfolio, programmes in the health, financial, business environment reform and human capital, innovation and technology sectors reacted particularly strongly.
- Action was taken to ensure programmes had access to relevant, up-to-date information to inform programme adaptation as the context changes. By using the established cross-Fund learning and knowledge sharing platform (PFLearning), programme teams were able, within days, to draw on a COVID-19 resource hub, which offered a reliable, independent resource[26] for adapting their work. The hub was populated by information provided by DFID’s Knowledge, Evidence and Learning for Development Programme (K4D),[27] ensuring cross-government resources were shared effectively.
  [26] See, for example, PF Portfolio Board Minutes June 2020
  [27] K4D is a five-year programme running to September 2021 to support the use of learning and evidence to improve the impact of development policy and programmes. It is funded by UK aid and is designed to assist the Foreign, Commonwealth and Development Office (FCDO) and other UK government departments and partners to be innovative and responsive to rapidly changing and complex development challenges.
- The COVID-19 crisis and the ODA reprioritisation process diverted PF staff from delivery right at a time that the Fund was hitting its stride, as it was working hard to pull out of the slow initial delivery phase and starting to deliver results. For example, at least 40 of the 270 government’s programme team members were released to support crisis response, including procurement of personal protective equipment and citizen repatriation efforts. Partner governments were also preoccupied with the crisis and were often unavailable to progress programmes. The impact of the COVID-19 pandemic and the ODA reprioritisation process will have a lasting effect as it has further reduced the likelihood of the Fund delivering the level of results hoped for in the timeframe available for implementation.
- The ODA reprioritisation process was time consuming. Reprioritisation was handled through a two-stage process. Feedback from senior stakeholders indicates that the process was generally consultative, but required substantial time and focus, creating uncertainty and distracting the PF from delivering results (see Annex 7.7 for further discussion of the process).
- The ODA reprioritisation process also resulted in reduced funding for the PF, although this was, in large part, achieved through deferral of spend. Reductions in planned activities and the pausing or cancellation of some workstreams were achieved via deferral of spend to future years. Given that about 60 per cent of the budget adjustments were deferrals of spend, there is a risk to delivery of results if further cuts are needed in future or if this deferred spend cannot be executed in the coming financial year.
- Despite the cuts, senior stakeholders interviewed indicated that ODA reprioritisation has not significantly damaged stakeholder relationships notably to date and is deemed in the case of some programmes to have improved delivery focus and overall VfM, although there is some perceived increase in risk. A small number of stakeholders perceived that ODA reprioritisation, which was focused on achieving reductions in the in-year calendar spend (April -December 2020), had in avertedly helped to improve the Fund’s VfM by “weeding out weaker elements”; others noted that VfM could be at risk where there is a need for programmes to maintain a certain level of critical mass to deliver results. However, the evaluation team notes that reported delivery confidence across the PF portfolio improved slightly between quarters 1 and 2, and even further in the third quarter of the financial year.[28]
  [28] PF Portfolio Board Report, December 2020 and additional data on quarter 3 provided by the MR Hub. Delivery confidence is based on self-reported data from programme teams reported in their quarterly reports.
- However, Fund stakeholders expect the responses to COVID-19 and ODA reprioritisation to reduce overall results. They believe delivery of the longer-term economic development ambitions of the Fund are challenged by the contextual changes over the past year. Some stakeholders reported that the COVID-19 crisis has slowed down progress with implementation; others reported the emergence of a more short-term focus on COVID-19 interventions, rather than the longer-term economic development initiatives that the Fund was originally designed to deliver. As set out above, the impact of COVID-19 and the ODA reprioritisation process is likely to be lasting and further limit the PF’s ability to deliver the anticipated results in the time available.
See Annex 7.8 for further analysis on the impact on results of COVID-19 and the ODA reprioritisation process.
# Reflections on Prosperity Fund results
In addition to helping to capture results and consider progress and performance of the PF, this annual evaluation also considered the factors that have contributed to or hindered achievements (EQ 2), with the aim to learn from the Fund’s experience to improve ongoing and future programming (EQ 3). Further analysis of the points made below is included in Annexes 7.9 and 7.10.
## Factors supporting achievement of results
Flexible and adaptive approaches to management are a key factor in generating results. Across Annual Reviews and evaluations, programmes report that they were successful in adapting to respond to external pressures and, in many cases, to hone and better target their programming on key priorities.[29] Evaluations found that this was clearly demonstrated with COVID-19 responses. Stakeholders noted that there would be benefit in having a flexible financial resource, held centrally, to support interventions when windows of opportunity opened up, or in response to emerging priorities.
[29] See further discussion on challenges above.
Programmes have built effective networks that contribute to producing results. About half of programme evaluations identified networking (that is, effective partnerships with a range of stakeholders) as a key success factor. Programmes note that multilateral delivery partners, in particular, integrate networking into their delivery models. Networking and coordination between different embassies, and within programme teams has also grown during this financial year, contributing to programme improvement by sharing ideas and approaches. This is observed both through programme evaluations and via PFLearning-based interactions.
The refinement of governance structures to suit local requirements contributes to achieving results. A number of Annual Reviews and evaluations pointed to the value of amending governance structures to suit local needs and to improve strategic focus. Engagement by Heads of Mission also increased; where Ambassadors and other senior Embassy staff have engaged with both the PF staff and the partner government, there has been a significant mutual benefit.
Alignment of priorities with external (particularly government) stakeholders continues to be critical for successful Fund programming. It is important to align programming with stakeholder priorities to achieve results. For global and regional programmes, this is a complex task that has to be undertaken with each partner government, requiring time and effort to tailor interventions to each national context. Alignment of priorities also requires understanding of the capacity of government counterparts in different countries. This can vary significantly, in particular where PF programmes support sub-national levels of government. PF programmes have needed to be flexible in providing support to partners at different levels of government.
Unsurprisingly, government and delivery partner capacity largely determine the ability to deliver results. A number of PF reviews and evaluations point to the importance and value of experienced implementation partners: early results are often credited to high-quality, respected partners. Despite the challenges of managing a multilateral partner where programme teams have had limited experience of doing so, of all implementing partners the World Bank was repeatedly singled out for the benefit its experience, expertise and its long-standing relationships with government partners brought to programme delivery. Stakeholders engaged in global sector programmes pointed to the benefits of having a programme overseen by those with deep technical sectoral expertise, rather than by non-technical Programme Managers. This allows them to be able to challenge implementing partners and make a significant contribution to programme direction.
Drawing on UK government technical expertise and offering government-to-government support proved successful. Programmes involving the National Health Service (NHS), Infrastructure and Projects Authority, Intellectual Property Office and Regulatory Delivery International all attracted counterpart attention and interest for their expertise and knowledge. Several counterparts valued this government-to-government model of delivery, which also supports the UK government’s economic diplomacy and contributes to soft power.
Cross-programme linkages allow for learning and implementation support, which can contribute to delivering results, though not to the extent originally envisioned for the Fund. Although most programmes are only now in full implementation – the time when sharing lessons and building linkages is most fruitful – issues such as COVID-19 and ODA reprioritisation appear to have led to cross-Fund learning and knowledge sharing being a lower priority in the past year. There are good examples, however, of coordination between bilateral programmes working in the same sectors. The Mexico PF and Global Finance programmes have worked together on fintech, and Mexico was a new country for the Global Finance Programme Catalyst Fund operations in 2020. The Brazil bilateral programme has also worked effectively with a number of global programmes in the same sector as its components. Likewise, some global programmes have been able to develop linkages with other global sectoral programmes, to better enable synergies. For example, the FCDO, DIT, HM Treasury and DCMS share a common interest in fintech and there is scope to improve cross-working through shared learning[30] between fintech workstreams.
[30] Financial and economic reform sector summary Cycle 1 Sector Report, 2020, p.8
## Factors hindering achievement of results
A wide range of context specific factors were identified by programme teams as hampering the delivery of results, although there is some overlap between programmes. On average, each programme identified nearly four factors hindering the delivery of results in that programme. Across all Annual Reviews and evaluations of specific programmes, 88 different factors impacting delivery of results were cited. The number of times each factor was identified is explored in Figure 9. The COVID-19 pandemic was the most often cited factor (20 per cent), followed by issues relating to partner country stakeholders (12 per cent) and procurement and contracting issues (also 12 per cent). Elections and political changes in the partner county are the fourth most often cited factor (10 per cent); in many cases, this finding correlates to issues relating to partner country stakeholders, as programmes need to build new relationships of trust when a government changes.
Figure 9: The range of factors identified by programmes that hinder delivery of results

Source: Analysis of Annual Reviews and evaluations
The capability and competence of implementing partners hinders delivery of results. Stakeholders note that capability and capacity vary across delivery partners and this impacted negatively on the delivery of results in some cases. This was most often observed in relation to delivery by departments new to ODA, and partner governments and smaller international organisations that had no previous experience working on development issues with the UK. While delivery by experienced government ODA partners was not always without problems, partners with more experience contributed to the faster delivery of results.
There are three factors that were not considered to be as critical as the factors already discussed. Although the ODA reprioritisation process was a distraction from delivery for programme teams, the impact of the changes in the budget were not seen as significant. Many programmes perceived that they had been able to remodel programmes and reprofile spend to adapt to the changes in funding while retaining their planned results.
Only a small number of programmes cited over ambitious programme design as a factor impacting delivery of results. Similarly, shortage of programme team staff was only a minor factor hindering delivery of results: staff shortages and challenges related to recruitment have dropped compared to the previous year; for the 2020/21 financial year, staff shortages accounted for only 5 per cent of factors cited, while in the 2019/20 financial year they accounted for 15 per cent.
## Performance of bilateral vs global programmes
There is little evidence that any one modality – bilateral, regional or global programmes – inherently provides greater benefit in producing results. The PF consists of 15 global, 10 bilateral and two regional programmes. The results discussed in this document were analysed by programme type (see Figure 10).
Figure 10: Results achieved by programme type

Source: Annual reviews and evaluations in 2020/21
This analysis suggests that regional programmes have overperformed in terms of delivery of results, global programmes have performed in proportion to their number, and bilateral programmes have slightly underperformed. However, there are many factors other than deliver modality that are important in terms of results (for example sector and the length of time programmes have been in implementation); as such there are no clear conclusions to be drawn at this stage in the life of PF about whether use of a specific modality is more likely to lead to results.
Although the distribution of results does not, on its own, provide any evidence about the efficacy of a particular programme design, stakeholder feedback indicates differing advantages between the two modalities. Stakeholder feedback and lessons from evaluations and Annual Reviews indicate that there are advantages to both types of programme as per Table 3.
Table 3: Advantages by programme type
Bilateral Programme Advantages	Global Programme Advantages
Bilateral programmes allow for in-depth knowledge and understanding of the local economic and political context. / Bilateral programmes can ensure effective coordination at Embassy level. / Heads of Mission and senior members of the political team have direct oversight, and can get involved not only in design but to support delivery. / Delivery of SBs was facilitated because of local understanding, and availability of other support available through the Embassy.	Global programmes have flexibility and ability to adapt, as funding can be readily allocated across different countries as opportunities arise and contexts change. / Programme management can be led by sectoral experts rather than generalists based in missions. / Sector experts who are UK civil servants can be deployed by their home department to provide government-to-government support in partner countries. / Global programmes offer real economies of scale, for example in research and data collection. / The global structure better enables learning and knowledge sharing across countries. / More likely to be working with international institutions, presenting stronger opportunities for influencing due to the respect these institutions hold. Pilots in one country can be rolled out in others with reduced additional cost.

Source: Input from stakeholders interviewed for this evaluation. A more detailed version of this table covering disadvantages as well as advantages is provided in Annex 7.5.
Heads of Mission in particular have welcomed the ability to coordinate the bilateral development programmes ongoing in their country, to shape them to meet country business plan objectives and to become involved in delivery to enhance results. Several government stakeholders also pointed to the value of regional programmes and suggested that regional approaches could combine some of the best characteristics of both global and bilateral approaches.
Bilateral programmes have reported more effective progress towards SB delivery than global programmes. However, global programmes reported more results relating to actual realisation of SB results in the areas of overseas direct investment and also soft power, even though bilateral programmes have identified more opportunities in these areas. Table 4 shows the distribution of realised and potential SBs by programme type and category of SB.
Table 4: Opportunities and realisation of secondary benefits by programme type
		Percentage of programmes	Exports	FDI	ODI	Market access	Network effects	Soft power
Opportunities	Bilateral	37%	54%	100%	83%	86%	83%	75%
	Regional	7%	0%	0%	0%	0%	0%	13%
	Global	56%	46%	0%	17%	14%	17%	13%
Realised	Bilateral	37%	62%	0%	50%	100%	71%	22%
	Regional	7%	8%	0%	0%	0%	0%	11%
	Global	56%	31%	0%	50%	0%	29%	67%

Source: Evaluation Reports and Annual Reviews for all programmes analysed.

# Lessons from the Prosperity Fund
At the Fund level, this evaluation and other evaluations this year identified several key lessons of value to future programmes:
1. Programmes can deliver primary purpose and SBs, and SBs can be delivered before, in parallel or after primary purpose. But non-ODA support and appropriate sharing of information with the private sector and beneficiary governments are usually required to help the private sector realise opportunities.
2. Both global and bilateral programmes can be successful; different modalities are useful in different contexts and to address different issues or problems. Each modality presents its own challenges and benefits but neither modality is inherently more or less likely to deliver results based on PF evidence.
3. Aligning programme priorities with partner government priorities, tailoring governance arrangements to local partner needs and involving partners in decisions around adaptation contribute to success.
4. Realistic VfM targets, ambitions and timeframes for delivery are essential. It is critical to allow enough time for implementation and to ensure efficiency in the management of procurement and contracting and programme set-up arrangements.
5. Gender and inclusion considerations need to be embedded into programme designs from the outset. Capacity and expertise in the area of G&I are needed in both the government and implementing partners throughout design and delivery phases to achieve results for women and other excluded groups. Adequate time to realise G&I results is imperative.
6. Appropriate guidance on VfM systems and processes are needed, specifically where departments and delivery teams are new to ODA programming.
7. Cross-Fund learning can be successful with enough time, investment and if this is prioritised. Learning can improve programme performance.
8. Having effective networks contributes to producing results, and the value-added of multilateral partners in this space should not be underestimated.
9. As addressed in the Cycle 2 Fund evaluation, cross-government working took time to establish. However, the ability to draw on cross-government expertise was beneficial in delivery and to generate soft power and partner counterpart engagement.
10. Large programmes can adapt quickly to changes in context, but to do this, processes and systems, including flexible funding pots, are needed; global programmes find it easier than bilateral programmes due to the ability to move funds to where opportunities are.
While this evaluation focusses on the PF portfolio, at the programme level there are some common themes identified in Annual Reviews and evaluations worth noting here:
- Lesson Theme 1: The need for appropriate and robust G&I: G&I is the most prevalent theme of lessons learned in 2020/21 by PF programmes identified in Annual Reviews and evaluations. The overarching lesson is that integration of G&I considerations has been a challenge for PF programme teams, but they have learned that a clear G&I strategy, access to specialist G&I support and effective monitoring and evaluation relating to G&I are all critical to success.
- Lesson Theme 2: Adaptive management is valuable: There are clear lessons about the benefits of adaptive management; adaptive management has also been found to be possible and make sense in complex contexts as those experienced by the PF.
- Lesson Theme 3: Ongoing revision of theories of change (ToCs), logframes and VfM are important. There has been a growing realisation amongst PF teams new to ODA of the need to review ToCs and logframes in an ongoing manner, as well as revisiting VfM claims made in their business cases, as programmes change.
- Lesson Theme 4: Grant management: While grant programmes have been effective in some PF programmes, setting up a large, formally-procured grants mechanism, to be operated by an implementing partner, can in some cases be inefficient. It requires long timescales, significant transaction costs and limited flexibility. It can also cause fragmentation. Alternative solutions might include ring-fenced call-off mechanisms managed by a supplier.
# Recommendations
As a result of uncertainty concerning the future of the Fund pending the outcome of the ODA reprioritisation exercise, two sets of recommendations are proposed in Table 5 below: for the scenario (1) that the Fund or its programmes continue delivery and (2) that the Fund and its programmes will be discontinued.
Table 5: Recommendations
Priority Order	Targeted to	Recommendation	Timeframe to act
Scenario 1: The PF continues as a Fund or programmes within the Fund continue delivery
1	Portfolio Board	The timeframe for delivery should be extended to allow progress towards intermediate outcomes and outcomes. Expectations on what can be achieved in the time available should be reviewed to be realistic; this includes careful consideration of timeframes and plans for programmes not yet in full implementation.	3 months
2	FCDO	More should be done to ensure delivery of results for women and excluded groups in accordance with the Fund’s ambitions in this area. The focus on G&I should be increased and more support on G&I should be made available to programme teams to address capacity gaps.	6 months
3	FCDO	VfM processes and systems should be strengthened to ensure all programmes more consistently have appropriate processes and systems in place, which will enable delivery of VfM. More guidance on VfM management and measurement should be provided by the centre to programme teams.	6 months
4	Programme teams	As indicated in the Year 2 Fund evaluation, programme teams should revisit VfM calculations and update logframes to ensure projected benefits are realistic within the timeframes available.	1 year
5	FDCO	Now that the Fund and its programmes are generating results, the FCDO should ensure comprehensive capture, validation and showcasing of these results.	Ongoing
6	FCDO/programme teams	As indicated in Year 2 Fund evaluation and in line with the increased government priority on climate change, and given that there are many PF programmes with climate change related components, programme teams and FCDO should develop a system for clear and regular reporting of climate change activities and results.	Ongoing
7	Portfolio Board	The Fund should continue to harness cross-government capability and inputs into delivery, in recognition of the appreciation of partner governments of its high quality and added value.	Ongoing
8	Portfolio Board	To better enable adaptive working, provision should be made for a flexible funding allocation, which can be used to respond to emerging opportunities and priority issues.	3-6 months
9	FCDO	The FCDO should continue to emphasise programme-level and cross-Fund learning and reflection, and the sharing of learning more widely outside the PF to inform design and delivery of other government programmes.	Ongoing
10	Programme teams/FCDO	As programmes move to completion, the FCDO should support programme teams though central guidance to ensure appropriate exit and sustainability plans are in place.	As programmes move to completion
Scenario 2: The Fund is discontinued (programmes stop following the ODA reprioritisation)
1	FDCO	Results to date should be captured, validated and better showcased. Specifically, results on climate change should be captured and shared in advance of COP26 in November 2021.	Ongoing
2	FCDO/DIT	The SB opportunities created by the Fund should be tracked and followed up, including through appropriate non-ODA support to the private sector, to ensure these results are realised in the future.	From now onwards
3	FCDO	Plans should be put in place to ensure results at outcome level are captured and shared after the life of the Fund (both primary purpose and SBs)	From now onwards
4	JFU/ FCDO	The JFU and the FCDO should capture and share learning (positive and negative) more widely beyond the PF. This includes lessons on the themes of: mutual prosperity; cross-government working; design, adaptive management and MREL of an ODA portfolio, lessons from adaptation in response to COVID-19, delivering ODA in middle-income countries and climate change action.	Before closure of the Fund.
5.	FCDO	Consideration should be given to how relationships established through the PF with partner government stakeholders in middle-income countries could be continued in light of ODA reprioritisation to ensure soft power benefits are sustained	Before closure of the Fund.
6.	FCDO/other government departments	Consideration should be given to the maintenance and use of cross-government staff capabilities in programme management and ODA delivery developed under the auspices of the Fund, to ensure this expertise is not eroded and remains accessible to departments.	Before closure of the Fund.