Evaluation report title and date: Overview of the Performance of the Prosperity Fund Portfolio In 2020/21: Fund-Level Evaluation Cycle 3. March 2021

Response to evaluation report (overarching narrative)
FCDO warmly welcomes this third independent evaluation of the Prosperity Fund. It sets out clearly the progress the Prosperity Fund has made over the past four years, as well as the challenges it has faced. / We are pleased to note that the evaluation finds that the Fund has shown that the concept of a cross-government Official Development Assistance (ODA) programme, based on the principle of mutual prosperity, is sound and can be successfully applied in practice. The evaluation also found that the fund has made good progress towards delivering the primary purpose of poverty alleviation through inclusive economic growth, and that we contributed to delivering commercial secondary benefits (exports and investment) for business (including UK firms) that are valued at over three times the total amount the fund has spent. We are also encouraged to note that the evaluation found that our response to the challenges of the COVID-19 pandemic was proactive and flexible. We accept that the original time scale for the Prosperity Fund was over ambitious and the time it took for programmes to complete set-up, design and procurement activities was longer than we had anticipated. / The Prosperity Fund closed on 31 March 2021 and prosperity programming transferred to the Foreign, Commonwealth & Development Office. This management response provides FCDO’s response to the recommendations under this scenario. The Management have accepted all the recommendations and provided details on our response to each recommendation below.

Recommendation	Party that recommendation is directed to	Accept, partially accept or reject	If “accepted” or “partially accepted”, give action plan for implementation and if “rejected” or “partially accepted”, give reason for rejection / only partial acceptance	If “accepted” or “partially accepted”, expected completion date
Results to date should be captured, validated and better showcased. Specifically, results on climate change should be captured and shared in advance of COP26 in November 2021.	FCDO	Accept	All programmes capture publish their results online through programme annual reviews and programme completion reports. Where programmes are working to address climate change, relevant indicators are included. / Now that the Prosperity Fund has closed, prosperity programming transferred into the FCDO; all programmes will continue reporting their results through programme annual reviews and programme completion reports.	Ongoing
The “Secondary Benefit” opportunities created by the Fund should be tracked and followed up, including through appropriate non-ODA support to the private sector, to ensure these results are realised in the future.	FCDO/DIT	Accept	FCDO gave programme teams chance to bid for additional non-ODA in 2021/22. Several programmes submitted bids that aim to realise Secondary Benefit opportunities to which the Prosperity Fund contributed. / The viability of a systematic approach Secondary Benefits tracking is under review.	Ongoing
Plans should be put in place to ensure results at outcome level are captured and shared after the life of the Fund (both primary purpose and SBs)	FCDO	Accept	As per the first recommendation, all programmes capture publish their results, including at outcome level, online through programme annual reviews and programme completion reports.	Ongoing
The JFU and the FCDO should capture and share learning (positive and negative) more widely beyond the PF. This includes lessons on the themes of: mutual prosperity; cross-government working; design, adaptive management and MREL of an ODA portfolio, lessons from adaptation in response to COVID-19, delivering ODA in middle-income countries and climate change action.	JFU/FCDO	Accept	We agree that much has been learned through the Prosperity Fund and we are committed to sharing that learning. / In April 2021 we shared key lessons on the Prosperity Fund as whole plus targeted sessions on gender and inclusion, and secondary benefits with hundreds of colleagues across FCDO and other government departments. Many staff who worked on the PF continue to work on related issues and will thus be able to build on what we learned. FCDO maintains a repository of lessons/learning: all material from “PF Learning” was transferred to an internal site for use within the FCDO.	Ongoing
Consideration should be given to how relationships established through the PF with partner government stakeholders in middle-income countries could be continued in light of ODA reprioritisation to ensure soft power benefits are sustained	FCDO	Accept	Even though the Prosperity Fund has closed, many of the programmes are continuing. Furthermore, we are building a prosperity network in FCDO to sustain not only PF relationships but bringing them together for future impact on building Economic Partnerships. Additionally, all Embassy staff continually engage with host governments.	Ongoing
Consideration should be given to the maintenance and use of cross-government staff capabilities in programme management and ODA delivery developed under the auspices of the Fund, to ensure this expertise is not eroded and remains accessible to departments.	FCDO/other government departments	Accept	We recognise that staff capabilities in ODA delivery have been built through the PF. FCO staff working on the PF are now part of the FCDO and so will be central to delivering the Department’s priorities, including on ODA.	Ongoing