Evaluation report title and date: Prosperity Fund Year 3 Secondary Benefits / Evaluation, April 2021

Response to evaluation report (overarching narrative)
We welcome this evaluation and its findings. We find the evaluation’s conclusions encouraging. Notably, that Prosperity Fund programmes have delivered substantial benefits to the UK and wider world, whilst focusing on poverty alleviation through economic growth in partner countries; that secondary benefits have arisen earlier and in more ways than expected; and that further secondary benefits are likely. / The evaluation also makes useful observations about barriers to achieving greater secondary benefits. Most of these barriers relate to awareness and understanding and arose due to the novelty of the Prosperity Fund’s approach. We agree with the evaluators in concluding that staff and partners have mostly learned how best to combine programmes’ primary purpose (inclusive growth) with the pursuit of secondary benefits, overcoming many of the barriers. / The Prosperity Fund closed on 31 March 2021 and prosperity programming transferred to the Foreign, Commonwealth & Development Office. This management response provides FCDO’s response to the recommendations under this scenario. The Management have accepted all the recommendations and provided details on our response to each recommendation below.

Recommendation	Party that recommendation is directed to	Accept, partially accept or reject	If “accepted” or “partially accepted”, give action plan for implementation and if “rejected” or “partially accepted”, give reason for rejection / only partial acceptance	If “accepted” or “partially accepted”, expected completion date
Major SB opportunities created by the Fund should be tracked and followed up, including through appropriate non-ODA support to the private sector, to ensure these results are realised in the future.	FCDO/DIT	Accept	FCDO has given Prosperity Fund programme teams the chance to bid for additional non-ODA in 2021/22. Several programmes have submitted bids that aim to realise secondary benefit opportunities to which the Prosperity Fund contributed.	Ongoing
The JFU and the FCDO should capture and share learning about SBs (positive and negative) more widely beyond the PF to inform the design of future programmes.	JFU/FCDO	Accept	In April 2021 we shared key lessons on secondary benefits with hundreds of colleagues across FCDO and Other Government Departments. Reaching beyond the Prosperity Fund network to inform wider discussions.	April 2021 (complete)