## HMLR_Government_Major_Projects_
GMPP ID Number	Project Name	Department	Annual Report Category	Description / Aims	IPA Delivery Confidence Assessment / (A Delivery Confidence Assessment of the project at a fixed point in time, using a three-point scale, Red – Amber – Green; definitions in the IPA Annual Report on Major Projects)	SRO Delivery Confidence Assessment / (A Delivery Confidence Assessment of the project at a fixed point in time, using a three-point scale, Red – Amber – Green; definitions in the IPA Annual Report on Major Projects)	Departmental commentary on actions planned or taken on the IPA RAG rating.	Project - Start Date / (Latest Approved Start Date)	Project - End Date / (Latest Approved End Date)	Departmental narrative on schedule, including any deviation from planned schedule (if necessary)	Financial Year Baseline (£m) (including Non-Government Costs)	Financial Year Forecast (£m) (including Non-Government Costs)	Financial Year Variance (%)	Departmental narrative on budget/forecast variance for 2021/22 / (if variance is more than 5%)	TOTAL Baseline Whole Life Costs (£m) (including Non-Government Costs)	Departmental Narrative on Budgeted Whole Life Costs
BIS_0015_1516-Q1	Local Land Charges (LLC) Programme	HMLR	Government Transformation and Service Delivery	The Programme has met all of it's FY21/22 (Year 1) HM Treasury commitments as defined in the current Business Case. / The 4 Year Delivery Plan has been refined to ensure delivery can be achieved within the ambitious timescales, which sees the Programme end in 2025.		Amber	NA The Programme has delivered all of it's HM Treasury commitments for FY21/22 (Year 1) . / The operating model is now embedded and has been independently assured. The HMLR internal delivery team is now working at full capacity and has been responsible for all delivery within this financial year, tripling the number of local authority (LA) migrations completed this year. / Two digitisation suppliers have been procured and are now working collaboratively with internal delivery teams on their first LA migrations. / Our Engagement Strategy continues to be successful, with 89% of all English LAs and all Welsh LAs signed up for data migration to the new service. / Customer feedback on the live service remains incredibly popular.	01/03/2014	31/03/2027	Compared to 2021-Q4, your project end-date remained scheduled to finish on 31 MAR 2027 . This is primarily due to the following factors: The Programme now has an approved 4 Year Delivery Plan, seeing the end date brought back to 2025.	£42.55	£23.38	-45%	The budget variance exceeds 5%. This year's forecast spend has been lower than predicted due to delayed spend with external digitisation suppliers, whilst requirements were defined.	£331	Compared to2021-Q4, the projects Baseline Whole Life Cost increased from 193.30 (£m) to 331.19 (£m). This is primarily due to the following factors: Whole life costs for our refined Delivery Plan, remain within the overall cost envelope in the approved Business Case.