## HMT_Government_Major_Projects_P
GMPP ID Number	Project Name	Department	Annual Report Category	Description / Aims	IPA Delivery Confidence Assessment / (A Delivery Confidence Assessment of the project at a fixed point in time, using a three-point scale, Red – Amber – Green; definitions in the IPA Annual Report on Major Projects)	SRO Delivery Confidence Assessment / (A Delivery Confidence Assessment of the project at a fixed point in time, using a three-point scale, Red – Amber – Green; definitions in the IPA Annual Report on Major Projects)	Departmental commentary on actions planned or taken on the IPA RAG rating.	Project - Start Date / (Latest Approved Start Date)	Project - End Date / (Latest Approved End Date)	Departmental narrative on schedule, including any deviation from planned schedule (if necessary)	Financial Year Baseline (£m) (including Non-Government Costs)	Financial Year Forecast (£m) (including Non-Government Costs)	Financial Year Variance (%)	Departmental narrative on budget/forecast variance for 2021/22 / (if variance is more than 5%)	TOTAL Baseline Whole Life Costs (£m) (including Non-Government Costs)	Departmental Narrative on Budgeted Whole Life Costs
HMT_0004_2021-Q2	NS&I Rainbow	HMT	Government Transformation and Service Delivery	The Programmes has three key aims to; 1) Deliver a measurable reduction to the cost of running and changing the business, 2) Become a self-service digital business with support for the vulnerable and excluded, 3) Deliver more nimbly, reduce risks and enhance scalability.		Amber	Compared to financial year 20/21-Q4, the Delivery Confidence Assessment rating at 21/22-Q4 remained at Amber We have successfully completed the procurement activity for procurement package A. / We are currently in the procurement process on package B and we awaiting CDDO and CO approval to launch competitive dialogue for procurement C and D respectively. / We have completed the addendum Outline Business Case refresh, which was presented to HMT on 17/03/2022. / Resource increase is in the process of being prepared.	03/06/2019	31/07/2024	Compared to 2021-Q4, your project end-date remained scheduled to finish on 31 JUL 2024 . This is primarily due to the following factors: No Changes to the Milestones have been made to this stage of the programme. The Preparation work currently underway for the business case refresh will assist with identifying any key changes to the Milestones and will align to intra Project Timescale changes.	£48.90	£10.57	-78%	During 2019-20 and 2020-21 NS&I created and assessed a long list of options for how to proceed after the existing outsourcing contract ended in March 2024. This essential discovery activity eventually led to the creation of a Strategic Outline Business Case and an Outline Business Case (OBC). The Programme's ability to spend in line with our allocation and earlier forecasting has been impacted by factors including delays in onboarding required programme resources impacting delivery to the original schedule, particularly for PPA and PPB meaning associated costs will be incurred FY 22/23 instead of FY 21/22; Atos' capacity to deliver against the Transformation Programme schedule and anticipated deliverables (Including Progressive Transformation Projects); Operational recovery delaying progression of planned legacy data work; PPA contract award being rescheduled to April 22 impacting originally forecast supplier costs.	£1,158	Compared to 2021-Q4,the projects Baseline Whole Life Cost remained at 1158.35 (£m). This is primarily due to the following factors: Compared to 2021-Q4, the Baseline Whole Life Cost remained at 1158.35 (£m). The WLC covers ten years and is based on the assumptions within our latest approved Outline Business Case.