## GMCA
Annex A: / Greater Manchester Combined Authority - / £1,070m City Region Sustainable Transport Settlement	Greater Manchester Combined Authority's (GMCA) delivery plan incorporates a proportion of overprogramming, additional to their agreed settlement. GMCA has flexibility to manage their programme in line with the approach to change control, but is responsible for sourcing any additional funding required to deliver the agreed schemes.
Name of Scheme	Description	Location	Start of project delivery	Completion date
Future Quality Bus Transit (QBT) Corridors including: Bury-Rochdale, Ashton-Stockport, Wigan-Leigh	Scheme to develop further Quality Bus Transit Corridors, learning from the development and delivery of the initial corridor between Rochdale-Oldham and Ashton. These will include: Bury-Rochdale; Ashton-Stockport and Wigan-Leigh.	Bury / Rochdale / Tameside / Stockport / Wigan	01/07/2023	31/03/2027
Initial phased delivery of Wigan-Bolton Corridor	Scheme to develop Quality Bus Transit Corridor between Wigan and Bolton (16km)	Wigan / Bolton	01/07/2023	31/03/2027
Initial phased delivery of Rochdale-Oldham-Ashton Corridor	Scheme to develop Quality Bus Transit Corridor between Rochdale, Oldham and Ashton (15km)	Rochdale / Oldham / Tameside	01/07/2023	31/03/2027
City Centre Bus Strategy Phase 1	Provides bus priority measures in Manchester City Centre	Regional Centre	01/01/2024	31/03/2027
Initial phased delivery of Salford Crescent-Media City UK Corridor	Delivery of new Quality Bus Transit (QBT) corridor between Salford Crescent and Media City (4.9km) involving a range of bus priority measures and schemes to improve bus stops.	Salford (Crescent / Media City)	01/07/2023	31/03/2027
City Centre Radials	Delivery of new bus priority corridors focused on Regional Centre	Regional Centre	01/01/2024	31/03/2027
Altrincham - Carrington bus priority	Active travel and bus priority measures to support delivery of housing allocation	Trafford (Altrincham / Carrington)	01/04/2024	31/03/2026
Sale West to Broadheath bus priority	Active travel and bus priority measures to support delivery of housing allocation	Trafford (Sale / Broadheath)	01/04/2024	31/03/2026
City Centre - Victoria North	Delivery of new priority corridor between Manchester City Centre and Victoria North	Manchester (Victoria North)	01/10/2024	31/03/2027
Victoria North - Northern Gateway	Delivery of new priority corridor between Victoria North and Northern Gateway	Manchester (Victoria North & Northwards)	01/10/2024	31/03/2027
Bus Pinchpoint Fund (Rolling Programme)	Range of measures to reduce delays to buses and increase bus service reliability	GM Wide	Started	31/03/2027
Bus priority signing and lining (Rolling Programme)	Range of measures to improving signing and lining arrangements to support use and enforcement of bus priority measures such as bus lanes	GM Wide	01/04/2023	31/03/2027
Bus Stop Enhancement Programme (Rolling Programme)	Range of measures to enhance level of facilities provided at bus stops	GM Wide	01/04/2023	31/03/2027
Intelligent Transport Systems (ITS) Enhancements (Rolling Programme)	ITS programme delivers a platform to integrate walking, cycling, bus, tram and highway data	GM Wide	01/04/2023	31/03/2025
Integrated Ticketing and Information	Delivery of technology and systems to support integrated ticketing and information	GM Wide	01/04/2023	31/03/2026
Bus Franchise Depots	Delivery of depots to support bus franchising	GM Wide	01/09/2023	31/03/2027
Depot Charging Infrastructure	Delivery of electric vehicle charging infrastructure at bus depots	GM Wide	01/01/2023	31/03/2027
Electric Vehicles (EV) Buses	Delivery of Electric Vehicles buses	GM Wide	01/09/2022	31/03/2027
Deliver a number of the remaining Access for All (AfA) stations	Deliver improved access to stations as part of Access for All programme. Stations could include: Reddish North, Hindley, Bryn	Reddish North, Hindley, Bryn	01/01/2024	31/12/2024
Develop and deliver Swinton Access for All (AfA) scheme	For Swinton station, progress the detailed design, surveys & cost plans for submissions and approvals encompassed by the Network Rail Governance for Railway Investment Projects (GRIP) stages 3 to 8	Salford (Swinton)	01/06/2023	01/01/2024
Develop further Access for All (AfA) schemes (Development Only)	Progress development of further Access for All improvements at rail stations	GM Wide	Started	31/03/2027
Station improvement regeneration and development	Provides support for delivery of new homes near new or existing rail stations	Cheadle Hulme, Hazel Grove, Navigation Road	01/01/2024	31/03/2027
Tameside: Hattersley Station Improved Access	Provides new pedestrian bridge (with step free access to rail platforms) to link station with new development at Godley Green Garden Village	Tameside (Hattersley)	01/05/2025	31/03/2027
Development of new stations	Further work to develop schemes to provide new stations across Greater Manchester. Potential locations include Kenyon Junction, Slattocks, Gamesley, Stanley Green and Little Hulton	GM Wide	Started	31/03/2027
Golborne Station*	Scheme to provide new station at Golborne / *Scheme retained by DfT and subject to business case approval by HMG	Wigan (Golborne)	01/10/2024	31/12/2025
Bury Interchange*	Delivery of a new Interchange at Bury with significantly improved passenger facilities for bus, Metrolink and active travel. It will be designed in accordance with decarbonisation and sustainability principles and deliver journey time improvements for passengers. These features along with increased safety, security and accessibility will encourage mode shift to public transport. The Interchange will accommodate future growth in public transport and as a key component in Bury's Town Centre Masterplan (March 2022), will act as a catalyst for regeneration in the area. *As agreed with DfT, the Scheme Opening date will go beyond the current CRSTS funding period with an estimated completion date in 2030, and not 31/03/27. / *Scheme retained by DfT and subject to business case approval by HMG	Bury	01/01/2027	31/03/2027*
Tyldesley Travel Hub / Park & Ride (P&R)	Scheme provides for the development and delivery of a Travel Hubs / P&R facility to improve access to, and reach of, the guided busway services.	Wigan (Tyldesley)	01/01/2026	31/12/2026
Programme of Travel Hubs / Park & Ride (P&R) at Stations and Stops	Scheme provides for the development and delivery of a programme of Travel Hubs / P&R to improve access to, and reach of Rapid Transit (Metrolink, suburban rail, guided busway) services across Greater Manchester.	GM Wide	01/04/2026	31/03/2027
Develop Potential New Guided Busway Stop - Mosley Common	Development of New Guided Busway Stop and Travel Hub to support the North of Mosley Common Places for Everyone (PfE) housing allocation. As a key component of the wider Bee Network, the stop will encourage mode shift to public transport for the adjacent residential led development site. The facility will be designed in accordance with decarbonisation and sustainability principles.	Wigan	Started	31/03/2027
Development of Potential New Metrolink Stops	Development of three new Metrolink stops with Travel Hub facilities at Oldham (Cop Road), Bury (Elton Reservoir) and Manchester (Victoria North/Sandhills). As a key component of the wider Bee Network, the stops will encourage mode shift to public transport for the adjacent residential led development sites. The stops will be designed in accordance with decarbonisation and sustainability principles. Cop Road and Elton are subject to the Places for Everyone process and will include Park & Ride (P&R)/Travel Hub facilities.	Oldham, Bury, Manchester	Started	31/03/2027
Metrolink Stop Improvements	Scheme seeks to support patronage recovery on the Metrolink network, including measures to address safety, security and access issues associated with ageing ex-heavy rail infrastructure. Initial proposals will focus on Bury and Heaton Park stops.	Bury	01/01/2026	31/03/2027
Development of long term rapid transit options	Preparation of feasibility studies etc. to support development of, and protect routes for, long-term rapid transit options across Greater Manchester.	GM Wide	Started	31/03/2027
Powers for 1 scheme and development for 2 schemes	Development of a Powers application for 1 scheme and pre-Powers development for 2 schemes.	GM Wide	01/04/2025	31/03/2027
Greek Street Bridge	Scheme will provide an additional twin track alignment for future capacity improvements such as the proposed Stockport to Airport tram-train/metro route.	Stockport	01/08/2024	30/11/2024
Next Generation Vehicles*	Procurement of up to seven new tram-train vehicles for use on the Pathfinder North tram-train scheme between Oldham and Bury via Rochdale and Heywood. *As agreed with DfT, the Scheme Opening Date will go beyond the current CRSTS funding period with an estimated completion date, subject to Network Rail programme, in 2029 and not 31/03/27. / *Scheme retained by DfT and subject to business case approval by HMG	Oldham, Rochdale, Bury and Manchester	01/09/2026	31/03/2027*
Pathfinder - Infrastructure*	Delivery of tram-train infrastructure between Oldham, Rochdale, Heywood and Bury (26 km) to support implementation of Next Generation Vehicles. *As agreed with DfT, the Scheme Opening Date will go beyond the current CRSTS funding period with an estimated completion date, subject to Network Rail programme, in 2029 and not 31/03/27. / *Scheme retained by DfT and subject to business case approval by HMG	Oldham, Rochdale, Bury and Manchester	01/04/2025	31/03/2027*
Preparatory works including utility diversions	Development and delivery of preparatory works, including utiity diversions, in respect of the Metrolink lines affected by the HS2 alignment. * As agreed with DfT, Scheme Opening Date will go beyond the current CRSTS funding period and is dependent on the HS2 Programme, and not 31/03/27.	GM Wide	Development work started	31/03/2027*
Design and Development work on Metrolink and High Speed Stations.	Design and Development work on Metrolink and high speed stations, station integration, costing and funding, and wider connectivity Packages for stations at Piccadilly, Airport, Wigan and Stockport. * As agreed with DfT, Scheme development will go beyond the current CRSTS funding period and is dependent on the HS2 Programme.	GM Wide	Development work started	31/03/2027*
Deferred and further renewals 2025+	Renewals of Metrolink network from 2025 onwards	GM Wide	01/04/2025	31/03/2027
Prioritised renewals 2022-2025	Renewals of Metrolink network from 2022 to 2025	GM Wide	Started	31/03/2025
Approved but unfunded schemes in MCF programme	Range of active travel schemes to be delivered across Greater Manchester to improve facilities for pedestrians and cyclists	GM Wide	01/04/2024	31/03/2027
Bolton: Farnworth Street for All (S4A) Town Centre Scheme	Delivery of a Streets for All design for Farnworth Town Centre High Street, reallocating road space to improve public realm for walking and cycling in support of a wider Future High Streets funded scheme	Bolton (Farnworth)	01/07/2024	31/03/2026
Bolton: Town Centre Package including Topp Way / Higher Bridge Street	Improvements focus on Active and Sustainable Travel and support Master Plan proposals for improved pedestrian and cycle connectivity between Bolton University / College campus and the town centre and public transport hub	Bolton Town Centre	01/07/2024	31/03/2026
Bury Town Centre Scheme (over and above interchange works)	Redesign of highway measures to the south of Bury town centre to improve bus priority and pedestrian and cycle connectivity across A58 and to /from proposed new interchange	Bury Town Centre	01/07/2024	31/03/2027
Bury: Radcliffe Town Centre Development	Redesign of highway arrangements in town centre to improve walking and cycling facilities and to provide improved bus priority	Bury (Radcliffe)	01/07/2024	31/03/2027
Bury: Ramsbottom Town Centre Development	Redesign of highway arrangements in town centre to improve walking and cycling facilities and to provide improved bus priority	Bury (Ramsbottom)	01/07/2024	31/03/2027
Manchester: Ancoats Active Neighbourhood (Mobility Hub)	Traffic management measures to complement delivery of Ancoats mobility hub and improve facilities for pedestrians and cyclists	Manchester (Ancoats)	01/07/2024	31/03/2027
Manchester: Deansgate car-free masterplan	Scheme to provide car-free Deansgate improving facilities for pedestrians and cyclists and bus services	Manchester City Centre	01/07/2024	31/03/2027
Oldham: Town Centre - Accessible Oldham Phase 2	Redesign of highway arrangements in town centre to improve walking and cycling facilities	Oldham Town Centre	01/07/2024	31/03/2026
Rochdale: Heywood Streets for All	Redesign of highway arrangements in town centre to improve walking and cycling facilities and to provide improved bus priority	Rochdale (Heywood)	01/07/2024	31/03/2026
Rochdale: Littleborough Streets for All	Redesign of highway arrangements in town centre to improve walking and cycling facilities and to provide improved bus priority	Rochdale (Littleborough)	01/07/2024	31/03/2026
Rochdale: Middleton Streets for All Phase 1	Redesign of roundabout in town centre to improve walking and cycling facilities	Rochdale (Middleton)	01/07/2025	31/03/2026
Stockport Interchange	Cycle ramp to be provided as part of new interchange	Stockport	01/07/2023	31/03/2024
Stockport: Town Centre West	Active travel and bus priority measures to support delivery of housing allocation	Stockport	01/07/2025	31/03/2027
Stockport: Greek Street Bridge Streets for All	Scheme provides new pedestrian and cycle bridge as part of wider transport scheme	Stockport	01/07/2026	31/03/2027
Bolton: De Havilland Way	Scheme provides for active travel along corridor to support modal shift	Bolton	01/07/2025	31/03/2027
Oldham Mumps Corridor Improvements	Active travel and bus priority measures to support delivery of housing allocation	Oldham	01/07/2025	31/12/2027
Oldham: Beal Valley & Broadbent Moss - Greenway Corridor	Active travel and bus priority measures to support delivery of housing allocation	Oldham	01/07/2024	31/12/2027
Salford Cos Cos	Scheme provides new active travel routes to development site	Salford	01/07/2023	31/03/2027
Salford: Quays Northern Access (Broadway/S Langworthy Road)	Scheme provides new access to development site to support active travel and bus services	Salford	01/07/2025	31/03/2027
Stockport: A6 / Manchester Road / School Lane	Scheme proposes active mode and bus priority measures in Key Route Network (KRN) corridor	Stockport	01/07/2024	31/03/2026
Stockport: Bredbury Economic Corridor Improvement (BECI) Package	Scheme proposes active mode and bus priority measures to support new employment developments	Stockport (Bredbury)	01/07/2024	31/03/2027
Stockport: Hempshaw Lane	Highway safety scheme for location with poor safety record (especially pedestrians)	Stockport	01/07/2024	31/03/2025
Tameside: A560 Stockport Road	New segregated cycle lane between Hattersley Viaduct and M67 J4	Tameside (Hattersley)	01/07/2025	31/03/2027
Trafford: Carrington Sustainable Transport Measures	Scheme to deliver improved bus route to/from an isolated community whilst also allowing for traffic calming and improved sustainable transport access on the existing A6144.	Trafford (Carrington)	01/07/2025	31/03/2027
Wigan: A577 Complementary Works	Reallocation of carriageway space at locations from Pemberton to Atherton for bus priority, cycling and walking. * Scheme delivery will go beyond the current CRSTS funding period with an estimated completion date in 2028.	Wigan	01/07/2025	31/03/2027*
Wigan: A580 Lane Head Improvements	Scheme proposes active mode and bus priority measures to tackle the poor air quality issues within the corridor. * Scheme delivery will go beyond the current CRSTS funding period with an estimated completion date in 2028.	Wigan	01/07/2025	31/03/2027*
Electric Vehicle Charging infrastructure (EVCI) Match funding	Support for delivery Electric Vehicle Charging Infrastructure across Greater Manchester with a potential focus on employment locations	GM Wide	01/07/2023	31/09/2024
Consolidated Highway Maintenance (Needs, Incentive & Potholes)	Ongoing maintenance work across Greater Manchester to maintain quality of road network	GM Wide	Started	31/03/2027
Bolton - Key Route Network (KRN) Carriageway	Ongoing maintenance to improve quality of Key Route Network	Bolton	01/08/2022	31/03/2024
Bury - Key Route Network (KRN) Carriageway	Ongoing maintenance to improve quality of Key Route Network	Bury	03/10/2022	31/03/2027
Manchester - Key Route Network (KRN) Carriageway	Ongoing maintenance to improve quality of Key Route Network	Manchester	01/09/2022	31/03/2025
Oldham - Manchester Street Viaduct	Refurbishment of viaduct to ensure ongoing operation of road network	Oldham	01/01/2024	01/09/2025
Rochdale - Queens Park Bridge Refurbishment & Key Route Network (KRN) carriageway	Refurbishment of bridge to ensure ongoing operation of road network	Rochdale	01/02/2023	31/03/2025
Salford - Key Route Network (KRN) Carriageway	Ongoing maintenance to improve quality of Key Route Network	Salford	01/04/2023	31/03/2027
Stockport: Greek Street Bridge Streets for All	Ongoing maintenance of bridge as part of wider transport scheme for Greek Street Bridge	Stockport	01/08/2024	20/02/2026
Tameside - Hattersley Viaduct Refurbishment and Widening	Refurbishment of viaduct and incorporation of improved cycle facilities	Tameside	01/04/2024	31/03/2026
Trafford - Key Route Network (KRN) Carriageway and Structures	Ongoing maintenance to improve quality of Key Route Network + works to structures in need of refurbishment	Trafford	01/09/2022	31/04/2024
Wigan - Key Route Network (KRN) Carriageway	Ongoing maintenance to improve quality of Key Route Network	Wigan	01/09/2022	31/03/2025
Integrated Transport Block (ITB) - Minor Works	Ongoing minor works to improve quality of road network	GM Wide	01/09/2022	31/03/2027
Integrated Transport Block (ITB) - Public Transport	Ongoing minor works to improve quality of road network	GM Wide	01/09/2022	31/03/2027
Transforming Cities Fund 2 (TCF2) Development	Ongoing minor works to improve quality of road network	GM Wide	started	31/03/2027

## LCRCA
Annex A: / Liverpool City Region Combined Authority - / £710m City Region Sustainable Transport Settlement	Liverpool City Region Combined Authority's (LCRCA) delivery plan incorporates a proportion of overprogramming, additional to their agreed settlement. LCRCA has flexibility to manage their programme in line with the approach to change control, but is responsible for sourcing any additional funding required to deliver the agreed schemes.
Name of Scheme	Description	Location	Start of project delivery	Completion date
Local Cycling and Walking Infrastructure Plan (LCWIP) Phase 3	Delivery of the third phase of high-quality walking and cycling network in line with the LCWIP, LTN 1/20 compliant active travel connectivity, Access for All and Green Bus Routes across the City Region.	Liverpool City Region-wide	01/01/2025	01/03/2027
Independently Powered Electric Multiple - Unit (IPEMU) – Network Expansion*	Expansion of the IPEMU project to fit Merseyrail trains with battery technology to enable services to run beyond the end of the existing network, enabling the new 777 Class Rolling stock to be deployed on a range of routes. / *Scheme retained by DfT and subject to business case approval by HMG	Liverpool City Region-wide	01/03/2023	01/03/2027
Key Route Network (KRN) Levelling Up	Delivery of a programme of KRN upgrades to provide a high-quality highway network for travel by bus, walk and cycle and reduce negative noise and air quality issues for local communities.	Liverpool City Region-wide	01/09/2022	01/07/2026
Highways Maintenance	A series of maintenance packages will deliver key improvements to the city region’s highway network and transport systems.	Liverpool City Region-wide	Started	01/03/2027
Non-Highways Maintenance	This is a supporting maintenance programme that will improve the MCAs ferry, bus and rail assets.	Liverpool City Region-wide	Started	01/03/2027
Transforming Cities Fund - Headbolt Lane Station	A new rail station providing an alternative to the car for people making longer journeys to and from Kirkby local centre, with supporting active travel links to and from the station.	Liverpool City Region-wide	Started	20/05/2023
Transforming Cities Fund – Active Travel	Delivery of high-quality walking and cycling network in line with our LCWIP, LTN 1/20 compliant active travel connectivity across the City Region.	Liverpool City Region-wide	01/09/2022	01/06/2023
Transforming Cities Fund – Hydrogen Buses	Provision of 20 hydrogen buses on the Liverpool – St Helens 10A corridor, which will provide a high-quality passenger journey with significantly reduced carbon emissions.	Liverpool City Region-wide	Started	01/03/2023
Liverpool Baltic Rail Station*	Delivery of a new rail station in the Baltic Triangle area of Liverpool with a 15-minute peak time frequency which provides direct rail access to the city centre’s growing creative and digital cluster. / *Scheme retained by DfT and subject to business case approval by HMG	Liverpool	01/04/2024	01/03/2027
Birkenhead Central Gateway	LTN 1/20 compliant new and upgraded walking and cycling links. / Supports sustainable access to key regeneration sites in central Birkenhead.	Wirral	01/03/2024	01/12/2025
St George's Gateway	LTN 1/20 compliant new and upgraded walking and cycling links which will link the city centre, Lime Street station, Liverpool John Moores University and the Knowledge Quarter.	Liverpool	01/09/2022	01/09/2024
Cross River Connectivity	Reconfiguration of the toll plazas at the Kingsway and Queensway Tunnels and the re-routing of strategic traffic to the Kingsway Tunnel, improving bus journey time and reliability via the Queensway tunnel. This will improve cross-river bus journey times.	Wirral	01/02/2024	01/04/2025
Green Bus Routes (79)	Delivery of a new Green Bus Corridor between Liverpool and Knowsley offering faster and more reliable journey times, enhanced journey quality and ticketing.	Liverpool, Knowsley	01/07/2025	01/06/2027
Green Bus Routes (20/21)	Delivery of a new Green Bus Corridor in Liverpool and Knowsley offering faster and more reliable journey times, enhanced journey quality and ticketing.	Liverpool, Knowsley	01/07/2025	01/06/2027
Local Cycling and Walking Infrastructure Plan (LCWIP) Phase 2 (Runcorn - Daresbury)	LTN 1/20 compliant active travel route connecting Runcorn with Sci-Tech Daresbury.	Halton	01/08/2022	01/11/2023
Runcorn Station Quarter Phase 2	A rebuild of Runcorn Station building with enhanced active travel links connecting to Runcorn.	Halton	01/07/2024	01/02/2026
Runcorn Busway Active Travel Corridor	Repurposing a bus-only corridor to include active travel, linking Runcorn to major housing developments and employment zones.	Halton	01/02/2023	01/03/2024
East Runcorn Connectivity	An integrated cycle network of LTN 1/20 compliant routes connecting communities, businesses and major multimodal interchanges.	Halton	01/01/2024	01/03/2026
Green Bus Routes (86)	A Green Bus Corridor in Liverpool with faster and more reliable journey times, enhanced journey quality and ticketing.	Liverpool	01/04/2024	01/03/2026
St Helens Town Centre Multimodal Interchange	Multimodal intervention in St Helens town centre. / Enhancements to the bus station area. / Active travel infrastructure around the town.	St Helens	01/04/2023	01/03/2025
Active Travel Improvements M57 J4	Delivery of high-quality walking and cycling network in line with our LCWIP, LTN 1/20 compliant. Connecting Knowsley and Liverpool across M57 J4.	Knowsley	01/04/2023	01/03/2024
St Helens North Housing Access	Improved LTN 1/20 compliant active travel connectivity between St Helens town centre and Cowley Hill development site.	St Helens	01/03/2023	01/06/2025
Huyton Active Travel Corridor	Improved LTN 1/20 compliant active travel connectivity between Huyton and local employment sites.	Knowsley	01/06/2023	01/12/2024
Green Bus Routes (10a)	Delivery of a new Green Bus Corridor between Liverpool and St Helens offering faster and more reliable journey times, enhanced journey quality and ticketing.	Liverpool, Knowsley and St Helens	Started	01/03/2025
Southport Eastern Access	Junction and roundabout improvements supporting active travel with segregated cycle facilities and additional crossings.	Sefton	01/11/2022	01/09/2024
Stanley Dock Rail Access (Sandhills)	Expansion of station capacity at Sandhills to support the development of Liverpool Waters.	Liverpool	01/02/2023	01/12/2023
Maritime Corridor	Enhanced multimodal connectivity along the Maritime Corridor in Sefton.	Sefton	01/02/2023	01/06/2024
Green Bus Routes (53)	Delivery of a new Green Bus Corridor between Liverpool and Sefton providing faster and more reliable journey times, enhanced journey quality and ticketing.	Liverpool, Sefton	01/04/2024	01/03/2026

## SYMCA
Annex A: / South Yorkshire Mayoral Combined Authority - / £570m City Region Sustainable Transport Settlement	South Yorkshire Mayoral Combined Authority's (SYMCA) delivery plan includes an additional reserve list of schemes as part on an approach to overprogramming. SYMCA has flexibility to manage their programme in line with the approach to change control, but remain responsible for sourcing any additional funding required to deliver the agreed schemes.
Name of Scheme	Description	Location	Start of project delivery	Completion date
A61 Active Travel - Barnsley – Royston via Smithies - Phase 1	An active travel scheme which provides 7.5km of new on and off road cycle routes. Full scheme is sequenced in two phases with phase 2 currently within the over-programming list and includes new pedestrian / cycle crossings at key junctions and decking of an existing disused rail bridge providing better connectivity. Also ties into the A61 Royston Bus Priority measures scheme being delivered by SYMCA.	Barnsley (S70) and Royston (S71)	01/01/2024	01/03/2025
Active Travel Cross city connections Sheffield	A series of scalable active travel network improvements which will plug the gaps within Sheffield City Centre to the radial cycle links. Maximise connections with existing schemes and consider options to connect other key destinations within the city centre.	Sheffield City Centre	01/04/2025	01/03/2027
Active Travel Hubs - Barnsley	3 x Active Travel Hubs at priority locations providing services including: / * Electric and regular bike loans; / * A Full workshop to carry out customer repairs and servicing; / * Free Dr Bike safety checks; / * Cycle retail sales; / * Accept donations of bikes and bike parts; / * Information on cycling and walking in the Barnsley area e.g. maps/leaflets/Trans-Pennine Trail (TPT) etc; / * Advice on route mapping.	Darton (S75) / Goldthorpe (S63) / Barnsley Town Centre (S70)	01/10/2023	31/03/2023
Active Travel Northern Communities - Phase 1	A series of scalable active travel network improvements connecting Sheffield City Centre with the Northern General Hospital (NGH), and onward to the surrounding communities. The project will seek to integrate with the bus corridors to provide a sustainable transport route to NGH and improved local access to district centres as well as strategic connections into the City and areas of high employment.	Sheffield City Centre to Northern General Hospital	01/07/2025	01/03/2027
Active Travel Schemes - Barnsley Phase 1	A scalable package of schemes (as included in the Capability Fund) comprising: / Provision of on and off-road sections; / Improvements to pedestrian crossings into Toucans / Pegasus; / Monitoring Equipment; / Wayfinding signage; / Improvements to public realm / Re-surfacing of existing routes	Barnsley (multiple)	01/01/2024	01/03/2027
Eastwood & Herringthorpe Active Travel Neighbourhoods	Provision of measures to manage traffic volumes, traffic speeds and parking in the Eastwood and Herringthorpe areas. Scheme to be designed in collaboration with the community it serves to enable specific local needs to inform the output.	Rotherham, S65 2	01/01/2024	01/12/2024
Moorgate Active Travel Neighbourhood	Provision of measures to manage traffic volumes, traffic speeds and parking in the Moorgate area. Scheme to be designed in collaboration with the community it serves to enable specific local needs to inform the output.	Rotherham, S60 3	01/01/2024	01/12/2024
River Dearne Long Route & Darton Active Travel Route	The proposed ‘River Dearne Long Route’ scheme consists of a package of measures which seeks to improve walking and cycling connectivity between A61 Gyratory at Old Mill Lane and A633 Grange Lane via A628 Pontefract Road. Including: / *Infrastructure improvements to 2.45km of off-road active travel rout / *Provision of Toucans crossing / *Wayfinding signage; / *Resurfacing improvements; / *Improvements to lighting;	River Dearne Long Route is in Barnsley S71. / Darton Active Travel route is in Barnsley (S70) Darton (S75)	01/10/2022	01/03/2023
Barnsley Town End Roundabout	Development of a "Dutch style" roundabout at the existing Town End roundabout within Barnsley town centre on the A628. The existing roundabout will be replaced and existing priority for motorists will be removed and replaced with pedestrian and cyclist priority at crossing points.	Barnsley (S70)	01/01/2025	01/03/2027
Trans Pennine Trail Active Travel and Accessibility Improvements Doncaster	Ensuring the National Cycle Network is fully accessible and has an appropriate sealed surface to enable more journeys by foot or by cycle. Improving local connections to the Trans Pennine Trail which passes through a number of deprived communities where car ownership levels are lower than other parts of the Borough.	NCN route 62	01/01/2024	01/03/2025
A61 Chesterfield Road Bus Priority	A scalable bus improvement project which will deliver bus priority along the A61 corridor from Meadowhead roundabout in the South to Sheffield city centre in the north. Bus priority measures will include signal technology, bus lane reviews and enforcement measures via red routes. There will also be a series of bus stop enhancements and pedestrian access improvements.	A61 Sheffield	01/10/2024	01/03/2026
Bus Service Improvement Plan (BSIP) Bus Improvements	Improvements to the bus network and facilities delivering the objectives defined in the BSIP to improve bus journey times, reliability, punctuality and customer satisfaction. This could include improvements to customer facilities on street and in interchanges and highway improvements to reduce delays to buses. CRSTS investment in BSIP objectives is not limited to this dedicated allocation, the other bus and multi-modal schemes within the programme will be monitored to ensure contribution to the region's BSIP.	South Yorkshire wide, with specific sites to be informed by the BSIP.	01/10/2024	01/03/2027
Bus Lane Review Implementation	A review has been carried out of existing bus priority across the region to assess the performance of existing bus priority and recommend improvements to improve the performance of each site in order to maximise the benefits to buses in the face of changing traffic patterns. Improvements would include: / Lengthening bus lanes / Widening bus lanes / Changes to operating times / Improvements to signing and lining	Multiple locations in Barnsley, Doncaster, Rotherham and Sheffield.	01/04/2025	01/03/2027
Bus Priority - City—Chapeltown/High Green	A scalable bus improvement project which will deliver bus priority along the A6135 corridor from Sheffield City Centre to northern communities of Chapeltown, Ecclesfield and Firth Park via the Northern General Hospital. The scheme will include the investigation of the major junctions on the route. There will also be an opportunity to improve connecting infrastructure such as bus stops, waiting restrictions and other traffic management opportunities which positively present themselves through consultation.	Sheffield	01/04/2025	01/03/2027
Bus Priority - Upper Don Valley	A scalable bus improvement project to deliver bus priority along the A61 corridor from Sheffield City Centre to northern communities of Stannington, Wisewood and Grenoside. The scheme will include the investigation of the major junctions on Penistone Road and Halifax Road. There will also be an opportunity to improve connecting infrastructure such as bus stops, waiting restrictions and other traffic management opportunities which positively present themselves through consultation.	Sheffield	01/04/2025	01/03/2027
Cleveland Street Junction Bus Priority Improvements	Revision of junction, replacing a roundabout where no bus prioritisation is possible and where congestion is an issue with a Microprocessor Optimised Vehicle Actuation (MOVA) controlled signalised junction prioritising bus movement.	Doncaster DN1	01/04/2025	31/03/2026
Meadowhall Interchange Mobility Hub	Increased park and ride capacity with supporting amenities including electric charging points for vehicles, family and disabled parking bays, waiting facilities, cycle stands, cycle lockers, and potentially mobility scooter lockers.	Meadowhall Interchange	01/04/2025	01/03/2027
Mexborough - Transport Network Sustainable Improvements	Improve bus connectivity and penetration into the heart of the town centre. Taking the results from the Transport Connectivity Study completed by ARUP to provide the bus access and prioritisation, with supporting facility and safety improvements.	Doncaster, Mexborough	01/04/2025	31/01/2027
Realtime Detection Priority	Expansion and roll out of bus priority through signalised junctions across the whole county with the aid of virtual triggers, new signal infrastructure and real-time detection including Urban Traffic Control (UTC) improvements where needed and links to operators. Outputs will include: / Upgrades to traffic signals to enable bus priority / Upgrades TO Urban Traffic Management and Control (UTMC) systems as appropriate	Across South Yorkshire region but primarily, Barnsley Doncaster and Rotherham.	01/02/2025	30/04/2027
Shaw Lane Bus Lane	Widening of highway to create a new bus lane and resolve a significant bus and congestion pinchpoint. Identified by Operators as a significant issue for service quality and reliability.	Doncaster, DN2	01/04/2023	31/03/2024
Sidings Junction Bus Priority Improvements	Revision of junction, replacing a roundabout where no bus prioritisation is possible and where congestion is an issue with a Microprocessor Optimised Vehicle Actuation (MOVA) controlled signalised junction prioritising bus movement.	Doncaster	01/04/2024	31/03/2025
Zero Emission Buses	Complementary to the submission for DfT Zero Emission Bus Regional Areas (ZEBRA) funding and earmarked gainshare funding, this allocation will enable the procurement of electric, zero-emission buses, including Community Transport and provision of charging infrastructure at Interchanges, on street and at depots to facilitate the goal of operating a zero emission fleet.	Across South Yorkshire	01/03/2022	01/02/2027
Transport Network Asset Maintenance - Barnsley, Doncaster & Rotherham	Development of the approach to asset management maintenance taking the fundamental requirements of the Highway Capacity Manual (HCM) regime (surfacing, potholes, footway and cycleway management, lighting and structures), and aligning these with the region’s strategic priorities, including the draft Key Route Network and supporting increased adoption of sustainable modes and the re-allocation of road space. Opportunities to use the maintenance regime to add further value to other CRSTS interventions will be developed.	Barnsley	01/10/2024	01/02/2027
A628 Bus and Active Travel priority corridor	Bus / Active Travel (AT) priority scheme; also mitigation for Local Plan developments . Will also include Active Travel routes to tie into existing routes delivered through Transforming Cities Fund (TCF) / AT funding. Direct Outputs / * Bus and Active Travel priority measures; / * Active travel routes which feed directly into existing TCF active travel and bus priority. / * Bus stop improvements to include new shelters / real time information / * Junction improvements to deliver journey time benefits	Barnsley (S70 & S72)	01/07/2024	01/03/2027
A635 Quality Bus Corridor - BRT	Support economic growth through investments at key junctions reducing current and forecast congestion, improving bus journey time reliability and widening sustainable travel opportunities. A corridor length of approximately 7.2km. / Enlarge footprint of roundabout, provide 2 new foot / ped / Equestrian Bridges / Provide One-Way gyratory system at junction / Upgrade Bus Stop infrastructure with new shelters providing real time information / Widen Grange Lane for inbound and outbound traffic flows / Dedicated bus lane along Wombwell Lane to industrial estate junction	Barnsley (S70) Stairfoot (S70), Cundy Cross (S71)	01/10/2023	01/04/2025
Broom Lane Cycleways	Onward extension of Broom Road cycleways under development as part of the Active Travel Fund (ATF). Provision of new cycleways alongside the B.6410 Broom Lane between Broom Road and Worrygoose Roundabout. Total affected length 1.4km	Rotherham, S60 4	01/01/2024	01/12/2024
East Doncaster Active Travel and Passenger Transport Connectivity	This scheme is for phase 2 of the West Moor Link A18-A630, to deliver essential connectivity improvements along the A630 between junction 4 of the M18 motorway to the A18 (Thorne Road) and between the A19 and A630 Wheatley Hall Road, providing active travel routes, bus priority measures and road capacity improvements.	Doncaster A630, DN2 5PS	01/07/2024	01/03/2026
Fitzwilliam Road sustainable travel corridor	Widening and improvement of Fitzwilliam Road between St Anne’s Roundabout and Mushroom Roundabout to provide an inbound bus lane and separate cycleways. Improvements will cover 2km	Rotherham, S65 1RY	01/01/2024	01/12/2024
Ickles Roundabout improvement	Replacement of roundabout with subways with a new junction with bus priority and improved pedestrian and cycle crossing. Delivering bus passenger journey time savings, improved bus journey reliability, better walking & cycling journey ambiance and mode shift.	Rotherham, S60 1DS	01/01/2025	01/12/2025
Integrated Strategic Public Transport	A programme of public transport led infrastructure interventions to enhance the service efficiency and provide the facilities that travellers and communities require. Focussing on a higher volume of smaller scale investments to complement the CRSTS scheme investments and manage the detailed needs including community transport vehicle fleet upgrade, shelter replacements, and bus hotspot rectification.	Region wide	Started	01/03/2027
Local and Neighbourhood Transport Complementary Programme - all four local authority areas	Broad range of the smaller scale interventions required to complement the CRSTS scheme allocations and provide efficiency and effectiveness across the network upon which the regional strategic objectives and investments can be delivered. Also delivering localised investments within communities to open up the network to all users and encourage sustainable access to leisure, facilities and employment.	Barnsley	Started	01/03/2027
Local and Neighbourhood Transport Programme Supplementary - SCC	Extension to the local network programme providing enhanced neighbourhood based interventions across the area, delivering small scale improvements, complementary to the CRSTS investments, whose aggregated benefits make a considerable contribution to achieving the networks that communities need. Interventions include active travel & accessibility improvements, air quality hotspots, public transport hot spots, safer roads, network management.	Sheffield	Started	01/03/2027
Royston Active Travel and Bus Priority Measure infrastructure scheme	Provision of infrastructure mitigation required to deliver 2 major Mixed Use (employment / residential) sites allocated in the Local Plan. MU3 and MU5 – which have been approved in the Royston Masterplan. The scheme will provide mitigation at several local junctions; provide active travel routes and an alternative bus priority route into the town centre	Barnsley	01/04/2024	01/03/2027
St Annes Roundabout improvement	Replacement of roundabout with subways with a new junction with bus priority and improved pedestrian and cycle crossing. Delivering bus passenger journey time savings, improved bus journey reliability, better walking & cycling journey ambiance and mode shift.	Rotherham, S65 1PH	01/01/2024	01/12/2024
Stag Inn Junction Improvement	Replacement of roundabout with subways with a new junction with bus priority and improved pedestrian and cycle crossing. Delivering bus passenger journey time savings, improved bus journey reliability, better walking & cycling journey ambiance and mode shift.	Rotherham, S60 4JN	01/01/2026	01/12/2026
Transforming Cities Fund (TCF) Completion	Additional allocation to support the completion of TCF schemes currently in delivery, largely allocated to conclusion of the Nether Edge Wedge to construct an active travel route connecting the fringes of Nether Edge into Sheffield city centre via Sharrow, and on toward the university and hospital campus via Broomhall.	Regional	Started	01/03/2023
Transforming Cities Fund (TCF) Final Year	Final year allocation, based on original profile, of the TCF programme. Definition to be agreed through further discussion ahead of final programme submission. / TCF Programme reporting already established with DfT.	Regional	Started	01/03/2023
Wickersley Road Sustainable Travel corridor	New bus lane and cycleways along 2km of existing highway space. Contributing to decarbonisation of transport, promoting modal shift from cars to public transport, walking and cycling by enabling mode shift, especially from car to bus for medium distance trips but also from car to cycle.	Rotherham, S60 4JN	01/01/2025	01/12/2025
Worrygoose Roundabout improvement	Replacement of roundabout with subways with a new junction with bus priority and improved pedestrian and cycle crossing. Delivering bus passenger journey time savings, improved bus journey reliability, better walking & cycling journey ambiance and mode shift.	Rotherham, S60 4LD	01/01/2025	01/12/2025
Accessibility Improvements – Thorne North Rail Station	Provision of fully accessible footbridge, stairs and lifts access to the platforms at the station. Current facilities only enable access while the station is staffed and is therefore only available part time.	Thorne North Station, Doncaster	01/04/2025	01/03/2027
Conisbrough Rail Station Park & Ride	Increase capacity by enlarging car park encouraging modal shift and improving improved access to opportunities. Facility regularly over-subsbribed resulting in local road side parking.	Conisborough Station, Doncaster	01/04/2025	01/03/2027
Gateway East*	DfT Retained scheme / Stage 1 of Gateway East rail will see the construction of a railway station that would consist of: / Two platforms each 100m long with passive provision for extension to 150m long; / Lifts, stairs and overbridge; / Station building; / Station forecourt including: / *Bus stops for terminal shuttle buses and local services; / *Set-down and pick-up areas; / *Taxi rank; / *Cycle parking; and / Station car park notionally at 50 spaces / *Scheme retained by DfT and subject to business case approval by HMG	DSA airport, DN9 3XA	01/01/2024	Full scheme (i.e. not just stage 1) post 2027
Park & Ride - Penistone Rail Station	Extension of existing car parking facilities by provision of a new car park on the eastern side of the existing station, providing an additional 99 spaces. Complementary to Barnsley Metropolitan Borough Council (BMBC) Penistone Station Accessibility Improvements / Scheme also includes alterations to existing car park and provision of a new footbridge to replace a barrow (at grade / across track) crossing.	Penistone Station	01/04/2025	01/03/2027
Penistone Station Accessibility Improvements	The scheme will improve accessibility to the proposed Park and Ride scheme at the Penistone station. The creation of a Park and Ride site at Penistone station is a priority of SYMCA and will also complement Kirklees Council Levelling Up Fund (LUF) submission to increase the number of trains on the Penistone Line, which connects Huddersfield with Sheffield via Barnsley. Services at Penistone are currently restricted to 2 trains per hour.	Penistone (S36)	01/04/2024	01/03/2027
Railway reinstatement: North Barnsley to Wakefield via Royston - Phase 1*	The restoration proposal for the North Midland Line is to run passenger services from Barnsley to Wakefield Kirkgate via the semi-operational freight route from Wakefield to Lundwood. This could form the first phase of a more fundamental reinstatement between Lundwood and Barnsley and / or Lundwood and Swinton on disused tracks. Currently, the route is a single track, infrequently used freight line, which runs parallel to parts of the National Cycle Network. (funding for development only) / *Scheme retained by DfT and subject to business case approval by HMG	Barnsley, Royston, Wakefield	Development started	TBC
Rotherham Mainline Station: tram-train development*	The CRSTS contribution is for the initial Outline Business Case development work for the integrated tram-train and mainline station project. Funding for further development of this scheme is subject to HMG approval. (funding for development only) / *Scheme retained by DfT and subject to business case approval by HMG	Rotherham, S60 1SD	01/07/2022	Full scheme post 2027
Waverley Station	Provision of new railway station on the Sheffield to Lincoln line at Waverley, providing rail connectivity to the Advanced Manufacturing Park and Waverley new community, as well as to potential housing allocations in Sheffield. / The CRSTS contribution would be for business case development work up to 2026.	Rotherham, S60	01/04/2025	01/12/2026
Mass Transit - Depot*	Existing DfT retained scheme / One element of the wider package of Tram Renewal measures / Improve existing layout and systems where required, look to increase sustainability (solar, grey water recycling etc) Includes improvements to Paint Shed. / *Scheme retained by DfT and subject to business case approval by HMG	Nunnery Square, Sheffield	01/07/2025	01/03/2027
Mass Transit - Network Infrastructure - Phases 1 & 2*	Existing DfT retained scheme / One element of the wider package of Tram Renewal measures / Replacement of tram slab, rails, points and strengthening of key structures and improvement of turnback facilities. / *Scheme retained by DfT and subject to business case approval by HMG	Sheffield / Rotherham	01/07/2025	01/03/2027
Mass Transit - Power - Phases 1 & 2*	Existing DfT retained scheme / One element of the wider package of Tram Renewal measures / 1. Additional and refurbished sub stations. / 2. Floating Earth System / *Scheme retained by DfT and subject to business case approval by HMG	Sheffield / Rotherham	01/07/2025	01/03/2027
Mass Transit - Vehicles - Phases 1 & 2*	Existing DfT retained scheme / One element of the wider package of Tram Renewal measures / Refurbishment and/or replacement of vehicles subject to the results of imminent assessment of existing fleet including new Vehicle Information System and Automatic Vehicle Location System. / *Scheme retained by DfT and subject to business case approval by HMG	Sheffield / Rotherham	01/07/2025	01/03/2027
Mass Transit -Customer Improvements - Phases 1 & 2*	Existing DfT retained scheme / One element of the wider package of Tram Renewal measures / Includes new shelters; CCTV, Passenger Information Points; seating; passenger information improvements, plus improvements to pedestrian crossing points to ensure they meet current LRSSB Guidance. / *Scheme retained by DfT and subject to business case approval by HMG	Sheffield / Rotherham	01/07/2025	01/03/2027
Overprogramming - Meadowhall Interchange Mobility Hub	This is the balance of allocation required based on the original forecast costs. This scheme spanned the £570m programme cut off point so this value currently sits below the line. Increased park and ride capacity with supporting amenities including electric charging points for vehicles, family and disabled parking bays, waiting facilities, cycle stands, cycle lockers, and potentially mobility scooter lockers.	Meadowhall Interchange	01/04/2025	01/03/2027
Overprogramming - A61 Active Travel - Barnsley – Royston via Smithies - Phase 2	Continuation of work currently sequenced within the main programme. An active travel scheme which provides 7.5km of new on and off road cycle routes. Full scheme includes new pedestrian / cycle crossings at key junctions and decking of an existing disused rail bridge providing better connectivity. Also ties into the A61 Royston Bus Priority measures scheme being delivered by SYMCA.	Barnsley (S70) and Royston (S71)	01/01/2024	01/03/2025
Overprogramming - Accessibility Improvements – Chapeltown Station	Provision of lifts to the platforms at the station. Making the station accessible to all travellers and thereby enabling mode shift from cars to public transport, walking and cycling.	Chapeltown Rail Station,	01/04/2025	01/03/2027
Overprogramming - Active Travel Schemes Barnsley Phase 2	A scalable schemes comprising / Provision of on and off-road sections; / Improvements to pedestrian crossings into Toucans / Pegasus; / Monitoring Equipment; / Wayfinding signage; / Improvements to public realm / Re-surfacing of existing routes	Barnsley (multiple)	01/01/2024	01/03/2027
Overprogramming - A.633 Rotherham to Dearne Valley sustainable transport corridor	Public transport priority and supporting active travel infrastructure along the A.633 corridor between Rotherham and the Dearne Valley employment area. Main intervention will be 1km of bus lane along the A.633 Warren Vale, to be supported with additional measures to provide bus priority and active travel between Wath, Manvers and Brampton.	A633 Warren Vale Rotherham	01/07/2025	01/12/2026
Overprogramming - Maltby to Hellaby Cycleways	Development work for provision of cycleways along the A.631 between Grange Lane, Maltby and Denby Way, Hellaby, total affected length of 3.4km	Bawtry Road, Hellaby.	01/01/2025	01/12/2025
Overprogramming - Maltby Active Travel Neighbourhood	Provision of measures to manage traffic volumes, traffic speeds and parking in the Maltby area, linking to the Maltby to Hellaby cycleway. Scheme to be designed in collaboration with the community it serves to enable specific local needs to inform the output.	Maltby, ROTHERHAM. S66.	01/01/2026	01/12/2026
Overprogramming - Active Travel Mosborough Townships	A series of scalable active travel network improvements connecting the Mosborough Communities with schools, local businesses, recreational greenspace (including Rother Valley Country Park), the Park and Ride at Halfway and a number of crossing facilities to enhance pedestrian permeability.	Sheffield	01/04/2024	01/03/2026
Overprogramming - Improvements to Trans-Pennine Trail Barnsley	This phaseable package of interventions includes: / * Provision of new active routes / * Improving the condition of the Trans-Pennine Trail (TPT) / * New Pegasus / toucan crossings in locations where the trail connects with the highway / * Providing circular links / * New Wayfinding / * Data Collection / Monitoring Equipment	Barnsley	01/03/2022	01/03/2027
Overprogramming - Railway reinstatement: North Barnsley to Wakefield via Royston - Phase 2	The restoration proposal for the North Midland Line is to run passenger services from Barnsley to Wakefield Kirkgate via the semi-operational freight route from Wakefield to Lundwood. This could form the first phase of a more fundamental reinstatement between Lundwood and Barnsley and / or Lundwood and Swinton on disused tracks. Currently, the route is a single track, infrequently used freight line, which runs parallel to parts of the National Cycle Network	Barnsley, Royston, Wakefield	01/03/2022	TBC
Overprogramming - Zero Emission Buses - additional scope opportunity	Complementary to the submission for DfT Zero Emission Bus Regional Areas (ZEBRA) funding and earmarked gainshare funding, this allocation will further enable the procurement of electric, zero-emission buses, including Community Transport and provision of charging infrastructure at Interchanges, on street and at depots to facilitate the goal of operating a zero emission fleet.	Across South Yorkshire	01/06/2025	01/03/2027
Overprogramming - Active Travel Northern Communities Phase 2	A series of scalable active travel network improvements connecting Sheffield City Centre with the Northern General Hospital (NGH), and onward to the surrounding communities. The project will seek to integrate with the bus corridors to provide a sustainable transport route to NGH and improved local access to district centres as well as strategic connections into the City and areas of high employment.	Sheffield	01/10/2024	01/03/2027
Overprogramming - Wickersley & Brecks Active Travel Neighbourhoods	Provision of measures to manage traffic volumes, traffic speeds and parking in areas served by Wickersley Road and Bawtry Road cycleways. Scheme to be designed in collaboration with the community it serves to enable specific local needs to inform the output	Wickersley, Rotherham.	01/01/2025	01/12/2026

## TVCA
Annex A: / Tees Valley Combined Authority £310m - City Region Sustainable Transport Settlement	Tees Valley Combined Authority's (TVCA) delivery plan includes an additional reserve list of schemes as part on an approach to overprogramming. TVCA has flexibility to manage their programme in line with the approach to change control, but remain responsible for sourcing any additional funding required to deliver the agreed schemes.
Name of Scheme	Description	Location	Start of project delivery	Completion date
Linthorpe Road Phase 2	Provision of safe facilities for pedestrians and cyclists along Linthorpe Road between Ayresome Street and Cumberland Road. This will complement the existing Phase 1 scheme between Borough Road and Ayresome Street and together will provide a continuous link between Linthorpe Village and Middlesbrough Town Centre. In addition to CRSTS funding this scheme has also attracted Active Travel Fund - tranche 3 money to support delivery.	Middlesbrough	31/03/2023	31/03/2024
Woodland Road Phase 2	The Woodland Road Phase 2 scheme will provide safe facilities for pedestrians and cyclists along Woodland Road (A68) between Hollyhurst Road and Deneside. This will complement the existing Phase 1 scheme between Hollyhurst Road and Skinnergate and together will provide a continuous link between Cockerton and Darlington Town Centre. In addition to CRSTS funding this scheme has also attracted Active Travel Fund - tranche 3 money to support delivery.	Darlington	31/03/2023	31/03/2024
Nunthorpe to Guisborough	The Nunthorpe to Guisborough Cycleway Phase 1 Scheme will provide a continuous off-road walking and cycling link between Nunthorpe, at the southern edge of Middlesbrough and the town of Guisborough.	Middlebrough / Redcar and Cleveland	31/03/2023	31/03/2024
A68 to Cockerton and Faverdale	This scheme will continue the route from Woodland Road Corridor phases 1 & 2 and extend existing cycling and walking provision to link Darlington Town Centre and Cockerton with the economic development site at Faverdale.	Darlington	31/03/2024	31/03/2025
Town Centre to Acklam and Hemlington	This scheme will continue the route from Linthorpe Road Corridor phases 1 & 2 and extend existing cycling and walking provision to link Middlesbrough Town Centre and Linthorpe with the residential areas of Acklam and Hemlington.	Middlesbrough	31/03/2025	31/03/2026
Norton to Stockton Town Centre	This scheme will provide safe facilities for pedestrians and cyclists along the Norton Road Corridor between Stockton Town Centre and Norton. The scheme will be delivered in two phases and onward links to Billingham will also be developed in phase 3.	Stockton	31/03/2024	31/03/2025
Redcar town centre to South Bank / Teesworks	This scheme will provide safe facilities for pedestrians and cyclists between Redcar Town Centre and South Bank, via the Teesworks site. It is a key access corridor to the major employment site from Redcar and Middlesbrough. The scheme will be delivered in phases	Redcar	31/03/2024	31/03/2025
A689 Hartlepool Town Centre to Wolviston	This scheme will provide safe, largely off road facilities for pedestrians and cyclists along the A689 between Hartlepool Town Centre / Transport Interchange, and Wynyard and Billingham to the south. It will link a number of new housing developments in the southwest of Hartlepool with employment sites in Hartlepool and seal sands. This scheme will be delivered in phases. In addition to CRSTS funding delivering all phases of this scheme is dependent upon securing funding from the DfT's Major Road Network programme for the A689 Corridor Improvements bid.	Hartlepool	31/03/2024	31/03/2026
Yarm Road to Teesside International Airport Business Park	This scheme will provide safe facilities for pedestrians and cyclists along the A67 between Darlington Town Centre/Darlington Railway Station and heading towards the Teesside International Airport and nearby villages. In addition to linking a number of residential areas with employment sites in Darlington Town Centre and on the outskirts of Darlington, it will also link with the growing demand at the airport.	Darlington	31/03/2024	31/03/2025
Marton Road to Nunthorpe	This scheme will provide safe facilities for pedestrians and cyclists along Marton Road between Middlesbrough Town Centre and James Cook University Hospital and Nunthorpe. This will link a number of residential areas with employment sites in Middlesbrough Town Centre and at the hospital. This scheme will be delivered in phases.	Middlesbrough	31/03/2024	31/03/2026
Thornaby to Stockton Town Centre	This scheme will provide safe facilities for pedestrians and cyclists between Thornaby Town Centre and Stockton Town Centre. This will link a number of residential areas with employment sites and Thornaby station.	Stockton	31/03/2024	31/03/2026
Hartlepool Town Centre to the Headland	This scheme will provide safe facilities for pedestrians and cyclists between Hartlepool Headland and Hartlepool Town Centre/Transport Interchange. This will link a number of residential areas with employment sites.	Hartlepool	31/03/2024	31/03/2025
Development of active travel hubs and cycle storage	Capital investment in the establishment of new active travel hubs aross the Tees Valley to provide a focal point for behaviour change activity to encourage walking and cycling. On-going operation of the Active Travel Hubs dependent upon securing Capability Fund revenue.	Tees Valley wide	31/03/2023	31/03/2024
Darlington Station*	Darlington Station is the largest rail investment project taking place in Tees Valley and is fundamental to the delivery of the Tees Valley Combined Authority's vision for rail service improvements. Located on the East Coast Main Line (ECML), the Darlington Station project is a fundamental part of the investment programme north of York, as outlined in the Government's Integrated Rail Plan. In addition to CRSTS funding this scheme is seeking funding from DfT's Rail Network Enhancements Pipeline / *Scheme retained by DfT and subject to business case approval by HMG	Darlington	30/09/2022	31/11/2024
Eaglescliffe Station	Eaglescliffe Station is currently only accessible from the eastern side of the railway lines. In terms of vehicular access, the station car park is at or near capacity and there is no scope for expansion due to the site constraints. Hence, this scheme involves the construction of a new access road and car park on the west side, a new fully accessible footbridge and station enhancements.	Eaglescliffe Station	31/10/2022	31/03/2024
Middlesbrough Station	This is the third phase of improvements at Middlesbrough Station. The current operational layout means that there are a number of performance and reliability issues and a capacity constraint, which acts as a barrier to the delivery of new services and extends journey times. This proposal comprises rail infrastructure, including the construction of a new platform to improve capacity, reduce journey times and provide resilience. In addition to CRSTS funding this scheme is seeking funding from DfT's Rail Network Enhancements Pipeline	Middlesbrough	31/12/2023	30/11/2024
Redcar Central Station Project	The CRSTS proposal at Redcar Central Station comprises the construction of a new footbridge, building repair work and improving walking, cycling and bus connectivity.	Redcar	01/04/2024	31/03/2025
Hartlepool Station Platform Reinstatement	Hartlepool Station is currently a key constraint on the Durham Coast Line on account of it having only one operational platform for through trains, despite there being two tracks through the station. The proposal at Hartlepool Station comprises re-opening the disused platform and constructing a new footbridge / lifts.	Hartlepool	31/08/2022	30/06/2023
Billingham Station Accessibility	Billingham Station is an island platform and is currently the only station on the Tees Valley rail network which doesn't have step free access to either of its platforms. The proposal at Billingham Station includes installing a new footbridge to replace the previous life-expired one and lifts, along with reconfiguring current car parking.	Billingham	01/07/2022	30/06/2023
Teesworks Stations and Transport hubs (South Bank Station and British Steel Redcar Station Improvements)*	Teesworks is the UK's largest regeneration site and is critical to the transformation of the Tees Valley economy. A railway line from Middlesbrough and Redcar runs through the site with Redcar British Steel Station providing good access to the east of the site and South Bank Station provide good access to the west of the site and the adjacent residential community. The proposal involves refurbishing the stations, enhancing facilities and seeking to improve accessibility. / *Scheme retained by DfT and subject to business case approval by HMG	South Bank	31/03/2024	31/03/2026
Station Accessibility and Modal Integration Enhancements	Programme involves a number of improvements across stations in the Tees Valley. Proposals across the 16 identified stations include improved cycling and parking infrastructure, pedestrian accessibility, bus connectivity, car parking facilities and working with the rail industry to secure additional funding to deliver passenger enhancements at the stations.	Tees Valley wide	31/03/2023	31/03/2025
Line Speed and Capacity Improvements	The purpose of this project is to: / * review and prioritise the pinchpoint locations where infrastructure improvements are needed; and / * work with Network Rail to identify where line speed improvements can be delivered to speed up journey times.	Tees Valley wide	31/03/2024	31/03/2026
Eaglescliffe to Northallerton W12 Gauge Clearance*	This project will provide a more direct W12 gauge cleared route to the East Coast Main Line (ECML) to enable more freight to be moved efficiently by rail, particularly between the Northallerton and Stockton Cut Junction. In addition to CRSTS funding this scheme is seeking funding from DfT's Rail Network Enhancements Pipeline.* / *Scheme retained by DfT and subject to business case approval by HMG	Yarm Town / Northallerton	31/09/2023	31/03/2025
Bus priority improvements: Darlington Branksome to Red Hall corridor	This corridor provides connectivity into Darlington town centre and offers links to employment and leisure opportunities along with an interchange to rail at Darlington station. This corridor serves local communities where car ownership is less than 50%, alongside providing access to local employment sites. Future developments have been identified along the corridor.	Darlington	01/01/2023	31/03/2025
Redcar to Middlesbrough bus corridor	This corridor provides an important connection to the major trauma centre and district general hospital at James Cook and Redcar Primary Care Hospital. The corridor offers links to employment opportunities by serving communities across the region, several of which have low car ownership and rely on bus services to access employment and education opportunities.	Redcar / Middlebrough	01/01/2023	31/03/2025
Middlesbrough to Hartlepool bus corridor	This corridor provides connectivity between three key centres: Middlesbrough, Stockton and Hartlepool and offers an interchange with the rail network at Hartlepool and Thornaby, alongside serving various local communities. The corridor provides Hartlepool residents with a public transport link to employment attractors located in town centres and industrial parks along the A689.	Middlebrough / Hartlepool	01/01/2023	31/03/2025
Middlesbrough to Ingleby Barwick bus corridor	This corridor provides an important link into Middlesbrough town centre and offers links to employment, education and leisure facilities together with an interchange with the rail network at Allens West. The corridor serves many communities in Stockton district who rely on bus journeys due to low car ownership.	Middlebrough / Ingleby Barwick	01/01/2023	31/03/2025
Middlesbrough to Coulby Newham bus corridor	This corridor offers an important connection between an area of development south of Middlesbrough and Middlesbrough town centre. The corridor offers a public transport link for various communities in the region, providing accessibility to employment, educational and leisure facilities.	Middlebrough / Coulby Newham	01/01/2023	31/03/2025
Middlesbrough to East Cleveland Hospital bus corridor	This corridor serves both Middlesbrough and Redcar & Cleveland residents, offering connectivity from Middlesbrough to Teesport and the development area of Teesworks / Tees Valley Freeport. The corridor connects various local communities to employment, leisure, education and healthcare facilities.	Middlebrough / Redcar	01/01/2023	31/03/2025
Middlesbrough to Netherfields / Overfields bus corridor	This corridor provides connectivity into Middlesbrough town centre for various local communities where car ownership is below 50%, allowing them to access employment, educational and leisure opportunities.	Middlebrough	01/01/2023	31/03/2025
Darlington to Middlesbrough (via Stockton) bus corridor	This corridor provides connectivity between three key centres: Darlington, Stockton and Middlesbrough and interchanges with the rail network at Thornaby. The corridor offers a public transport link to employment attractors both in the town centres and at industrial estates out of town, meaning that employees can travel across districts to access employment.	Darlington / Middlebrough	01/01/2023	31/03/2025
Darlington to Durham bus corridor	This corridor serves various communities in both Tees Valley and Durham County Council, offering connectivity into Darlington and Durham centres and links to employment, leisure and education opportunities. The corridor requires a collaboration between the neighbouring authorities to ensure that aspirations and proposals along the corridor are aligned between neighbouring authorities and bus operators.	Darlington	01/01/2023	31/03/2025
Tees Valley wide Bus Shelter Improvements	Tees Valley wide project to complement the bus corridor work by developing a hierarchy of bus shelter provision and specifying the expected level of provision / facilities for each category. It is envisaged that the level of provision / facilities will be of a higher specification on the key bus corridors.	Tees Valley wide	01/01/2023	31/03/2024
Electric vehicle programme	TVCA is committed to delivering a step-change in the provision of electric vehicle charging infrastructure, which is one of the main deterrents for people considering a transition to electric vehicles. The Combined Authority has already started to create a comprehensive network of charge points to kickstart the transition to electric vehicles. This project will build upon the initial phase of roll-out.	Tees Valley wide	31/03/2024	31/03/2025
Digital transport programme - Data Platform	A data platform will form the foundational digital infrastructure for TVCA, allowing for data analytics capabilities. It will enable data to be collected, aggregated, analysed and shared. It will provide convenient access for TVCA and third parties to work with data to gain insights and identify trends.	Tees Valley wide	31/03/2023	31/03/2024
Digital transport programme - Digital Services	Digital services are the customer-facing offering that will enable TVCA to communicate, engage and interact with users. Digital services can take many forms, from web-based, to mobile applications, or voice activated services and interactive installations, offering a range of services such as real-time data, integrated parking services and customer services.	Tees Valley wide	31/03/2023	31/03/2024
Digital transport programme - Digital Twin	A Digital twin is a virtual digital replica of an asset or system that incorporates associated real-time data during operation, allowing for greater understanding and network performance of the asset. Digital twins enable modern digital analysis techniques, such as condition-based monitoring and predictive analysis, to plan for the continued functioning of the infrastructure. A Digital twin will enable TVCA to better envision, design, build, operate, maintain and manage virtually everything in the built environment.	Tees Valley wide	31/03/2023	31/03/2024
Wheels to work (Capital) April 2024 - March 2027	The project leases electric motorcycles to working age people at a subsidised rate for a short period enabling individuals to access to employment, training or education where public transport is not a viable option. Extension of the current scheme beyond 2023/24 is subject to evaluation. CRSTS will be used to fund the replacement of the vehicle fleet. In addition to CRSTS capital funding the extension of this scheme will need revenue funding to support the operational costs.	Tees Valley wide	01/04/2024	31/03/2027
Tees Flex On-Demand Service	Tees Flex is an on-demand bus service currently in operation as a 3-year pilot project. Extension of this project is subject to evaluation of the pilot. CRSTS will be used to fund the provision of new vehicles. In addition to CRSTS capital funding the extension of this scheme will need revenue funding to support the operational costs.	Parts of Tees Valley where there is limited commercially operated public transport	01/03/2023	31/03/2027
Local Highway Authority Consolidated Funding	This is an allocation of funding for each of the five local authorities and is a 5-year settlement based upon the level awarded for 2020/21	Tees Valley wide	Started	31/03/2027
Transforming Town Centre Accessibility	Ensuring that transformational transport interventions can be implemented to help meet the ambition and support the delivery of the proposed Hartlepool and Middlesbrough Mayoral Development Corporations and other town centre major regeneration projects. Masterplanning work is to commence later in 2022/23, following designation of the Mayoral Development Corporations and will help to define the specific investment proposals	Hartlepool / Middlesbrough / Other major town centre regeneration projects	31/03/2024	31/03/2027
Over-programming	Additional scope on Transforming Town Centre accessibility	TBC	TBC	TBC
Over-programming	Additional scope on: / * Wheels to work (Capital) April 2024 - March 2027, or / * Tees Flex On-Demand Service	TBC	TBC	TBC
Over-programming	Additional scope on Digital Transport Programme packages	TBC	TBC	TBC
Over-programming	Additional scope on Electric Vehicle Programme	TBC	TBC	TBC
Over-programming	Either additional scope on identified schemes which may have to be value engineered if inflation continues to exert pressure on the identified scheme costs / Or / Delivery of additional interventions identified during further project development work on each of the 9 corridors	TBC	TBC	TBC
Over-programming	Additional scope on: / * Station Accessibility and Modal Integration Enhancements, or / * Line Speed and Capacity Improvements	TBC	TBC	TBC
Over-programming	Either additional scope on identified schemes which may have to be value engineered if inflation continues to exert pressure on costs, or delivery of other phases of active travel corridors identified in the Tees Valley Local Cycling and Walking Improvement Plan.	TBC	TBC	TBC

## WECA
Annex A: / West of England Combined Authority £540m - City Region Sustainable Transport Settlement	The West of England Combined Authority's (WECA) delivery plan includes an additional reserve list of schemes as part on an approach to overprogramming. WECA has flexibility to manage their programme in line with the approach to change control, but remain responsible for sourcing any additional funding required to deliver the agreed schemes.
Name of Scheme	Description	Location	Start of project delivery	Completion date
Bristol City Centre Sustainable Transport Corridor	Improving the appeal and effectiveness of public transport offer in Bristol City Centre, this project includes upgrading cycling and walking infrastructure, implementing Bus Priority and creating effective transport hubs/interchange across the city centre. This will deliver significant multi-modal transport benefits across the city.	Bristol	30/09/2024	30/09/2026
Long Ashton Metrobus Improvements	Network improvements to the Metrobus service to Long Ashton. These include changes to infrastructure at Bedminster Bridges roundabout, Bedminster Parade and Redcliff Hill to enable a more reliable service.	Bristol	30/09/2024	30/09/2026
Bath City Centre Sustainable Transport Corridor	Improving the appeal and effectiveness of public transport offer in Bath City Centre, this project includes upgrading cycling and walking infrastructure, improvements to the Bus Station and links across the river. This will deliver significant multi-modal transport benefits across the city.	Bath city centre	30/09/2024	31/03/2026
Bristol to Bath Sustainable Transport Corridor - Bristol to Emery Road	Improving public transport services along the A4 Strategic Corridor from Bristol Temple Meads to the existing Park and Ride at Emery Road (5km). This already popular public transport service is hampered by a lack of continuous bus priority. This project would address much of the challenges to enable a more reliable and faster service. Walking and cycling infrastructure along the route is also being significantly improved.	A4 Corridor	30/09/2024	31/03/2027
Bristol to Bath Sustainable Transport Corridor - Keynsham to Bath	There is no bus priority at present along this 12.5km route that connects Bath to it's largest town - Keynsham. Therefore, Improving public transport offer along this section of the A4 is a priority. Walking and cycling infrastructure along the route is also being significantly improved.	A4 Corridor	30/09/2024	30/06/2026
Bristol to Bath Sustainable Transport Corridor - Transport Hub	The existing Park and Ride at Emery Road is near to capacity. Relocation to the A4/A4174 (ring road) junction would not only resolve the capacity issue, but would also reduce the amount of travel between the ring road and the existing park and ride. This would reduce air quality issues and trip generation. There is a strong business case as the existing site is owned by Bristol City Council.	A4 Corridor	30/06/2025	31/03/2027
M32 Sustainable Transport Corridor and Hub*	Providing a new transport hub, improvements to bus priority and improved active travel offer. This scheme removes substantial traffic entering the centre of Bristol that at present is generated from the M4. It includes a new junction off the M32, a new transport hub and parking, improvements to bus priority into the centre of Bristol and walking and cycling connections. / *Scheme retained by DfT and subject to business case approval by HMG	Bristol (M32 is in Bristol)	30/09/2025	30/06/2027
Portway Sustainable Transport Corridor and Hub	Focused on enhancing the corridor between central Bristol, employment sites in Avonmouth and connections to the M5. These initiatives consist of upgrading the existing P&R site, bus segregation measures and improved cycling infrastructure.	Bristol	30/06/2024	30/06/2025
Stockwood to Cribbs Causeway Sustainable Transport Corridor	These are a number of activities related to infrastructure improvement regarding public transport offer in the A37/A4018 corridor. These upgrades include the provision of bus priority measures, road design and enhancement of cycling and walking routes across the covered area.	Bristol city	30/06/2024	30/06/2026
Thornbury to North Bristol Sustainable Transport Corridor	This is about a series of interventions focused on improving transport links and public transport services along the A38 connections from Thornbury to the M32.	A38 Thornbury to M32	30/09/2024	30/06/2026
Bristol to Hengrove Metrobus extension	This consist of a series of upgrades to the existing metrobus route to Hengrove, in combination with bus stop upgrades and bus priority measures throughout the corridor.	Thornbury and Charfield (Bristol and South Gloucestershire)	31/12/2023	30/06/2025
Somer Valley to Bath Sustainable Transport Corridor	This activity is focused on improving links from the Somer Valley to Bath, including connections to rural communities. Interventions include better bus priority measures, creation of transport hubs and provision of new cycling infrastructure to connect those rural communities with Bath.	Somer Valley to Bath	31/03/2024	31/12/2025
Chipping Sodbury to Hambrook Sustainable Transport Corridor	These are a number of interventions focused on improving Active Travel links and public transport services in from University of the West of England (Frenchay) to Yate and Chipping Sodbury. Activities include enhancement of cycling infrastructure, creation of new transport hubs and road design.	Frenchay, Yate, Chipping Sodbury	31/03/2024	31/12/2025
Regional Station Accessibility	This activity aims to bring Lawrence Hill railway station up to a MetroWest standard regarding accessibility. Enhancements include full step free access, and where required improvements to wayfinding, easy walking and cycling access, improvements to security, CCTV and lighting.	Lawrence Hill	30/09/2024	30/09/2025
Charfield Railway Station*	This activity is focused on the construction of a new station at Charfield, between Gloucester and Yate. This will enable additional development and sustainable transport for new and existing residents of the village, including a transport hub. / *Scheme retained by DfT and subject to business case approval by HMG	Charfield	31/09/2024	31/01/2026
BANES – Bath & Midsomer Norton Walking and Cycling Packages	We will invest in walking and cycling facilities across Bath and Midsomer Norton area to improve the attractiveness of active travel, including new modes. The facilities include increased provision of cycle parking spaces and off-road and segregated walking and cycling routes.	BANES – Bath & Midsomer Norton	30/06/2024	31/12/2025
Bristol to Bath Railway Path improvements	This activity aims to deliver enhancement to the Bristol Bath Railway Path in the South Gloucestershire area. Upgrading of lighting and access to the path is required. To achieve year round model shift improved lighting and access is essential. This will enable commuters to access employment sites in Bristol, Bath and north fringe sustainably year round.	South Glos	30/06/2023	30/12/2023
Bath and North East Somerset Liveable Neighbourhoods	Proposed liveable neighbourhood scheme in Bath which will engage with local residents and business through the 'co-design' process to understand the barriers to walking, cycling, public transport and wider 'liveability'. The project will see improvements to 5 Local Cycling and Walking Improvement Plan (LCWIP) routes and 5 Core Walking Zones alongside enhancements to local connections, and ecological assets (e.g. Sustainable Drainage Systems, tree planting and parklets)	BANES	30/09/2022	31/03/2025
Bristol City Liveable Neighbourhoods	Proposed liveable neighbourhood scheme in Bristol focused on delivering 4 LCWIP routes and one Core Walking Zone alongside enhancements to local connections and ecological assets (e.g. SUDS, Tree planting and Parklets). The scheme will interface with the regeneration of the Temple Quarter Enterprise Zone, St Phillips Marsh and Temple Meads.	Central Bristol	30/09/2022	30/06/2026
South Gloucestershire Liveable Neighbourhoods	This is one of the liveable neighbourhood proposed schemes. It is focused on the delivery of Liveable Neighbourhood Strategy and policy across South Gloucestershire.	Yate & Thornbury	30/09/2023	30/09/2025
Integrated Smart Ticketing	Development of new and simplified bus ticketing options across all buses in the West of England Combined Authority and North Somerset Council. It will deliver tap-on, tap-off contactless ticketing. It will allow the introduction of fare capping, faster boarding processes and the removal of the need for prior network knowledge across users.	West of England and North Somerset	30/06/2022	30/06/2023
Regional Transport Branding	This activity is focused on the delivery of a Regional Transport Branding. This aims to drive higher patronage across public transport and active travel modes in the West of England.	Regional	30/09/2022	30/09/2024
Maintenance - ITB/Maintenance Funding	The Combined Authority (CA) will dedicate a section of the highway maintenance funding to cater for as yet unidentified localised safety and highway management improvements at locations which are outside the main proposals in the submission. This portion of funding will allow the CA to address any safety or traffic management issues which arise, in a timely fashion.	Regional	30/09/2022	30/06/2027
Maintenance Challenge Fund	The Combined Authority (CA) will dedicate a section of the highway maintenance funding to cater for as yet unidentified localised safety and highway management improvements at locations which are outside the main proposals in the submission. This portion of funding will allow the CA to address any safety or traffic management issues which arise, in a timely fashion.	Regional	30/09/2022	30/06/2027
Non-highways Maintenance	The Combined Authority (CA) will dedicate a section of the highway maintenance funding to cater for as yet unidentified localised safety and highway management improvements at locations which are outside the main proposals in the submission. This portion of funding will allow the CA to address any safety or traffic management issues which arise, in a timely fashion.	Regional	30/09/2022	31/06/2027
Overprogramming - Sustainable Transport Corridor Additional Value pot	This is the opportunity for all strategic corridors to enhance their existing offer through further walking and cycling provision, Enhancing connections to rural communities, first and last mile journey improvements and transport hubs	Regional	TBC	TBC
Overprogramming - Liveable Neighbourhoods Additional Value pot	This is the opportunity to enhance the liveable neighbourhood programme once trials are completed.	Regional	TBC	TBC
Overprogramming - Bus stop upgrades outside of Sustainable Transport Corridor routes	Further bus stops outside of the CRSTS sustainable transport corridors also require upgrade and standardisation.	Regional	TBC	TBC
Overprogramming - Bath City Centre sustainable transport corridor enhancements	This is the opportunity to enhance the Bath City Centre Sustainable Transport Corridor offer including further walking and cycling provision and further improvement for buses accessing the bus station.	Bath	TBC	TBC
Overprogramming - Concorde Way/ Dovercourt Depot	Off-road extension to cycling & walking strategic cycle route in North Bristol section, replacing current on-road section from Muller Road to Constable Road with high-quality walking and cycling path.	Lockleaze, Bristol	TBC	TBC
Overprogramming - Filton to MoD	Improvements to W&C routes alongside the A4174 Ring Road in Filton, from Great Stoke Way (GSW) roundabout to the Ministry of Defence facility.	Filton, North Fringe	TBC	TBC
Overprogramming - Keynsham Road	Creation of a high quality protected cycle and walking route between Bitton Station on the BBRP and Keynsham Station, along the Keynsham Road.	Bitton, SGC and Keynsham, B&NES	TBC	TBC
Overprogramming - Grovesend to Gillingstool	Stage 2 of the Thornbury Link, providing a segregated cycle route linking Thornbury to the A38 SC.	Thornbury	TBC	TBC

## WMCA
Annex A: / West Midlands Combined Authority - £1,050m City Region Sustainable Transport Settlement	West Midlands Combined Authority's (WMCA) delivery plan includes an additional reserve list of schemes as part on an approach to overprogramming. WMCA has flexibility to manage their programme in line with the approach to change control, but remain responsible for sourcing any additional funding required to deliver the agreed schemes.
Name of Scheme	Description	Location	Start of project delivery	Completion date
Highways maintenance and structures	Five year rolling Highways infrastructure maintenance programme	West Midlands	Started	01/03/2027
Wednesbury to Brierley Hill Metro Extension	Extension of the Metro from Wednesbury to Brierley Hill. Final year of Transforming Cities Fund project incorporated into CRSTS	Sandwell/Dudley	Started	30/05/2025
Very Light Rail Regional Programme*	Funding split between research and development (R&D), delivery of a demonstration project and scheme development for a complete first route. Demonstration project is a 2km route between Coventry Railway Station and Pool Meadow Bus Station in Coventry city centre, route 1 will extend this to University Hospital in the East of the city / *Scheme retained by DfT and subject to business case approval by HMG	Coventry, Dudley, Birmingham, Solihull	01/11/2022	30/09/2025
Bus Priority Cross-city Routes	Greater priority for buses through a step-change in road space re-allocation and bus priority measures (23km new bus lanes) across the region, to speed up buses and improve reliability on new cross-city and cross-regional services.	Birmingham	01/09/2024	30/09/2026
Metro Depot	The Depot upgrade will support a more than doubling of the tram fleet capacity and an even greater increase in maintenance, welfare, office and storage capacity. This project is urgently required to support the on-going Metro extension programme.	Sandwell	Started	31/03/2025
Sprint A34 Phase 2	The A34 Sprint Corridor covers North Birmingham, Sandwell, and Walsall. Scheme extends from Birmingham City Centre with 3km of new bus lane along the Walsall Road and Birmingham Road to Walsall Town Centre. The scheme includes new terminus facilities, cycling and walking enhancements.	Walsall, Birmingham and Sandwell	01/06/2023	30/11/2024
Metro Line 1 Renovation costs	Metro Line 1 is over 20 years old and the key components of Overhead Line Equipment (OLE) and track are nearing life expiry and overdue for renewal. The renewal project will include a significant redesign element for the OLE.	Wolverhampton / Sandwell / Birmingham	Started	31/12/2025
Aldridge Station*	This scheme proposes the introduction of passenger services between Walsall and a new station at Aldridge on the "Sutton Park" route, with potential future direct links through to central Birmingham. / *Scheme retained by DfT and subject to business case approval by HMG	Walsall	01/01/2025	31/03/2027
A4123 Walk, Cycle and Bus Corridor	Corridor scheme which reallocates road space to ensure that the highway suitably caters for all modes, particularly improving conditions for active travel in line with LTN 1/20 and bus priority. Scheme extends from Wolverhampton Ring Road to Hagley Road in Sandwell.	Dudley/Sandwell/Walsall	01/01/2025	01/03/2027
Sprint A45 Phase 2	The A45 Sprint Corridor covers East Birmingham and North Solihull. This scheme extends the existing route from Birmingham City Centre along the Small Heath Highway and Coventry Road with a split in Sheldon and spurs to Solihull Town Centre and to Birmingham Airport. / The scheme includes a 4km of new bus lane, new terminus facilities, cycling and walking enhancements.	Solihull	01/06/2023	30/11/2024
East Birmingham to Solihull Corridor	Enhancements in the East Birmingham to Solihull (EBS) Corridor including bus priority measures and improved access to employment sites at UK Central Hub via A45 / Damson Parkway improvements, as well as cycling and walking improvements in the corridor and the introduction of Mobility Hubs	East Birmingham/Solihull	01/06/2024	31/03/2027
Hagley Road Rapid Transit	Investigation and development of a rapid transit route, along the Hagley Road corridor between Birmingham and the Black Country, which would serve areas without access to a heavy rail network. In parallel the proposal will also deliver future-proofed bus priority measures and walking and cycling improvements between Bearwood and Birmingham City Centre in advance of any Rapid Transit proposals.	Birmingham/Sandwell	01/09/2024	31/12/2026
Sutton Gateway	Sutton Gateway is an exciting package of investment to transform access to Sutton Coldfield Town Centre by bus and active travel modes.	Birmingham	01/03/2026	31/03/2027
Inclusive growth Local Network Improvement Plan	Five year programme of minor schemes to support inclusive growth across the seven local authorities and TfWM. Schemes could include minor junction improvements to support active travel, safety upgrades or public transport information provision on the inclusive growth corridors.	West Midlands	Started	31/03/2027
Connecting our places Local Network Improvement Plan	Five year programme of minor schemes to support Connecting our Places Theme across the seven local authorities and TfWM. Schemes could include public transport information provision, park and ride improvements or bus reliability improvements on key corridors.	West Midlands	Started	31/03/2027
Healthy Streets and Spaces Local Network Improvement Plan	Five year programme of minor schemes to support Healthy Streets theme across the seven local authorities and TfWM. Schemes could include highway safety improvements to benefit cyclists or public realm improvements to support place making initiatives.	West Midlands	Started	31/03/2027
Resilient Networks and Communities Local Network Improvement Plan	Five year programme of minor schemes to support Resilient Network Theme across the seven local authorities and TfWM. Schemes could include minor junction improvements, safety upgrades or bus reliability improvements on key corridors.	West Midlands	Started	31/03/2027
Making behaviour change easy Local Network Improvement Plan	Five year programme of minor schemes and behaviour change programmes to support Making Behaviour Change Easy Theme across the seven local authorities and TfWM. Schemes could include minor junction improvements, safety upgrades or travel demand management support.	West Midlands	Started	31/03/2027
City Centre Active Travel Connections to Interchange	This scheme seeks to improve walking and cycling routes across Birmingham City Centre connecting public transport interchanges with key destinations. Will provide high-quality active travel corridors, greater priority for pedestrians and cyclists and enhanced signage and wayfinding in the city centre.	Birmingham	01/09/2025	31/03/2027
Smethwick - Birmingham Inclusive Growth Corridor Transport Package	Corridor improvements to support connectivity between deprived areas of Smethwick and West Birmingham including segregated cycling facilities. Estimated 1km of cycle interventions.	Sandwell and Birmingham	01/03/2025	31/03/2027
A41 Moxley Iron Park to Walsall Town Centre Walk, Cycle and Bus Corridor Phase 1	This corridor (A41/A4038) provides a key strategic link between Darlaston and Walsall town centre. The scheme extends from Moxley Junction to Walsall Rd, Darlaston Rd and Wednesbury Rd leading into Walsall town centre. This first phase will focus on LTN1/20 cycle improvements and integration with bus and rail (Darlaston Rail Station opening 2023).	Walsall	01/04/2026	01/03/2027
A454 Walk, Cycle and Bus Corridor	Corridor scheme which reallocates space to ensure that the highway suitably caters for all modes, particularly improving conditions for active travel in line with LTN 1/20 and bus priority. Aspiration to deliver 5.5km of high quality cycle route and 1.5km of bus priority.	Walsall/Wolverhampton	01/09/2024	31/03/2027
Swift contactless payment (cEMV) broker	To deliver a broker that will enable integrated cEMV contactless payment transactions with best value capping across operators and modes removing the current issue where customers are overcharged when using their bank card to travel on multiple operators services.	West Midlands	01/11/2022	01/12/2025
Coventry South Sustainable Transport (inc access to proposed GIGA Factory site)	The South of Coventry is an area experiencing substantial economic growth, with the establishment of a Battery Innovation Centre (BIC), the expansion of Jaguar Land Rover’s global HQ and plans to build the UK’s largest Gigafactory. This scheme will deliver sustainable transport links between the centre of Coventry and these locations	Coventry	01/01/2023	01/03/2025
Wednesbury to Brierley Hill Extension Sustainable Access Measures	Improve active travel connectivity to WBHE stops to reduce reliance on private cars and the possibility of informal and undesirable parking taking place. The scheme will also consider public transport interchange between metro and other public transport infrastructure. Aspiration to deliver 6km of segregated cycle route through this scheme.	WBHE corridor (Sandwell / Dudley)	01/01/2024	31/03/2027
Selly Oak to Longbridge Segregated Cycling Route	The A38 Active Travel Route will provide a continuous 7.2km segregated cycle route, LTN 1/20 compliant link from Selly Oak to Longbridge, completing the full A38 corridor within Birmingham.	Birmingham	01/05/2025	31/01/2027
Active Travel - A45 Segregated Cycleway	The A45 Active Travel Route provides a continuous, LTN 1/20 compliant link from Birmingham City Centre towards Birmingham Airport.	Birmingham	01/03/2025	30/04/2026
Ultra Rapid Charging Transit Stations	The project will see the development of 10 Transit Stations located on or in close proximity to the Key Route Network/Major Road Network/Strategic Road Network for the West Midlands and hinterland.	West Midlands	01/08/2023	30/06/2025
Metro Traction power	The power supply that provides the backbone of the wider network is over 20 years old and increasingly unreliable and obsolete. In order to accommodate the increased service levels and numbers of trams , traction power upgrades to Line One are required.	West Midlands	01/10/2022	30/09/2025
A461 Dudley Walk, Cycle and Bus Corridor	Corridor scheme which reallocates space to ensure that the highway suitably caters for all modes, particularly improving conditions for active travel in line with LTN 1/20 and bus priority. This scheme extends along the Amblecote to Dudley corridor, with 4-key nodes which require specific connectivity improvements.	Dudley	01/03/2025	31/03/2027
A461 Sandwell Walk, Cycle and Bus Corridor	Major Road Network Corridor spanning Dudley, Sandwell and Walsall Boroughs. Scheme extends from Dudley to the A41, Great Bridge Aspiration to deliver 3.2km of cycle route and 1km of bus priority as part of scheme. Scheme development of A461 Walsall partially included within this scheme to maximise benefits.	Sandwell/Walsall	01/03/2025	31/03/2027
Ultra Low Emission Vehicles	To deliver electric vehicle chargepoint infrastructure and associated interventions across the West Midlands with particular focus on areas of deprivation and grid upgrade requirements for residents and businesses in the West Midlands.	West Midlands	01/04/2023	31/03/2027
Dickens Heath to Solihull Town Centre LCWIP Scheme	Delivery of 6.4km of LTN 1/20-compliant two-way segregated cycle infrastructure, along a key priority corridor as identified within both the West Midlands and Solihull Local Cycle and Walking Implementation Plans (LCWIPs)	Solihull	01/02/2024	28/02/2025
One Station and Smallbrook Queensway	Investment around Moor Street Station and Smallbrook Queensway, to better connect Moor Street Station and Birmingham New Street Station through enhancements to the active travel route, which currently is extremely hostile and unattractive. The scheme will also explore feasibility of onwards access to Curzon Street HS2 station.	Birmingham	01/10/2025	31/03/2027
Demand Responsive Bus (inc diversification of Ring & Ride)	Demand Responsive Transport enables customers to book journeys on demand, either via phone or through an app. DRT offers greater flexibility than fixed bus services and by pooling together similar journeys at similar times it is more efficient than taxis.	West Midlands	01/09/2025	31/03/2027
Wolverhampton City Centre Movement - Walk, Cycle and Bus Package	Reallocation of road space in the city centre in favour of high quality active travel and public transport infrastructure. Increased and improved bus stop facilities. LTN 1/20 compliant cycle infrastructure, linking to National Cycle Network route 81. New bus lane and bus gates.	Wolverhampton	01/03/2023	30/04/2024
Mobility Hubs	Mobility hubs are compact public spaces that bring together shared mobility services, support for active travel and community enterprise areas.	West Midlands	01/04/2024	31/03/2027
Black Country Walking and Cycling Package	Black Country wide package of walking and cycling interventions covering routes in Dudley, Sandwell and Wolverhampton. Routes included are; Oldhill to Halesowen (Dudley), West Bromwich to Cradley Heath and West Bromwich to Wednesbury (Sandwell), and A4124 Wednesfield Road, and Ring Road Linking Scheme (Wolverhampton).	Dudley/Sandwell/Walsall/Wolverhampton	01/10/2023	31/03/2027
Knowle to Solihull Town Centre LCWIP Scheme.	Delivery of 4.2km of LTN 1/20-compliant two-way segregated cycle infrastructure, along a key priority corridor as identified within the Solihull LCWIP	Solihull	01/02/2024	28/02/2025
A449 Walk, Cycle and Bus Corridor	A highway scheme with a particular focus on improving conditions for pedestrians, cyclists and bus passengers by installing high-quality walking and cycling infrastructure through reallocating road space. Scheme aspiration to deliver 4.2km of cycle lane and 0.25km of bus priority measures.	Wolverhampton	01/04/2023	30/09/2024
Dudley Town Centre Interchange Sustainable Connectivity Package	This package will focus on the bus and metro interchange area of the town centre, and will improve pedestrian and cycle connectivity to the wider town centre through integration with infrastructure and public realm enhancements previously delivered in the Market Place and Castle Street areas.	Dudley	01/01/2025	31/03/2027
Data to support scheme development plus M&E	There is usually additional specific data needs for individual scheme development, managing the impacts of the scheme and also the Monitoring & Evaluation (M&E).	West Midlands	Started	31/03/2032
Chester Road Corridor – Segregated Cycleway and Capacity Enhancement.	Delivery of 1.2km of LTN 1/20-compliant two-way segregated cycle infrastructure, along a key section of the Major Road Network that has been identified as a priority corridor within the Solihull Local Cycle and Walking Implementation Plan (LCWIP), along with modest amendment to two junctions to relieve current bottlenecks.	Solihull	01/06/2025	31/12/2026
Solihull Rail Station	Planned improvements to Solihull Station to safely accommodate forecast passenger demand, encourage and enable modal shift and to sustainably support significant employment and housing growth ambitions for Solihull Town Centre. The scheme will improve interchange facilities between bus and rail and cater for new Sprint Bus Rapid Transit vehicles (Development only in this period)	Solihull	01/11/2022	31/03/2027
UK Central - Solihull - Dorridge Bus Priority	Delivery of a cross-Solihull bus route, with priority infrastructure to connect the UK Central Hub area (HS2 Interchange, Birmingham Airport, NEC, JLR and Birmingham Business Park) with Solihull Town Centre, Cranmore and Blythe Valley Business Parks and Knowle / Dorridge.	Solihull	01/03/2026	31/03/2027
Snow Hill Growth Strategy	This project will see the development of a scheme which will improve the both active and sustainable transport connectivity within the Snow Hill area, addressing connectivity issues and access barriers into and within the area and addressing severance caused by highways. Scheme development will also support a proposed office-led development of the area. (Development only in this period)	Birmingham	03/01/2023	31/9/2026
Multi-modal Access to HS2 Enhancement.	Enhancement to public transport, cycle, pedestrian and highways infrastructure being delivered by HS2 to accommodate demand associated with the employment growth that HS2 is intended to generate. (Development only in this period)	Solihull	03/01/2023	31/03/2027
West Coast Mainline and M42 Public Transport and Active Travel bridge links to HS2 Hub.	Delivery of public transport and active travel bridge links to connect Birmingham Airport with the NEC and HS2 Interchange Station / Arden Cross development; three major trip generators that are currently severed by the West Coast Mainline and M42 and, as a result, tend to function as discrete entities. (Development only in this period)	Solihull	03/01/2023	31/03/2027
Park & Ride Estate Development (Tile Hill & Whitlocks End)	Park and Ride facility for Tile Hill, a popular station on the West Coast Mainline between Coventry and Birmingham International. In addition, the scheme will include development funding for Park and Ride at Whitlocks End Railway Station in Solihull	Coventry/Solihull	01/08/2024	31/10/2026
Foleshill Transport Package	Funding will complement Local Air Quality Action Plan (LAQAP) and Active Travel Fund (ATF) funded projects aimed at substantially reducing through traffic on Foleshill Road, promoting public transport and active travel	Coventry	01/07/2023	31/12/2024
Walk, Cycle and Bus Access: Darlaston and Willenhall Train Stations	Development of walk, cycle, bus and general traffic improvements to complement the new railway stations in Willenhall and Darlaston. Ensures the full regeneration potential of new stations is realised. Improves access to jobs at Black Country Enterprise Zone sites adjacent to Darlaston Station and brownfield land housing sites around Willenhall Station.	Walsall	01/04/2024	31/03/2025
Rail Development	Following on from TfWM’s current delivery of five new stations, the Rail Development fund will support the early development and business case work on further new station projects	West Midlands	03/01/2023	31/03/2027
Stourbridge Town Centre Sustainable Connectivity Package	The scheme is primarily located in Stourbridge Town Centre, creating an improved and safer pedestrian environment by making permanent some of the road space reallocation measures that were temporarily installed under the Emergency Active Travel Fund (EATF). This includes the removal of some on-street parking and widening footways to support pedestrian movement	Dudley	01/06/2024	30/09/2026
BSIP Retrofit Programme (120 buses to Euro 6)	Fund to make all buses on local bus services at least Euro VI, becoming the first Mayoral Combined Authority region to achieve this. It would fund the remaining 120 non-Euro VI buses operating local bus services in the West Midlands, and be protected by setting minimum Euro VI standards through the Enhanced Partnership.	West Midlands	01/06/2025	31/03/2026
Dudley Port ITH - Phase 1 and Phase 2 Development	The proposals for the integrated transport hub (ITH) include improvements to interchange connections between public transport modes and to the accessibility of the railway station, which is already the busiest non-accessible station in the West Midlands. It will be the only location of Metro and rail interchange on the Wednesbury to Brierley Hill Metro Extension (WBHE) which is due to open in 2024.	Sandwell	01/01/2024	01/12/2024
Walk, Cycle and Bus Access: Walsall Town Centre Interchange	At the heart of Walsall town centre, providing improved access and connectivity for pedestrians, cyclists, bus and SPRINT users, enabling the Town Centre Masterplan and creating an environment where regeneration can thrive. Development only in this period.	Walsall	08/01/2024	31/03/2027
Overprogramming - Eastern Green or Keresley Cycleways	Eastern Green Cycleway connects a major new housing site, on the western fringe of Coventry, with Coventry City Centre to the east and to Tile Hill Station to the south. / Kersley Connects Cycleway links a major new housing site, with Coventry City Centre to the south east and to Allesley and Lyons Park employment area to the south west.	Coventry	TBC	TBC
Overprogramming - University of Warwick Cycle Routes	University of Warwick is a major employment and education site, which is expanding. Improvements to cycle connectivity to neighbouring residential areas, stations and the city centre.	Coventry	TBC	TBC
Overprogramming - Birmingham Airport to Castle Bromwich LCWIP Scheme.	This scheme would connect the North of the Borough to Birmingham Airport/UK Central Hub (HS2) area.	Solihull	TBC	TBC
Overprogramming - LCWIP Priorities: Birmingham	Birmingham wide package of walking and cycling interventions covering routes across the City linked to the Local Cycling and Walking Implementation Plan (LCWIP)	Birmingham	01/04/2023	31/03/2027
Overprogramming - LCWIP Priorities: Black Country	Black Country wide package of walking and cycling interventions covering routes in Dudley, Sandwell and Wolverhampton linked to the Local Cycling and Walking Implementation Plan (LCWIP)	Dudley/Sandwell/Walsall/Wolverhampton	01/04/2023	31/03/2027
Overprogramming - Demand Responsive Transport	Demand Responsive Transport enables customers to book journeys on demand, either via phone or through an app. DRT offers greater flexibility than fixed bus services and by pooling together similar journeys at similar times it is more efficient than taxis. Additional funding would increase the deployment of these services across the region.	West Midlands	01/04/2022	31/03/2025
Overprogramming - Mobility Hubs	Mobility hubs are compact public spaces that bring together shared mobility services and support access to sustainable transport modes. Additional funding would increase the deployment of these facilities across the region.	West Midlands	01/04/2022	31/03/2025
Overprogramming - A41 Moxley Walk, Cycle and Bus corridor - Walsall	Large highway junction improvement to address congestion, improve pedestrian facilities, improve cycle facilities and improve public transport reliability. Additional funding would accelerate the delivery of the full scheme in the CRSTS period.	Walsall	TBC	TBC
Overprogramming - Rail and Rapid Transit programme inc Metro Lifecycle	Metro Line 1 is over 20 years old and the key components of OLE and track are nearing life expiry and overdue for renewal. Additional funding would deliver a range of enhancements and renewals to the line across track, comms systems, structures and stops.	Wolverhampton / Sandwell / Birmingham	01/04/2022	31/03/2027
Overprogramming - East Birmingham to Solihull Corridor	Enhancements in the East Birmingham to Solihull (EBS) Corridor including bus priority measures and cycling and walking improvements in the corridor. The additional funding would support the delivery of additional infrastructure schemes, identified in the draft SOBC, aimed at improving first/last mile connectivity.	East Birmingham/Solihull	TBC	TBC
Overprogramming - Rules of the Road	Building upon the work started within the Future Transport Zone (FTZ) to build a fully digitised (and live) view of the network this continuation request is aimed at finishing that work.	West Midlands	01/04/2023	01/04/2025

## WYCA
Annex A: / West Yorkshire Mayoral Combined Authority - £830m City Region Sustainable Transport Settlement	West Yorkshire Combined Authority's (WYCA) delivery plan incorporates a proportion of overprogramming, additional to their agreed settlement. WYCA has flexibility to manage their programme in line with the approach to change control, but is responsible for sourcing any additional funding required to deliver the agreed schemes.
Name of Scheme	Description	Location	Start of project delivery	Completion date
West Bradford - Cycle Superhighway Extension	Delivering a direct, segregated cycle route to provide cyclists with a safe, secure space to travel easily and conveniently between Bradford city centre and areas to the west of the city.	Bradford	01/11/2022	20/03/2024
Bradford Interchange Station Access	Improving Bradford Interchange and access to it, including a new station approach and entrance for pedestrians giving a direct, safe and legible route from the civic quarter and City Park through to the interchange.	Bradford	01/01/2023	26/04/2024
Bradford City Centre Cycling and Walking Improvements	Removing through traffic from key civic areas, create corridors for cycling and walking including the introduction of new green spaces. Create a new bus priority corridor around Bradford city centre for more efficient movement of buses, with new bus hubs serving key locations in the city centre.	Bradford	01/02/2023	24/07/2024
South Bradford Park & Ride and Bus Expressway	Deliver a high-quality, high frequency dedicated bus service between Bradford city centre and the M606 motorway, via Manchester Road by providing a bus expressway. This scheme will be complemented by introducing segregated cycle routes, new bus hub locations, bus priority measures and linking to a park and ride site.	Bradford	01/02/2023	26/03/2024
Halifax Rail Station Gateway	Transformation of Halifax railway station including a new footbridge to improve access to the station, better pedestrian and cycle links by re-opening a disused underpass, and improved connections to local public transport and the town centre.	Halifax	01/02/2023	30/06/2025
West Halifax Improved Streets for People	Provide improvements for walking and cycling in West Halifax, one of the most deprived wards in Calderdale and create safer connections to Halifax town centre for those walking and cycling providing new cycle routes and footpaths, crossing facilities, changes to parking and measures to address inappropriate speeds.	Halifax	01/10/2022	14/08/2023
North Halifax Improved Streets for People	Create a new cycleway from North Halifax to Halifax town centre, improve pavements and crossing points for walking and cycling and improve street lighting.	Halifax	01/10/2022	18/08/2023
Elland Rail Station Walking and Cycling Access	Improve walking and cycling routes to the proposed new Elland railway station, this includes two new pedestrian/cycle bridges across the River Calder/Calder Hebble Navigation/West Vale., providing connections to existing cycleways and future development areas to help connect the Town Centre/station with the wider housing and employment catchment.	Elland	01/04/2023	01/03/2024
Brighouse Cycling and Walking Improvements	Forming part of the wider A641 Corridor project being delivered through the West Yorkshire plus Transport Fund, providing improved crossing facilities and linking existing cycling and walking routes to the rail station and new bus priority measures to improve bus journey times and reliability.	Brighouse	01/12/2023	01/12/2025
Heckmondwike Bus Hub	A new bus station facility in the centre of Heckmondwike, increasing bus capacity, improving passenger waiting facilities, including new toilet facilities and better bus information along with improved access arrangements to the station for buses, reducing journey times, boarding arrangements and measures to improve associated bus movements and journey times within the town.	Heckmondwike,	01/09/2022	01/07/2023
Dewsbury - Cleckheaton Bus, cycling and walking corridor	New bus priority measures, new/widened footways and crossings along the length of the A638 corridor, from the outskirts of Dewsbury town centre, through Heckmondwike and Cleckheaton, to Chain Bar roundabout on the M62. The scheme will also deliver sections of new segregated cycle route between Cleckheaton and Heckmondwike.	Dewsbury/Cleckheaton	01/10/2022	30/09/2023
Dewsbury - Batley - Chidswell Bus, cycling and walking corridor	Provide a series of bus, cycle and footway improvements along routes between Dewsbury, Batley and Chidswell. These include new cycle links, widened footways, new crossing points, bus priority at junctions and enhanced waiting facilities and bus information at stops.	Dewsbury/Batley/Cleckheaton	01/03/2023	01/02/2024
Dewsbury Town Centre Walking & Cycling Improvements	Improve the provision and safety of walking and cycling in and to/from Dewsbury town centre through the delivery of new and upgraded footways, crossing facilities, cycle routes and improved connectivity between the rail/bus stations and reduce severance of residential areas on the periphery of the town.	Dewsbury	01/10/2022	30/09/2023
A629 Wakefield Road Sustainable Transport scheme	Deliver enhancements to existing bus priority alongside introduction of a segregated cycle route along the A629 route between Waterloo and Huddersfield town centre.	Huddersfield	01/03/2023	31/03/2024
Huddersfield Rail Station walking and cycling connections	Deliver more attractive and safer walking and cycling routes on key approaches to Huddersfield town centre and to its key rail and bus sites, education sites and across the ring road to reduce segregation from using more sustainable modes of transport.	Huddersfield	01/11/2022	30/11/2023
A64 Bus, Cycle and Walking Improvements and bus P&R	Improve bus journey times through creation of bus priority measures along the A64 and provide enhancements to existing cycle infrastructure, with additional connections to the existing cycle superhighway. The scheme will also link to a future park and ride site to provide more attractive bus journeys.	Leeds	01/05/2023	01/02/2024
Leeds Station - Sustainable Travel Gateway (Bishopgate)	Create a multi-modal gateway at Leeds Rail Station, including pedestrian priority areas, improved accessibility to the station, create step-free access for passengers, installation of segregated cycle lanes and widened footways, enhanced lighting within these areas and the provision of a 700 space cycle hub and infrastructure for e-bikes.	Leeds	01/06/2022	31/03/2024
Leeds City Centre Cycle Improvements	Consolidating and fully connecting cycle infrastructure in Leeds city centre, creating a fully segregated cycle network across the city.	Leeds	11/07/2022	30/04/2023
Leeds Public E- Bike Cycle Share	Provide and maintain a network of electric bikes for hire by the public within the centre of Leeds, this will complement a range of current and future cycling initiatives and infrastructure, enabling people to make journeys by bike across the city, whatever their ability.	Leeds	01/04/2023	01/06/2023
Wakefield City Centre Bus, Cycle and Walking Improvements	Remove elements of through traffic from parts of Wakefield city centre and provide walking and segregated cycle links from/to key locations as well as links to wider cycle provision outside of the city. New bus priority measures around the bus station will also improve bus journey times and reliability.	Wakefield	01/02/2023	01/02/2024
A61 Bus, Cycle and Walking Improvements	Enhanced bus priority and new, targeted, high quality cycle infrastructure. New and improved crossings for pedestrians and cyclists at key locations. New bus lanes / priority at locations in Leeds and Wakefield to improve bus journey times.	Leeds and Wakefield	01/11/2023	01/12/2024
A639 Bus, Cycle and Walking Improvements	Enhanced bus priority and new, targeted, high quality cycle infrastructure. New and improved crossings for pedestrians and cyclists at key locations. New bus lanes / priority at locations in Leeds and Wakefield to improve bus journey times.	Leeds and Wakefield	01/11/2023	01/12/2024
Halifax Bus Station	Deliver a modern, fit for purpose bus station, creates a public transport gateway into the town centre, a key place of interchange for bus services, and includes a fully enclosed and level concourse facility (including customer information, toilets and retail), cycle parking and improved access for pedestrians.	Halifax	01/09/2021	28/07/2023
White Rose Station	Deliver a new train station which aims to provide enhanced connectivity for local people and businesses to Leeds, as well as providing improved access to Dewsbury, Huddersfield and improving accessibility to the existing White Rose site, a key employment, retail and educational hub.	Leeds	Started	31/03/2023
Dewsbury Bus Station	Transform Dewsbury Bus Station, improving both operational and passenger facilities, including improvements to bus flow, pedestrian access, passenger concourse and waiting areas, journey information and facilities for customers. This will significantly improve passenger experience and support the drive to encourage increased bus travel in the town.	Dewsbury	01/04/2023	09/02/2024
Huddersfield Bus Station	Transform Huddersfield Bus Station, improve both operational and passenger facilities, including improvements to bus flow, pedestrian access, waiting areas, journey information and facilities for customers as well as a new cycle hub. This will significantly improve passenger experience and encourage increased bus travel into the town.	Huddersfield	01/08/2023	08/07/2024
Public Transport Network Navigation	Making it easier for bus passengers to navigate the bus network by improving legibility and improving accessibility expanding the existing Leeds Network Navigation project across the core bus network in West Yorkshire, through real-time information, bus stop information, access improvements, and journey/route planning tools.	West Yorkshire-wide	01/10/2022	31/03/2024
Wakefield Road, Bradford transformational bus priority and cycle corridor	Bus priority measures on A650 Wakefield Road to deliver a Bus Rapid Transit-level provision, improving bus journey times and journey reliability through road space reallocation, including upgrade and making permanent temporary segregated cycle scheme on from Dudley Hill to Bradford city centre to be improved and made permanent.	Bradford	01/08/2024	01/03/2027
Kings Road sustainable transport (bus + cycle) corridor	Bus priority measures along Kings Road and Canal Road corridor, improving bus journey times and journey reliability through road space reallocation, alongside protected cycle lanes on Kings Road	Bradford	31/01/2026	31/01/2027
Bradford Bus Hotspots (Westgate / Drewton Rd / Lumb Lane; Leeds Rd gyratory; Bolton Rd / Leeds Rd / Stone Hall Rd)	A package of measures including road space reallocation, bus lanes, bus gates and junction modifications to improve journey times. Specifically, the package aims to improve the travel time through key junctions.	Bradford	04/09/2024	28/02/2025
Calderdale Bus hotspots and priority incl. bus lane camera enforcement	A package of interventions to improve bus journey times and reliability, including camera enforcement of bus lanes along main bus corridors and bus gates within Halifax and other district centres alongside other potential measures e.g., traffic regulation measures particularly focusing on pinch points on popular routes.	Calderdale District	01/07/2025	01/03/2027
North-East Calderdale Bus Priority and Cycle corridor – phase 1	Development and initial delivery of a major scheme to improve bus and active travel in north east Calderdale, reducing the impact of through traffic on local communities. The scheme enables development work on the major scheme as well as delivering bus priority between Halifax and Stump Cross. Delivery will be for the construction of the bus priority element.	Halifax and NE Calderdale	30/06/2026	31/03/2027
A62 – A644 Bus priority corridors- Huddersfield – Cooper Bridge – Ravensthorpe – Dewsbury	Bus infrastructure enhancements to improve bus journey times and reliability, along two main corridors within Kirklees, A62 Leeds Road / A644 Huddersfield Road. This project sits alongside several transport schemes already in progression in order to provide continuity and additionality to provide sustainable transport enhancements over a wider area.	Cooper Bridge/Mirfield	31/03/2025	01/09/2026
Dalton Deighton Active Travel	Quality, off-road walking and cycling route, complementing future on-road infrastructure by improving access to settlements and new development by active modes. Benefits include less congestion, reduced journey times, improved air quality, improved safety, reduced noise, and better social and economic outcomes in local communities.	Dalton/Deighton	31/03/2025	30/09/2026
Beckett Street, Leeds – transformational bus priority scheme	Bus priority scheme combining bus lane and junction upgrades and active travel improvements to link the city centre to St James Hospital and north-east Leeds. The scheme will provide continuous bus priority, segregated cycle infrastructure, and improved pedestrian provision, to improve bus journey times and reliability and provide safe walking and cycling provision	Leeds	01/04/2024	30/09/2025
Leeds City Centre Bus Priority and Active Travel	A package of measures that builds on the success of Leeds city centres schemes being delivered through other funding programmes (TCF, LPTIP , and the Transport Fund) to enhance the sustainable transport offer in Leeds city centre by re-allocating existing carriageway to more sustainable modes, in accordance with LTN 1/20 and the National Bus Strategy. (Delivery dates are for start of work on first package, and end date for last package)	Leeds	30/09/2022	30/06/2025
A660 bus priority & cycle corridor incl. Lawnswood roundabout	Bus priority and cycle provision along key corridor in north Leeds, providing bus priority and segregated cycle provision on the corridor, including improvements to Lawnswood roundabout to address cycling safety issues	Leeds	01/10/2023	31/12/2024
A61 (N) multi modal corridor improvements - Scott Hall Road bus lane	Deliver 1km of outbound bus lane to remove the source of significant bus delay on this important corridor between north Leeds and Leeds city centre. It will also re-prioritise traffic at two large, congested junctions to prioritise bus services, resulting in faster and more reliable bus journey times. There are also associated cycling and walking improvements.	Leeds	01/07/2023	30/09/2024
A660 - Northern/University Gateway inclusive of the Headrow to St Marks Road.	Addressing bus delay through improvements in Leeds city centre up to the Inner Ring Road. From there, the scheme will remove general traffic from Blenheim Terrace in both directions, creating a bus, cycle and walking only environment, facilitated through the provision of bus gates and complementing the proposed A660 protected cycle lane.	Leeds	01/04/2025	01/01/2027
Elland Road South/Churwell Hill	Introduce a bus bypass lane to allow buses to avoid queuing traffic at a busy junction onto the ring road and improve bus waiting facilities. The scheme also provides new cycling facilities with bi-directional cycleways and controlled crossing facilities to all arms of the junction.	Leeds	01/10/2023	31/12/2024
Thirsk Row Bus gate	Enable an existing one-way street to be two-way for buses (remaining one way for general traffic) along with a new bus gate enabling buses to avoid unnecessary and highly congested movement in the city centre. It will also enable a wider footway and an extension of the existing bi-directional cycle track.	Leeds	01/10/2022	31/03/2023
Heath Common to Knottingley Bus Priority	Targeted bus priority at key locations. This may include new bus lanes and priority provision at junctions along the core bus corridor to improve bus journey times.	Wakefield, Featherstone, Pontefract and Knottingley	01/01/2025	31/03/2026
Horbury to Wakefield / Ossett to Wakefield bus priority	Bus priority measures and associated cycle improvements on bus corridors linking communities in the west of Wakefield district linking Wakefield city to Ossett and Horbury	Wakefield, Horbury and Ossett	01/01/2025	31/03/2026
A639 Park Road, Pontefract – on and off highways improvements	New bus priority at signalised junctions to improve bus journey times alongside new or improved, targeted, high quality cycle infrastructure. The scheme will also deliver new and improved crossings for pedestrians and cyclists at key locations to improves access to bus stops and existing /new cycle routes.	Pontefract	01/03/2024	31/03/2025
South Wakefield Bus Package (including; A636 Denby Dale Road bus priority measures)	Targeted bus priority at key locations in Wakefield district. This is expected to include new bus lanes and priority provision at junctions along the bus corridor to improve bus journey times.	Wakefield	01/01/2025	31/03/2026
North Wakefield Bus Package (including; A642 Aberford Road corridor bus priority measures)	Targeted bus priority at key locations in Wakefield district which could include new bus lanes, bus gates and priority provision at junctions along the bus corridor to improve bus journey times	Wakefield	01/01/2025	31/03/2026
Wakefield City – extension to LCWIP1 (Local Cycling and Walking Improvement Plan) schemes	Targeted, high quality cycle infrastructure. The proposals will provide a connection between new facilities provided in Wakefield city centre (by the Transforming Cities Fund programme) to the north (where other facilities are currently being delivered). The aim is to complete schemes identified in the Wakefield Local Cycling and Walking Infrastructure Plan	Wakefield	01/11/2024	31/03/2026
Castleford Wheldon Road pedestrian and cycle bridge	New bridge for cyclists and pedestrians, to address safety issues on existing road bridge that has no provision. Links to wider Castleford growth corridor scheme that provides new cycle lanes, pedestrian facilities to the north of the town centre.	Castleford	30/09/2023	01/08/2024
North Halifax Streets for People enhancements (Illingworth/Ovenden)	Provide cycle links from the centre Halifax towards Ovenden, and Illingworth, which have all been identified in the Calderdale Cycling Strategy. The project also creates greater space for walking in Ovenden and Holmfield	Halifax	08/09/2023	12/07/2024
Leeds Creating Healthier Streets, Spaces and Communities	Delivering safer streets across Leeds district through reducing through traffic and modal filters supporting mode shift from car and reduced carbon emissions. Package of measures to deliver walking and cycling improvements, through active travel neighbourhoods, school streets, improved cycle parking, District Centre enhancements and traffic signal upgrades to give greater priority for pedestrians and cyclists.	Leeds District	01/10/2024	30/09/2026
Steeton and Silsden cycling and walking Improvements	An active travel corridor including a pedestrian and cycle bridge over the A629 dual carriageway reducing the severance between two communities, provide protected cycleways and wider footways connecting to the bridge creating a safe and attractive route between the two settlements	Steeton and Silsden	31/01/2025	31/01/2026
West Yorkshire neighbourhood improvement package (incl. active travel and electric vehicle charging)	Improvements within local neighbourhoods to create safer, more economically active local areas and high streets. Delivering improvements to walking and cycling provision alongside other potential measures improvements such as electric vehicle charging points, bus gates, car club spaces, cycle parking, sustainable urban drainage and the creation of informal/formal mobility hubs.	West Yorkshire wide	01/09/2024	31/03/2027
Mobility hubs	Delivery of seven mobility hubs in locations across West Yorkshire. These hubs will increase local transport accessibility by providing access to demand responsive transport services, shared bikes, car club and EV charging facilities to complement existing public transport networks. Facilities delivered at the hubs include – cycle parking, cycle hire, EV charging points, passenger information and improved waiting facilities.	Specific locations within West Yorkshire	01/04/2024	01/01/2026
Car club network electrification	Electrification of the existing car club network within West Yorkshire. This will include delivery of EV charge points, replacement of some existing charging infrastructure that is no longer fit for purpose and creation of a fund for operators to bid into in order to gap fund EV car club vehicles. Delivery of the charge points will be aligned with the mobility hubs and wider EV charge point delivery programme in West Yorkshire.	West Yorkshire wide	01/01/2024	01/06/2025
Demand Responsive Transport (DRT)	Delivery of demand responsive bus schemes across West Yorkshire. Based on the lessons learned from the East Leeds Flexibus scheme DRT schemes will be developed to address specific areas of need where public transport access is currently poor.	Specific locations within West Yorkshire	01/01/2024	01/10/2024
Integrated ticketing and information	A range of initiatives, complemented with BSIP revenue funding, that support improved ticketing and information including: / • Installation of tap-out card readers and electronic ticketing machines (to enable pay-as-you-go capping) / • Retrofitting of vehicles with onboard audio-visual information technology / • Further development of the MCard mobile app / • Enhanced disruption messaging / • Information accessibility enhancements	West Yorkshire wide	01/10/2023	01/10/2025
Highways Asset Management and Enhancement	The programme will implement renewal and improvement of highway assets, including roads, structures, cycleways, footways, lighting and drainage across West Yorkshire. Asset enhancement will also benefit sustainable modes of travel by introducing elements of bus, cycle and walking improvements into traditional asset renewal projects.	West Yorkshire wide	Started	31/03/2027
Highways Network Management and Enhancement	The programme will replace out-of-date and high-risk signal infrastructure as well as introduce modern network management systems that allow opportunities for detection and priority of pedestrians, cyclists and buses at junctions, including smart traffic control that can automatically respond to congestion and air quality information.	West Yorkshire wide	Started	31/03/2027
Bradford Interchange – bus station essential works	The scheme will upgrade the bus station and address high priority defects in waterproofing for slabs at Bradford Interchange.	Bradford	05/09/2022	01/08/2023
Bus shelter improvement programme.	Shelter refurbishment, renewal and improvement package, delivering renewal of life expired shelters and new features and facilities to create greener and more innovative shelters. These could include intelligent shelters, phone charging, Real Time I information screens, advertising, and solar panels	West Yorkshire wide	01/01/2023	31/03/2027
Safety Accessibility and Efficiency Programme	The scheme will deliver improvements at bus stations and stops to make public transport more accessible to everyone, developing solutions through engagement with disabled people. It will also deliver an Invest to Save programme to reduce consumption and waste, leading to carbon reductions across the public transport estate. Phase 1 of this project is currently underway (funded elsewhere), CRSTS will fund Phase 2.	West Yorkshire wide	06/02/2023	01/09/2025
Bus Station improvements programme	Improvements to bus stations across the region to improve customer experience and make bus journeys a more attractive and competitive option	Bradford	08/05/2023	31/03/2027
Community Transport Vehicle renewal and upgrade to electric vehicles	Access Bus community transport vehicle fleet replacement and upgrade to electric vehicles.	West Yorkshire wide	01/07/2024	01/07/2026
Off Highway walking and cycling routes	Improvements to the Public Rights of Way (PROW) Network to support active travel and place improvements within the CRSTS programme, delivering measures to support accessible, active travel modes and links to public transport facilities on existing rights of way and cycle routes.	West Yorkshire wide	01/04/2027	31/03/2027
Mass transit development and delivery*	Development and initial delivery of a new form of public transport system for West Yorkshire, to increases capacity and provide an alternative to car travel for the region, linked to bus, rail, cycling and walking networks across the region as part of an integrated transport system. / *Scheme retained by DfT and subject to business case approval by HMG	West Yorkshire	Started / (Development only)	31/03/2027 / (Development within CRSTS period ends – development and delivery will continue into next period)
West Yorkshire Rail Accessibility Package	Improve the accessibility and inclusivity of West Yorkshire rail stations, reducing the barriers to travel and improving passengers’ travel experience especially for those with disabilities and other disadvantaged groups. Contribute towards making a fully accessible transport system	Various Stations across West Yorkshire	01/04/2024	31/03/2027
Leeds City Rail Station - Platform 13/17 extension - allowing longer trains and better rail services to the Five Towns/Wakefield district	Extension of platforms at Leeds City Rail Station to allow longer trains and improved capacity on the rail network, reducing barriers to travel and increasing the attractiveness of rail, as more sustainable mode of transport. This will improve access to jobs and support mode shift from car and reducing impacts associated with car travel.	Leeds	31/03/2024	31/03/2025
Kirklees enhanced Electric Vehicle programme - residential charging and support programme	Developing Kirklees as a national demonstrator for larger scale Electric Vehicle Charging deployment, including the provision of charging on residential streets without impinging on the walking or cycling experience. This package includes a “try before you buy” Electric Vehicle scheme and delivery of on-street charging points.	Kirklees district wide	01/04/2024	01/10/2026
Kirklees district wide speed limit review	The scheme will lower speed limits where appropriate to 20mph in built up areas and 40mph and 50mph on some busy rural routes, improving safety, reducing pollution and carbon emissions, on roads where traffic speeds are dangerous and reduce the ability of the network to support walking, cycling or accommodate bus.	Kirklees district wide	31/03/2023	31/03/2025
Highways Safer Roads programme	The programme will deliver highway engineering projects to target known collision locations and inappropriate speed, and also proactively deliver projects to better manage safety risks and encourage and reduce barriers to active travel. The programme is aligned with existing road safety training activities and the regional Vision Zero Action Plan.	West Yorkshire wide	Started	31/04/27
Zero emission buses	Introducing Zero Emission Buses and related infrastructure, building on current zero emission bus programmes to help achieve our targets in the Bus Service Improvement Plan to raise the total proportion of the fleet to 50% by 2030	West Yorkshire wide	01/05/2023	01/03/2026