## Table Key
TRANSMISSION OWNER MAJOR PROJECT STATUS UPDATE - DECEMBER 2021
KEY explaining individual columns
Ref No cross refers to the associated map showing the geographical location of projects. cross refers to the associated map showing the geographical location of projects.
Project TEXT Grey | Grey text denotes Project is on hold | Dark Grey | Dark Grey denotes project is complete | Light Blue | Light blue shading denotes minor change since previous update. | Dark Blue | Dark blue shading denotes significant change since last update, e.g. revised delivery date.
TO identifies the relevant Transmission Owner i.e. Scottish Hydro Electric Transmission plc (SHE Transmission) Scottish Power Transmission (SPT) and National Grid Electricity Transmission (NGET).
Project/Component/Driver(s) describes the project.
Area/Transmission Boundary provides the geographical area and boundary zone(s) showing where projects are and the boundaries they will affect where relevant.
Project with Mutiple TO's: highlights duplicate projects due to the involvement of multiple TO's
Increase in Transfer Capacity or Generation Accommodated shows how much the network capacity is expected to grow allowing greater transfer of electricity across the boundaries and/or allowing new generation to connect.
Current Project Stage: 1.Scoping – Identification of broad need case and consideration of number of design and reinforcement options to solve boundary constraint issues; 2.Optioneering – TO believes that the need case is firm; design of a number of design options provided for public consultation so that a preferred design solution can be identified; 3.Design – Designing the preferred solution into greater levels of detail and preparing for the planning process; 4.Planning – Continuing with public consultation and adjusting the design as required all the way through the planning application process; 5.Construction – Planning consent has been granted and/or contracts have been awarded and manufacturing underway.
RAG Status (Project Stage) presents an assessment by the TO of any issues affecting the particular project stage and how they impact on the expected completion of that stage. This and the other RAG Status column only apply to projects where the TO believes that the need case is firm and has not moved (although the need case might not yet have been submitted to Ofgem for assessment). So, projects at the earliest 2 stages (scoping and optioneering) do not generally have a RAG rating. Where a project does have a RAG status, below are the indicators;
| Green means that particular project stage is within 6 months of expected completion date |  |  | Amber indicates a delay of 6-12 months; |  |  | Red a delay of over 12 months.
Issues presents any substantive issues or risks identified by the TO.
Comments provides information on mitigating actions, recent or upcoming milestones, etc.
Earliest completion date refers to the date included in the ENSG 2020 Vision Update Report from Feb 2012. This indicated the earliest date a project could be completed. This is not necessarily the same as the delivery date (see below).
Delivery date is the TO's view of when the work will be completed. Implicit in some of these dates are certain assumptions about planning permission, but these entries do not prejudge those decisions. Also, these entries are not used for regulatory purposes, and might not reflect the dates in the transmission licences: for some projects, the date in this table differs from the existing date in the TO's transmission licence; for others, a date will not be determined and put into the licence until a later date. Note: The Delivery Year quarters are based on the financial year calendar. Take for example the 2017 year, Q1 2017 = April - June 2017; Q2 2017 = July - September 2017; Q3 2017 = October - December 2017; Q4 2017 = January - March 2018
RAG Status (against delivery date) is an assessment by the TO of meeting that delivery date: The indicators are described below. Where the TO does not yet have a set view of the delivery date, this entry is blank.
| Green indicates within 6 months of required delivery date; |  |  | Amber indicates a delay of 6-12 months; |  |  | Red a delay of over 12 months.
Weblink provides web references for further project information from the TO.

## TO Major Project Update
TRANSMISSION OWNER MAJOR PROJECT STATUS UPDATE - DECEMBER 2021
Ref No | TO | Project / Component/Driver(s) | Area / Transmission Boundary, where appropriate | Project with Multiple TO's | Increase in Transfer Capacity or generation accommodated (MW) | SEP 2021 Update | DEC 2021 Update | SEP 2021 Update | DEC 2021 Update | SEP 2021 Update | DEC 2021 Update | SEP 2021 Update | DEC 2021 Update | Earliest completion date (as per 2012 ENSG) | SEP 2021 Update | DEC 2021 Update | SEP 2021 Update | DEC 2021 Update | Weblink (where available)
[6 empty] | Current Project Stage (previous status where different): 1. Scoping 2. Optioneering 3. Design 4. Planning 5. Construction | Current Project Stage (previous status where different): 1. Scoping 2. Optioneering 3. Design 4. Planning 5. Construction | RAG Status (Project Stage) - TO view | RAG Status (Project Stage) - TO view | Issues (including reasons for slippage, etc.) | Issues (including reasons for slippage, etc.) | Comments (Mitigating actions, etc.) | Comments (Mitigating actions, etc.) |  | Delivery Date - TO view | Delivery Date - TO view | RAG Status (Against Delivery Date) - TO view | RAG Status (Against Delivery Date) - TO view
1HP | SHE Transmission | Beauly-Denny 400kV line to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from North to South of Scotland | Northern Scotland (B1) | Yes | 850 | Complete |  | Complete |  | Complete |  | Complete |  | Complete | Complete |  | Complete |  | http://www.sse.com/BeaulyDenny/
3H | SHE Transmission | Knocknagael 275/132kV Substation | Northern Scotland (B1) | No | 50 | Complete |  | Complete |  | Complete |  | Complete |  | Complete | Complete |  | Complete
3NHP | SHE Transmission | Eastern HVDC Link to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and improve security of supply | NE Scotland (B4) to NE England (B6, B7, B7a) | Yes | 2200 (B4) 2200 (B6) 1000(B7) 700 (B7a) | 2. Optioneering | 2. Optioneering |  |  | Project is currently on programme. TOs and ESO are continuing to work collaboratively to develop the Final Needs Case for each project, which is due for submission in December 2021. Consenting submissions and market tender engagement will commence in Q1/Q2 2022. | Project is currently on programme. TOs and ESO are continuing to work collaboratively to develop the Final Needs Case for each project, which is due for submission this month. Consenting submissions and market tender engagement are to commence in Q1 and Q2 2022 respectively. | Final Needs Case CBA is progressing along with continued engagement with key stakeholders. Onshore and offshore environmental surveys are ongoing with consenting due to submitted in Q1/Q2 2022. Commercial Strategies agreed by the TOs and Works Information preparation underway. | Final Needs Case CBA complete and being fed into Final Needs Case for submission in Dec 21. Onshore and offshore environmental surveys are close to completion and consenting submissions will occur in Q1 and Q2 2022 respectively. Continuation of tendering documentation and ready for submission in Q2 2022. | 2018 | The EISD for Torness - Hawthorn Pit is 2027; EISD for Peterhead to Drax is 2029 as per NOA 20/21. | The EISD for Torness - Hawthorn Pit is 2027; EISD for Peterhead to Drax is 2029 as per NOA 20/21. |  |  | http://www.sse.com/EasternHVDClink/
4H | SHE Transmission | Beauly - Blackhillock - Kintore 275kV Reconductoring to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from North to South of Scotland | Northern Scotland (B1) | No | 300 | Complete |  | Complete |  | Complete |  | Complete |  | 2014 Q4 | Complete |  | Complete Q2 2016 |  | https://www.ssepd.co.uk/BeaulyBlackhillockKintore/
7H | SHE Transmission | Beauly - Dounreay - 2nd 275kV circuit | Northern Scotland (B0) | No | 100 | Complete |  | Complete |  | Complete |  | Complete |  | 2012 Q4 | Complete |  | Complete |  | http://www.sse.com/dounreaybeauly/
9H | SHE Transmission | Shetland HVDC Link to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and Onshore wind and marine for Scottish Islands | Island Link | No | 600 | 5. Construction | 5. Construction |  |  | All key project activities remain on schedule with no major issues to report. COVID remains a threat, but extensive testing and protocols in place have prevented any significant impact on the project to date. Minor issues with construction material supply chain continue but mitigation plans in place and effective with no impact to date. At Kergord, steel erection on the HVDC building continues with the Reactor Hall and Service Building substantially complete and cladding completed on Reactor Hall roof. At Noss Head, Switching Station steelwork erection is substantially complete and roof cladding commenced. All 3 Horizontal Directional Drills (HDD) at Noss Head have been completed. HVDC Land Cable duct installation 97% complete in Caithness and 47% complete in Shetland. NKT Land and subsea cable manufacturing continues to programme. | All key project activities remain on schedule with no major issues to report. COVID remains a threat, but extensive testing and protocols in place have prevented any significant impact on the project to date, although infections and isolations within the workforce have increased in Dec 2021 with the onset of the Omicron variant. At Kergord all structural steel erection is complete and cladding is circa 85% complete. At Noss Head, Switching Station steelwork erection is complete and cladding circa 80% complete. Building Services M&E fit-out commenced at both sites. HVDC Land Cable duct installation is complete in Caithness with joint bay construction commenced and HVDC duct installation is c88% complete in Shetland. All Cable system Type tests complete and subsea cable manufacturing continues to programme. All HVDC Land Cable manufactured and shipped to site in Dec 21. Offshore Boulder clearance commenced in late Nov and scheduled to complete in Jan 22. HVDC Transformer and Valve manufacturing progressing to schedule. ModApp received changing VEWF Connection date to 1st July 2024. | Project is on programme. Stringent COVID Risk assessments and processes in place for the project with specific testing procedures in place for all work on Shetland, in alignment with Scottish Government requirements and recommendations. Issues with construction materials shortage and price inflation flagged by supply chain, immediate impact mitigated and mitigation plans being put in place to prevent future impact. Stakeholder engagement continues with active engagement with local communities and Viking Energy Wind Farm. | Project is on programme. Stringent COVID Risk assessments and processes in place for the project with specific testing procedures in place for all work on Shetland, in alignment with Scottish Government requirements and recommendations. Issues with construction materials shortage and price inflation flagged by supply chain, immediate impact mitigated and mitigation plans being put in place to prevent future impact. Stakeholder engagement continues with active engagement with local communities and Viking Energy Wind Farm. | 2017 Q4 | 2024 Q2 (tbc) | 2024 Q2 (tbc) |  |  | http://www.sse.com/Shetland/
11HP | SHE Transmission | East Coast 400kV Upgrade to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from North to South of Scotland | Northern Scotland (B2/B4) | Yes | ECU2 (610MVA) ECUP (480MVA) | 3. Design | 5. Construction |  |  | The East Coast 275kV and 400kV upgrades are progressing through the development and refinement stages. Kintore, Alyth, Peterhead and Tealing substation works and overhead line works are progressing in line with programme. | The East Coast 275kV and 400kV upgrades are progressing as per the programme, with no slippage on the programme currently. | Works continue to progress to deliver the required outputs for 2023 and 2026 respectively. Works to deliver the 2023 scope (ECU2) are progressing, Alyth has commenced works on site as have the OHL reprofiling, tenders are ongoing for Tealing PSTs. Works to deliver the ECUP scope are also progressing with tenders undertaken for the OHL and Kintore 400kV Substation works, with detailed design ongoing. Development works for Fetteresso and the Blackhillock PSTs are ongoing to inform tenders and detailed design requirements. | Works continue to progress to deliver the required outputs for 2023 and 2026 respectively. Works to deliver the 2023 scope (ECU2) are progressing, Alyth continues works on site as does the OHL reprofiling, tenders are being completed for Tealing PSTs. Works to deliver the ECUP scope are also progressing with tenders undertaken for the OHL, with detailed design ongoing. Kintore 400kV Substation development is on site and prgoressing. Development works for Fetteresso and the Blackhillock PSTs are ongoing to inform tenders and detailed design requirements. | 2017 Q1 | ECU2 - 2023 ECUP - 2026 | ECU2 - 2023 ECUP - 2026 |  |  | http://www.sse.com/ECR400kV/
12H | SHE Transmission | Beauly - Mossford 132kV Line & Switch Substation to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from North to South of Scotland | Northern Scotland (Radial circuit) | No | 300 | Complete |  | Complete |  | Complete |  | Complete |  | 2014 Q4 | Complete |  | Complete Q2 2016 |  | http://www.sse.com/beaulymossford/
13HP | SHE Transmission | Hunterston ‐ Kintyre 240MVA AC subsea link to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from North to South of Scotland | Northern Scotland (B3) to Central Scotland (B3) | Yes | Up to 350MW additional generation | Complete |  | Complete |  | Complete |  | Complete |  | 2015 Q4 | Complete |  | Completed in Q2 2016 |  | http://www.sse.com/KintyreHunterston/
14H | SHE Transmission | Western Isles HVDC Link to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and Onshore wind and marine for Scottish Islands | Island Link | No | 600 | 3. Design | 3. Design |  |  | SSEN Transmission is committed and ready to progress the 600MW HVDC transmission link, providing a timetable for doing so should the conditionality be met through the Contracts for Difference (CfD) Auction Round 4 (AR4). Pre-construction activities continue in order to protect the planned energisation date of Q1 2027. SSEN Transmission’s view remains that the 600MW transmission link remains the most economic, efficient, and practical solution. | SSEN Transmission is committed and ready to progress the 600MW HVDC transmission link, providing a timetable for doing so should the conditionality be met through the Contracts for Difference (CfD) Auction Round 4 (AR4). Pre-construction activities continue in order to protect the planned energisation date of Q1 2027. SSEN Transmission’s view remains that the 600MW transmission link remains the most economic, efficient, and practical solution. | Continued focus on delivering Pre-Construction activities. External Legal review concludes that existing Preferred Tenderer remains valid and refresh of tender complete. Lease Agreement for site at Arnish exercised. Reassessment of Beauly Convertor Station location ongoing. | Continued focus on delivering Pre-Construction activities. Preliminary site assessment exercise for Mainland Convertor Station complete and Detailed Assessment ongoing. Planning in Principle activities for Arnish ongoing. | 2015 Q4 | Q1 2027 | Q1 2027 |  |  | http://www.sse.com/WesternIsles/
17H | SHE Transmission | Orkney 220kV Subsea Link to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from North to South of Scotland | Island Link | No | 220 | 3. Design | 3. Design |  |  | Continued monthly engagement with developers on Orkney to monitor progress towards the conditionality threshold for December 2022. | Continued monthly engagement with developers on Orkney to monitor progress towards the conditionality threshold for December 2022. | Indicative programme based on 12 month extension of Ofgem conditionality means project completion in Q2 2027. Programme is currently being assessed for deliverability. | Indicative programme based on 12 month extension of Ofgem conditionality means project completion in Q2 2027. Programme is currently being assessed for deliverability. | 2015 Q4 | Q2 2027 | Q2 2027 |  |  | http://www.sse.com/OrkneyCaithness/
21H | SHE Transmission | Caithness-Moray HVDC Reinforcement to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from North to South of Scotland | Northern Scotland (BO,B1) | No | 800 (BO), 850 (B1) | Complete |  | Complete |  | The HVDC link was successfully commissioned, energised and handed over to the System Operator in line with baseline plan during December 2018. |  | There is currently no change to the delivery date. |  | 2016 Q4 | Complete |  | Complete 2018 Q3 |  | http://www.ssepd.co.uk/CaithnessMoray/
1HP | SPT | Beauly-Denny 400kV line to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from North to South of Scotland | Northern Scotland (B1) to Central Scotland (B4) | Yes | 1200 (B4) | [8 empty] | 2014 Q4 |  |  |  |  | http://www.spenergynetworks.co.uk/pages/beauly_denny_overhead_line_upgrade.asp
2NP | SPT | Incremental Reinforcement: (a) Series Compensation (b)) East-West 400kV Upgrade To accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from Scotland-England | Central Scotland (B6) to Northern England (B6) | No | 1100 (B6) | [8 empty] | (a) 2015 (b) 2016 Q4 |  |  |  |  | N/A
1NP | SPT | Western HVDC link to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and improve security of supply | Central Scotland (B6) to NW England (B6, B7, B7a) | Yes | 2200 (B6) | [8 empty] | 2015 |  |  |  |  | http://www.spenergynetworks.co.uk/pages/western_hvdc_link.asp
11HP | SPT | (i) East Coast 400kV Upgrade to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from Scotland-England | Northern to Central Scotland (B4) | Yes | TBC | [8 empty] | 2017 Q1 |  |  |  |  | N/A
| SPT | (ii) Central 400kV Upgrade (Denny – Wishaw ) to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from Scotland-England | Northern to Central Scotland (B4), Central Scotland (B5) and Central Scotland to Northern England (B6) | No | 1700 (B5) | [8 empty] | 2017 |  |  |  |  | N/A
3NHP | SPT | Eastern HVDC Link to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and improve security of supply | NE Scotland (B4) to NE England (B6, B7, B7a) | Yes | 2200 (B4) 2200 (B6) 1000(B7) 700 (B7a) | 2. Optioneering | 2. Optioneering | See 'RAG Status Notes' | See 'RAG Status Notes' | We have been looking at a range of options as part of the Strategic Wider Works process to provide the capacity onshore and offshore. NOA 18/19 recommended two links: one for delivery in 2027 and one in 2029. | We have been looking at a range of options as part of the Strategic Wider Works process to provide the capacity onshore and offshore. NOA 18/19 recommended two links: one for delivery in 2027 and one in 2029. |  |  | 2018 |  |  |  |  | N/A
13HP | SPT | Hunterston ‐ Kintyre 240MVA AC subsea link to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from North to South of Scotland | Northern Scotland (B3) to Central Scotland (B3) | Yes | Up to 350MW additional generation | [8 empty] | 2015 Q4 |  |  |  |  | http://www.spenergynetworks.co.uk/pages/kintyre_hunterston_link.asp
1P | SPT | South West Scotland Collector Network to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and transfer power from Scotland-England | Southern Scotland | No | Up to 800MW of additional generation by 2018 | [8 empty] | n/a |  |  |  |  | http://www.spenergynetworks.co.uk/pages/south_west_scotland_connections_project.asp
1NP | NGET | Western HVDC link - HVDC cable and converters to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and improve security of supply | Central Scotland (B6) to NW England (B6, B7, B7a) | Yes | 2200 | [8 empty] | 2015 |  |  |  | Completed November 2019 | http://westernhvdclink.co.uk/
2NP | NGET | Scotland-England Reinforcement (Series and shunt compensation) to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and improve security of supply | Central Scotland (B6) to Northern England (B6) | No | 1000 | [8 empty] | 2015 |  |  |  | Completed in 2015 Q1 | N/A
3NHP | NGET | Eastern HVDC Link to accommodate increase in Generation (predominantly Onshore & Offshore Wind) in Scotland and improve security of supply | NE Scotland (B4) to NE England (B6, B7, B7a) | Yes | 2200 (B4) 2200 (B6) 1000(B7) 700 (B7a) |  | 4. Planning |  |  | We continue to progress key onshore and offshore design and consenting work to work to the targeted programme dates as outlined in the NOA6 recommendations. Non-statutory consultation has finished for NGET onshore works with the next key phase the statutory consultation. The FNC is currently expected to be submitted to Ofgem before the end of this year. | We continue to progress key onshore and offshore design and consenting work to work to the targeted programme dates as outlined in the NOA6 recommendations. The FNC has been drafted and is under review, forecasted submission is December 2021. | None identified at this stage. |  | 2018 | The EISD for Torness - Hawthorn Pit is 2027; EISD for Peterhead to Drax is 2029. |  |  |  | https://www.nationalgrid.com/uk/electricity-transmission/network-and-infrastructure/segl1 https://www.nationalgrid.com/uk/electricity-transmission/network-and-infrastructure/segl2
4N | NGET | Western HDVC Link: - Deeside / Connah's Quay substation Works only | Northern Wales and NW England | No | N/A | [8 empty] | 2015 |  |  |  | Completed in 2014 Q3 | N/A
5N | NGET | Scotland-England Reinforcement (Harker-Hutton reconductoring) | Northern England (B7) | No | 1400 | [8 empty] | 2014 |  |  |  | Completed in 2013 Q4 | N/A
6N | NGET | North Wales (New 400 kV, Pentir – Wylfa Transmission circuit) to accommodate connection of large amount of offshore wind and nuclear generation in the North Wales and renewables connection from Ireland | North Wales (NW1) | No | 3800 | [8 empty] | 2018 |  |  |  |  | http://www.northwalesconnection.com/
7N | NGET | North Wales (Second Pentir – Trawsfynydd 400 kV Transmission circuit) to accommodate connection of large amount of offshore wind and nuclear generation in the North Wales | North Wales (NW2) | No | 2220 | [8 empty] | 2016 |  |  |  |  | http://www.northwalesconnection.com/
8N | NGET | North Wales (Deeside – Trawsfynydd series compensation) to accommodate offshore wind and nuclear generation in North Wales | North Wales | No | TBC | [8 empty] | 2015 |  |  |  |  | N/A
9N | NGET | North Wales (Reconductor Trawsfynydd – Treuddyn) | North Wales (NW3) | No | 2800 | [8 empty] | 2014 |  |  |  | Completed in 2014 Q4 | N/A
10N | NGET | Wylfa-Pembroke HVDC Link to accommodate connection of large amount of offshore wind and nuclear generation in the North Wales | North Wales (NW1, NW2, NW3, NW4) | No | 2000-2500 | [8 empty] | 2017 |  |  |  |  | N/A
11N | NGET | Central Wales (Mid Wales 400kV substation and Transmission circuit) to accommodate connection of new onshore wind in Mid Wales | Central Wales | No | 1800 (Infeed Loss Risk Criterion) | [8 empty] | 2016 |  |  |  |  | http://www.midwalesconnection.com/
12N | NGET | Humber - Killingholme South New Substation (KISO); and new transmission circuit from KISO to West Burton to accommodate connection of new Round 3 offshore windfarms and new CCGT generation within Humber area | NE England (EC1) | No | 3900 | [8 empty] | 2018 |  |  |  |  | N/A
13N | NGET | East Anglia (i) Reconductoring Bramford-Norwich + | East Anglia (EC5) | No | 400 | [8 empty] | 2015 |  |  |  |  | N/A
13N | NGET | East Anglia (ii) Bramford Substation Reconfiguration to accommodate connection of new offshore windfarms (Round 2, 2.5 and 3) and new CCGT generation in East Anglia |  | No | N/A | 5. Construction | 5. Construction |  |  | While there have been delays in delivery, the network remains compliant and we are able to connect customers at the dates requested. | While there have been delays in delivery, the network remains compliant and we are able to connect customers at the dates requested. | While there have been delays in delivery, the network remains compliant and we are able to connect customers at the dates requested. Progress of works is supported by cost-benefit analysis. | While there have been delays in delivery, the network remains compliant and we are able to connect customers at the dates requested. Progress of works is supported by cost-benefit analysis. | 2015 | 2022 | 2022 |  |  | N/A
14N | NGET | East Anglia (New Bramford – Twinstead 400kV Transmission circuit) to accommodate connection of new offshore windfarms (Round 2, 2.5 and 3), nuclear and new CCGT generation in East Anglia | East Anglia (EC5) | No | 2600 | 4. Planning | 4. Planning |  |  | The project has progressed and a round of non-statutory consultation has been completed. | The project is preparing for statutory consultation in 2022. | None identified at this stage. | None identified at this stage. | 2018 | The EISD for the project in NOA is 2028/29. | The EISD for the project in NOA is 2028/29. |  |  | https://www.nationalgrid.com/uk/electricity-transmission/network-and-infrastructure/bramford-twinstead
15N | NGET | London (Uprate Hackney – Tottenham – Waltham Cross circuit to 400kV+ Pelham Rye House Reconductoring) to accommodate connection of new offshore windfarms (Round 2, 2.5 and 3) and new CCGT generation in in East Anglia and high demand in London as well as possible coincidental interconnector exports | London (B14) | No | 800 | [8 empty] | 2015 |  |  |  |  | http://www.northlondonreinforcement.com/
16N | NGET | South West (Hinckley Point – Seabank and assoc. infra. Works) to accommodate connection of new nuclear in South West | SW England (B13) | No | 0 | 5. Construction | 5. Construction | [6 empty] | 2019 | Aligned as required to Hinkley C delivery programme | Aligned as required to Hinkley C delivery programme |  |  | http://www.hinkleyconnection.co.uk/
17N | NGET | North West Coast Connection - (Harker to Middleton and assoc. infra. works) to accommodate connection of new nuclear in Cumbria | Northern England (B7) | No | 3387 | [8 empty] | None |  |  |  |  | http://www.northwestcoastconnections.com/