## Introduction
Public Land for Housing Programme 2015-20 Concluding Summary Report 2022
Data on progress of sites sold through the Public Land for Housing Programmes, England

In April 2017 MHCLG (now DLUHC) began to monitor the progress of sites sold through both the 2011-15 and 2015-20 Public Land for Housing Programmes, in order to estimate the number of homes under construction and completed. An experimental methodology has been developed by Ordnance Survey to monitor sites through the planning system to completion. This is explained more in detail in the narrative to this annex. / The figures reported are based on activity on 96% of sites sold for housing (1,410 sites with capacity for 149,662 homes) up to end March 2020. Further investigation is being undertaken on the remaining 4% of sites where data is incomplete or unclear to ensure figures are robust. Therefore, the figures do not reflect performance across the Programmes as a whole and report the likely minimum that has been delivered.

A total of 1,473 sites are listed across this spreadsheet (in annexes C, D and E) because the method deployed by Ordnance Survey required some sites to be separated out for monitoring purposes.

Geographic extent: England only
Date of publication: September 2022
Contact for enquires: PublicSectorLand@levellingup.gov.uk

Explanation of columns
Unique ref	Unique site reference
Sold by dept.	The Department that disposed of the land / property
Site name	A descriptor of the site
Site address	Site address
Site postcode	A standard UK postcode for the site
Local Authority	The local authority areas the site lies within
Region	The region the site lies within
Disposal year	The year the site was disposed of
Forecast housing capacity	The number of housing units that were originally forecast to be possible to build on the site
Planning status	Shows progress of sites through the planning system to completion. The categorise are as follows: / 'Development completed' - site completed / 'Development started' - construction on site started but not completed / 'Planning stage' - / 1) sites with a planning permission but not yet started / 2) sites with a planning application submitted but no decision / 3) sites that have a recent positive support/commitment for residential development by a local planning authority in advance of a planning application / 4) sites that are allocated in a local plan or other development plan document. / 'No current planning activity' - sites that were released that have no current planning activity
Planning ref	A planning reference number for the site that can be used to identify the associated planning application within the relevant local authority planning system
Date planning permission secured	The date the planning application was decided (as per the decision notice)
Nature of plan for site	Sites were grouped into four categories – residential, residential institute, commercial, mixed. These are defined as – / - residential – all buildings proposed on site are planning category C3 (as declared in the planning application) / - residential institute – all buildings proposed on site are planning category C2 (as declared in the planning application) / - commercial – all buildings proposed on site are non-residential (as defined above) / - mixed – the buildings proposed on site are a combination of at least two of the categories defined above. / - residential sales/ built residential development -previously held public sector accommodation being sold off directly as private housing or where new residential development for military personnel is already built.
Part of a larger application	If the application is only for the disposed site this field is populated with ‘N’. Where the disposed site forms part of a larger application, this field is populated with a ‘Y’. Where it is unclear e.g. if the extent of the disposed site is unknown this field is populated with ‘information not in planning application’ or ‘unknown’
Housing capacity in planning application	Housing capacity number taken from the planning application / Note on sites where the former government land makes up part of a wider planning application site, the housing capacity in the planning application refers to the wider site.
Date started on site	The date at which the first building on site was added to the OS MasterMap Topography Layer
Number of homes started not completed	Number of homes started but not completed before 01/04/2019
Number of homes completed to date	The total number of dwellings within the site boundary that have been completed as per methodology between the date of planning approval for the site and the end of the reporting period
All affordable housing on government land	If all the affordable housing is on government land this field is populated with 'Yes'. Where the affordable housing may also be on non-government land part of the application this field is marked 'No'. Where it is unclear this field is populated 'unknown' or 'Not applicable'.
Affordable homes expected	Used to determine if affordable housing is expected on sites based on a search through planning documents to determine whether the developer addressed affordable housing in their proposal and whether it formed part of the legal agreement between the local authority and developer via a Section 106. If affordable housing was included in the planning agreement further investigation was carried out to determine the type of affordable housing being provided.
Number of affordable rent	A count of the number of planned affordable homes that are classified, on planning documents, as affordable rent
Number of social rent	A count of the number of planned affordable homes that are classified, on planning documents, as social rent
Number of intermediate rent	A count of the number of planned affordable homes that are classified, on planning documents, intermediate rent
Number of affordable home ownership	A count of the number of planned affordable homes that are classified, on planning documents, as affordable home ownership
Number of affordable unknown	A count of the number of planned affordable homes that are classified, on planning documents, as affordable unknown
Tenure No. of freehold	A count of the number of dwellings on the site, using Land Registry data, that have freehold tenure
Tenure No. of leasehold	A count of the number of dwellings on the site, using Land Registry data, that have leasehold tenure
Tenure No. of unknown	A count of the number of dwelling on the site for which tenure cannot (currently) be ascertained from Land Registry data
Type No. of detached	A count of the number of total completions that are classified, within AddressBase Premium, as detached residential dwellings
Type No. of semi-detached	A count of the number of total completions that are classified, within AddressBase Premium, as semi-detached residential dwellings
Type No. of terrace	A count of the number of total completions that are classified, within AddressBase Premium, as terraced residential dwellings
Type No. of flats	A count of the number of total completions that are classified, within AddressBase Premium, as residential flats or maisonettes
Type No. of unknown	A count of the number of total completions that cannot be fully classified using AddressBase Premium, or which fall into other categories (such as residential institutions)

x	No data available
unknown	Relevant information not found
n/a	Does not apply to this data field
*	These sites are being developed for employment use only and therefore the housing capacity is recorded as zero
†	Site has been separated out to support accurate monitoring. The forecast housing capacity given is for the original unseparated site.
SFA	New Service Family Accommodation (SFA), which is new housing built on Ministry of Defence land for service personnel and their families
SLA	New Single Living Accommodation (SLA) which is new housing built on Ministry of Defence land for single service personnel comprising accommodation with communal living space and shared facilities
Anningtons	A home previously leased to the Ministry of Defence by Anningtons and sold back to the market
Double underlined PSLR number	These sites have data issues which are acceptable to include as part of the dataset as they do not impact the validity of overall buildout numbers

## Annex_C
Public Land for Housing Programme 2015-20 Concluding Summary Report 2022
Annex C : Data on progress of 96% of sites sold through the 2011-15 and 2015-20 Public Land for Housing Programmes up to the end of March 2020.

Unique ref	Disposed in	Sold by	Site name	Site address	Site postcode	Local authority	Region	Disposal year	Forecast housing capacity	Planning Status	Planning reference	Date planning application submitted	Date planning permission secured	Nature of plan for site	Part of larger application	Housing capacity in planning application	Date started on site	Number of homes started not completed	Number of homes completed to date	All affordable homes on government land	Affordable Homes Expected	Number of affordable rent	Number of social rent	Number of intermediate rent	Number of affordable home ownership	Number of affordable unknown	Tenure no. of freehold	Tenure no. of leasehold	Tenure no. of unknown	Type no. of detached	Type no. of semi-detached	Type no. of terrace	Type no. of flats	Type no. of unknown
PSLR0001	PLHP 1	MoD	ACIO Barnstable 2 Litchdon Street	Barnstaple	EX32 8ND	North Devon	South West	2013/2014	1	Planning stage	x	x	x	Permitted development	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0002	PLHP 1	MoD	ACIO Torquay 180 Union Street	Torquay	TQ2 5QP	Torbay	South West	2013/2014	1	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0003	PLHP 1	MoD	ACIO Wembley	High Road London	HA0 2AF	Brent	London	2013/2014	1	Development completed	13/2916	09/10/2013	04/12/2013	Residential	No	2	09/03/2016	0	2	Yes	No	0	0	0	0	0	0	0	2	0	0	0	2	0
PSLR0004	PLHP 1	MoD	AHL surrender/freehold sales	Various	Various	x	x	2011/2012	143	Development completed	x	x	x	Residential sale	No	143	x	x	143	Not applicable	Unknown	0	0	0	0	0	x	x	143	x	x	x	x	143
PSLR0005	PLHP 1	MoD	Aldershot Urban Extension Sites	Various, Aldershot, Hampshire	Various	Rushmoor	South East	2012/2013	3850	Development started	12/00958/OUT	19/12/2012	10/03/2014	Mixed	Yes	3850	16/11/2015	115	794	No	Yes	808	0	539	0	0	496	91	207	134	211	166	283	0
PSLR0006	PLHP 1	MoD	Annington/SFA2	Various	Various	x	x	2013/2014	68	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0007	PLHP 1	MoD	Anningtons/Service Family Accom 1	Various	Various	x	x	2012/2013	122	Development completed	x	x	x	Residential sale	No	122	x	x	122	Not applicable	Unknown	0	0	0	0	0	x	x	122	x	x	x	x	122
PSLR0008	PLHP 1	MoD	Anningtons/SFA 2	Various	Various	x	x	2013/2014	256	Development completed	x	x	x	Residential sale	No	256	x	x	256	Not applicable	Unknown	0	0	0	0	0	x	x	256	x	x	x	x	256
PSLR0009	PLHP 1	MoD	Anningtons/SFA 3 (FY 14/15 Phase 1)	Various	Various	x	x	2014/2015	39	Development completed	x	x	x	Residential sale	No	39	x	x	39	Not applicable	Unknown	0	0	0	0	0	x	x	39	x	x	x	x	39
PSLR0010	PLHP 1	MoD	Anningtons/SFA 3 (FY 14/15 Phase 2)	Various	Various	x	x	2014/2015	64	Development completed	x	x	x	Residential sale	No	64	x	x	64	Not applicable	Unknown	0	0	0	0	0	x	x	64	x	x	x	x	64
PSLR0011	PLHP 1	MoD	Anningtons/SFA 3 (FY 14/15 Phase 3)	Various	Various	x	x	2014/2015	116	Development completed	x	x	x	Residential sale	No	116	x	x	116	Not applicable	Unknown	0	0	0	0	0	x	x	116	x	x	x	x	116
PSLR0012	PLHP 1	MoD	Army Cadet Force Feltham,	Elmwood Avenue, Feltham, Middx	TW137AD	Hounslow	London	Before 2011	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0013	PLHP 1	MoD	Army Cadet Force Waltham Cross	34 Station Road, Waltham Cross, Hertfordshire	EN9 1AA	Broxbourne	East	Before 2011	1	Development completed	7/1037/04/F/WX	22/11/2004	10/12/2004	Residential	No	1	21/02/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	0	0	0	0	1
PSLR0014	PLHP 1	MoD	Army Medals Office, Droitwich Government Buildings,	Medallion Park, Worcester Road, Droitwich Spa, Worcestershire,	WR9 8AU	Wychavon	West Midlands	Before 2011	57	Development completed	W/11/02289/RM	17/10/2011	20/07/2012	Residential	No	64	08/08/2012	0	64	Yes	Yes	0	13	6	0	0	60	4	0	30	6	28	0	0
PSLR0015	PLHP 1	MoD	Barrack Road, Weymouth -Sea Cadets Training Centre,	Barrack Road, Weymouth, Dorset	DT4 8TZ	Weymouth and Portland	South West	Before 2011	32	Development started	09/00162/FULE	20/03/2009	19/06/2009	Mixed	No	32	16/06/2010	0	26	Yes	No	0	0	0	0	0	17	9	0	0	0	17	9	0
PSLR0016a	PLHP 1	MoD	Barracks, 5 sites: Balance of units	Colchester, Essex	CO2 7QG	Colchester	East	Before 2011	400	Development completed	91619120895	15/12/2009	29/04/2010	Residential,Infill	No,No	266	04/08/2011	0	265	Yes,Yes	Unknown,No	0	0	0	0	0	239	26	0	56	68	111	30	0
PSLR0016b	PLHP 1	MoD	Barracks, 5 sites: Balance of units	Colchester, Essex	CO2 7QG	Colchester	East	Before 2011	400†	Planning stage	100982	18/05/2010	22/09/2010	Mixed	No	14	x	0	0	Yes	Yes	0	0	0	0	14	0	0	0	0	0	0	0	0
PSLR0016c	PLHP 1	MoD	Barracks, 5 sites: Balance of units	Colchester, Essex	CO2 7QG	Colchester	East	Before 2011	400†	Development completed	111241	01/07/2011	22/09/2011	Infill	Yes	2	11/11/2013	0	19	Yes	No	0	0	0	0	0	3	16	0	0	0	2	17	0
PSLR0016d	PLHP 1	MoD	Barracks, 5 sites: Balance of units	Colchester, Essex	CO2 7QG	Colchester	East	Before 2011	400†	Development completed	121426	01/08/2012	06/06/2013	Residential	No	5	10/07/2014	0	5	Yes	No	0	0	0	0	0	5	0	0	0	0	5	0	0
PSLR0017a	PLHP 1	MoD	Barracks, 5 sites: SITE A, Hyderabad and Meanee Barracks.	Colchester, Essex	CO2 7GS	Colchester	East	Before 2011	400	Development completed	120098	13/01/2012	06/08/2012	Residential	Yes	37	21/07/2014	0	37	Unknown	Unknown	0	0	0	0	0	1	36	0	0	0	0	37	0
PSLR0017b	PLHP 1	MoD	Barracks, 5 sites: SITE A, Hyderabad and Meanee Barracks.	Colchester, Essex	CO2 7GS	Colchester	East	Before 2011	400†	Development completed	151087	27/05/2015	22/07/2015	Residential	Yes	6	11/05/2019	0	6	Unknown	Unknown	0	0	0	0	0	0	6	0	0	0	0	6	0
PSLR0017c	PLHP 1	MoD	Barracks, 5 sites: SITE A, Hyderabad and Meanee Barracks.	Colchester, Essex	CO2 7GS	Colchester	East	Before 2011	400†	Development completed	122229	17/12/2012	12/06/2013	Residential	Yes	7	28/03/2014	0	7	Unknown	Unknown	0	0	0	0	0	7	0	0	0	4	3	0	0
PSLR0017d	PLHP 1	MoD	Barracks, 5 sites: SITE A, Hyderabad and Meanee Barracks.	Colchester, Essex	CO2 7GS	Colchester	East	Before 2011	400†	Development completed	101059	27/05/2010	27/08/2010	Residential	No	438	14/06/2012	0	436	Yes	Unknown	0	0	0	0	0	413	11	12	51	47	302	36	0
PSLR0018	PLHP 1	MoD	Barracks, 5 sites: SITE B, Flagstaff House and land adjoining: northern section	Colchester, Essex	CO2 7GA	Colchester	East	Before 2011	67	Development started	131935	01/10/2013	05/03/2015	Residential	No	138	08/11/2016	0	105	Not applicable	Unknown	0	0	0	0	0	10	74	21	5	2	13	85	0
PSLR0020	PLHP 1	MoD	Barracks, 5 sites: SITE D, Central section west of Berechurch Road and south of Abbey Field.	Colchester, Essex	CO2 7SZ	Colchester	East	Before 2011	9	Development completed	RM/COL/04/1951	20/10/2004	07/01/2005	Residential	No	284	22/11/2005	0	284	Not applicable	Unknown	0	0	0	0	0	154	130	0	9	41	86	148	0
PSLR0021	PLHP 1	MoD	Barton Stacey (2 units)	Barton Stacey	SO213SA	Test Valley	South East	2013/2014	2	Development completed	15/02014/FULLN	18/08/2015	13/01/2016	Residential	No	2	01/09/2017	0	2	Yes	No	0	0	0	0	0	2	0	0	2	0	0	0	0
PSLR0022	PLHP 1	MoD	Birchwood Estate Army Cadet Force	Fulmar Road, Birchwood, Lincolnshire	LN6 0LE	Lincoln	East Midlands	Before 2011	8	Development completed	2009/0503/F	07/08/2009	08/03/2010	Residential	Unknown	22	01/04/2011	0	16	Yes	Yes	0	0	0	0	22	16	0	0	0	10	6	0	0
PSLR0023aa	PLHP 1	MoD	Bordon Masterplanning, Bordon	Bordon Garrison, Bordon, Hampshire	GU35 9QE	East Hampshire	South East	2014/2015	2400	Development started	14/06604/FUL	16/12/2014	09/11/2015	Mixed	No	2400	05/07/2017	17	69	Yes	Unknown	0	0	0	0	0	43	10	16	13	12	0	11	33
PSLR0023ac	PLHP 1	MoD	Bordon Masterplanning, Bordon	Bordon Garrison, Bordon, Hampshire	GU35 9QE	East Hampshire	South East	2014/2015	2400†	Development started	55587/065	09/11/2017	31/01/2019	Mixed	No	170	01/10/2019	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0023ae	PLHP 1	MoD	Bordon Masterplanning, Bordon	Bordon Garrison, Bordon, Hampshire	GU35 9QE	East Hampshire	South East	2014/2015	2400†	Planning stage	55587/096	14/11/2018	05/11/2019	Residential	No	190	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0023af	PLHP 1	MoD	Bordon Masterplanning, Bordon	Bordon Garrison, Bordon, Hampshire	GU35 9QE	East Hampshire	South East	2014/2015	2400†	Planning stage	55587/102	10/01/2019	x	Mixed	No	70	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0023b	PLHP 1	MoD	Bordon Masterplanning, Bordon - Louisburg Barracks	Bordon Garrison, Bordon, Hampshire	GU35 9QE	East Hampshire	South East	2014/2015	504	Development started	55369/005	26/01/2016	29/04/2016	Residential	No	504	21/02/2012	55	374	Yes	Yes	60	0	40	0	0	276	58	40	34	129	111	36	64
PSLR0024	PLHP 1	MoD	Brize Norton SFA, Stanmore Crescent	Northwood Crescent‚ Abingdon Road, Stanmore Crescent, Carterton	OX18 3UH	West Oxfordshire	South East	2013/2014	167	Development started	17/01561/RES	18/05/2017	08/09/2017	Residential	No	135	27/11/2018	23	44	Yes	Yes	9	0	4	0	0	14	5	25	5	20	10	9	0
PSLR0025	PLHP 1	MoD	Brompton Barracks, RSME Chatham (Brompton Barracks)	Amherst Hill, Chatham, Kent	ME7 5AX	Medway	South East	2012/2013	34	Development completed	MC/12/1400	16/06/2012	14/03/2013	Residential	No	34	10/02/2014	0	34	Yes	Yes	0	0	0	0	9	25	9	0	5	14	15	0	0
PSLR0026	PLHP 1	MoD	Brompton Road Kensington	206 Brompton Road, Chealsea, Kensington and Chelsea	SW3 2BQ	Kensington and Chelsea	London	2013/2014	20	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0027	PLHP 1	MoD	Broughton Moor	Broughton Moor, Maryport	CA157SP	Allerdale	North West	Before 2011	200	Planning stage	2/2017/0219	05/05/2017	28/06/2017	Residential	No	24	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0028	PLHP 1	MoD	Building Plot/Garages - Manchester SFA	Hillside Crescent, Ashton-under-Lyne, Mancheste	OL6 9DG	Tameside	North West	Before 2011	2	Planning stage	16/00932/OUT	12/10/2016	07/12/2016	Residential	No	3	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0029	PLHP 1	MoD	Catterick Garrison Miscellaneous, Land at Arras/Colburn (Site H15 & H/16)	off Catterick Road, Catterick Garrison, North Yorkshire	DL9 4GL	Richmondshire	Yorkshire and The Humber	2014/2015	130	Development completed	15/00258/AORM	17/04/2015	08/07/2015	Residential	Unknown	126	19/09/2016	0	126	Yes	Yes	0	0	0	0	39	117	4	5	47	48	30	0	1
PSLR0030	PLHP 1	MoD	Catterick Garrison Miscellaneous, Land at Gough Road West (Site H/03)	Gough Road, Catterick Garrison, North Yorkshire	DL9 3EN	Richmondshire	Yorkshire and The Humber	2014/2015	25	Planning stage	18/00826/FULL	20/11/2018	x	Residential	No	29	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0031	PLHP 1	MoD	Catterick Garrison Miscellaneous, Land at Somerset Close (Site 5)( H/04)	Somerset Close, Catterick Garrison, North Yorkshire	DL9 3HE	Richmondshire	Yorkshire and The Humber	2014/2015	40	Planning stage	18/00827/FULL	20/11/2018	x	Residential	No	40	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0032	PLHP 1	MoD	Catterick: Veteran's Housing Site 1 - Hipswell Road West, Catterick	Catterick	DL9 3AU	Richmondshire	Yorkshire and The Humber	Before 2011	31	Development completed	09/00612/FULL	30/07/2009	29/10/2009	Residential	Yes	43	03/10/2011	0	31	Yes	Yes	12	0	0	0	0	25	0	6	0	0	0	31	0
PSLR0033	PLHP 1	MoD	Catterick:Ã‚Â Hipswell Road West	Catterick	DL9 3AU	Richmondshire	Yorkshire and The Humber	Before 2011	12	Development completed	09/00612/FULL	30/07/2009	29/10/2009	Residential	Yes	43	03/10/2011	0	12	Yes	Yes	12	0	0	0	0	12	0	0	0	0	0	0	12
PSLR0034a	PLHP 1	MoD	Chelsea Barracks	Westminster	SW1W8PQ	Westminster	London	Before 2011	400	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0034b	PLHP 1	MoD	Chelsea Barracks	Westminster	SW1W8PQ	Westminster	London	Before 2011	400†	Planning stage	18/04104/RESMAT	17/05/2018	11/01/2019	Mixed	No	126	x	0	0	Yes	Unknown	x	x	x	x	x	0	0	0	0	0	0	0	0
PSLR0034c	PLHP 1	MoD	Chelsea Barracks	Westminster	SW1W8PQ	Westminster	London	Before 2011	400†	Planning stage	17/07177/RESMAT	10/08/2017	18/04/2018	Residential	No	119	x	0	0	Yes	Unknown	x	x	x	x	x	0	0	0	0	0	0	0	0
PSLR0035	PLHP 1	MoD	Chilcombe Range, land by Manor House Farm, Barton Stacey	Barton Stacey	SO213RY	Test Valley	South East	Before 2011	6	Development completed	13/02855/FULLN	20/12/2013	24/03/2014	Residential	No	4	14/06/2016	0	4	Yes	No	0	0	0	0	0	0	0	4	4	0	0	0	0
PSLR0036	PLHP 1	MoD	Church (Preston Lane), Calne Road, Wilts (RAF Lyneham)	Lyneham, Chippenham	SN15 4ST	Wiltshire	South West	Before 2011	15	Development completed	N/11/00528/REM	09/02/2011	11/05/2011	Residential	Unknown	32	10/10/2011	0	32	Yes	Yes	0	7	2	0	0	30	2	0	4	19	7	2	0
PSLR0037	PLHP 1	MoD	Church Farringdon Road, Abingdon	Abingdon	OX13 6QJ	Vale of White Horse	South East	Before 2011	1	Development completed	P09/V0934	11/05/2009	02/07/2009	Residential	Unknown	1	06/04/2011	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0038	PLHP 1	MoD	Civilian - The White House	Old Sarum, Salisbury	SP9 7AP	Wiltshire	South West	2011/2012	8	Development completed	x	x	x	Residential sale	Not applicable	8	x	x	8	Not applicable	Unknown	0	0	0	0	0	x	x	8	x	x	x	x	8
PSLR0039a	PLHP 1	MoD	Copenacre, Hartham Surface	Bath Rd, Hawthorn, Corsham, Wiltshire	SN13 8AA	Wiltshire	South West	2011/2012	100	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0039b	PLHP 1	MoD	Copenacre, Hartham Surface	Bath Rd, Hawthorn, Corsham, Wiltshire	SN13 8AA	Wiltshire	South West	2011/2012	100†	Development completed	17/03113/REM	19/04/2017	27/07/2017	Residential	No	9	25/05/2018	0	9	Yes	Unknown	x	x	x	x	x	6	3	0	7	2	0	0	0
PSLR0039c	PLHP 1	MoD	Copenacre, Hartham Surface	Bath Rd, Hawthorn, Corsham, Wiltshire	SN13 8AA	Wiltshire	South West	2011/2012	100†	Development started	15/11889/REM	02/12/2015	30/03/2016	Residential	No	58	25/05/2018	0	58	Yes	Unknown	x	x	x	x	x	55	0	3	40	12	6	0	0
PSLR0039d	PLHP 1	MoD	Copenacre, Hartham Surface	Bath Rd, Hawthorn, Corsham, Wiltshire	SN13 8AA	Wiltshire	South West	2011/2012	100†	Development completed	15/11882/REM	02/12/2015	01/03/2016	Residential	No	29	28/03/2017	0	28	Yes	Unknown	x	x	x	x	x	28	0	0	28	0	0	0	0
PSLR0040	PLHP 1	MoD	Defence Academy Shrivenham, Depot Cowans Camp	Star Lane, Shrivenham, Oxfordshire	SN6 8TH	Vale of White Horse	South East	2012/2013	200	Development started	P13/V2359/RM	28/10/2013	05/03/2014	Mixed	No	150	29/09/2015	0	133	Yes	Yes	0	0	10	0	30	102	10	21	65	45	15	8	0
PSLR0041a	PLHP 1	MoD	Defence Logistics Org Malvern, North Site	Malvern	WR141FG	Malvern Hills	West Midlands	Before 2011	200	Development completed	07/00464/REM	04/04/2007	03/07/2007	Residential	Yes	76	21/07/2008	0	76	Yes	Yes	18	0	10	0	0	58	18	0	10	22	23	21	0
PSLR0041b	PLHP 1	MoD	Defence Logistics Org Malvern, North Site	Malvern	WR141FG	Malvern Hills	West Midlands	Before 2011	200†	Development completed	08/00135/REM,09/00431/REM	30/01/2008	22/04/2008	Residential,Infill	Yes,Yes	68	22/04/2009	0	68	Yes,Unknown	Unknown,Unknown	0	0	0	0	0	67	1	0	40	12	14	2	0
PSLR0041c	PLHP 1	MoD	Defence Logistics Org Malvern, North Site	Malvern	WR141FG	Malvern Hills	West Midlands	Before 2011	200†	Development completed	09/00794/REM	04/06/2009	17/09/2009	Residential	Yes	49	15/12/2009	0	49	Yes	Yes	0	19	14	0	0	49	0	0	9	14	17	9	0
PSLR0041d	PLHP 1	MoD	Defence Logistics Org Malvern, North Site	Malvern	WR141FG	Malvern Hills	West Midlands	Before 2011	200†	Development completed	09/00943/REM	03/07/2009	21/08/2009	Residential	Yes	50	15/12/2009	0	50	Yes	Yes	0	2	10	0	0	40	10	0	9	18	23	0	0
PSLR0041e	PLHP 1	MoD	Defence Logistics Org Malvern, North Site	Malvern	WR141FG	Malvern Hills	West Midlands	Before 2011	200†	Development completed	10/00259/REM	22/02/2010	24/05/2010	Residential	Yes	88	23/08/2011	0	88	Yes	Yes	0	15	13	0	0	67	21	0	15	34	30	9	0
PSLR0041f	PLHP 1	MoD	Defence Logistics Org Malvern, North Site	Malvern	WR141FG	Malvern Hills	West Midlands	Before 2011	200†	Development completed	10/00624/REM	17/05/2010	30/07/2010	Residential	Yes	74	23/11/2010	0	74	Yes	Yes	0	14	14	0	0	62	12	0	31	21	13	9	0
PSLR0041g	PLHP 1	MoD	Defence Logistics Org Malvern, North Site	Malvern	WR141FG	Malvern Hills	West Midlands	Before 2011	200†	Development completed	12/01488/REM	09/11/2012	18/11/2015	Residential	Yes	48	20/09/2017	0	48	Yes	Yes	0	0	36	12	0	5	36	7	0	0	0	48	0
PSLR0041h	PLHP 1	MoD	Defence Logistics Org Malvern, North Site	Malvern	WR141FG	Malvern Hills	West Midlands	Before 2011	200†	Development completed	15/00644/FUL	06/05/2015	08/12/2015	Residential	Yes	21	20/09/2017	0	21	Yes	Yes	0	19	0	0	0	17	0	4	0	0	0	21	0
PSLR0042	PLHP 1	MoD	Defence Logistics Org Malvern, North Site	Malvern	WR141FJ	Malvern Hills	West Midlands	Before 2011	61	Development completed	12/01240/FUL	06/09/2012	10/04/2013	Residential	Yes	58	12/08/2013	0	58	No	Yes	0	15	14	0	0	45	13	0	16	19	14	9	0
PSLR0043a	PLHP 1	MoD	Defence Logistics Org, Exeter, SEF	Exeter	EX2 7GA	Exeter	South West	Before 2011	200	Development completed	12/0870/RES	14/06/2012	05/11/2012	Residential	Unknown	289	30/09/2013	0	196	No	Yes	0	61	11	0	0	166	14	16	64	50	24	8	50
PSLR0043b	PLHP 1	MoD	Defence Logistics Org, Exeter, SEF	Exeter	EX2 7GA	Exeter	South West	Before 2011	200†	Development completed	12/0131/RES	27/01/2012	25/04/2012	Residential	No	112	22/04/2013	0	19	No	Yes	0	26	4	0	0	19	0	0	6	6	7	0	0
PSLR0044	PLHP 1	MoD	Defence School of Languages, Beaconsfield (Wilton Park)	Wilton Park, Beaconsfield, Buckinghamshire	HP9 2RB	South Buckinghamshire	South East	2013/2014	330	Development started	17/01763/OUT	27/09/2017	20/09/2019	Mixed	No	304	21/02/2012	0	95	Yes	Yes	12	0	67	0	0	84	0	11	24	24	38	0	9
PSLR0045	PLHP 1	MoD	Deysbrook Barracks	Liverpool	L12 4YW	Liverpool	North West	Before 2011	27	Development completed	03RM/1849	16/06/2003	29/04/2004	Residential	No	340	20/05/2004	0	342	Yes	No	0	0	0	0	0	13	329	0	188	18	59	76	1
PSLR0046	PLHP 1	MoD	E Block Ensleigh	Ensleigh South site, Granville Road/Lansdown Road, Bath, Avon	BA1 9BE	Bath & NE Somerset	South West	2012/2013	39	Development started	13/00734/FUL	20/02/2013	24/12/2013	Residential	No	39	20/07/2016	0	35	Yes	Yes	0	10	3	0	0	25	0	10	10	4	12	9	0
PSLR0047	PLHP 1	MoD	Eastbourne Air Training Corps	Eastbourne	BN212TR	Eastbourne	South East	Before 2011	6	Development completed	80505	06/08/2008	30/09/2008	Residential	No	5	24/06/2009	0	5	Yes	No	0	0	0	0	0	5	0	0	3	2	0	0	0
PSLR0048	PLHP 1	MoD	Erlestoke (1 unit)	Devizes	SN10 5UA	Wiltshire	South West	2013/2014	1	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0049	PLHP 1	MoD	Erskine Barracks Playing Fields, Partridge Way, Salisbury	Salisbury	SP4 6GE	Wiltshire	South West	Before 2011	30	Development completed	S/2005/0619	30/03/2005	31/12/2010	Residential	No	44	23/06/2014	0	44	Yes	Yes	0	0	15	0	0	28	16	0	13	21	2	8	0
PSLR0050a	PLHP 1	MoD	Erskine Barracks, Wilton - HQ Land	The Avenue, Wilton, Wiltshire	SP2 0AG	Wiltshire	South West	2012/2013	450	Development started	13/04870/OUT	12/04/2011	14/02/2013	Mixed	No	292	16/04/2015	0	292	Yes	Yes	27	0	3	0	0	251	40	1	108	127	1	56	0
PSLR0050b	PLHP 1	MoD	Erskine Barracks, Wilton - HQ Land	The Avenue, Wilton, Wiltshire	SP2 0AG	Wiltshire	South West	2012/2013	450†	Development started	15/09129/REM	15/09/2015	13/01/2016	Mixed	No	65	28/06/2019	0	44	Yes	No	0	0	0	0	0	0	0	44	0	0	0	44	0
PSLR0050c	PLHP 1	MoD	Erskine Barracks, Wilton - HQ Land	The Avenue, Wilton, Wiltshire	SP2 0AG	Wiltshire	South West	2012/2013	450†	Planning stage	15/02808/REM	24/03/2015	21/08/2015	Commercial	No	0	x	x	x	Yes	No	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0050d	PLHP 1	MoD	Erskine Barracks, Wilton - HQ Land	The Avenue, Wilton, Wiltshire	SP2 0AG	Wiltshire	South West	2012/2013	450†	Development completed	14/12101/REM	17/04/2015	13/07/2015	Residential	No	40	06/04/2017	0	39	Yes	No	0	0	0	0	0	0	39	0	0	0	0	39	0
PSLR0051a	PLHP 1	MoD	Farnborough, Queens Gate, Government House Road, Aldershot	Aldershot	GU146FD	Rushmoor	South East	Before 2011	200	Development completed	10/00269/REM	30/04/2010	01/07/2010	Residential	No	42	24/09/2010	0	42	No	Unknown	0	0	0	0	0	42	0	0	0	6	36	0	0
PSLR0051b	PLHP 1	MoD	Farnborough, Queens Gate, Government House Road, Aldershot	Aldershot	GU146FD	Rushmoor	South East	Before 2011	200†	Development completed	11/00192/REM	24/03/2011	23/06/2011	Residential	No	11	14/03/2012	0	11	No	Unknown	0	0	0	0	0	11	0	0	1	2	8	0	0
PSLR0051c	PLHP 1	MoD	Farnborough, Queens Gate, Government House Road, Aldershot	Aldershot	GU146FD	Rushmoor	South East	Before 2011	200†	Planning stage	12/00279/OUT	12/04/2012	27/07/2012	Residential	No	8	x	0	0	No	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0051d	PLHP 1	MoD	Farnborough, Queens Gate, Government House Road, Aldershot	Aldershot	GU146FD	Rushmoor	South East	Before 2011	200†	Development completed	12/00624/REMPP	06/08/2012	23/10/2012	Residential	No	56	29/07/2013	0	56	No	Unknown	0	0	0	0	0	0	56	0	0	0	0	56	0
PSLR0051e	PLHP 1	MoD	Farnborough, Queens Gate, Government House Road, Aldershot	Aldershot	GU146FD	Rushmoor	South East	Before 2011	200†	Development completed	12/00776/REM	01/10/2012	16/11/2012	Residential	No	44	18/06/2013	0	44	No	Unknown	0	0	0	0	0	23	21	0	0	0	23	21	0
PSLR0051f	PLHP 1	MoD	Farnborough, Queens Gate, Government House Road, Aldershot	Aldershot	GU146FD	Rushmoor	South East	Before 2011	200†	Development completed	12/00800/REMPP	12/10/2012	06/12/2012	Residential	No	44	28/07/2014	0	44	No	Unknown	0	0	0	0	0	0	44	0	0	0	0	44	0
PSLR0051g	PLHP 1	MoD	Farnborough, Queens Gate, Government House Road, Aldershot	Aldershot	GU146FD	Rushmoor	South East	Before 2011	200†	Development completed	14/00008/REM	24/12/2013	06/03/2014	Residential	No	76	20/01/2015	0	76	No	Unknown	0	0	0	0	0	8	68	0	0	0	9	67	0
PSLR0051h	PLHP 1	MoD	Farnborough, Queens Gate, Government House Road, Aldershot	Aldershot	GU146FD	Rushmoor	South East	Before 2011	200†	Development completed	14/00340/REM	08/05/2014	12/06/2014	Residential	No	37	04/07/2016	0	37	No	Unknown	0	0	0	0	0	9	9	19	0	0	12	25	0
PSLR0051i	PLHP 1	MoD	Farnborough, Queens Gate, Government House Road, Aldershot	Aldershot	GU146FD	Rushmoor	South East	Before 2011	200†	Development completed	08/00605/REMPP	18/08/2008	06/11/2008	Residential	No	81	29/04/2010	0	81	No	Unknown	0	0	0	0	0	63	18	0	1	18	44	18	0
PSLR0051j	PLHP 1	MoD	Farnborough, Queens Gate, Government House Road, Aldershot	Aldershot	GU146FD	Rushmoor	South East	Before 2011	200†	Development completed	14/00343/FULPP	09/05/2014	08/08/2014	Residential	No	26	04/07/2016	0	26	No	Unknown	0	0	0	0	0	13	13	0	0	14	0	12	0
PSLR0052	PLHP 1	MoD	Farnborough, Queens Gate, Government House Road, Aldershot	Aldershot	GU146FD	Rushmoor	South East	Before 2011	81	Development completed	16/00961/FULPP	26/11/2016	24/03/2017	Residential	No	80	11/06/2018	0	80	Yes	Unknown	0	0	0	0	0	3	38	39	0	0	0	80	0
PSLR0053	PLHP 1	MoD	Fort Blockhouse, Hasler Road, Gosport (Hasler Hospital)	Gosport	PO122FA	Gosport	South East	Before 2011	50	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0054	PLHP 1	MoD	Fort Monkton Paddock House	Gosport	PO122AT	Gosport	South East	2011/2012	1	Development completed	x	x	x	Residential sale	Unknown	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0055	PLHP 1	MoD	Gosport & Fareham Service Family Accommodation, Play Area at Titchfield Park	Northway/Southway, Titchfield, Hampshire	PO15 5EF	Fareham	South East	2013/2014	14	Development completed	P/12/0110/RM	09/02/2012	03/05/2012	Residential	No	14	07/05/2014	0	14	Yes	No	0	0	0	0	0	14	0	0	2	12	0	0	0
PSLR0056	PLHP 1	MoD	Government Comms HQ Oakley site	Harp Hill, Cheltenham	GL52 5AQ	Cheltenham	South West	2013/2014	311	Development started	13/01683/REM	01/10/2013	24/03/2014	Residential	No	311	13/05/2016	7	236	Yes	Yes	0	0	0	0	37	188	27	21	88	63	39	15	31
PSLR0057a	PLHP 1	MoD	Government Pipeline Storage System, Swanvale, (combined Navy and BPA site)	Falmouth PSD, Hillside Road, Swanvale, Cornwall	TR115GD	Cornwall	South West	Before 2011	50	Development started	C1/EA02/0456/10/M	25/05/2010	08/04/2011	Residential	No	125	26/01/2012	9	89	Yes	Yes	0	25	25	0	0	62	6	21	29	24	22	14	0
PSLR0058	PLHP 1	MoD	Gravesend Air Traing Corps	Gravesend	DA11 0QQ	Gravesham	South East	2014/2015	1	Development completed	20140609	23/06/2014	10/03/2015	Residential	No	4	10/02/2017	0	4	Yes	No	0	0	0	0	0	1	3	0	0	0	0	4	0
PSLR0059	PLHP 1	MoD	Gunwharf Barracks	St Georges Rd, Old Portsmouth	PO1 3TD	Portsmouth	South East	Before 2011	37	Development completed	A*36334/GQ	10/02/2005	05/12/2005	Mixed	No	315	13/03/2007	0	314	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	4	307	3	0	0	0	314	0
PSLR0060a	PLHP 1	MoD	Hackbridge (Wallington) Cadet Unit	Corbet Close, Wallington, Surrey	SM6 7AR	Sutton	London	2013/2014	7	Development completed	C2009/62104	03/12/2009	12/05/2010	Residential	No	31	25/09/2012	0	31	Yes	Yes	0	0	0	0	31	31	0	0	0	0	0	31	0
PSLR0060b	PLHP 1	MoD	Hackbridge (Wallington) Cadet Unit	Corbet Close, Wallington, Surrey	SM6 7AR	Sutton	London	2013/2014	7†	Development started	C2012/66014	31/05/2012	14/05/2013	Residential	No	54	17/04/2018	1	38	Yes	Unknown	0	0	0	0	0	38	0	0	0	0	38	0	0
PSLR0061	PLHP 1	MoD	Hazebrouck Barracks, Arborfield (Hazebrouck / Rowcroft) Barracks (DTR) All Phases	Arborfield, Arborfield, Berkshire	RG41 4TL	Wokingham	South East	2013/2014	2000	Development started	O/2014/2280	13/10/2014	02/04/2015	Mixed	Unknown	2000	10/08/2015	24	294	No	Mix of pay and houses	0	56	46	0	0	164	57	73	144	31	10	109	0
PSLR0062	PLHP 1	MoD	Heyford Park,	Camp Road, Upper Heyford, Bicester	OX255LS	Cherwell	South East	Before 2011	200	Development started	10/01642/OUT	27/10/2010	22/12/2011	Mixed	Yes	1075	21/02/2012	135	936	Yes	Yes	168	0	155	0	0	775	68	93	251	467	180	37	1
PSLR0063	PLHP 1	MoD	Hilton JV	Hilton, Derby	DE655HY	South Derbyshire	East Midlands	Before 2011	165	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0064	PLHP 1	MoD	ISS St Eval, South of Neptune Avenue and South of Lincoln Row	St Eval, Cornwall	PL27 7TX	Cornwall	South West	2013/2014	100	Planning stage	PA15/06939	29/07/2015	07/04/2017	Residential	No	100	x	0	0	Yes	Mix of pay and houses	15	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0065	PLHP 1	MoD	Kent Volunteer Estate - Faversham	Preston Street	ME13 8PG	Swale	South East	2011/2012	1	Development completed	SW/13/0106	30/01/2013	02/05/2013	Residential	No	1	31/05/2017	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0066a	PLHP 1	MoD	Kent Volunteer Estates, Ashford Barracks	Rowcroft Barracks	TN233RY	Ashford	South East	Before 2011	200	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0066b	PLHP 1	MoD	Kent Volunteer Estates, Ashford Barracks	Rowcroft Barracks	TN233RY	Ashford	South East	Before 2011	200†	Development completed	15/00589/AS	28/04/2015	15/09/2015	Residential	Yes	59	14/03/2016	0	59	Yes	Unknown	0	0	0	0	0	39	20	0	12	20	6	21	0
PSLR0066c	PLHP 1	MoD	Kent Volunteer Estates, Ashford Barracks	Rowcroft Barracks	TN233RY	Ashford	South East	Before 2011	200†	Development started	15/01301/AS	01/10/2015	25/08/2016	Residential	Yes	105	28/04/2017	0	83	Yes	Unknown	0	0	0	0	0	65	18	0	17	44	3	19	0
PSLR0066d	PLHP 1	MoD	Kent Volunteer Estates, Ashford Barracks	Rowcroft Barracks	TN233RY	Ashford	South East	Before 2011	200†	Development completed	15/01518/AS	18/11/2015	10/08/2016	Residential	Yes	24	10/10/2017	0	24	Yes	No	0	0	0	0	0	24	0	0	3	16	3	2	0
PSLR0066e	PLHP 1	MoD	Kent Volunteer Estates, Ashford Barracks	Rowcroft Barracks	TN233RY	Ashford	South East	Before 2011	200†	Planning stage	17/00597/AS	17/04/2017	17/12/2017	Residential	Yes	40	x	0	0	Yes	Yes	0	0	0	0	40	0	0	0	0	0	0	0	0
PSLR0066f	PLHP 1	MoD	Kent Volunteer Estates, Ashford Barracks	Rowcroft Barracks	TN233RY	Ashford	South East	Before 2011	200†	Planning stage	20/00408/AS	25/03/2020	x	Residential	No	39	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0066g	PLHP 1	MoD	Kent Volunteer Estates, Ashford Barracks	Rowcroft Barracks	TN233RY	Ashford	South East	Before 2011	200†	Development completed	13/01094/AS	27/09/2013	04/07/2014	Residential	No	57	01/04/2015	0	56	Yes	No	0	0	0	0	0	41	15	0	8	26	7	15	0
PSLR0066h	PLHP 1	MoD	Kent Volunteer Estates, Ashford Barracks	Rowcroft Barracks	TN233RY	Ashford	South East	Before 2011	200†	Development completed	10/01046/AS	21/07/2010	16/08/2011	Residential	Yes	63	19/06/2012	0	60	Yes	Yes	0	0	0	0	11	28	32	0	11	12	9	28	0
PSLR0066i	PLHP 1	MoD	Kent Volunteer Estates, Ashford Barracks	Rowcroft Barracks	TN233RY	Ashford	South East	Before 2011	200†	Development started	12/00133/AS	02/02/2012	13/08/2013	Residential	Yes	40	22/04/2014	0	37	Yes	Yes	0	0	0	0	7	34	3	0	7	11	16	3	0
PSLR0066j	PLHP 1	MoD	Kent Volunteer Estates, Ashford Barracks	Rowcroft Barracks	TN233RY	Ashford	South East	Before 2011	200†	Development started	10/00704/AS	20/05/2010	01/03/2011	Residential	Yes	54	11/04/2011	0	50	Yes	Yes	0	0	0	0	11	36	14	0	7	7	17	19	0
PSLR0066k	PLHP 1	MoD	Kent Volunteer Estates, Ashford Barracks	Rowcroft Barracks	TN233RY	Ashford	South East	Before 2011	200†	Development completed	11/01399/AS	06/12/2011	13/11/2012	Residential	Yes	49	25/10/2013	0	49	Yes	Yes	0	0	0	0	12	27	16	6	1	15	13	20	0
PSLR0066l	PLHP 1	MoD	Kent Volunteer Estates, Ashford Barracks	Rowcroft Barracks	TN233RY	Ashford	South East	Before 2011	200†	Development completed	12/00176/AS	12/02/2012	13/08/2013	Residential	Yes	30	30/04/2014	0	30	Yes	Yes	0	0	0	0	9	30	0	0	4	2	14	10	0
PSLR0066m	PLHP 1	MoD	Kent Volunteer Estates, Ashford Barracks	Rowcroft Barracks	TN233RY	Ashford	South East	Before 2011	200†	Development started	15/00315/AS	09/03/2015	18/08/2015	Residential	Yes	104	28/04/2016	0	104	Yes	Unknown	0	0	0	0	0	67	35	2	22	37	7	38	0
PSLR0066n	PLHP 1	MoD	Kent Volunteer Estates, Ashford Barracks	Rowcroft Barracks	TN233RY	Ashford	South East	Before 2011	200†	Development started	16/00808/AS	27/05/2016	22/12/2017	Residential	Yes	86	13/06/2018	0	86	Yes	Unknown	0	0	0	0	0	84	0	2	38	48	0	0	0
PSLR0066o	PLHP 1	MoD	Kent Volunteer Estates, Ashford Barracks	Rowcroft Barracks	TN233RY	Ashford	South East	Before 2011	200†	Development started	17/00396/A	14/03/2017	22/12/2017	Residential	Yes	62	12/01/2018	0	55	Yes	Yes	0	0	0	0	20	1	29	25	0	0	0	55	0
PSLR0066p	PLHP 1	MoD	Kent Volunteer Estates, Ashford Barracks	Rowcroft Barracks	TN233RY	Ashford	South East	Before 2011	200†	Planning stage	17/00578/AS	10/04/2017	22/12/2017	Residential	Yes	31	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0066q	PLHP 1	MoD	Kent Volunteer Estates, Ashford Barracks	Rowcroft Barracks	TN233RY	Ashford	South East	Before 2011	200†	Development started	05/00894/AS	05/05/2005	17/10/2007	Residential	Yes	124	03/12/2007	0	3	Yes	Yes	0	0	0	0	18	1	2	0	1	2	0	0	0
PSLR0066r	PLHP 1	MoD	Kent Volunteer Estates, Ashford Barracks	Rowcroft Barracks	TN233RY	Ashford	South East	Before 2011	200†	Development completed	08/00650/AS	07/04/2008	08/08/2008	Mixed	Yes	23	10/11/2009	0	23	Yes	No	0	0	0	0	0	0	23	0	0	0	0	23	0
PSLR0066s	PLHP 1	MoD	Kent Volunteer Estates, Ashford Barracks	Rowcroft Barracks	TN233RY	Ashford	South East	Before 2011	200†	Development completed	05/01795/AS	05/10/2005	16/04/2008	Residential	Yes	99	09/11/2009	0	99	Yes	Yes	0	0	0	0	23	60	39	0	13	14	45	27	0
PSLR0066t	PLHP 1	MoD	Kent Volunteer Estates, Ashford Barracks	Rowcroft Barracks	TN233RY	Ashford	South East	Before 2011	200†	Development completed	06/01385/AS	31/07/2006	08/01/2008	Residential	Yes	14	11/02/2008	0	14	Yes	No	0	0	0	0	0	2	12	0	0	5	0	9	0
PSLR0066u	PLHP 1	MoD	Kent Volunteer Estates, Ashford Barracks	Rowcroft Barracks	TN233RY	Ashford	South East	Before 2011	200†	Development completed	05/02135/AS	23/12/2005	17/02/2011	Residential	Yes	129	12/09/2011	0	127	Yes	Yes	19	0	19	0	x	91	36	0	13	32	40	42	0
PSLR0066v	PLHP 1	MoD	Kent Volunteer Estates, Ashford Barracks	Rowcroft Barracks	TN233RY	Ashford	South East	Before 2011	200†	Development completed	03/01492/AS	05/09/2003	19/12/2003	Residential	Yes	83	26/07/2004	0	83	Yes	Unknown	0	0	0	0	0	41	42	0	15	2	32	34	0
PSLR0067	PLHP 1	MoD	Killingworth Cadet Unit	West Lane, Killingworth, North Tyneside	NE12 7AB	North Tyneside	North East	2013/2014	5	Development completed	14/00730/FUL	09/05/2014	23/01/2015	Residential	Yes	125	12/05/2016	0	30	Yes	Yes	0	0	0	0	31	23	7	0	6	6	18	0	0
PSLR0068	PLHP 1	MoD	Kingsbury	Brick Kiln Lane, Atherstone	CV9 2LS	North Warwickshire	West Midlands	2011/2012	1	Development completed	x	x	x	Residential sale	Unknown	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0069a	PLHP 1	MoD	Kitchener Barracks, Kitchener Barracks (Dock Road)	Kitchener Barracks, Dock Road, Chatham, Kent	ME4 4UB	Medway	South East	2014/2015	270	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0069b	PLHP 1	MoD	Kitchener Barracks, Kitchener Barracks (Dock Road)	Kitchener Barracks, Dock Road, Chatham, Kent	ME4 4UB	Medway	South East	2014/2015	270†	Development started	MC/17/1392	19/04/2017	29/08/2017	Residential	No	302	18/06/2019	0	302	Yes	Yes	0	0	0	0	49	25	0	277	0	29	71	202	0
PSLR0070	PLHP 1	MoD	Land adjacent to 9 Ladysmith Road, Ashton-under-Lyne (Manchester SFA)	9 Ladysmith Road, Ashton-under-Lyne	OL6 9DJ	Tameside	North West	Before 2011	1	Development completed	11/00034/FUL	24/02/2011	11/07/2011	Residential	Yes	2	05/02/2014	0	2	Yes	No	0	0	0	0	0	2	0	0	0	2	0	0	0
PSLR0071	PLHP 1	MoD	Lincolnshire Volunteer Estate	Newport Road	LN1 3ES	Lincoln	East Midlands	Before 2011	29	Development completed	2008/0543/F	28/07/2008	20/08/2009	Residential	No	76	21/02/2012	0	76	Yes	Yes	6	0	8	0	0	5	63	8	0	0	0	14	62
PSLR0072	PLHP 1	MoD	Littlehampton Army Cadet Force	47 Pier Road, Littlehampton, West Sussex	BN175LW	Arun	South East	Before 2011	3	Planning stage	LU/287/17/PL	02/09/2017	19/12/2017	Mixed	Yes	8	x	0	0	Unknown	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0073a	PLHP 1	MoD	Lower Upnor Depot, Chatham	Off Upnor Road, Lower Upnor, Medway	ME2 4GP	Medway	South East	2013/2014	23	Development completed	MC/13/1804	26/07/2013	30/06/2014	Mixed	Unknown	20	22/05/2018	0	20	Yes	No	0	0	0	0	0	10	1	9	0	0	12	8	0
PSLR0073b	PLHP 1	MoD	Lower Upnor Depot, Chatham	Off Upnor Road, Lower Upnor, Medway	ME2 4GP	Medway	South East	2013/2014	23†	Development started	MC/16/3795	12/09/2016	13/03/2017	Residential	No	8	19/03/2019	0	0	Not applicable	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0073c	PLHP 1	MoD	Lower Upnor Depot, Chatham	Off Upnor Road, Lower Upnor, Medway	ME2 4GP	Medway	South East	2013/2014	23†	Development completed	MC/15/3793	27/10/2015	27/05/2016	Residential	No	16	22/02/2018	0	16	Yes	No	0	0	0	0	0	0	16	0	0	0	0	16	0
PSLR0074	PLHP 1	MoD	Main site Ensleigh	Lansdown Road, Bath, Avon	BA1 5AB	Bath & NE Somerset	South West	2012/2013	300	Development started	14/01853/EFUL	18/04/2014	01/04/2015	Mixed	No	253	27/11/2016	8	161	Yes	Yes	0	18	6	0	4	136	7	18	78	37	42	4	0
PSLR0075	PLHP 1	MoD	Manchester SFA	Ladysmith Road, Ashton-under-Lyne	OL6 9DJ	Tameside	North West	2011/2012	1	Development completed	x	x	x	Residential sale	Yes	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0076	PLHP 1	MoD	Martlesham Heath Family Quarters	Portal Avenue, RAF Martlesham Heath	IP5 3QY	Suffolk Coastal	East	2011/2012	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0077	PLHP 1	MoD	Menwith Hill	Harrogate	HG3 1SD	Harrogate	Yorkshire and The Humber	2012/2013	10	Development completed	x	x	x	Residential sale	Unknown	10	x	x	10	Not applicable	Unknown	0	0	0	0	0	x	x	10	x	x	x	x	10
PSLR0078b	PLHP 1	MoD	Minley Manor, Minley Manor	Minley Road, Minley, Hampshire	GU17 9JT	Hart	South East	2014/2015	50	Planning stage	19/01426/FUL	25/06/2019	25/10/2019	Commercial	No	0	x	x	x	No	No	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0079	PLHP 1	MoD	Minor sales	various	various	x	x	2012/2013	11	Development completed	x	x	x	Residential sale	No	11	x	x	11	Not applicable	Unknown	0	0	0	0	0	x	x	11	x	x	x	x	11
PSLR0080	PLHP 1	MoD	MoD Bicester (Graven Hill)	Ambrosden, Bicester, Oxon	OX25 2PX	Cherwell	South East	2013/2014	1900	Development started	11/01494/OUT	03/10/2011	08/08/2014	Mixed	No	1900	19/07/2017	12	183	No	Yes	0	399	0	0	171	111	49	23	50	7	126	0	0
PSLR0081	PLHP 1	MoD	MOD Foxhill	Bradford Road, Bath, Avon	BA2 5BZ	Bath & NE Somerset	South West	2012/2013	700	Development started	14/04354/EOUT	25/09/2014	30/03/2015	Mixed	No	700	02/02/2017	15	298	Yes	Unknown	0	0	0	0	0	222	34	42	44	71	96	87	0
PSLR0082	PLHP 1	MoD	Mount Wise, Coleridge Training Area Residential	Crownhill, Plymouth, Devon	PL6 5EQ	Plymouth	South West	2013/2014	100	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0083	PLHP 1	MoD	Mount Wise, Crownhill	Plymouth	PL6 5EQ	Plymouth	South West	Before 2011	50	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0084	PLHP 1	MoD	0	Plymouth	PL1 4SW	Plymouth	South West	Before 2011	200	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0085a	PLHP 1	MoD	North Donnington building B7 - Defence Estates	Land off, Primmer Road, Donnington, Telford, Shropshire	TF2 8JU	Telford and Wrekin	West Midlands	Before 2011	69	Development completed	W2007/1521	06/11/2007	05/02/2008	Residential	Unknown	54	22/08/2008	0	54	Yes	Unknown	0	0	0	0	0	45	9	0	0	54	0	0	0
PSLR0085b	PLHP 1	MoD	North Donnington building B7 - Defence Estates	Land off, Primmer Road, Donnington, Telford, Shropshire	TF2 8JU	Telford and Wrekin	West Midlands	Before 2011	69†	Development completed	W2006/0068	25/01/2006	11/12/2006	Residential	Unknown	210	15/06/2007	0	209	Yes	Yes	26	0	26	11	0	155	54	0	27	12	124	46	0
PSLR0086a	PLHP 1	MoD	Norton Barracks	Worcester	WR5 2PJ	Wychavon	West Midlands	2013/2014	10	Development completed	W/13/00858/PN	22/04/2013	13/12/2013	Residential	No	10	23/12/2014	0	10	Yes	Yes	0	10	0	0	0	8	2	0	0	4	0	6	0
PSLR0086b	PLHP 1	MoD	Norton Barracks	Worcester	WR5 2PJ	Wychavon	West Midlands	2013/2014	10†	Development completed	W/11/01290/RM	13/06/2011	15/09/2011	Residential	No	74	16/03/2012	0	51	No	Yes	0	14	8	0	0	43	8	0	10	20	21	0	0
PSLR0087	PLHP 1	MoD	Old Ranges, Shoeburyness	Shoeburyness	SS3 9QN	Southend-on-Sea	East	Before 2011	55	Development completed	04/01160/RES	09/08/2004	01/04/2005	Residential	No	76	06/06/2005	0	75	Yes	Unknown	0	0	0	0	0	63	12	0	0	50	8	17	0
PSLR0088	PLHP 1	MoD	Old War Office Building, London	57 Whitehall, London	SW1A 2EU	Westminster	London	2014/2015	100	Planning stage	16/09548/FULL	04/10/2016	10/07/2017	Mixed	No	85	x	0	0	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0089a	PLHP 1	MoD	OSU Liphook,	Midhurst Road, Liphook	GU307TG	East Hampshire	South East	Before 2011	128	Development completed	33992/001	06/03/1998	29/09/1998	Residential	Yes	120	29/04/1999	0	131	Yes	Yes	0	0	48	0	0	131	0	0	111	10	10	0	0
PSLR0089b	PLHP 1	MoD	OSU Liphook,	Midhurst Road, Liphook	GU307TG	East Hampshire	South East	Before 2011	128†	Development completed	33993/072	21/12/2012	12/07/2013	Residential	Yes	62	16/10/2014	0	62	Yes	Yes	6	0	0	0	0	60	2	0	0	0	0	0	62
PSLR0089c	PLHP 1	MoD	OSU Liphook,	Midhurst Road, Liphook	GU307TG	East Hampshire	South East	Before 2011	128†	Planning stage	33993/082	11/07/2016	12/09/2016	Commercial	Yes	0	x	x	x	Yes	No	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0090	PLHP 1	MoD	Otterburn TA (part), Whitburn Rifle Range	Whitburn Rifle Range, Sunderland, South Tyneside	SR6 7EU	South Tyneside	North East	2013/2014	42	Development completed	ST/0938/14/FUL	02/10/2014	23/01/2015	Residential	No	42	14/07/2015	0	42	Yes	Unknown	0	0	0	0	0	38	4	0	31	0	11	0	0
PSLR0092	PLHP 1	MoD	Parkhurst Road Islington	65 Parkhurst Road, Holloway, London	N7 0LJ	Islington	London	2013/2014	147	Planning stage	P2018/4197/FUL	20/12/2018	x	Residential	No	96	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0093	PLHP 1	MoD	Part of the former Roussillon Barracks site,	Broyle Road, Chichester	PO19 6BL	Chichester	South East	2011/2012	4	Development completed	10/03490/FUL,15/04080/FUL,15/00891/FUL	26/07/2010	02/03/2011	Residential,Infill,Infill	No,No,No	254	16/04/2012	0	254	Yes,Yes,Yes	Yes,No,No	51	0	50	0	0	184	65	5	16	71	115	52	0
PSLR0094	PLHP 1	MoD	Princess Royal Barracks, Princess Royal Barracks Disposal (Deepcut Barracks)	Princess Royal Bks, Deepcut, Surrey	GU16 6RW	Surrey Heath	South East	2014/2015	1200	Development started	12/0546	07/08/2012	27/03/2014	Residential	No	1200	01/08/2014	14	59	Yes	Yes	0	100	100	0	0	34	12	13	14	25	8	12	0
PSLR0095	PLHP 1	MoD	RAF Bentley Priory, London	Stanmore	HA7 3HR	Harrow	London	Before 2011	103	Development completed	P/1452/08CFU,P/1840/11,P/1842/11	23/04/2008	16/09/2010	Mixed,Infill,Infill	No,No,No	115	22/06/2012	0	114	No,No,No	Developer paid local authority to put them somewhere else,No,No	0	0	0	0	0	46	56	12	2	22	32	57	1
PSLR0096	PLHP 1	MoD	RAF Brampton	Brampton, Huntingdon, Cambridgeshire	PE28 4QE	Huntingdonshire	East	2013/2014	402	Development started	15/00368/OUT	24/03/2015	26/02/2016	Mixed	Yes	437	28/06/2017	63	367	Yes	Unknown	0	0	0	0	0	224	34	109	93	143	43	57	31
PSLR0097	PLHP 1	MoD	RAF Burtonwood Warrington	Warrington	WA5 3AN	Warrington	North West	Before 2011	200	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0098a	PLHP 1	MoD	RAF Cardington, Bedford (first phases)Ã‚Â	Bedford	MK420GL	Bedford	East	Before 2011	200	Development started	07/01295/MAR	23/04/2007	12/10/2007	Mixed	Yes	175	09/12/2010	0	155	Yes	Unknown	0	0	0	0	0	103	51	1	7	10	71	67	0
PSLR0098b	PLHP 1	MoD	RAF Cardington, Bedford (first phases)Ã‚Â	Bedford	MK420GL	Bedford	East	Before 2011	200†	Development completed	07/02347/MAR	27/07/2007	18/12/2007	Residential	Yes	135	11/12/2012	0	130	Yes	Unknown	0	0	0	0	0	102	28	0	48	47	19	16	0
PSLR0099a	PLHP 1	MoD	RAF Cardington, Bedford (future phases)Ã‚Â	Bedford	MK420GD	Bedford	East	Before 2011	200	Development started	13/00612/MAR	26/03/2013	12/09/2013	Mixed	No	93	03/10/2014	0	93	Yes	Mix of pay and houses	0	0	0	0	18	59	25	9	31	28	7	27	0
PSLR0099b	PLHP 1	MoD	RAF Cardington, Bedford (future phases)Ã‚Â	Bedford	MK420GD	Bedford	East	Before 2011	200†	Development completed	13/00829/MAR	22/04/2013	24/01/2014	Residential	Yes	128	11/08/2015	0	128	Yes	Mix of pay and houses	0	0	0	0	16	123	4	1	49	42	24	13	0
PSLR0100	PLHP 1	MoD	RAF Daws Hill, Technical Site (Daws Hill)	Daws Hill Lane, High Wycombe, Buckinghamshire	HP11 1PZ	Wycombe	South East	2011/2012	500	Development started	13/05799/FULEA	09/07/2013	03/10/2014	Mixed	No	441	13/01/2016	30	289	Yes	Yes	83	0	36	0	0	181	23	85	94	130	16	49	0
PSLR0101	PLHP 1	MoD	RAF Eastcote	Eastcote	HA4 8FS	Hillingdon	London	Before 2011	200	Development completed	10189/APP/2004/1781,10189/APP/2014/3354,10189/APP/2014/3359,10189/APP/2014/3358,10189/APP/2014/3360	14/06/2004	06/03/2006	Residential,Infill,Infill,Infill,Infill	No,No,No,No,No	409	08/12/2009	0	397	Yes,Not applicable,Not applicable,Not applicable,Not applicable	Developer paid local authority to put them somewhere else,No,No,No,No	0	0	0	0	0	235	155	7	42	19	117	219	0
PSLR0102a	PLHP 1	MoD	RAF Halton	Halton Hospital, Wendover	HP225PP	Aylesbury Vale	South East	Before 2011	200	Development started	07/03446/ADP	19/12/2007	17/06/2008	Mixed	Yes	400	07/05/2009	0	356	Yes	Yes	96	0	24	40	0	226	130	0	14	13	193	136	0
PSLR0102b	PLHP 1	MoD	RAF Halton	Halton Hospital, Wendover	HP225PP	Aylesbury Vale	South East	Before 2011	200†	Development completed	10/00157/APP	03/03/2010	23/02/2011	Residential	No	4	16/08/2012	0	4	Not applicable	No	0	0	0	0	0	4	0	0	0	3	0	1	0
PSLR0103	PLHP 1	MoD	RAF Halton, (Nursing Officers' Mess)	Halton Hospital & Tennis Court Area,Wendover, Bucks	HP225PP	Aylesbury Vale	South East	Before 2011	32	Development started	07/03446/ADP	19/12/2007	17/06/2008	Mixed	Yes	400	10/08/2009	0	44	Yes	Yes	96	0	24	40	0	34	10	0	15	1	18	10	0
PSLR0104	PLHP 1	MoD	RAF Hemswell Cliffe	Capper Avenue, Gainsborough	DN21	West Lindsey	East Midlands	2011/2012	1	Development completed	128621	26/04/2012	02/05/2013	Residential	No	1	02/08/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0105	PLHP 1	MoD	RAF HendonÃ‚Â	East Camp tranches, Barnet	NW9 5JE	Barnet	London	Before 2011	200	Development completed	W00198BT/07	22/10/2007	20/08/2009	Residential	No	190	05/03/2013	0	190	Yes	Yes	0	27	57	0	0	0	0	190	0	0	0	0	190
PSLR0106	PLHP 1	MoD	RAF Kirton in Lindsey, Gainsborough, North Lincs	Gainsborough, North Lincs	DN21 4GG	North Lincolnshire	Yorkshire and The Humber	2014/2015	250	Planning stage	PA/2017/1199	24/07/2017	15/08/2018	Residential	Unknown	302	x	0	0	Yes	Yes	0	0	30	0	0	0	0	0	0	0	0	0	0
PSLR0107	PLHP 1	MoD	RAF Lakenheath	Adririan Avenue/ Armstrong Road/ Collins Avenue	Unknown	Forest Heath	East	2011/2012	52	Development completed	x	x	x	Residential sale	Unknown	52	x	x	52	Not applicable	Unknown	0	0	0	0	0	x	x	52	x	x	x	x	52
PSLR0108	PLHP 1	MoD	RAF Lakenheath	1 Cecil Lodge Close	Unknown	Forest Heath	East	2011/2012	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0109	PLHP 1	MoD	RAF Lakenheath	2 Cecil Lodge Close	Unknown	Forest Heath	East	2011/2012	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0110	PLHP 1	MoD	RAF Lakenheath	40 Edinburgh Road	Unknown	Forest Heath	East	2011/2012	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0111	PLHP 1	MoD	RAF Lakenheath	42 Edinburgh Road	Unknown	Forest Heath	East	2011/2012	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0112	PLHP 1	MoD	RAF Menwith Hill	25 Leadhall Lane	HG2 9NJ	Harrogate	Yorkshire and The Humber	2011/2012	4	Development completed	12/01554/ful	13/04/2012	19/06/2012	Residential	No	1	21/02/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0113	PLHP 1	MoD	RAF Menwith Hill	36 Kirkstone Road	HG1 4SJ	Harrogate	Yorkshire and The Humber	2011/2012	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0114	PLHP 1	MoD	RAF Menwith Hill	19 Kirkstone Road	HG1 4SJ	Harrogate	Yorkshire and The Humber	2011/2012	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0115	PLHP 1	MoD	RAF Menwith Hill	22 Kirkstone Road	HG1 4SJ	Harrogate	Yorkshire and The Humber	2011/2012	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0116	PLHP 1	MoD	RAF Menwith Hill	24 Kirkstone Road	HG1 4SJ	Harrogate	Yorkshire and The Humber	2011/2012	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0117	PLHP 1	MoD	RAF Menwith Hill	23 Kirkstone Road	HG1 4SJ	Harrogate	Yorkshire and The Humber	2011/2012	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0118	PLHP 1	MoD	RAF Menwith Hill	25 Kirkstone Road	HG1 4SJ	Harrogate	Yorkshire and The Humber	2011/2012	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0119	PLHP 1	MoD	RAF Menwith Hill	31 Kirkstone Road	HG1 4SJ	Harrogate	Yorkshire and The Humber	2011/2012	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0120	PLHP 1	MoD	RAF Menwith Hill	28 Kirkstone Road	HG1 4SJ	Harrogate	Yorkshire and The Humber	2011/2012	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0121	PLHP 1	MoD	RAF Menwith Hill	32 Kirkstone Road	HG1 4SJ	Harrogate	Yorkshire and The Humber	2011/2012	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0122	PLHP 1	MoD	RAF Menwith Hill	38 Kirkstone Road	HG1 4SJ	Harrogate	Yorkshire and The Humber	2011/2012	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0123	PLHP 1	MoD	RAF Menwith Hill- Hookstone Drive	43 and 45 Hookstone Drive, Harrogate	HG2 8PR	Harrogate	Yorkshire and The Humber	2013/2014	2	Development completed	x	x	x	Residential sale	No	2	x	x	2	Not applicable	Unknown	0	0	0	0	0	x	x	2	x	x	x	x	2
PSLR0124	PLHP 1	MoD	RAF Rudloe Manor, Number 2 Site (RAF Rudloe Manor)	Westwells Rd, Corsham, Wiltshire	SN13 9RA	Wiltshire	South West	2013/2014	150	Planning stage	14/11354/OUT	03/12/2014	05/08/2016	Residential	No	180	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0125a	PLHP 1	MoD	RAF Stanbridge, Stanbridge (Enclave)	Leighton Buzzard, Bedfordshire	LU7 4QT	Central Bedfordshire	East	2013/2014	175	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0125b	PLHP 1	MoD	RAF Stanbridge, Stanbridge (Enclave)	Leighton Buzzard, Bedfordshire	LU7 4QT	Central Bedfordshire	East	2013/2014	175†	Development started	CB/14/04336/RM	04/11/2014	10/02/2015	Mixed	No	175	23/05/2017	0	90	No	Yes	38	0	15	0	0	62	26	2	3	71	1	15	0
PSLR0125c	PLHP 1	MoD	RAF Stanbridge, Stanbridge (Enclave)	Leighton Buzzard, Bedfordshire	LU7 4QT	Central Bedfordshire	East	2013/2014	175†	Planning stage	CB/15/01574/RM0	24/04/2015	24/07/2015	Commercial	No	0	x	x	x	Not applicable	No	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0125d	PLHP 1	MoD	RAF Stanbridge, Stanbridge (Enclave)	Leighton Buzzard, Bedfordshire	LU7 4QT	Central Bedfordshire	East	2013/2014	175†	Planning stage	CB/19/00080/FULL	09/01/2019	09/04/2019	Residential	No	3	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0126	PLHP 1	MoD	RAF West Drayton	West Drayton	UB7 9FR	Hillingdon	London	Before 2011	200	Development completed	5107/APP/2009/2348	02/11/2009	11/03/2010	Mixed	Yes	773	21/02/2012	0	790	Yes	Unknown	0	0	0	0	0	299	407	84	3	35	238	513	1
PSLR0127	PLHP 1	MoD	RAF West Drayton, Porters way	West Drayton	UB7 9GL	Hillingdon	London	Before 2011	400	Development started	5107/APP/2010/2678	03/11/2010	02/02/2011	Mixed	Yes	574	27/05/2011	0	247	Yes	Yes	0	145	58	0	0	43	202	2	4	0	19	224	0
PSLR0128	PLHP 1	MoD	RAF West Raynham (tech site)	West Raynham, Fakenham	NR217DG	North Norfolk	East	Before 2011	58	Planning stage	PO/08/0506	28/03/2008	x	Residential	No	58	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0129	PLHP 1	MoD	RAF West Ruislip	West Ruislip	UB108TP	Hillingdon	London	Before 2011	200	Development completed	38402/APP/2007/1072	11/04/2007	10/07/2007	Mixed	Unknown	495	18/10/2010	0	492	Yes	Yes	0	68	57	0	0	189	287	16	50	22	63	357	0
PSLR0130	PLHP 1	MoD	RAF Wyton, Huntingdon, Part Airfield	Huntingdon, Cambridgeshire	PE27 3LJ	Huntingdonshire	East	2014/2015	4500	Planning stage	18/00437/FUL	27/02/2018	24/08/2018	Commercial	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0131	PLHP 1	MoD	Reserve Forces' and Cadets' Associations Centre	Ypres Barracks, Macclesfield	SK118LJ	Cheshire East	North West	Before 2011	114	Development started	15/0585M	16/02/2015	18/05/2015	Residential	No	75	14/06/2018	1	38	No	Yes	0	15	0	0	0	31	0	7	16	18	4	0	0
PSLR0132	PLHP 1	MoD	Risborough Bks, Main Site Folkestone Phase 1	Shorncliffe Garrison, Shorncliffe, Kent	CT20 3EU	Folkestone and Hythe	South East	2013/2014	1160	Development started	Y14/0300/SH	13/05/2014	17/12/2015	Residential	Yes	1200	12/07/2016	0	290	No	Yes	130	0	86	0	0	206	46	38	69	119	73	29	0
PSLR0133	PLHP 1	MoD	RM Turnchapel, Barton Road, Plymouth	Plymouth	PL9 9SY	Plymouth	South West	2013/2014	20	Planning stage	14/01337/FUL	16/07/2014	08/10/2014	Commercial	No	0	x	x	x	Not applicable	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0135	PLHP 1	MoD	Roussillon Barracks, Roussillon Barracks	Broyle Road, Chichester, West Sussex	PO191DQ	Chichester	South East	2011/2012	20	Development completed	13/03113/FUL	20/09/2013	11/04/2014	Residential	No	17	12/12/2016	0	17	Yes	Yes	4	0	2	0	0	15	2	0	2	8	2	5	0
PSLR0136a	PLHP 1	MoD	Saighton Camp (future phases)	Chester	CH3 6DH	Cheshire West and Chester	North West	Before 2011	200	Development completed	11/05737/REM	08/12/2011	28/05/2012	Mixed	Yes	349	11/09/2012	0	344	Yes	Yes	0	0	0	0	69	292	38	14	130	28	159	27	0
PSLR0136b	PLHP 1	MoD	Saighton Camp (future phases)	Chester	CH3 6DH	Cheshire West and Chester	North West	Before 2011	200†	Development started	15/05210/FUL	24/12/2015	10/06/2016	Residential	Yes	266	04/08/2016	9	296	Yes	Yes	29	0	31	0	0	263	13	20	105	53	138	0	0
PSLR0136c	PLHP 1	MoD	Saighton Camp (future phases)	Chester	CH3 6DH	Cheshire West and Chester	North West	Before 2011	200†	Development completed	06/01269/REM,08/01555/REM	19/07/2006	13/10/2006	Residential,Infill	Yes,No	103	17/08/2007	0	103	Yes,Yes	Yes,No	0	0	0	0	25	44	59	0	72	0	31	0	0
PSLR0136d	PLHP 1	MoD	Saighton Camp (future phases)	Chester	CH3 6DH	Cheshire West and Chester	North West	Before 2011	200†	Development completed	15/04326/REM	22/10/2015	06/04/2016	Residential	Yes	105	17/11/2016	0	105	Yes	Yes	0	0	0	0	22	103	1	1	63	26	12	4	0
PSLR0138	PLHP 1	MoD	Sheerness Cadet Unit	Sheerness	ME12 2BX	Swale	South East	2014/2015	3	Planning stage	18/500437/FULL	22/01/2018	26/02/2018	Residential	No	5	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0139a	PLHP 1	MoD	Shrewsbury TA Centre, Shrewsbury TA Centre	Sundorne , Shrewsbury, Shropshire	SY1 4RL	Shropshire	West Midlands	Unknown	47	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0139b	PLHP 1	MoD	Shrewsbury TA Centre, Shrewsbury TA Centre	Sundorne , Shrewsbury, Shropshire	SY1 4RL	Shropshire	West Midlands	Unknown	47†	Development started	14/03165/FUL	15/07/2014	02/10/2014	Residential institute	No	90	08/02/2017	0	1	Yes	No	0	0	0	0	0	0	0	1	0	0	0	0	1
PSLR0139c	PLHP 1	MoD	Shrewsbury TA Centre, Shrewsbury TA Centre	Sundorne , Shrewsbury, Shropshire	SY1 4RL	Shropshire	West Midlands	Unknown	47†	Development completed	14/03187/FUL	16/07/2014	09/10/2014	Residential	No	23	30/09/2016	0	23	Yes	Yes	0	0	0	0	23	0	0	23	0	0	23	0	0
PSLR0140	PLHP 1	MoD	Stanford Army Field Training Centre, Watton Training Area - Site 1	Watton, Mundford, Norfolk	IP25 6QZ	Breckland	East	2011/2012	10	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0141	PLHP 1	MoD	Thetford SFA	West Tofts, Thetford	Unknown	Breckland	East	2011/2012	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0142	PLHP 1	MoD	Three Rivers Volunteer Est, HMS Wildfire (Brackenhill House)	The Woods, Northwood, Hertfordshire	HA6 3EX	Three Rivers	East	2011/2012	2	Development started	12/1232/FUL	25/06/2012	10/09/2012	Residential	No	5	23/02/2015	0	2	Yes	No	0	0	0	0	0	2	0	0	2	0	0	0	0
PSLR0143	PLHP 1	MoD	Tidworth Garrison Misc The Gas House	Bulford Road, TidworthÃ‚Â	SP9 7AQ	Wiltshire	South West	2011/2012	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0144	PLHP 1	MoD	Tidworth Garrison Zouch market	Tidworth garrison, Wiltshire	SP9 7ET	Wiltshire	South West	2014/2015	5	Development completed	x	x	x	Residential sale	No	5	x	x	5	Not applicable	Unknown	0	0	0	0	0	x	x	5	x	x	x	x	5
PSLR0145b	PLHP 1	MoD	Tidworth Garrison, Wiltshire	Tidworth	SP9 7LX	Wiltshire	South West	Before 2011	500	Development started	15/05084/REM	03/06/2015	19/11/2015	Residential	No	311	01/11/2016	30	270	Yes	Yes	0	59	25	0	0	188	79	3	73	73	111	13	0
PSLR0145c	PLHP 1	MoD	Tidworth Garrison, Wiltshire	Tidworth	SP9 7LX	Wiltshire	South West	Before 2011	500†	Development completed	E/2012/1447/REM	22/11/2012	28/03/2013	Residential	No	289	17/09/2013	0	289	Yes	Yes	0	0	0	0	66	219	70	0	44	83	149	13	0
PSLR0146	PLHP 1	MoD	Tipner Range, Portsmouth	Portsmouth	PO2 8RA	Portsmouth	South East	2014/2015	600	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0147	PLHP 1	MoD	Upwood Clinic, Cambs	Ramsay, Huntingdon	PE26 2PF	Huntingdonshire	East	2013/2014	25	Planning stage	15/00029/FUL	28/01/2015	23/12/2015	Residential	Unknown	60	x	0	0	Yes	Yes	17	0	7	0	0	0	0	0	0	0	0	0	0
PSLR0148	PLHP 1	MoD	Victoria House	Bilston	SE184LH	Greenwich	London	Before 2011	75	Planning stage	17/3609/F	13/11/2017	08/01/2018	Commercial	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0149	PLHP 1	MoD	Wainscott Barracks, Land (Higham Road) North of Hoo Road, Wainscott, Rochester	Rochester, Kent	ME3 8FG	Medway	South East	Before 2011	200	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0150	PLHP 1	MoD	Warminster Road, Pay & Personnel Agency	Warminster Road, Bath, Avon	BA1 1YT	Bath & NE Somerset	South West	2012/2013	100	Development started	14/02272/eful	16/05/2014	30/03/2015	Mixed	Unknown	204	20/06/2017	17	62	Yes	Yes	0	59	22	0	0	48	9	5	0	0	62	0	0
PSLR0151	PLHP 1	MoD	Waterbeach Barracks, Cambridgeshire	Denny End Road, Cambridge, Cambridgeshire	CB25 9PQ	South Cambridgeshire	East	2014/2015	7600	Planning stage	S/0559/17/OL	17/02/2017	27/09/2019	Mixed	No	6500	x	0	0	Yes	Yes	0	0	0	0	2600	0	0	0	0	0	0	0	0
PSLR0152	PLHP 1	MoD	Wellington Barracks	Bolton Road, Bury, Lancashire	BL8 2PL	Bury	North West	2011/2012	10	Planning stage	55549	26/01/2012	21/03/2012	Commercial	No	0	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0153	PLHP 1	MoD	West Everleigh Down Cottage, SPTA	Lower Everleigh, Wiltshire	SN8 3HE	Wiltshire	South West	2014/2015	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0154	PLHP 1	MoD	West Malling Camp, RSME Chatham (West Malling Camp)	Teston Road, West Malling, Kent	ME19 4GW	Tonbridge and Malling	South East	2013/2014	50	Planning stage	10/03340/OA	29/11/2010	x	Residential	No	64	x	x	x	Yes	Yes	0	18	8	0	0	x	x	x	x	x	x	x	x
PSLR0155	PLHP 1	MoD	Winchester SFA, Sparkford Road	Sparkford Road, Winchester, Hampshire	SO22 4NZ	Winchester	South East	2013/2014	18	Development completed	12/02574/FUL	07/12/2012	12/08/2013	Residential	No	18	19/01/2015	0	18	Yes	Yes	11	0	7	0	0	12	6	0	0	2	16	0	0
PSLR0156a	PLHP 1	Homes England	Ditchburn Street (Blackwall Reach) Regeneration Project	Tower Hamlets	E14 9QE	Tower Hamlets	London	2011/2012	1575	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0156b	PLHP 1	Homes England	Ditchburn Street (Blackwall Reach) Regeneration Project	Tower Hamlets	E14 9QE	Tower Hamlets	London	2011/2012	1575†	Development started	PA/14/02480/P2	08/09/2014	24/12/2014	Mixed	Yes	242	x	0	0	Unknown	Unknown	x	x	x	x	x	0	0	0	0	0	0	0	0
PSLR0157	PLHP 1	Homes England	Greenwich District Hospital (Heart of East Greenwich)	Greenwich	SE10 9GA	Greenwich	London	2011/2012	645	Development started	08/0688/F	18/03/2008	31/03/2009	Mixed	Yes	645	24/09/2014	193	490	Yes	Yes	158	0	67	0	0	6	275	209	0	38	24	428	0
PSLR0158	PLHP 1	Homes England	Park Prewett (Northern Area),	Basingstoke	RG249NB	Basingstoke and Deane	South East	2011/2012	300	Development started	15/00537/RES	17/02/2015	04/12/2015	Residential	No	300	18/12/2017	21	133	Yes	Yes	76	0	44	0	0	87	24	22	14	42	64	13	0
PSLR0159	PLHP 1	Homes England	Severalls Hospital Site (phase1)	Colchester, Essex	CO4 5XN	Colchester	East	2011/2012	248	Development completed	100502	17/03/2010	04/08/2011	Residential	Yes	248	02/10/2012	0	248	Yes	Yes	50	0	12	0	0	200	45	3	64	89	65	30	0
PSLR0160	PLHP 1	Homes England	Queen Elizabeth Hospital	Hackney Road, Tower Hamlets	E2	Tower Hamlets	London	2011/2012	181	Development completed	PA/13/00384/A1	14/02/2013	07/11/2013	Mixed	No	188	21/07/2016	0	187	Yes	Yes	48	0	24	0	0	0	185	2	0	0	0	187	0
PSLR0161	PLHP 1	Homes England	Banbury Lane, Land at Upton,	Northampton	NN4 9DP	Northampton	East Midlands	2011/2012	176	Development completed	N/2010/1064	07/12/2010	31/03/2011	Residential	No	176	03/05/2012	0	176	Yes	Unknown	0	0	0	0	0	152	24	0	49	36	71	19	1
PSLR0162	PLHP 1	Homes England	Centenary Quay	John Thornycroft Avenue, Woolston, Southampton	SO19 9UE	Southampton	South East	2011/2012	168	Development completed	11/01923/REM	05/12/2011	16/03/2012	Residential	No	168	15/07/2013	0	168	Yes	Yes	0	0	18	0	85	0	168	0	0	0	0	168	0
PSLR0163	PLHP 1	Homes England	Ancoats Urban Village	Great Ancoats Street, Manchester	M4Ã‚Â 6AN	Manchester	North West	2011/2012	135	Development completed	079367/FO/2006/N1	22/05/2006	06/12/2006	Mixed	No	135	01/03/2013	0	135	Yes	Unknown	0	0	0	0	0	0	119	16	0	0	0	135	0
PSLR0164	PLHP 1	Homes England	Trenchard House	Westminster	W1F 0JE	Westminster	London	2011/2012	78	Development completed	12/03439/FULL	30/03/2012	07/12/2012	Mixed	No	78	15/07/2016	0	78	Yes	Mix of pay and houses	0	0	65	0	0	0	78	0	0	0	0	71	7
PSLR0165	PLHP 1	Homes England	Westcroft (Site 16)	Milton Keynes	MK4 4JX	Milton Keynes	South East	2011/2012	57	Development completed	12/01179/REM	24/05/2012	06/08/2012	Residential	No	57	16/04/2013	0	57	Yes	Yes	0	10	7	0	0	54	3	0	19	21	13	4	0
PSLR0166	PLHP 1	Homes England	Buckland Mill	Crabble Hill, Dover	CT162AQ	Dover	South East	2011/2012	56	Development started	06/01455	08/12/2006	14/07/2009	Mixed	Yes	141	x	0	0	No	Yes	0	0	0	0	56	0	0	0	0	0	0	0	0
PSLR0167a	PLHP 1	Homes England	Land at Wellington Road	Telford	TF2 8NG	Telford and Wrekin	West Midlands	2011/2012	50	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0167b	PLHP 1	Homes England	Land at Wellington Road	Telford	TF2 8NG	Telford and Wrekin	West Midlands	2011/2012	50†	Planning stage	TWC/2020/0168	24/02/2020	x	Residential	No	43	x	x	x	Yes	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0168a	PLHP 1	Homes England	St Mary's Island	Chatham Maritime	ME4 3SR	Medway	South East	2011/2012	42	Development completed	MC/07/1175	21/05/2007	21/09/2007	Residential	Yes	32	05/09/2014	0	32	Yes	No	0	0	0	0	0	5	27	0	0	4	1	27	0
PSLR0168b	PLHP 1	Homes England	St Mary's Island	Chatham Maritime	ME4 3SR	Medway	South East	2011/2012	42†	Development completed	MC/08/1571	06/08/2013	01/10/2013	Residential	No	10	05/09/2014	0	10	Yes	No	0	0	0	0	0	10	0	0	2	5	3	0	0
PSLR0169	PLHP 1	Homes England	Daisy Bank, Donnington, Telford	Donnington, Telford	TF2 9UQ	Telford and Wrekin	West Midlands	2011/2012	35	Development completed	TWC/2016/0162	23/02/2016	28/12/2016	Residential	No	40	03/11/2017	0	39	Yes	No	0	0	0	0	0	38	0	1	3	29	7	0	0
PSLR0170	PLHP 1	Homes England	Land at Park Road	Dawley, Telford	TF4 2BG	Telford and Wrekin	West Midlands	2011/2012	22	Planning stage	TWC/2010/0502	17/09/2010	23/11/2010	Residential	No	20	x	0	0	No	Yes	0	0	0	0	20	0	0	0	0	0	0	0	0
PSLR0171	PLHP 1	Homes England	Pool Hill Road	Dawley, Telford	TF4 2NH	Telford and Wrekin	West Midlands	2011/2012	15	Development completed	TWC/2015/0217	12/03/2015	11/11/2015	Residential	No	14	29/09/2017	0	14	Yes	Yes	0	0	14	0	0	3	10	1	1	13	0	0	0
PSLR0172	PLHP 1	Homes England	Land at the Sidings	Delabole, Cornwall	PL33 9AX	Cornwall	South West	2011/2012	14	Development completed	E1/2009/01635	19/11/2009	26/08/2011	Residential	No	14	20/02/2012	0	14	Yes	Yes	0	0	0	0	14	13	0	1	0	10	4	0	0
PSLR0173	PLHP 1	Homes England	Marshbrook Way (Site A1),	Muxton, Telford	TF2 8JH	Telford and Wrekin	West Midlands	2011/2012	12	Development completed	TWC/2012/0408	24/05/2012	17/07/2012	Residential	No	12	03/09/2013	0	12	Yes	Unknown	0	0	0	0	0	8	4	0	0	6	6	0	0
PSLR0174	PLHP 1	Homes England	Bickershaw Colliery (South)	Leigh	WN7 4BB	Wigan	North West	2012/2013	474	Development started	A/13/78383	08/08/2013	11/02/2014	Mixed	No	471	25/11/2014	55	368	Yes	Mix of pay and houses	0	0	0	0	75	276	62	30	56	130	144	38	0
PSLR0175	PLHP 1	Homes England	Site F & G Phase 1 Upton - Northampton	Northampton	NN5 4FR	Northampton	East Midlands	2012/2013	401	Development started	11/0046/FULWNN	01/07/2011	28/03/2012	Mixed	No	401	18/12/2013	0	380	Yes	Yes	0	113	0	0	113	279	11	90	10	13	150	111	96
PSLR0176	PLHP 1	Homes England	B4.4 Centre MK (Milton Keynes)	Milton Keynes	MK9 2FR	Milton Keynes	South East	2012/2013	400	Planning stage	13/00967/REM	13/05/2013	x	Mixed	Yes	400	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0177a	PLHP 1	Homes England	Lancaster Moor Hospital	Lancaster	LA1 3SY	Lancaster	North West	2012/2013	389	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0177b	PLHP 1	Homes England	Lancaster Moor Hospital	Lancaster	LA1 3SY	Lancaster	North West	2012/2013	389†	Development started	15/00494/REM	23/04/2015	05/05/2015	Residential	No	33	24/11/2014	0	29	Yes	No	0	0	0	0	0	1	28	0	0	0	0	29	0
PSLR0177c	PLHP 1	Homes England	Lancaster Moor Hospital	Lancaster	LA1 3SY	Lancaster	North West	2012/2013	389†	Planning stage	13/00653/REM	25/06/2013	27/09/2013	Residential	No	34	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0177d	PLHP 1	Homes England	Lancaster Moor Hospital	Lancaster	LA1 3SY	Lancaster	North West	2012/2013	389†	Development started	13/00232/REM	05/03/2013	07/06/2013	Residential	No	197	13/03/2014	0	182	Yes	No	0	0	0	0	0	180	1	1	115	48	19	0	0
PSLR0177e	PLHP 1	Homes England	Lancaster Moor Hospital	Lancaster	LA1 3SY	Lancaster	North West	2012/2013	389†	Development started	14/01011/REM	18/09/2014	12/11/2014	Residential	No	60	27/01/2016	0	14	Yes	No	0	0	0	0	0	0	14	0	0	0	0	14	0
PSLR0177f	PLHP 1	Homes England	Lancaster Moor Hospital	Lancaster	LA1 3SY	Lancaster	North West	2012/2013	389†	Development started	14/00659/REM	16/06/2014	28/07/2014	Residential	No	51	22/09/2014	0	42	Yes	No	0	0	0	0	0	0	42	0	0	0	0	42	0
PSLR0178	PLHP 1	Homes England	Centenary Quay, Southampton	Southampton	SO19 9EF	Southampton	South East	2012/2013	329	Development completed	12/00474/FUL	05/04/2012	12/12/2012	Mixed	No	329	07/04/2015	0	86	No	Yes	0	0	72	0	0	0	48	38	0	0	0	86	0
PSLR0179	PLHP 1	Homes England	Blackberry Hill Hospital	Bristol	BS162EN	Bristol	South West	2012/2013	310	Development started	16/05398/LA	03/10/2016	02/02/2018	Mixed	No	305	12/12/2018	165	52	Yes	Yes	15	0	5	0	0	38	13	1	0	3	49	0	0
PSLR0180	PLHP 1	Homes England	Carr Lodge Farm	Doncaster	DN4 8DY	Doncaster	Yorkshire and The Humber	2012/2013	304	Development completed	13/00073/REMM,15/02694/FULM	14/01/2013	25/03/2013	Residential,Infill	No,No	311	02/04/2014	0	310	Yes,Yes	Unknown,No	0	0	0	0	0	255	51	4	108	129	73	0	0
PSLR0180.1	PLHP 1	Homes England	Carr Lodge Farm	Doncaster	DN4 8DY	Doncaster	Yorkshire and The Humber	2012/2013	12	Development completed	14/00290/REMM	03/03/2014	30/05/2014	Residential	Yes	12	10/12/2014	0	12	No	No	0	0	0	0	0	12	0	0	12	0	0	0	0
PSLR0180.2	PLHP 1	Homes England	Carr Lodge Farm	Doncaster	DN4 8DY	Doncaster	Yorkshire and The Humber	2012/2013	8	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0181	PLHP 1	Homes England	Kingsway Business Park, Rochdale	Rochdale	OL164FY	Rochdale	North West	2012/2013	300	Development completed	10/D53925	29/11/2010	28/02/2011	Residential	Unknown	167	04/05/2012	0	166	Yes	No	0	0	0	0	0	165	1	0	60	25	71	0	10
PSLR0182	PLHP 1	Homes England	Oakgrove - Phase 1 (Main Site)	Milton Keynes	MK109SR	Milton Keynes	South East	2012/2013	231	Development started	11/02404/REM	01/11/2011	05/03/2012	Mixed	No	271	12/02/2013	0	231	Yes	Yes	0	0	0	0	69	124	88	19	87	19	3	122	0
PSLR0183	PLHP 1	Homes England	South Shields Riverside (Circatex and Harton Staithes)	South Shields	NE335EE	South Tyneside	North East	2012/2013	222	Development started	ST/0081/13/FUL	29/01/2013	29/04/2013	Residential	No	222	23/08/2016	0	49	No	Unknown	0	0	0	0	0	49	0	0	1	12	36	0	0
PSLR0184	PLHP 1	Homes England	Bruche Training Centre, Warrington	Warrington	WA1 3JR	Warrington	North West	2012/2013	220	Development started	2013/22541	27/09/2013	06/12/2013	Residential	No	220	21/07/2016	0	32	No	Mix of pay and houses	17	17	33	0	0	0	32	0	29	3	0	0	0
PSLR0185a	PLHP 1	Homes England	Bentley	Doncaster	DN5 0PT	Doncaster	Yorkshire and The Humber	2012/2013	170	Development completed	07/03241/REMM	10/10/2007	30/06/2010	Residential	Yes	33	09/01/2013	0	33	Yes	Yes	0	0	5	0	0	33	0	0	6	24	3	0	0
PSLR0185b	PLHP 1	Homes England	Bentley	Doncaster	DN5 0PT	Doncaster	Yorkshire and The Humber	2012/2013	170†	Development completed	07/03226/REMM	10/10/2007	30/06/2010	Residential	Yes	137	01/11/2013	0	137	Yes	Unknown	0	0	0	0	0	137	0	0	14	58	48	17	0
PSLR0186a	PLHP 1	Homes England	Trevenson Park South Phase 1	Redruth	TR15 3SL	Cornwall	South West	2012/2013	138	Development completed	PA12/02491	12/04/2012	31/05/2012	Mixed	Yes	138	18/02/2014	0	133	Yes	No	0	0	0	0	0	64	66	3	0	2	93	38	0
PSLR0186b	PLHP 1	Homes England	Trevenson Park South Phase 1	Redruth	TR15 3SL	Cornwall	South West	2012/2013	138†	Development started	PA14/06416	24/11/2014	30/01/2015	Residential	Yes	90	29/11/2017	0	89	Yes	Yes	0	0	16	0	60	72	16	1	0	18	32	39	0
PSLR0187	PLHP 1	Homes England	Booth Rise, Northampton	Northampton	NN3 6HU	Northampton	East Midlands	2012/2013	111	Development completed	N/2008/0970	02/09/2008	29/03/2011	Residential	No	111	26/11/2013	0	111	Yes	Yes	55	0	56	0	0	56	54	1	6	42	51	12	0
PSLR0188	PLHP 1	Homes England	Cottam Hall Site K	Preston	PR4 0PE	Preston	North West	2012/2013	104	Development completed	06/2013/0148	12/03/2013	08/08/2013	Residential	No	104	06/01/2015	0	101	Yes	Yes	4	0	17	0	0	87	14	0	38	24	33	6	0
PSLR0189	PLHP 1	Homes England	Castle College Northside, Sheffield	Sheffield	S2 2BZ	Sheffield	Yorkshire and The Humber	2012/2013	84	Development completed	12/03953/FUL	19/12/2012	28/03/2013	Residential	No	84	08/01/2015	0	84	Yes	Yes	6	0	11	0	6	74	10	0	13	48	22	1	0
PSLR0190	PLHP 1	Homes England	Site 22 (5) Pattison, Washington	Washington	NE38 8FL	Sunderland	North East	2012/2013	84	Development completed	11/03442/FUL	25/11/2011	24/04/2012	Residential	No	83	15/11/2013	0	83	Yes	Yes	7	0	2	0	0	83	0	0	30	43	10	0	0
PSLR0191	PLHP 1	Homes England	Lower Ouseburn East Bank	Newcastle-upon-Tyne	NE6 1LT	Newcastle upon Tyne	North East	2012/2013	76	Development completed	2012/1277/01/DET	02/10/2012	20/03/2013	Mixed	No	76	09/12/2014	0	76	Yes	Unknown	0	0	0	0	0	0	76	0	2	0	15	59	0
PSLR0192	PLHP 1	Homes England	Land at Bearbrook	Aylesbury	HP198FU	Aylesbury Vale	South East	2012/2013	75	Development completed	12/02600/ADP	16/11/2012	08/03/2013	Residential	No	75	08/04/2015	0	75	Yes	Yes	20	0	6	0	0	57	18	0	1	0	52	22	0
PSLR0193	PLHP 1	Homes England	Oakgrove - Phase 1 (Parcel 13/Middelton West)	Milton Keynes	MK109SR	Milton Keynes	South East	2012/2013	64	Development completed	12/00733/REM	30/03/2012	07/09/2012	Residential	No	64	07/08/2013	0	64	Yes	Yes	0	16	3	0	0	61	3	0	7	26	17	14	0
PSLR0194	PLHP 1	Homes England	Hospital Crossings - Brindle Road	Preston	PR5 6AX	South Ribble	North West	2012/2013	46	Development started	07/2014/0608/FUL	01/09/2014	13/11/2014	Residential	No	46	11/06/2015	0	20	Yes	No	0	0	0	0	0	20	0	0	12	8	0	0	0
PSLR0195	PLHP 1	Homes England	Chatham Maritime	Chatham	ME4 3JG	Medway	South East	2012/2013	42	Development completed	MC/09/1613	18/09/2009	18/12/2009	Residential	Yes	101	07/08/2013	0	10	No	Yes	0	15	11	0	0	10	0	0	0	10	0	0	0
PSLR0196	PLHP 1	Homes England	ABP Site - Humber Quays Phase 2	Unknown	HU1 2DG	Kingston upon Hull	Yorkshire and The Humber	2012/2013	41	Development started	13/00479/FULL	13/05/2013	07/08/2013	Mixed	Yes	32	08/09/2014	0	0	No	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0197	PLHP 1	Homes England	Western Woodcraft, Frome	Frome	BA111RZ	Mendip	South West	2012/2013	36	Planning stage	120416/004	06/10/2008	02/06/2017	Mixed	Yes	350	x	0	0	No	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0198	PLHP 1	Homes England	Edgbaston Cricket Ground (land & buildings adjacent to)	Birmingham	B5 7SD	Birmingham	West Midlands	2012/2013	22	Development started	2011/05161/PA	20/12/2011	08/02/2012	Residential	Yes	212	02/07/2014	0	15	No	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	15	0	0	1	12	0	2
PSLR0199	PLHP 1	Homes England	Melrose Clinic	Tiverton	EX166RB	Mid Devon	South West	2012/2013	22	Development completed	13/01358/MFUL	16/10/2013	14/05/2014	Residential	Yes	71	23/11/2015	0	23	No	Yes	0	0	0	0	17	15	8	0	1	2	16	4	0
PSLR0200	PLHP 1	Homes England	Middlehaven	Middlesbrough	TS2 1DG	Middlesbrough	North East	2012/2013	12	Development completed	M/RES/1223/14/P	05/12/2014	31/03/2015	Residential	No	9	26/08/2016	0	9	Yes	No	0	0	0	0	0	0	9	0	0	0	9	0	0
PSLR0201	PLHP 1	Homes England	Station Road, Halwill Junction, Beaworthy, Devon	Beaworthy	EX215XB	Torridge	South West	2012/2013	5	Development completed	1/0901/2012/FULM	10/10/2012	21/02/2013	Residential	No	13	04/03/2014	0	4	No	Yes	0	13	0	0	0	4	0	0	0	1	3	0	0
PSLR0202	PLHP 1	Homes England	73 High Street, Chatham	Chatham	ME4 4EE	Medway	South East	2012/2013	3	Planning stage	MC/14/1821	25/06/2014	26/08/2014	Residential	No	3	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0203	PLHP 1	Homes England	Charles Street	Dartford	DA9 9AQ	Dartford	South East	2012/2013	2	Development completed	13/00304/FUL	13/03/2013	08/05/2013	Residential	No	2	17/08/2015	0	2	Yes	No	0	0	0	0	0	2	0	0	0	2	0	0	0
PSLR0204	PLHP 1	Homes England	Plot 10 Ashford Crescent, Grange Farm 8	Milton Keynes	MK8 0NA	Milton Keynes	South East	2012/2013	1	Development completed	12/01341/FUL	18/06/2012	24/08/2012	Residential	No	1	06/03/2014	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0205	PLHP 1	Homes England	Plot 8 Ashford Crescent, Grange Farm 8	Milton Keynes	MK8 0NA	Milton Keynes	South East	2012/2013	1	Development completed	12/01639/FUL	27/07/2012	27/09/2012	Residential	Yes	2	28/04/2014	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0206	PLHP 1	Homes England	Plot 9 Ashford Crescent, Grange Farm 8	Milton Keynes	MK8 0NA	Milton Keynes	South East	2012/2013	1	Development completed	12/01639/FUL	27/07/2012	27/09/2012	Residential	Yes	2	28/04/2014	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0207	PLHP 1	Homes England	Manor/Kingsway Hospital,	Derby	DE223XB	Derby	East Midlands	2013/2014	700	Planning stage	08/18/01304	07/09/2018	14/08/2019	Mixed	Yes	580	x	0	0	No	Yes	0	0	0	0	162	0	0	0	0	0	0	0	0
PSLR0208	PLHP 1	Homes England	Runwell Hospital, Wickford	Wickford	SS117DY	Chelmsford	East	2013/2014	575	Development started	12/01480/OUT	03/10/2012	21/11/2013	Mixed	No	575	30/04/2014	0	308	No	Unknown	0	0	0	0	0	245	39	24	160	37	65	46	0
PSLR0209	PLHP 1	Homes England	Former Cherry Knowle Hospital	Sunderland	SR2 0NB	Sunderland	North East	2013/2014	520	Development started	16/01524/HYB	03/08/2016	26/06/2017	Mixed	Yes	496	04/10/2017	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0210	PLHP 1	Homes England	Killingworth Stores, Killingworth	Killingworth	NE270BZ	North Tyneside	North East	2013/2014	450	Development completed	14/00730/FUL	09/05/2014	23/01/2015	Residential	Yes	125	15/08/2016	0	95	Yes	Yes	0	0	0	0	31	67	28	0	79	10	6	0	0
PSLR0211	PLHP 1	Homes England	Spencers Park	Hemel Hempstead	WA7 1QU	Dacorum	East	2013/2014	357	Development started	4/02351/13/RES	16/12/2013	26/06/2015	Mixed	No	357	12/02/2016	0	357	Yes	Unknown	0	0	0	0	0	323	16	18	50	140	103	51	13
PSLR0212	PLHP 1	Homes England	Prudhoe Hospital, Prudhoe	Prudhoe, Northumberland	NE425NN	Northumberland	North East	2013/2014	350	Development started	14/04160/FUL	16/12/2014	27/04/2016	Residential	Yes	404	07/11/2017	12	103	Yes	Yes	61	0	60	0	0	50	13	40	71	29	3	0	0
PSLR0213	PLHP 1	Homes England	St Georges Hospital, Morpeth (part A&B)	Morpeth	NE612NW	Northumberland	North East	2013/2014	300	Development started	14/02750/FUL	18/08/2014	23/06/2015	Mixed	Yes	375	24/06/2016	8	114	Yes	Unknown	0	0	0	0	0	90	18	6	56	16	22	20	0
PSLR0214a	PLHP 1	Homes England	Forge Farm - North East Sector	Crawley	RH103NQ	Crawley	South East	2013/2014	283	Development completed	CR/2013/0610/ARM	14/11/2013	14/03/2014	Mixed	Yes	204	12/11/2015	0	55	No	Unknown	0	0	0	0	0	48	1	6	15	12	22	6	0
PSLR0214b	PLHP 1	Homes England	Forge Farm - North East Sector	Crawley	RH103NQ	Crawley	South East	2013/2014	283†	Development started	CR/2016/0114/ARM	15/02/2016	28/04/2017	Residential	Yes	75	20/12/2017	0	73	Yes	Yes	0	0	0	0	30	47	6	20	35	16	10	12	0
PSLR0215	PLHP 1	Homes England	Cherry Knowle Hospital, Sunderland	Sunderland	SR2 0NB	Sunderland	North East	2013/2014	250	Development started	16/01524/HYB	03/08/2016	26/06/2017	Mixed	Yes	496	21/11/2018	1	47	Yes	Unknown	0	0	0	0	0	27	17	3	26	10	11	0	0
PSLR0216	PLHP 1	Homes England	Sandymoor North	Runcorn	WA7 1QU	Halton	North West	2013/2014	219	Development started	14/00161/FUL	03/04/2014	18/07/2014	Residential	No	219	23/03/2015	1	194	Yes	No	0	0	0	0	0	47	140	7	119	22	38	15	0
PSLR0217	PLHP 1	Homes England	Kingsmead South - Sites 1 & 2 Disposal	Milton Keynes	MK4 4AN	Milton Keynes	South East	2013/2014	206	Development started	15/00699/REM	30/03/2015	16/10/2015	Mixed	No	206	06/03/2017	13	154	Yes	Yes	52	0	10	0	0	124	19	11	66	44	8	36	0
PSLR0218	PLHP 1	Homes England	Telford - Hadley Park West	Telford	TF7 4LU	Telford and Wrekin	West Midlands	2013/2014	195	Development completed	TWC/2013/1003	16/12/2013	11/04/2014	Residential	No	209	30/01/2015	0	205	Yes	Yes	0	0	0	0	52	195	0	10	79	76	38	12	0
PSLR0219	PLHP 1	Homes England	Trent Basin, Nottingham	Nottingham	NG2 4DS	Nottingham	East Midlands	2013/2014	175	Development started	13/03029/PFUL3	13/12/2013	30/06/2014	Residential	Unknown	160	22/09/2016	0	45	Yes	Unknown	0	0	0	0	0	37	8	0	1	3	31	10	0
PSLR0220a	PLHP 1	Homes England	Tattenhoe Park - Site 1 Disposal	Milton Keynes	MK4 4LH	Milton Keynes	South East	2013/2014	154	Development completed	12/00968/MKPCR	23/04/2012	05/11/2012	Residential	No	16	23/04/2014	0	16	Yes	Yes	4	0	1	0	0	16	0	0	8	8	0	0	0
PSLR0220b	PLHP 1	Homes England	Tattenhoe Park - Site 1 Disposal	Milton Keynes	MK4 4LH	Milton Keynes	South East	2013/2014	154†	Development completed	12/00969/MKPCR	23/04/2012	05/11/2012	Residential	No	138	22/01/2014	0	138	Yes	Yes	32	2	7	0	0	126	12	0	64	39	10	25	0
PSLR0221	PLHP 1	Homes England	Lancashire Land	Preston	PR3 2JE	Preston	North West	2013/2014	150	Development started	06/2014/0535	15/07/2014	14/10/2014	Residential	No	150	07/01/2016	0	128	Yes	Mix of pay and houses	0	0	0	0	17	43	72	13	31	59	22	16	0
PSLR0222	PLHP 1	Homes England	Wharfedale Hospital, Otley	Otley	LS21 2FD	Leeds	Yorkshire and The Humber	2013/2014	132	Development completed	13/03022/FU,15/02093/LI	16/07/2013	12/02/2014	Residential,Infill	No,No	62	25/03/2015	0	62	Yes,Yes	No,No	0	0	0	0	0	38	24	0	10	7	22	23	0
PSLR0223	PLHP 1	Homes England	Trevenson Park North	Redruth	TR15 3SL	Cornwall	South West	2013/2014	130	Development completed	PA15/09993	26/10/2015	16/02/2016	Residential	Unknown	101	14/12/2016	0	68	No	Yes	0	0	0	0	25	52	9	7	9	9	35	15	0
PSLR0224	PLHP 1	Homes England	Milford Hospital, Milford	Milford	GU7 1UJ	Waverley	South East	2013/2014	120	Development started	WA/2013/1926	14/11/2013	20/03/2014	Residential	No	120	15/01/2015	0	107	Yes	Yes	14	12	22	0	0	89	18	0	57	26	12	12	0
PSLR0225	PLHP 1	Homes England	Daedalus Airfield	Lee on Solent, Gosport	PO139FT	Gosport	South East	2013/2014	104	Development completed	13/00431/FULL	11/12/2013	11/03/2014	Residential	Yes	101	09/06/2014	0	101	Yes	Yes	28	0	12	0	0	87	14	0	4	4	14	0	79
PSLR0226	PLHP 1	Homes England	Kingswood 8	Warrington	WA5 7AA	Warrington	North West	2013/2014	99	Development completed	2013/22269	06/08/2013	07/11/2013	Residential	No	99	16/12/2014	0	99	Yes	Yes	0	16	13	0	0	75	24	0	50	18	22	9	0
PSLR0227	PLHP 1	Homes England	Mere Bank	Greenbank Drive, Liverpool	L17 1AE	Liverpool	North West	2013/2014	73	Development completed	13F/1802	14/08/2013	11/11/2013	Residential	No	78	19/03/2012	0	79	Yes	No	0	0	0	0	0	0	78	1	0	0	0	0	79
PSLR0228	PLHP 1	Homes England	Homesland Hospital	Crook	DL150SA	County Durham	North East	2013/2014	49	Development started	3/2013/0043	15/02/2013	18/09/2014	Residential	No	49	18/10/2017	0	49	Yes	No	0	0	0	0	0	43	0	6	29	20	0	0	0
PSLR0229a	PLHP 1	Homes England	Northshore Regeneration (formerley Northbank)	Stockton on Tees	TS18 2NE	Stockton-on-Tees	North East	2013/2014	47	Development completed	09/3072/REM	21/12/2009	19/03/2010	Residential	No	50	19/03/2012	0	50	Yes	Yes	12	0	3	0	0	50	0	0	0	4	46	0	0
PSLR0229b	PLHP 1	Homes England	Northshore Regeneration (formerley Northbank)	Stockton on Tees	TS18 2NE	Stockton-on-Tees	North East	2013/2014	47†	Development completed	12/1836/REM	27/07/2012	14/09/2012	Residential	No	76	14/02/2014	0	76	Yes	No	0	0	0	0	0	75	0	1	3	6	67	0	0
PSLR0230	PLHP 1	Homes England	Telford - Cuckoo Oak	Telford	TF7 4LU	Telford and Wrekin	West Midlands	2013/2014	44	Development completed	TWC/2014/0010	08/01/2014	07/07/2014	Residential	No	44	30/09/2015	0	44	Yes	Yes	0	44	0	0	0	0	0	44	0	24	12	8	0
PSLR0231	PLHP 1	Homes England	Parkland Gateway Corby	Corby	NN172UN	Corby	East Midlands	2013/2014	43	Planning stage	11/00164/DPA	04/05/2011	28/03/2014	Commercial	Unknown	0	x	x	x	No	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0233	PLHP 1	Homes England	The Angle, Harlow	Harlow	CM201DW	Harlow	East	2013/2014	36	Planning stage	HW/FUL/15/00193	29/04/2015	19/01/2016	Residential	Unknown	69	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0234	PLHP 1	Homes England	Bedgebury Place, Kents Hill - Re-development	Milton Keynes	MK7 6JQ	Milton Keynes	South East	2013/2014	32	Development completed	13/02328/FUL	31/10/2013	01/04/2014	Residential	No	40	29/01/2015	0	40	Yes	Yes	8	2	2	0	0	19	20	1	24	3	0	13	0
PSLR0235	PLHP 1	Homes England	Former First School Shenley Brook End, Milton Keynes	Milton Keynes	MK5 7GX	Milton Keynes	South East	2013/2014	24	Development completed	13/01619/FUL	25/07/2013	11/03/2014	Residential	No	24	12/09/2014	0	24	Yes	Yes	5	1	1	0	0	22	1	1	17	4	3	0	0
PSLR0236	PLHP 1	Homes England	Brunel Place	Crawley	RH101JB	Crawley	South East	2013/2014	22	Development completed	CR/2013/0632/RG3	13/11/2013	12/02/2014	Residential	No	22	25/08/2015	0	22	Yes	Yes	0	0	0	0	22	0	0	22	0	0	0	22	0
PSLR0237	PLHP 1	Homes England	Radford	Coventry	CV6 3LL	Coventry	West Midlands	2013/2014	14	Development completed	RM/2014/1062	01/04/2014	14/08/2014	Residential	No	14	12/04/2016	0	14	Yes	No	0	0	0	0	0	13	1	0	14	0	0	0	0
PSLR0238	PLHP 1	Homes England	The Marlowe Centre	St Peter's Lane, Canterbury	CT1 2BP	Canterbury	South East	2013/2014	11	Development completed	CA//13/01269	08/07/2013	17/10/2013	Residential	No	11	07/12/2015	0	11	Yes	No	0	0	0	0	0	9	2	0	0	0	8	2	1
PSLR0240	PLHP 1	Homes England	Plots - Dark Lane - Priorslee - Telford	Telford	TF2 9NN	Telford and Wrekin	West Midlands	2013/2014	8	Planning stage	TWC/2019/0228	19/03/2019	27/06/2019	Residential	No	18	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0241	PLHP 1	Homes England	Broughton A North (1-5,10)	Milton Keynes	MK109NY	Milton Keynes	South East	2013/2014	7	Development completed	12/01549/FUL	25/07/2012	19/10/2012	Residential	No	7	26/02/2014	0	7	Yes	No	0	0	0	0	0	6	1	0	5	0	2	0	0
PSLR0242	PLHP 1	Homes England	Chase Ave Walton Park, Milton Keynes	Milton Keynes	MK7 7HP	Milton Keynes	South East	2013/2014	5	Development started	13/02569/OUT	09/12/2013	30/07/2014	Residential	No	5	14/09/2018	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0244	PLHP 1	Homes England	Ambulance/ Market site	10/11 Grand Parade, Crawley	RH11 7AG	Crawley	South East	2013/2014	4	Development started	CR/2016/0596/FUL	05/08/2016	11/11/2016	Mixed	No	5	04/01/2019	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0245	PLHP 1	Homes England	Lee Chapel Lane	Basildon	SS165NX	Basildon	East	2013/2014	1	Development completed	14/00411/FULL	31/03/2014	19/05/2014	Residential	No	4	12/10/2015	0	4	Yes	No	0	0	0	0	0	4	0	0	4	0	0	0	0
PSLR0246a	PLHP 1	Homes England	Nethermayne/Dry Street	Basildon	SS165TU	Basildon	East	2014/2015	566	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0246b	PLHP 1	Homes England	Nethermayne/Dry Street	Basildon	SS165TU	Basildon	East	2014/2015	566†	Development started	15/00734/REM	05/06/2015	04/09/2015	Residential	Yes	181	10/04/2017	0	160	Unknown	Unknown	0	0	0	0	0	146	0	14	85	65	10	0	0
PSLR0247a	PLHP 1	Homes England	Oakgrove - Disposal (remainder of site Phases 2, 3 & 4)	Milton Keynes	MK15 0AA	Milton Keynes	South East	2014/2015	391	Development completed	13/01924/REM	05/09/2013	04/12/2013	Residential	Yes	112	22/04/2015	0	112	Yes	Yes	30	0	4	0	0	82	29	1	37	21	0	54	0
PSLR0247b	PLHP 1	Homes England	Oakgrove - Disposal (remainder of site Phases 2, 3 & 4)	Milton Keynes	MK15 0AA	Milton Keynes	South East	2014/2015	391†	Development started	14/00207/REM	31/01/2014	01/05/2014	Mixed	Yes	279	30/07/2015	0	264	Yes	Yes	72	0	17	0	0	121	140	3	79	18	0	167	0
PSLR0248	PLHP 1	Homes England	Maghull - Former Ashworth Hospital Site (South)	Parkbourn, Maghull, Liverpool	L31 1HQ	Sefton	North West	2014/2015	370	Development started	DC/2015/01527	13/10/2015	11/03/2016	Mixed	No	369	15/02/2017	10	177	Yes	Yes	0	0	0	0	128	125	2	50	35	24	22	9	87
PSLR0249a	PLHP 1	Homes England	Bilston Urban Village	Bilston	WV14 0JS	Wolverhampton	West Midlands	2014/2015	367	Development started	18/00833/FUL	18/07/2018	20/12/2018	Residential	Yes	420	19/12/2019	7	4	No	Yes	85	0	20	0	0	0	0	4	4	0	0	0	0
PSLR0249b	PLHP 1	Homes England	Bilston Urban Village	Bilston	WV14 0JS	Wolverhampton	West Midlands	2014/2015	367†	Planning stage	18/00235/FUL	01/03/2018	28/09/2018	Commercial	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0250	PLHP 1	Homes England	Cotgrave	Nottingham	NG12 3HA	Rushcliffe	East Midlands	2014/2015	291	Development started	13/01973/REM,13/02479/FUL,14/01405/FUL	13/09/2013	31/01/2014	Residential,Infill,Infill	Yes,Yes,Yes	460	14/08/2015	0	301	No,No,No	Yes,No,No	0	81	56	0	0	240	52	9	112	109	53	27	0
PSLR0251	PLHP 1	Homes England	Cottam Hall - Residential Area	Preston	PR4 0WJ	Preston	North West	2014/2015	283	Development started	06/2015/0243	24/03/2015	23/07/2015	Mixed	No	283	20/07/2016	0	85	Yes	Yes	59	0	0	0	26	75	9	1	16	39	30	0	0
PSLR0252	PLHP 1	Homes England	Avenue Coking Works	Chesterfield	S42 6NB	North East Derbyshire	East Midlands	2014/2015	265	Development started	13/00386/OL	25/04/2013	07/02/2014	Mixed	Unknown	469	21/03/2019	19	37	No	Yes	0	47	47	0	0	18	1	18	9	24	4	0	0
PSLR0253	PLHP 1	Homes England	Former Westgate House	Newcastle-upon-Tyne	NE1 1TT	Newcastle upon Tyne	North East	2014/2015	259	Development completed	2014/0667/01/DET	24/04/2014	14/08/2014	Residential institute	No	259	04/10/2016	0	259	No	Unknown	0	0	0	0	0	0	0	259	0	0	0	259	0
PSLR0254	PLHP 1	Homes England	Icknield Port Loop	Birmingham	B16 0AA	Birmingham	West Midlands	2014/2015	254	Development started	2011/07399/PA	03/11/2011	20/09/2013	Mixed	Yes	1150	23/02/2015	0	0	No	Yes	0	0	0	0	115	0	0	0	0	0	0	0	0
PSLR0255	PLHP 1	Homes England	Askern Colliery	Doncaster	DN6 0BX	Doncaster	Yorkshire and The Humber	2014/2015	227	Development started	13/01424/FULM	02/07/2013	20/06/2014	Residential	No	227	26/06/2017	0	172	No	No	0	0	0	0	0	128	39	5	40	62	70	0	0
PSLR0256	PLHP 1	Homes England	GKN North Works	East Cowes	PO326FN	Isle of Wight	South East	2014/2015	225	Development completed	P/00771/10	24/05/2010	23/12/2010	Residential	Unknown	180	17/08/2011	0	147	No	Yes	0	33	21	0	0	103	44	0	4	21	85	37	0
PSLR0257	PLHP 1	Homes England	Horsehay Land - Lightmoor	Telford	TF4 3BU	Telford and Wrekin	West Midlands	2014/2015	200	Development started	TWC/2014/1072	28/11/2014	27/11/2015	Residential	No	200	18/07/2017	7	135	Yes	Yes	0	0	0	0	50	116	1	18	37	91	5	2	0
PSLR0258	PLHP 1	Homes England	City Gateway (formerly Ashton Gate)	Bristol	BS3 2BN	Bristol	South West	2014/2015	192	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Not applicable	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0259	PLHP 1	Homes England	Allerton Bywater MC	Castleford	WF10 2AS	Leeds	Yorkshire and The Humber	2014/2015	189	Development started	13/05235/FU	05/12/2013	10/11/2014	Mixed	No	189	04/12/2015	0	188	Yes	Yes	0	0	0	0	28	130	47	11	24	76	67	21	0
PSLR0260	PLHP 1	Homes England	Oakgrove - Disposal (remainder of site Phases 2, 3 & 4) Phase 2	Milton Keynes	MK15 0AA	Milton Keynes	South East	2014/2015	182	Development started	14/02178/REM	26/09/2014	23/12/2014	Mixed	Yes	183	21/02/2017	1	181	Yes	Yes	45	0	10	0	0	89	6	86	30	24	45	82	0
PSLR0261	PLHP 1	Homes England	Cotgrave Colliery	Nottingham	NG12 3HA	Rushcliffe	East Midlands	2014/2015	153	Development started	13/01973/REM,13/02479/FUL,14/01405/FUL	13/09/2013	31/01/2014	Residential,Infill,Infill	Yes,Yes,Yes	460	21/05/2015	0	159	No,No,No	Yes,No,No	0	81	56	0	0	151	7	1	141	6	12	0	0
PSLR0262	PLHP 1	Homes England	Knowle West Regeneration (Hengrove Way and Jarmans)	Bristol	BS4 1UE	Bristol	South West	2014/2015	150	Development started	17/00684/M	08/02/2017	16/06/2017	Residential	No	150	19/10/2018	3	77	No	No	0	0	0	0	0	27	50	0	1	26	0	50	0
PSLR0263a	PLHP 1	Homes England	Lightmoor Urban Village	Telford	TF4 3TB	Telford and Wrekin	West Midlands	2014/2015	150	Development completed	W2009/0118	10/02/2009	09/04/2009	Residential	Yes	11	09/12/2009	0	11	Yes	Unknown	0	0	0	0	0	11	0	0	3	8	0	0	0
PSLR0263b	PLHP 1	Homes England	Lightmoor Urban Village	Telford	TF4 3TB	Telford and Wrekin	West Midlands	2014/2015	150†	Development completed	W2009/0716	25/08/2009	11/03/2010	Residential	Yes	36	05/07/2010	0	36	Yes	Unknown	0	0	0	0	0	33	3	0	4	20	12	0	0
PSLR0263c	PLHP 1	Homes England	Lightmoor Urban Village	Telford	TF4 3TB	Telford and Wrekin	West Midlands	2014/2015	150†	Development completed	TWC/2011/0506	17/06/2011	02/09/2011	Residential	Yes	66	15/05/2014	0	66	No	No	0	0	0	0	0	64	2	0	26	24	15	1	0
PSLR0265	PLHP 1	Homes England	Central Ambulance Station	Bristol	BS2 0JB	Bristol	South West	2014/2015	120	Planning stage	17/04267/F	28/07/2017	06/09/2018	Residential	No	375	x	0	0	No	Yes	58	0	17	0	0	0	0	0	0	0	0	0	0
PSLR0266	PLHP 1	Homes England	Moorgreen Hospital	Southampton	SO303PY	Eastleigh	South East	2014/2015	120	Development started	F/15/77247	21/09/2015	15/03/2016	Residential	No	121	06/04/2017	0	119	Yes	Yes	36	0	7	0	36	73	44	2	4	22	11	36	46
PSLR0267	PLHP 1	Homes England	Gemini 16 - Residue	Warrington	WA5 8WD	Warrington	North West	2014/2015	117	Development completed	2015/26158,2016/28891	08/07/2015	12/10/2015	Residential,Infill	Yes,Yes	118	20/06/2016	0	73	No,No	Developer paid local authority to put them somewhere else,Developer paid local authority to put them somewhere else	0	0	0	0	0	72	0	1	48	22	3	0	0
PSLR0268	PLHP 1	Homes England	Aintree Triangle	Bull Lane, Aintree	L9 8HF	Sefton	North West	2014/2015	109	Development started	DC/2014/01655	20/10/2014	14/12/2015	Residential	No	109	19/01/2017	0	103	Yes	Yes	0	23	5	0	0	84	12	7	25	4	19	0	55
PSLR0269	PLHP 1	Homes England	Grimsby District General Hospital	Grimsby	DN331DS	North East Lincolnshire	Yorkshire and The Humber	2014/2015	104	Development completed	DM/0947/14/FUL	29/08/2014	04/03/2015	Residential	No	104	03/02/2016	0	104	Yes	Yes	0	16	5	0	0	83	6	15	0	18	86	0	0
PSLR0270	PLHP 1	Homes England	Ashington General Hospital, Ashington	Ashingtom	NE630DZ	Northumberland	North East	2014/2015	104	Development completed	13/03856/FUL	18/12/2013	16/10/2014	Residential	No	104	21/01/2016	0	104	Yes	Yes	83	0	21	0	0	21	20	63	0	51	13	0	40
PSLR0271	PLHP 1	Homes England	Quebec Barracks	Bordon, E Hampshire	GU350LA	East Hampshire	South East	2014/2015	100	Development completed	28353/004	24/03/2014	03/02/2015	Residential	No	100	22/03/2017	0	100	Yes	Yes	25	0	10	0	0	84	14	2	24	21	35	20	0
PSLR0272	PLHP 1	Homes England	Magdalen Green & Former Day Nursery	Magdalen Street, Colchester, Essex	CO1 2JR	Colchester	East	2014/2015	94	Planning stage	152730	04/12/2015	24/10/2016	Residential	Unknown	58	x	0	0	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0273	PLHP 1	Homes England	Marksbury Road (Kingsweir & Torpoint Dev Site)	Bristol	BS3 5JQ	Bristol	South West	2014/2015	80	Development started	12/05581/P	14/12/2012	20/06/2013	Mixed	No	85	07/03/2018	0	81	Yes	No	0	0	0	0	0	37	26	18	21	30	0	30	0
PSLR0274	PLHP 1	Homes England	Sandymoor	Runcorn	WA7 1QW	Halton	North West	2014/2015	76	Development completed	14/00575/FUL,16/00125/FUL	10/10/2014	16/03/2015	Residential,Infill	No,No	110	04/08/2016	0	109	Yes,Unknown	No,Unknown	0	0	0	0	0	65	42	2	83	8	18	0	0
PSLR0275	PLHP 1	Homes England	St Georges Hospital, Morpeth Phase 2	Morpeth	NE612NW	Northumberland	North East	2014/2015	76	Development started	14/02750/FUL	18/08/2014	23/06/2015	Mixed	Yes	375	x	1	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0276	PLHP 1	Homes England	Telford - Park Road, Malinslee	Telford	TF4 2AY	Telford and Wrekin	West Midlands	2014/2015	75	Development completed	TWC/2015/0177	03/03/2015	15/05/2015	Residential	No	81	27/05/2016	0	81	Yes	Yes	0	81	0	0	0	0	0	81	0	51	30	0	0
PSLR0277	PLHP 1	Homes England	Moorpark Offices, Sewing Room	Lancaster	LA1 3SA	Lancaster	North West	2014/2015	70	Development started	15/00813/FUL	24/06/2015	31/03/2016	Residential	No	62	15/06/2017	0	60	Yes	No	0	0	0	0	0	33	26	1	7	28	5	20	0
PSLR0278	PLHP 1	Homes England	Gorton Monastery, Manchester	Manchester	M12 5XH	Manchester	North West	2014/2015	67	Development completed	104446/FO/2013/N2	17/12/2013	19/02/2014	Residential	No	67	12/03/2015	0	67	Yes	Unknown	0	0	0	0	0	0	67	0	0	34	33	0	0
PSLR0279	PLHP 1	Homes England	Devonshire Road Industrial Estate	Millom	LA184JS	Copeland	North West	2014/2015	60	Planning stage	4/16/2340/0F1	18/11/2015	06/06/2018	Commercial	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0280	PLHP 1	Homes England	Telford Place	Crawley	RH101SY	Crawley	South East	2014/2015	59	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Not applicable	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0282	PLHP 1	Homes England	Carr Lodge Farm Phase 2	Doncaster	DN4 8DY	Doncaster	Yorkshire and The Humber	2014/2015	25	Development completed	14/00290/REMM	03/03/2014	30/05/2014	Residential	Yes	12	x	0	0	No	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0283	PLHP 1	Homes England	City Wharf	Lichfield	WS14 9DZ	Lichfield	West Midlands	2014/2015	24	Development completed	14/00028/FULM	13/01/2014	14/08/2014	Residential	No	24	23/08/2016	0	24	Yes	Yes	24	0	0	0	0	0	0	24	0	2	2	20	0
PSLR0284	PLHP 1	Homes England	Hitchin Hospital	Hichin	SG5 2QU	North Hertfordshire	East	2014/2015	19	Development completed	15/01385/1	26/05/2015	27/11/2015	Residential	No	18	24/11/2016	0	18	Yes	No	0	0	0	0	0	18	0	0	12	6	0	0	0
PSLR0285	PLHP 1	Homes England	Edge Lane nos 353-355 and nos 73-81	Liverpool	L7 9LG	Liverpool	North West	2014/2015	18	Development completed	14F/2881	10/12/2014	16/03/2015	Residential	No	18	20/12/2016	0	18	Yes	Yes	0	18	0	0	0	2	0	16	0	0	0	18	0
PSLR0286	PLHP 1	Homes England	Beechwood Avenue	Runcorn	WA7 3JW	Halton	North West	2014/2015	16	Planning stage	14/00087/FUL	21/02/2014	17/09/2017	Residential	No	15	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0287	PLHP 1	Homes England	Sites NE, Telford - Donnington	Telford	TF2 7QD	Telford and Wrekin	West Midlands	2014/2015	16	Development completed	TWC/2013/0936	27/11/2013	26/02/2014	Mixed	No	25	13/09/2016	0	12	No	No	0	0	0	0	0	0	0	12	0	0	0	0	12
PSLR0288	PLHP 1	Homes England	Northfleet Embankment	Northfleet, Kent	DA11 9NE	Gravesham	South East	2014/2015	12	Development completed	20140545	04/06/2014	09/09/2014	Residential	No	12	14/10/2016	0	12	Yes	No	0	0	0	0	0	0	0	12	0	0	0	12	0
PSLR0289	PLHP 1	Homes England	GKN North Works	East Cowes	PO32 6FN	Isle of Wight	South East	2014/2015	8	Development completed	TCP/31812/A	19/06/2014	11/08/2014	Residential	Yes	8	21/06/2016	0	8	Yes	No	0	0	0	0	0	5	3	0	0	0	8	0	0
PSLR0290	PLHP 1	DEFRA	Wood Wharf	Tower Hamlets	E14 9SB	Tower Hamlets	London	2011/2012	1668	Development started	PA/08/01215/EX	20/06/2008	18/05/2009	Mixed	No	1668	29/06/2010	0	0	Yes	Yes	0	403	181	0	0	0	0	0	0	0	0	0	0
PSLR0291	PLHP 1	DEFRA	Gloucester Quays,	Gloucester	GL1 5SF	Gloucester	South West	2011/2012	1000	Development started	02/00271/OUT	26/03/2002	22/06/2006	Mixed	Yes	1000	19/03/2012	0	35	No	No	0	0	0	0	0	0	0	35	0	0	0	4	31
PSLR0292	PLHP 1	DEFRA	Marsh Lane	Nantwich	CW5 5LH	Cheshire East	North West	2011/2012	14	Development completed	12/1488N	13/04/2012	25/06/2012	Residential	No	13	26/03/2013	0	13	Yes	No	0	0	0	0	0	13	0	0	13	0	0	0	0
PSLR0293	PLHP 1	DEFRA	John Dower House	Cheltenham	GL50 3RA	Cheltenham	South West	2011/2012	10	Development started	16/01499/FUL	12/08/2016	22/12/2016	Residential institute	Yes	80	09/06/2018	1	41	No	Developer paid local authority to put them somewhere else	0	0	0	0	0	12	0	29	0	0	0	12	29
PSLR0294	PLHP 1	DEFRA	Slepe Farm	Arne, Wareham, Dorset	BH20 5BN	Purbeck	South West	2011/2012	1	Development completed	6/2013/0511	16/09/2013	11/11/2013	Mixed	No	1	x	0	1	Yes	No	0	0	0	0	0	0	0	1	0	0	0	1	0
PSLR0295	PLHP 1	DEFRA	Icknield Port Loop, Birmingham,	Birmingham	B16 0BE	Birmingham	West Midlands	2012/2013	950	Development started	2011/07399/PA	03/11/2011	20/09/2013	Mixed	Yes	1150	12/12/2014	6	34	No	Yes	0	0	0	0	115	20	0	14	0	0	34	0	0
PSLR0296	PLHP 1	DEFRA	Trent Basin,	Nottingham	NG2 4DS	Nottingham	East Midlands	2012/2013	800	Planning stage	x	x	x	x	Unknown	x	x	x	x	Unknown	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0297	PLHP 1	DEFRA	Commerce Road, Brentford,	Brentford	TW8 8LE	Hounslow	London	2012/2013	480	Development started	00297/R/P7	05/06/2013	08/10/2013	Mixed	No	520	01/07/2014	0	232	No	Yes	0	0	22	0	0	0	232	0	0	0	15	216	1
PSLR0298	PLHP 1	DEFRA	Land at Leigh, Nr Wigan,	Leigh	WN7 4QP	Wigan	North West	2012/2013	400	Planning stage	A/16/82492/OUTMES	10/05/2016	20/07/2017	Residential	No	470	x	0	0	No	Yes	0	0	0	0	118	0	0	0	0	0	0	0	0
PSLR0299	PLHP 1	DEFRA	Hale Wharf	Haringey	N17 9NF	Haringey	London	2012/2013	320	Development started	HGY/2016/1719	07/06/2016	12/06/2017	Residential	Yes	505	27/09/2017	0	0	Yes	Yes	34	0	143	0	0	0	0	0	0	0	0	0	0
PSLR0300	PLHP 1	DEFRA	West Quay, Gloucester,	Gloucester	GL1 2EH	Gloucester	South West	2012/2013	150	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0303	PLHP 1	DEFRA	City Road Basin	Unknown	N1 7SA	Islington	London	2012/2013	130	Development completed	P2014/2131/FUL	04/07/2014	31/03/2015	Residential	No	98	09/07/2018	0	97	Yes	Yes	64	0	15	0	0	28	69	0	0	0	0	97	0
PSLR0304	PLHP 1	DEFRA	Land at Slough Basin/Stoke Road, Slough,	Slough	SL2 5AS	Slough	South East	2012/2013	110	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Not applicable	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0305	PLHP 1	DEFRA	New Islington, Manchester Phase 2,	Manchester	M4 6EQ	Manchester	North West	2012/2013	100	Development completed	100317/FO/2012/N2	24/08/2012	22/11/2012	Mixed	No	46	15/05/2015	0	46	Yes	Unknown	0	0	0	0	0	0	46	0	0	0	20	26	0
PSLR0306	PLHP 1	DEFRA	Meadow Lane, Nottingham,	Nottingham	NG2 3BP	Nottingham	East Midlands	2012/2013	100	Planning stage	13/02877/PFUL3	02/12/2013	29/10/2015	Mixed	No	95	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0307	PLHP 1	DEFRA	Attercliffe Waterside, Sheffield,	Sheffield	S9 3QP	Sheffield	Yorkshire and The Humber	2012/2013	80	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0308	PLHP 1	DEFRA	Ashley Lane Warehouse	Shipley	BD17 7DB	Bradford	Yorkshire and The Humber	2012/2013	73	Planning stage	13/05144/MAF	13/12/2013	14/03/2014	Commercial	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0309	PLHP 1	DEFRA	Buxton Road Wharf, Macclesfield,	Macclesfield	SK10 1LX	Cheshire East	North West	2012/2013	61	Development completed	15/2412M	20/12/2013	02/05/2014	Residential institute	No	64	28/03/2019	0	62	Yes	No	0	0	0	0	0	32	30	0	0	0	0	62	0
PSLR0310	PLHP 1	DEFRA	Northwich Marina,	Northwich	CW9 5JJ	Cheshire West and Chester	North West	2012/2013	58	Development completed	12/00618/FUL	10/02/2012	27/07/2012	Mixed	No	57	25/11/2013	0	0	No	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0311	PLHP 1	DEFRA	Boot Wharf, Nuneaton,	Nuneaton	CV11 5VD	Nuneaton and Bedworth	West Midlands	2012/2013	53	Development started	33050	28/10/2014	18/02/2016	Residential	No	53	07/11/2018	0	18	Unknown	Yes	7	0	6	0	0	16	0	2	7	10	1	0	0
PSLR0312	PLHP 1	DEFRA	Land at Store Street, Manchester,	Manchester	M1 2NE	Manchester	North West	2012/2013	52	Planning stage	115545/FO/2017	07/03/2017	06/06/2017	Mixed	Yes	360	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0313	PLHP 1	DEFRA	Sharpness Docks,	Sharpness	GL13 9UA	Stroud	South West	2012/2013	50	Planning stage	S.17/0798/OUT	03/04/2017	x	Mixed	No	400	x	x	x	Yes	Yes	0	0	0	0	90	x	x	x	x	x	x	x	x
PSLR0314	PLHP 1	DEFRA	Clayton Triangle, Clayton le Moors,	Clayton le Moors	BB5 5JF	Hyndburn	North West	2012/2013	42	Development started	11/10/0511	28/01/2011	10/05/2011	Residential	Unknown	128	21/02/2012	0	1	No	Unknown	0	0	0	0	0	1	0	0	0	1	0	0	0
PSLR0315	PLHP 1	DEFRA	Fenny Stratford Milton Keynes	Fenny Stratford	MK2 2AU	Milton Keynes	South East	2012/2013	40	Development completed	16/02331/FUL	16/08/2016	08/02/2017	Residential	No	39	09/05/2018	0	39	Yes	Yes	8	0	0	0	0	39	0	0	7	31	0	0	1
PSLR0316	PLHP 1	DEFRA	Carolina Street, Bootle,	Bootle	L20 4AB	Sefton	North West	2012/2013	40	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0317	PLHP 1	DEFRA	Hazelmere Marina	Waltham Abbey	EN9 1AZ	Broxbourne	East	2012/2013	37	Development started	07/15/0119/F	28/01/2015	12/11/2015	Mixed	No	114	21/03/2017	1	113	Yes	Yes	18	0	3	0	0	17	94	2	0	2	10	101	0
PSLR0318	PLHP 1	DEFRA	Bow Wharf	Tower Hamlets	E3 5SN	Tower Hamlets	London	2012/2013	34	Development started	PA/11/03371/A1	01/11/2011	18/06/2014	Mixed	Yes	34	15/12/2017	0	28	Yes	Yes	0	0	0	0	10	0	27	1	0	0	5	23	0
PSLR0319	PLHP 1	DEFRA	Sherborne Wharf, Birmingham	Birmingham	B16 8DE	Birmingham	West Midlands	2012/2013	30	Planning stage	2017/08095/PA	20/09/2017	11/05/2018	Residential	No	87	x	0	0	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0320	PLHP 1	DEFRA	Navigation Road	Northwich	CW8 1BH	Cheshire West and Chester	North West	2012/2013	20	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0321	PLHP 1	DEFRA	Bulbourne Yard	Tring	HP23 5QE	Aylesbury Vale	South East	2012/2013	20	Development started	16/01079/APP	21/03/2016	16/08/2017	Residential	No	21	21/02/2012	7	3	Yes	No	0	0	0	0	0	3	0	0	0	0	3	0	0
PSLR0322	PLHP 1	DEFRA	Bridge Street, Smethwick,	Birmingham	B66 3DR	Birmingham	West Midlands	2012/2013	17	Planning stage	x	x	x	x	Unknown	x	x	x	x	Unknown	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0323	PLHP 1	DEFRA	Land at Lock Street	Northwich	CW8 1AN	Cheshire West and Chester	North West	2012/2013	17	Planning stage	x	x	x	x	Unknown	x	x	x	x	Unknown	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0324	PLHP 1	DEFRA	Aldcliffe Road,	Lancaster	LA1 1SU	Lancaster	North West	2012/2013	14	Development completed	09/00123/FUL	12/02/2009	29/01/2010	Residential	No	14	22/02/2016	0	14	Yes	No	0	0	0	0	0	9	5	0	0	4	10	0	0
PSLR0325	PLHP 1	DEFRA	Marsworth Junction	Marsworth, Tring	HP23 4LZ	Aylesbury Vale	South East	2012/2013	13	Development started	10/01336/APP	23/06/2010	20/04/2012	Residential	No	13	02/07/2015	0	12	Yes	No	0	0	0	0	0	1	11	0	3	0	9	0	0
PSLR0326	PLHP 1	DEFRA	Hawkesbury Pump House, Nuneaton,	Nuneaton	CV6 6QR	Nuneaton and Bedworth	West Midlands	2012/2013	12	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0327	PLHP 1	DEFRA	Kilby Bridge, Oadby,	Oadby	LE18 3TE	Oadby and Wigston	East Midlands	2012/2013	12	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0329	PLHP 1	DEFRA	Aldermaston Wharf, Padworth,	Padworth	RG7 4JS	West Berkshire	South East	2012/2013	11	Development completed	11/01564/FULMAJ	21/07/2011	16/03/2012	Residential	No	11	10/07/2017	0	11	Unknown	No	0	0	0	0	0	11	0	0	0	2	9	0	0
PSLR0330	PLHP 1	DEFRA	Norwood Yard	Westminster	W10 4RH	Ealing	London	2012/2013	10	Development completed	P/2007/4416	21/05/2013	22/10/2015	Residential	Unknown	10	18/05/2015	0	10	Yes	No	0	0	0	0	0	10	0	0	1	5	2	0	2
PSLR0331	PLHP 1	DEFRA	Harrow Road,	Westminster	W10 4RH	Westminster	London	2012/2013	9	Planning stage	15/03369/FULL	17/04/2015	30/11/2017	Mixed	No	8	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0332	PLHP 1	DEFRA	Hurst Lane Bollington	Bollington	SK10 5LP	Cheshire East	North West	2012/2013	8	Development completed	15/3461M	29/07/2015	03/06/2016	Residential	No	7	16/03/2018	0	7	No	No	0	0	0	0	0	6	0	1	3	4	0	0	0
PSLR0333	PLHP 1	DEFRA	Market Place, Brentford,	Brentford	TW8 8LB	Hounslow	London	2012/2013	5	Development completed	P/2012/0089	17/01/2012	27/06/2013	Residential	No	5	16/05/2016	0	5	Yes	No	0	0	0	0	0	5	0	0	0	0	5	0	0
PSLR0334	PLHP 1	DEFRA	Land & Premises at Church Road, Marple,	Marple	SK6 6BN	Stockport	North West	2012/2013	5	Planning stage	DC/067001	31/08/2017	x	Mixed	No	7	x	x	x	Yes	No	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0335	PLHP 1	DEFRA	New Covent Garden Market	London	SW8 5NPP	Wandsworth	London	2013/2014	2491	Development started	2014/2810	22/05/2014	11/02/2015	Mixed	Yes	3019	16/06/2017	0	0	Yes	Yes	223	0	223	0	0	0	0	0	0	0	0	0	0
PSLR0336	PLHP 1	DEFRA	Leeds Rivers House	21 Park Square South, Leeds	LS1 2QG	Leeds	Yorkshire and The Humber	2013/2014	50	Development completed	14/00671/DPD	04/02/2014	17/03/2014	Residential	No	63	22/04/2016	0	63	Yes	No	0	0	0	0	0	0	0	63	0	0	0	63	0
PSLR0337	PLHP 1	DEFRA	Sunbury Depot	Riverside Works, Fordbridge Road, Sunbury	TW16 6BT	Spelthorne	South East	2013/2014	37	Development completed	13/00153/FUL	29/01/2013	14/08/2013	Mixed	No	37	19/03/2015	0	37	Yes	Yes	0	0	8	0	0	27	10	0	5	10	14	8	0
PSLR0338	PLHP 1	DEFRA	Hitchin Stotfold Pig Development Unit	Stotfold, Near Letchworth, Hitchen Road, Hitchen	SG5 4JH	Central Bedfordshire	East	2013/2014	5	Development started	CB/14/04048/FULL	07/11/2014	21/08/2015	Mixed	No	116	07/08/2017	2	105	Yes	Mix of pay and houses	0	0	5	0	43	80	16	9	25	57	4	19	0
PSLR0339a	PLHP 1	DEFRA	Diglis Basin, Worcester phase 2	Worcester	WR5 3BX	Worcester	West Midlands	Before 2011	323	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0339b	PLHP 1	DEFRA	Diglis Basin, Worcester phase 2	Worcester	WR5 3BX	Worcester	West Midlands	Before 2011	323†	Development completed	P06D0364,P07D0031,P09D0445	10/07/2006	21/09/2006	Mixed,Infill,Infill	No,No,No	219	29/01/2008	0	219	Yes,Yes,Yes	Unknown,No,No	0	0	0	0	0	61	158	0	1	7	41	170	0
PSLR0339c	PLHP 1	DEFRA	Diglis Basin, Worcester phase 2	Worcester	WR5 3BX	Worcester	West Midlands	Before 2011	323†	Development started	P07D0218	10/04/2007	05/07/2007	Residential	No	114	08/10/2013	0	108	Yes	Unknown	0	0	0	0	0	2	106	0	0	0	2	106	0
PSLR0339d	PLHP 1	DEFRA	Diglis Basin, Worcester phase 2	Worcester	WR5 3BX	Worcester	West Midlands	Before 2011	323†	Development completed	P07D0551	20/09/2007	19/11/2007	Residential	No	29	06/06/2016	0	35	Yes	Unknown	0	0	0	0	0	19	16	0	0	0	5	30	0
PSLR0339e	PLHP 1	DEFRA	Diglis Basin, Worcester phase 2	Worcester	WR5 3BX	Worcester	West Midlands	Before 2011	323†	Development completed	P05D0598	12/10/2005	29/11/2005	Residential	Yes	30	23/04/2007	0	30	Yes	Unknown	0	0	0	0	0	30	0	0	0	3	10	17	0
PSLR0339f	PLHP 1	DEFRA	Diglis Basin, Worcester phase 2	Worcester	WR5 3BX	Worcester	West Midlands	Before 2011	323†	Development completed	P13D0130	11/03/2013	05/07/2013	Residential	No	1	19/03/2012	0	2	Yes	No	0	0	0	0	0	2	0	0	2	0	0	0	0
PSLR0340	PLHP 1	DEFRA	Land at Barn Hall	Wickford, Essex	SS117FN	Basildon	East	Before 2011	200	Development completed	10/00481/REM	05/05/2010	23/12/2010	Residential	Yes	152	18/10/2011	0	56	Yes	Yes	0	0	0	0	53	51	5	0	12	27	16	0	1
PSLR0341	PLHP 1	DEFRA	Land at Epsom Road	Guildford	GU1 2RW	Guildford	South East	Before 2011	200	Development completed	08/P/01937	02/10/2008	20/02/2009	Residential	No	199	21/02/2012	0	199	Yes	Unknown	0	0	0	0	0	163	36	0	16	44	73	34	32
PSLR0342	PLHP 1	DEFRA	Granary Wharf	Leeds	LS1 4BR	Leeds	Yorkshire and The Humber	Before 2011	188	Development completed	20/190/05/FU	06/05/2005	26/10/2006	Mixed	No	282	21/02/2012	0	122	No	Yes	0	0	0	0	27	0	122	0	0	0	0	122	0
PSLR0343	PLHP 1	DEFRA	Site at Former RAF Tangmere	Lysander Way, Tangmere, Chichester	PO202GS	Chichester	South East	Before 2011	160	Development completed	14/02413/REM	08/08/2014	02/04/2015	Residential	No	160	19/04/2016	0	160	Yes	Unknown	0	0	0	0	0	124	31	5	22	65	35	38	0
PSLR0344	PLHP 1	DEFRA	Brooklands Avenue	Cambridge	CB2 8BZ	Cambridge	East	Before 2011	132	Development completed	C/02/0999,06/0524/REM,06/0527/REM,C/03/1166	26/09/2002	03/06/2003	Mixed,Infill,Infill,Infill	No,No,No,No	395	16/12/2004	0	379	Yes,Unknown,Unknown,Unknown	Yes,Unknown,Unknown,Unknown	0	0	0	0	114	216	159	4	0	0	226	153	0
PSLR0345	PLHP 1	DEFRA	Land at Barn Hall,	Wickford, Essex	SS117FN	Basildon	East	Before 2011	120	Development completed	10/00481/REM	05/05/2010	23/12/2010	Residential	Yes	152	18/10/2011	0	96	Yes	Yes	0	0	0	0	53	87	9	0	4	25	61	6	0
PSLR0347	PLHP 1	DEFRA	259, City Road	Islington	N1 7SA	Islington	London	Before 2011	100	Development completed	P092620	26/01/2010	02/03/2010	Mixed	No	304	09/12/2011	0	290	Yes	Yes	0	50	50	0	0	0	290	0	0	0	0	290	0
PSLR0348	PLHP 1	DEFRA	Tower Wharf, Chester	Chester	CH1 4EJ	Cheshire West and Chester	North West	Before 2011	88	Development completed	08/00045/FUL	08/01/2008	09/04/2008	Mixed	No	105	07/12/2010	0	111	Yes	Yes	0	0	46	0	0	0	111	0	0	0	0	111	0
PSLR0349a	PLHP 1	DEFRA	Land at HRI Littlehampton,	West Sussex	BN176FL	Arun	South East	Before 2011	65	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0350	PLHP 1	DEFRA	Branch Place	London	N1 5PH	Hackney	London	Before 2011	23	Development completed	2008/0237	05/03/2008	24/03/2009	Mixed	No	23	20/09/2011	0	23	Yes	No	0	0	0	0	0	0	23	0	0	0	0	23	0
PSLR0354	PLHP 1	DEFRA	Greenacres	Braunston	NN11 7JQ	Daventry	East Midlands	Before 2011	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Yes	No	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0355	PLHP 1	DfT	Stratford City, Plot S25	Monfichet Road, Stratford City	E20 1BY	Newham	London	2011/2012	214	Development started	11/90618/FUMODA	17/10/2011	30/03/2012	Residential institute	No	951	23/01/2015	0	170	Yes	No	0	0	0	0	0	0	0	170	0	0	0	0	170
PSLR0356	PLHP 1	DfT	Marks Tey: Site of Stanway Sidings	Halstead Road, Colchester	CO3 0JT	Colchester	East	2011/2012	123	Development completed	120848	04/05/2012	25/06/2013	Residential	No	123	07/10/2015	0	122	Yes	Yes	31	0	0	0	0	108	11	3	35	24	36	27	0
PSLR0357	PLHP 1	DfT	Bexhill: Former Galley Hill Sidings	Galley Hill View, Bexhill	TN401SX	Rother	South East	2011/2012	65	Development completed	RR/2011/2332/P	08/11/2011	15/03/2012	Residential	No	65	28/03/2013	0	65	Yes	Yes	0	25	0	0	0	57	8	0	13	6	38	8	0
PSLR0358	PLHP 1	DfT	Stafford: Land off Wolverhampton Road	Wolverhampton Road, Stafford	ST16 1BB	Stafford	West Midlands	2011/2012	50	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0359	PLHP 1	DfT	Brains Lane	SparkfordÃ‚Â Ã‚Â	BA22 7LA	South Somerset	South West	2011/2012	1	Planning stage	09/00987/FUL	09/03/2009	21/05/2010	Residential	No	1	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0360	PLHP 1	DfT	Angel Lane	Stratford City, Stratford, London	E20 1BY	Newham	London	2012/2013	274	Planning stage	16/02650/FUL	09/09/2016	22/12/2017	Commercial	Yes	0	x	x	x	No	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0361	PLHP 1	DfT	Hertford East: Coal yard	Mill Road, Hertford	SG137UB	East Hertfordshire	East	2012/2013	141	Development completed	3/15/0413/FUL	28/02/2015	19/11/2015	Mixed	No	120	01/12/2015	0	117	Yes	Yes	36	0	12	0	0	39	77	1	0	0	4	113	0
PSLR0362	PLHP 1	DfT	Hull Springbank: Land at Calvert Lane	Calvert Lane, Hull	HU4 6BU	Kingston upon Hull	Yorkshire and The Humber	2012/2013	120	Development completed	12/01108/RES	30/12/2012	05/03/2013	Residential	No	120	28/10/2013	0	120	Yes	No	0	0	0	0	0	118	0	2	47	42	30	1	0
PSLR0363	PLHP 1	DfT	Whitchurch: Former Goods Yard & Branch	Black Park Road, Whitchurch	SY13 1QA	Shropshire	West Midlands	2012/2013	40	Planning stage	13/01405/OUT	22/09/2015	x	Residential	No	40	x	x	x	No	Mix of pay and houses	3	0	2	0	0	x	x	x	x	x	x	x	x
PSLR0364a	PLHP 1	DfT	400 Caledonian Road	400 Caledonian Road, Islington	N1 1DN	Islington	London	2012/2013	23	Development completed	P072550	05/02/2008	03/03/2008	Residential	No	23	18/01/2016	0	25	Yes	Yes	0	8	3	0	0	0	25	0	0	0	2	23	0
PSLR0364b	PLHP 1	DfT	400 Caledonian Road	400 Caledonian Road, Islington	N1 1DN	Islington	London	2012/2013	23†	Planning stage	P2013/0327/FUL	13/02/2013	10/06/2013	Mixed	No	2	x	0	0	Not applicable	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0365	PLHP 1	DfT	Former goods yard, Gobowen	Opposite Gobowen Station, Gobowen	SY11 3JS	Shropshire	West Midlands	2012/2013	23	Development completed	13/04953/FUL	12/12/2013	11/09/2014	Residential	No	22	06/04/2016	0	22	Yes	Yes	0	0	0	0	22	0	0	22	0	10	4	8	0
PSLR0366	PLHP 1	DfT	Tadworth: British Transport Police Training Centre	Sandlands Grove, Epsom, Surrey	KT207UZ	Reigate and Banstead	South East	2012/2013	14	Development completed	12/01885/F	14/11/2012	24/01/2013	Residential	No	13	09/06/2014	0	13	Yes	No	0	0	0	0	0	13	0	0	13	0	0	0	0
PSLR0367	PLHP 1	DfT	Prince Of Wales Public House	Stourbridge Road, Hagley, Worcestershire County	DY9 0QB	Bromsgrove	West Midlands	2012/2013	12	Development completed	13/0304	25/04/2013	27/03/2014	Residential	No	12	05/02/2015	0	5	No	No	0	0	0	0	0	4	0	1	2	3	0	0	0
PSLR0368	PLHP 1	DfT	Swinton: Site of Electric House	Manchester	M27 4FA	Salford	North West	2012/2013	7	Development completed	12/61563/FUL	19/03/2012	01/06/2012	Residential	No	7	03/10/2014	0	7	Yes	No	0	0	0	0	0	0	7	0	0	0	7	0	0
PSLR0369	PLHP 1	DfT	Wivelsfield: Land to rear of Valebridge Road	Valebridge Road, Burgess Hill, East Sussex	RH150RZ	Mid Sussex	South East	2012/2013	6	Planning stage	14/00080/FUL	13/01/2014	x	Residential	No	9	x	x	x	No	No	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0370	PLHP 1	DfT	Wivelsfield: Land at Keymer Jn (east of line)	East Sussex	RH158BQ	Mid Sussex	South East	2012/2013	5	Planning stage	DM/18/3151	31/07/2018	x	Residential	No	4	x	x	x	No	No	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0371	PLHP 1	DfT	351 Caledonian Road	351 Caledonian Road, Islington	N1 1DW	Islington	London	2013/2014	156	Development completed	P2014/0609/FUL	05/03/2014	20/07/2015	Residential	No	156	20/08/2018	0	156	Yes	Yes	0	60	4	0	0	0	156	0	0	0	0	156	0
PSLR0372	PLHP 1	DfT	Winterstoke Road, Weston super Mare	Weston super Mare	BS23 3YS	North Somerset	South West	2013/2014	100	Development completed	13/P/1876/F	26/09/2013	27/05/2014	Residential	Unknown	24	06/03/2015	0	24	Yes	Yes	0	24	0	0	0	24	0	0	0	0	0	0	24
PSLR0374	PLHP 1	DfT	Chobham Farm North 4	Leyton Road, Stratford, London	E15 1AA	Newham	London	2014/2015	477	Development started	15/00266/REM	10/06/2015	19/11/2015	Mixed	No	471	29/10/2018	0	430	Yes	Yes	109	0	65	0	0	148	264	18	0	0	0	430	0
PSLR0375	PLHP 1	DfT	Glasshouse Gardens, Zone 2, Stratford City	Stratford City, Stratford, London	E20 1AS	Newham	London	2014/2015	333	Development completed	13/00409/REM	02/09/2013	23/01/2014	Residential	No	333	28/03/2017	0	333	Yes	No	0	0	0	0	0	0	331	2	0	0	0	331	2
PSLR0376	PLHP 1	DfT	Chobham Farm North 1	Leyton Road, Stratford, London	E15 1AA	Newham	London	2014/2015	65	Development completed	12/00146/FUM	12/09/2012	28/02/2014	Mixed	Yes	173	21/03/2017	0	44	No	Yes	0	23	15	0	0	6	38	0	0	0	6	38	0
PSLR0377	PLHP 1	DfT	The Barns at Radnalls	Chieveley Newbury Berkshire	RG20 8XF	West Berkshire	South East	2014/2015	2	Planning stage	13/00525/FULD	22/03/2013	05/09/2013	Residential	No	2	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0378	PLHP 1	DfT	Land at Hunter's Yard	Ashford Kent	TN240US	Ashford	South East	Before 2011	272	Development completed	07/02294/AS	20/12/2007	13/03/2009	Residential	Unknown	350	21/10/2009	0	341	Yes	Mix of pay and houses	0	0	7	0	90	187	154	0	1	2	159	178	1
PSLR0379	PLHP 1	DfT	Yate Stores, Yate: Land At Sea Stores	Kennedy Way, Yate, Bristol	BS37 4DQ	South Gloucestershire	South West	Before 2011	178	Development completed	PK09/1388/F	15/07/2009	27/09/2010	Residential	No	228	11/03/2011	0	228	Yes	Yes	0	60	16	0	0	162	66	0	8	61	82	77	0
PSLR0380	PLHP 1	DfT	Plot T6	King's Cross Opportunity Area, York Way	N1C 4AJ	Camden	London	Before 2011	172	Development completed	2010/4468/P	25/08/2010	11/01/2011	Residential institute	No	669	30/08/2013	0	196	Yes	No	0	0	0	0	0	0	0	196	0	0	0	193	3
PSLR0381	PLHP 1	DfT	New Cross Gate: Land at Goodwood Road/New Cross Road	Lewisham	SE14 6BL	Lewisham	London	Before 2011	160	Planning stage	DC/11/077418/X	01/06/2011	16/03/2012	Residential	No	148	x	x	x	Unknown	Yes	0	0	15	0	0	x	x	x	x	x	x	x	x
PSLR0382	PLHP 1	DfT	Tweedmouth: Former Goods Yard	Tweedmouth	TD152AW	Northumberland	North East	Before 2011	120	Planning stage	11/02030/OUT	22/04/2015	02/09/2016	Residential	No	71	x	0	0	Yes	Yes	7	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0383	PLHP 1	DfT	South Tottenham: Land to rear of Plevna Crescent	Haringey	N15 6DW	Haringey	London	Before 2011	107	Planning stage	HGY/2017/2036	26/06/2017	05/04/2018	Residential	Unknown	72	x	0	0	Yes	Yes	4	0	10	0	0	0	0	0	0	0	0	0	0
PSLR0384	PLHP 1	DfT	Plot R5Ã‚Â (North)	King's Cross Opportunity Area, York Way	N1C 4AD	Camden	London	Before 2011	105	Development completed	2011/0431/P	31/01/2011	08/04/2011	Mixed	Yes	144	04/03/2013	0	144	Yes	Unknown	0	0	0	0	0	0	143	1	0	0	0	143	1
PSLR0385	PLHP 1	DfT	Plot J (2)	King's Cross Opportunity Area, York Way	N1C 4AA	Camden	London	Before 2011	104	Development completed	2010/6688/P	14/12/2010	11/03/2011	Residential	Yes	143	29/11/2013	0	144	Yes	Yes	0	29	0	0	0	91	27	26	0	0	0	144	0
PSLR0386	PLHP 1	DfT	Coal Yard	Kesteven Street, Lincoln	LN5 7ED	Lincoln	East Midlands	Before 2011	100	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0387	PLHP 1	DfT	Severn Beach: Former Goods Yard	Severn Beach, Bristol	BS354PT	South Gloucestershire	South West	Before 2011	97	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0388	PLHP 1	DfT	Nuneaton: Abbey Sidings	Nuneaton	CV115EG	Nuneaton and Bedworth	West Midlands	Before 2011	90	Development started	33374	28/04/2015	05/07/2015	Residential	No	84	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0389	PLHP 1	DfT	Plot R4	King's Cross Opportunity Area, York Way	N1C 4AD	Camden	London	Before 2011	85	Development completed	2010/0389/P	26/01/2010	15/04/2010	Residential	Yes	117	06/11/2012	0	117	Yes	Yes	0	78	24	0	15	38	79	0	0	0	0	117	0
PSLR0390	PLHP 1	DfT	Workington: Goods Yard	Workington	CA142XJ	Allerdale	North West	Before 2011	72	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0391	PLHP 1	DfT	Folkestone East: Former goods yard	Folkestone	CT196DD	Folkestone and Hythe	South East	Before 2011	50	Planning stage	Y14/0928/SH	13/08/2014	29/06/2016	Mixed	No	41	x	0	0	No	Yes	0	0	0	0	12	0	0	0	0	0	0	0	0
PSLR0392	PLHP 1	DfT	Stonehouse: Former Goods Yard and Branch Line	Stonehouse	GL103PJ	Stroud	South West	Before 2011	48	Development started	S.16/0922/REM	25/04/2016	24/11/2016	Residential	No	49	25/05/2018	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0394	PLHP 1	DfT	Greenford: Station yard	Greenford	UB6 0FD	Ealing	London	Before 2011	41	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0395	PLHP 1	DfT	Stapleford & Sandiacre: Part of former Toton marshalling yard	Toton	NG9 6JA	Broxtowe	East Midlands	Before 2011	40	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0396	PLHP 1	DfT	Iver: Land east of Hollow Hill Lane (part in Berks)	Iver	SL0 9HF	Slough	South East	Before 2011	40	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Not applicable	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0397	PLHP 1	DfT	Frome: Former East Goods Yard	Frome	BA111RE	Mendip	South West	Before 2011	35	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0398	PLHP 1	DfT	Harling Road: Former goods yard	Norwich	NR162QP	Breckland	East	Before 2011	34	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0399	PLHP 1	DfT	Crewkerne: Coal Yard	Crewkerne	TA188LW	South Somerset	South West	Before 2011	31	Development started	14/02913/REM	10/07/2014	03/02/2017	Residential	No	16	05/11/2018	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0400	PLHP 1	DfT	Elstree: Former goods yard	Borehamwood	WD6 3HU	Hertsmere	East	Before 2011	30	Development completed	TP/10/2095	19/10/2010	19/05/2011	Residential	No	74	03/08/2013	0	59	Yes	Yes	11	3	11	0	0	0	45	14	0	0	0	56	3
PSLR0401	PLHP 1	DfT	Walkden: Closed line at Little Hulton	Walkden	M38 9DZ	Salford	North West	Before 2011	29	Development completed	13/63301/FUL	18/05/2013	19/08/2013	Residential	No	30	12/02/2015	0	26	No	No	0	0	0	0	0	0	0	26	0	2	12	12	0
PSLR0402	PLHP 1	DfT	Silverdale: Former Goods Yard	Newcastle-upon-Tyne	ST5 6JS	Newcastle-under-Lyme	West Midlands	Before 2011	26	Development completed	11/00284/FUL	08/07/2011	18/02/2013	Residential	No	23	17/08/2018	0	23	Yes	No	0	0	0	0	0	23	0	0	1	10	12	0	0
PSLR0403	PLHP 1	DfT	Wilnecote: Former Goods Yard	Wilnecote	B77 1EF	Tamworth	West Midlands	Before 2011	26	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Not applicable	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0404	PLHP 1	DfT	Henbury: Former Goods Yard	Henbury, Bristol	BS107LR	South Gloucestershire	South West	Before 2011	25	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0405a	PLHP 1	DfT	Tunbridge Wells: Former goods yard	Tunbridge Wells	TN1 2FB	Tunbridge Wells	South East	Before 2011	25	Development completed	09/01312/FULMJ	05/05/2009	27/08/2009	Residential	Yes	150	16/02/2010	0	12	No	Yes	0	0	0	0	45	0	12	0	0	0	0	12	0
PSLR0405b	PLHP 1	DfT	Tunbridge Wells: Former goods yard	Tunbridge Wells	TN1 2FB	Tunbridge Wells	South East	Before 2011	25†	Development completed	06/01969/FULMJ	03/07/2006	10/04/2007	Residential	Yes	94	03/10/2008	0	94	Yes	Yes	21	0	8	0	0	25	69	0	0	2	4	88	0
PSLR0406	PLHP 1	DfT	Patchway: Land at Station Road	Patchway, Bristol	BS346LR	South Gloucestershire	South West	Before 2011	21	Planning stage	PT18/3922/O	23/08/2018	26/07/2019	Commercial	Yes	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0407	PLHP 1	DfT	Southall: Land at Park Avenue,Ã‚Â West Site	Southall	UB1 3AQ	Ealing	London	Before 2011	20	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0408	PLHP 1	DfT	Lydd: Former station and yard	Lydd	TN299JX	Folkestone and Hythe	South East	Before 2011	20	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0409	PLHP 1	DfT	Ware: Land at Crane Mead Road	Ware	SG129PZ	East Hertfordshire	East	Before 2011	18	Planning stage	3/14/1408/FP	31/07/2014	12/11/2014	Mixed	No	101	x	0	0	No	Yes	15	0	86	0	0	0	0	0	0	0	0	0	0
PSLR0410	PLHP 1	DfT	Alresford: Station Yard	Alresford	CO7 8BN	Tendring	East	Before 2011	14	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0411	PLHP 1	DfT	Lowestoft: Former goods yard, Denmark Road	Lowestoft	NR322ED	Waveney	East	Before 2011	13	Planning stage	DC/16/3844/OUT	14/09/2016	15/12/2016	Commercial	Yes	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0412	PLHP 1	DfT	Gateshead: Land east of St. James Road	Gateshead	NE8 3BU	Gateshead	North East	Before 2011	12	Development started	587/00	06/09/2000	09/01/2001	Mixed	Yes	1018	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0413	PLHP 1	DfT	Yatton: Former Goods Yard & part of Clevedon Branch	Yatton	BS49 4BP	North Somerset	South West	Before 2011	12	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0414	PLHP 1	DfT	Land at Arbour Lane	Chelmsford	CM1 7QY	Chelmsford	East	Before 2011	11	Development completed	10/00693/REM	29/04/2010	03/08/2010	Residential	No	11	15/04/2011	0	11	Yes	No	0	0	0	0	0	11	0	0	3	0	8	0	0
PSLR0415a	PLHP 1	DfT	Jeans Way	Dunstable	LU5 4FD	Central Bedfordshire	East	Before 2011	10	Development completed	CB/11/04135/OUT	28/11/2011	25/09/2012	Residential	No	8	29/11/2013	0	4	No	No	0	0	0	0	0	4	0	0	0	4	0	0	0
PSLR0415b	PLHP 1	DfT	Jeans Way	Dunstable	LU5 4FD	Central Bedfordshire	East	Before 2011	10†	Development completed	CB/14/03727/FULL	22/09/2014	26/11/2014	Residential	No	3	04/05/2016	0	3	Yes	No	0	0	0	0	0	3	0	0	3	0	0	0	0
PSLR0415c	PLHP 1	DfT	Jeans Way	Dunstable	LU5 4FD	Central Bedfordshire	East	Before 2011	10†	Development completed	CB/15/03247/FULL	22/09/2015	13/06/2016	Residential	No	2	21/04/2017	0	2	Yes	No	0	0	0	0	0	2	0	0	2	0	0	0	0
PSLR0416	PLHP 1	DfT	Corkickle Goods Yard	Coach Road, Whitehaven	CA287TQ	Copeland	North West	Before 2011	8	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0417	PLHP 1	DfT	Whittlesey: Former goods yard,	Station Road, Whittlesey	PE7 1NH	Fenland	East	Before 2011	8	Planning stage	F/YR17/0450/F	02/05/2017	17/07/2017	Commercial	No	0	x	x	x	No	No	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0418	PLHP 1	DfT	96 Springhead Road.	Northfleet, Kent	DA11 9QY	Gravesham	South East	Before 2011	7	Development completed	20120254	20/03/2012	24/05/2012	Residential	No	8	13/11/2014	0	8	Yes	No	0	0	0	0	0	8	0	0	1	4	3	0	0
PSLR0419	PLHP 1	DfT	Ryde St John's Road: Land	Ryde	PO331FL	Isle of Wight	South East	Before 2011	6	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0420	PLHP 1	DfT	March: Land by station	March	PE158SJ	Fenland	East	Before 2011	5	Planning stage	F/YR16/0364/O	17/03/2016	22/12/2017	Residential	Yes	34	x	0	0	No	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0421	PLHP 1	DfT	9 Navarino Grove	Hackney	E8 1AJ	Hackney	London	Before 2011	5	Planning stage	2016/2242	20/07/2016	05/09/2017	Residential	No	21	x	0	0	No	Yes	0	0	9	0	0	0	0	0	0	0	0	0	0
PSLR0422	PLHP 1	DfT	South Tottenham: Land to rear of Ermine Road	Haringey	N15 6DW	Haringey	London	Before 2011	5	Planning stage	HGY/2017/3586	15/11/2017	09/09/2019	Residential	Unknown	6	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0423	PLHP 1	DfT	Caterham: Land to rear of Stafford Road	Caterham	CR3 6JA	Tandridge	South East	Before 2011	4	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0424	PLHP 1	GLA	CIQ phase 1	62 - 92 Abbey Road, Barking	IG11 7BT	Barking and Dagenham	London	2011/2012	134	Development started	10/01038/FUL	29/11/2010	31/03/2011	Mixed	Yes	278	20/02/2015	0	64	Yes	Yes	0	23	30	0	0	63	1	0	0	0	0	64	0
PSLR0425	PLHP 1	GLA	Cane Hill	Brighton Road, Coulsdon	CR5 3QA	Croydon	London	2012/2013	650	Development started	13/02527/P	10/01/2017	09/03/2017	Mixed	No	677	21/03/2016	0	661	Yes	Yes	98	0	65	0	0	511	119	31	253	248	55	91	14
PSLR0426	PLHP 1	GLA	Saint Clements	Tower Hamlets	E3 4QL	Tower Hamlets	London	2012/2013	223	Development completed	PA/13/01532/A1	01/07/2013	20/06/2014	Mixed	No	252	22/02/2016	0	257	Yes	Yes	0	51	23	0	0	65	188	4	1	0	3	253	0
PSLR0427	PLHP 1	GLA	Amberley Residential	New Road, Rainham	RM13 8QN	Havering	London	2012/2013	50	Development completed	P1534.12	14/12/2012	15/03/2013	Residential	No	51	30/07/2015	0	51	Yes	Yes	0	0	0	0	26	0	0	51	0	0	34	17	0
PSLR0428	PLHP 1	GLA	Land at Barking Riverside	Barking	IG110XL	Barking and Dagenham	London	2012/2013	33	Development completed	13/00171/REM	04/03/2013	29/05/2013	Mixed	No	83	23/09/2014	0	83	Yes	Unknown	0	0	0	0	0	0	82	1	0	0	12	71	0
PSLR0430	PLHP 1	GLA	Newington Butts	Southwark	SE11 4RB	Southwark	London	2013/2014	457	Development completed	14/AP/2207	23/06/2014	05/11/2014	Residential	No	470	23/11/2017	0	467	Yes	Yes	86	0	64	0	29	0	338	129	0	0	0	467	0
PSLR0431	PLHP 1	GLA	Lymington Fields Plots 1B and 2	Chadwell Heath, London, RM8 1EL.	RM8 1EL	Barking and Dagenham	London	2013/2014	362	Development started	12/00170/FUL	01/03/2012	22/03/2013	Mixed	Yes	602	05/01/2015	0	415	No	Yes	0	125	86	0	0	269	131	15	0	30	279	106	0
PSLR0432	PLHP 1	GLA	CIQ phase 2	94 - 98 Abbey Road, Barking	IG11 7BT	Barking and Dagenham	London	2013/2014	138	Development started	10/01038/FUL	29/11/2010	31/03/2011	Mixed	Yes	278	03/05/2016	0	146	Yes	Yes	0	23	30	0	0	0	0	146	0	0	2	144	0
PSLR0433	PLHP 1	GLA	Rainham Interchange	Ferry Lane, Rainham	RM13 9YH	Havering	London	2013/2014	16	Development completed	U0018.09	21/12/2009	22/07/2010	Mixed	No	16	03/09/2014	0	16	Yes	Unknown	0	0	0	0	0	0	16	0	0	0	0	16	0
PSLR0434	PLHP 1	DHSC	1 - 18 Springwood Close	Maidstone	ME16 9PA	Maidstone	South East	2013/2014	17	Development completed	x	x	x	Residential sale	No	17	x	x	17	Not applicable	Unknown	0	0	0	0	0	x	x	17	x	x	x	x	17
PSLR0435	PLHP 1	DHSC	1 - 21 Heatherstones	Queensgate, Halifax	HX3 0DH	Calderdale	Yorkshire and The Humber	2013/2014	21	Development completed	13/01303/FUL	21/10/2013	17/12/2013	Residential	No	25	19/03/2012	0	26	Yes	No	0	0	0	0	0	14	12	0	0	0	13	12	1
PSLR0436	PLHP 1	DHSC	1 Rosebury Avenue	1 Rosebery Avenue, Eastbourne, East Sussex	BN22 9PY	Eastbourne	South East	2013/2014	1	Development completed	141199	15/09/2014	06/11/2014	Residential	No	1	04/01/2016	0	1	Yes	No	0	0	0	0	0	0	0	1	0	0	0	1	0
PSLR0437	PLHP 1	DHSC	12 Black Heath	12 Black Heath Road, Colchester	CO2 0AE	Colchester	East	2012/2013	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0438	PLHP 1	DHSC	14 Clovelly Road	Bideford	EX39 3BU	Torridge	South West	2014/2015	1	Development started	1/1089/2014/FUL	21/10/2014	06/01/2015	Residential institute	No	5	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	0	0	0	0	1
PSLR0439	PLHP 1	DHSC	1-5 Larkey View	Chartham, Canterbury,Kent,	CT4 7PR	Canterbury	South East	2013/2014	5	Development completed	x	x	x	Residential sale	No	5	x	x	5	Not applicable	Unknown	0	0	0	0	0	x	x	5	x	x	x	x	5
PSLR0440	PLHP 1	DHSC	16A Cleveland Street	16 Cleveland Street	W1T 5HX	Camden	London	2013/2014	1	Development completed	2014/4508/P	02/09/2014	03/09/2015	Residential	No	2	15/11/2017	0	2	Yes	No	0	0	0	0	0	0	0	2	0	0	0	2	0
PSLR0441	PLHP 1	DHSC	17 Castle Street	Worcester	WR1 3AD	Worcester	West Midlands	2013/2014	1	Planning stage	P14D0487	15/10/2014	31/12/2014	Residential	No	11	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0442	PLHP 1	DHSC	17 Paddington Green	Westminster	W2 1LQ	Westminster	London	2014/2015	6	Development started	16/11562/FUL	06/12/2016	21/12/2017	Residential	Yes	200	x	0	0	Yes	Mix of pay and houses	0	12	27	0	0	0	0	0	0	0	0	0	0
PSLR0443	PLHP 1	DHSC	18 Epsom Road	Guildford	GU1 2EJ	Guildford	South East	2013/2014	10	Development started	14/P/01544	15/08/2014	23/12/2014	Residential	No	12	22/11/2017	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0444	PLHP 1	DHSC	186 Heene Road	Kendal House, 186-188 Heene Road	BN11 4NY	Worthing	South East	2014/2015	2	Development completed	AWDM/0382/14	24/03/2014	15/05/2014	Residential	No	2	19/03/2012	0	2	Yes	No	0	0	0	0	0	2	0	0	0	2	0	0	0
PSLR0445	PLHP 1	DHSC	21-22 Vicarage Drive, Eastbourne	Eastbourne, East Sussex	BN20 8AR	Eastbourne	South East	2014/2015	2	Development completed	141280	09/10/2014	10/12/2014	Residential	No	2	19/03/2012	0	2	Yes	No	0	0	0	0	0	2	0	0	0	0	0	0	2
PSLR0446	PLHP 1	DHSC	26 Charlton Road, Shepton Mallet, Somerset	Shepton Mallet	BA4 5NZ	Mendip	South West	Before 2011	7	Development started	030734/007	10/06/2008	28/06/2008	Residential	No	7	10/08/2016	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0447	PLHP 1	DHSC	2-6 Heathway	Seaham	SR7 7UH	County Durham	North East	2012/2013	3	Development completed	x	x	x	Residential sale	No	3	x	x	3	Not applicable	Unknown	0	0	0	0	0	x	x	3	x	x	x	x	3
PSLR0448	PLHP 1	DHSC	3 Daisy Bank, Lancaster	Lancaster	LA1 3JR	Lancaster	North West	2014/2015	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0449	PLHP 1	DHSC	3 Delenty Drive	3 Delenty Drive, Birchwood, Warrington	WA3 6AN	Warrington	North West	2014/2015	10	Development started	2015/25391	05/03/2015	23/04/2015	Residential	No	9	06/01/2017	0	2	No	No	0	0	0	0	0	0	0	2	2	0	0	0	0
PSLR0450	PLHP 1	DHSC	3 Windlesham Road	3 Windlesham Road, Brighton	BN1 3AG	Brighton and Hove	South East	2014/2015	1	Development completed	BH2014/01565	13/05/2014	05/08/2014	Residential	No	1	21/02/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0451b	PLHP 1	DHSC	31 Boundary Place	Corse, Staunton	GL19 3RG	Forest of Dean	South West	2012/2013	1	Development completed	P1469/12/FUL,P0286/13/FUL	12/10/2012	20/12/2012	Residential,Infill	No,No	2	19/03/2012	0	2	Yes,Yes	No,No	0	0	0	0	0	2	0	0	1	0	0	0	1
PSLR0452	PLHP 1	DHSC	32-34 Kimbolton Road	32-34 Kimbolton Road, Bedford	MK40 2NT	Bedford	East	2013/2014	6	Development completed	17/02151/MAF	25/07/2017	23/10/2017	Residential	No	11	25/04/2019	0	11	Yes	No	0	0	0	0	0	0	0	11	0	0	0	11	0
PSLR0453	PLHP 1	DHSC	34 Danby Terrace	34 Danby Terrace, Exmouth	EX8 1QS	East Devon	South West	2013/2014	1	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0454	PLHP 1	DHSC	354 Lodge Causeway	352-354 Lodge Causeway, Bristol	BS16 3PL	Bristol	South West	2012/2013	2	Development completed	13/01732/F	18/04/2013	13/06/2013	Mixed	No	5	15/12/2014	0	5	Yes	No	0	0	0	0	0	1	0	4	1	0	0	4	0
PSLR0455	PLHP 1	DHSC	38 West Cliff road, Ramsgate	38 West Cliff Road, Ramsgate	CT11 9NT	Thanet	South East	2012/2013	1	Development completed	F/TH/12/0574	16/07/2012	27/09/2012	Residential	No	1	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	0	1	0	0	0
PSLR0456	PLHP 1	DHSC	39 Osmond Road	39 Osmond Road, Hove	BN3 1TD	Brighton and Hove	South East	2014/2015	1	Development completed	BH2014/01487	07/05/2014	30/07/2014	Residential	No	1	21/02/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0457	PLHP 1	DHSC	47 Boulevard	47 The Boulevard, Weston-Super-Mare	BS23 1PG	North Somerset	South West	2011/2012	2	Development completed	12/P/2007/F	08/11/2012	21/12/2012	Residential	No	2	11/04/2016	0	2	Yes	No	0	0	0	0	0	0	0	2	0	0	0	2	0
PSLR0458	PLHP 1	DHSC	5 Highfield Road	5 Highfield Road, Purley, Surrey	CR8 2JJ	Croydon	London	2013/2014	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0459	PLHP 1	DHSC	50 Scattergate Green, Appleby	50 Scattergate Green, Appleby	CA166SP	Eden	North West	2011/2012	1	Development completed	x	x	x	Residential sale	Unknown	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0460	PLHP 1	DHSC	57 Manchester Road	57 Manchester Road, Southport	PR9 9BN	Sefton	North West	2013/2014	1	Development completed	DC/2014/02207	22/12/2014	16/02/2015	Residential	No	4	20/04/2015	0	4	Yes	No	0	0	0	0	0	4	0	0	0	0	0	3	1
PSLR0461	PLHP 1	DHSC	63 Newby Drive	63 Newby Drive, Huyton	L36 2QT	Knowsley	North West	2014/2015	4	Development completed	x	x	x	Residential sale	No	4	x	x	4	Not applicable	Unknown	0	0	0	0	0	x	x	4	x	x	x	x	4
PSLR0462	PLHP 1	DHSC	64 St Thomas RdÃ‚Â	64 St Thomas Road Road, Spalding	PE11 2XT	South Holland	East Midlands	2011/2012	1	Development completed	H16-0746-11	28/09/2011	15/11/2011	Residential	No	1	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	0	1	0	0	0
PSLR0463	PLHP 1	DHSC	6-9 Larkey View	Chartham, Nr. Canterbury, Kent	CT4 7PR	Canterbury	South East	2012/2013	4	Development completed	x	x	x	Residential sale	Unknown	4	x	x	4	Not applicable	Unknown	0	0	0	0	0	x	x	4	x	x	x	x	4
PSLR0464	PLHP 1	DHSC	69 Oakley Square	69 Oakley Square, London. Greater London	NW1 1NJ	Camden	London	2013/2014	6	Development started	2013/5652/P	17/09/2013	21/11/2013	Residential	No	3	06/01/2015	0	2	Yes	No	0	0	0	0	0	0	0	2	0	0	0	2	0
PSLR0465	PLHP 1	DHSC	7 Craven Road	7 Craven Road, Reading	RG1 5LE	Reading	South East	2013/2014	1	Development completed	131249	05/09/2013	24/01/2014	Residential	No	1	19/03/2012	0	1	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0466	PLHP 1	DHSC	78 London Road	78 London Road, Croydon	CR0 2TB	Croydon	London	2013/2014	3	Planning stage	15/04659/P	16/10/2015	11/12/2015	Residential	No	3	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0467	PLHP 1	DHSC	87 London Road	Sittingbourne	ME10 1NL	Swale	South East	2012/2013	4	Planning stage	14/500615/FULL	18/06/2014	x	Residential institute	No	32	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0468	PLHP 1	DHSC	96 Croydon Road	96 Croydon Road	SE20 7AB	Bromley	London	2013/2014	2	Development completed	14/02484/FULL1	24/06/2014	07/11/2014	Residential	No	2	19/03/2012	0	2	Yes	No	0	0	0	0	0	0	2	0	0	0	0	2	0
PSLR0469	PLHP 1	DHSC	Abbey Road Clinic	Abbey Road. Blackpool	FY4 2LW	Blackpool	North West	2014/2015	6	Development completed	15/0679	06/10/2015	15/01/2016	Residential	No	6	11/01/2018	0	6	Yes	No	0	0	0	0	0	0	0	6	0	6	0	0	0
PSLR0470b	PLHP 1	DHSC	Abbot's Lodge	Abbey Hill, Netley Abbey, Southampton, Hampshire	SO31 5FA	Eastleigh	South East	2012/2013	1	Development completed	C/14/73873	08/01/2014	28/03/2014	Residential	No	9	11/04/2016	0	9	No	No	0	0	0	0	0	0	8	1	0	0	0	1	8
PSLR0471	PLHP 1	DHSC	Aberford Field	Aberford Road, Wakefield, West Yorkshire	WF1 4AL	Wakefield	Yorkshire and The Humber	2014/2015	66	Development started	13/02623/HYB	10/09/2013	22/08/2014	Residential	Yes	329	21/05/2017	0	73	No	Unknown	0	0	0	0	0	62	1	10	38	15	19	0	1
PSLR0472	PLHP 1	DHSC	Acer House	97-101 East Street, Epsom, Surrey	KT17 1EA	Epsom and Ewell	South East	2013/2014	6	Development completed	14/01837/FUL	03/09/2014	03/12/2014	Residential	No	13	02/12/2016	0	13	Yes	No	0	0	0	0	0	0	13	0	0	0	0	13	0
PSLR0473	PLHP 1	DHSC	Acorn Lodge	Sevenoaks Road, Cosham, Portsmouth	PO6 3PH	Portsmouth	South East	2014/2015	8	Development completed	14/01563/FUL	02/12/2014	22/01/2015	Residential	No	7	22/02/2016	0	7	Yes	No	0	0	0	0	0	7	0	0	0	0	0	7	0
PSLR0474	PLHP 1	DHSC	Adwick Road	Mexborough Dental Clinic, Mexborough	S64 0DB	Doncaster	Yorkshire and The Humber	2013/2014	3	Planning stage	14/02699/FUL	14/11/2014	07/01/2015	Commercial	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0475	PLHP 1	DHSC	Albion Mill Site	Water Street, Great Harwood, Great Harwood, Lancashire	BB6 7QR	Hyndburn	North West	2014/2015	22	Planning stage	11/15/0432	17/12/2015	20/04/2016	Residential	No	12	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0476	PLHP 1	DHSC	Alcester Hospital	Kinwharton Road, Alcester, Warwickshire	B49 6PX	Stratford-on-Avon	West Midlands	2013/2014	40	Development completed	14/02929/FUL	24/10/2014	31/05/2016	Residential	No	39	11/09/2017	0	39	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	5	33	1	0	0	0	0	39
PSLR0477	PLHP 1	DHSC	All Saints House	47 & 49 All Saints Road Bromsgrove Worcestershire	B610AQ	Bromsgrove	West Midlands	2014/2015	2	Development completed	15/1037	07/12/2015	23/03/2016	Residential	No	2	19/03/2012	0	2	Yes	No	0	0	0	0	0	2	0	0	0	2	0	0	0
PSLR0478	PLHP 1	DHSC	Alma Road Primary Care Centre	Peterborough	PE1 3FG	Peterborough	East	2014/2015	26	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0479	PLHP 1	DHSC	Almond Road Dental Clinic	Almond Rd, St Neots	PE19 1DZ	Huntingdonshire	East	2014/2015	6	Planning stage	1401988FUL	22/01/2015	18/03/2015	Commercial	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0481	PLHP 1	DHSC	Alston Clinic	Dene View, Overwater, Nenthead	CA9 3NP	Eden	North West	2012/2013	1	Development completed	12/0944	07/11/2012	13/06/2013	Residential	No	1	06/05/2016	0	1	Yes	No	0	0	0	0	0	0	1	0	0	0	1	0	0
PSLR0482	PLHP 1	DHSC	Amersham Hospital	70-78 Whielden Street, Amersham, Bucks	HP7 0JD	Chiltern	South East	2011/2012	12	Development started	CH/2013/1543/FA	17/09/2013	12/11/2013	Residential	No	8	22/02/2016	0	7	Yes	No	0	0	0	0	0	7	0	0	0	0	0	0	7
PSLR0483	PLHP 1	DHSC	Angus House	Church Approach Cudham	TN14 7QF	Bromley	London	2011/2012	4	Development completed	11/02727/FULL1	06/09/2011	13/12/2011	Residential	No	4	04/09/2012	0	4	Yes	No	0	0	0	0	0	4	0	0	2	2	0	0	0
PSLR0484	PLHP 1	DHSC	Arton Wilson House Site	Wandsworth	SW155FP	Wandsworth	London	Before 2011	100	Development completed	2010/3273	28/07/2010	31/03/2011	Residential	No	134	28/05/2013	0	129	No	Yes	0	3	18	0	0	35	91	3	0	0	38	91	0
PSLR0486	PLHP 1	DHSC	Ashley Road	43 Ashley Road,	N19 3AG	Islington	London	2013/2014	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0487	PLHP 1	DHSC	Aston Hall Hospital - Lot 2 (Development Land)	Aston on Trent	DE72 2DF	South Derbyshire	East Midlands	Before 2011	200	Development started	9/2014/0232	07/03/2014	17/09/2014	Residential institute	No	259	25/10/2016	0	163	Yes	Yes	0	0	6	0	16	59	104	0	27	9	2	125	0
PSLR0488	PLHP 1	DHSC	Astor House	12 Oakwood Avenue Purley Surrey	CR8 1AQ	Croydon	London	2013/2014	1	Development completed	13/03202/P	23/09/2013	20/11/2013	Residential	No	1	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	0	0	0	0	1
PSLR0489	PLHP 1	DHSC	Atherton Clinic	Atherton	M46 0HQ	Wigan	North West	2014/2015	7	Development started	A/15/80284/MAJOR	19/01/2015	11/05/2015	Residential	No	11	06/04/2016	0	9	Yes	No	0	0	0	0	0	0	9	0	1	8	0	0	0
PSLR0490	PLHP 1	DHSC	Auckland Road	Scunthorpe	DN15 7BT	North Lincolnshire	Yorkshire and The Humber	2013/2014	1	Development completed	x	x	x	Residential sale	Unknown	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0491	PLHP 1	DHSC	Auckland Road Clinic	Auckland Road, Cambridge	CB5 8DW	Cambridge	East	2014/2015	5	Development completed	14/0978/FUL	20/06/2014	22/01/2015	Residential	No	5	15/09/2016	0	5	Yes	No	0	0	0	0	0	5	0	0	1	4	0	0	0
PSLR0492	PLHP 1	DHSC	Balderton Hospital	Balderton	NG24 3US	Newark and Sherwood	East Midlands	Before 2011	60	Development completed	00/50004/RMA	22/12/1999	10/04/2000	Residential	No	53	03/01/2002	0	53	Yes	Unknown	0	0	0	0	0	53	0	0	20	8	25	0	0
PSLR0493	PLHP 1	DHSC	Balsall Common Clinic	148 Station Road, Balsall Common, Coventry	CV7 7FF	Solihull	West Midlands	2013/2014	1	Development completed	PL/2013/00927/FULL	13/08/2013	30/09/2013	Residential	No	4	19/09/2016	0	4	Yes	No	0	0	0	0	0	4	0	0	0	4	0	0	0
PSLR0494	PLHP 1	DHSC	Baltic Road Clinic	2 Baltic Road, Tonbridge	TN9 2NA	Tonbridge and Malling	South East	2014/2015	4	Development completed	15/01350/FL	23/04/2015	05/08/2015	Residential	No	6	18/04/2016	0	6	Yes	No	0	0	0	0	0	0	6	0	0	0	0	6	0
PSLR0495	PLHP 1	DHSC	Banbury Ambulance Station	Cope Road, Banbury, Oxfordshire	OX16 2EH	Cherwell	South East	2014/2015	3	Development completed	14/02149/CDC	29/12/2014	24/06/2015	Residential	No	28	21/09/2018	0	28	Yes	No	0	0	0	0	0	0	0	28	0	0	0	28	0
PSLR0496	PLHP 1	DHSC	Barnoldswick Ambulance Station	Brogden View, Barnoldswick	BB18 5LH	Pendle	North West	2013/2014	9	Planning stage	16/0617/FUL	15/09/2016	28/09/2017	Residential	No	9	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0499a	PLHP 1	DHSC	Batley Health Centre	68 - 70 Batley Rd, Wakefield	WF2 0AD	Wakefield	Yorkshire and The Humber	2011/2012	2	Development completed	12/00140/FUL	19/01/2012	10/10/2012	Residential	No	2	23/07/2018	0	2	Yes	No	0	0	0	0	0	0	0	2	0	2	0	0	0
PSLR0499b	PLHP 1	DHSC	Batley Health Centre	68 - 70 Batley Rd, Wakefield	WF2 0AD	Wakefield	Yorkshire and The Humber	2011/2012	2†	Planning stage	14/01114/FUL	15/05/2014	10/02/2015	Residential	No	2	x	0	0	Not applicable	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0500	PLHP 1	DHSC	Bedensfield Clinic	Sidcup	DA14 5LE	Bexley	London	2013/2014	6	Planning stage	14/02425/FUL	23/12/2014	05/06/2015	Residential	No	7	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0501	PLHP 1	DHSC	Beechmount Resource Centre	Manchester	M9 5XS	Manchester	North West	2014/2015	12	Planning stage	124481/FO/2019	04/09/2019	13/11/2019	Residential	No	11	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0502	PLHP 1	DHSC	Belle Vue Flats & Paston Place, Brighton Sale 2	Brighton	BN1 2HA	Brighton and Hove	South East	2014/2015	2	Development completed	x	x	x	Residential sale	Unknown	2	x	x	2	Not applicable	Unknown	0	0	0	0	0	x	x	2	x	x	x	x	2
PSLR0503	PLHP 1	DHSC	Belle Vue Flats & Paston Place, Brighton Sale 3	Brighton	BN1 2HA	Brighton and Hove	South East	2014/2015	3	Development completed	x	x	x	Residential sale	Unknown	3	x	x	3	Not applicable	Unknown	0	0	0	0	0	x	x	3	x	x	x	x	3
PSLR0504	PLHP 1	DHSC	Belle Vue Flats & Paston Place, Brighton Sale 3	Brighton	BN1 2HA	Brighton and Hove	South East	2014/2015	1	Development completed	x	x	x	Residential sale	Unknown	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0505	PLHP 1	DHSC	Belle Vue Flats & Paston, Brighton	Brighton	BN1 2HA	Brighton and Hove	South East	2014/2015	8	Development completed	x	x	x	Residential sale	Unknown	8	x	x	8	Not applicable	Unknown	0	0	0	0	0	x	x	8	x	x	x	x	8
PSLR0506	PLHP 1	DHSC	Belmont House	Belmont House, Technical Street, Burnham on Sea, TA8 1PN	TA8 1PN	Sedgemoor	South West	2011/2012	5	Planning stage	11/12/00009	27/01/2012	19/03/2012	Commercial	No	0	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0507	PLHP 1	DHSC	Bemrose and Sovereign Car Parks	Carrington Street Derby	DE1 2QY	Derby	East Midlands	2011/2012	50	Development started	05/12/00563	09/05/2012	08/02/2013	Mixed	Yes	660	19/06/2015	0	50	Yes	Yes	26	0	8	0	0	22	27	1	4	4	25	17	0
PSLR0508	PLHP 1	DHSC	Berkeley Hospital	Marybrook Street, Berkeley	GL13 9AD	Stroud	South West	2014/2015	18	Development started	S.16/1186/FUL	25/05/2016	19/10/2016	Residential	No	20	03/01/2019	0	12	No	No	0	0	0	0	0	11	0	1	0	0	12	0	0
PSLR0509	PLHP 1	DHSC	Bestwood Health Centre	Pedmore Valley, Nottingham NG5 5NN	NG5 5NN	Nottingham	East Midlands	2014/2015	15	Development completed	14/01822/PFUL3	30/07/2014	26/11/2014	Residential	No	16	21/07/2016	0	16	Yes	No	0	0	0	0	0	0	0	16	0	0	0	16	0
PSLR0510	PLHP 1	DHSC	Bicester Hospital	Kings End, Bicester, Oxfordshire	OX26 6DU	Cherwell	South East	2014/2015	14	Development completed	12/00809/F	06/06/2012	27/09/2012	Mixed	No	14	20/01/2017	0	14	Yes	No	0	0	0	0	0	12	2	0	0	0	12	2	0
PSLR0511a	PLHP 1	DHSC	Billinge Hospital	Upholland Road, Billinge, Wigan	WN5 7EG	Wigan	North West	2013/2014	76	Development completed	A/11/75943,A/13/78868	02/08/2011	01/11/2011	Residential,Infill	No,No	65	17/11/2011	0	65	Yes,Yes	No,No	0	0	0	0	0	62	3	0	46	4	14	1	0
PSLR0511b	PLHP 1	DHSC	Billinge Hospital	Upholland Road, Billinge, Wigan	WN5 7EG	Wigan	North West	2013/2014	76†	Development started	A/05/65382	04/11/2005	13/12/2005	Residential	No	212	28/01/2008	0	135	Yes	No	0	0	0	0	0	128	6	1	53	10	68	4	0
PSLR0511c	PLHP 1	DHSC	Billinge Hospital	Upholland Road, Billinge, Wigan	WN5 7EG	Wigan	North West	2013/2014	76†	Development started	A/13/78608	30/09/2013	28/10/2014	Residential	Yes	37	04/01/2018	0	37	Yes	Yes	0	0	0	0	9	20	17	0	33	4	0	0	0
PSLR0511d	PLHP 1	DHSC	Billinge Hospital	Upholland Road, Billinge, Wigan	WN5 7EG	Wigan	North West	2013/2014	76†	Development started	A/13/78607	20/09/2013	28/10/2014	Residential	Yes	21	05/10/2017	0	21	Yes	Yes	0	0	0	0	9	3	18	0	11	4	6	0	0
PSLR0512	PLHP 1	DHSC	Bingley Hospital	Fernbank Drive, Bingley	BD16 4TL	Bradford	Yorkshire and The Humber	2013/2014	46	Development started	13/02125/MAF	29/05/2013	26/09/2013	Residential institute	No	77	30/08/2016	0	41	Yes	No	0	0	0	0	0	0	0	41	0	0	0	39	2
PSLR0513	PLHP 1	DHSC	Blacon Health Centre	Blacon Clinic, Church Way, Blacon, Chester,	CH1 5HS	Cheshire West and Chester	North West	2013/2014	7	Development completed	12/04925/FUL	02/11/2012	25/03/2013	Mixed	Yes	62	29/09/2014	0	1	No	Yes	0	62	0	0	0	0	0	1	0	0	1	0	0
PSLR0514	PLHP 1	DHSC	Boothall Hospital	Charlestown Road, Blackley, Manchester	M9 7AA	Manchester	North West	2013/2014	257	Development started	102608/MO/2013/N1,108188/JO/2015/N1	06/06/2013	25/11/2013	Residential,Infill	No,No	260	01/05/2014	0	260	Yes,Unknown	Yes,Unknown	0	0	0	0	51	66	193	1	69	100	91	0	0
PSLR0515	PLHP 1	DHSC	Boulton Clinic	6/8 Wyndam Street, Alvaston, Derby	DE24 0EP	Derby	East Midlands	2014/2015	2	Development completed	04/12/00434	16/04/2012	11/06/2012	Residential	No	2	20/06/2012	0	2	Yes	No	0	0	0	0	0	2	0	0	0	2	0	0	0
PSLR0516	PLHP 1	DHSC	Bramcote Hospital	off Lutterworth Road, Nuneaton	CV11 6QL	Nuneaton and Bedworth	West Midlands	2014/2015	29	Development completed	33160	23/12/2014	09/10/2015	Residential	No	28	25/07/2016	0	28	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	28	0	0	28	0	0	0	0
PSLR0517	PLHP 1	DHSC	Bristol General Hospital	Guinea Street, Bristol	BS1 6SY	Bristol	South West	2011/2012	190	Development started	12/03900/F,13/03372/X	04/09/2012	12/12/2012	Mixed,Infill	No,No	205	01/12/2016	31	175	No,Unknown	Developer paid local authority to put them somewhere else,Developer paid local authority to put them somewhere else	0	0	0	0	0	18	92	65	0	0	0	84	91
PSLR0518	PLHP 1	DHSC	Bristol Road Ambulance Station	Bristol Road, Bournbrook, Birmingham	B5 7SN	Birmingham	West Midlands	2013/2014	1	Development completed	2013/07698/PA	19/12/2013	31/01/2014	Residential institute	No	259	18/09/2015	0	64	Yes	No	0	0	0	0	0	0	0	64	0	0	0	64	0
PSLR0519	PLHP 1	DHSC	Broadmoor Hospital 1	School Hill, Crowthorne, Berkshire	RG45 7HE	Bracknell Forest	South East	2012/2013	18	Development completed	13/00294/REM	22/04/2013	22/07/2013	Residential	No	18	23/05/2014	0	18	Yes	No	0	0	0	0	0	12	6	0	0	10	2	6	0
PSLR0520	PLHP 1	DHSC	Bromley Primary Care Trust HQ Bassetts House	Broadwater Gardens, Orpington, Kent	BR6 7AR	Bromley	London	2014/2015	90	Development started	15/04941/FULL3	03/11/2015	18/08/2016	Residential	No	115	20/01/2017	0	114	Yes	Yes	7	0	5	0	0	45	54	15	8	11	40	55	0
PSLR0521	PLHP 1	DHSC	Bromyard Ambulance Station	New Road, Bromyard	HR7 4AJ	Herefordshire	West Midlands	2012/2013	1	Development completed	N122221/F	06/08/2012	21/09/2012	Residential	No	1	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0522	PLHP 1	DHSC	Brunel Lodge (Wolborough site)	Wolborough Hospital, Totnes Road, Newton Abbot	TQ12 6AA	Teignbridge	South West	2013/2014	13	Planning stage	13/01497/MAJ	21/05/2013	21/01/2014	Residential	No	13	x	0	0	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0523	PLHP 1	DHSC	Brunswick Health Centre	Manchester	M13 9YA	Manchester	North West	2014/2015	10	Development started	101664/FO/2013/N2	18/02/2013	30/05/2013	Mixed	Yes	522	10/09/2019	0	1	Yes	Unknown	0	0	0	0	0	1	0	0	0	1	0	0	0
PSLR0525	PLHP 1	DHSC	Cabot House	Cabot House, 69 Fore Street, Totnes, Devon	TQ9 5NJ	South Hams	South West	2013/2014	1	Planning stage	56/1567/13/CU	21/06/2013	03/10/2013	Commercial	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0526	PLHP 1	DHSC	Carr Mill Clinic, St Helens	Eskdale Ave, St Helens	WA11 7EJ	St Helens	North West	2014/2015	8	Planning stage	P/2017/0210/FUL	09/03/2017	04/05/2017	Residential	No	5	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0527	PLHP 1	DHSC	Carshalton War Memorial Hospital	The Park, Carshalton, Surrey	SM5 3DB	Sutton	London	2012/2013	13	Development completed	C2011/64809/FUL	15/08/2011	30/03/2012	Residential	No	13	17/09/2013	0	13	Yes	No	0	0	0	0	0	13	0	0	0	0	13	0	0
PSLR0528	PLHP 1	DHSC	Cavendish House	18 Victoria Road, Southsea, Portsmouth,	PO5 2BZ	Portsmouth	South East	2014/2015	15	Development completed	15/00502/FUL	30/04/2015	25/06/2015	Residential institute	No	15	26/07/2017	0	15	Yes	No	0	0	0	0	0	0	0	15	0	0	0	11	4
PSLR0529	PLHP 1	DHSC	Cedar Close Care Centre	Cedar Close, Carshalton, Surrey	SM5 3BZ	Sutton	London	2011/2012	6	Development started	C2012/65994	29/05/2012	09/01/2013	Residential	No	9	11/02/2014	0	8	Yes	No	0	0	0	0	0	8	0	0	4	4	0	0	0
PSLR0530	PLHP 1	DHSC	Cedar Cross Medical Practice	Cedar Road, Prescot	L35 2XA	Knowsley	North West	2013/2014	10	Planning stage	16/000027/CLD	15/01/2016	04/04/2016	Commercial	Unknown	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0531	PLHP 1	DHSC	Central Clinic	Carlisle	CA1 1HP	Carlisle	North West	2013/2014	9	Development started	14/0547	25/06/2014	03/10/2014	Residential institute	No	57	08/03/2016	0	11	Yes	No	0	0	0	0	0	0	0	11	0	0	0	11	0
PSLR0532	PLHP 1	DHSC	Chalfont Centre for Epilepsy Debenham House	Chalfont St Peter, Bucks	SL9 0RN	Chiltern	South East	2013/2014	1	Development completed	x	x	x	Residential sale	Unknown	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0533	PLHP 1	DHSC	Cherry Tree Hospital	Cherry Tree Lane, Stockport	SK2 7PZ	Stockport	North West	2012/2013	65	Development completed	DC/050984	05/10/2012	08/07/2014	Residential	No	65	16/11/2015	0	64	Yes	Yes	0	4	12	0	0	3	61	0	29	14	21	0	0
PSLR0534	PLHP 1	DHSC	Child Health Clinic	21 Woods Terrace, Murton, Seaham	SR7 9AG	County Durham	North East	2013/2014	1	Development started	DM/14/01402/FPA	22/05/2014	16/07/2014	Residential	No	5	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	0	0	0	0	1
PSLR0535	PLHP 1	DHSC	Child Health Clinic	Oaklea School Clinic, Wingate, Co. Durham	TS28 5HY	County Durham	North East	2013/2014	1	Development completed	DM/15/03463/FPA	05/11/2015	14/07/2016	Residential	No	6	05/07/2017	0	1	No	No	0	0	0	0	0	1	0	0	0	0	0	0	1
PSLR0536	PLHP 1	DHSC	Child Health ClinicÃ‚Â	22 Tudor Court, Shotton, Peterlee	DH6 2RE	County Durham	North East	2014/2015	1	Development completed	DM/14/02551/FPA	26/08/2014	22/10/2014	Residential	No	1	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	0	0	0	0	1
PSLR0537	PLHP 1	DHSC	Chipping Norton Hospital	Horsefair, Chipping Norton, Oxfordshire	OX7 5AJ	West Oxfordshire	South East	2012/2013	14	Planning stage	17/02814/FUL	01/09/2017	17/08/2018	Residential	No	14	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0538	PLHP 1	DHSC	Church Farm House	Church Farm Way, Nayland Road, Mile End, Colchester, Essex	CO4 5FD	Colchester	East	2013/2014	3	Development completed	144679	22/04/2014	22/07/2014	Residential	No	1	22/02/2016	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0539	PLHP 1	DHSC	Church Hill House	23-25 Church Hill, Honiton, Devon	EX14 2DB	East Devon	South West	2013/2014	2	Development completed	13/2487/FUL	21/11/2013	23/12/2013	Residential	No	4	01/07/2014	0	4	Yes	No	0	0	0	0	0	4	0	0	0	0	4	0	0
PSLR0540	PLHP 1	DHSC	Church Road Flats	11 Church Road, Old Maldon	KT4 7RD	Kingston upon Thames	London	2014/2015	10	Development completed	15/15388	21/12/2015	08/03/2016	Residential	No	4	18/07/2018	0	4	Yes	No	0	0	0	0	0	4	0	0	0	0	4	0	0
PSLR0541	PLHP 1	DHSC	Cleator Moor Health Centre	Ennerdale Road, Cumbria	CA25 5HR Ã‚Â	Copeland	North West	2013/2014	1	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0542	PLHP 1	DHSC	Coldeast Hospital	Bridge Rd, Sarisbury Green, Fareham	SO31 7YA	Fareham	South East	2014/2015	124	Development completed	P/12/0299/FP	27/03/2012	30/04/2013	Mixed	Unknown	208	x	0	0	Unknown	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0543	PLHP 1	DHSC	College Street Health Centre	Leigh	WN7 2RF	Wigan	North West	2013/2014	12	Development completed	A/14/80170/MAJOR	26/11/2014	21/04/2015	Residential	No	14	25/02/2016	0	14	Yes	No	0	0	0	0	0	8	0	6	0	0	0	14	0
PSLR0544	PLHP 1	DHSC	Community Offices	Kings Avenue, Ashford, Kent	TN23 1NT	Ashford	South East	2011/2012	56	Development completed	11/01328/AS	16/11/2011	20/01/2014	Residential	No	56	04/03/2015	0	56	Yes	Yes	10	0	6	0	0	50	6	0	4	13	32	7	0
PSLR0545	PLHP 1	DHSC	Constable House, Flax Bourton	20-21 Old Western Road, Farleigh, Flax Bourton North Somerset	BS48 1UL	North Somerset	South West	2014/2015	5	Development completed	15/P/0593/F	20/02/2015	06/03/2015	Residential	No	4	14/02/2019	0	1	No	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0546	PLHP 1	DHSC	Constable Road	Constable Road, Felixstowe	IP11 7HJ	Suffolk Coastal	East	2014/2015	5	Development completed	DC/15/3469/FUL	25/08/2015	08/10/2015	Residential	No	1	27/05/2017	0	2	Yes	No	0	0	0	0	0	2	0	0	1	0	1	0	0
PSLR0547a	PLHP 1	DHSC	Cookridge Hospital	Hospital Lane, Cookridge, Leeds	LS16 6FH	Leeds	Yorkshire and The Humber	Before 2011	50	Development started	11/03324/FU	19/09/2011	20/06/2013	Mixed	No	175	05/05/2014	0	62	Yes	Yes	0	30	30	0	0	62	0	0	2	10	50	0	0
PSLR0548	PLHP 1	DHSC	Coundon Clinic	Barkers Butts Lane, Coventry	CV6 1DU	Coventry	West Midlands	2013/2014	11	Development completed	FUL/2014/0735	04/03/2014	04/08/2014	Residential	No	10	08/09/2015	0	10	Yes	No	0	0	0	0	0	10	0	0	0	0	10	0	0
PSLR0549	PLHP 1	DHSC	County Hospital	North Road, Durham, County Durham	DH1 4RN	County Durham	North East	2013/2014	100	Development started	DM/14/03694/FPA	05/12/2014	09/04/2015	Residential institute	No	364	15/10/2018	0	126	Yes	No	0	0	0	0	0	0	0	126	0	0	0	126	0
PSLR0550	PLHP 1	DHSC	Coventry & Warwickshire Hospital	Stoney Stanton Road, Coventry	CV1 4JN	Coventry	West Midlands	2014/2015	76	Planning stage	FUL/2014/1326	25/04/2014	15/08/2014	Commercial	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0551	PLHP 1	DHSC	Cranbrook Ambulance Station	Cranbrook	TN17 3BP	Tunbridge Wells	South East	2013/2014	7	Development completed	14/01221/FULL	11/04/2014	14/07/2015	Residential	No	9	06/09/2017	0	9	Yes	No	0	0	0	0	0	4	5	0	0	4	0	5	0
PSLR0553	PLHP 1	DHSC	Devizes Family Health Centre	New Park Street, Devizes	SN10 1DR	Wiltshire	South West	2012/2013	7	Development started	E/2012/1432/FUL,14/01771/VAR	19/11/2012	01/03/2013	Mixed,Infill	No,No	15	11/04/2015	0	8	Yes,Yes	No,No	0	0	0	0	0	0	8	0	0	0	0	8	0
PSLR0554	PLHP 1	DHSC	Dorset County HospitalÃ‚Â	Bridport Road, Dorchester, Dorset	DT1 2NQ	West Dorset	South West	2012/2013	39	Development completed	1/D/12/000936,1/D/13/001388	08/10/2013	18/12/2013	Residential,Infill	No,No	40	16/04/2014	0	40	Yes,Not applicable	Developer paid local authority to put them somewhere else,No	0	0	0	0	0	0	40	0	0	0	0	40	0
PSLR0555	PLHP 1	DHSC	Dovercourt Health Centre	Main Road, Harwich, CO12 4ET	CO12 4ET	Tendring	East	2013/2014	24	Development completed	14/01782/FUL	28/11/2014	09/01/2015	Residential	No	24	06/07/2017	0	24	Yes	Yes	0	6	0	0	0	0	20	4	0	0	0	24	0
PSLR0556	PLHP 1	DHSC	Downer Court Wilson Avenue	Rochester, Kent	ME1 2SA	Medway	South East	2014/2015	2	Development completed	x	x	x	Residential sale	Unknown	2	x	x	2	Not applicable	Unknown	0	0	0	0	0	x	x	2	x	x	x	x	2
PSLR0557	PLHP 1	DHSC	Downham Cottage	111 Longdown Lane, South Epsom, Surrey	KT17 4JL	Epsom and Ewell	South East	2012/2013	1	Development completed	12/00797	23/10/2012	18/12/2012	Residential	No	1	21/02/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0558	PLHP 1	DHSC	Durham House	69 Canterbury Rd, Herne Bay	CT6 5SA	Canterbury	South East	2014/2015	9	Development completed	CA//14/02238	20/11/2014	13/01/2015	Residential	No	9	19/03/2012	0	9	Yes	No	0	0	0	0	0	0	9	0	0	0	0	9	0
PSLR0559	PLHP 1	DHSC	EaglehurstÃ‚Â	6 Valley Road, Clacton on Sea	CO15 4AR	Tendring	East	2013/2014	1	Development completed	13/01103/FUL	27/09/2013	21/11/2013	Residential	No	1	21/02/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0560	PLHP 1	DHSC	Easington Clinic	8 Seaside Lane South, Easington Colliery, Easington Colliery, Durham	SR8 3PN	County Durham	North East	2014/2015	1	Development completed	DM/14/03626/FPA	24/11/2014	09/03/2015	Residential	No	1	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	0	0	1	0	0
PSLR0561	PLHP 1	DHSC	East Ardsley Health Centre	East Ardsley Health Centre, Bradford Road, East Ardsley, Wakefield	WF3 2DN	Leeds	Yorkshire and The Humber	2013/2014	10	Development completed	13/04119/FU	10/09/2013	20/12/2013	Residential	No	12	03/06/2014	0	12	Yes	No	0	0	0	0	0	12	0	0	6	6	0	0	0
PSLR0563	PLHP 1	DHSC	East Surry Hospital	Harrowlands Park, Dorking, Surrey	RH4 2RA	Mole Valley	South East	2012/2013	5	Development started	MO/2013/0894	28/06/2013	24/02/2014	Residential	No	9	14/01/2016	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0564	PLHP 1	DHSC	Elm House	Elm House, 84 Ewell Road, Surbiton	KT6 6EX	Kingston upon Thames	London	2014/2015	12	Development completed	16/16198	16/03/2016	19/04/2016	Residential	No	4	26/07/2017	0	4	Yes	No	0	0	0	0	0	0	0	4	0	0	0	4	0
PSLR0565	PLHP 1	DHSC	Elm House Clinic	15 New Road Ave, Chatham	ME4 6BA	Medway	South East	2014/2015	12	Planning stage	MC/15/1316	20/04/2015	x	Commercial	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0566	PLHP 1	DHSC	Elmwood Avenue	20 Elmwood Road, Harrow	HA3 8AH	Harrow	London	2014/2015	1	Planning stage	P/0347/16	28/01/2016	27/05/2016	Residential	No	3	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0567	PLHP 1	DHSC	Elwick Road Centre	1 Elwick Rd, Ashford	TN23 1PF	Ashford	South East	2013/2014	1	Planning stage	x	x	x	Permitted development	Unknown	0	x	x	x	Not applicable	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0568	PLHP 1	DHSC	Ethel Bailey Close nos 1-9	Manor Park, Epsom, Surrey	KT19 8NQ	Epsom and Ewell	South East	2014/2015	42	Development completed	14/00825/FUL	03/09/2014	16/01/2015	Residential	No	48	19/04/2016	0	48	Yes	Yes	6	0	13	0	0	29	6	13	20	6	18	4	0
PSLR0569	PLHP 1	DHSC	Fairfield Hospital	Stotfold	SG5 4FJ	Central Bedfordshire	East	Before 2011	100	Planning stage	CB/15/02748/FULL	23/07/2015	13/11/2015	Residential	No	4	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0570	PLHP 1	DHSC	Fairview Nursing Homes	Gipsy Lane, Warminster, Wilts	BA12 9LR	Wiltshire	South West	2013/2014	14	Development completed	14/05980/FUL	25/06/2014	15/05/2015	Residential	No	12	11/05/2016	0	12	Yes	Yes	0	0	0	0	4	12	0	0	0	6	0	6	0
PSLR0571	PLHP 1	DHSC	Fakenham Health Office, Greenway Lane	Barons Close, Fakenham	NR21 8BJ	North Norfolk	East	2014/2015	6	Development completed	PF/15/1603	03/09/2015	21/07/2016	Residential	No	13	22/11/2017	0	13	Yes	Yes	0	13	0	0	0	6	3	4	0	0	3	10	0
PSLR0572	PLHP 1	DHSC	Fall Birch Hospital	Horwich, Bolton	BL6 4GF	Bolton	North West	Before 2011	10	Development completed	78526/07	01/10/2007	31/12/2007	Residential	No	45	26/05/2010	0	45	Yes	Yes	0	4	0	0	0	8	37	0	28	11	6	0	0
PSLR0573	PLHP 1	DHSC	Finchdean House	St Mary's Hospital, Milton Rd, Portsmouth	PO3 6AD	Portsmouth	South East	2012/2013	73	Development completed	12/00349/FUL	23/03/2012	31/08/2012	Residential	Yes	73	24/03/2015	0	73	Yes	Yes	42	0	31	0	0	42	31	0	0	0	0	73	0
PSLR0574	PLHP 1	DHSC	Foleshill Road	216 Foleshill Road, Coventry	CV1 4JH	Coventry	West Midlands	2013/2014	1	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0575	PLHP 1	DHSC	Folkestone Ambulance Station	Folkestone	CT20 3EW	Folkestone and Hythe	South East	2013/2014	14	Development completed	Y13/0595/SH	12/06/2013	11/09/2013	Residential	No	14	11/11/2014	0	14	Yes	No	0	0	0	0	0	8	6	0	2	12	0	0	0
PSLR0576	PLHP 1	DHSC	Fordingbridge Hospital	Bartons Rd, Fordingbridge	SP6 1JD	New Forest	South East	2014/2015	16	Development completed	14/11156	15/08/2014	05/09/2014	Residential	No	15	13/05/2016	0	15	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	15	0	0	0	0	15	0
PSLR0577	PLHP 1	DHSC	Forest Hill House	Forest Hill, Bideford, North Devon	EX39 5HB	Torridge	South West	2011/2012	1	Development completed	1/1226/2008/FUL	29/11/2008	19/03/2009	Residential	No	1	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0578	PLHP 1	DHSC	Former Grounds & Gardens Department, Former Rubery Hill Hospital	Bristol Road South, Rubery, Birmingham.	B45 9BB	Birmingham	West Midlands	2014/2015	51	Development completed	2014/07452/PA	16/10/2014	25/03/2015	Residential	No	46	10/12/2015	0	46	Yes	Yes	0	0	0	0	16	7	39	0	12	7	9	0	18
PSLR0579	PLHP 1	DHSC	Former Leicester Frith Farm	Lady Hay Road, Leicester	LE3 9QY	Leicester	East Midlands	2011/2012	30	Development started	20120650	08/05/2012	11/04/2013	Residential	No	29	19/01/2015	0	20	Yes	Yes	5	0	1	0	0	17	2	1	0	4	13	2	1
PSLR0580	PLHP 1	DHSC	Former Newton Abbot Hospital East Street	Newton Abbot Hospital (East Street), East Street, Newton Abbot	TQ12 4PT	Teignbridge	South West	2011/2012	103	Development started	11/01475/MAJ	12/05/2011	12/03/2012	Residential	No	104	02/09/2013	0	98	Yes	Yes	0	0	4	0	9	47	51	0	0	8	44	42	4
PSLR0581a	PLHP 1	DHSC	Fountains Way (also known as former Old Manor Hospital)	Wilton Road, Salisbury	SP2 7EP	Wiltshire	South West	2014/2015	80	Development started	15/09465/FUL	05/10/2015	24/10/2016	Mixed	No	71	14/11/2018	0	48	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	22	0	26	0	0	0	46	2
PSLR0581b	PLHP 1	DHSC	Fountains Way (also known as former Old Manor Hospital)	Wilton Road, Salisbury	SP2 7EP	Wiltshire	South West	2014/2015	80†	Development started	16/10839/FUL	08/11/2016	21/07/2017	Residential	No	21	18/09/2018	0	1	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	1	0	0	0	0	0	1	0
PSLR0582	PLHP 1	DHSC	Franklin Road	Franklin Road / Gleave Road, Whitnash, Leamington Spa,	CV31 2JN	Warwick	West Midlands	2012/2013	9	Development started	W/13/1792	24/12/2013	03/03/2014	Residential	No	9	02/09/2015	0	8	Yes	No	0	0	0	0	0	8	0	0	2	6	0	0	0
PSLR0583	PLHP 1	DHSC	Fulbeck Grange	Fulbeck Lane, Morpeth	NE61 3JU	Northumberland	North East	2014/2015	6	Development started	17/01942/FUL	01/06/2017	21/03/2018	Residential	Yes	13	22/05/2019	0	13	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	9	0	4	13	0	0	0	0
PSLR0584	PLHP 1	DHSC	Gables	Plymouth	PL7 1UG	Plymouth	South West	2014/2015	4	Development completed	14/00275/FUL	13/02/2014	25/04/2014	Residential	No	1	21/02/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	0	0	1	0	0
PSLR0585	PLHP 1	DHSC	Gambier House	West Hill Road, St Leonards on Sea, East Sussex.	TN38 0NG	Hastings	South East	2012/2013	10	Planning stage	HS/FA/14/00839	10/10/2014	18/05/2016	Mixed	Yes	85	x	0	0	No	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0586	PLHP 1	DHSC	Glasgow Road, Jarrow	Jarrow	NE32 4AU	South Tyneside	North East	2013/2014	6	Planning stage	x	x	x	Permitted development	No	0	x	x	x	Not applicable	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0587	PLHP 1	DHSC	Greenlaws	65 Cranley Road, Guildford, Surrey	GU1 2JW	Guildford	South East	2013/2014	4	Development completed	14/P/01113	17/06/2014	29/08/2014	Residential	No	6	02/03/2016	0	6	Yes	No	0	0	0	0	0	6	0	0	0	6	0	0	0
PSLR0588	PLHP 1	DHSC	Grey Gables (part of South Shore freehold site)	Dunes Avenue. South Shore Blackpool	FY4 1PU	Blackpool	North West	2013/2014	1	Planning stage	14/0470	13/06/2014	25/07/2014	Residential	No	1	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0589	PLHP 1	DHSC	Grove Road Day Hospital	12 Grove Road, Redland, Bristol	BS6 6UJ	Bristol	South West	2012/2013	1	Planning stage	15/05956/F	19/11/2015	15/02/2016	Residential	No	1	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0590	PLHP 1	DHSC	Gunnersbury Day Hospital	Cloister Road, Acton	W3 0DE	Ealing	London	2013/2014	4	Development completed	PP/2013/3426	13/08/2013	24/10/2013	Residential	No	4	24/03/2015	0	4	Yes	No	0	0	0	0	0	4	0	0	0	0	4	0	0
PSLR0591	PLHP 1	DHSC	Hackney Hospital Site	Hackney	E9Ã‚Â 5GX	Hackney	London	Before 2011	37	Development completed	2009/0259	10/02/2009	17/06/2009	Mixed	No	37	28/04/2011	0	37	Yes	Yes	0	13	6	0	0	37	0	0	0	0	0	37	0
PSLR0592	PLHP 1	DHSC	Hackney Nurses Home	Kenworthy Rd, Hackney	E9 5GX	Hackney	London	Before 2011	200	Development completed	2007/2786	08/01/2008	01/07/2011	Mixed	No	119	28/11/2012	0	123	Yes	Yes	0	31	28	0	0	108	15	0	0	0	0	110	13
PSLR0593	PLHP 1	DHSC	Hales Hospital, Norwich	Norwich	NR146AB	South Norfolk	East	Before 2011	44	Development completed	2003/1007	19/05/2003	23/02/2006	Residential	No	44	20/07/2015	0	44	Yes	No	0	0	0	0	0	26	18	0	0	0	29	15	0
PSLR0594	PLHP 1	DHSC	Hall Green Clinic	Skelmersdale	WN8 0DX	West Lancashire	North West	2014/2015	3	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0595	PLHP 1	DHSC	Halstead Road	78 Hedingham Road, Halstead, Colchester	CO9 2DL	Braintree	East	2013/2014	2	Development completed	14/00108/FUL	24/01/2014	02/06/2014	Residential	Unknown	2	23/02/2015	0	2	Yes	No	0	0	0	0	0	1	0	1	0	0	0	2	0
PSLR0596	PLHP 1	DHSC	Harp's Close Meadow (Peoples Park)	Waldingfield Road, Sudbury, Suffolk	CO10 1YU	Babergh	East	2014/2015	75	Development completed	B/14/01520	26/11/2014	16/03/2015	Residential	Yes	100	07/04/2016	0	100	Yes	Yes	0	0	0	0	35	77	15	8	47	41	4	8	0
PSLR0597	PLHP 1	DHSC	Hartletpool Ambulance Station	Elwick Road, Hartlepool	TS26 0BE	Hartlepool	North East	2012/2013	8	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0598	PLHP 1	DHSC	Haunch Lane	126-128 Haunch Lane, Birmingham	B13 0PY	Birmingham	West Midlands	2014/2015	2	Planning stage	2016/05917/PA	08/08/2016	27/09/2016	Residential	No	1	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0599	PLHP 1	DHSC	Hawthorn House	Wilfred Terrace, Lower Wortley, Leeds	LS12 5DE	Leeds	Yorkshire and The Humber	2013/2014	2	Development completed	14/04101/FU	27/08/2014	06/10/2014	Residential	No	2	18/05/2015	0	2	Yes	No	0	0	0	0	0	0	0	2	0	2	0	0	0
PSLR0600	PLHP 1	DHSC	Hawtonville Health Clinic	14-22 Portland Street	NG24 4XG	Newark and Sherwood	East Midlands	2014/2015	9	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0601	PLHP 1	DHSC	Health Clinic Market Square/ Bishop Stortford Clinic	Market Square Bishops Stortford	CM23 3UU	East Hertfordshire	East	2013/2014	6	Planning stage	3/13/1724/FP	25/09/2013	20/11/2013	Commercial	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0602	PLHP 1	DHSC	Health Promotion	Worksop	S80 2BQ	Bassetlaw	East Midlands	2014/2015	2	Planning stage	15/00034/PDN	13/01/2015	11/03/2015	Residential	No	1	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0603	PLHP 1	DHSC	Hedgecock Centre 1	Upney Lane, Barking	IG11 9LS	Barking and Dagenham	London	2013/2014	27	Development completed	13/00814/REM	18/09/2013	11/02/2014	Residential	No	27	19/10/2015	0	27	Yes	No	0	0	0	0	0	27	0	0	7	20	0	0	0
PSLR0604	PLHP 1	DHSC	Hednesford Health Centre	Eskrett Street, Hednesford	WS12 5AR	Cannock Chase	West Midlands	2012/2013	9	Development completed	CH/12/0428	03/12/2012	10/02/2013	Residential	No	10	27/05/2014	0	10	Yes	Yes	0	10	0	0	0	0	0	10	0	10	0	0	0
PSLR0605	PLHP 1	DHSC	Hempstead Road	Hempstead Road, Medway	ME7 3RH	Medway	South East	2014/2015	1	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0606	PLHP 1	DHSC	Henderson Hospital	2 Homeland Drive, Sutton	SM2 5LT	Sutton	London	2013/2014	9	Development completed	B2013/68157/FUL	06/08/2014	05/11/2014	Mixed	No	9	12/04/2016	0	9	Yes	No	0	0	0	0	0	9	0	0	0	4	5	0	0
PSLR0607	PLHP 1	DHSC	Hernes House, Hernes Crescent, Summertown, Oxford	Oxford	OX2 7PS	Oxford	South East	Before 2011	24	Development started	07/02120/RES	10/09/2007	18/01/2008	Residential	No	24	17/07/2014	0	9	Yes	Yes	0	0	3	0	4	8	0	1	1	2	6	0	0
PSLR0608	PLHP 1	DHSC	High Royds	Menston, Ilkley,	LS29 6AQ	Leeds	Yorkshire and The Humber	Before 2011	200	Development started	28/198/03/FU	23/07/2003	26/01/2005	Mixed	No	625	21/02/2012	6	603	Yes	Yes	10	0	99	0	0	290	293	20	99	16	89	367	32
PSLR0609	PLHP 1	DHSC	Hinchingbrooke Hospital	Hinchingbrooke Park Road, Huntingdon	PE29 6NT	Huntingdonshire	East	2013/2014	52	Planning stage	15/00486/FUL	08/04/2015	x	Residential	No	45	x	x	x	Yes	Mix of pay and houses	0	0	0	0	16	x	x	x	x	x	x	x	x
PSLR0610	PLHP 1	DHSC	Horncastle Health Centre,	Manor House Street, Horncastle	LN9 5HF	East Lindsey	East Midlands	2014/2015	5	Planning stage	S/086/00448/17	13/03/2017	30/08/2017	Residential	No	1	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0611	PLHP 1	DHSC	Horton House	Horton Lane, Epsom	KT197HA	Epsom and Ewell	South East	Before 2011	9	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0612	PLHP 1	DHSC	Hoyland Health Centre	2 Duke Street, Hoyland, Barnsley	S74 9QS	Barnsley	Yorkshire and The Humber	2013/2014	8	Planning stage	2015/0711	09/06/2015	28/10/2015	Commercial	Yes	0	x	x	x	No	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0613	PLHP 1	DHSC	Hubert Grove	108A Landor Road, Stockwell, London	SW9 9NT	Lambeth	London	2013/2014	1	Development started	15/02913/FUL	20/05/2015	21/03/2016	Residential	No	9	15/07/2019	0	5	Yes	No	0	0	0	0	0	1	0	4	0	0	0	2	3
PSLR0614	PLHP 1	DHSC	Huthwaite Health Centre	New Street, Huthwaite	NG17 2LR	Ashfield	East Midlands	2014/2015	6	Development completed	V/2016/0576	07/09/2016	10/01/2017	Residential	No	8	29/11/2017	0	8	Yes	No	0	0	0	0	0	6	2	0	0	0	6	2	0
PSLR0615	PLHP 1	DHSC	Hutton Community Clinic	Coram Green, Hutton, Brentwood, Essex	CM13 1LR	Brentwood	East	2014/2015	6	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0616	PLHP 1	DHSC	Hyde Hospital	Grange Road South, Hyde, Cheshire	SK14 5NY	Tameside	North West	2012/2013	31	Development completed	13/00562/FUL	12/07/2013	28/11/2013	Residential	No	33	21/01/2015	0	31	Yes	No	0	0	0	0	0	0	31	0	11	3	1	0	16
PSLR0617	PLHP 1	DHSC	Ida Road Clinic	2A Ida Road, Walsall	WS2 9SR	Walsall	West Midlands	2014/2015	2	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0618	PLHP 1	DHSC	Incefield House	Ince Green Lane, Ince in Makerfield	WN3 4RJ	Wigan	North West	2013/2014	14	Development completed	A/19/86852/MAJOR	04/03/2019	25/06/2019	Residential	No	10	25/01/2020	0	10	Yes	Unknown	0	0	0	0	0	0	0	10	0	0	0	10	0
PSLR0619	PLHP 1	DHSC	John Telford Clinic	Ilford	IG1 1EE	Redbridge	London	2014/2015	30	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0620	PLHP 1	DHSC	Josiah Thomas Memorial Hall	Trevithick Road, Camborne	TR14 8LQ	Cornwall	South West	2014/2015	4	Development completed	PA15/12054,PA17/06703	29/12/2015	09/05/2016	Residential,Infill	No,No	16	21/07/2018	0	16	Yes,Unknown	No,No	0	0	0	0	0	0	0	16	0	0	0	0	16
PSLR0621	PLHP 1	DHSC	Kent and Sussex Hospital	Mount Ephraim, Tunbridge Wells, Kent	TN4 8AT	Tunbridge Wells	South East	2011/2012	243	Development started	12/02547/EIAMJ	11/09/2012	11/12/2012	Residential	No	243	01/07/2014	6	235	Yes	Mix of pay and houses	0	43	10	0	0	145	90	0	0	38	50	147	0
PSLR0622	PLHP 1	DHSC	Kings Road Clinic	Kings Road, Chatham	ME5 7JY	Medway	South East	2012/2013	3	Planning stage	MC/16/4659	16/11/2016	21/02/2018	Residential	No	2	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0623	PLHP 1	DHSC	Kingswood Hall Nursing Home	Frodsham	WA6 9EX	Cheshire West and Chester	North West	2014/2015	4	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0625	PLHP 1	DHSC	Kingswood Resource Centre	54 Moravian Road, Kingswood	BS15 8ND	South Gloucestershire	South West	2012/2013	2	Planning stage	PK15/1269/RVC	23/03/2015	27/05/2015	Commercial	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0626	PLHP 1	DHSC	Knottingley Health Centre	Hazel Rd, Knottingley	WF11 0LG	Wakefield	Yorkshire and The Humber	2012/2013	6	Development completed	12/01371/FUL	29/01/2012	27/09/2012	Residential	No	18	15/11/2013	0	8	No	Yes	18	0	0	0	0	0	0	8	0	8	0	0	0
PSLR0627	PLHP 1	DHSC	Laburnum Avenue	72 Laburnum Avenue Wallsend	NE28 8HG	North Tyneside	North East	2013/2014	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0628	PLHP 1	DHSC	Lady Eden Hospital	Bishop Auckland	DL146EN	County Durham	North East	Before 2011	5	Development started	3/2012/0121	20/03/2012	08/08/2012	Residential institute	No	5	24/08/2013	0	1	Yes	No	0	0	0	0	0	0	0	1	0	0	0	0	1
PSLR0629	PLHP 1	DHSC	Lakeview Close, Walsall	Walsall	B43 7EU	Walsall	West Midlands	Before 2011	5	Planning stage	15/1364	07/09/2015	06/11/2015	Residential	No	7	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0630	PLHP 1	DHSC	Lamellion Hospital	Liskeard	PL14 4SZ	Cornwall	South West	Before 2011	32	Development started	E2/05/01612/FUL	03/02/2006	09/04/2008	Residential	No	33	01/07/2014	0	25	Yes	Yes	0	5	3	0	0	14	11	0	3	2	9	11	0
PSLR0631	PLHP 1	DHSC	Land at Almond Villa	31-33 The Broadway Knaphill Woking Surrey	GU21 2DR	Woking	South East	2012/2013	5	Development completed	PLAN/2013/0117	27/02/2013	29/05/2013	Residential	No	10	19/06/2015	0	10	Yes	No	0	0	0	0	0	10	0	0	1	0	9	0	0
PSLR0633	PLHP 1	DHSC	Land At Diana Princess of Wales Hospital,	Northside Grimsby	DN33 2BA	North East Lincolnshire	Yorkshire and The Humber	2014/2015	181	Development started	DM/0294/17/REM	07/04/2017	19/07/2017	Residential	No	148	16/05/2019	0	21	Yes	Unknown	0	0	0	0	0	0	0	21	0	0	0	21	0
PSLR0636	PLHP 1	DHSC	Land at Malvern Gardens	175 Malvern Road, London	NW6 5PZ	Brent	London	2014/2015	6	Planning stage	04/0381	03/03/2004	01/07/2004	Residential	No	6	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0637	PLHP 1	DHSC	Land at Michigan Way, Totton	Land at Michigan Way, Totton, Southampton	SO40 8AN	New Forest	South East	2012/2013	10	Development completed	13/10659	04/06/2013	03/09/2013	Residential	No	10	08/05/2014	0	10	Yes	No	0	0	0	0	0	10	0	0	6	4	0	0	0
PSLR0638	PLHP 1	DHSC	Land at Napsbury Hospital, Napsbury	London Colney	AL2 1UD	St Albans	East	Before 2011	40	Development started	5/2002/1256	12/06/2002	01/07/2004	Mixed	Yes	545	18/03/2005	0	175	No	Unknown	0	0	0	0	0	89	86	0	19	0	75	81	0
PSLR0639	PLHP 1	DHSC	Land at Old Winshall Health Centre	West St, Winshall, Burton upon Trent	DE15 0BW	East Staffordshire	West Midlands	2013/2014	6	Development completed	P/2015/00065	30/01/2015	24/03/2015	Residential	No	10	19/12/2016	0	10	Yes	No	0	0	0	0	0	0	0	10	0	10	0	0	0
PSLR0640	PLHP 1	DHSC	Land at Princes Road	Redhill, Surrey	RH1	Reigate and Banstead	South East	2012/2013	8	Development completed	13/01858/S73	14/10/2013	13/12/2013	Residential	No	8	09/12/2015	0	8	Yes	No	0	0	0	0	0	0	8	0	0	0	0	8	0
PSLR0641	PLHP 1	DHSC	Land at Rooley Avenue (known as Northern View)	Bradford	BD6 1BB	Bradford	Yorkshire and The Humber	2012/2013	115	Development completed	13/00308/FUL	25/01/2013	07/10/2013	Residential	No	109	18/09/2014	0	109	Yes	Yes	0	0	0	0	15	14	89	6	44	39	26	0	0
PSLR0642a	PLHP 1	DHSC	Land at Royal Shrewsbury Hospital North, Shrewsbury Part A ( adj to Shelton Hospital)	Land at Royal Shrewsbury Hospital North, Racecourse Lane, Shrewsbury	SY3 5BJ	Shropshire	West Midlands	2013/2014	14	Development started	14/02402/FUL,15/02751/VAR,19/05172/AMP,18/02604/AMP	30/05/2014	17/07/2015	Residential,Infill,Infill,Infill	No,No,No,No	249	09/06/2016	0	231	Yes,Yes,Yes,Yes	Yes,Yes,No,No	0	10	6	0	0	70	14	147	40	26	9	9	147
PSLR0642b	PLHP 1	DHSC	Land at Royal Shrewsbury Hospital North, Shrewsbury Part A ( adj to Shelton Hospital)	Land at Royal Shrewsbury Hospital North, Racecourse Lane, Shrewsbury	SY3 5BJ	Shropshire	West Midlands	2013/2014	14†	Planning stage	16/05797/FUL	09/01/2017	02/05/2017	Residential	No	12	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0642c	PLHP 1	DHSC	Land at Royal Shrewsbury Hospital North, Shrewsbury Part A ( adj to Shelton Hospital)	Land at Royal Shrewsbury Hospital North, Racecourse Lane, Shrewsbury	SY3 5BJ	Shropshire	West Midlands	2013/2014	14†	Development completed	16/01418/FUL	11/04/2016	03/06/2016	Residential	No	4	18/05/2018	0	4	Yes	No	0	0	0	0	0	4	0	0	0	0	4	0	0
PSLR0642d	PLHP 1	DHSC	Land at Royal Shrewsbury Hospital North, Shrewsbury Part A ( adj to Shelton Hospital)	Land at Royal Shrewsbury Hospital North, Racecourse Lane, Shrewsbury	SY3 5BJ	Shropshire	West Midlands	2013/2014	14†	Development completed	15/05530/FUL	05/01/2016	13/09/2016	Residential	No	1	14/06/2018	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0643	PLHP 1	DHSC	Land at Sylvan	Summervale House, Sarisbury Green, Southampton	SO31 7YD	Fareham	South East	2014/2015	2	Development completed	P/15/0577/FP	17/06/2015	10/08/2015	Residential	No	2	08/11/2016	0	2	Yes	No	0	0	0	0	0	2	0	0	2	0	0	0	0
PSLR0644	PLHP 1	DHSC	Land at Woodside, Plymouth	Plymouth	PL4 8QE	Plymouth	South West	Before 2011	11	Development completed	15/00431/FUL	09/03/2015	27/05/2015	Residential	Unknown	7	16/09/2016	0	7	Yes	No	0	0	0	0	0	0	7	0	0	0	0	7	0
PSLR0645	PLHP 1	DHSC	Land of former Haweside Clinic & House	Blackpool	FY4 5AJ	Blackpool	North West	2013/2014	10	Planning stage	14/0009	02/01/2014	14/02/2014	Residential	No	8	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0646	PLHP 1	DHSC	Larkhill Health Centre	Blackburn	BB1 5BJ	Blackburn with Darwen	North West	2014/2015	25	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0647	PLHP 1	DHSC	Lavendar Lodge	59 Watts Lane, Eastbourne, East Sussex	BN21 2LL	Eastbourne	South East	2014/2015	1	Development completed	140416	01/04/2014	19/06/2014	Residential	No	1	21/02/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0649	PLHP 1	DHSC	Leigh Clinic	Not known	Not known	Bradford	Yorkshire and The Humber	Before 2011	4	Planning stage	x	x	x	x	Unknown	x	x	x	x	Yes	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0650	PLHP 1	DHSC	Lennard Lodge	3 Lennard Road, Croydon, Surrey	CR0 2UL	Croydon	London	2013/2014	27	Development completed	14/02810/P	04/07/2014	29/04/2015	Residential	No	26	16/05/2017	0	26	Yes	Yes	5	0	3	0	0	0	26	0	0	3	3	20	0
PSLR0651	PLHP 1	DHSC	Limber	49 Church lane, Loughton	IG10 1PD	Epping Forest	East	2014/2015	1	Planning stage	EPF/1915/04	18/10/2004	02/02/2005	Residential	No	1	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0652	PLHP 1	DHSC	Linden	15-17 London Road, Stony Stratford, Milton Keynes	MK11 1JA	Milton Keynes	South East	2014/2015	2	Planning stage	15/00412/FUL	24/02/2015	07/04/2015	Commercial	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0653	PLHP 1	DHSC	Linden House	Beechdale Road Aspley Nottingham	NG8 3EY	Nottingham	East Midlands	2014/2015	27	Development completed	14/02703/PRES4	07/11/2014	13/03/2015	Residential	No	25	22/07/2016	0	25	Yes	Yes	0	25	0	0	0	15	7	3	0	11	11	3	0
PSLR0654	PLHP 1	DHSC	Lingfield Clinic	Bakers Lane Lingfield	RH7 6HD	Tandridge	South East	2013/2014	1	Planning stage	2015/869	06/06/2015	x	Residential	No	2	x	x	x	Yes	No	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0658	PLHP 1	DHSC	Longford Road	235 Longford Road, Coventry	CV6 6BG	Coventry	West Midlands	2014/2015	8	Development started	FUL/2014/3823	12/11/2014	17/02/2015	Residential	No	7	02/10/2019	0	5	Yes	No	0	0	0	0	0	0	0	5	0	0	0	5	0
PSLR0659	PLHP 1	DHSC	Longview	216 Turner Road, Colchester, Essex	CO4 5JR	Colchester	East	2012/2013	60	Development started	131287	27/06/2013	07/10/2013	Residential institute	No	60	13/10/2015	0	1	Yes	No	0	0	0	0	0	0	0	1	0	0	0	0	1
PSLR0660	PLHP 1	DHSC	Lordswood Road	329 Lordswood Road	B17 8PR	Birmingham	West Midlands	2014/2015	1	Development completed	2014/00481/PA	12/02/2014	25/03/2014	Residential	No	1	21/02/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0661	PLHP 1	DHSC	Louth County Hospital	46, 48, 50 and 52 Sandringham drive,Louth	LN11 0JE	East Lindsey	East Midlands	2013/2014	4	Development completed	x	x	x	Residential sale	No	4	x	x	4	Not applicable	Unknown	0	0	0	0	0	x	x	4	x	x	x	x	4
PSLR0662	PLHP 1	DHSC	Lucy Baldwin Hospital	Olive Grove, Stourport on Severn, Worcestershire	DY13 8XY	Wyre Forest	West Midlands	2012/2013	41	Development completed	13/0033/FULL	23/01/2013	10/04/2013	Residential	No	41	22/01/2014	0	40	Yes	Yes	6	0	6	0	0	34	5	1	19	10	5	6	0
PSLR0663	PLHP 1	DHSC	Lytham Road Health Centre	352 Lytham Road, Blackpool	FY4 1TJ	Blackpool	North West	2014/2015	10	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0664	PLHP 1	DHSC	Macclesfield District General Hospital	Victoria Road, Macclesfield, Cheshire	SK10 3BL	Cheshire East	North West	2012/2013	70	Development completed	16/1015M	29/02/2016	30/08/2016	Mixed	Yes	34	22/07/2017	0	34	Yes	Yes	0	0	2	0	3	10	23	1	0	30	4	0	0
PSLR0665a	PLHP 1	DHSC	Macclesfield District General Hospital	Macclesfield	SK103GR	Cheshire East	North West	Before 2011	50	Development completed	09/1296M	03/06/2009	18/12/2009	Mixed	No	36	21/02/2012	0	37	Yes	Yes	36	0	0	0	0	0	0	37	0	0	0	36	1
PSLR0665b	PLHP 1	DHSC	Macclesfield District General Hospital	Macclesfield	SK103GR	Cheshire East	North West	Before 2011	50†	Planning stage	11/2064M0	07/06/2011	09/09/2011	Residential	No	5	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0665c	PLHP 1	DHSC	Macclesfield District General Hospital	Macclesfield	SK103GR	Cheshire East	North West	Before 2011	50†	Development completed	12/1170M	02/04/2012	25/06/2012	Residential	No	15	21/01/2014	0	15	Yes	Unknown	0	0	0	0	0	0	15	0	1	2	12	0	0
PSLR0666	PLHP 1	DHSC	Maidstone Ambulance Station	Maidstone	ME15 9QB	Maidstone	South East	2013/2014	14	Development completed	13/1292	21/07/2013	19/09/2013	Mixed	No	8	23/01/2015	0	8	Yes	No	0	0	0	0	0	8	0	0	0	0	8	0	0
PSLR0667	PLHP 1	DHSC	Maidstone General Hospital	Magnolia House, Spingwood Road, Maidstone, Kent	ME16 9PB	Maidstone	South East	2013/2014	8	Development completed	x	x	x	Residential sale	No	8	x	x	8	Not applicable	Unknown	0	0	0	0	0	x	x	8	x	x	x	x	8
PSLR0668	PLHP 1	DHSC	Malvern Health Centre	Victoria Park Rd, Malvern	WR142NQ	Malvern Hills	West Midlands	Before 2011	16	Development completed	10/00007/FUL	17/12/2009	07/04/2010	Residential	No	14	08/05/2012	0	14	Yes	Yes	0	14	0	0	0	0	0	14	0	5	3	6	0
PSLR0669	PLHP 1	DHSC	Manor Gate Mental Health Resource Centre	1A Manor Gate, Northolt	UB5 5TG	Ealing	London	2013/2014	10	Development started	PP/2014/4398	22/08/2014	27/11/2014	Residential	No	11	x	0	2	Yes	No	0	0	0	0	0	0	0	2	0	0	0	2	0
PSLR0670	PLHP 1	DHSC	Maplewood	Tamworth Road, Keresley, Coventry	CV7 8JJ	Coventry	West Midlands	2014/2015	3	Development started	FUL/2014/3023	08/09/2014	28/10/2014	Residential	No	3	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	0	0	0	0	1
PSLR0671	PLHP 1	DHSC	Mary Seacole Nursery	52 Tollington Way, London	N7 6QX	Islington	London	2014/2015	9	Development completed	P2015/2900/FUL	27/07/2015	08/12/2015	Residential	No	15	31/08/2018	0	15	Yes	Yes	0	8	0	0	0	7	1	7	0	0	0	15	0
PSLR0672	PLHP 1	DHSC	Mascalls Park	Mascalls Lane, Brentwood, Essex	CM13 3AL	Brentwood	East	2013/2014	70	Development completed	13/01169/FUL,15/01187/FUL	11/11/2013	18/03/2014	Residential,Infill	No,No	77	30/07/2015	0	77	Yes,Yes	Yes,No	0	0	0	0	27	70	4	3	41	6	9	21	0
PSLR0673	PLHP 1	DHSC	Meir Health Centre	Meir Health Centre, Saracen Way, Meir, Stoke-on-Trent	ST3 7DS	Stoke-on-Trent	West Midlands	2013/2014	15	Development completed	61440/FUL	17/07/2017	16/10/2017	Residential	No	12	28/03/2019	0	12	Yes	No	0	0	0	0	0	12	0	0	0	12	0	0	0
PSLR0674	PLHP 1	DHSC	Melbourne House, Derby	Nooning Lane, Derby	DE72 3NZ	Erewash	East Midlands	2013/2014	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0675	PLHP 1	DHSC	Melton War Memorial Hospital	Ankle Hill, Melton Mowbray, Leicestershire	LE13 0QJ	Melton	East Midlands	2013/2014	98	Development started	13/00522/FUL	23/07/2013	26/01/2015	Residential	No	98	12/07/2017	9	49	Yes	No	0	0	0	0	0	11	4	34	30	2	8	9	0
PSLR0676	PLHP 1	DHSC	Minehead & West Somerset Community Hospital	Minehead	TA24 5LY	Somerset West and Taunton	South West	2014/2015	15	Development started	3/21/15/114	15/12/2015	30/09/2016	Mixed	No	4	19/12/2017	0	2	Yes	No	0	0	0	0	0	0	0	2	0	0	0	2	0
PSLR0677	PLHP 1	DHSC	Moat Croft	9 Moatcroft Road, Eastbourne, East Sussex	BN21 1NL	Eastbourne	South East	2013/2014	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0679	PLHP 1	DHSC	Moor Lane Centre	Moor Lane, Burley-in-Wharfedale, West Yorkshire	LS29 7SG	Bradford	Yorkshire and The Humber	2013/2014	38	Development completed	13/01241/MAF	28/03/2013	09/01/2014	Residential	No	37	16/07/2015	0	30	No	Yes	0	0	0	0	9	30	0	0	6	18	6	0	0
PSLR0680a	PLHP 1	DHSC	Moresdale Lane/Former Wilsons Arms Site	Leeds	LS14 6TL	Leeds	Yorkshire and The Humber	Before 2011	20	Development completed	15/01949/FU	23/04/2015	06/10/2016	Residential	No	16	07/10/2016	0	16	Yes	No	0	0	0	0	0	0	13	3	0	0	0	16	0
PSLR0680b	PLHP 1	DHSC	Moresdale Lane/Former Wilsons Arms Site	Leeds	LS14 6TL	Leeds	Yorkshire and The Humber	Before 2011	20†	Development started	16/03891/FU	21/06/2016	07/10/2016	Residential institute	No	10	04/01/2018	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0681	PLHP 1	DHSC	Morpeth Cottage Hospital	South Road, Morpeth, Northumberland	NE61 2BT	County Durham	North East	2014/2015	28	Development completed	15/02779/FUL	21/08/2015	04/02/2016	Residential	No	39	25/08/2017	0	39	Yes	Yes	0	0	0	0	6	28	6	5	19	6	0	14	0
PSLR0682	PLHP 1	DHSC	Musgrove Park Hospital	12 & 14 Avon Close, Galmington, Taunton	TA1 4SU	Taunton Deane	South West	2014/2015	2	Development completed	x	x	x	Residential sale	No	2	x	x	2	Not applicable	Unknown	0	0	0	0	0	x	x	2	x	x	x	x	2
PSLR0683	PLHP 1	DHSC	Nelson Hospital	Nelson Hospital, Kingston Road, West Wimbledon	SW20 8DB	Merton	London	2012/2013	50	Development completed	12/P0418	21/02/2012	18/12/2012	Residential	Yes	51	21/11/2014	0	51	Yes	No	0	0	0	0	0	0	51	0	0	0	0	51	0
PSLR0684	PLHP 1	DHSC	Netherfield Rd Family Health Clinic	Netherfield Rd, Liverpool	L5 3NW	Liverpool	North West	2012/2013	2	Planning stage	x	x	x	x	Unknown	0	x	x	x	Not applicable	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0685	PLHP 1	DHSC	Newbiggin Hall health Centre	Trevelyan Drive, Newcastle Upon Tyne	NE5 4BS	Newcastle upon Tyne	North East	2014/2015	10	Planning stage	2016/1364/01/DET	24/08/2016	x	Commercial	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0686	PLHP 1	DHSC	Newland House	Oak Lane, Twickenham	TW1 3PH	Richmond upon Thames	London	2013/2014	5	Development completed	13/1923/FUL	03/06/2013	25/02/2014	Residential	No	7	22/02/2016	0	7	Yes	No	0	0	0	0	0	1	6	0	0	0	0	7	0
PSLR0687	PLHP 1	DHSC	Newlands	3 Oak Hill Grove, Surbiton	KT66EN	Kingston upon Thames	London	2014/2015	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0688	PLHP 1	DHSC	Nightingale McMillan Continuing Care Unit	Trinity Street Derby	DE1 2RE	Derby	East Midlands	2011/2012	18	Development started	04/12/00520	04/05/2012	05/09/2012	Mixed	No	13	19/03/2012	0	1	Yes	No	0	0	0	0	0	0	0	1	0	0	0	0	1
PSLR0690	PLHP 1	DHSC	North Middlesex University Hospital NHS Trust	Sterling Way, London	N18 1QX	Enfield	London	2011/2012	81	Development completed	P12-02651REM	30/10/2012	04/04/2013	Residential	No	81	15/09/2015	0	81	Yes	Unknown	0	0	0	0	0	52	24	5	0	0	0	81	0
PSLR0693	PLHP 1	DHSC	Northgate Hospital	Morpeth, Northumberland	NE61 3BP	Northumberland	North East	2014/2015	210	Development started	11/01439/FUL	14/06/2011	15/12/2011	Mixed	Yes	225	22/02/2016	30	192	No	Unknown	0	0	0	0	0	110	0	82	152	37	3	0	0
PSLR0694	PLHP 1	DHSC	Northwick Park Road	16 Northwick Park Road, Harrow, HA1 2NU	HA1 2NU	Harrow	London	2014/2015	1	Planning stage	P/3051/16	08/08/2016	10/11/2016	Commercial	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0695	PLHP 1	DHSC	Nuffield Orthopaedic Centre	Girdlestone Close, Headington, Oxford	OX3 7LD	Oxford	South East	2013/2014	9	Development completed	x	x	x	Residential sale	Unknown	9	x	x	9	Not applicable	Unknown	0	0	0	0	0	x	x	9	x	x	x	x	9
PSLR0696	PLHP 1	DHSC	Oak Glade blocks 1-5	Manor Park, Epsom, Surrey	KT19 8NQ	Epsom and Ewell	South East	2012/2013	15	Development completed	14/00306/FUL	30/06/2014	25/09/2014	Residential	No	15	02/11/2015	0	15	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	15	0	0	0	0	15	0	0
PSLR0698	PLHP 1	DHSC	Oakhill Clinic	Oakhill Road, Surbiton	KT6 6EN	Kingston upon Thames	London	2014/2015	29	Planning stage	15/16883/FUL	30/10/2015	10/02/2017	Residential	No	41	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0699	PLHP 1	DHSC	Oaklands	103 Duffield Road, Derby	DE22 1AE	Derby	East Midlands	2014/2015	10	Development started	06/15/00809	02/07/2015	23/09/2016	Residential	No	10	17/10/2017	0	9	Yes	No	0	0	0	0	0	9	0	0	0	0	9	0	0
PSLR0700	PLHP 1	DHSC	Oaklands House	Oaklands House, Coulsdon Road, Caterham	CR3 5YA	Tandridge	South East	2011/2012	176	Development completed	2011/1117,2013/1347	22/08/2011	29/06/2012	Residential,Infill	No,No	163	06/09/2013	0	163	Yes,No	Yes,No	36	0	18	0	0	143	19	1	41	58	33	30	1
PSLR0701	PLHP 1	DHSC	Odsal Health Centre/ The Elms	Odsal Health Centre, 55 Odsal Road, Bradford, West Yorkshire	BD6 1PR	Bradford	Yorkshire and The Humber	2013/2014	1	Planning stage	12/03755/FUL	14/09/2012	15/11/2012	Residential	No	1	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0702	PLHP 1	DHSC	Old Heysham health centre	Middleton Way, Heysham, Morecambe	LA3 2LL	Lancaster	North West	2014/2015	10	Planning stage	15/00294/CU	16/03/2015	29/07/2015	Commercial	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0703	PLHP 1	DHSC	Old School House	41-45 Beadles Lane, Oxted	RH8 9JG	Tandridge	South East	2013/2014	2	Development completed	2015/2252	21/12/2015	06/06/2016	Residential	No	6	18/08/2017	0	6	Yes	No	0	0	0	0	0	6	0	0	2	4	0	0	0
PSLR0704	PLHP 1	DHSC	Orchard Hills Residential Land	Fallow Field Road Walsall	WS5 3DY	Walsall	West Midlands	2013/2014	2	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0705	PLHP 1	DHSC	Orford Clinic	Capesthorne Rd, Warrington	WA2 9AR	Warrington	North West	2014/2015	10	Development started	2015/25355	26/02/2015	29/04/2015	Residential institute	No	8	x	0	1	Yes	No	0	0	0	0	0	0	0	1	0	0	0	0	1
PSLR0706	PLHP 1	DHSC	Osborne House,	245 The Ridge, Hastings, East Sussex	TN34 2AE	Hastings	South East	2012/2013	55	Development completed	HS/FA/13/00322	02/05/2013	17/12/2013	Residential	No	55	11/11/2014	0	55	Yes	Yes	0	0	0	0	34	40	15	0	14	2	31	8	0
PSLR0707	PLHP 1	DHSC	Oswestry Ambulance Station	Morda Road, Oswestry, Shropshire	SY10 9PL	Shropshire	West Midlands	2013/2014	7	Development started	14/00721/FUL	25/02/2014	14/07/2014	Residential	No	7	25/10/2016	0	6	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	5	0	1	6	0	0	0	0
PSLR0708	PLHP 1	DHSC	Oswestry Health Centre	Thomas Savin Road, Oswestry, Shropshire	SY11 1GA	Shropshire	West Midlands	2014/2015	15	Development completed	x	x	x	Residential sale	Unknown	15	x	x	15	Not applicable	Unknown	0	0	0	0	0	x	x	15	x	x	x	x	15
PSLR0709	PLHP 1	DHSC	Park Road, Bridport, Dorset	BridportÃ‚Â Ã‚Â	DT6 5DA	West Dorset	South West	Before 2011	2	Development completed	1/D/09/000475	03/04/2009	20/05/2009	Residential	No	4	21/02/2012	0	4	Yes	No	0	0	0	0	0	4	0	0	0	0	4	0	0
PSLR0710	PLHP 1	DHSC	Part Harperbury Hospital, Radlett	Harperbury Hospital, Harper Lane, Radlett	WD7 9HQ	St Albans	East	2014/2015	206	Development started	5/2015/0990	02/04/2015	26/05/2017	Residential	No	206	08/07/2019	32	22	No	Unknown	0	0	0	0	0	8	0	14	4	10	8	0	0
PSLR0711	PLHP 1	DHSC	Part of the Carleton Clinic Site, Westmorland House, Cumberland House and the Coppice	Cumwhinton Drive, Carlisle, Cumbria	CA1 3SX	Carlisle	North West	2014/2015	198	Development started	15/0918	05/10/2015	04/05/2016	Residential	No	189	12/06/2017	9	139	Yes	Yes	0	0	0	0	30	124	4	11	67	56	16	0	0
PSLR0712a	PLHP 1	DHSC	Patient Advivce Liaison Service	117 -119 Uxbridge Road, Hanwell	W7 3ST	Ealing	London	2013/2014	2	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0712b	PLHP 1	DHSC	Patient Advivce Liaison Service	117 -119 Uxbridge Road, Hanwell	W7 3ST	Ealing	London	2013/2014	2†	Development completed	PP/2015/1117	02/03/2015	26/08/2016	Residential	No	2	04/12/2018	0	2	Yes	No	0	0	0	0	0	0	0	2	0	0	0	2	0
PSLR0713	PLHP 1	DHSC	Pattens Lane	20 Pattens Lane, Rochester	ME4 6JS	Medway	South East	2014/2015	1	Development completed	MC/15/3682	13/10/2015	08/06/2016	Residential	No	1	21/02/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	0	0	0	0	1
PSLR0714	PLHP 1	DHSC	Peel House	Avenue Parade, Accrington	BB5 6RD	Hyndburn	North West	2014/2015	4	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0716	PLHP 1	DHSC	Peterborough District Hospital and Maternity Unit	3 Thorpe Road, Peterborugh	PE3 6DA	Peterborough	East	2013/2014	350	Development started	14/00536/OUT	02/04/2014	31/10/2014	Mixed	No	350	29/07/2016	18	173	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	123	38	12	25	80	25	43	0
PSLR0717	PLHP 1	DHSC	Phoenix House	Brentry Lane, Westbury-on-Trym, Bristol	BS10 6NB	Bristol	South West	2013/2014	80	Development completed	13/04558/M	30/09/2013	27/03/2014	Residential	No	80	23/11/2015	0	77	Yes	Yes	0	9	6	0	0	47	25	5	1	12	30	30	4
PSLR0718	PLHP 1	DHSC	Pine Lodge	Manor Park, Epsom, Surrey	KT19 8PQ	Epsom and Ewell	South East	2013/2014	10	Development completed	14/00032/FUL	07/04/2014	20/06/2014	Residential	No	10	03/01/2017	0	10	Yes	No	0	0	0	0	0	1	0	9	8	2	0	0	0
PSLR0719	PLHP 1	DHSC	Plaistow Hospital	Samson Street, Plaistow Newham	E13 9JD	Newham	London	2011/2012	169	Development completed	12/01892/FUL	17/10/2012	28/03/2013	Residential	No	169	22/06/2015	0	168	Yes	Yes	0	0	0	0	59	54	85	29	2	0	47	119	0
PSLR0720	PLHP 1	DHSC	Plympton Hospital	Market Road, Plymouth, Devon	PL7 1QR	Plymouth	South West	2014/2015	47	Development started	16/02233/FUL	15/11/2016	01/03/2017	Residential	No	54	11/01/2018	0	54	Yes	Yes	8	0	8	0	0	45	9	0	0	40	14	0	0
PSLR0721	PLHP 1	DHSC	Poole House	Stokesley Road, Nunthorpe, Middlesbrough	TS7 0NJ	Middlesbrough	North East	2012/2013	16	Development completed	M/FP/1206/12/P	11/12/2012	04/02/2013	Residential	No	16	25/11/2013	0	16	Yes	No	0	0	0	0	0	16	0	0	16	0	0	0	0
PSLR0722	PLHP 1	DHSC	Prescot Clinic	Park Road, Prescot	L34 3LN	Knowsley	North West	2012/2013	2	Development completed	12/00286/FUL	10/10/2012	29/11/2012	Residential	No	2	19/03/2012	0	2	Yes	No	0	0	0	0	0	1	0	1	1	1	0	0	0
PSLR0723	PLHP 1	DHSC	Preston Hall	London Road, Aylesford, Kent	ME20 7NH	Tonbridge and Malling	South East	2013/2014	208	Development started	14/01505/RM	17/04/2014	19/12/2014	Residential	No	208	10/02/2016	0	176	Yes	Yes	0	48	20	0	0	152	22	2	53	26	44	53	0
PSLR0724a	PLHP 1	DHSC	Princess Marina Hospital	Upton, Northampton,Northamptonshire	NN5 6UH	Northampton	East Midlands	2011/2012	535	Development completed	N/2012/0660	09/07/2012	08/10/2012	Residential	No	53	09/09/2013	0	53	No	Yes	0	0	0	0	8	45	8	0	32	5	16	0	0
PSLR0724b	PLHP 1	DHSC	Princess Marina Hospital	Upton, Northampton,Northamptonshire	NN5 6UH	Northampton	East Midlands	2011/2012	535†	Development completed	N/2012/0698	11/07/2012	10/10/2012	Residential	No	63	23/10/2013	0	63	No	Yes	0	0	0	0	22	54	9	0	27	20	16	0	0
PSLR0724c	PLHP 1	DHSC	Princess Marina Hospital	Upton, Northampton,Northamptonshire	NN5 6UH	Northampton	East Midlands	2011/2012	535†	Development completed	N/2012/1198	11/12/2012	12/03/2013	Residential	No	29	04/06/2014	0	24	No	Yes	0	0	0	0	17	24	0	0	5	4	3	12	0
PSLR0724d	PLHP 1	DHSC	Princess Marina Hospital	Upton, Northampton,Northamptonshire	NN5 6UH	Northampton	East Midlands	2011/2012	535†	Development completed	N/2013/0759	15/08/2013	31/10/2013	Residential	No	106	04/06/2014	0	106	No	Yes	0	0	0	0	40	85	13	8	49	32	25	0	0
PSLR0724e	PLHP 1	DHSC	Princess Marina Hospital	Upton, Northampton,Northamptonshire	NN5 6UH	Northampton	East Midlands	2011/2012	535†	Development completed	N/2014/1396	04/12/2014	04/03/2015	Residential	No	107	27/07/2015	0	107	No	Yes	0	0	0	0	36	92	3	12	26	51	21	9	0
PSLR0724f	PLHP 1	DHSC	Princess Marina Hospital	Upton, Northampton,Northamptonshire	NN5 6UH	Northampton	East Midlands	2011/2012	535†	Development completed	N/2015/0680	09/07/2015	03/12/2015	Residential	No	114	03/08/2016	0	114	No	Yes	0	0	0	0	42	97	12	5	23	44	20	27	0
PSLR0724g	PLHP 1	DHSC	Princess Marina Hospital	Upton, Northampton,Northamptonshire	NN5 6UH	Northampton	East Midlands	2011/2012	535†	Development completed	N/2016/0812	08/07/2016	07/10/2016	Residential	No	15	03/01/2018	0	15	No	Yes	0	0	0	0	6	15	0	0	1	0	0	6	8
PSLR0724h	PLHP 1	DHSC	Princess Marina Hospital	Upton, Northampton,Northamptonshire	NN5 6UH	Northampton	East Midlands	2011/2012	535†	Development completed	N/2014/0558	03/06/2014	15/09/2014	Residential	No	63	21/05/2015	0	63	No	Yes	0	0	0	0	22	51	2	10	7	32	24	0	0
PSLR0725	PLHP 1	DHSC	Princess Royal Hospital	Saltshouse Road,Ã‚Â Hull	HU8 9HE	Kingston upon Hull	Yorkshire and The Humber	2012/2013	104	Development completed	12/00858/RES	14/09/2012	09/01/2013	Residential	No	103	09/09/2013	0	103	Yes	No	0	0	0	0	0	95	0	8	91	12	0	0	0
PSLR0726	PLHP 1	DHSC	Progress House	36-38 Kimbolton Road, Bedford	MK40 2NS	Bedford	East	2013/2014	6	Development started	14/02672/COU	23/10/2014	30/04/2015	Residential	No	17	19/03/2012	0	2	Yes	No	0	0	0	0	0	2	0	0	0	0	2	0	0
PSLR0727	PLHP 1	DHSC	Prospect House	3 Prospect Road, Barrow in Furness, Cumbria	LA13 9AA	Barrow-in-Furness	North West	2013/2014	1	Development completed	B26/2014/0161	28/02/2014	03/04/2014	Residential	No	1	x	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0728a	PLHP 1	DHSC	Prudhoe Hospital	Prudhoe, Northumberland	NE42 5NT	Northumberland	North East	2012/2013	74	Development completed	12/01815/REM	07/06/2012	23/10/2012	Residential	No	60	10/12/2012	0	60	Yes	Yes	4	0	9	0	0	59	1	0	43	14	3	0	0
PSLR0728b	PLHP 1	DHSC	Prudhoe Hospital	Prudhoe, Northumberland	NE42 5NT	Northumberland	North East	2012/2013	74†	Development completed	12/02490/FUL	10/08/2012	25/04/2013	Residential	No	5	29/06/2016	0	5	Yes	No	0	0	0	0	0	5	0	0	5	0	0	0	0
PSLR0728c	PLHP 1	DHSC	Prudhoe Hospital	Prudhoe, Northumberland	NE42 5NT	Northumberland	North East	2012/2013	74†	Development completed	14/01047/FUL	09/04/2014	24/06/2014	Residential	No	9	20/01/2016	0	9	Yes	No	0	0	0	0	0	9	0	0	9	0	0	0	0
PSLR0729	PLHP 1	DHSC	Putney Hospital	Former Putney Hospital site, Lower Richmond Road, Putney	SW15 1HP	Wandsworth	London	2011/2012	24	Development completed	2012/0758	26/07/2012	13/12/2013	Mixed	No	24	14/02/2017	0	24	Yes	No	0	0	0	0	0	0	24	0	0	0	0	24	0
PSLR0730	PLHP 1	DHSC	QEII Hospital	QEII Hospital, Howlands, Welwyn Garden City, Herts	AL7 4RJ	Welwyn Hatfield	East	2014/2015	163	Development started	6/2015/1901/RM	09/09/2015	15/02/2016	Residential	No	163	18/09/2017	0	162	Yes	Yes	0	0	0	0	49	96	64	2	12	46	39	65	0
PSLR0731	PLHP 1	DHSC	Queen Mary's Hospital, Area 3	Frognal Avenue, Sidcup	DA14 6LT	Bexley	London	2014/2015	83	Development started	13/00593/FULM	17/04/2013	26/11/2013	Mixed	No	107	17/04/2019	0	75	Yes	No	0	0	0	0	0	0	0	75	0	0	0	0	75
PSLR0732	PLHP 1	DHSC	Ramsbottom Cottage Hospital	Nuttall Lane, Bury, Lancashire	BL0 9JZ	Bury	North West	2014/2015	14	Development completed	58022	30/09/2014	15/01/2015	Residential	No	13	14/12/2015	0	13	Yes	No	0	0	0	0	0	0	13	0	13	0	0	0	0
PSLR0733	PLHP 1	DHSC	Rannoch Lodge	146 Broomfields Road, Chelmsford	CM1 1RN	Chelmsford	East	2013/2014	1	Development completed	13/01417/FUL	05/11/2013	18/12/2013	Residential	No	1	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0734	PLHP 1	DHSC	Rauceby Hospital, Lincolnshire	Sleaford	NG348GF	North Kesteven	East Midlands	Before 2011	196	Planning stage	11/0518/FULEXT	13/05/2011	04/08/2011	Mixed	Unknown	58	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0735	PLHP 1	DHSC	Redcliffe Day Hospital	49-51 Hatton Park Road, Wellingborough, Northamptonshire	NN8 5AH	Wellingborough	East Midlands	2014/2015	4	Planning stage	WP/16/00268/FUL	14/07/2017	12/09/2017	Residential	No	4	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0736a	PLHP 1	DHSC	Ridgewood Centre	Ridgewood Centre, Old Bisley Road, Frimley	GU16 9QE	Surrey Heath	South East	2013/2014	120	Development started	14/0800	28/08/2014	01/04/2015	Residential	No	100	25/04/2016	0	102	Yes	Mix of pay and houses	0	15	15	0	0	77	7	18	44	19	10	29	0
PSLR0736b	PLHP 1	DHSC	Ridgewood Centre	Ridgewood Centre, Old Bisley Road, Frimley	GU16 9QE	Surrey Heath	South East	2013/2014	120†	Development completed	12/0239	03/04/2012	13/12/2012	Residential	No	12	19/03/2012	0	12	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	11	0	1	12	0	0	0	0
PSLR0737	PLHP 1	DHSC	Rivendale	Rivendale, 38 Columbus Drive, Sarisbury Green,	SO31 7LW	Fareham	South East	2013/2014	12	Development completed	P/13/0477/DP/A	27/08/2013	08/11/2013	Residential	No	12	23/01/2015	0	12	Yes	Yes	3	0	0	0	0	12	0	0	1	2	9	0	0
PSLR0738	PLHP 1	DHSC	Roe Farm Clinic	Winchester Crescent, Chaddesdan, Derby	DE21 4EN	Derby	East Midlands	2011/2012	3	Development completed	10/11/01192	19/10/2011	14/12/2011	Residential	No	6	03/09/2013	0	6	Yes	No	0	0	0	0	0	4	0	2	0	0	0	6	0
PSLR0739	PLHP 1	DHSC	Roselands Resource Centre	163B Kingston Rd, New Malden	KT3 3NN	Kingston upon Thames	London	2013/2014	32	Planning stage	17/14185	13/02/2017	x	Commercial	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0740	PLHP 1	DHSC	Rossendale Hospital	Rossendale	BB4 6SW	Rossendale	North West	2013/2014	139	Development completed	2012/0162	28/03/2012	01/08/2013	Residential	No	139	02/04/2014	0	132	Yes	Yes	0	7	21	0	0	24	108	0	105	27	0	0	0
PSLR0741.1	PLHP 1	DHSC	Rosslyn House	The Drive, Hellingly, Hailsham, East Sussex	BN27 4EP	Wealden	South East	2013/2014	1	Development completed	WD/2014/0265/F	06/02/2014	09/04/2014	Residential	No	2	x	x	x	Yes	No	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0741.2	PLHP 1	DHSC	Rosslyn House	The Drive, Hellingly, Hailsham, East Sussex	BN27 4EP	Wealden	South East	2013/2014	1	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0741a	PLHP 1	DHSC	Rosslyn House	The Drive, Hellingly, Hailsham, East Sussex	BN27 4EP	Wealden	South East	2013/2014	1	Development completed	WD/2013/1245/F	17/06/2013	09/08/2013	Residential	No	1	19/03/2012	0	1	Yes	No	0	0	0	0	0	0	0	1	1	0	0	0	0
PSLR0741b	PLHP 1	DHSC	Rosslyn House	The Drive, Hellingly, Hailsham, East Sussex	BN27 4EP	Wealden	South East	2013/2014	1†	Development completed	WD/2014/1558/F	23/07/2014	18/09/2014	Residential	No	1	12/02/2016	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0741c	PLHP 1	DHSC	Rosslyn House	The Drive, Hellingly, Hailsham, East Sussex	BN27 4EP	Wealden	South East	2013/2014	1†	Development completed	WD/2014/0265/F	06/02/2014	09/04/2014	Residential	No	2	12/02/2016	0	2	Yes	No	0	0	0	0	0	2	0	0	2	0	0	0	0
PSLR0742	PLHP 1	DHSC	Ross-On-Wye Ambulance Station	The Mead, Ross on Wye	HR9 7NF	Herefordshire	West Midlands	2012/2013	8	Development started	S122195/F,132295	06/08/2012	30/01/2013	Residential,Infill	No,No	12	26/08/2014	0	10	Yes,Unknown	No,No	0	0	0	0	0	0	0	10	1	6	0	3	0
PSLR0743	PLHP 1	DHSC	Royal Hospital, former Royal Hospital and Bus Depot Site,	Cleveland Road, All Saints, Wolverhampton, West Midlands	WV2 1BP	Wolverhampton	West Midlands	Before 2011	200	Planning stage	17/01209/FUL	13/10/2017	x	Mixed	No	192	x	x	x	Yes	No	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0744	PLHP 1	DHSC	Royal Manchester Childrens Hospital	Hospital Road, Pendlebury, Salford, Manchester	M27 4HA	Salford	North West	2011/2012	229	Development completed	11/60470/REM,12/62556/FUL,12/62419/FUL,13/63994/FUL	31/05/2011	15/09/2011	Residential,Infill,Infill,Infill	No,No,No,No	244	14/05/2012	0	244	Yes,Not applicable,Not applicable,Not applicable	Yes,No,No,No	7	17	22	0	0	41	201	2	82	71	81	9	1
PSLR0745	PLHP 1	DHSC	Rugby Ambulance Station	Rugby	CV211HL	Rugby	West Midlands	2013/2014	28	Development completed	R13/1169	30/09/2013	28/03/2014	Residential	No	29	23/06/2015	0	29	Yes	Yes	0	19	10	0	0	0	10	19	0	0	21	8	0
PSLR0746	PLHP 1	DHSC	Rushbrook House	Royd St, Milnsbridge, Huddersfield	HD3 4RB	Kirklees	Yorkshire and The Humber	2014/2015	2	Development started	2014/62/93204/W	09/10/2014	04/12/2014	Residential institute	No	2	19/03/2012	0	1	Yes	No	0	0	0	0	0	0	0	1	0	0	0	0	1
PSLR0747	PLHP 1	DHSC	Rushden Hospital	Wymington Road, Rushden, Northamptonshire	NN10 9JS	East Northamptonshire	East Midlands	2012/2013	125	Development started	10/01017/OUT	24/03/2017	19/05/2017	Mixed	Unknown	125	24/01/2018	0	4	Yes	Yes	0	17	8	0	0	4	0	0	4	0	0	0	0
PSLR0748	PLHP 1	DHSC	Rushden Memorial Clinic	The Hayway, Rushden, Northants	NN10 6AG	East Northamptonshire	East Midlands	2014/2015	8	Planning stage	19/00594/FUL	10/04/2018	29/07/2019	Residential	No	14	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0749	PLHP 1	DHSC	Sand Ends Health Centre	170 Wandsworth Bridge Road, London	SW6 2UQ	Hammersmith and Fulham	London	2014/2015	2	Development completed	2016/00134/FUL	13/01/2016	18/03/2016	Mixed	No	3	19/01/2018	0	3	Yes	No	0	0	0	0	0	0	0	3	0	0	0	3	0
PSLR0750	PLHP 1	DHSC	Selbrook	19 Washpool ,West Swindon	SN5 3PN	Wiltshire	South West	2013/2014	1	Development completed	N/10/01493/FUL	27/04/2010	21/06/2010	Residential	No	1	21/02/2012	0	1	No	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0751	PLHP 1	DHSC	Selly Oak Hospital	Raddlebarn Road, Selly Oak, Birmingham	B29 6JA	Birmingham	West Midlands	2014/2015	650	Development started	2012/02303/PA	20/04/2012	14/10/2013	Residential	No	650	05/03/2015	19	359	Yes	Yes	57	0	28	0	28	68	259	32	43	106	51	129	30
PSLR0752	PLHP 1	DHSC	Sevenoaks Ambulance Station	Sevenoaks	TN14 5EB	Sevenoaks	South East	2013/2014	11	Development completed	14/00494/MMA	18/02/2014	20/05/2014	Residential	No	11	26/10/2015	0	11	Yes	No	0	0	0	0	0	1	9	1	0	5	4	2	0
PSLR0753b	PLHP 1	DHSC	Sheila Henry Centre (Bryan-Sutherland House)	Dunnock Avenue, Bradford, West Yorkshire	BD6 3HX	Bradford	Yorkshire and The Humber	2012/2013	10	Development completed	12/00049/FUL,13/01339/FUL	07/01/2012	04/04/2012	Residential,Infill	No,No	12	03/11/2014	0	12	Yes,Not applicable	No,No	0	0	0	0	0	3	0	9	1	0	9	2	0
PSLR0754b	PLHP 1	DHSC	Shelton Hospital	Bicton Heath, Shrewsbury, Shropshire	SY3 8DN	Shropshire	West Midlands	2013/2014	194	Planning stage	16/05797/FUL	09/01/2017	02/05/2017	Residential	No	12	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0755	PLHP 1	DHSC	Sheridan Road	75 Sheridan Road	HR4 0NH	Herefordshire	West Midlands	2014/2015	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0756	PLHP 1	DHSC	Shrubbery Avenue Rehab Hostel	11 Shrubbery Avenue, Worcester	WR1 1QN	Worcester	West Midlands	2014/2015	1	Development completed	P14A0120	19/03/2014	14/05/2014	Residential	No	1	21/02/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0757	PLHP 1	DHSC	Site adjacent to South Shore Primary Care Centre. Land only.	Stonyhill Avenue, South Shore, Blackpool	FY4 1PN	Blackpool	North West	2013/2014	8	Development started	16/0493	09/08/2016	29/09/2016	Residential	No	8	06/11/2019	0	8	Yes	No	0	0	0	0	0	6	0	2	0	2	6	0	0
PSLR0758	PLHP 1	DHSC	South Elmshall Health Centre	Pontefract	WF9 2NJ	Wakefield	Yorkshire and The Humber	2013/2014	6	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0759	PLHP 1	DHSC	Southall/ Norwood Mental Health Resource Centre	The Green, Southall	UB2 4BL	Ealing	London	2014/2015	18	Development started	PP/2013/5409,173151FUL	27/11/2013	03/06/2014	Residential,Infill	No,No	21	04/04/2019	0	21	Yes,Not applicable	No,No	0	0	0	0	0	18	0	3	0	0	6	15	0
PSLR0760	PLHP 1	DHSC	Southampton Podiatry Centre	7 Archers Road	SO15 2LQ	Southampton	South East	2014/2015	10	Development completed	13/01308/FUL	19/08/2013	17/04/2014	Residential	No	14	26/08/2015	0	14	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	4	10	0	1	3	1	9	0
PSLR0761	PLHP 1	DHSC	Southfield Hall, Anexe & Town Houses	Stafford Road, Halifax	HX3 0PA	Calderdale	Yorkshire and The Humber	2013/2014	14	Development completed	13/01393/FUL	08/11/2013	06/08/2014	Residential	No	14	24/06/2017	0	14	Yes	No	0	0	0	0	0	13	0	1	0	0	14	0	0
PSLR0762	PLHP 1	DHSC	Southlands Hospital	Upper Shoreham Road, Shoreham-by-Sea, West Sussex	BN43 6TQ	Adur	South East	2014/2015	106	Development completed	AWDM/1200/15	07/08/2015	06/11/2015	Residential	No	106	07/07/2016	0	106	Yes	Yes	0	0	0	0	32	63	42	1	9	18	37	42	0
PSLR0763	PLHP 1	DHSC	Southport and Formby District General Hospital	Town Lane, Southport, Merseyside	PR8 6PN	Sefton	North West	2012/2013	110	Development started	S/2012/0008	06/01/2012	07/03/2013	Mixed	No	110	20/01/2020	7	0	No	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0764a	PLHP 1	DHSC	Sports Field, Kingsway Hospital	Sports Field to Kingsway Site, Kingsway Site, Kingsway, Derby	DE22 3LZ	Derby	East Midlands	2013/2014	20	Development started	08/16/01056	26/08/2016	08/03/2017	Residential	No	172	05/03/2018	38	112	Yes	Yes	0	0	0	0	28	104	7	1	10	18	23	61	0
PSLR0764b	PLHP 1	DHSC	Sports Field, Kingsway Hospital	Sports Field to Kingsway Site, Kingsway Site, Kingsway, Derby	DE22 3LZ	Derby	East Midlands	2013/2014	20†	Development completed	10/12/01240	12/10/2012	20/06/2013	Residential	Yes	100	14/03/2014	0	99	Yes	Yes	20	0	0	0	0	90	5	4	16	29	54	0	0
PSLR0764c	PLHP 1	DHSC	Sports Field, Kingsway Hospital	Sports Field to Kingsway Site, Kingsway Site, Kingsway, Derby	DE22 3LZ	Derby	East Midlands	2013/2014	20†	Development completed	07/14/01024	25/07/2014	29/10/2014	Residential	Yes	110	03/05/2016	0	110	Yes	Yes	24	0	0	0	0	64	46	0	20	12	39	39	0
PSLR0765	PLHP 1	DHSC	Springside	Springside, 2 Spring Lane, Walsall	WS4 1AZ	Walsall	West Midlands	2014/2015	16	Development started	16/0148	17/02/2016	14/06/2016	Residential	No	18	29/10/2018	0	6	Yes	No	0	0	0	0	0	0	0	6	0	0	0	6	0
PSLR0766	PLHP 1	DHSC	St Ann's Health Centre	2 Livingstone Road, Nottingham, NG3 3GG	NG3 3GG	Nottingham	East Midlands	2013/2014	8	Development completed	13/02738/PFUL3	13/11/2013	28/01/2014	Mixed	Yes	45	14/08/2015	0	0	No	Yes	45	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0767	PLHP 1	DHSC	St Bernards Wing 1	St Bernards Site, Uxbridge Road, Southall	UB1 3EU	Ealing	London	2013/2014	270	Development started	PP/2012/3827	01/10/2012	08/05/2013	Mixed	Yes	306	09/04/2014	0	13	Yes	Yes	0	50	24	0	0	0	10	3	0	0	0	13	0
PSLR0769	PLHP 1	DHSC	St Clement Vean	3 St Clement Vean	TR1 1RN	Cornwall	South West	2013/2014	4	Planning stage	PA14/11698	09/12/2014	29/01/2015	Commercial	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0770	PLHP 1	DHSC	St Davids Health Centre	Hadrian Way, Stanwell, Staines	TW19 7HU	Spelthorne	South East	2014/2015	14	Development completed	15/00559/FUL	21/04/2015	30/07/2015	Residential	No	12	14/06/2017	0	12	Yes	No	0	0	0	0	0	7	5	0	0	0	6	6	0
PSLR0771	PLHP 1	DHSC	St Edwards Hospital	Cheadle Rd, Cheddleton, Leek, Staffordshire ST13 7EB	ST13 7EB	Staffordshire Moorlands	West Midlands	Before 2011	160	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0772a	PLHP 1	DHSC	St Giles and Sheldon Centre	St Giles Road	SE5 7RN	Southwark	London	2011/2012	10	Development completed	09/AP/2332	19/10/2009	26/01/2011	Residential	No	12	26/07/2013	0	12	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	12	0	0	0	0	12	0
PSLR0772b	PLHP 1	DHSC	St Giles and Sheldon Centre	St Giles Road	SE5 7RN	Southwark	London	2011/2012	10†	Development completed	11/AP/0196	25/01/2011	12/05/2011	Residential	No	9	26/07/2013	0	9	Yes	Yes	0	0	0	0	3	9	0	0	0	0	9	0	0
PSLR0773	PLHP 1	DHSC	St James - The Orchards	Locksway Rd, Milton, Portsmouth	PO4 8FE	Portsmouth	South East	2014/2015	31	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0774	PLHP 1	DHSC	St James' Court	Florence Way, London	SW12 8EW	Wandsworth	London	2011/2012	33	Development completed	2012/3610	09/08/2012	29/10/2012	Residential	No	31	23/07/2014	0	31	Yes	Yes	7	0	3	0	0	0	30	1	0	0	0	31	0
PSLR0775	PLHP 1	DHSC	St James Hospital	Locksway Rd, Milton, Portsmouth	PO4 8LD	Portsmouth	South East	2013/2014	13	Development completed	13/00407/REM	22/04/2013	20/06/2013	Residential	No	13	03/02/2014	0	13	Yes	No	0	0	0	0	0	10	3	0	3	2	5	0	3
PSLR0776a	PLHP 1	DHSC	St John Street Health Centre	24 St John Street, Mansfield	NG18 1QJ	Mansfield	East Midlands	2014/2015	20	Development completed	2015/0267/ST	12/05/2015	02/10/2015	Residential	No	8	24/03/2017	0	8	Yes	No	0	0	0	0	0	8	0	0	0	0	8	0	0
PSLR0776b	PLHP 1	DHSC	St John Street Health Centre	24 St John Street, Mansfield	NG18 1QJ	Mansfield	East Midlands	2014/2015	20†	Development completed	2016/0005/ST	06/01/2016	23/06/2016	Residential	No	7	24/03/2017	0	6	Yes	No	0	0	0	0	0	6	0	0	0	6	0	0	0
PSLR0777	PLHP 1	DHSC	St Lukes Hospital	Woodside Avenue	N10 3HU	Haringey	London	2011/2012	100	Development completed	HGY/2013/2379	15/11/2013	24/04/2014	Mixed	Yes	161	05/04/2017	0	161	Yes	Yes	35	0	13	0	0	24	135	2	0	4	16	141	0
PSLR0778	PLHP 1	DHSC	St Mary's Hospital	Milton Road, Portsmouth	PO3 6AD	Portsmouth	South East	2012/2013	251	Development started	13/01120/REM	10/10/2013	16/01/2014	Mixed	No	251	15/05/2014	0	192	Yes	Yes	40	0	17	0	0	174	17	1	63	88	40	0	1
PSLR0779a	PLHP 1	DHSC	St Mary's Hospital, Green Lane, Stannington	Stannington	NE61 6BL	Northumberland	North East	Before 2011	172	Development started	CM/20080874,14/03197/FUL	08/12/2008	01/10/2009	Mixed,Infill	No,No	265	22/11/2012	37	247	Yes,Not applicable	Unknown,Developer paid local authority to put them somewhere else	0	0	0	0	0	199	43	5	117	28	45	52	5
PSLR0779c	PLHP 1	DHSC	St Mary's Hospital, Green Lane, Stannington	Stannington	NE61 6BL	Northumberland	North East	Before 2011	172†	Development completed	11/02980/FUL	15/11/2011	08/11/2012	Residential	No	73	25/10/2013	0	77	Unknown	Unknown	0	0	0	0	0	77	0	0	77	0	0	0	0
PSLR0780	PLHP 1	DHSC	St Oswald's Hospital	Belle Vue Road, Ashbourne, Derbyshire	DE6 1AU	Derbyshire Dales	East Midlands	2013/2014	30	Development completed	12/00606/FUL	09/10/2012	18/10/2013	Residential	No	30	05/02/2015	0	30	Yes	Yes	0	12	0	0	0	29	1	0	18	4	0	8	0
PSLR0781	PLHP 1	DHSC	St Thomas Hospital	Shaw Heath, Stockport	SK3 8BL	Stockport	North West	2014/2015	76	Development completed	DC/060491	07/12/2015	20/01/2017	Residential	No	59	20/09/2018	0	59	Yes	Yes	28	0	31	0	0	0	31	28	0	10	37	12	0
PSLR0782	PLHP 1	DHSC	Stairfoot Clinic	Hunningley Close, Stairfoot, Barnsley	S70 3DP	Barnsley	Yorkshire and The Humber	2013/2014	12	Development completed	2015/0892	20/07/2015	19/10/2015	Residential	No	10	13/01/2017	0	10	Yes	No	0	0	0	0	0	10	0	0	0	0	10	0	0
PSLR0783	PLHP 1	DHSC	Stanleyfield Road	19 Stanleyfield Road, Preston	PR1 1QL	Preston	North West	2013/2014	2	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0784	PLHP 1	DHSC	Station Approach Clinic	Bexleyheath	DA16 3AT	Bexley	London	2013/2014	1	Planning stage	18/00852/FUL	10/04/2018	20/09/2018	Residential	No	5	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0785	PLHP 1	DHSC	Stead Memorial Hospital	Kirkleatham Street, Redcar	TS10 1QR	Redcar and Cleveland	North East	2012/2013	89	Development started	R/2012/0838/CAM	07/11/2012	19/03/2013	Residential institute	No	89	20/10/2014	0	3	Yes	No	0	0	0	0	0	0	0	3	0	0	0	2	1
PSLR0786	PLHP 1	DHSC	Stewart Street	136 Stewart St, Crewe	CW2 8LY	Cheshire East	North West	2014/2015	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0787	PLHP 1	DHSC	Stoke Mandeville Hospital - land	Stoke Mandeville	HP219EP	Aylesbury Vale	South East	Before 2011	200	Development completed	07/00778/APP	20/03/2007	26/02/2008	Residential	No	330	17/06/2008	0	330	Yes	Yes	16	0	6	0	0	259	71	0	2	6	216	106	0
PSLR0788	PLHP 1	DHSC	Stone Cross Clinic	Jervoise Lane, West Bromwich	B71 3AR	Sandwell	West Midlands	2014/2015	2	Planning stage	x	x	x	Permitted development	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0789	PLHP 1	DHSC	Stonelea (Langthorne Hospital)	Lamgthorne Hospital, Langthorne Rd,Leytonstone London	E11 4JZ	Waltham Forest	London	2014/2015	38	Development started	153090	10/10/2015	06/03/2017	Residential	Yes	79	19/12/2019	0	0	Yes	Yes	0	19	5	0	0	0	0	0	0	0	0	0	0
PSLR0790	PLHP 1	DHSC	Stourbridge Ambulance Station	Margaret Drive, Stourbridge, West Midlands	DY8 1NE	Dudley	West Midlands	2012/2013	4	Development completed	P12/0918	13/08/2012	11/10/2012	Residential	No	4	21/10/2013	0	4	Yes	No	0	0	0	0	0	4	0	0	4	0	0	0	0
PSLR0791	PLHP 1	DHSC	Stourmead Site	Stourmead Close, Mill Road, Kedington, Haverhill	CB9 7PA	St Edmundsbury	East	2012/2013	80	Development completed	SE/13/0196/FUL	11/02/2013	16/10/2013	Residential	No	63	14/10/2014	0	63	Yes	Mix of pay and houses	14	0	0	0	0	60	0	3	32	10	21	0	0
PSLR0792	PLHP 1	DHSC	Stowford	Stowford, Withdean Road, Brighton	BN1 5BL	Brighton and Hove	South East	2014/2015	1	Development completed	BH2015/00386,BH2017/03342	06/02/2015	20/07/2015	Mixed,Infill	No,No	8	27/01/2018	0	8	Yes,Unknown	No,No	0	0	0	0	0	0	0	8	0	0	0	3	5
PSLR0793	PLHP 1	DHSC	Sudbury health centre	Acton Lane, Sudbury	CO1 1QN	Babergh	East	2014/2015	4	Planning stage	B/16/00510	15/04/2016	09/06/2016	Commercial	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0794	PLHP 1	DHSC	Summerfold House	152 Leylands Road, Burgess Hill, West Sussex	RH15 8JE	Mid Sussex	South East	2013/2014	8	Development completed	14/02395/FUL	04/07/2014	12/01/2015	Residential	No	6	20/05/2016	0	6	Yes	No	0	0	0	0	0	6	0	0	2	4	0	0	0
PSLR0795	PLHP 1	DHSC	Summerland Avenue	54 Summerland Avenue, Minehead	TA24 5BN	Somerset West and Taunton	South West	2013/2014	1	Development completed	3/21/13/074	12/08/2013	17/09/2013	Residential	No	1	x	0	1	Yes	No	0	0	0	0	0	0	0	1	0	0	0	1	0
PSLR0796	PLHP 1	DHSC	Surrey Docks Health Centre	Downtown Road, Rotherhithe, London SE16 1NP	SE16 6NP	Southwark	London	2014/2015	51	Development completed	08/AP/1563	23/06/2008	26/05/2010	Mixed	Yes	212	19/05/2014	0	212	Yes	Yes	0	0	0	0	51	37	157	18	4	0	0	201	7
PSLR0797	PLHP 1	DHSC	Surrey House Clinic	Sullivan Road, Southampton	SO19 0HS	Southampton	South East	2014/2015	11	Planning stage	14/00711/OUT	30/04/2014	x	Residential	No	11	x	x	x	Yes	Yes	0	11	0	0	0	x	x	x	x	x	x	x	x
PSLR0798	PLHP 1	DHSC	Swallownest Health Centre	Hepworth Drive, Swallownest	S26 2BG	Rotherham	Yorkshire and The Humber	2013/2014	10	Development started	RB2014/1497	29/10/2014	22/07/2015	Residential	No	10	24/05/2017	0	8	Yes	No	0	0	0	0	0	0	0	8	6	2	0	0	0
PSLR0799	PLHP 1	DHSC	Tattenhall Ambulance Station	Regis Road, Tettenhall, Wolverhampton	WV6 8RH	Wolverhampton	West Midlands	2012/2013	14	Development completed	12/01173/FUL	28/09/2012	06/03/2013	Residential	No	14	11/12/2014	0	14	Yes	No	0	0	0	0	0	0	0	14	0	0	0	14	0
PSLR0800	PLHP 1	DHSC	Teignview	16 Orchard Gardens, Teignmouth, Devon	TQ14 8DS	Teignbridge	South West	2014/2015	3	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0801	PLHP 1	DHSC	Tenterfield	Tenterfield, Brigsteer Road, Kendal	LA9 5EA	South Lakeland	North West	2014/2015	18	Development completed	SL/2015/0425	27/04/2015	16/05/2016	Residential	No	18	12/07/2017	0	18	Yes	No	0	0	0	0	0	11	7	0	2	6	0	10	0
PSLR0802	PLHP 1	DHSC	The Beeches	4 The Drive, Roundhay, Leeds, West Yorkshire	LS8 1JF	Leeds	Yorkshire and The Humber	2014/2015	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0803	PLHP 1	DHSC	The Cedars	The Cedars, Whittaker Road, Derby	DE23 6AP	Derby	East Midlands	2012/2013	4	Development started	09/11/01073	01/11/2011	09/02/2012	Residential	No	4	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	0	0	0	0	1
PSLR0804	PLHP 1	DHSC	The Cedars	Cedar House, 29 Bedfordwell Road, Eastbourne, East Sussex	BN21 2BQ	Eastbourne	South East	2013/2014	1	Development completed	140172	25/02/2014	09/05/2014	Residential	No	1	21/02/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	0	0	1	0	0
PSLR0805	PLHP 1	DHSC	The Cedars	Worcester	Unknown	Worcester	West Midlands	Before 2011	10	Planning stage	x	x	x	x	Unknown	x	x	x	x	Yes	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0806	PLHP 1	DHSC	The Gables	5 Thornhill Road, Edgerton, Huddersfield	HD3 3AT	Kirklees	Yorkshire and The Humber	2012/2013	2	Development completed	2010/62/91869/W2	06/06/2010	11/04/2011	Residential	No	3	01/07/2013	0	3	Yes	No	0	0	0	0	0	3	0	0	3	0	0	0	0
PSLR0807a	PLHP 1	DHSC	The Grove	Stoke on Trent	Unknown	Stoke-on-Trent	West Midlands	Before 2011	9	Development completed	41266/RES	29/04/2003	25/06/2003	Residential	No	1	26/01/2005	0	1	Not applicable	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0807b	PLHP 1	DHSC	The Grove	Stoke on Trent	Unknown	Stoke-on-Trent	West Midlands	Before 2011	9†	Development started	41279/RES	24/04/2003	01/07/2003	Residential	No	1	22/01/2004	0	0	Not applicable	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0807c	PLHP 1	DHSC	The Grove	Stoke on Trent	Unknown	Stoke-on-Trent	West Midlands	Before 2011	9†	Development completed	41172/RES	07/04/2003	30/05/2003	Residential	No	2	22/01/2004	0	2	Not applicable	No	0	0	0	0	0	2	0	0	2	0	0	0	0
PSLR0807d	PLHP 1	DHSC	The Grove	Stoke on Trent	Unknown	Stoke-on-Trent	West Midlands	Before 2011	9†	Development completed	40954/RES	25/02/2003	17/04/2003	Residential	No	2	22/01/2004	0	2	Not applicable	No	0	0	0	0	0	2	0	0	1	1	0	0	0
PSLR0808	PLHP 1	DHSC	The Homestead	17 Reigate Road, Sidlow, Reigate	RH2 8QH	Reigate and Banstead	South East	2012/2013	1	Development completed	12/00826/CU	04/05/2012	29/06/2012	Residential	No	1	21/02/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0809	PLHP 1	DHSC	The Oaks Kenley	Firs Road, Kenley, Surrey	CR8 5LH	Croydon	London	2012/2013	3	Development completed	13/00570/P	25/02/2013	16/05/2013	Residential	No	3	18/05/2015	0	3	Yes	No	0	0	0	0	0	3	0	0	3	0	0	0	0
PSLR0810	PLHP 1	DHSC	The Old Court House, Midhurst	Grange Road, Midhurst	GU29 9LT	Chichester	South East	2013/2014	8	Development completed	12/01844/PENP	18/04/2012	29/05/2012	Residential	No	8	29/10/2016	0	8	Yes	No	0	0	0	0	0	5	3	0	0	0	0	8	0
PSLR0811	PLHP 1	DHSC	The Old Hall	Main Road, Balderton	NG243NU	Newark and Sherwood	East Midlands	2014/2015	12	Development completed	14/00579/FUL	27/03/2014	17/06/2014	Residential	No	9	24/08/2015	0	9	Yes	No	0	0	0	0	0	0	8	1	1	0	0	8	0
PSLR0812	PLHP 1	DHSC	The Princess Royal Hospital	Old Farm Close, Wivelsfield Road. Haywards Heath	RH17 7GA	Mid Sussex	South East	2014/2015	39	Development completed	x	x	x	Residential sale	Unknown	39	x	x	39	Not applicable	Unknown	0	0	0	0	0	x	x	39	x	x	x	x	39
PSLR0813	PLHP 1	DHSC	The Rock Clinic	High St, Frodsham	WA6 7AN	Cheshire West and Chester	North West	2014/2015	2	Planning stage	17/00268/FUL	20/01/2017	12/05/2017	Residential	Yes	14	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0814	PLHP 1	DHSC	The Royal Sussex County Hospital	178 Eastern Road Brighton	BN2 5BE/A	Brighton and Hove	South East	2013/2014	6	Development completed	x	x	x	Residential sale	Unknown	6	x	x	6	Not applicable	Unknown	0	0	0	0	0	x	x	6	x	x	x	x	6
PSLR0815	PLHP 1	DHSC	The Spinney and Howard's Pasture	31 Luton Road, Wilstead. Bedfordshire	MK45 3ER	Bedford	East	2014/2015	6	Development completed	12/01424/FUL	20/07/2012	27/03/2014	Residential	No	6	09/05/2016	0	6	Yes	Mix of pay and houses	1	0	1	0	0	6	0	0	6	0	0	0	0
PSLR0816	PLHP 1	DHSC	The Stable Block	The Stable Block, Claremont House 7-9, Welholme Avenue, Grimsby, South Humberside	DN32 7QL	North East Lincolnshire	Yorkshire and The Humber	2014/2015	25	Development started	DM/0932/16/FUL	07/10/2016	12/09/2017	Residential	No	23	x	17	0	Yes	Yes	0	2	0	0	0	0	0	0	0	0	0	0	0
PSLR0817	PLHP 1	DHSC	The Willows	40 Searchwood Road WARLINGHAM Surrey CR6 9BA	CR6 9BA	Tandridge	South East	2013/2014	4	Development completed	2014/519	31/03/2014	20/06/2014	Residential	No	10	28/10/2016	0	10	Yes	No	0	0	0	0	0	0	10	0	0	0	0	10	0
PSLR0818	PLHP 1	DHSC	Thingoe House, Cotton Lane, Bury St Edmunds	Cotton Lane, Bury St Edmunds	IP33 1XY	St Edmundsbury	East	Before 2011	50	Development completed	SE/11/1052	26/08/2011	02/12/2011	Residential institute	No	56	01/07/2014	0	56	Yes	No	0	0	0	0	0	0	56	0	0	0	0	0	56
PSLR0819	PLHP 1	DHSC	Thornley Clinic	10 The Villas	DH6 3EU	County Durham	North East	2014/2015	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0820	PLHP 1	DHSC	Toddington Clinic	Mander Close, Toddington	LU5 6FP	Central Bedfordshire	East	Before 2011	7	Development completed	CB/09/06171/FULL	02/10/2009	27/11/2009	Residential	No	7	13/01/2011	0	7	Yes	No	0	0	0	0	0	5	2	0	0	2	3	2	0
PSLR0821	PLHP 1	DHSC	Towers Hospital East	Towers Hospital, Gipsy Lane, Leicester	LE5 0TD	Leicester	East Midlands	2011/2012	122	Development completed	20121051	18/07/2012	31/08/2012	Residential	No	127	27/01/2014	0	126	Yes	Unknown	0	0	0	0	0	114	10	2	96	10	20	0	0
PSLR0822	PLHP 1	DHSC	Towers Hospital West	Towers Hospital,Gipsy Lane, Leicester	LE5 0TD	Leicester	East Midlands	2013/2014	90	Development started	20132315	02/01/2014	04/09/2014	Residential	No	95	21/09/2015	6	55	Yes	Unknown	0	0	0	0	0	48	0	7	29	0	26	0	0
PSLR0823	PLHP 1	DHSC	Townland Hospital Site	Henley on Thames	RG9 2EB	South Oxfordshire	South East	2014/2015	45	Development started	P12/S1424/FUL	10/07/2012	19/03/2013	Residential institute	No	109	26/07/2018	0	46	No	No	0	0	0	0	0	45	0	1	0	0	0	46	0
PSLR0824	PLHP 1	DHSC	Tunstall Health Centre	Tunstall Health Centre, Dunning Street, Stoke-on-Trent	ST6 5BE	Stoke-on-Trent	West Midlands	2014/2015	19	Planning stage	60777/RES	26/01/2017	11/04/2017	Residential	No	19	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0825	PLHP 1	DHSC	Upney Lane Health Centre,	132 Upney Lane, Barking Essex	IG11 9YD	Barking and Dagenham	London	2013/2014	27	Development completed	11/00476/FUL	08/06/2011	03/01/2013	Residential	No	26	11/09/2014	0	26	Yes	Yes	0	0	0	0	7	12	14	0	1	0	0	25	0
PSLR0826	PLHP 1	DHSC	Upton Clinic	69 Old Street, Upton on Severn, Worcestershire	WR8 0HN	Malvern Hills	West Midlands	2013/2014	1	Development completed	13/00217/FUL	08/02/2013	05/04/2013	Residential	No	1	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0827	PLHP 1	DHSC	Vanbrugh Health Centre	Greenwich	SE109GA	Greenwich	London	Before 2011	13	Development started	08/0688/F	18/03/2008	31/03/2009	Mixed	Yes	645	03/10/2016	0	7	Yes	Yes	158	0	67	0	0	0	7	0	0	1	6	0	0
PSLR0828	PLHP 1	DHSC	Victoria central health centre	Mill, lane, Wallasey	CH44 5UF	Wirral	North West	2014/2015	48	Planning stage	APP/15/01259	11/09/2015	03/03/2016	Residential	No	20	x	0	0	Yes	Yes	0	0	0	0	1	0	0	0	0	0	0	0	0
PSLR0829	PLHP 1	DHSC	Victoria House	Eign Street, Hereford	HR4 0AW	Herefordshire	West Midlands	2014/2015	42	Planning stage	P180752/F	27/02/2017	x	Commercial	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0830	PLHP 1	DHSC	Victoria House	Holloway, Runcorn	WA7 4TH	Halton	North West	2014/2015	36	Development completed	16/00069/FUL	17/02/2016	06/07/2016	Residential	No	28	x	0	0	Yes	Yes	28	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0831	PLHP 1	DHSC	Wadham Court	15 Edgeway Road, Oxford	OX3 0HD	Oxford	South East	2013/2014	1	Development completed	13/03082/B56	11/11/2013	17/01/2014	Residential	No	11	03/11/2014	0	11	Yes	No	0	0	0	0	0	0	0	11	0	0	0	11	0
PSLR0832	PLHP 1	DHSC	Waller Lane	Caterham, Surrey	CR3 5EA	Tandridge	South East	2014/2015	4	Development completed	x	x	x	Residential sale	No	4	x	x	4	Not applicable	Unknown	0	0	0	0	0	x	x	4	x	x	x	x	4
PSLR0833	PLHP 1	DHSC	Wansbeck General Hospital	Woodhorn Lane, Ashington	NE63 9JL	Northumberland	North East	2014/2015	97	Development started	15/03123/FUL	21/09/2015	17/03/2017	Residential	No	89	06/11/2018	5	41	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	38	0	3	13	26	2	0	0
PSLR0834	PLHP 1	DHSC	Wardle Ambulance Station	Birch Road, Wardle, Rochdale	OL12 9QN	Rochdale	North West	2013/2014	10	Development completed	14/01146/FUL	21/10/2014	11/02/2015	Residential	No	5	21/11/2016	0	5	Yes	No	0	0	0	0	0	5	0	0	5	0	0	0	0
PSLR0836	PLHP 1	DHSC	Wendover	170 Downend Road, Downend, Bristol	BS16 5EB	South Gloucestershire	South West	2013/2014	6	Planning stage	PK14/2622/F	03/07/2014	10/10/2014	Commercial	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0837	PLHP 1	DHSC	Wessex Place	35 Magrath Avenue, Cambridge	CB4 3BL	Cambridge	East	2011/2012	8	Development started	11/1539/FUL	16/12/2011	05/07/2012	Residential institute	No	42	11/04/2013	0	1	Yes	No	0	0	0	0	0	0	0	1	0	0	0	1	0
PSLR0838	PLHP 1	DHSC	West Wylam Health Centre	Adderlane Road Prudhoe, Northumberland	NE42 5JE	Northumberland	North East	2013/2014	10	Development started	13/02527/FUL	20/08/2013	14/04/2014	Residential	No	10	15/04/2015	0	9	Yes	Yes	8	0	2	0	0	7	2	0	0	4	5	0	0
PSLR0839	PLHP 1	DHSC	Westcliff Clinic	415 Westborough Road, Westcliff-on-Sea	SS0 9TN	Southend-on-Sea	East	2014/2015	4	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0840	PLHP 1	DHSC	Westwood Hospital	The Woodlands, Beverley	HU17 8BU	East Riding of Yorkshire	Yorkshire and The Humber	2013/2014	40	Development completed	13/03875/STPLF	25/11/2013	09/09/2014	Residential	No	61	23/11/2015	0	60	Yes	No	0	0	0	0	0	36	24	0	8	24	7	21	0
PSLR0841	PLHP 1	DHSC	Whelley Hospital	Bradshaw Street, Whelley, Wigan	WN1 3UX	Wigan	North West	2014/2015	72	Development started	A/15/81579/MAJOR	27/10/2015	13/07/2016	Residential	No	122	31/10/2017	0	57	Yes	No	0	0	0	0	0	42	0	15	0	4	37	16	0
PSLR0842	PLHP 1	DHSC	Whiston Hospital 1	Delph Lane, Prescot, Merseyside	L35 5DR	Knowsley	North West	2012/2013	36	Planning stage	16/00795/OUT	16/12/2016	19/02/2018	Residential	No	43	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0843	PLHP 1	DHSC	Whiston Hospital 4	Sandstone Drive, Prescott, Merseyside	L35 7JE	Knowsley	North West	2012/2013	1	Planning stage	13/00404/FUL	16/09/2013	23/12/2013	Commercial	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0844	PLHP 1	DHSC	White Lodge	21 Coggeshall Road, Braintree	CM7 9DB	Braintree	East	2013/2014	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0845	PLHP 1	DHSC	White Lodge	131 New Penkridge Road Cannock	WS11 1HT	Cannock Chase	West Midlands	2014/2015	6	Development completed	CH/16/410,CH/17/195	21/10/2016	28/02/2017	Residential,Infill	No,No	15	03/08/2018	0	15	Yes,No	Unknown,No	0	0	0	0	0	0	0	15	0	0	0	15	0
PSLR0846	PLHP 1	DHSC	Willesden Ambulance Station	Willesden	NW103SF	Brent	London	Before 2011	6	Planning stage	165335	18/11/2009	26/02/2010	Residential	No	8	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0847	PLHP 1	DHSC	William Julien Courtaild Hospital	London Road, Braintree	CM7 2LJ	Braintree	East	2012/2013	29	Development started	13/00692/REM	13/06/2013	03/09/2013	Residential	No	29	11/11/2014	0	26	Yes	Unknown	0	0	0	0	0	26	0	0	8	11	7	0	0
PSLR0848	PLHP 1	DHSC	Willington Health Centre	Chapel Street, Willington, Crook	DL15 0EQ	County Durham	North East	2013/2014	3	Planning stage	DM/15/00597/FPA	26/02/2015	11/08/2015	Residential	No	12	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0849	PLHP 1	DHSC	Willows Respite Care	7 Vicarage Road, Amblecote, Stourbridge	DY8 4JA	Dudley	West Midlands	2013/2014	1	Development started	P16/1281	15/09/2016	17/11/2016	Residential institute	No	15	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	0	0	0	0	1
PSLR0850a	PLHP 1	DHSC	Wilson Avenue	340 Wilson Avenue, Rochester	ME1 2ST	Medway	South East	2013/2014	1	Development completed	MC/13/1924	06/08/2013	01/10/2013	Residential	No	1	21/02/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	0	1	0	0	0
PSLR0850b	PLHP 1	DHSC	Wilson Avenue	340 Wilson Avenue, Rochester	ME1 2ST	Medway	South East	2013/2014	1†	Development completed	MC/14/1643	12/06/2014	31/07/2014	Residential	No	1	21/09/2017	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0851a	PLHP 1	DHSC	Wilton Place Car Park	Salford	M3 6FA	Salford	North West	Before 2011	150	Development started	09/57950/EIAHYB	28/07/2009	21/01/2010	Mixed	Yes	861	x	x	x	No	Developer paid local authority to put them somewhere else	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0851b	PLHP 1	DHSC	Wilton Place Car Park	Salford	M3 6FA	Salford	North West	Before 2011	150†	Development started	19/73075/REM	12/02/2019	01/05/2019	Residential	No	33	30/08/2019	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0852	PLHP 1	DHSC	Wincanton Health Centre	Wincanton	BA9 9JT	South Somerset	South West	2013/2014	7	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0853	PLHP 1	DHSC	Windmill House	Everett Close, Bushey , Herts	WD23 1RN	Hertsmere	East	2013/2014	54	Development completed	TP/13/1677	12/07/2013	10/12/2013	Residential	No	53	13/08/2015	0	51	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	23	9	19	5	10	7	29	0
PSLR0854	PLHP 1	DHSC	Wolfson Medical Rehab Centre	Copse Hill, Wimbledon	SW20 0NQ	Merton	London	2011/2012	9	Planning stage	12/P2157	22/08/2012	02/05/2013	Residential	No	8	x	0	0	No	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0855	PLHP 1	DHSC	Wombourne Ambulance Station	Giggetty Lane, Wombourne, Wolverhampton	WV5 0AX	South Staffordshire	West Midlands	2013/2014	8	Development completed	13/00999/FUL	10/12/2013	07/03/2014	Residential	No	9	28/10/2014	0	9	Yes	No	0	0	0	0	0	9	0	0	6	3	0	0	0
PSLR0856	PLHP 1	DHSC	Wood Lane	35 Wood Lane	B20 2AQ	Birmingham	West Midlands	2013/2014	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Yes	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0857	PLHP 1	DHSC	Woodfield Centre	Netherwood Road, Werneth, Oldham	OL9 7AP	Oldham	North West	2011/2012	12	Development started	PA/333239/12	30/10/2012	16/10/2013	Residential	No	12	04/09/2019	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0858	PLHP 1	DHSC	Worthing Hospital	39 Seldon Road, Worthing	BN11 2LL	Worthing	South East	2014/2015	12	Development completed	NOTICE/0012/15,AWDM/1046/16	18/05/2015	13/07/2015	Residential,Infill	No,No	19	07/12/2017	0	19	Yes,Yes	No,No	0	0	0	0	0	0	0	19	0	0	0	19	0
PSLR0859	PLHP 1	DHSC	Yateley Avenue	50 Yateley Avenue, Great Barr	B42 1JN	Birmingham	West Midlands	2013/2014	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0860	PLHP 1	DHSC	York Hospital	Groves Chapel, Union Terrace, York	YO31 7EW	York	Yorkshire and The Humber	2014/2015	23	Development started	15/02833/FULM	11/12/2015	20/06/2016	Mixed	Yes	16	14/05/2018	0	15	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	0	15	0	0	0	15	0
PSLR0861	PLHP 1	Thurrock Council	Schoolfield Road Part 1	Thurrock	RM20 3AP	Thurrock	East	2011/2012	89	Development started	06/01034/TTGREM	12/10/2006	19/01/2009	Residential	Yes	452	26/05/2010	0	297	Yes	Yes	0	0	0	0	46	216	69	12	9	10	161	116	1
PSLR0863	PLHP 1	Thurrock Council	Wm Ball Ltd	Thurrock	RM20 4BF	Thurrock	East	2012/2013	200	Development started	13/00352/REM	10/04/2013	20/03/2014	Residential	No	154	29/09/2014	0	134	Yes	No	0	0	0	0	0	60	68	6	3	4	80	47	0
PSLR0864a	PLHP 1	LLDC	ODA Olympic Village including 6 development plots	Newham	E20 1YY	Newham	London	2013/2014	4893	Development completed	x	x	x	Residential sale	No	2818	x	x	2818	x	x	0	0	0	0	0	0	0	2818	0	0	0	0	2818
PSLR0864b	PLHP 1	LLDC	ODA Olympic Village including 6 development plots	Newham	E20 1YY	Newham	London	2013/2014	4893†	Development started	14/00066/REM	27/02/2014	29/04/2014	Mixed	No	48	27/06/2014	0	0	Yes	Yes	0	48	0	0	0	0	0	0	0	0	0	0	0
PSLR0864c	PLHP 1	LLDC	ODA Olympic Village including 6 development plots	Newham	E20 1YY	Newham	London	2013/2014	4893†	Planning stage	14/00185/REM	30/05/2014	23/07/2014	Residential	No	422	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0864d	PLHP 1	LLDC	ODA Olympic Village including 6 development plots	Newham	E20 1YY	Newham	London	2013/2014	4893†	Development started	14/00034/REM	31/01/2014	29/05/2014	Mixed	No	481	21/05/2019	0	482	Yes	No	0	0	0	0	0	0	480	2	0	0	0	482	0
PSLR0864e	PLHP 1	LLDC	ODA Olympic Village including 6 development plots	Newham	E20 1YY	Newham	London	2013/2014	4893†	Development started	14/00056/REM	17/02/2014	30/05/2014	Mixed	No	188	28/08/2015	0	0	Yes	Yes	0	37	20	0	0	0	0	0	0	0	0	0	0
PSLR0864f	PLHP 1	LLDC	ODA Olympic Village including 6 development plots	Newham	E20 1YY	Newham	London	2013/2014	4893†	Planning stage	14/00141/REM	24/04/2014	08/07/2014	Mixed	No	710	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0865a	PLHP 1	LLDC	Olympic: Phase 1 (Chobham Manor)	Newham	E15 2EE	Newham	London	2013/2014	828	Development completed	13/00504/REM	06/11/2013	31/01/2014	Mixed	Yes	259	12/01/2016	0	262	Yes	Yes	14	14	25	0	0	57	201	4	0	0	89	169	4
PSLR0865b	PLHP 1	LLDC	Olympic: Phase 1 (Chobham Manor)	Newham	E15 2EE	Newham	London	2013/2014	828†	Planning stage	16/00518/REM	27/09/2016	09/05/2017	Mixed	Yes	140	x	0	0	Unknown	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0865c	PLHP 1	LLDC	Olympic: Phase 1 (Chobham Manor)	Newham	E15 2EE	Newham	London	2013/2014	828†	Development started	14/00356/REM	18/09/2014	10/12/2014	Mixed	Yes	207	22/02/2019	0	207	Unknown	Unknown	0	0	0	0	0	63	144	0	0	0	67	140	0
PSLR0865d	PLHP 1	LLDC	Olympic: Phase 1 (Chobham Manor)	Newham	E15 2EE	Newham	London	2013/2014	828†	Planning stage	16/00510/REM	03/10/2016	23/06/2017	Mixed	Yes	253	x	0	0	Unknown	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0866	PLHP 1	LLDC	Olympic: Phase 2	Newham	E15 2EE	Newham	London	2014/2015	1500	Planning stage	16/00520/REM	29/09/2016	08/02/2017	Mixed	Yes	302	x	0	0	Yes	Yes	9	9	94	0	0	0	0	0	0	0	0	0	0
PSLR0868	PLHP 1	MoJ	Horseferry Road Magistrates Court	Westminster	SW1P 2AX	Westminster	London	2011/2012	130	Development completed	12/00258/FULL	09/01/2012	30/05/2012	Residential	No	129	26/06/2014	0	129	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	1	128	0	0	0	0	129	0
PSLR0869	PLHP 1	MoJ	Marylebone Road/Seymour Place	181, Marylebone Road, London, NW1 5QJ	NW1 5QJ	Westminster	London	2011/2012	60	Development started	09/05979/FULL	21/07/2009	28/06/2010	Residential	No	60	06/12/2012	0	0	No	Yes	0	40	20	0	0	0	0	0	0	0	0	0	0
PSLR0870	PLHP 1	MoJ	Acton Magistrates Court	Winchester Street Acton London	W3 8PA	Ealing	London	2011/2012	9	Development completed	P/2012/0737	15/02/2012	22/03/2013	Residential	No	9	26/07/2013	0	9	Yes	No	0	0	0	0	0	7	2	0	0	0	7	2	0
PSLR0871	PLHP 1	MoJ	Brentford Magistrates Court	Market Place Brentford Middlesex	TW8 8EN	Hounslow	London	2011/2012	9	Development completed	P/2012/1486,P/2015/0885	28/05/2012	26/10/2012	Mixed,Infill	No,No	10	24/11/2014	0	10	Yes,No	No,No	0	0	0	0	0	0	9	1	0	0	0	10	0
PSLR0872	PLHP 1	MoJ	St Dunstan's House	133-137 Fetter Lane	EC4A 1BT	City of London	London	2012/2013	76	Development completed	10/00569/FULMAJ	03/08/2010	30/03/2012	Residential	No	76	28/01/2015	0	75	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	2	73	0	0	0	0	75	0
PSLR0873	PLHP 1	MoJ	Sutton Magistrates Court	Sutton	SM6 0JA	Sutton	London	2012/2013	50	Development completed	D2012/66638,D2017/78297	29/10/2012	24/04/2013	Residential,Infill	No,No	59	18/06/2015	0	58	Yes,No	No,No	0	0	0	0	0	0	58	0	0	0	0	58	0
PSLR0875	PLHP 1	MoJ	Cromer Magistrates’ Court	Summerhouse Close (off Holt Road), Cromer	NR27 9EB	North Norfolk	East	2012/2013	35	Development completed	13/0111	30/01/2013	15/07/2013	Residential institute	No	35	21/04/2016	0	35	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	35	0	0	0	0	35	0
PSLR0876	PLHP 1	MoJ	Barking Magistrates Court	Barking	IG11 8EW	Barking and Dagenham	London	2012/2013	30	Development completed	13/00378/FUL	08/05/2013	22/07/2013	Mixed	No	40	22/02/2016	0	40	Yes	No	0	0	0	0	0	37	0	3	0	0	0	40	0
PSLR0877	PLHP 1	MoJ	Bristol Magistrates Court	Rupert Street, Bristol	BS1 2PZ	Bristol	South West	2012/2013	27	Development started	13/00452/F	31/01/2013	23/07/2013	Mixed	No	348	08/02/2016	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0878	PLHP 1	MoJ	Thetford MC	Thetford	IP24 3AQ	Breckland	East	2012/2013	14	Development completed	3PL/2013/0310/F	02/04/2013	26/07/2013	Residential	No	14	15/12/2014	0	14	Yes	Yes	0	14	0	0	0	0	0	14	0	0	0	14	0
PSLR0879	PLHP 1	MoJ	Wantage MC	Larch Road, Wantage	OX12 8BW	Vale of White Horse	South East	2012/2013	12	Development completed	P15/V0729/FUL	27/03/2015	28/07/2015	Residential	No	32	23/11/2017	0	32	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	32	0	0	0	0	32	0
PSLR0880	PLHP 1	MoJ	Blaydon Magistrates Court	Blaydon on Tyne	NE21 5AJ	Gateshead	North East	2012/2013	1	Development completed	DC/12/00800/COU	11/07/2012	14/03/2013	Mixed	No	1	28/09/2013	0	1	Yes	No	0	0	0	0	0	0	0	1	1	0	0	0	0
PSLR0881	PLHP 1	MoJ	Salford Magistrates Court	Salford	M3 6DD	Salford	North West	2013/2014	125	Development completed	13/63615/FUL,15/65902/FUL	02/08/2013	24/02/2014	Mixed,Infill	No,No	134	26/04/2017	0	134	Yes,Unknown	Unknown,No	0	0	0	0	0	0	0	134	0	0	0	134	0
PSLR0882	PLHP 1	MoJ	Halesowen MC	Laurel lane, Halesowen	B63 3DA	Dudley	West Midlands	2013/2014	56	Planning stage	P16/0251	23/02/2016	20/09/2016	Residential	No	30	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0883	PLHP 1	MoJ	Haringey Magistrates Court	Highgate Court House Bishops Road Archway Road, Highgate	N6 4HS	Haringey	London	2013/2014	55	Development completed	HGY/2014/2464	02/09/2014	20/03/2015	Residential	No	82	14/09/2017	0	82	Yes	Yes	0	17	9	0	0	0	65	17	0	0	0	82	0
PSLR0884	PLHP 1	MoJ	HMP Canterbury	46 Longport, Canterbury, Kent	CT1 1PJ	Canterbury	South East	2013/2014	52	Planning stage	CA//16/02081	12/09/2016	20/12/2016	Commercial	No	0	x	x	x	No	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0885	PLHP 1	MoJ	Ashley House	Monck Street, London, SW1	SW1P 2BQ	Westminster	London	2013/2014	44	Development started	14/05686/FULL	12/06/2014	10/12/2014	Mixed	No	51	x	0	0	No	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0886	PLHP 1	MoJ	Mid-Sussex Magistrates Court (Haywards Heath)	Haywards Heath	RH16 4AB	Mid Sussex	South East	2013/2014	36	Development started	13/04256/FUL	12/12/2013	21/10/2014	Residential	No	36	17/01/2017	0	34	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	2	32	0	0	0	0	34	0
PSLR0887a	PLHP 1	MoJ	Grammar School/Old County Building	Grammar School Walk, Huntingdon	PE29 3LQ	Huntingdonshire	East	2013/2014	5	Development completed	1301759FUL	04/11/2013	10/04/2014	Residential	No	5	28/09/2015	0	5	Yes	No	0	0	0	0	0	0	5	0	0	0	0	5	0
PSLR0887b	PLHP 1	MoJ	Grammar School/Old County Building	Grammar School Walk, Huntingdon	PE29 3LQ	Huntingdonshire	East	2013/2014	5†	Development completed	1400029PACOU	10/01/2014	27/02/2014	Residential	No	14	02/11/2015	0	14	Yes	No	0	0	0	0	0	0	14	0	0	0	0	14	0
PSLR0888	PLHP 1	MoJ	Ashford Magistrates and County Court	AshfordÃ‚Â	TN23 1DG	Ashford	South East	2013/2014	14	Planning stage	13/01159/AS	16/10/2013	30/12/2013	Commercial	No	0	x	x	x	No	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0889	PLHP 1	MoJ	Oakes House, Gloucester	53-57 London Road, Gloucester	GL1 3HF	Gloucester	South West	2013/2014	12	Development completed	14/00162/JPA	05/02/2014	31/03/2014	Residential	No	12	19/03/2012	0	12	Yes	No	0	0	0	0	0	0	0	12	0	0	0	12	0
PSLR0890	PLHP 1	MoJ	Didcot Magistrates Court	The Court House, Mereland Road, Didcot, Oxfordshire	OX11 8BG	South Oxfordshire	South East	2013/2014	12	Development started	P14/S1121/FUL	09/04/2014	23/10/2014	Residential	No	8	15/06/2019	0	7	Yes	Yes	2	0	2	0	0	0	0	7	0	3	2	2	0
PSLR0891	PLHP 1	MoJ	Melton Mowbray Magistrates Court	The Courthouse Norman Way, Melton, Mowbray, Leciestershire	LE13 1NH	Melton	East Midlands	2013/2014	9	Development completed	14/00499/FUL	16/06/2014	05/09/2014	Residential	No	9	18/05/2015	0	9	Yes	No	0	0	0	0	0	0	9	0	0	0	0	9	0
PSLR0892	PLHP 1	MoJ	Sudbury MC	Acton Lane, Sudbury, Suffolk	CO10 1QN	Babergh	East	2013/2014	6	Development completed	B/14/01627	23/12/2014	18/02/2015	Residential	No	6	25/05/2016	0	6	Yes	No	0	0	0	0	0	0	0	6	0	0	0	6	0
PSLR0893	PLHP 1	MoJ	Dewsbury County Court	Eightlands Road, Dewsbury, West Yorkshire	WF13 2PE	Kirklees	Yorkshire and The Humber	2013/2014	4	Development completed	2013/62/91140/E	08/04/2013	08/08/2013	Residential	No	12	19/01/2015	0	12	Yes	No	0	0	0	0	0	0	0	12	0	0	0	12	0
PSLR0894	PLHP 1	MoJ	Gosforth Magistrates Court	West Avenue Gosforth Newcastle upon Tyne	NE3 4ES	Newcastle upon Tyne	North East	2013/2014	2	Development completed	2013/1207/01/DET	19/08/2013	18/12/2013	Residential	No	2	13/07/2015	0	2	Yes	No	0	0	0	0	0	1	0	1	0	2	0	0	0
PSLR0895	PLHP 1	MoJ	Swaffham Magistrates Court	West Acre Road, Swaffham, Norfolk	PE37 7NB	Breckland	East	2013/2014	1	Development completed	3PL/2013/0131/F	12/02/2013	21/05/2013	Residential	No	1	26/07/2013	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0896	PLHP 1	MoJ	HMP Gloucester	Barrack Square, Gloucester, Gloucestershire	GL1 2JN	Gloucester	South West	2014/2015	110	Planning stage	17/00659/FUL	20/06/2017	06/12/2018	Mixed	No	202	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0897	PLHP 1	MoJ	HMP Kingston	122 Milton Rd, Portsmouth	PO3 6AS	Portsmouth	South East	2014/2015	100	Planning stage	18/01868/FUL	08/11/2018	29/08/2019	Mixed	No	230	x	0	0	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0898	PLHP 1	MoJ	HMP Dorchester	North Square, Dorchester, Dorset	DT1 1JD	West Dorset	South West	2014/2015	100	Development started	WD/D/15/002841	04/12/2015	18/08/2016	Residential	No	189	18/01/2016	0	4	No	No	0	0	0	0	0	4	0	0	0	0	4	0	0
PSLR0899	PLHP 1	MoJ	HMP Shepton Mallet	Cornhill Shepton Mallet	BA4 5LT	Mendip	South West	2014/2015	90	Planning stage	2019/0598/FUL	19/03/2019	x	Mixed	No	146	x	x	x	Yes	No	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0900	PLHP 1	MoJ	Deerbolt North	Barnard Castle	DL12 9BG	County Durham	North East	2014/2015	75	Development completed	DM/14/02696/RM	08/09/2014	03/12/2014	Residential	No	64	29/02/2016	0	64	Yes	Yes	0	8	0	2	0	63	0	1	35	24	3	0	2
PSLR0901	PLHP 1	MoJ	HMP Shrewsbury	The Dana, Shrewsbury, Shropshire	SY1 2HR	Shropshire	West Midlands	2014/2015	40	Planning stage	17/02809/OUT	12/06/2017	14/09/2017	Residential	No	78	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0902	PLHP 1	MoJ	Bridport MC	The Court House, Mountfield, Bridport, Dorset	DT6 3JP	West Dorset	South West	2014/2015	26	Development completed	WD/D/15/000075	04/02/2015	11/08/2015	Residential	No	26	26/06/2017	0	26	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	26	0	0	0	0	26	0
PSLR0903	PLHP 1	MoJ	Huish Lane, Yeovil	Pool site, Huish Lane, Huish, Yeovil	BA20 1BT	South Somerset	South West	2014/2015	24	Development started	14/05634/FUL	18/12/2014	05/06/2015	Residential	No	24	17/01/2018	0	22	Yes	Unknown	0	0	0	0	0	7	0	15	0	0	0	22	0
PSLR0904	PLHP 1	MoJ	Bedford	1-4 St Paul's Street, St Paul's Square, Bedford	MK40 1SQ	Bedford	East	2014/2015	10	Development started	13/02199/MAF	30/10/2013	09/12/2013	Residential	No	10	15/12/2014	0	4	Yes	Yes	0	10	0	0	0	4	0	0	0	0	0	4	0
PSLR0905	PLHP 1	MoJ	Witham Magistrates Court	Witham	CM8 2AS	Braintree	East	2014/2015	10	Development completed	15/01062/FUL	17/08/2015	22/03/2016	Residential	No	11	21/04/2016	0	11	Yes	No	0	0	0	0	0	11	0	0	5	6	0	0	0
PSLR0906	PLHP 1	MoJ	Epping Magistrates Court	The Court House, Epping, Essex	CM16 4AP	Epping Forest	East	2014/2015	7	Development started	EPF/0663/15	23/03/2015	28/08/2015	Residential	No	8	05/02/2018	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0907	PLHP 1	MoJ	Abel House and Cleland House	Westminster	SW1P4DD	Westminster	London	Before 2011	285	Development completed	11/03034/FULL,15/07726/FULL,15/07725/FULL	31/03/2011	21/03/2012	Residential,Infill,Infill	No,No,No	277	03/08/2016	0	144	Yes,Yes,Yes	Yes,No,No	37	0	30	0	0	0	0	144	0	0	0	144	0
PSLR0908	PLHP 1	Home Office	Huntingdon Laboratory	Huntingdon	PE29 6NU	Huntingdonshire	East	2012/2013	100	Development started	17/01597/FUL	23/07/2017	08/11/2017	Residential	No	103	31/10/2018	15	82	Yes	Yes	0	0	0	0	41	64	1	17	16	28	26	12	0
PSLR0909	PLHP 1	DCMS	British Library	Colindale Avenue, London	NW9 5HE	Barnet	London	2013/2014	345	Development completed	H/05856/13	12/12/2013	23/12/2014	Mixed	No	395	25/05/2016	0	395	Yes	Unknown	0	0	0	0	0	58	309	28	0	0	0	395	0
PSLR0910	PLHP 1	Home Office	Harrogate - National Policing Improvement Agency	Yew Tree Lane, Pannal Ash, Harrogate, North Yorkshire,	HG2 9JZ	Harrogate	Yorkshire and The Humber	2013/2014	151	Development started	14/02970/FULMAJ	22/07/2014	25/10/2018	Residential	No	149	21/02/2012	0	12	Yes	Yes	0	0	0	0	64	12	0	0	4	8	0	0	0
PSLR0911	PLHP 1	Land Registry	Stevenage Office - Brickdale House	Dane Street, Stevenage	SG1 1XG	Stevenage	East	2013/2014	118	Development completed	14/00705/CPA,14/00043/FP	22/01/2014	24/03/2014	Residential,Infill	Yes,Yes	150	x	0	0	Yes,No	No,No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0912	PLHP 1	Home Office	Wetherby Laboratory	Audby Lane, Wetherby	LS22 7DN	Leeds	Yorkshire and The Humber	2013/2014	49	Development completed	14/00611/FU	13/02/2014	01/04/2015	Residential	No	57	17/05/2016	0	57	Yes	Yes	0	12	8	0	0	15	39	3	37	0	10	10	0
PSLR0913	PLHP 1	Land Registry	Chalfont Drive Northern Plot	Chalfont Drive, Nottingham	NG8 3RN	Nottingham	East Midlands	2014/2015	323	Development started	14/02823/PRES4	24/11/2014	01/05/2015	Residential	Yes	351	22/08/2016	1	311	Yes	Yes	0	10	0	0	48	228	73	10	172	54	67	18	0
PSLR0914	PLHP 1	Land Registry	Chalfont Drive HMS Sherwood plot	Chalfont Drive, Nottingham	NG8 3SU	Nottingham	East Midlands	2014/2015	16	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0915	PLHP 1	HM Treasury	Government Buildings, Harrow	Stanmore	HA7 1DT	Harrow	London	Before 2011	200	Development started	P/2563/09	16/08/2006	12/11/2007	Residential	Yes	816	17/05/2010	0	765	Yes	Yes	0	122	133	0	0	84	680	1	0	55	1	709	0
PSLR0916	PLHP 1	Home Office	Former Detention Centre	Gringley-on-the-Hill, Gainsborough	DN104FQ	Bassetlaw	East Midlands	Before 2011	72	Development completed	23/08/00017,14/00316/FUL	04/08/2008	09/09/2010	Residential,Infill	No,No	75	04/05/2011	0	75	Yes,Unknown	Yes,Yes	7	0	7	0	2	38	37	0	50	15	10	0	0
PSLR0917	PLHP 1	Home Office	Former St Charles Youth Treatment Centre	Brentwood	CM144JQ	Brentwood	East	Before 2011	54	Development completed	06/01081/FUL	11/12/2006	20/12/2007	Residential	Unknown	120	10/06/2009	0	120	Yes	Yes	36	0	6	0	0	84	18	18	11	18	31	60	0
PSLR0918	PLHP 1	DCMS	Land to the rear of the British Library	Somerstown	NW1 2DB	Camden	London	Before 2011	50	Planning stage	2010/4721/P	14/09/2010	10/03/2011	Commercial	No	0	x	x	x	No	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0919	PLHP 1	Royal Mail	Twickenham Delivery Office	109 London Road, Twickenham	TW1 1AA	Richmond upon Thames	London	2011/2012	110	Development completed	12/3650/FUL	19/11/2012	06/03/2014	Residential	No	110	11/05/2016	0	109	Yes	Yes	0	0	0	0	16	28	81	0	0	0	28	81	0
PSLR0920	PLHP 1	Royal Mail	Rathbone Place	West End Delivery Office, 35-50 Rathborne Place London	W1T 1AA	Westminster	London	2011/2012	90	Development completed	13/04844/FULL	16/05/2013	17/02/2014	Mixed	No	162	22/01/2018	0	162	Yes	Mix of pay and houses	0	0	20	0	0	1	161	0	0	0	0	162	0
PSLR0921	PLHP 1	Crown Estate	Green Lane	Green Lane, Hemel Hempstead	HP2 4GF	Dacorum	East	2011/2012	88	Development completed	4/02276/11/RES	19/12/2011	14/06/2012	Residential	No	87	18/03/2013	0	87	Yes	Unknown	0	0	0	0	0	72	13	2	13	8	35	31	0
PSLR0922a	PLHP 1	Crown Estate	Tithby Road, Bingham	Tithby Road, Bingham	NG13 8GF	Rushcliffe	East Midlands	2011/2012	88	Development started	17/02106/REM	27/09/2017	12/02/2018	Residential	Yes	317	05/07/2019	31	71	Yes	Yes	0	0	0	0	60	57	0	14	48	17	4	0	2
PSLR0922b	PLHP 1	Crown Estate	Tithby Road, Bingham	Tithby Road, Bingham	NG13 8GF	Rushcliffe	East Midlands	2011/2012	88†	Planning stage	18/01468/REM	21/06/2018	01/02/2019	Residential	Yes	733	x	0	0	Yes	Yes	0	0	0	0	140	0	0	0	0	0	0	0	0
PSLR0923	PLHP 1	Royal Mail	Notting Hill	222-224 Westbourne Grove London	W11 2RQ	Kensington and Chelsea	London	2011/2012	6	Development completed	PP/12/04471	13/11/2012	01/05/2013	Mixed	No	3	02/08/2012	0	3	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	1	1	1	0	0	2	1	0
PSLR0924	PLHP 1	Crown Estate	Land north of Pod Corner, Brenzett Farm, Romney Marsh	Romney Marsh	TN29 9SD	Folkestone and Hythe	South East	2011/2012	4	Planning stage	Y17/1409/SH	01/11/2017	25/05/2018	Residential	Unknown	9	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0925	PLHP 1	Crown Estate	Coleman’s Farm, Stapleford Abbotts	Unknown	CM16 7PP	Epping Forest	East	2011/2012	2	Development completed	EPF/1980/12	30/10/2012	14/12/2012	Residential	No	3	22/10/2013	0	3	Yes	No	0	0	0	0	0	2	0	1	3	0	0	0	0
PSLR0926	PLHP 1	BBC	White City Television Centre	Wood Lane, Shepherd's Bush, London,	W12 7RJ	Hammersmith and Fulham	London	2012/2013	1025	Development started	2013/02355/COMB	30/05/2013	09/07/2014	Mixed	No	968	24/11/2016	19	415	Yes	Yes	10	0	111	0	0	24	281	110	0	0	0	415	0
PSLR0927	PLHP 1	Royal Mail	Reading former Sorting Office	80 Caversham Road, Reading	RG1 1AA	Reading	South East	2012/2013	160	Planning stage	182252	21/12/2018	x	Mixed	No	658	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0928	PLHP 1	Royal Mail	Former Delivery Office Kensington High Street	Earls Court Road and Post Office 257 and 24 Earls Court Road	W8 6EA	Kensington and Chelsea	London	2012/2013	50	Planning stage	PP/15/02618	29/04/2015	01/10/2015	Mixed	No	62	x	0	0	No	Mix of pay and houses	17	0	0	0	3	0	0	0	0	0	0	0	0
PSLR0929	PLHP 1	Royal Mail	Coton House	Coton House, Rugby, Warwickshire	CV23 0AA	Rugby	West Midlands	2012/2013	30	Development started	R12/1353,R15/2009,R15/1892	22/08/2013	09/05/2014	Residential,Infill,Infill	Unknown,Unknown,Unknown	84	05/06/2015	0	85	No,Unknown,Unknown	Unknown,No,Unknown	0	0	0	0	0	72	0	13	65	8	0	8	4
PSLR0930	PLHP 1	Royal Mail	Hitchin Delivery Office	Portmill Land, Hitchin, Herts	SG5 1AA	North Hertfordshire	East	2012/2013	20	Development completed	13/02151/1	12/09/2013	30/01/2014	Mixed	No	24	12/05/2015	0	24	Yes	No	0	0	0	0	0	0	24	0	0	0	0	24	0
PSLR0931	PLHP 1	Royal Mail	Kings Langley Delivery Office	32 High Street	WD4 8AA	Dacorum	East	2012/2013	14	Development started	4/03473/16/MFA	21/12/2016	02/05/2017	Residential institute	No	61	13/11/2019	0	1	Yes	No	0	0	0	0	0	0	0	1	0	0	0	0	1
PSLR0932	PLHP 1	Royal Mail	Mount Pleasant sorting office - Catthorpe Street	Catthorpe Street London	WC1X 0AR	Islington	London	2013/2014	533	Development started	P2013/1423/FUL	28/06/2013	30/03/2015	Mixed	No	336	21/12/2019	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0933a	PLHP 1	Royal Mail	Nine Elms	Block B, Nine Elms Lane, Nine Elms, London,	SW8 5BA	Wandsworth	London	2013/2014	388	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0933b	PLHP 1	Royal Mail	Nine Elms	Block B, Nine Elms Lane, Nine Elms, London,	SW8 5BA	Wandsworth	London	2013/2014	388†	Planning stage	2019/1696	25/04/2019	19/06/2019	Mixed	No	262	x	0	0	Yes	Yes	40	0	26	0	0	0	0	0	0	0	0	0	0
PSLR0933c	PLHP 1	Royal Mail	Nine Elms	Block B, Nine Elms Lane, Nine Elms, London,	SW8 5BA	Wandsworth	London	2013/2014	388†	Planning stage	2019/2324	12/08/2019	x	Residential	No	297	x	x	x	Yes	Yes	57	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0933d	PLHP 1	Royal Mail	Nine Elms	Block B, Nine Elms Lane, Nine Elms, London,	SW8 5BA	Wandsworth	London	2013/2014	388†	Planning stage	2019/2325	01/07/2019	x	Mixed	No	462	x	x	x	Yes	Yes	19	0	52	0	0	x	x	x	x	x	x	x	x
PSLR0933e	PLHP 1	Royal Mail	Nine Elms	Block B, Nine Elms Lane, Nine Elms, London,	SW8 5BA	Wandsworth	London	2013/2014	388†	Planning stage	2017/6764	08/12/2017	29/03/2019	Residential	No	894	x	0	0	Yes	Yes	0	0	161	0	0	0	0	0	0	0	0	0	0
PSLR0934a	PLHP 1	Royal Mail	Nine Elms	Block A, Nine Elms Lane, Nine Elms, London,	SW8 5BA	Wandsworth	London	2013/2014	382	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0934b	PLHP 1	Royal Mail	Nine Elms	Block A, Nine Elms Lane, Nine Elms, London,	SW8 5BA	Wandsworth	London	2013/2014	382†	Planning stage	2019/2293	13/06/2019	05/03/2020	Commercial	No	0	x	x	x	Yes	No	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0934c	PLHP 1	Royal Mail	Nine Elms	Block A, Nine Elms Lane, Nine Elms, London,	SW8 5BA	Wandsworth	London	2013/2014	382†	Planning stage	2017/6764	08/12/2017	29/03/2019	Residential	No	894	x	0	0	Yes	Yes	0	0	161	0	0	0	0	0	0	0	0	0	0
PSLR0935	PLHP 1	Royal Mail	Mount Pleasant - Phoenix Place	Phoenix Place London	WC1X 0AR	Camden	London	2013/2014	214	Development started	2013/3807/P	28/06/2013	30/03/2015	Mixed	No	345	21/12/2019	0	0	Yes	Yes	98	0	65	0	82	0	0	0	0	0	0	0	0
PSLR0936	PLHP 1	Royal Mail	Croydon	1-5 Addiscombe Road, Croydon, Surrey	CR0 6BT	Croydon	London	2013/2014	170	Development started	13/03126/P	17/09/2013	19/02/2014	Mixed	No	201	15/09/2017	0	0	Yes	Mix of pay and houses	18	0	12	0	0	0	0	0	0	0	0	0	0
PSLR0937	PLHP 1	Royal Mail	Parcel Force Worldwide London Central London Distribution	24-58 Royal College Street	NW1 0QA	Camden	London	2013/2014	150	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0938	PLHP 1	Royal Mail	Paddington former sorting office	31 London Street	W2 1PF	Westminster	London	2013/2014	141	Planning stage	16/09050/FULL	12/09/2016	14/08/2017	Commercial	No	0	x	x	x	No	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0939	PLHP 1	Royal Mail	Islington Delivery Office	5 Almeida Street, Islington	N1 1AS	Islington	London	2013/2014	76	Development started	P090774	25/04/2009	22/04/2010	Residential	No	76	03/12/2019	0	38	Yes	Yes	0	21	15	0	0	0	0	38	0	0	0	38	0
PSLR0941	PLHP 1	Royal Mail	Berkhamstead Delivery Office	300 High Street Berkhamstead	HP4 1ZZ	Dacorum	East	2013/2014	23	Planning stage	4/01211/12/MFA	26/06/2012	17/09/2012	Commercial	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0942	PLHP 1	Crown Estate	Elsenham	Essex	CM22 6LL	Uttlesford	East	2014/2015	155	Development completed	UTT/14/3279/DFO	31/10/2014	01/05/2015	Residential	No	155	17/05/2016	0	155	Yes	Yes	43	0	19	0	0	108	30	17	63	51	12	28	1
PSLR0943	PLHP 1	Crown Estate	Skirlaugh	Yorkshire East Riding	HU11 5DZ	East Riding of Yorkshire	Yorkshire and The Humber	2014/2015	87	Development started	15/01062/STREM	01/04/2015	09/09/2015	Residential	No	87	18/01/2017	0	87	Yes	Yes	13	0	0	0	0	85	2	0	57	23	3	4	0
PSLR0944a	PLHP 1	Crown Estate	Dunster Marsh	Dunster, Minehead, Somerset	TA24 6PH	Somerset West and Taunton	South West	2014/2015	54	Development completed	3/10/15/001	14/04/2015	03/08/2015	Residential	Yes	54	15/07/2016	0	55	Yes	Yes	0	11	0	0	0	55	0	0	18	20	17	0	0
PSLR0944b	PLHP 1	Crown Estate	Dunster Marsh	Dunster, Minehead, Somerset	TA24 6PH	Somerset West and Taunton	South West	2014/2015	54†	Development started	3/10/12/004	16/04/2012	08/06/2012	Residential	Yes	3	17/01/2018	0	1	Unknown	No	0	0	0	0	0	1	0	0	0	1	0	0	0
PSLR0945	PLHP 1	Crown Estate	Hemel Hempstead	Hertfordshire	HP2 4PA	Dacorum	East	2014/2015	26	Planning stage	4/01519/17/MFA	13/06/2017	13/09/2017	Residential	No	25	x	0	0	Yes	Mix of pay and houses	7	0	2	0	0	0	0	0	0	0	0	0	0
PSLR0946	PLHP 2	Cabinet Office	Admiralty Arch	The Mall, London, SW1A 2WH	SW1A 2WH	Westminster	London	2015/2016	1	Development completed	13/03364/FULL	12/04/2013	16/09/2013	Mixed	No	1	x	0	1	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	0	1	1	0	0	0	0
PSLR0947	PLHP 2	DEFRA	Bury St Edmunds - 100 Southgate Street	Government Buildings, 100 Southgate Street, Bury St Edmunds, IP33 2BD	IP33 2BD	St Edmundsbury	East	2015/2016	32	Development completed	DC/16/0798/FUL	17/05/2016	21/10/2016	Residential	No	42	19/05/2018	0	42	Yes	No	0	0	0	0	0	18	23	1	0	0	3	39	0
PSLR0948	PLHP 2	DEFRA	Worcester - Whittington Road	Government Buildings, Whittington Road, Worcester	WR5 2LQ	Worcester	West Midlands	2016/2017	120	Development started	P16G0178	31/03/2016	30/08/2016	Residential	No	120	11/05/2017	1	109	Yes	Unknown	0	0	0	0	0	98	5	6	51	50	6	2	0
PSLR0950	PLHP 2	DfT	Federated House, Dorking	RH4 1SZ	RH4 1SZ	Mole Valley	South East	2015/2016	71	Development completed	MO/2015/0426	02/04/2015	15/05/2015	Residential	No	71	15/01/2018	0	71	Yes	No	0	0	0	0	0	1	70	0	0	0	0	71	0
PSLR0951	PLHP 2	DfT	PASTURE LAND AT HIGH LEIGH, KENNEDY AVENUE, HODDESDON, HERTFORDSHIRE COUNTY	Kennedy Avenye, Hoddesdon, Hertfordshire County	EN11 8NN	Broxbourne	East	2016/2017	14	Planning stage	07/14/1133/O	18/12/2014	03/05/2016	Residential	No	14	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0952	PLHP 2	DfT	Kidbrooke (Berkeley Homes)	Land South Side of Kidbrooke Station, Grenwich, London	SE3 9PL	Greenwich	London	2016/2017	306	Development started	14/2607/F	19/09/2014	27/03/2015	Mixed	Yes	1238	10/11/2017	0	286	No	Unknown	0	0	0	0	0	31	254	1	0	0	0	286	0
PSLR0953	PLHP 2	DfT	Kingswood	Station Approach, Waterhouse Lane, Kingswood, Surrey KT20 6EN	KT20 6EN	Reigate and Banstead	South East	2016/2017	18	Development started	16/01777/F	26/08/2016	24/05/2017	Residential	No	18	11/01/2018	0	0	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0954	PLHP 2	DfT	Leamington Spa	Land off Park Drive/Station Approach, Leamington Spa, Warwickshire	CV313PJ	Warwick	West Midlands	2016/2017	28	Development started	W/15/0905	05/06/2015	04/02/2016	Residential	Yes	212	19/12/2018	4	19	Yes	Yes	83	0	76	0	0	0	0	19	0	5	4	10	0
PSLR0955	PLHP 2	DfT	Manchester Victoria Fishdock	off Corporation Street, M3 1NX	M3 1NX	Manchester	North West	2016/2017	520	Planning stage	111777/FO/2016/C1	06/06/2016	29/09/2016	Mixed	No	520	x	0	0	No	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0956	PLHP 2	DfT	Old Oak Common - Genesis	Oaklands House, Old Oak Common Ln, London NW10 6DU	NW10 6DU	Hammersmith and Fulham	London	2016/2017	605	Planning stage	2016/00539/OBS	02/02/2016	27/07/2017	Mixed	No	611	x	0	0	Yes	Yes	45	61	136	0	0	0	0	0	0	0	0	0	0
PSLR0957	PLHP 2	DfT	Potters Bar	Albany Gate, Darkes Lane, Potters Bar, Hertfordshire	EN6 1AG	Hertsmere	East	2016/2017	34	Development completed	16/1371/PD56	11/07/2016	06/09/2016	Residential	No	39	28/07/2017	0	39	Yes	No	0	0	0	0	0	0	39	0	0	0	0	39	0
PSLR0958	PLHP 2	DfT	Salford Exchange West - Ph 1	Chapel Street Salford, M3 7	M3 7	Salford	North West	2016/2017	694	Development started	15/66621/FULEIA	26/06/2015	02/12/2016	Mixed	Yes	694	x	0	0	No	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0959	PLHP 2	DfT	Southwark, Tanner Street	Tanner St Southwark SE1	SE1 3PL	Southwark	London	2016/2017	9	Planning stage	16/AP/5180	22/12/2016	17/01/2018	Commercial	No	0	x	x	x	No	No	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR0960	PLHP 2	DfT	Walthamstow Central	Land around Walthamstow Central Station, Walthamstow.	Unknown	Waltham Forest	London	2016/2017	79	Development started	142873	28/11/2014	15/06/2016	Mixed	Yes	79	11/07/2019	0	79	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	1	78	0	0	0	0	79	0
PSLR0961	PLHP 2	DfT	Wyvil Road, Vauxhall	SW8 2TG	SW8 2TG	Lambeth	London	2016/2017	148	Development started	14/03701/FUL	17/07/2014	05/03/2015	Residential	Unknown	219	29/04/2015	0	0	Yes	Yes	16	0	28	0	0	0	0	0	0	0	0	0	0
PSLR0962	PLHP 2	DHSC	Land adjoining Bucknall Hospital	Cambrian Way off Eaves Lane, Bucknall, ST2 8LD	ST2 8LD	Stoke-on-Trent	West Midlands	2015/2016	12	Development started	58877/FUL	28/09/2015	29/02/2016	Residential	Yes	201	24/03/2017	24	103	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	20	0	83	8	10	0	0	85
PSLR0963	PLHP 2	DHSC	Land at Bob Dunn Way	Dartford, Kent	DA1 5HN	Dartford	South East	2015/2016	18	Development completed	15/01509/FUL	05/10/2015	23/02/2016	Residential	No	18	27/03/2017	0	18	Yes	Yes	2	0	3	0	0	0	0	18	1	2	15	0	0
PSLR0964a	PLHP 2	DHSC	Little Plumstead Hospital, West site	Hospital Road, Little Plumstead	NR1 35E	Broadland	East	2015/2016	109	Development started	20171008	12/06/2017	11/07/2019	Residential	No	20	04/02/2019	0	9	Yes	Unknown	0	0	0	0	0	6	0	3	0	2	3	0	4
PSLR0964b	PLHP 2	DHSC	Little Plumstead Hospital, West site	Hospital Road, Little Plumstead	NR1 35E	Broadland	East	2015/2016	109†	Development started	20160808	03/05/2016	24/10/2016	Residential	No	88	16/12/2017	16	84	Yes	Yes	20	0	4	0	0	76	3	5	25	20	1	0	38
PSLR0965	PLHP 2	DHSC	1 & 2 Foxholme & Primrose Cottages	1 & 2 FOXHOLME & PRIMROSE COTTAGES CHICHESTER WEST SUSSEX PO19 6WL	PO19 6WL	Chichester	South East	2015/2016	4	Development completed	15/03543/FUL	11/11/2015	11/03/2016	Residential	No	8	11/01/2019	0	8	Yes	No	0	0	0	0	0	8	0	0	0	0	8	0	0
PSLR0966	PLHP 2	DHSC	14 Creffield Road	14 CREFFIELD ROAD COLCHESTER ESSEX CO3 3JA	CO3 3JA	Colchester	East	2015/2016	1	Development completed	151697	08/08/2015	14/09/2015	Residential	No	1	21/02/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	0	0	1	0	0
PSLR0967	PLHP 2	DHSC	14 Stratford Road+C718	14 STRATORD ROAD CASSIO UNIT) WATFORD HERTFORDHIRE	WD17 4DG	Watford	East	2016/2017	38	Development completed	15/01662/FULM	27/11/2015	26/05/2016	Residential	No	38	19/09/2018	0	38	Yes	Yes	8	3	2	0	0	16	22	0	0	5	0	33	0
PSLR0968	PLHP 2	DHSC	17 Quay Haven	17 QUAY HAVEN LOWER SWANWICK SOUTHAMPTON SO31 7DE	SO31 7DE	Fareham	South East	2015/2016	1	Development completed	P/15/0479/CU	21/05/2015	14/07/2015	Residential	No	1	21/02/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0969	PLHP 2	DHSC	2 Eastfield Road	2 EASTFIELD ROAD LOUTH LN11 7AN	LN11 7AN	East Lindsey	East Midlands	2016/2017	1	Development completed	N/105/01477/16	13/07/2016	13/09/2016	Mixed	No	1	31/10/2017	0	1	Yes	No	0	0	0	0	0	0	0	1	0	0	0	1	0
PSLR0970	PLHP 2	DHSC	2-3, 4 Pitfields Chelmsford	2-3, 4 PITFIELDS CHELMSFORD CM2 9QY	CM2 9QY	Chelmsford	East	2015/2016	7	Development completed	15/01928/FUL	20/11/2015	11/03/2016	Residential	No	7	28/04/2017	0	7	Yes	No	0	0	0	0	0	7	0	0	0	0	7	0	0
PSLR0971	PLHP 2	DHSC	59 - 65 Whipton Barton Road	59 - 65 WHIPTON BARTON ROAD EXETER DEVON EX1 3NE	EX1 3NE	Exeter	South West	2016/2017	22	Development started	16/0398/FUL	24/03/2016	09/08/2016	Residential	No	22	24/05/2019	0	22	Yes	Yes	0	0	0	0	22	0	0	22	0	0	0	22	0
PSLR0972	PLHP 2	DHSC	61 Rectory Lane	61 RECTORY LANE BURY BL9 7TA	BL9 7TA	Bury	North West	2015/2016	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0973	PLHP 2	DHSC	61 Vernon Avenue	61 VERNON AVENUE BASFORD NOTTINGHAM NG6 0AQ	NG6 0AQ	Nottingham	East Midlands	2015/2016	1	Development completed	x	x	x	Residential sale	No	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR0974	PLHP 2	DHSC	68-69 Swanmore Road	68-69 SWANMORE ROAD RYDE, ISLE OF WIGHT PO33 2TF	PO33 2TF	Isle of Wight	South East	2015/2016	3	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR0976	PLHP 2	DHSC	Abbey Road CMHT	ABBEY ROAD CMHT 15-19 BLENHEIM TERRACE LONDON NW8 0EH	NW8 0EH	Westminster	London	2015/2016	3	Development started	14/12517/FULL	18/12/2014	26/04/2016	Residential	No	3	29/01/2020	0	3	No	No	0	0	0	0	0	1	0	2	0	0	0	0	3
PSLR0977	PLHP 2	DHSC	Alex Stables Alexandra House	ALEX STABLES ALEXANDRA HOUSE VINES LANE HILDENBROROUGH TONBRIDGE	TN11 9LT	Tonbridge and Malling	South East	2016/2017	2	Development completed	14/03644/FL	27/10/2014	21/09/2015	Residential	No	2	09/08/2017	0	2	Yes	No	0	0	0	0	0	2	0	0	2	0	0	0	0
PSLR0978	PLHP 2	DHSC	Ann moss way SE162TL	Ann moss way SE162TL	SE16 2TL	Southwark	London	2016/2017	1	Development completed	15/AP/4160	13/10/2015	04/02/2016	Residential	No	1	01/12/2016	0	1	Yes	No	0	0	0	0	0	0	0	1	1	0	0	0	0
PSLR0979	PLHP 2	DHSC	Audley House	AUDLEY HOUSE LEYBOURNE ME19 5JA	ME19 5JA	Tonbridge and Malling	South East	2015/2016	1	Development completed	14/03703/PD3J	30/10/2014	16/12/2014	Residential	No	1	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR0980	PLHP 2	DHSC	Bowhill The Drive	BOWHILL THE DRIVE HELLINGLY EAST SUSSEX BN27 4EP	BN27 4EP	Wealden	South East	2016/2017	8	Planning stage	WD/2014/2231/MAO	23/10/2014	26/01/2015	Residential	No	8	x	0	0	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0981	PLHP 2	DHSC	Bucknall Hospital	BUCKNALL HOSPITAL EAVES LANE BUKNALLSTOKE ON TRENT ST2 8LD	ST2 8LD	Stoke-on-Trent	West Midlands	2015/2016	165	Development started	58877/FUL	28/09/2015	29/02/2016	Residential	Yes	201	24/03/2017	0	60	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	43	0	17	32	27	0	0	1
PSLR0982	PLHP 2	DHSC	Campsall Clinic	CAMPSALL CLINIC PARK DRIVE CAMPSALL DONCASTER DN6 9NS	DN6 9NS	Doncaster	Yorkshire and The Humber	2016/2017	3	Development completed	16/01547/FUL	13/06/2016	20/01/2017	Residential	No	3	25/07/2017	0	3	Yes	No	0	0	0	0	0	3	0	0	1	2	0	0	0
PSLR0983	PLHP 2	DHSC	Canterbury Ambulance Station	CANTERBURY AMBULANCE STATION, OLD RUTTINGTON LANE, CANTERBURY, KENT	CT1 1NY	Canterbury	South East	2015/2016	14	Development completed	CA/15/02311/FUL	06/07/2016	03/08/2016	Residential	No	14	26/04/2018	0	14	Yes	No	0	0	0	0	0	8	6	0	1	1	6	6	0
PSLR0984	PLHP 2	DHSC	Castle Hill House	65 Bournemouth road, Poole, BH140EN	BH140EN	Poole	South West	2016/2017	36	Development completed	APP/16/00262/R	19/02/2016	19/05/2016	Residential	No	36	12/12/2017	0	35	Yes	Unknown	0	0	0	0	0	0	35	0	0	0	0	35	0
PSLR0985	PLHP 2	DHSC	Chase Farm Plot A Hospital	CHASE FARM PLOT A HOSPITAL THE RIDGEWAY ENFIELD EN2 8JL	EN2 8JL	Enfield	London	2016/2017	138	Development started	16/05535/RM	17/02/2017	29/06/2017	Residential	No	138	13/08/2017	68	38	No	Yes	0	0	0	0	26	36	0	2	0	0	13	1	24
PSLR0986	PLHP 2	DHSC	Coval Lane Ambulance station	Coval Lane, Chelmsford, Essex CM1 1TD	CM1 1TD	Chelmsford	East	2016/2017	30	Development completed	15/01462/FUL	09/04/2015	03/02/2017	Residential	No	30	08/08/2018	0	30	Yes	Yes	7	0	4	0	0	11	19	0	1	0	10	19	0
PSLR0987	PLHP 2	DHSC	Craven Arms Ambulance Station	Ludlow Road, Craven Arms, SY7 9QL	SY7 9QL	Shropshire	West Midlands	2016/2017	7	Development completed	14/04924/FUL	11/05/2014	31/03/2015	Residential	No	7	10/10/2016	0	7	Yes	No	0	0	0	0	0	0	0	7	0	0	7	0	0
PSLR0988	PLHP 2	DHSC	Cricket Field Grove	CRICKET FIELD GROVE CRICKET FIELD GROVE CROWTHORNE BERKSHIRE	RG45 7ES	Bracknell Forest	South East	2015/2016	145	Development started	16/00914/FUL	20/09/2016	12/01/2018	Residential	No	130	10/01/2019	20	46	No	Yes	15	0	7	0	0	38	0	8	11	15	15	5	0
PSLR0989	PLHP 2	DHSC	Disposal Charter House - Trowbridge (planned February 2017)	Charter House Seymour Road , Trowbridge, Wiltshire, BA14 8LS	BA14 8LS	Wiltshire	South West	2016/2017	16	Development completed	16/03974/FUL	26/04/2016	09/12/2016	Residential	No	40	31/05/2018	0	39	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	39	0	0	0	1	1	37
PSLR0990	PLHP 2	DHSC	Disposal of Heath End Road building	72 Heath End Road Nuneaton Warwickshire CV10 7JQ	CV10 7DJ	Nuneaton and Bedworth	West Midlands	2016/2017	1	Development completed	33415	19/05/2015	08/07/2015	Residential	No	1	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	0	1	0	0	0
PSLR0991	PLHP 2	DHSC	Disposal Red Gables - Trowbridge	Red Gables Hilperton road Trowbridge BA14 7JE	BA14 7JE	Wiltshire	South West	2016/2017	8	Development started	16/04021/PNCOU	26/04/2016	15/06/2016	Residential	No	8	29/03/2017	0	7	Yes	No	0	0	0	0	0	0	7	0	0	0	0	7	0
PSLR0992	PLHP 2	DHSC	Elmfield House	Elmfield House 50-52 Prescott Street Halifax HX1 2QW	HX1 2QW	Calderdale	Yorkshire and The Humber	2016/2017	14	Planning stage	16/00585/FUL	03/05/2016	10/10/2016	Residential	No	14	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR0993	PLHP 2	DHSC	Eric Shepherd Administration	ERIC SHEPHERD ADMINISTRATION,WOODSIDE ROAD, ABBOTS LANGLEY, HERTFORDSHIRE	WD5 0HT	Three Rivers	East	2015/2016	20	Development completed	15/2000/AOD	01/10/2015	22/12/2015	Residential	No	20	18/11/2016	0	17	No	Yes	0	8	0	0	0	17	0	0	0	0	9	8	0
PSLR0994	PLHP 2	DHSC	Farnham Road Hospital	FARNHAM ROAD HOSPITAL FARNHAM ROAD GUILDFORD SURREY GU2 7LX	GU2 7LX	Guildford	South East	2015/2016	14	Development completed	15/P/02156	17/11/2015	25/02/2016	Residential	No	14	05/03/2018	0	14	Yes	No	0	0	0	0	0	0	14	0	0	0	0	14	0
PSLR0995	PLHP 2	DHSC	Frenchay Hospital	FRENCHAY HOSPITAL FRENCHAY PARK ROAD BRISTOL	BS16 1LE	South Gloucestershire	South West	2015/2016	490	Development started	PT13/0002/O	21/12/2012	05/12/2014	Mixed	No	490	12/04/2016	9	160	Yes	Yes	0	0	0	0	123	134	18	8	57	63	19	21	0
PSLR0996	PLHP 2	DHSC	Frimley Children's Centre	FRIMLEY CHILDREN'S CENTRE CHURCH ROAD GU16 7AD	GU16 7AD	Surrey Heath	South East	2015/2016	63	Development started	13/0374	29/05/2013	22/10/2013	Residential	No	63	15/09/2016	0	44	Yes	No	0	0	0	0	0	14	20	10	0	0	14	30	0
PSLR0998	PLHP 2	DHSC	Guy's and St Thomas' NHS Trust HQ 221 Consort Road	GUY'S AND ST THOMAS' NHS TRUST HQ 221 CONSORT ROAD LONDON SE15 3SB	SE15 3SB	Southwark	London	2016/2017	8	Development completed	16/AP/2434	14/06/2016	01/11/2016	Residential	No	8	11/10/2018	0	8	Yes	No	0	0	0	0	0	8	0	0	0	0	0	8	0
PSLR0999	PLHP 2	DHSC	HILCOTE HOUSE	HILCOTE HOUSE SALISBURY 22 MANOR ROAD SALISBURY SP1 1JS	SP1 1JS	Wiltshire	South West	2016/2017	3	Development started	16/10852/LBC	07/11/2016	09/01/2017	Residential	No	5	19/03/2012	0	4	No	No	0	0	0	0	0	4	0	0	2	1	0	0	1
PSLR1000	PLHP 2	DHSC	Lambourne End Radio mast	Lambourne End, Romford Essex RM4 11LX	RM4 11LX	Epping Forest	East	2016/2017	1	Development started	EPF/2045/15	12/09/2015	20/10/2015	Residential	No	1	27/01/2020	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1001	PLHP 2	DHSC	Littlemore Park	LITTLEMORE PARK OX4 4XN	OX4 4FY	Oxford	South East	2015/2016	270	Planning stage	14/02940/OUT	23/10/2014	31/03/2016	Residential	No	270	x	0	0	Yes	Yes	0	108	28	0	0	0	0	0	0	0	0	0	0
PSLR1002	PLHP 2	DHSC	Moneyhull Hall Road	MONEYHULL HALL ROAD BIRMINGHAM B30 3QJ	B0 3QJ	Birmingham	West Midlands	2015/2016	6	Planning stage	2012/07072/PA	18/10/2012	12/12/2012	Residential	No	6	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1003	PLHP 2	DHSC	Mulfords hill centre	37-39 Mulfords Hill, Tadley, RG26 3HX	RG26 3HX	Basingstoke and Deane	South East	2016/2017	1	Planning stage	16/04074/FUL	02/11/2016	02/03/2017	Residential	No	8	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1004	PLHP 2	DHSC	North Tyneside General Hospital (rear staff car park & adjacent fields)	NORTH TYNESIDE GENERAL HOSPITAL (REAR STAFF CAR PARK & ADJACENT FIELDS) RAKE LANE NORTH SHIELDS TYNE & WEAR NE29 8NH	NE29 8NH	North Tyneside	North East	2016/2017	61	Development completed	15/00617/REM	22/04/2015	01/09/2015	Residential	Unknown	61	05/07/2016	0	60	Yes	Yes	0	0	0	0	13	60	0	0	36	16	8	0	0
PSLR1005	PLHP 2	DHSC	Old Ivy Chimneys	OLD IVY CHIMNEYS HATFIELD ROAD WITHAM	CM8 1EN	Braintree	East	2015/2016	26	Planning stage	19/00109/FUL	21/01/2019	x	Residential	Yes	19	x	x	x	Yes	No	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1006	PLHP 2	DHSC	Old Severalls Hospital	OLD SEVERALLS HOSPITAL BOXTED ROAD COLCHESTER	C04 5HG	Colchester	East	2015/2016	547	Development started	152733	10/12/2015	28/04/2016	Residential	Yes	730	03/02/2017	51	396	No	Yes	89	0	23	0	0	171	183	42	127	91	117	61	0
PSLR1007	PLHP 2	DHSC	Pontefract General Infirmary	PONTEFRACT GENERAL INFIRMARY FRIARWOOD LANE PONTERACT	WF8 1PL	Wakefield	Yorkshire and The Humber	2015/2016	124	Development started	15/01463/FUL	16/06/2015	02/12/2015	Residential	No	124	20/12/2016	6	112	Yes	Yes	5	0	0	0	0	65	39	8	37	48	25	2	0
PSLR1009	PLHP 2	DHSC	QEII hospital	QEII Hospital Howlands Welwyn Garden City Herts AL7 4HQ	AL7 4HQ	Welwyn Hatfield	East	2016/2017	64	Development started	6/2015/2132/RM	15/10/2015	18/02/2016	Residential institute	No	64	18/09/2017	0	1	Yes	No	0	0	0	0	0	0	0	1	0	0	0	0	1
PSLR1010	PLHP 2	DHSC	Queens Road Clinic 29-31 Queens Road	29-31 Queens Road, Barnsley, S71 1AN	S71 1AN	Barnsley	Yorkshire and The Humber	2015/2016	2	Development completed	2015/1079	28/08/2015	29/10/2015	Residential	No	2	19/03/2012	0	2	Yes	No	0	0	0	0	0	2	0	0	0	2	0	0	0
PSLR1011	PLHP 2	DHSC	SANDBACH MENTAL HEALTH RESOURCE CENTRE Field House	40 Congleton Road Sandbach CW11 1HJ	CW11 1HJ	Cheshire East	North West	2016/2017	9	Planning stage	18/0433C	12/03/2018	09/04/2018	Commercial	No	0	x	x	x	Yes	No	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1012a	PLHP 2	DHSC	St Clements Hospital	ST CLEMENTS HOSPITAL FOXHALL ROAD IPSWICH SUFFOLK IP3 8LS	IP3 8LS	Ipswich	East	2015/2016	227	Development completed	16/00659/REM	08/07/2016	04/10/2016	Residential	No	47	26/05/2017	2	47	Yes	Yes	13	0	5	0	0	24	19	4	0	0	25	22	0
PSLR1012b	PLHP 2	DHSC	St Clements Hospital	ST CLEMENTS HOSPITAL FOXHALL ROAD IPSWICH SUFFOLK IP3 8LS	IP3 8LS	Ipswich	East	2015/2016	227†	Development started	16/00677/REM	18/07/2016	16/12/2016	Residential	No	179	28/12/2017	25	154	Yes	Yes	14	0	4	0	0	137	11	6	38	80	16	20	0
PSLR1013	PLHP 2	DHSC	St Leonards Hospital	ST LEONARDS HOSPITAL NEWTON ROAD SUDBURY	CO10 2RQ	Babergh	East	2016/2017	12	Development completed	B/14/00585	02/05/2014	22/02/2016	Residential	No	12	14/12/2017	0	12	Yes	No	0	0	0	0	0	12	0	0	4	6	1	1	0
PSLR1014	PLHP 2	DHSC	St Waleric & Coach House	ST WALERIC & COACH HOUSE 112 ST WALERIC PARK ROAD ABBOTS Barton	SO23 7BE	Winchester	South East	2016/2017	1	Development completed	16/01338/FUL	14/06/2016	02/08/2016	Residential	No	1	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR1015	PLHP 2	DHSC	Stanley House	STANLEY HOUSE, CHARTHAM DOWN RD CHARTHAM KENT	CT4 7PS	Canterbury	South East	2015/2016	3	Planning stage	CA//18/00644	27/03/2018	x	Residential	No	3	x	x	x	Yes	No	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1016	PLHP 2	DHSC	The London Chest Hospital	THE LONDON CHEST HOSPITAL BONNER ROAD LONDON	E2 9JX	Tower Hamlets	London	2015/2016	450	Planning stage	PA/16/03342/A1	06/12/2016	x	Residential	No	291	x	x	x	Yes	Yes	0	44	26	0	0	x	x	x	x	x	x	x	x
PSLR1017	PLHP 2	DHSC	Tindal Centre	TINDAL CENTRE AYLESBURY BIERTON ROAD AYLESBURY	HP20 1HU	Aylesbury Vale	South East	2015/2016	112	Development completed	16/02917/ADP,17/01113/APP	08/08/2016	23/12/2016	Residential,Infill	No,No	69	10/05/2017	0	69	Yes,Yes	Yes,Yes	13	0	8	0	0	43	21	5	7	2	30	30	0
PSLR1018	PLHP 2	DHSC	WHITE LODGE COMMUNITY UNIT	New Penkridge Rd, Cannock, Staffs, WS11 1HN	WS11 1HN	Cannock Chase	West Midlands	2016/2017	3	Planning stage	CH/11/0312	09/09/2011	18/04/2012	Residential	Yes	3	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1019	PLHP 2	DHSC	Withington Hospital (old site)	WITHINGTON HOSPITAL (OLD SITE) NELL LANE MANCHESTER CAVENDISH ROAD WITHINGTON MANCHESTER M20 2LR	M20 2LR	Manchester	North West	2016/2017	79	Development started	113937/MO/2016	16/09/2016	16/12/2016	Residential	No	74	05/02/2018	0	71	Yes	Unknown	0	0	0	0	0	43	23	5	16	27	4	24	0
PSLR1020	PLHP 2	DHSC	221-225 Erith Road (Main Building)	Bexleyheath, DA7 6HZ	DA7 6HZ	Bexley	London	2016/2017	28	Planning stage	16/03252/PRIOR	21/12/2016	17/02/2017	Residential	No	28	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1021	PLHP 2	DHSC	Bidford Health Centre	Highstreet, Bidford-on-Avon, Alcester	B50 4BQ	Stratford-on-Avon	West Midlands	2016/2017	9	Planning stage	17/03422/REM	13/11/2017	17/01/2018	Residential	No	9	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1022	PLHP 2	DHSC	Bridgwater Hospital	Salmon Parade, Bridgwater, TA6 5AH	TA6 5AH	Sedgemoor	South West	2016/2017	3	Development completed	08/16/00009	05/02/2016	12/03/2016	Mixed	No	3	x	0	2	Yes	No	0	0	0	0	0	0	0	2	0	0	0	2	0
PSLR1023	PLHP 2	DHSC	Cherry Tree Hospital - Administration Block	Dialstone Lane, Great Moor, Stockport	SK2 6AU	Stockport	North West	2016/2017	15	Planning stage	DC/058756	29/05/2015	14/12/2016	Residential	No	15	x	0	0	Yes	Yes	0	1	2	0	0	0	0	0	0	0	0	0	0
PSLR1024	PLHP 2	DHSC	Conway House	156 Whalley Road, Accrington, BB5 1BS	BB5 1BS	Hyndburn	North West	2015/2016	1	Development completed	11/15/0406	18/11/2015	18/01/2016	Residential	No	1	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	0	0	1	0	0
PSLR1025	PLHP 2	DHSC	Coppins Court	Coppins Road, Clacton-on-Sea	CO15 3HS	Tendring	East	2016/2017	52	Planning stage	16/01916/FUL	22/11/2016	24/02/2017	Residential institute	No	60	x	0	0	Yes	Yes	0	0	0	0	30	0	0	0	0	0	0	0	0
PSLR1026	PLHP 2	DHSC	Countess of Chester Health Park (Land)	Chester, CH2 1HJ	CH2 1HJ	Cheshire West and Chester	North West	2015/2016	90	Development started	17/01543/FUL	03/04/2017	30/08/2017	Residential	No	74	10/08/2018	0	0	Yes	Yes	0	0	0	0	22	0	0	0	0	0	0	0	0
PSLR1027	PLHP 2	DHSC	Highwood Hospital Holly Bungalow	Geary Drive, Brentwood, Essex,	CM14 4FZ	Brentwood	East	2016/2017	2	Development completed	16/00641/FUL	29/06/2016	21/10/2016	Residential	Yes	11	08/07/2017	0	1	No	No	0	0	0	0	0	1	0	0	0	0	1	0	0
PSLR1028	PLHP 2	DHSC	Highwood Hospital Ivy Bungalow	Geary Drive, Brentwood, Essex,	CM14 4FZ	Brentwood	East	2016/2017	3	Development completed	16/00641/FUL	29/06/2016	21/10/2016	Residential	Yes	11	08/07/2017	0	2	No	No	0	0	0	0	0	1	0	1	0	0	2	0	0
PSLR1029	PLHP 2	DHSC	Kingswood CLDT	Hanham Road , Kingswood, Bristol, BS15 9PQ	BS15 9PQ	South Gloucestershire	South West	2016/2017	9	Development started	PK16/4214/F	08/07/2016	21/10/2016	Residential	No	9	07/03/2018	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1030	PLHP 2	DHSC	Moreton Hospital (Moreton in the Marsh)	Moreton in Marsh, GL56 2AZ	GL56 2AZ	Cotswold	South West	2016/2017	21	Development started	17/03221/FUL	04/08/2017	21/11/2017	Residential	No	20	22/11/2019	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1031	PLHP 2	DHSC	Pershore Cottage Hospital (Retained)	Defford, WR10 1HZ	WR10 1HZ	Wychavon	West Midlands	2016/2017	23	Development completed	15/03239	23/12/2015	15/03/2016	Residential	No	23	22/06/2017	0	23	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	23	0	0	0	0	23	0
PSLR1032	PLHP 2	DHSC	Pinetree Place	36 A,B,C & D Ashingdon Road, Rochford	SS4 1NJ	Rochford	East	2015/2016	7	Development completed	15/00419/FUL	19/06/2015	15/10/2015	Residential	No	4	18/04/2016	0	4	Yes	No	0	0	0	0	0	1	0	3	0	4	0	0	0
PSLR1033	PLHP 2	DHSC	Railton Road Health Centre	Brixton, SE24 0LT	SE24 0LT	Lambeth	London	2016/2017	5	Planning stage	15/04741/OUT	20/08/2015	07/04/2016	Residential	No	5	x	0	0	No	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1034	PLHP 2	DHSC	Sheldon Health Land Only	Birmingham, B26 2DS	B26 2DS	Birmingham	West Midlands	2015/2016	30	Development completed	2015/05549/PA	19/10/2015	24/05/2016	Residential	No	30	26/03/2018	0	30	Yes	Yes	15	0	0	0	0	0	9	21	1	0	0	0	29
PSLR1035	PLHP 2	DHSC	Springman House	Lewes, BN7 2PB	BN7 2PB	Lewes	South East	2016/2017	10	Planning stage	SDNP/14/03118/DCOUPN	16/06/2014	04/09/2014	Residential	No	10	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1036	PLHP 2	DHSC	Stockburn Memorial Clinic	Southlands, Kettering, NN15 7QG	NN15 7QG	Kettering	East Midlands	2016/2017	6	Development started	KET/2015/0895	02/02/2016	20/05/2016	Residential	No	6	09/07/2019	4	2	Yes	No	0	0	0	0	0	2	0	0	2	0	0	0	0
PSLR1037	PLHP 2	DHSC	Stockmead Nurses Bungalow, Lower Langford, Langford, Bristol, BS40 5JD	Stockmead, Lower Langford, Langford, Bristol, BS40 5JD	BS40 5JD	North Somerset	South West	2016/2017	1	Development completed	15/P/1552/F	23/06/2015	08/09/2015	Residential	No	1	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR1038	PLHP 2	DHSC	Tring Health Centre	Station Road, Tring, HP23 5NF	HP23 5NF	Dacorum	East	2016/2017	4	Development completed	4/00157/17/FUL	20/01/2017	02/05/2017	Residential	No	4	01/05/2018	0	4	Yes	No	0	0	0	0	0	4	0	0	0	4	0	0	0
PSLR1039	PLHP 2	DHSC	Upton Clinic	Chester, CH2 1QJ	CH2 1QJ	Cheshire West and Chester	North West	2016/2017	5	Development completed	16/01991/FUL	12/05/2016	02/09/2016	Residential	No	5	22/02/2018	0	5	Yes	No	0	0	0	0	0	5	0	0	1	4	0	0	0
PSLR1040	PLHP 2	Homes England	51-55, Great Ancoats Street [key ref 43] - aka Selhide	M4 6JG	M4 6JG	Manchester	North West	2015/2016	150	Planning stage	112256/FO/2016	27/09/2016	13/01/2017	Mixed	Yes	143	x	0	0	No	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1041	PLHP 2	Homes England	6 Loom Street [key ref 13] aka the Ice Cream Factory	M4 6JG	M4 6JG	Manchester	North West	2015/2016	1	Planning stage	108469/FO/2015/N1	09/06/2015	20/08/2015	Residential	No	1	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1042	PLHP 2	Homes England	66 Jersey St key ref 41A and 41B	M4 6JG	M4 6JG	Manchester	North West	2015/2016	100	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Not applicable	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1043	PLHP 2	Homes England	Apley B1 & B3	TF1 6TJ	TF1 6TJ	Telford and Wrekin	West Midlands	2016/2017	100	Development started	TWC/2015/0843	18/09/2015	17/03/2017	Residential	No	100	12/10/2018	1	60	Yes	Unknown	0	0	0	0	0	34	0	26	30	30	0	0	0
PSLR1044	PLHP 2	Homes England	Belle Vue Ambulance Station - NHS_05	M12 5PW	M12 5PW	Manchester	North West	2015/2016	14	Development completed	111404/MO/2016/N2	08/03/2016	07/06/2016	Residential	No	14	12/07/2017	0	14	Yes	No	0	0	0	0	0	5	9	0	2	12	0	0	0
PSLR1045	PLHP 2	Homes England	Bill Howarths Yard [key ref 27b, 27c], 99-111 Jersey St and 30a Poland St [27a]	M4 6JG	M4 6JG	Manchester	North West	2015/2016	100	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Not applicable	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1046	PLHP 2	Homes England	Brodsworth Colliery	DN6 7PA	DN6 7PA	Doncaster	Yorkshire and The Humber	2016/2017	350	Development started	10/02812/EXTM	28/10/2010	30/03/2017	Residential	Yes	343	27/07/2018	13	102	Yes	Yes	0	0	0	0	89	92	0	10	29	73	0	0	0
PSLR1047	PLHP 2	Homes England	Bucknall Main Site	ST2 8LS	ST2 8LS	Stoke-on-Trent	West Midlands	2015/2016	43	Development started	58877/FUL	28/09/2015	29/02/2016	Residential	Yes	201	29/07/2017	0	17	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	13	0	4	16	0	0	0	1
PSLR1048	PLHP 2	Homes England	Car Park At Kilnmead	RH101YD	RH101YD	Crawley	South East	2015/2016	40	Planning stage	CR/2017/0444/FUL	26/05/2017	30/01/2018	Residential	No	37	x	0	0	Yes	Yes	0	0	0	0	37	0	0	0	0	0	0	0	0
PSLR1049	PLHP 2	Homes England	Celsea Place, Fair Mile, Cholsey Meadows	OX10 9QW	OX10 9QW	South Oxfordshire	South East	2016/2017	60	Development started	P15/S0262/O	02/02/2015	26/08/2015	Residential	No	60	24/07/2018	1	58	Yes	Mix of pay and houses	18	0	6	0	0	44	0	14	5	43	6	4	0
PSLR1051	PLHP 2	Homes England	Chelmsley ADR Land	B37 7GW	B37 7GW	Solihull	West Midlands	2016/2017	68	Development started	PL/2017/01434/PPFL	03/06/2017	19/12/2017	Residential	No	68	31/08/2018	0	68	Yes	Yes	17	0	10	0	0	49	11	8	20	13	15	20	0
PSLR1052	PLHP 2	Homes England	Chequer Lane, Up Holland	WN8 0DE	WN8 0DE	West Lancashire	North West	2016/2017	116	Development started	2017/0880/FUL	18/08/2017	15/08/2018	Residential	No	116	17/09/2019	8	12	Yes	No	0	0	0	0	0	5	0	7	11	1	0	0	0
PSLR1053	PLHP 2	Homes England	Cheshire Cheese PH site [key ref 3], 32-40 Oldham Rd aka	M4 6JG	M4 6JG	Manchester	North West	2016/2017	40	Planning stage	119731/FO/2018	19/04/2018	15/11/2018	Mixed	No	38	x	0	0	No	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1054	PLHP 2	Homes England	Cornwall Council Plot 1 (Formally Plot 9) Residential Land at Tolvaddon Business Park	TR140EP	TR14 0EP	Cornwall	South West	2016/2017	38	Development started	PA16/08453	21/09/2016	18/01/2017	Residential	No	38	21/06/2019	0	38	Yes	Unknown	0	0	0	0	0	0	0	38	0	4	31	3	0
PSLR1055	PLHP 2	Homes England	Daedalus Direct Commissioning Residential Plots	PO139JY	PO139JY	Gosport	South East	2016/2017	200	Development started	11/00282/OUT	13/03/2012	28/01/2016	Mixed	Yes	200	21/02/2012	14	180	Yes	No	0	0	0	0	0	154	0	26	1	35	108	31	5
PSLR1056	PLHP 2	Homes England	Deerbolt - MoJ_02	DL129BG	DL129BG	County Durham	North East	2016/2017	162	Development started	DM/16/03310/FPA	17/10/2016	21/08/2017	Residential	No	162	19/10/2018	2	32	Yes	Yes	0	0	10	0	14	25	1	6	12	8	0	0	12
PSLR1057	PLHP 2	Homes England	DoH Transfer - Standish Hospital, Housemarling Lane, Standish, Gloucestershire - NHSPS_08	GL103DA	GL103DA	Stroud	South West	2016/2017	130	Development started	S.17/2729/FUL	01/12/2017	14/02/2019	Residential	Yes	147	19/03/2012	0	3	Yes	No	0	0	0	0	0	0	0	3	1	2	0	0	0
PSLR1058	PLHP 2	Homes England	Donnington H - Phase III	TF2 7RY	TF2 7RY	Telford and Wrekin	West Midlands	2015/2016	79	Development completed	TWC/2015/0028	13/01/2015	04/11/2015	Residential	No	79	17/06/2016	0	79	Yes	Yes	0	14	6	0	0	73	6	0	8	33	38	0	0
PSLR1059	PLHP 2	Homes England	East Quayside (ONS_05)	NE1 2PE	NE1 2PE	Newcastle upon Tyne	North East	2016/2017	262	Planning stage	2016/1416/01/DET	31/08/2016	x	Mixed	No	124	x	x	x	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1060	PLHP 2	Homes England	Eastway Development Site	PR2 9RN	PR2 9RN	Preston	North West	2015/2016	300	Development started	06/2015/0968	04/10/2016	19/01/2017	Mixed	No	300	15/03/2017	0	79	No	Mix of pay and houses	0	0	0	0	45	55	14	10	79	0	0	0	0
PSLR1061	PLHP 2	Homes England	Enfield 7, Redditch	B97 6AD	B97 6AD	Redditch	West Midlands	2016/2017	44	Development started	2015/042/FUL	17/02/2015	03/12/2015	Residential	No	44	20/10/2017	0	44	Yes	Yes	44	0	0	0	0	40	3	1	2	30	12	0	0
PSLR1062	PLHP 2	Homes England	Former All Saints School Site	M18 8BR	M18 8BR	Manchester	North West	2015/2016	48	Development completed	111403/MO/2016/N2	09/03/2016	22/06/2016	Residential	No	48	19/02/2018	0	48	Yes	Unknown	0	0	0	0	0	18	28	2	10	38	0	0	0
PSLR1063	PLHP 2	Homes England	Former Well Road Car Park	PO326EZ	PO326EZ	Isle of Wight	South East	2015/2016	9	Planning stage	TCP/11809/A	03/05/2012	02/10/2012	Residential	Yes	9	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1064	PLHP 2	Homes England	Gedling Colliery Building Lease Area	NG4 4HF	NG4 4HF	Gedling	East Midlands	2015/2016	1050	Development started	2015/1376	28/11/2015	03/03/2017	Residential	No	1050	01/02/2018	2	149	No	Unknown	0	0	0	0	0	124	7	18	39	25	19	11	55
PSLR1065	PLHP 2	Homes England	German Warehouses, 11 Radium St Key ref 44 Ancoats Estate	M4 6JG	M4 6JG	Manchester	North West	2015/2016	35	Development completed	111616/FO/2016/N1	18/03/2016	03/06/2016	Residential	No	32	12/10/2018	0	32	Yes	Unknown	0	0	0	0	0	0	32	0	0	0	0	32	0
PSLR1066	PLHP 2	Homes England	Hood St site [key ref 29], 2-22 Hood St & 21-35 Jersey St aka New Mill site	M4 6JG	M4 6JG	Manchester	North West	2016/2017	31	Development completed	109593/FO/2015/N1	27/07/2015	19/10/2015	Mixed	No	31	19/06/2018	0	30	Yes	Unknown	0	0	0	0	0	0	30	0	0	0	2	28	0
PSLR1067	PLHP 2	Homes England	Kings Waterfront remaining site	L3 4FP	L3 4FP	Liverpool	North West	2016/2017	309	Planning stage	17F/3261	03/11/2017	x	Mixed	No	400	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1068a	PLHP 2	Homes England	Kingsmead South Site 3 and 4	MK4 4HQ	MK4 4HQ	Milton Keynes	South East	2016/2017	154	Development started	17/00098/REM	16/01/2017	23/10/2017	Residential	No	114	23/11/2018	28	21	Yes	Yes	20	0	4	0	0	14	2	5	19	1	1	0	0
PSLR1068b	PLHP 2	Homes England	Kingsmead South Site 3 and 4	MK4 4HQ	MK4 4HQ	Milton Keynes	South East	2016/2017	154†	Planning stage	17/00103/REM	16/01/2017	23/10/2017	Residential	No	49	x	0	0	Yes	Yes	19	0	4	0	0	0	0	0	0	0	0	0	0
PSLR1069	PLHP 2	Homes England	Knowle Hospital	PO175LS	PO175LS	Winchester	South East	2016/2017	19	Development started	14/00421/OUT	17/02/2014	01/12/2015	Residential	No	18	20/11/2019	0	2	Yes	Yes	0	0	0	0	10	2	0	0	0	0	2	0	0
PSLR1070	PLHP 2	Homes England	Land At Admirals Road	WA3 6NX	WA3 6NX	Warrington	North West	2016/2017	20	Development completed	2016/28810	26/08/2016	18/05/2017	Residential	Unknown	66	27/09/2017	0	66	Yes	Yes	0	0	20	0	0	58	8	0	1	30	35	0	0
PSLR1071	PLHP 2	Homes England	Land at Chapel Street Site	TR151AU	TR151AU	Cornwall	South West	2016/2017	16	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Not applicable	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1072	PLHP 2	Homes England	Land at Clifton Road and Church Street	TN355AH	TN355AH	Hastings	South East	2015/2016	5	Planning stage	HS/DS/17/00194	15/03/2017	21/07/2017	Residential	No	5	x	0	0	Yes	Yes	0	1	0	0	0	0	0	0	0	0	0	0	0
PSLR1073	PLHP 2	Homes England	Land At Corner Of Abbeystead	WN8 9NU	WN8 9NU	West Lancashire	North West	2016/2017	45	Planning stage	2017/0876/FUL	18/08/2017	15/08/2018	Residential	No	45	x	0	0	Yes	Yes	0	0	18	0	27	0	0	0	0	0	0	0	0
PSLR1074	PLHP 2	Homes England	Land At Croston Road South - Phase 1	PR267QF	PR267QF	South Ribble	North West	2015/2016	96	Development started	07/2015/1726/REM	02/11/2015	24/03/2016	Residential	Yes	175	20/01/2017	0	76	Yes	Mix of pay and houses	16	0	10	0	0	56	19	1	53	4	19	0	0
PSLR1075	PLHP 2	Homes England	Land At Croston Road South - Phase 2	PR267QF	PR267QF	South Ribble	North West	2015/2016	79	Development started	07/2015/1726/REM	02/11/2015	24/03/2016	Residential	Yes	175	12/10/2018	4	56	Yes	Mix of pay and houses	16	0	10	0	0	42	0	14	32	12	12	0	0
PSLR1076	PLHP 2	Homes England	Land At Lightfoot Lane Preston	Unknown	PR4 0AJ	Preston	North West	2016/2017	125	Development started	06/2015/0546	05/11/2015	08/01/2016	Residential	No	125	17/11/2016	0	26	Yes	Yes	0	0	0	0	38	23	0	3	26	0	0	0	0
PSLR1077	PLHP 2	Homes England	Land North Of Granville Road	TF2 7QD	TF2 7QD	Telford and Wrekin	West Midlands	2015/2016	22	Development started	TWC/2016/0159	19/02/2016	13/04/2016	Residential	No	34	16/04/2018	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1078	PLHP 2	Homes England	Land South of Elwick Road (inc Cattle Market and DC Site)	TN231LH	TN231LH	Ashford	South East	2015/2016	200	Planning stage	15/01195/AS	08/09/2015	22/12/2015	Commercial	No	0	x	x	x	No	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1079	PLHP 2	Homes England	Lea Green Farm West	tbc	WA9 5GG	St Helens	North West	2016/2017	120	Development started	P/2016/0567/HYBR	22/07/2016	14/11/2016	Residential	No	120	x	0	0	No	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1080	PLHP 2	Homes England	Limekilns, Wellington Street	L3 6JH	L3 6JH	Liverpool	North West	2016/2017	35	Development started	17F/1911	07/07/2017	28/11/2018	Mixed	No	614	x	0	0	No	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1081	PLHP 2	Homes England	Lnd Abbotts Farm & Shady Lane	PR255RQ	PR25 5RQ	Chorley	North West	2016/2017	220	Development started	17/00369/REMMAJ	04/04/2017	18/08/2017	Residential	No	220	29/11/2018	10	49	Yes	Yes	0	0	0	0	66	19	0	30	19	18	12	0	0
PSLR1082	PLHP 2	Homes England	Locking Parklands Phs 3+	BS24 8BB	BS24 8BB	North Somerset	South West	2016/2017	166	Development started	15/P/1777/RM	20/06/2015	17/07/2015	Residential	Yes	168	20/10/2016	0	165	Yes	Yes	0	0	0	0	50	125	37	3	50	54	26	35	0
PSLR1083	PLHP 2	Homes England	Loom St, Smith Arms, Express Motors[Key Refs 8a, 8b, 8c]	M4 6JG	M4 6JG	Manchester	North West	2016/2017	278	Development completed	111742/FO/2016/N1	04/05/2016	03/06/2016	Mixed	No	199	12/02/2019	0	199	Yes	Unknown	0	0	0	0	0	0	122	77	0	0	14	185	0
PSLR1084	PLHP 2	Homes England	Maiden Law Hospital	DH7 0QS	DH7 0QS	County Durham	North East	2016/2017	38	Development started	DM/16/03019/RM	19/09/2016	20/01/2017	Residential	No	47	05/04/2019	1	23	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	13	0	10	23	0	0	0	0
PSLR1085	PLHP 2	Homes England	Middlefield, Dorridge	B93 0PF	B93 0PF	Solihull	West Midlands	2015/2016	110	Development started	PL/2015/52196/PPFL	29/09/2015	25/02/2016	Residential	No	110	12/01/2017	0	110	Yes	Yes	24	0	20	0	0	84	21	5	22	33	37	18	0
PSLR1086	PLHP 2	Homes England	Murray's Mills [key ref 36a], Murray St incl New Mill, Old Mill & Decker Mill	M4 6JG	M4 6JG	Manchester	North West	2015/2016	125	Development started	108566/FO/2015/N2	08/05/2015	02/07/2015	Residential	No	124	08/02/2019	5	119	Yes	Unknown	0	0	0	0	0	0	54	65	0	0	0	119	0
PSLR1087	PLHP 2	Homes England	New Little Mill [key ref 36b], 54 Jersey St	M4 6JG	M4 6JG	Manchester	North West	2015/2016	60	Development started	116300/FO/2017	12/05/2017	28/07/2017	Residential	No	68	x	68	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1088	PLHP 2	Homes England	Northfleet Embankment - Former TT Site	DA119AA	DA11 9AA	Gravesham	South East	2016/2017	632	Planning stage	20170316	27/03/2017	x	Mixed	Unknown	628	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1089	PLHP 2	Homes England	Park Prewett Northern Area Phase 2A	RG249RD	RG249RD	Basingstoke and Deane	South East	2016/2017	142	Development started	17/03356/RES	04/10/2017	28/03/2018	Residential	No	142	05/04/2019	2	22	Yes	Yes	0	0	0	0	67	16	0	6	2	14	6	0	0
PSLR1090	PLHP 2	Homes England	Parkside 2, Coventry	CV1 2JT	CV1 2JT	Coventry	West Midlands	2015/2016	398	Planning stage	FUL/2015/3153	08/09/2015	15/01/2016	Residential institute	Unknown	586	x	0	0	No	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1091	PLHP 2	Homes England	Part Of Silvester's Farm	PR7 6DR	PR7 6DR	Chorley	North West	2016/2017	170	Development started	17/00356/REMMAJ	10/04/2017	17/08/2017	Residential	No	140	06/07/2018	10	102	Yes	Unknown	0	0	0	0	0	85	0	17	71	12	19	0	0
PSLR1092	PLHP 2	Homes England	Part of site to be sold to TRL, Tipner Grehound Stadium	PO2 8RE	PO2 8RE	Portsmouth	South East	2016/2017	40	Planning stage	10/00849/OUT	20/08/2010	30/03/2012	Mixed	Yes	518	x	0	0	No	Yes	45	0	0	0	20	0	0	0	0	0	0	0	0
PSLR1093	PLHP 2	Homes England	PD fuels	PO2 8PE	PO2 8PE	Portsmouth	South East	2015/2016	80	Planning stage	15/01854/REM	10/11/2015	17/11/2015	Mixed	No	80	x	0	0	Yes	Yes	0	0	4	0	0	0	0	0	0	0	0	0	0
PSLR1094	PLHP 2	Homes England	Phase 1, Upton Park	NN5 4UX	NN5 4UX	Northampton	East Midlands	2016/2017	250	Planning stage	N/2011/0997	03/10/2011	31/03/2015	Mixed	Yes	250	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1095	PLHP 2	Homes England	Phase 2, Upton Park	NN5 4UX	NN5 4UX	Northampton	East Midlands	2016/2017	250	Planning stage	N/2011/0997	03/10/2011	31/03/2015	Mixed	Yes	250	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1096	PLHP 2	Homes England	Phase 3, Upton Park	NN5 4UX	NN5 4UX	Northampton	East Midlands	2016/2017	250	Planning stage	N/2011/0997	03/10/2011	31/03/2015	Mixed	Yes	250	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1097	PLHP 2	Homes England	Phase 4, Upton Park	NN5 4UX	NN5 4UX	Northampton	East Midlands	2016/2017	250	Planning stage	N/2011/0997	03/10/2011	31/03/2015	Mixed	Yes	250	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1098	PLHP 2	Homes England	Phase 4a Centenary Quay	SO199SS	SO19 9SS	Southampton	South East	2015/2016	346	Development completed	15/01985/REM	29/10/2015	30/03/2016	Mixed	No	185	02/11/2017	0	185	No	No	0	0	0	0	0	0	120	65	0	0	0	185	0
PSLR1099	PLHP 2	Homes England	Pleasley Colliery	NG197EY	NG197EY	Bolsover	East Midlands	2016/2017	23	Development completed	17/00337/REM	07/07/2017	06/10/2017	Residential	No	19	04/05/2018	0	19	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	19	0	0	19	0	0	0	0
PSLR1100	PLHP 2	Homes England	Plot C2 at Millbay Docks	PL1 3FQ	PL13FQ	Plymouth	South West	2016/2017	80	Planning stage	17/00140/REM	09/01/2017	15/02/2017	Mixed	No	80	x	0	0	Yes	Yes	70	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1101	PLHP 2	Homes England	Plot Y&Z3, Castle Court Area	DT5 1BL	DT5 1BL	Weymouth and Portland	South West	2015/2016	65	Development started	WP/15/00920/RES	09/02/2016	13/07/2016	Residential	No	68	25/04/2018	1	19	No	Yes	0	0	21	0	0	13	0	6	3	7	8	1	0
PSLR1102	PLHP 2	Homes England	Priorslee East E and F	TF2 9NQ	TF2 9NQ	Telford and Wrekin	West Midlands	2016/2017	220	Development started	TWC/2017/0347	26/04/2017	10/08/2017	Residential	No	220	14/09/2018	14	95	Yes	Yes	0	45	10	0	0	66	9	20	40	33	22	0	0
PSLR1103	PLHP 2	Homes England	Priorslee East Plot D3 - Phase II	TF2 9GZ	TF2 9GZ	Telford and Wrekin	West Midlands	2016/2017	25	Development started	TWC/2016/0804	30/08/2016	22/02/2017	Residential	No	20	10/12/2018	0	20	Yes	Yes	0	4	1	0	0	0	0	20	0	17	0	3	0
PSLR1104	PLHP 2	Homes England	Q&R Residential Phase 1	ME115HX	ME11 5HX	Swale	South East	2016/2017	100	Development started	16/507298/FULL	10/10/2016	07/07/2017	Residential	Yes	101	17/04/2018	0	99	Yes	Yes	0	0	0	0	30	68	26	5	11	79	5	4	0
PSLR1105	PLHP 2	Homes England	Remaining Development Plots	NE243AT	NE243AT	Northumberland	North East	2016/2017	10	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Not applicable	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1106	PLHP 2	Homes England	Res Dev Parcel N2 Cottam Hall	PR4 0WD	PR4 0WD	Preston	North West	2015/2016	119	Development started	06/2017/0324	28/03/2017	15/03/2018	Residential	Yes	119	16/01/2020	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1107	PLHP 2	Homes England	Reserve Site 84	MK4 2AN	MK4 2AN	Milton Keynes	South East	2016/2017	8	Development started	16/03394/FUL	28/11/2016	30/06/2017	Residential	No	9	18/01/2019	3	6	Yes	No	0	0	0	0	0	4	0	2	5	1	0	0	0
PSLR1108	PLHP 2	Homes England	RoC Tanyard Farm, Runcorn	Unknown	Unknown	Halton	North West	2016/2017	34	Development completed	16/00024/FUL	08/01/2016	19/05/2016	Residential	No	34	13/09/2017	0	32	No	No	0	0	0	0	0	17	14	1	16	3	11	0	2
PSLR1109	PLHP 2	Homes England	Rochester Riverside	ME1 1PB	ME1 1PB	Medway	South East	2016/2017	240	Development started	MC/17/2333	27/07/2017	01/02/2018	Mixed	Yes	1400	x	0	0	No	Yes	210	0	140	0	0	0	0	0	0	0	0	0	0
PSLR1110	PLHP 2	Homes England	Saltergate Health Centre and Marsden Street Clinic - NHS_02	S40 1LA	S40 1LA	Chesterfield	East Midlands	2016/2017	35	Development completed	CHE/17/00263/FUL	04/07/2017	08/08/2017	Residential	No	34	08/05/2018	0	34	Yes	Yes	0	0	0	0	4	28	6	0	19	9	0	6	0
PSLR1111	PLHP 2	Homes England	Seaham Colliery East	SR7 0BL	SR7 0BL	County Durham	North East	2016/2017	150	Planning stage	DM/17/02872/FPA	25/08/2017	x	Residential	Yes	160	x	x	x	No	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1113	PLHP 2	Homes England	Site 18R Royal Quays, North Shore	NE296YJ	NE296YJ	North Tyneside	North East	2016/2017	34	Development started	16/01692/FUL	19/10/2016	18/04/2017	Residential	No	34	19/10/2018	0	33	No	Developer paid local authority to put them somewhere else	0	0	0	0	0	17	16	0	0	17	0	16	0
PSLR1114	PLHP 2	Homes England	South Omega Residential Zone 6	WA5 3XA	WA5 3XA	Warrington	North West	2016/2017	915	Development started	2015/26469	27/08/2015	01/06/2016	Mixed	Yes	1100	22/03/2019	10	75	No	Yes	0	0	0	0	220	59	0	16	57	10	8	0	0
PSLR1115	PLHP 2	Homes England	South Omega Zone 5	WA5 3XA	WA5 3XA	Warrington	North West	2016/2017	85	Development started	2015/26469	27/08/2015	01/06/2016	Mixed	Yes	1100	x	0	0	No	Yes	0	0	0	0	220	0	0	0	0	0	0	0	0
PSLR1116	PLHP 2	Homes England	South Omega Zones 3 and 4	WA5 3XA	WA5 3XA	Warrington	North West	2016/2017	100	Development started	2015/26469	27/08/2015	01/06/2016	Mixed	Yes	1100	x	0	0	No	Yes	0	0	0	0	220	0	0	0	0	0	0	0	0
PSLR1118a	PLHP 2	Homes England	St Lawrences & part of Beacon Technology Park Building Agreement	PL312QT	PL31 2QT	Cornwall	South West	2016/2017	175	Development started	PA16/08465	21/09/2016	09/03/2017	Residential	No	75	25/02/2019	1	72	No	Unknown	0	0	0	0	0	1	0	71	0	5	55	12	0
PSLR1118b	PLHP 2	Homes England	St Lawrences & part of Beacon Technology Park Building Agreement	PL312QT	PL31 2QT	Cornwall	South West	2016/2017	175†	Planning stage	PA19/05744	03/07/2019	23/10/2019	Residential	No	100	x	0	0	No	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1119	PLHP 2	Homes England	St Marys Island	ME4 3ER	ME4 3ER	Medway	South East	2015/2016	85	Development started	MC/13/2210	06/09/2013	18/07/2014	Mixed	No	339	16/03/2016	0	84	Unknown	Yes	x	19	21	x	x	68	15	1	28	50	6	0	0
PSLR1120	PLHP 2	Homes England	Stockbridge Airco site [key ref 24a,b] 5 Murray Street, 73-83 Jersey Street and 74-90 Blossom Street	M4 6JG	M4 6JG	Manchester	North West	2016/2017	79	Development completed	110077/FO/2015/N1	16/09/2015	11/12/2015	Mixed	Unknown	158	22/06/2018	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1121	PLHP 2	Homes England	The Beeches, Lincoln	TF8 7NY	TF8 7NY	Telford and Wrekin	West Midlands	2016/2017	85	Development started	TWC/2016/0562	27/06/2016	15/11/2016	Residential	Unknown	89	02/03/2019	16	50	Yes	Yes	2	0	2	0	0	43	0	7	5	12	33	0	0
PSLR1122	PLHP 2	Homes England	Tomsett Way Sites (former Neats Court site)	ME115JS	ME115JS	Swale	South East	2016/2017	60	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Unknown	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1123	PLHP 2	Homes England	Tower Works Developable Site (904036) (904543)	LS115PS	LS11 5PS	Leeds	Yorkshire and The Humber	2015/2016	147	Development started	15/06578/FU	04/11/2015	12/07/2016	Mixed	Yes	160	28/11/2019	0	0	Yes	Yes	0	4	5	0	0	0	0	0	0	0	0	0	0
PSLR1124a	PLHP 2	Homes England	Town Centre Sites - Findon and Land East of Northway - Skelmersdale	WN8 6PG	WN8 6PG	West Lancashire	North West	2016/2017	208	Development started	2017/0664/FUL	22/06/2017	10/11/2017	Residential	No	104	20/12/2018	1	6	Yes	No	0	0	0	0	0	5	0	1	2	4	0	0	0
PSLR1124b	PLHP 2	Homes England	Town Centre Sites - Findon and Land East of Northway - Skelmersdale	WN8 6PG	WN8 6PG	West Lancashire	North West	2016/2017	208†	Development started	2017/0663/FUL	22/06/2017	10/11/2017	Residential	No	35	08/07/2019	1	3	Yes	No	0	0	0	0	0	1	0	2	0	3	0	0	0
PSLR1125	PLHP 2	Homes England	Trumpet Land - Park Prewett - HA_03	RG249GY	RG249GY	Basingstoke and Deane	South East	2016/2017	122	Development started	17/02383/RES	07/07/2017	14/02/2018	Residential	No	122	23/01/2020	6	1	Yes	Yes	29	0	15	0	0	0	0	1	1	0	0	0	0
PSLR1126	PLHP 2	Homes England	Upton Cottages, Northampton	NN5 4UY	NN5 4UY	Northampton	East Midlands	2016/2017	2	Planning stage	N/2017/0321	28/03/2017	22/05/2017	Residential	No	1	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1127	PLHP 2	Homes England	Victoria Road (South Hotel & Residential)	TN237RP	TN237RP	Ashford	South East	2015/2016	216	Development started	16/01157/AS	01/08/2016	10/04/2017	Mixed	Yes	216	11/06/2019	0	10	No	No	0	0	0	0	0	0	0	10	0	0	0	10	0
PSLR1128	PLHP 2	Homes England	VIVO Phase 3 - University of Durham, North Shore	TS18 2SZ	TS18 2SZ	Stockton-on-Tees	North East	2016/2017	62	Development started	16/2306/FUL	05/09/2016	30/01/2017	Residential	Yes	82	12/04/2018	4	73	Yes	No	0	0	0	0	0	47	8	18	1	20	52	0	0
PSLR1129	PLHP 2	Homes England	Whalleys 4 North (Development land)	WN8 6TD	WN8 6TD	West Lancashire	North West	2016/2017	202	Development started	2016/0769/ARM	15/07/2016	07/02/2017	Residential	No	202	03/10/2017	12	119	Yes	Yes	0	0	60	0	0	63	30	26	26	88	5	0	0
PSLR1130a	PLHP 2	Homes England	Nottingham, Peace Mills site	NG139FQ	NG139FQ	Nottingham	East Midlands	2016/2017	22	Development completed	17/00487/PFUL3	03/03/2017	04/07/2017	Residential	No	21	26/06/2018	0	21	Yes	No	0	0	0	0	0	21	0	0	0	0	21	0	0
PSLR1130b	PLHP 2	Homes England	Nottingham, Peace Mills site	NG139FQ	NG139FQ	Nottingham	East Midlands	2016/2017	22†	Development started	18/00579/PFUL3	22/03/2018	01/06/2018	Residential	No	9	09/08/2019	0	3	Unknown	No	0	0	0	0	0	3	0	0	0	0	3	0	0
PSLR1131	PLHP 2	MoD	Annington Homes SFA - various locations Q11617	Various locations	Unknown	x	x	2016/2017	392	Development completed	x	x	x	Residential sale	No	392	x	x	392	Not applicable	Unknown	0	0	0	0	0	x	x	392	x	x	x	x	392
PSLR1132	PLHP 2	MoD	Annington Homes SFA - various locations Q21617	Various locations	Unknown	x	x	2016/2017	8	Development completed	x	x	x	Residential sale	No	8	x	x	8	Not applicable	Unknown	0	0	0	0	0	x	x	8	x	x	x	x	8
PSLR1133	PLHP 2	MoD	Catterick Garrison Misc - Shute Road Complex - Part	Off Catterick Road, DL9	DL9 4SU	Richmondshire	Yorkshire and The Humber	2015/2016	19	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Not applicable	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1134	PLHP 2	MoD	Howe Barracks. Old Park Training Area - Housing Unit Record	Littlebourne Road, CT1 1JY	CT1 1JY	Canterbury	South East	2015/2016	500	Development started	CA//14/01230	01/07/2014	15/12/2015	Mixed	No	500	12/11/2018	41	58	Yes	Yes	76	0	57	0	0	35	3	20	12	37	9	0	0
PSLR1135	PLHP 2	MoD	SFA New Build Q31617	Various locations	Unknown	x	x	2016/2017	14	Development completed	x	x	x	Residential sale	No	14	x	x	14	Not applicable	Unknown	0	0	0	0	0	x	x	14	x	x	x	x	14
PSLR1136	PLHP 2	MoD	SFA New Build Q41516	Stafford	Unknown	Stafford	West Midlands	2015/2016	289	Development completed	x	x	x	Residential sale	No	289	x	x	289	Not applicable	Unknown	0	0	0	0	0	x	x	289	x	x	x	x	289
PSLR1137	PLHP 2	MoD	SFA New Build Q416/17	Various locations	Unknown	x	x	2016/2017	66	Development completed	x	x	x	Residential sale	No	66	x	x	66	Not applicable	Unknown	0	0	0	0	0	x	x	66	x	x	x	x	66
PSLR1138	PLHP 2	MoD	SLA New Build Normandy Barracks	Building 804, Normandy Barracks, Leconfield, Beverley HU17 7LX	HU17 7LX	East Riding of Yorkshire	Yorkshire and The Humber	2015/2016	48	Development completed	x	x	x	Residential sale	No	48	x	x	48	Not applicable	Unknown	0	0	0	0	0	x	x	48	x	x	x	x	48
PSLR1139	PLHP 2	MoD	SLA New Build Q11617	Various locations	Unknown	x	x	2016/2017	153	Development completed	x	x	x	Residential sale	No	153	x	x	153	Not applicable	Unknown	0	0	0	0	0	x	x	153	x	x	x	x	153
PSLR1140	PLHP 2	MoD	SLA New Build Q21617	Various locations	Unknown	x	x	2016/2017	125	Development completed	x	x	x	Residential sale	No	125	x	x	125	Not applicable	Unknown	0	0	0	0	0	x	x	125	x	x	x	x	125
PSLR1141	PLHP 2	MoD	SLA New Build Q31617	Various locations	Unknown	x	x	2016/2017	57	Development completed	x	x	x	Residential sale	No	57	x	x	57	Not applicable	Unknown	0	0	0	0	0	x	x	57	x	x	x	x	57
PSLR1142	PLHP 2	MoD	SLA New Build Q41617	Various locations	Unknown	x	x	2016/2017	64	Development completed	x	x	x	Residential sale	No	64	x	x	64	Not applicable	Unknown	0	0	0	0	0	x	x	64	x	x	x	x	64
PSLR1143	PLHP 2	MoJ	Dorking Magistrates' Court	The Court House, London Road, Dorking, Surrey RH4 1SX	RH4 1SX	Mole Valley	South East	2016/2017	21	Development started	MO/2016/0340	18/03/2016	24/03/2017	Mixed	No	21	x	22	0	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1144	PLHP 2	MoJ	Tower House (Judges Lodgings)	Tower House, 58, Bracon Dale, Norwich, Norfolk, NR1 2AP	NR1 2AP	Norwich	East	2016/2017	2	Planning stage	18/01681/F	08/11/2018	16/07/2019	Residential	No	6	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1145	PLHP 2	MoJ	HMP Blundeston	Blundeston, Norfolk, NR32 5BG	NR32 5BG	Waveney	East	2015/2016	75	Planning stage	DC/17/2675/ARM	16/06/2017	31/05/2018	Mixed	Yes	130	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1146	PLHP 2	MoJ	HMP Bullwood Hall	BULLWOOD HALL LANE	SS5 4TE	Rochford	East	2015/2016	60	Planning stage	15/00379/OUT	08/06/2015	21/12/2015	Residential	No	60	x	0	0	Yes	Yes	15	0	6	0	0	0	0	0	0	0	0	0	0
PSLR1147	PLHP 2	MoJ	Wandsworth, Land adjacent to railway	SW18 3HS	SW18 3HS	Wandsworth	London	2016/2017	18	Development started	2016/5168	08/09/2016	13/06/2017	Residential	No	18	12/02/2020	6	12	Yes	Yes	0	0	4	0	0	9	2	1	0	0	7	5	0
PSLR1148	PLHP 2	Homes England	Whittle Hall Farm & Buildings	WA5 3AQ	WA5 3AQ	Warrington	North West	2016/2017	84	Development started	2015/26350	05/08/2015	10/11/2015	Residential institute	No	74	13/12/2017	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1149	PLHP 2	Homes England	Woodlands farm buildings	TF4 3QF	TF4 3QF	Telford and Wrekin	West Midlands	2016/2017	4	Planning stage	TWC/2018/0033	12/01/2018	10/05/2019	Residential	No	8	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1150	PLHP 2	DfT	Chobham Farm North Zone 2	Leyton Road, Stratford, London		Newham	London	2017/2018	154	Development started	17/00175/REM	24/04/2017	17/08/2017	Mixed	No	154	20/08/2019	0	15	Yes	Yes	16	16	22	0	0	2	6	7	0	0	0	15	0
PSLR1151	PLHP 2	DfT	Lincoln 179 High Street	179 High Street, Lincoln	LN5 7AF	Lincoln	East Midlands	2017/2018	44	Planning stage	2016/0203/F	14/03/2016	05/07/2016	Mixed	No	44	x	0	0	No	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1152	PLHP 2	DHSC	26 Ditchling road	26 Ditchling Road, Brighton	BN1 4SF	Brighton and Hove	South East	2017/2018	4	Development completed	BH2016/05884	28/10/2016	12/05/2017	Mixed	No	4	03/07/2019	0	4	Yes	No	0	0	0	0	0	0	0	4	0	0	0	4	0
PSLR1153	PLHP 2	DHSC	36 Posthill Tiverton EX16 4ND	36 Posthill Tiverton	EX16 4ND	Mid Devon	South West	2017/2018	76	Planning stage	14/00604/MFUL	28/04/2014	20/04/2017	Residential	Yes	76	x	0	0	Yes	Yes	4	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1154	PLHP 2	DHSC	Barrowby House Highland Grove	Barrowby House 9 Highland Grove Worksop Nottinghamshire	S81 0JN	Bassetlaw	East Midlands	2017/2018	8	Development started	17/00141/FUL	30/01/2017	18/04/2017	Residential	No	8	23/09/2019	3	4	Yes	No	0	0	0	0	0	0	0	4	4	0	0	0	0
PSLR1155	PLHP 2	DHSC	Boiler House adjacent to Clayton hospital, Wakefield	Clayton Hospital Northgate Wakefield	WF1 3JS	Wakefield	Yorkshire and The Humber	2017/2018	5	Development started	16/02033/FUL	16/08/2016	13/04/2017	Residential	No	5	13/06/2017	0	3	Yes	No	0	0	0	0	0	2	0	1	1	2	0	0	0
PSLR1156a	PLHP 2	DHSC	Cheltenham General Hospital 1 & 2 COLLEGE LAWN CHELTENHAM	Cheltenham General Hospital Sandford Road Cheltenham Gloucestershire	GL53 7AN	Cheltenham	South West	2017/2018	13	Planning stage	17/02163/FUL	07/11/2017	09/02/2018	Residential	No	3	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1156b	PLHP 2	DHSC	Cheltenham General Hospital 1 & 2 COLLEGE LAWN CHELTENHAM	Cheltenham General Hospital Sandford Road Cheltenham Gloucestershire	GL53 7AN	Cheltenham	South West	2017/2018	13†	Planning stage	17/01005/LBC	24/05/2017	06/07/2017	Residential institute	No	70	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1157	PLHP 2	DHSC	Coppett's Wood Hospital	Coppetts Wood Hospital Coppetts Road Muswell Hill London	N10 1JN	Haringey	London	2017/2018	80	Planning stage	HGY/2016/3482	18/09/2016	27/04/2017	Residential	No	80	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1158	PLHP 2	DHSC	Culverhay	Culverhay 24 Midvale Road Paignton	TQ4 5BD	Torbay	South West	2017/2018	3	Development started	P/2016/1230	11/11/2016	13/04/2017	Residential	No	3	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	0	1	0	0	0
PSLR1159	PLHP 2	DHSC	Ex Social Club West Park	Epsom Social Club, Horton Lane Epsom Surrey	KT19 8NX	Epsom and Ewell	South East	2017/2018	1	Planning stage	16/00096/FUL	18/04/2016	20/06/2016	Residential	No	1	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1160	PLHP 2	DHSC	Fareham Ambulance Station	Fareham Ambulance Station, Highlands Road, Fareham	PO15 6JP	Fareham	South East	2017/2018	10	Development started	P/17/0213/FP	23/02/2017	31/05/2017	Residential	No	10	11/06/2018	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1161	PLHP 2	DHSC	Maghull Ambulance Station	Maghull Ambulance Station, Kenyons Lane, Lydiate, Liverpool	L31 0BP	Sefton	North West	2017/2018	3	Development started	DC/2017/00231	27/02/2017	24/04/2017	Residential	No	3	07/11/2019	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1162	PLHP 2	DHSC	Park House, Leamington Spa	Park House 17 Avenue Road Leamington Spa	CV31 3PG	Warwick	West Midlands	2017/2018	8	Development completed	W/16/1064	02/05/2016	03/08/2016	Residential	No	8	06/06/2017	0	8	Yes	No	0	0	0	0	0	0	8	0	0	0	0	8	0
PSLR1163	PLHP 2	DHSC	The Stepping Stones	The Stepping Stones, 34/36 Highland Grove Worksop, NOTTS	S81 0JN	Bassetlaw	East Midlands	2017/2018	2	Development completed	13/01449/COU	12/12/2013	31/03/2014	Residential	No	2	19/03/2012	0	2	Yes	No	0	0	0	0	0	2	0	0	1	1	0	0	0
PSLR1164	PLHP 2	DHSC	Underleaf	Underleaf,13 Boxbush road Coleford	GL16 8DN	Forest of Dean	South West	2017/2018	1	Development completed	P1679/16/FUL	02/12/2016	08/02/2017	Residential	No	1	02/12/2017	0	1	Yes	No	0	0	0	0	0	0	0	1	1	0	0	0	0
PSLR1165	PLHP 2	DHSC	Walnut Tree Hospital	Walnut Tree Hospital, Walnut Treet Lane Sudbury	CO10 1BE	Babergh	East	2017/2018	55	Development completed	B/16/01192	30/06/2016	30/01/2017	Residential	No	55	02/06/2017	0	54	Yes	No	0	0	0	0	0	13	41	0	2	7	4	41	0
PSLR1166	PLHP 2	MoD	Annington Homes SFA - various locations Q11718	Various locations		x	x	2017/2018	2	Development completed	x	x	x	Residential sale	No	2	x	x	2	Not applicable	Not applicable	0	0	0	0	0	x	x	2	x	x	x	x	2
PSLR1167	PLHP 2	MoD	SFA New Build 17/18 Q11718	Tidworth		x	x	2017/2018	75	Development completed	x	x	x	Residential sale	No	75	x	x	75	Not applicable	Not applicable	0	0	0	0	0	x	x	75	x	x	x	x	75
PSLR1168	PLHP 2	MoD	SLA New Build Q11718	Larkhill		x	x	2017/2018	7	Development completed	x	x	x	Residential sale	No	7	x	x	7	Not applicable	Unknown	0	0	0	0	0	x	x	7	x	x	x	x	7
PSLR1169	PLHP 2	MoJ	Standford Hill, Plot at Brabazon Road	Brabazon Road, Standford Hill	ME12 4AA	Swale	South East	2017/2018	2	Planning stage	16/507201/FULL	04/10/2016	01/02/2017	Residential	No	2	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1170	PLHP 2	MoJ	Thurrock, Five Wells	Five Wells, West Street, Thurrock, Essex		Thurrock	East	2017/2018	17	Planning stage	17/00704/PAOFFR	25/05/2017	11/07/2017	Residential	No	17	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1171	PLHP 2	Homes England	Marine Parade A (AKA Stubbington Parcels)		PO13 9JY	Fareham	South East	2017/2018	15	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Not applicable	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1172	PLHP 2	Homes England	Wootton Basset Road - BRBR_07		SN1 5ES	Swindon	South West	2017/2018	200	Planning stage	x	x	x	x	Unknown	x	x	x	x	Not applicable	Not applicable	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1173	PLHP 2	DEFRA	Taunton Quantock House	Quantock House, Paul Street, Taunton, Somerset	TA1 3PF	Taunton Deane	South West	2017/2018	120	Planning stage	38/16/0345	08/09/2016	06/07/2017	Residential	No	120	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1174	PLHP 2	DfT	Crosby	Land off Hall Rd West, Blundellsands, Crosby, Liverpool	L23 8SZ	Sefton	North West	2017/2018	14	Development started	DC/2016/01523	10/08/2016	26/06/2017	Residential	No	14	19/03/2019	2	8	Yes	No	0	0	0	0	0	6	0	2	8	0	0	0	0
PSLR1175	PLHP 2	DHSC	67-69 St. Giles Street	67-69 St Giles Street, Northampton	NN1 1JF	Northampton	East Midlands	2017/2018	60	Planning stage	N/2016/1138	15/09/2016	20/09/2017	Mixed	No	60	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1176	PLHP 2	DHSC	9 - 10 Trim Street	9 - 10 Trim Street Bath	BA1 1HB	Bath & NE Somerset	South West	2017/2018	10	Planning stage	17/02636/FUL	02/06/2017	30/08/2017	Mixed	No	10	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1177	PLHP 2	DHSC	Chase Farm Plot B Hospital	Chase Farm Hospital, Plot B, The Ridgeway, Enfield	EN2 8JL	Enfield	London	2017/2018	362	Development started	14/04574/OUT	01/02/2016	30/08/2016	Mixed	Yes	362	07/02/2017	0	0	No	Yes	0	13	53	0	115	0	0	0	0	0	0	0	0
PSLR1178a	PLHP 2	DHSC	Elmsleigh Lodge	Elmsleigh Lodge, 118 Maidstone Road, Chatham	ME4 6DQ	Medway	South East	2017/2018	4	Planning stage	MC/16/2653	20/06/2016	12/10/2017	Residential	No	4	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1178b	PLHP 2	DHSC	Elmsleigh Lodge	Elmsleigh Lodge, 118 Maidstone Road, Chatham	ME4 6DQ	Medway	South East	2017/2018	4†	Development started	MC/16/2333	27/05/2016	22/06/2016	Residential	No	9	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR1179	PLHP 2	DHSC	Moorland Road	13 Moorland Road, Par	PL24 2PA	Cornwall	South West	2017/2018	1	Planning stage	PA17/05090	30/05/2017	20/06/2017	Residential	No	1	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1180	PLHP 2	DHSC	Preston Skreens	Preston Skreens, 402 Minister Road, Minister On Sea Sheppey	ME12 3NZ	Swale	South East	2017/2018	12	Development completed	17/501162/FULL	22/02/2017	09/08/2017	Residential	No	12	10/10/2018	0	12	Yes	No	0	0	0	0	0	12	0	0	0	4	7	1	0
PSLR1181	PLHP 2	DHSC	South Moor Hospital	South Moor Hospital, Middles Road, South Moore, Stanley, Co Durham	DH9 6AG	County Durham	North East	2017/2018	65	Development started	DM/16/02732/FPA	22/08/2016	15/08/2017	Residential	No	65	18/02/2019	11	32	Yes	No	0	0	0	0	0	24	0	8	6	18	0	0	8
PSLR1182	PLHP 2	DHSC	11 Station Road	11 Station Road, Maidstone Kent	ME14 1QJ	Maidstone	South East	2017/2018	24	Development completed	18/502806/PNOCLA	23/05/2018	17/07/2018	Residential	No	27	21/08/2018	0	27	Yes	No	0	0	0	0	0	0	0	27	0	0	0	27	0
PSLR1183	PLHP 2	DHSC	Chestnut Farm Surgery	174 Dunvegan Road, Hull	HU8 9LF	Kingston upon Hull	Yorkshire and The Humber	2017/2018	1	Development completed	17/00693/FULL	23/05/2017	26/09/2017	Residential	No	1	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	0	1	0	0	0
PSLR1184	PLHP 2	DHSC	Lansdowne Road Clinic	23 Landsdowne Road, Tunbridge Wells, Kent	TN1 2NG	Tunbridge Wells	South East	2017/2018	10	Development completed	17/00482/FULL	10/02/2017	15/05/2017	Residential	No	10	06/09/2019	0	10	Yes	No	0	0	0	0	0	0	0	10	0	0	0	10	0
PSLR1185	PLHP 2	MoD	SFA New Build 17/18 Q21718	Tidworth, Wiltshire	SP9 7BB	Wiltshire	South West	2017/2018	74	Development completed	x	x	x	Residential sale	Yes	74	x	x	74	Not applicable	Not applicable	0	0	0	0	0	x	x	74	x	x	x	x	74
PSLR1186	PLHP 2	MoD	SLA New Build Q21718	Various locations		x	x	2017/2018	155	Development completed	x	x	x	Residential sale	No	155	x	x	155	Not applicable	Not applicable	0	0	0	0	0	x	x	155	x	x	x	x	155
PSLR1187	PLHP 2	Homes England	Plot A2 at Millbay Docks	Plot A2, Millbay Docks, Plymouth	PL1 3LS	Plymouth	South West	2017/2018	136	Development started	15/02241/REM	02/12/2015	06/04/2016	Residential	No	136	18/11/2019	0	20	Yes	No	0	0	0	0	0	15	5	0	0	0	20	0	0
PSLR1188	PLHP 2	BEIS	Mill Hill NW7 1AA	National Institute for Medical Research, The Ridgeway, London	NW7 1AA	Barnet	London	2017/2018	460	Development started	16/4545/FUL	15/07/2016	22/12/2017	Mixed	No	460	23/07/2019	14	120	Yes	Yes	54	0	131	0	0	11	109	0	2	0	0	118	0
PSLR1189	PLHP 2	DEFRA	Drayton Farm - clawback	Barn, Drayton Manor Drive, Alcester Road, Stratford upon Avon, Warwickshire	CV37 9RQ	Stratford-on-Avon	West Midlands	2017/2018	2	Development started	15/02611/FUL	15/07/2015	01/10/2015	Residential	No	2	23/05/2018	0	1	Yes	No	0	0	0	0	0	1	0	0	0	1	0	0	0
PSLR1190	PLHP 2	DfT	Elstree & Borehamwood	Land off Byron Avenue, Borehamwood, Hertfordshire	WD6	Hertsmere	East	2017/2018	18	Development started	14/1111/FUL	18/07/2014	28/11/2014	Residential	No	43	04/10/2019	38	6	Yes	Yes	11	0	4	0	0	2	0	4	0	6	0	0	0
PSLR1191	PLHP 2	DfT	Wellingborough	Stanton Cross Wellingborough, N'hamptonshire	NN8 1NA	Wellingborough	East Midlands	2017/2018	173	Development started	WP/2004/0600/O	09/08/2004	28/08/2008	Mixed	Yes	3202	23/10/2019	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1192	PLHP 2	DHSC	18 Old Oak Road	18 Old Oak Road London	W3 7HQ	Hammersmith and Fulham	London	2017/2018	2	Development completed	2017/02025/FUL	17/05/2017	11/10/2017	Residential	No	3	18/06/2019	0	3	Yes	No	0	0	0	0	0	0	0	3	0	0	0	3	0
PSLR1193	PLHP 2	DHSC	ASHBY HOSPITAL (ESTATES TRANSFORMATION PROGRAMME)	Ashby Hospital, Leicester Road, Ashby-de-la-Zouch	LE65 1DG	North West Leicestershire	East Midlands	2017/2018	5	Development started	17/01034/FUL	25/07/2017	21/11/2017	Residential	No	5	22/01/2019	0	4	No	No	0	0	0	0	0	2	0	2	0	4	0	0	0
PSLR1194a	PLHP 2	DHSC	Castleford Normanton & District Hospital	Castleford Normanton & District Hospital Lumley Street, CastleforD	WF10 5LT	Wakefield	Yorkshire and The Humber	2017/2018	149	Development started	17/01065/REM	27/03/2015	25/02/2016	Mixed	No	100	06/12/2018	13	37	Yes	Yes	0	8	6	0	0	32	0	5	23	12	2	0	0
PSLR1194b	PLHP 2	DHSC	Castleford Normanton & District Hospital	Castleford Normanton & District Hospital Lumley Street, CastleforD	WF10 5LT	Wakefield	Yorkshire and The Humber	2017/2018	149†	Development started	17/01066/FUL	24/04/2017	09/11/2017	Mixed	No	49	02/10/2019	1	4	Yes	No	0	0	0	0	0	1	0	3	4	0	0	0	0
PSLR1195	PLHP 2	DHSC	Homeopathic Hospital	41 Church road Tunbridge Wells	TN1 1JU	Tunbridge Wells	South East	2017/2018	12	Development completed	17/01848/FULL	01/06/2017	05/01/2018	Residential	No	12	29/06/2018	0	12	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	0	12	0	0	0	12	0
PSLR1196	PLHP 2	DHSC	Middlesex Outpatients	Middlesex Outpatients Cleveland Street London	T 4JU	Camden	London	2017/2018	50	Development started	2017/0414/P	25/01/2017	15/01/2018	Mixed	No	50	x	0	3	Yes	Yes	0	36	4	0	0	0	0	3	0	0	0	3	0
PSLR1197	PLHP 2	DHSC	PINE LODGE	79 Liverpool Road, Chester	CH2 1AW	Cheshire West and Chester	North West	2017/2018	7	Development completed	17/02742/FUL	22/06/2017	30/08/2017	Residential	No	7	19/03/2012	0	7	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	7	0	0	7	0	0	0	0
PSLR1198	PLHP 2	DHSC	The Gate House Ann Moss Way	THE GATE HOUSE ANN MOSS WAY LOWER ROAD ROTHERHITHE LONDON	SE16 2TH	Southwark	London	2017/2018	1	Planning stage	17/AP/2094	24/05/2017	19/07/2017	Residential	No	1	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1199	PLHP 2	DHSC	WEST HILL HOUSE	West Hill House, 47 Romsey Road	SO22 5DG	Winchester	South East	2017/2018	3	Development completed	17/00612/FUL	01/03/2017	05/06/2017	Residential	No	5	27/11/2018	0	5	Yes	No	0	0	0	0	0	0	0	5	0	0	0	5	0
PSLR1200	PLHP 2	DHSC	73 Barbridge Road	73 Barbridge Road, Bulkington	CV129PD	Nuneaton and Bedworth	West Midlands	2017/2018	2	Development completed	35157	21/09/2017	02/11/2017	Residential	No	2	19/03/2012	0	2	Yes	No	0	0	0	0	0	2	0	0	0	0	0	2	0
PSLR1201	PLHP 2	DHSC	80 Rodney Street	80 Rodney Street, Liverpool	L1 9AR	Liverpool	North West	2017/2018	11	Planning stage	17F/1817	28/07/2017	14/12/2017	Residential	No	11	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1202	PLHP 2	DHSC	Greenhill Health Centre	482 Lupton Rd, Sheffield	S8 7NQ	Sheffield	Yorkshire and The Humber	2017/2018	4	Planning stage	17/04769/FUL	21/11/2017	23/11/2017	Residential	No	4	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1203	PLHP 2	DHSC	Oakswood (Haunch Lane)	282 Haunch Lane, Kings Heath, Birmingham	B13 0QS	Birmingham	West Midlands	2017/2018	11	Development started	2017/05511/PA	14/08/2017	24/11/2017	Residential	No	11	06/12/2018	0	7	Yes	No	0	0	0	0	0	7	0	0	7	0	0	0	0
PSLR1204	PLHP 2	DHSC	Oswaldtwisle Clinic	119 Union Road, Oswaldtwisle, Accrington	BB5 3DD	Hyndburn	North West	2017/2018	9	Development started	11/17/0355	13/07/2017	12/10/2017	Residential	No	9	19/03/2012	0	1	No	No	0	0	0	0	0	0	1	0	0	0	0	0	1
PSLR1205	PLHP 2	HM Treasury	NSI Marton, Blackpool, Mythrop Road, Blackpool, FY3 9YP	Mythrop Road, Blackpool	FY3 9YP	Blackpool	North West	2017/2018	118	Development started	15/0420	30/06/2015	28/10/2016	Residential	No	118	17/08/2018	19	57	Yes	No	0	0	0	0	0	41	0	16	48	7	0	0	2
PSLR1206	PLHP 2	Homes England	Cranes Farm Road (home Ideal)		SS142NT	Basildon	East	2017/2018	20	Planning stage	x	x	x	x	Not applicable	x	x	x	x	Not applicable	Not applicable	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1207	PLHP 2	Homes England	Land At Church Road		SS141RA	Basildon	East	2017/2018	12	Planning stage	x	x	x	x	Not applicable	x	x	x	x	Not applicable	Not applicable	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1208	PLHP 2	Homes England	Land at Wavertree Tech Pk		L15 4LR	Liverpool	North West	2017/2018	40	Development started	17F/2788	09/10/2017	11/04/2018	Residential	No	48	18/07/2019	1	47	Yes	Unknown	0	0	0	0	0	0	0	47	0	37	0	10	0
PSLR1209	PLHP 2	Homes England	Paston Reserve (EP land), PB		PE4 7AA	Peterborough	East	2017/2018	115	Development started	15/01771/WCPP	13/05/2015	11/08/2017	Residential	Yes	1050	x	0	0	No	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1210	PLHP 2	Homes England	Plot 1 - Land at Warwickshire Cricket Ground		B5 7QT	Birmingham	West Midlands	2017/2018	371	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1211	PLHP 2	Homes England	Plot 108 Popes Crescent		SS133AD	Basildon	East	2017/2018	10	Planning stage	x	x	x	x	Not applicable	x	x	x	x	Not applicable	Not applicable	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1212	PLHP 2	Homes England	Pound Lane (Plot 10)		SS155SP	Basildon	East	2017/2018	4	Planning stage	x	x	x	x	Yes	x	x	x	x	Not applicable	Not applicable	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1213	PLHP 2	Homes England	Site B, Station Road, Corby		NN17 1UJ	Corby	East Midlands	2017/2018	150	Planning stage	17/00663/DPA	05/12/2017	03/06/2019	Residential	No	150	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1214	PLHP 2	MoD	SFA New Build 17/18 Q21718 additional	Tidworth		x	x	2017/2018	7	Development completed	x	x	x	Residential sale	Not applicable	7	x	x	7	Not applicable	Not applicable	0	0	0	0	0	x	x	7	x	x	x	x	7
PSLR1215	PLHP 2	MoD	SFA New Build 17/18 Q31718	Tidworth		x	x	2017/2018	113	Development completed	x	x	x	Residential sale	Not applicable	113	x	x	113	Not applicable	Not applicable	0	0	0	0	0	x	x	113	x	x	x	x	113
PSLR1216	PLHP 2	MoD	SLA New Build Q31718	Various locations		x	x	2017/2018	18	Development completed	x	x	x	Residential sale	Not applicable	18	x	x	18	Not applicable	Not applicable	0	0	0	0	0	x	x	18	x	x	x	x	18
PSLR1217	PLHP 2	MoJ	SPALDING MAGISTRATES' COURT	SHEEP MARKET, SESSIONS HOUSE, SPALDING	PE11 1BB	South Holland	East Midlands	2017/2018	1	Planning stage	H16-1017-16	06/10/2016	10/01/2017	Residential	No	1	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1218	PLHP 2	MoJ	Accrington,Burnley Road	84 Burnley Road, Accrington, Lancashire	BB5 1AF	Hyndburn	North West	2017/2018	2	Development completed	11/17/0245	14/03/2017	12/07/2017	Residential	No	2	19/03/2012	0	2	Yes	No	0	0	0	0	0	2	0	0	0	0	2	0	0
PSLR1219	PLHP 2	MoJ	Birmingham, 326-326 Hamstead Rd	326-326 Hamstead Rd, Handsworth, Birmingham, West Midlands	B20 2RA	Birmingham	West Midlands	2017/2018	2	Development started	2017/03692/PA	28/04/2017	27/07/2017	Residential	No	2	28/02/2020	0	1	Yes	No	0	0	0	0	0	0	0	1	0	0	0	1	0
PSLR1220	PLHP 2	MoJ	Bishop Auckland, Beechburn House	Beechburn House, Cockton Hill Road, Bishop Auckland, County Durham	DL14 6HX	County Durham	North East	2017/2018	1	Development completed	DM/17/01799/PNC	30/05/2017	17/07/2017	Residential	No	1	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	0	0	0	0	1
PSLR1221	PLHP 2	MoJ	Bournemouth, 43 Oxford Rd	43 Oxford Rd, Bournemouth	BH8 8EY	Bournemouth	South West	2017/2018	1	Development completed	7-2017-1453-B	14/06/2017	07/08/2017	Residential	No	1	19/03/2012	0	1	Yes	No	0	0	0	0	0	0	0	1	0	1	0	0	0
PSLR1222	PLHP 2	MoJ	Gosforth, Landsdowne Terrace	6 Lansdowne Terrace, Gosforth, Newcastle Upon Tyne	NE3 1HW	Newcastle upon Tyne	North East	2017/2018	9	Development completed	17/00215/NRE	20/04/2017	19/05/2017	Residential	No	9	29/11/2017	0	4	No	No	0	0	0	0	0	0	0	4	0	0	0	4	0
PSLR1223	PLHP 2	MoJ	Newcastle upon Tyne, West Road	717 West Road, Newcastle upon Tyne	NE15 7PS	Newcastle upon Tyne	North East	2017/2018	4	Development completed	17/00226/NRE	28/04/2017	15/06/2017	Residential	No	4	02/05/2018	0	4	Yes	No	0	0	0	0	0	0	3	1	0	0	0	4	0
PSLR1224	PLHP 2	MoJ	North Shields, Lovaine House	Lovaine House, 9 Lovaine Terrace, North Shields, Tyne and Wear	Tyne and Wear NE29 0HJ	North Tyneside	North East	2017/2018	2	Planning stage	17/00771/FUL	26/05/2017	17/08/2017	Residential	No	2	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1225	PLHP 2	MoJ	Sunderland, Kings Road	Kings Road, Southwick, Sunderland	SR5 2LS	Sunderland	North East	2017/2018	1	Development completed	16/02071/FUL	01/11/2016	02/03/2017	Residential	No	1	21/03/2017	0	1	Yes	No	0	0	0	0	0	0	0	1	1	0	0	0	0
PSLR1226	PLHP 2	MoJ	Trowbridge, Rothermere	Rothermere, Bythesea Road, Trowbridge, Wiltshire	B14 8JQ	Wiltshire	South West	2017/2018	1	Planning stage	17/06331/FUL	24/07/2017	19/10/2017	Residential	No	1	x	0	0	Yes	Yes	0	1	0	0	0	0	0	0	0	0	0	0	0
PSLR1227	PLHP 2	MoJ	Wisbech, Castle Lodge	Castle Lodge, 1 Museum Square, Wisbech, Cambridgeshire	PE131ES	Fenland	East	2017/2018	1	Development completed	F/YR17/0912/F	20/09/2017	12/12/2017	Residential	No	1	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR1228	PLHP 2	DEFRA	East Malling - Clawback	92 The Rocks Road And Rocks Farm East Malling West Malling Kent	ME19 6AU	Tonbridge and Malling	South East	2017/2018	4	Development started	15/00547/FL	19/02/2015	13/01/2016	Residential	No	4	18/12/2019	1	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1229	PLHP 2	DEFRA	Water Lane, York - Clawback 2	Land To South East Of Ryedale Caravan Site Green Lane Clifton York		York	Yorkshire and The Humber	2017/2018	66	Development started	17/02420/FULM	20/10/2017	19/01/2018	Residential institute	No	66	07/08/2019	0	1	Yes	No	0	0	0	0	0	0	0	1	0	0	0	0	1
PSLR1230	PLHP 2	DfT	Bishops Stortford - Ph1,2&3	Land off Dane St, Bishops Stortford	CM3 3BP	East Hertfordshire	East	2017/2018	378	Planning stage	3/17/2588/OUT	03/12/2017	18/07/2018	Residential	Yes	641	x	0	0	Yes	Yes	32	0	32	0	0	0	0	0	0	0	0	0	0
PSLR1231	PLHP 2	DfT	Redhill, Site C	Market Field Road, Redhill Surrey	RH1	Reigate and Banstead	South East	2017/2018	50	Development started	17/02876/F	11/12/2017	18/05/2018	Mixed	Yes	50	01/09/2018	0	0	Yes	Yes	0	0	0	0	7	0	0	0	0	0	0	0	0
PSLR1232	PLHP 2	DfT	Wembley High Road (Fairgate Car park plus)		HA9 6AS	Brent	London	2017/2018	178	Planning stage	18/3111	06/08/2018	x	Mixed	Yes	256	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1233	PLHP 2	DHSC	Ambulance Station, Horncastle	Horncastle Ambulance Station, Mareham Road, Horncastle	LN9 6PH	East Lindsey	East Midlands	2017/2018	1	Development completed	S/086/00079/18	15/01/2018	09/03/2018	Residential	No	1	30/10/2018	0	1	Yes	No	0	0	0	0	0	0	0	1	0	0	0	1	0
PSLR1234	PLHP 2	DHSC	Queens Hospital - Outwood Site Margaret Stanhope building	Belvedere Rd, Burton-on-Trent	DE13 0RB	East Staffordshire	West Midlands	2017/2018	45	Development started	P/2017/01579	13/12/2017	05/01/2018	Residential institute	Unknown	45	29/10/2019	3	0	No	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1235	PLHP 2	DHSC	St Ann's Hospital	St Ann's Hospital St Ann's Road London	N15 3TH	Haringey	London	2017/2018	470	Development started	HGY/2014/1691	20/06/2014	10/07/2015	Mixed	No	463	25/09/2017	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1236	PLHP 2	DHSC	The Elms	The Elms 50 Cowley Hill Lane	WA10 2AW	St Helens	North West	2017/2018	6	Planning stage	P/2017/0795/FUL	06/10/2017	04/12/2017	Residential	Yes	6	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1237	PLHP 2	DHSC	15-16 Daisybank & Garage	Quernmore Road, Lancaster	LA1 3JW	Lancaster	North West	2017/2018	1	Development completed	18/00050/FUL	16/01/2018	01/03/2018	Residential	No	2	19/03/2012	0	2	Yes	No	0	0	0	0	0	1	0	1	0	2	0	0	0
PSLR1238	PLHP 2	DHSC	Alma Street	2-4 Frederick Street, Stockon on Tees	TS18 2BF	Stockton-on-Tees	North East	2017/2018	34	Planning stage	17/2772/FUL	08/11/2017	23/02/2018	Residential	No	34	x	0	0	Yes	Yes	0	0	0	0	34	0	0	0	0	0	0	0	0
PSLR1239	PLHP 2	DHSC	Bromley North Clinic	23 Station Road, Bormley, Kent	BR1 3LP	Bromley	London	2017/2018	9	Planning stage	16/02770/OUT	09/06/2016	18/08/2016	Residential	No	9	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1240	PLHP 2	DHSC	Clitheroe Community Hospital	Chatburn Road Clitheroe	BB7 4JX	Ribble Valley	North West	2017/2018	60	Development started	3/2017/0616	03/07/2017	09/02/2018	Residential	No	60	16/10/2018	3	53	Yes	Yes	0	0	0	0	15	47	0	6	20	22	11	0	0
PSLR1241	PLHP 2	DHSC	Collingwood Road	Witham, Essex	CM8 2TT	Braintree	East	2017/2018	98	Development completed	17/02315/COUPA	22/12/2017	16/02/2018	Residential	No	98	18/07/2019	0	98	Yes	Unknown	0	0	0	0	0	95	1	2	0	0	0	98	0
PSLR1242	PLHP 2	DHSC	Colne Health Centre	Colne		Pendle	North West	2017/2018	11	Planning stage	17/0589/FUL	06/10/2017	12/03/2018	Mixed	No	11	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1243	PLHP 2	DHSC	Cowley Hill Lane Site	WA10 2AP	WA10 2AP	St Helens	North West	2018/2019	75	Planning stage	P/2018/0535/FUL	30/07/2018	29/11/2018	Residential	No	75	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1244	PLHP 2	DHSC	Gravesham Community Hospital	Bath Street, Gravesend		Gravesham	South East	2017/2018	80	Planning stage	20160670	01/07/2016	18/01/2018	Residential	No	80	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1245	PLHP 2	DHSC	Guisborough General Hospital - Challoner Building	Guisborough	TS14 6DD	Redcar and Cleveland	North East	2017/2018	14	Development completed	R/2017/0353/FFM	24/05/2017	25/10/2017	Mixed	Yes	14	20/10/2018	0	14	Yes	No	0	0	0	0	0	0	0	14	0	0	0	14	0
PSLR1246	PLHP 2	DHSC	Southwold Hospital	Fieldstile Road, Southwold	IP18 6LD	Waveney	East	2017/2018	9	Planning stage	DC/17/3564/FUL	17/08/2017	04/01/2018	Mixed	No	9	x	0	0	Yes	Yes	0	4	0	0	0	0	0	0	0	0	0	0	0
PSLR1247	PLHP 2	DHSC	St Andrews Counselling & Psychotherapy Unit	59 Huntington Road, York	YO31 8RL	York	Yorkshire and The Humber	2017/2018	1	Development completed	18/00206/FUL	31/01/2018	25/04/2018	Residential	No	1	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	0	0	1	0	0
PSLR1248	PLHP 2	DHSC	St Georges Hospital	117 Suttons Lane, Hornchurch, Essex	RM12 6RS	Havering	London	2017/2018	290	Development started	P0321.15	09/03/2015	13/07/2017	Residential	No	290	x	160	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1249	PLHP 2	Homes England	Northstowe Phase 2		CB24 3DE	South Cambridgeshire	East	2017/2018	3500	Development started	S/2011/14/OL	29/08/2014	09/01/2017	Mixed	No	3500	28/10/2019	0	0	Yes	Yes	0	350	0	0	1400	0	0	0	0	0	0	0	0
PSLR1250	PLHP 2	Homes England	Parcel 1 Main Site & Brackmills Wood	Land To The East Of Hardingstone North Of Newport Pagnell Road, Northampton	NN4 7BW	Northampton	East Midlands	2017/2018	750	Development started	N/2013/0338	12/12/2013	15/05/2014	Mixed	Yes	1000	11/11/2019	0	0	No	Yes	69	0	29	0	0	0	0	0	0	0	0	0	0
PSLR1251	PLHP 2	Homes England	Phase 1 development land	Land For Redevelopment Ransome Road, Northampton, Northamptonshire	NN4 8AA	Northampton	East Midlands	2017/2018	515	Planning stage	x	x	x	x	Yes	x	x	x	x	Not applicable	Not applicable	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1252	PLHP 2	Homes England	Phase 2 Carr Lodge		DN4 8TU	Doncaster	Yorkshire and The Humber	2017/2018	466	Development started	18/02284/FULM	12/09/2018	01/08/2019	Residential	No	460	06/12/2019	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1253	PLHP 2	Homes England	Cobbs Clough / Whalleys 2		L40 6JH	West Lancashire	North West	2017/2018	299	Development started	2013/1060/WL3	27/09/2013	28/08/2014	Residential	Yes	630	x	0	0	Yes	Yes	0	151	38	0	0	0	0	0	0	0	0	0	0
PSLR1254	PLHP 2	Homes England	Land At Eldon Whins		DL5 7JL	County Durham	North East	2017/2018	256	Planning stage	DM/18/01810/RM	17/07/2018	19/10/2018	Residential	Yes	240	x	0	0	No	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1255	PLHP 2	Homes England	A435 Redditch		B80 7BT	Stratford-on-Avon	West Midlands	2017/2018	205	Planning stage	x	x	x	x	Not applicable	x	x	x	x	Not applicable	Not applicable	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1256	PLHP 2	Homes England	Brookvale Phase 1B		NG20 8AT	Bolsover	East Midlands	2017/2018	200	Development started	18/00304/REM	01/06/2018	23/10/2018	Residential	No	200	27/01/2020	5	0	No	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1257	PLHP 2	Homes England	Land At Leyland House Farm / Altcar Lane		PR25 1LE	South Ribble	North West	2017/2018	200	Development started	07/2018/3247/REM	17/05/2018	06/09/2018	Residential	Yes	200	16/12/2019	24	4	Yes	Unknown	0	0	0	0	0	0	0	4	4	0	0	0	0
PSLR1258	PLHP 2	Homes England	Pewterspear Green 13		WA4 5GH	Warrington	North West	2017/2018	180	Development started	2018/32672	24/04/2018	12/10/2018	Residential	No	180	30/05/2019	4	80	Yes	Yes	0	27	27	0	0	42	0	38	45	25	10	0	0
PSLR1259	PLHP 2	Homes England	Graylingwell NHS_21		PO19 6GS	Chichester	South East	2017/2018	160	Development started	17/02571/REM	31/08/2017	26/01/2018	Residential	No	160	03/06/2019	59	33	Yes	Unknown	0	0	0	0	0	1	1	31	14	7	0	12	0
PSLR1260	PLHP 2	Homes England	Sedgeletch Industrial Estate (ONS_15)		DH4 6JN	Sunderland	North East	2017/2018	138	Planning stage	19/00963/FUL	04/06/2019	30/10/2019	Residential	No	138	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1261	PLHP 2	Homes England	Whalleys 5, Lucas Cottage		WN8 7SE	West Lancashire	North West	2017/2018	129	Development started	2013/1060/WL3	27/09/2013	28/08/2014	Residential	Yes	630	09/01/2020	5	3	Yes	Yes	0	151	38	0	0	0	0	3	2	1	0	0	0
PSLR1262	PLHP 2	Homes England	Maynes Site, Pool		TR15 3QT	Cornwall	South West	2017/2018	100	Planning stage	PA18/07631	03/09/2018	x	Residential	No	99	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1263	PLHP 2	Homes England	Events Car Park, Public Open Space		TS17 6PY	Stockton-on-Tees	North East	2017/2018	96	Planning stage	16/1603/OUT	20/06/2016	20/10/2017	Residential	No	150	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1264	PLHP 2	Homes England	Former Coop Building		DA1 1BP	Dartford	South East	2017/2018	92	Planning stage	x	x	x	x	Yes	x	x	x	x	Not applicable	Not applicable	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1265	PLHP 2	Homes England	Site N3 Eaves Green		PR7 3QA	Chorley	North West	2017/2018	88	Development started	16/00805/FULMAJ	26/08/2016	18/01/2018	Residential	Yes	88	31/07/2018	10	55	Yes	Yes	0	13	0	0	0	36	0	19	20	29	6	0	0
PSLR1266	PLHP 2	Homes England	Officers Mess within Connaught Barracks, Dover		CT15 5LZ	Dover	South East	2017/2018	64	Planning stage	18/00981	12/09/2018	18/04/2019	Residential	Yes	64	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1267	PLHP 2	Homes England	Hanford site disposal		ST4 8QT	Stoke-on-Trent	West Midlands	2017/2018	45	Development started	62680/FUL	14/06/2018	15/05/2019	Residential	No	13	16/01/2020	0	0	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1268	PLHP 2	Homes England	Former Site of Altbridge Park		L11 9BR	Liverpool	North West	2017/2018	120	Planning stage	x	x	x	x	Not applicable	x	x	x	x	Not applicable	Not applicable	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1269	PLHP 2	Homes England	Camrex House, Sunderland		SR1 2AQ	Sunderland	North East	2017/2018	50	Development started	18/00825/FUL	11/05/2018	01/11/2018	Residential	No	50	29/10/2014	0	1	Yes	Unknown	0	0	0	0	0	0	0	1	0	0	0	0	1
PSLR1270	PLHP 2	Homes England	Phase 5b, Dolcoath		TR14 8FP	Cornwall	South West	2017/2018	42	Planning stage	PA17/09966	02/11/2017	20/12/2018	Residential	No	42	x	0	0	Yes	Yes	0	8	3	0	0	0	0	0	0	0	0	0	0
PSLR1271	PLHP 2	Homes England	Cross Keys House (8104)		L2 2BL	Liverpool	North West	2017/2018	37	Planning stage	x	x	x	x	Not applicable	x	x	x	x	Not applicable	Not applicable	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1272	PLHP 2	Homes England	Land Snedshill/Church Road		TF2 9HF	Telford and Wrekin	West Midlands	2017/2018	39	Development started	TWC/2017/0714	22/09/2017	12/03/2018	Residential	No	39	20/12/2018	0	39	Yes	Yes	0	0	0	0	6	38	0	1	8	28	3	0	0
PSLR1273	PLHP 2	Homes England	Land At Blackstock Street Liverpool		L3 6JH	Liverpool	North West	2017/2018	97	Planning stage	18F/2910	08/11/2018	24/07/2019	Residential	No	97	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1274	PLHP 2	Homes England	Whitehouse Farm		WA2 0SU	Warrington	North West	2017/2018	18	Planning stage	x	x	x	x	Not applicable	x	x	x	x	Not applicable	Not applicable	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1275	PLHP 2	Homes England	1118 Hudson Road, Sunderland		SR1 2AQ	Sunderland	North East	2017/2018	16	Planning stage	x	x	x	x	Yes	x	x	x	x	Not applicable	Not applicable	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1276	PLHP 2	Homes England	Cuerden Regional Investment Site		tbc	South Ribble	North West	2017/2018	105	Planning stage	07/2017/0211/ORM	27/01/2017	20/12/2017	Mixed	Not applicable	210	x	0	0	No	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1277	PLHP 2	Homes England	Mowden Hall, Cockerton		DL3 9BG	Darlington	North East	2017/2018	30	Planning stage	18/00989/FUL	23/10/2018	28/03/2019	Residential	No	30	x	0	0	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1278	PLHP 2	Homes England	Lancaster Farms, Land		LA1 3QZ	Lancaster	North West	2017/2018	14	Planning stage	x	x	x	x	Not applicable	x	x	x	x	Not applicable	Not applicable	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1279	PLHP 2	Homes England	OLDHAM MAGISTRATES' COURT		OL1 1QE	Oldham	North West	2017/2018	100	Planning stage	x	x	x	x	Not applicable	x	x	x	x	Not applicable	Not applicable	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1280	PLHP 2	MoD	SFA New Build 17/18 Q417/18		Various locations	x	x	2017/2018	7	Development completed	x	x	x	Residential sale	Not applicable	7	x	x	7	Not applicable	Not applicable	0	0	0	0	0	x	x	7	x	x	x	x	7
PSLR1281	PLHP 2	MoD	SLA New Build Q41718		Various locations	x	x	2017/2018	91	Development completed	x	x	x	Residential sale	Not applicable	91	x	x	91	Not applicable	Not applicable	0	0	0	0	0	x	x	91	x	x	x	x	91
PSLR1282	PLHP 2	MoJ	Chester Le Street, Oakdale Terrace	Oakdale House, Oakdale Terrace, Chester Le Street, County Durham	DH3 3DH	County Durham	North East	2017/2018	2	Development started	DM/17/03039/PNC	13/09/2017	20/10/2017	Residential	No	2	11/01/2018	0	1	Yes	No	0	0	0	0	0	1	0	0	0	0	0	0	1
PSLR1283	PLHP 2	MoJ	Wigston, Station Road	26-28 Station Road, Wigston, Leicestershire	LE18 2DH	Oadby and Wigston	East Midlands	2017/2018	6	Development completed	17/00360/FUL	24/07/2017	17/11/2017	Residential	No	6	17/09/2018	0	7	Yes	No	0	0	0	0	0	4	0	3	0	0	1	6	0
PSLR1284	PLHP 1	Homes England	Land at Seacroft Hospital	Land at Seacroft Hospital, York Roads, Leeds	LS14 6UH	Leeds	Yorkshire and The Humber	2014/2015	500	Development started	15/07300/FU	07/12/2015	22/08/2016	Residential	No	503	23/11/2017	30	220	Yes	Yes	30	45	0	0	0	167	8	45	20	168	1	4	27
PSLR1285	PLHP 2	DfT	Queen Mary and Westfield College, Mile End	Mile End	E1 4DR	Tower Hamlets	London	2018/2019	120	Development started	PA/10/01458	07/07/2010	26/03/2013	Residential institute	No	412	19/12/2019	0	126	Yes	No	0	0	0	0	0	0	0	126	0	0	0	0	126
PSLR1286	PLHP 2	DfT	Twickenham, Whitton Road	TW2 7BA	TW2 7BA	Richmond upon Thames	London	2018/2019	6	Development started	11/1443/FUL	06/05/2011	30/03/2012	Mixed	No	115	03/02/2020	9	0	Yes	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1287	PLHP 2	DHSC	Agricultural land to the south side of Castle Hill Hospital	HU16 5JF	HU16 5JF	East Riding of Yorkshire	Yorkshire and The Humber	2018/2019	180	Development started	17/02757/STREM	10/08/2017	01/06/2018	Residential	Yes	180	26/02/2019	24	53	Yes	Mix of pay and houses	15	16	14	0	31	36	0	17	32	7	14	0	0
PSLR1288	PLHP 2	DHSC	David Pitt House	24-28 Norwood High Street , London	SE27 9NR	Lambeth	London	2018/2019	15	Planning stage	17/03688/P3O	26/07/2017	10/10/2017	Residential	No	15	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1289	PLHP 2	DHSC	Former Barnard Castle Ambulance Station	Victoria Road, Barnard Castle	DL12 8HW	County Durham	North East	2018/2019	3	Development started	DM/18/00435/FPA	09/02/2018	06/04/2018	Residential	No	3	29/08/2019	0	3	Yes	No	0	0	0	0	0	3	0	0	0	0	3	0	0
PSLR1291	PLHP 2	DHSC	Heanor Health Centre	Heanor Health Centre, Wilmot Street	DE75 7EZ	Amber Valley	East Midlands	2018/2019	6	Development started	AVA/2018/0658	06/07/2018	23/08/2018	Residential	No	6	29/08/2019	0	3	Yes	No	0	0	0	0	0	1	0	2	1	2	0	0	0
PSLR1292	PLHP 2	DHSC	Land at Halton	Warwick	CV35 7JW	Warwick	West Midlands	2018/2019	2	Development completed	W/17/0265	15/02/2017	12/07/2017	Residential	No	2	28/02/2019	0	2	Yes	No	0	0	0	0	0	0	0	2	2	0	0	0	0
PSLR1293	PLHP 2	DHSC	Laudon House	17 East Gate, Sleaford	NG34 7DW	North Kesteven	East Midlands	2018/2019	10	Development completed	17/1008/FUL	20/07/2017	17/11/2017	Residential	No	10	24/04/2018	0	10	Yes	No	0	0	0	0	0	2	8	0	0	0	0	10	0
PSLR1294	PLHP 2	DHSC	Midhurst Ambulance Station	Bepton Road, Midhurst, West Sussex	GU29 9HQ	Chichester	South East	2018/2019	4	Planning stage	SDNP/17/04026/FUL	07/08/2017	04/09/2017	Residential	No	4	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1295	PLHP 2	DHSC	Pullborough Ambulance Station	Moat Lane, Pulborough, West Sussex	RH20 2AP	Horsham	South East	2018/2019	3	Planning stage	DC/17/2125	20/09/2017	05/01/2018	Residential	No	3	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1296	PLHP 2	DHSC	Orchard House	Sleaford	NG34 8PP	North Kesteven	East Midlands	2018/2019	40	Planning stage	17/0880/FUL	26/06/2017	15/06/2018	Residential	No	40	x	0	0	Yes	Yes	0	0	0	0	8	0	0	0	0	0	0	0	0
PSLR1297	PLHP 2	DHSC	Westbury Community Hospital - Part A	Westbury	BA13 3EL	Wiltshire	South West	2018/2019	58	Development started	17/12513/REM	27/12/2017	01/05/2018	Residential	No	56	21/11/2019	5	8	Yes	Yes	4	0	3	0	0	0	0	8	0	1	7	0	0
PSLR1298	PLHP 2	Homes England	Land at Ingersley Vale, Bollington	Bollington	SK10 5BP	Cheshire East	North West	2018/2019	66	Planning stage	08/0791P	30/04/2008	30/12/2009	Residential	No	66	x	0	0	Yes	Yes	0	0	0	0	15	0	0	0	0	0	0	0	0
PSLR1299	PLHP 2	Homes England	Residential Land	GU341UF	GU341UF	East Hampshire	South East	2018/2019	280	Planning stage	30021/066	13/07/2018	02/07/2019	Residential	No	280	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1300	PLHP 2	Homes England	Trafford Magistrates Court and Altrincham County Court	M33 7NR	M33 7NR	Trafford	North West	2018/2019	35	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1301	PLHP 2	Homes England	Wealstun Phase 1	LS237AZ	LS237AZ	Leeds	Yorkshire and The Humber	2018/2019	23	Planning stage	18/07278/FU	21/11/2018	06/09/2019	Residential	No	26	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1302a	PLHP 2	MoD	Copthorne Barracks, Shrewsbury	Copthorne Road	SY3 8LZ	Shropshire	West Midlands	2018/2019	236	Development started	19/01288/REM	01/04/2019	14/06/2019	Residential	No	150	x	12	0	No	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1302b	PLHP 2	MoD	Copthorne Barracks, Shrewsbury	Copthorne Road	SY3 8LZ	Shropshire	West Midlands	2018/2019	236†	Development started	18/03637/REM	23/08/2018	21/12/2018	Residential	No	66	21/02/2012	30	38	No	No	0	0	0	0	0	19	1	18	0	4	31	0	3
PSLR1303	PLHP 2	MoD	SFA New Build 18/19 - Q1	Various locations		x	x	2018/2019	24	Development completed	x	x	x	Residential sale	Unknown	24	x	x	24	Not applicable	Unknown	0	0	0	0	0	x	x	24	x	x	x	x	24
PSLR1304	PLHP 2	MoD	SLA New Build 18/19 - Q1	Various locations		x	x	2018/2019	64	Development completed	x	x	x	Residential sale	Unknown	64	x	x	64	Not applicable	Unknown	0	0	0	0	0	x	x	64	x	x	x	x	64
PSLR1305	PLHP 2	MoJ	Hinckley, Station Road	35 Station Road, Hinckley, Leicestershire	LE10 1AP	Hinckley and Bosworth	East Midlands	2018/2019	1	Development completed	18/01239/FUL	06/12/2018	30/01/2019	Residential	No	1	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	0	1	0	0	0
PSLR1306	PLHP 2	MoJ	Newark, Probation Office, Apppleton Gate	Probation Office, 11 Appleton Gate, Newark, Nottinghamshire	NG24 1JR	Newark and Sherwood	East Midlands	2018/2019	5	Planning stage	17/01799/FUL	05/10/2017	10/04/2018	Residential	No	5	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1307	PLHP 2	DfT	Oxford South End Yard	Osney Lane, Oxford	OX1 1TB	Oxford	South East	2018/2019	188	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1308	PLHP 2	DfT	White Post Street	White Post Street, Lewisham, London	SE15 1DR	Lewisham	London	2018/2019	15	Planning stage	DC/17/104772	29/11/2017	05/12/2018	Mixed	Yes	25	x	0	0	No	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1309	PLHP 2	DHSC	BELVEDERE HOUSE	341 Harlesden Road, London	NW10 3RX	Brent	London	2018/2019	9	Planning stage	18/1683	03/05/2018	20/07/2018	Residential	No	9	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1310	PLHP 2	DHSC	Carbis Bay Ambulance Station	Trewartha Estate St Ives	TR26 2TQ	Cornwall	South West	2018/2019	8	Planning stage	PA17/10334	16/01/2018	17/07/2018	Residential	No	8	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1311	PLHP 2	DHSC	Chaddeslode House	130-131 Abbey Foregate, Shrewsbury, Shropshire	SY2 6AX	Shropshire	West Midlands	2018/2019	10	Development started	18/01820/FUL	18/04/2018	30/07/2018	Residential	No	10	13/12/2019	3	6	Yes	No	0	0	0	0	0	1	0	5	1	2	2	1	0
PSLR1312	PLHP 2	DHSC	Garforth Clinic	Garforth Clinic, Lidgett Lane, Garforth, Leeds	LS25 1LJ	Leeds	Yorkshire and The Humber	2018/2019	6	Planning stage	18/00690/FU	12/03/2018	28/09/2018	Residential	No	6	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1313	PLHP 2	DHSC	Hydrotherapy Pool (ex)	Hydrotherapy Pool Balderton Newark	NG24 3JR	Newark and Sherwood	East Midlands	2018/2019	3	Development started	18/00953/FUL	17/05/2018	27/07/2018	Residential	No	3	11/04/2019	0	3	Yes	No	0	0	0	0	0	0	0	3	3	0	0	0	0
PSLR1314	PLHP 2	DHSC	Keresforth - former PCT estate	Keresforth Close, Barnsley	S70 6RS	Barnsley	Yorkshire and The Humber	2018/2019	1	Development completed	2018/0969	27/07/2018	08/08/2018	Residential	No	12	21/02/2012	0	12	Yes	No	0	0	0	0	0	12	0	0	0	8	4	0	0
PSLR1315	PLHP 2	DHSC	Romsey Road	59, 61, 63 Romsey Road Winchester	SO22 5DE	Winchester	South East	2018/2019	10	Planning stage	17/02899/OUT	10/11/2017	21/09/2018	Residential	No	10	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1316	PLHP 2	DHSC	SOUTH PLACE ADJACENT LAND (South Place Day Centre)	SOUTH PLACE DAY CENTRE, SOUTH PLACE, SURBITON, SURREY	KT5 8RX	Kingston upon Thames	London	2018/2019	49	Planning stage	18/16123	12/02/2018	28/09/2018	Residential	No	49	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1317	PLHP 2	DHSC	Standish Ambulance Station Phase 2	Glebe Close, Standish, Wigan	WN6 0DD	Wigan	North West	2018/2019	9	Planning stage	A/19/87000/RM	05/04/2019	x	Residential	No	9	x	x	x	Yes	Yes	0	0	9	0	0	x	x	x	x	x	x	x	x
PSLR1318	PLHP 2	DHSC	Whitehawk Clinic	Whitehawk Clinic, Whitehawk Way, Brighton	BN2 5NP	Brighton and Hove	South East	2018/2019	38	Planning stage	BH2017/01665	16/05/2017	01/08/2018	Residential	No	38	x	0	0	Yes	Yes	8	0	7	0	0	0	0	0	0	0	0	0	0
PSLR1319	PLHP 2	DHSC	Cockermouth Cottage Hospital	Isel Road, Cockermouth	CA13 9HT	Allerdale	North West	2018/2019	40	Planning stage	2/2017/0579	13/12/2017	31/07/2018	Residential	No	40	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1320	PLHP 2	Homes England	Land adj Horton Farm, Horton Lane (Plot B)	TF6 6DT	TF6 6DT	Telford and Wrekin	West Midlands	2018/2019	3	Planning stage	TWC/2017/0302	30/03/2017	13/06/2017	Residential	No	3	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1321	PLHP 2	Homes England	Site 3.2 Sandymoor (Local Cent	WA7 1XJ	WA7 1XJ	Halton	North West	2018/2019	21	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1322	PLHP 2	Homes England	BURY AND ROCHDALE MAGISTRATES' COURT	BL9 0HX	BL9 0HX	Bury	North West	2018/2019	37	Planning stage	64093	18/04/2019	x	Residential	No	49	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1323	PLHP 2	MoD	ANNINGTON HOMES SFA - VARIOUS LOCATIONS (SCORE IN Q2 FY18/19)	SFA Releases at various locations		x	x	2018/2019	72	Development completed	x	x	x	Residential sale	Unknown	72	x	x	72	Not applicable	Unknown	0	0	0	0	0	x	x	72	x	x	x	x	72
PSLR1324	PLHP 2	MoD	ANNINGTON HOMES SFA - VARIOUS LOCATIONS 18/19	SFA Releases at various locations		x	x	2018/2019	236	Development completed	x	x	x	Residential sale	Unknown	236	x	x	236	Not applicable	Unknown	0	0	0	0	0	x	x	236	x	x	x	x	236
PSLR1325	PLHP 2	MoD	SLA NEW BUILD 1819 - Q2	Tidworth & Bulford	SP9 7AB	x	x	2018/2019	40	Development completed	x	x	x	Residential sale	Unknown	40	x	x	40	Not applicable	Unknown	0	0	0	0	0	x	x	40	x	x	x	x	40
PSLR1326	PLHP 2	MoJ	Rhodes Centre, OLDHAM	64 Bridge Street Oldham	OL1 1ED	Oldham	North West	2018/2019	8	Planning stage	PA/340648/17	16/08/2017	16/01/2018	Residential	No	8	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1327	PLHP 2	DfT	Wakefield Belle Vue	WF1 5DA	WF1 5DA	Wakefield	Yorkshire and The Humber	2018/2019	170	Planning stage	19/01136/FUL	09/05/2019	x	Residential	No	135	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1328	PLHP 2	DHSC	37 COVERTON ROAD	SW17 0QP	SW17 0QP	Wandsworth	London	2018/2019	8	Development started	2014/2617	12/05/2014	18/07/2014	Residential	No	8	17/11/2015	0	7	Yes	No	0	0	0	0	0	5	2	0	0	0	5	2	0
PSLR1329	PLHP 2	DHSC	Battle Hospital	Portman Road	RG30 1AH	Reading	South East	2018/2019	211	Planning stage	180319	19/02/2018	29/10/2018	Residential	No	211	x	0	0	Yes	Yes	11	14	25	0	0	0	0	0	0	0	0	0	0
PSLR1330	PLHP 2	DHSC	Essex County Hospital	CO3 3NB	CO3 3NB	Colchester	East	2018/2019	108	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1331	PLHP 2	DHSC	Ridge Lea Hospital	LA1 3JT	LA1 3JT	Lancaster	North West	2018/2019	70	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1333	PLHP 2	DHSC	Land lying to the South of Haygate Road, Telford, TR1 2BJ	Telford	TR1 2BJ	Telford and Wrekin	West Midlands	2018/2019	23	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1334	PLHP 2	DHSC	Leafield House	109 King Lane Moortown, Leeds	LS17 5BP	Leeds	Yorkshire and The Humber	2018/2019	12	Planning stage	19/04781/FU	04/09/2019	x	Commercial	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1335	PLHP 2	DHSC	Newton Clinic	WA12 9TX	WA12 9TX	St Helens	North West	2018/2019	16	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1336	PLHP 2	DHSC	Old Newton Community Hospital	WA12 8RB	WA12 8RB	St Helens	North West	2018/2019	24	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1337	PLHP 2	DHSC	Teams Family Centre	NE8 2PN	NE8 2PN	Gateshead	North East	2018/2019	4	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1338	PLHP 2	DHSC	Twig Lane Clinic	L36 2LE	L36 2LE	Knowsley	North West	2018/2019	12	Planning stage	18/00413/FUL	26/07/2018	07/10/2019	Commercial	No	0	x	x	x	Yes	Not applicable	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1339	PLHP 2	DHSC	Wotton Under Edge Clinic	GL12 7DN	GL12 7DN	Stroud	South West	2018/2019	3	Planning stage	17/1339/FUL	13/06/2017	07/09/2017	Residential	No	3	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1340	PLHP 2	DHSC	1HA Parcel - GLS			Basildon	East	2018/2019	33	Development started	17/01450/FULL	06/10/2017	21/01/2019	Residential	Yes	33	06/08/2019	0	0	Yes	Yes	6	0	5	0	0	0	0	0	0	0	0	0	0
PSLR1341	PLHP 2	Homes England	Centenary Quay - Phase 5	SO19 9SS	SO19 9SS	Southampton	South East	2018/2019	103	Development started	17/02514/REM	11/12/2017	13/03/2018	Residential	No	103	17/06/2019	0	16	No	Yes	0	0	46	0	0	15	0	1	0	1	15	0	0
PSLR1342	PLHP 2	Homes England	Land off Ladybank Avenue	PR2 9LY	PR2 9LY	Preston	North West	2018/2019	42	Planning stage	06/2019/0135	07/02/2019	28/06/2019	Residential	No	34	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1344	PLHP 2	Homes England	Pound Lane (Plot 11) Custom Build	SS15 5SZ	SS15 5SZ	Basildon	East	2018/2019	12	Planning stage	19/00643/REM	24/04/2019	15/10/2019	Residential	No	12	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1347	PLHP 2	Homes England	Meacham Day Centre	MK12 5LX	MK12 5LX	Milton Keynes	South East	2018/2019	6	Planning stage	19/01150/REM	01/05/2019	26/06/2019	Residential	No	6	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1348	PLHP 2	MoD	SFA NEW BUILD 18/19 - Q3			x	x	2018/2019	17	Development completed	x	x	x	Residential sale	Unknown	17	x	x	17	Not applicable	Unknown	0	0	0	0	0	x	x	17	x	x	x	x	17
PSLR1349	PLHP 2	MoD	SLA NEW BUILD 1819 - Q3			x	x	2018/2019	59	Development completed	x	x	x	Residential sale	Unknown	59	x	x	59	Not applicable	Unknown	0	0	0	0	0	x	x	59	x	x	x	x	59
PSLR1350	PLHP 2	DfT	Horwich, Red Moss	LAND AT FORMER HORWICH LOCO WORKS, HORWICH, BOLTON	BL6 5UE	Bolton	North West	2018/2019	400	Development started	91352/14	20/01/2014	14/09/2015	Mixed	Yes	1700	x	0	0	Not applicable	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1351	PLHP 2	DfT	Land to the rear of Kew Bridge Station Building.	Land to the rear of Kew Bridge Station, London Borough of Brentford	TW8 0EW	Hounslow	London	2018/2019	30	Planning stage	00657/D/P17	21/03/2017	20/12/2018	Residential	No	30	x	0	0	Not applicable	Yes	0	0	14	0	0	0	0	0	0	0	0	0	0
PSLR1352	PLHP 2	DfT	LAND AT PANT RAILWAY STATION, OSWESTRY, SHROPSHIRE COUNTY	LAND AT PANT RAILWAY STATION, OSWESTRY, SHROPSHIRE COUNTY	SY10 8JY	Shropshire	West Midlands	2018/2019	2	Planning stage	19/02166/OUT	20/05/2019	07/11/2019	Residential	No	3	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1353	PLHP 2	MoJ	HMP Holloway	Parkhurst Rd, London	N7 0NU	Islington	London	2018/2019	1000	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1354	PLHP 2	MoD	NORFOLK VOLUNTEER ESTATE-GREAT YARMOUTH ACF	80A Southtown Road	NR31 6PB	Great Yarmouth	East	2018/2019	1	Development completed	x	x	x	Residential sale	Unknown	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR1355	PLHP 2	MoD	CATTERICK TRAINING AREA-WOOD HOUSE FARM	Woodhouse Farm	DL11 6DF	Richmondshire	Yorkshire and The Humber	2018/2019	1	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1356	PLHP 2	MoD	WARCOP ARMY FIELD TRAINING CENTRE-STREET HOUSE FARM	Street House Farmhouse	CA16 6PA	Eden	North West	2018/2019	1	Development completed	x	x	x	Residential sale	Unknown	1	x	x	1	Not applicable	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR1357	PLHP 2	MoD	ANNINGTON HOMES SFA - VARIOUS LOCATIONS 18/19 Q4	SFA Releases at various locations		x	x	2018/2019	5	Development completed	x	x	x	Residential sale	Unknown	5	x	x	5	Not applicable	Unknown	0	0	0	0	0	x	x	5	x	x	x	x	5
PSLR1358	PLHP 2	MoD	ANNINGTON HOMES SFA - 2 YEAR SUB-LETS AT VARIOUS LOCATIONS (SCORE BY Q4 FY18/19)	SFA Releases at various locations		x	x	2018/2019	7	Development completed	x	x	x	Residential sale	Unknown	7	x	x	7	Not applicable	Unknown	0	0	0	0	0	x	x	7	x	x	x	x	7
PSLR1359	PLHP 2	DHSC	Welland Hospital Site A and C	Welland Hospital Site Roman Bank, Spalding, Lincolnshire	PE11 2HN	South Holland	East Midlands	2018/2019	36	Planning stage	H16-0853-17	11/09/2017	15/01/2019	Residential	No	36	x	0	0	Yes	Yes	0	0	36	0	0	0	0	0	0	0	0	0	0
PSLR1360	PLHP 2	DHSC	St Peters Hospital	Guildford Rd Chertsey Surrey	KT16 0PZ	Runnymede	South East	2018/2019	472	Development started	RU.17/1815	09/11/2017	07/02/2019	Mixed	No	475	02/05/2019	0	0	Yes	Yes	0	0	0	0	144	0	0	0	0	0	0	0	0
PSLR1361	PLHP 2	DHSC	Phase 2 Maidstone nurses home / trees properties	Hermitage Lane Maidstone	ME16 9NN	Maidstone	South East	2018/2019	22	Planning stage	15/502970/OUT	01/04/2015	28/09/2018	Residential	No	57	x	0	0	Yes	Yes	12	0	5	0	0	0	0	0	0	0	0	0	0
PSLR1362	PLHP 2	DfT	Hither Green, land at Nightingale Grove	Nightingale Grove	SE13 6HE	Lewisham	London	2018/2019	29	Planning stage	DC/18/110288	24/12/2018	x	Residential	No	30	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1363	PLHP 2	DHSC	36 Maplestead Road	36 Maplestead Road, Dagenham	RM9 4XR	Barking and Dagenham	London	2018/2019	3	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1364	PLHP 2	DHSC	Ashford Hospital Land	Site of former Ashford Hospital N H S Trust land between 3 and 23, Chart Road, Ashford, Kent	TN23 3HY	Ashford	South East	2018/2019	32	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1365	PLHP 2	DHSC	Baildon Clinic	Cliffe Avenue, Baildon, Shipley	BD17 6NX	Bradford	Yorkshire and The Humber	2018/2019	3	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1366	PLHP 2	DHSC	Crow Wood - Land	Land east of Crow Wood Lane, Widnes, Cheshire	WA8 3LZ	Halton	North West	2018/2019	8	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1367	PLHP 2	DHSC	Greenhithe Clinic	Knockhall Chase, Greenhithe	DA9 9EN	Dartford	South East	2018/2019	5	Planning stage	19/00657/REM	08/05/2019	13/09/2019	Residential	No	5	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1368	PLHP 2	DHSC	Madeira Grove Health Centre	Woodford Green, Essex	IG8 7QH	Redbridge	London	2018/2019	8	Planning stage	2355/19	01/06/2019	x	Residential	No	9	x	x	x	Yes	No	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1369	PLHP 2	DHSC	Monkwick Clinic	Health Service Clinic, Monkwick Health Service Clinic, Queen Elizabeth Way, Colchester	CO2 8LT	Colchester	East	2018/2019	10	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1370	PLHP 2	DHSC	Poulton Road Offices	90-92 Poulton Road, Southport	PR9 7BW	Wyre	North West	2018/2019	1	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1371	PLHP 2	DHSC	Shaftesbury House	Leeds	LS9 6NG	Leeds	Yorkshire and The Humber	2018/2019	15	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1372	PLHP 2	DHSC	Site for West Newcastle PCC (West One)	Caroline Street, Elswick, Newcastle upon Tyne	NE4 7TJ	Newcastle upon Tyne	North East	2018/2019	82	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1373	PLHP 2	DHSC	Wrotham Road Clinic	90 c Wrotham Road, Gravesend	DA11 0PQ	Gravesham	South East	2018/2019	9	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1374	PLHP 2	Homes England	Nottingham Road	Nottingham Road, Ashby-de-la-Zouch, Leicestershire	LE65 1JP	North West Leicestershire	East Midlands	2018/2019	12	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1375	PLHP 2	Homes England	Luddington - Stratford VIC	Veterinary Investigation Centre Luddington Stratford-upon-Avon	CV37 9SJ	Stratford-on-Avon	West Midlands	2018/2019	20	Planning stage	18/00940/OUT	27/03/2018	22/02/2019	Residential	No	20	x	0	0	Yes	Yes	0	0	0	0	7	0	0	0	0	0	0	0	0
PSLR1376	PLHP 2	Homes England	Chesterfield County Court	Chesterfield County Court St Marys Gate Chesterfield Derbyshire	S41 7TD	Chesterfield	East Midlands	2018/2019	12	Planning stage	CHE/18/00779/FUL	08/11/2018	14/01/2019	Residential	No	12	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1377	PLHP 2	Homes England	North Avon Magistrates' Court	North Avon Magistrates Court Kennedy Way Yate Bristol South Gloucestershire	BS37 4PY	South Gloucestershire	South West	2018/2019	45	Planning stage	P19/15929/RM	01/11/2019	x	Residential	No	45	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1378	PLHP 2	Homes England	Consett Magistrates' Court	Magistrates Court Ashdale Road Consett	DH8 6LY	County Durham	North East	2018/2019	20	Planning stage	DM/17/04130/OUT	22/12/2017	09/02/2018	Residential	No	20	x	0	0	Yes	Yes	0	0	0	0	3	0	0	0	0	0	0	0	0
PSLR1379	PLHP 2	Homes England	Phase 1 Houghton Grange	Houghton Grange Houghton Hill Houghton Huntingdon	PE28 2BZ	Huntingdonshire	East	2018/2019	96	Planning stage	19/01180/REM	10/06/2019	x	Residential	No	98	x	x	x	Yes	Yes	0	0	12	0	27	x	x	x	x	x	x	x	x
PSLR1380	PLHP 2	Homes England	Wakefield Magistrates' Court	Wakefield Magistrates Cliff Parade Wakefield	WF1 2TW	Wakefield	Yorkshire and The Humber	2018/2019	14	Development started	19/00393/FUL	20/02/2019	14/06/2019	Mixed	No	14	x	0	1	Yes	No	0	0	0	0	0	0	0	1	0	0	0	1	0
PSLR1381	PLHP 2	Homes England	Halifax County Court	County Court Coleridge Street Halifax Calderdale	HX1 2JJ	Calderdale	Yorkshire and The Humber	2018/2019	14	Planning stage	18/01545/FUL	24/12/2018	01/05/2019	Residential	No	14	x	0	0	Yes	Yes	14	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1382	PLHP 2	Homes England	Kettering County Court	Dryland Street Kettering	NN16 0BH	Kettering	East Midlands	2018/2019	14	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1383	PLHP 2	Homes England	Kendal Magistrates' Court	BURNESIDE ROAD, KENDAL, CUMBRIA	LA9 4TJ	South Lakeland	North West	2018/2019	60	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1384a	PLHP 2	Homes England	Kirkleatham Residential Phase 1		TS10 5NJ	Redcar and Cleveland	North East	2018/2019	375	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1384b	PLHP 2	Homes England	Kirkleatham Residential Phase 1		TS10 5NJ	Redcar and Cleveland	North East	2018/2019	375†	Development started	R/2019/0485/RMM	29/07/2019	31/10/2019	Residential	Yes	550	x	0	0	No	Yes	39	0	17	0	0	0	0	0	0	0	0	0	0
PSLR1385	PLHP 2	Homes England	Phase 2B, Park Prewett		RG24 9RF	Basingstoke and Deane	South East	2018/2019	143	Planning stage	17/03355/RES	04/10/2017	28/03/2018	Residential	No	141	x	0	0	Yes	Yes	0	0	0	0	46	0	0	0	0	0	0	0	0
PSLR1386	PLHP 2	Homes England	Banbury Lane, Northampton	Development Land Upton Valley Way East	NN4 9QE	Northampton	East Midlands	2018/2019	34	Planning stage	N/2015/0872	07/08/2015	20/11/2017	Residential	No	34	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1387	PLHP 2	Homes England	Phase 3a Locking Parklands	Locking Parklands (Former RAF Locking) Locking Weston-super-Mare	BS24 8BB	North Somerset	South West	2018/2019	36	Development started	18/P/3175/FUL	03/05/2018	01/04/2019	Residential	No	36	10/01/2020	14	22	Yes	Yes	9	0	2	0	0	17	1	4	1	6	3	12	0
PSLR1388	PLHP 2	Homes England	Phase 5 Locking Parklands	Locking Parklands (Former RAF Locking) Locking Weston-super-Mare	BS24 8BB	North Somerset	South West	2018/2019	99	Planning stage	19/P/0032/RM	07/01/2019	06/09/2019	Residential	No	99	x	0	0	Yes	Yes	0	0	0	0	12	0	0	0	0	0	0	0	0
PSLR1389	PLHP 2	Homes England	Phase 12 Locking Parklands	Phase 12 Locking Parklands Land Off Farnborough Road Locking	BS24 8BB	North Somerset	South West	2018/2019	15	Development started	17/P/5631/RM	15/12/2017	02/10/2019	Residential	No	15	27/11/2019	3	7	Yes	Unknown	0	0	0	0	0	3	0	4	5	2	0	0	0
PSLR1390	PLHP 2	Homes England	Phase 12 A - Locking Parklands	Land Off Bowen Road And Farnborough Road Parcel 12A Locking Parklands Locking	BS24 8BB	North Somerset	South West	2018/2019	27	Planning stage	18/P/2925/RM	06/04/2018	02/10/2019	Mixed	No	27	x	0	0	Yes	Yes	0	0	0	0	9	0	0	0	0	0	0	0	0
PSLR1391	PLHP 2	Homes England	Phases 1 and 2, Appleton Cross 3, Warrington	Land bounded by Green Lane &, Dipping Brook Avenue, Appleton, Warrington	WA4 5NN	Warrington	North West	2018/2019	370	Planning stage	2017/29930	02/03/2017	18/01/2018	Mixed	No	370	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1392	PLHP 2	Homes England	Grappenhall Heys Local Centre Sites		WA4 3HJ	Warrington	North West	2018/2019	180	Planning stage	2017/29929	02/03/2017	18/01/2018	Residential	Yes	400	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1393	PLHP 2	Homes England	Phase 3 Tattenhoe Park	Tattenhoe Park Snelshall Street H7 To H8 Milton Keynes	MK4 3FN	Milton Keynes	South East	2018/2019	303	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1394	PLHP 2	Homes England	Sandymoor North Phase 2		WA7 1XJ	Halton	North West	2018/2019	334	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1395	PLHP 2	Homes England	Land at D'Urton Lane	Land north of Durton Lane, Preston	PR3 5LE	Preston	North West	2018/2019	250	Planning stage	06/2017/0831	11/07/2017	20/12/2018	Residential	No	250	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1396	PLHP 2	Homes England	Phase 2 Tattenhoe Park	Tattenhoe Park Snelshall Street H7 To H8 Milton Keynes	MK4 3FN	Milton Keynes	South East	2018/2019	121	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1397	PLHP 2	Homes England	Royal Albert Farm - DoH Transfer NHSPS_02	Land At Royal Albert Farm Pathfinders Drive Lancaster Lancashire	LA1 4JJ	Lancaster	North West	2018/2019	77	Planning stage	17/01074/HYB	25/08/2017	x	Residential	No	77	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1398	PLHP 2	Homes England	Res Dev Parcel R1 Cottam Hall		PR4 0WD	Preston	North West	2018/2019	141	Planning stage	06/2019/0114	29/01/2019	06/08/2019	Residential	No	141	x	0	0	Yes	Yes	14	0	14	0	14	0	0	0	0	0	0	0	0
PSLR1399	PLHP 2	Homes England	Priorslee East J1/J2	Off, Priorslee East, Gatcombe Way/York Road/Hereford Drive, Priorslee, Telford, Shropshire	TF2 9GZ	Telford and Wrekin	West Midlands	2018/2019	90	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1400	PLHP 2	Homes England	Priorslee Road (Phase 2)	Off, Priorslee East, Gatcombe Way/York Road/Hereford Drive, Priorslee, Telford, Shropshire	TF2 9HE	Telford and Wrekin	West Midlands	2018/2019	76	Planning stage	TWC/2018/0780	25/09/2018	27/08/2019	Residential	No	76	x	0	0	Yes	Yes	0	0	0	0	19	0	0	0	0	0	0	0	0
PSLR1401	PLHP 2	Homes England	Parcel 0 (New Towns Land Portfolio - 2013 transfer to MKDP)	Site At Campbell Park H3 And H4 Overgate Campbell Park Milton Keynes		Milton Keynes	South East	2018/2019	383	Development started	17/00850/REM	24/03/2017	14/11/2017	Mixed	Yes	383	09/01/2020	2	30	No	Yes	20	0	95	0	0	18	10	2	0	0	0	30	0
PSLR1402	PLHP 2	Homes England	MKDP 2013 Land Transfer - Lilleshall Avenue, Monkston	Land West of Lilleshall Avenue Monkston Milton Keynes		Milton Keynes	South East	2018/2019	24	Development completed	16/01100/FUL	27/04/2016	25/01/2017	Residential	No	24	08/12/2017	0	24	Yes	Yes	5	0	2	0	0	21	3	0	10	4	8	2	0
PSLR1403	PLHP 2	Homes England	MKDP 2013 Land Transfer - Atterbury	Land Off Tongwell Street Atterbury Broughton Milton Keynes		Milton Keynes	South East	2018/2019	118	Planning stage	17/00541/FUL	01/03/2017	26/06/2018	Residential	No	118	x	0	0	Yes	Yes	0	0	0	0	35	0	0	0	0	0	0	0	0
PSLR1404	PLHP 2	Homes England	MKDP 2013 Land Transfer - Worrelle Avenue, Monkston	Worrelle Avenue Middleton Milton Keynes		Milton Keynes	South East	2018/2019	20	Planning stage	17/02415/FUL	08/09/2017	27/07/2018	Residential	No	20	x	0	0	Yes	Yes	0	0	0	0	6	0	0	0	0	0	0	0	0
PSLR1405	PLHP 2	Homes England	The Croppings Phase 2	Land at, Lightmoor, Telford, Shropshire	TF4 3QH	Telford and Wrekin	West Midlands	2018/2019	290	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1406	PLHP 2	Homes England	Daedalus DC Phase 2		PO13 9JY	Gosport	South East	2018/2019	19	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1407	PLHP 2	DfT	Kidbrooke (TfL)	Land North Side of Kidbrooke Station, Grenwich, London	SE3 9PL	Greenwich	London	2018/2019	91	Planning stage	18/4187/F	29/11/2018	x	Mixed	Yes	619	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1408	PLHP 2	DHSC	Westridge	Former Westridge Hospital Standish Stonehouse Gloucestershire	GL10 3HA	Stroud	South West	2018/2019	17	Development started	S.17/2729/FUL	01/12/2017	14/02/2019	Residential	Yes	147	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1409	PLHP 2	DHSC	NASEBERRY COURT	2 Merriam Close Chingford London	E4 9JQ	Waltham Forest	London	2018/2019	119	Development started	182249	29/06/2018	25/01/2019	Residential	No	119	06/02/2020	0	0	Yes	Yes	17	0	16	0	0	0	0	0	0	0	0	0	0
PSLR1410	PLHP 2	DHSC	Richmond Royal	Kew Foot Road, Richmond	TW9 2TE	Richmond upon Thames	London	2018/2019	68	Planning stage	18/3950/FUL	03/12/2018	15/07/2019	Mixed	No	71	x	0	0	Yes	Yes	0	0	0	0	15	0	0	0	0	0	0	0	0
PSLR1411	PLHP 2	DHSC	West Bank	Site of Bowring Hall, 300 Holyhead Road, Wellington, Telford, Shropshire	TF1 2EF	Telford and Wrekin	West Midlands	2018/2019	16	Development started	TWC/2018/0435	22/05/2018	08/03/2019	Residential	No	16	06/02/2020	6	5	Yes	No	0	0	0	0	0	0	0	5	0	0	0	5	0
PSLR1412	PLHP 2	DHSC	The Spring	The Springs 18 Tonbridge Road Pembury Royal Tunbridge Wells Kent	TN2 4QL	Tunbridge Wells	South East	2018/2019	10	Planning stage	18/03307/FULL	23/10/2018	25/01/2019	Residential	No	10	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1413	PLHP 2	DHSC	Dover Ambulance Station	Ambulance Depot Winchelsea Road Dover	CT17 9TT	Dover	South East	2018/2019	9	Planning stage	12/00120	13/02/2012	26/08/2016	Mixed	No	9	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1414	PLHP 2	DHSC	Marie Foster Centre	Marie Foster Home Wood Street Barnet	EN5 4BS	Barnet	London	2018/2019	18	Development started	18/5926/FUL	03/10/2018	15/02/2019	Residential institute	No	25	03/01/2020	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1415	PLHP 2	DHSC	Market Harborough and District Hospital	58 Coventry Road Market Harborough Leicestershire	LE16 9DD	Harborough	East Midlands	2018/2019	17	Planning stage	18/00687/FUL	18/04/2018	28/02/2019	Residential institute	No	17	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1416	PLHP 2	DHSC	St Olaves Nursing Home	Ann Moss Way, London	SE16 2TL	Southwark	London	2018/2019	35	Planning stage	19/AP/1612	14/05/2019	x	Residential	Yes	61	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1417	PLHP 2	DHSC	Stocks Lane	58, Stocks Lane, Gamlingay, Sandy	SG19 3JR	South Cambridgeshire	East	2018/2019	1	Development completed	S/1945/18/FL	29/05/2018	10/08/2018	Residential	No	1	19/03/2012	0	1	Yes	No	0	0	0	0	0	1	0	0	0	0	0	0	1
PSLR1418	PLHP 2	DHSC	The Chapel (part of St Martins)	Clara Cross Lane, Odd Down, Bath, Bath And North East Somerset	BA2 5RP	Bath & NE Somerset	South West	2018/2019	5	Planning stage	19/00021/FUL	03/01/2019	x	Mixed	No	5	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1419	PLHP 2	Homes England	Central Ambulance Station - NHS_17	Station Marybush Lane Bristol	BS2 0JB	Bristol	South West	2018/2019	121	Planning stage	17/04267/F	28/07/2017	06/09/2018	Residential	No	375	x	0	0	No	Yes	58	0	17	0	0	0	0	0	0	0	0	0	0
PSLR1420	PLHP 2	Homes England	Scout Hut Site	Former Scout Hut Coldeast Way Sarisbury Green FAREHAM	SO31 7NJ	Fareham	South East	2018/2019	7	Planning stage	P/17/1420/OA	21/11/2017	18/05/2018	Residential	No	7	x	0	0	Yes	Yes	0	0	0	0	7	0	0	0	0	0	0	0	0
PSLR1421	PLHP 2	Homes England	Land at John Street, Derby		DE1 2LU	Derby	East Midlands	2018/2019	64	Planning stage	03/18/00378	23/04/2018	x	Residential	Yes	180	x	x	x	No	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1422	PLHP 2	Homes England	7 John Street and New Street, Derby		DE1 2LU	Derby	East Midlands	2018/2019	94	Development started	05/12/00563	09/05/2012	08/02/2013	Mixed	Yes	660	x	0	0	Yes	Yes	26	0	8	0	0	0	0	0	0	0	0	0	0
PSLR1423	PLHP 2	Homes England	65 Canal Street		DE1 2LU	Derby	East Midlands	2018/2019	10	Development started	05/12/00563	09/05/2012	08/02/2013	Mixed	Yes	660	x	0	0	Yes	Yes	26	0	8	0	0	0	0	0	0	0	0	0	0
PSLR1424	PLHP 2	Homes England	Unit 1 and 2 New Street		DE1 2LU	Derby	East Midlands	2018/2019	5	Development started	05/12/00563	09/05/2012	08/02/2013	Mixed	Yes	660	x	0	0	Yes	Yes	26	0	8	0	0	0	0	0	0	0	0	0	0
PSLR1425	PLHP 2	HE Transfers	Blood Centre Brentwood	Crescent Drive	CM15 8DP	Brentwood	East	2018/2019	55	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1426	PLHP 2	DfT	Nottingham, Queens Road	Nottingham, Queens Road	NG2 3AN	Nottingham	East Midlands	2018/2019	337	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1427	PLHP 2	DfT	Southall (Parcels A, B and C near Southall, LB Ealing)	Parcels A, B and C off Park Avenue ,Middx	UB1 3AD	Ealing	London	2018/2019	100	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1428	PLHP 2	MoD	SLA NEW BUILD 1819 - Q4	Various locations - Larkhill & Bulford		x	x	2018/2019	142	Development completed	x	x	x	Residential sale	Not applicable	142	x	x	142	Not applicable	Unknown	0	0	0	0	0	x	x	142	x	x	x	x	142
PSLR1429	PLHP 2	MoD	SFA NEW BUILD 18/19 - Q4	Various locations - Bulford & Ludgershall		x	x	2018/2019	172	Development completed	x	x	x	Residential sale	Not applicable	172	x	x	172	Not applicable	Unknown	0	0	0	0	0	x	x	172	x	x	x	x	172
PSLR1430	PLHP 2	MoD	HOLCOMBE MOOR TRAINING CAMP-HOLCOMBE MOOR TRAINING CAMP	Hawkshaw	BL8 4JJ	x	x	2019/2020	1	Development completed	x	x	x	Residential sale	Unknown	1	x	x	1	Unknown	Unknown	0	0	0	0	0	x	x	1	x	x	x	x	1
PSLR1431	PLHP 2	DHSC	Rushden Ambulance Station	Station Road	NN10 9SJ	East Northamptonshire	East Midlands	2019/2020	11	Planning stage	18/01092/FUL	11/06/2018	06/06/2019	Residential	No	11	x	0	0	Unknown	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1432	PLHP 2	DHSC	Part of land adjacent to 7a Woodfield Road used as a car park	7a Woodfield Road, London	W9 2BA	Westminster	London	2019/2020	74	Planning stage	18/01481/FULL	21/02/2018	30/04/2019	Residential	No	73	x	0	0	Unknown	Yes	0	0	0	0	19	0	0	0	0	0	0	0	0
PSLR1434	PLHP 2	MoD	Arborfield & Lyneham SFA	Various Locations		x	x	2019/2020	29	Development completed	x	x	x	Residential sale	Unknown	29	x	x	29	Unknown	Unknown	0	0	0	0	0	x	x	29	x	x	x	x	29
PSLR1435	PLHP 2	MoD	Ludgershall & Bulford SFA	Various Locations		x	x	2019/2020	193	Development completed	x	x	x	Residential sale	Unknown	193	x	x	193	Unknown	Unknown	0	0	0	0	0	x	x	193	x	x	x	x	193
PSLR1436	PLHP 2	MoD	HUNTINGDON SLA	Various Locations		x	x	2019/2020	165	Development completed	x	x	x	Residential sale	Unknown	165	x	x	165	Unknown	Unknown	0	0	0	0	0	x	x	165	x	x	x	x	165
PSLR1437	PLHP 2	DHSC	Carnegie Centre	Hunters Road, Hockley, Birmingham	B19 1DR	Birmingham	West Midlands	2019/2020	16	Planning stage	2017/04331/PA	18/05/2017	26/10/2017	Residential institute	No	16	x	0	0	Unknown	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1438	PLHP 2	DfT	Salford, land adjacent to 48 Chapel Street	48-50 CHAPEL STREET, SALFORD	M3 7AA	Salford	North West	2019/2020	40	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1439	PLHP 2	DHSC	Coburg Court	Maud Road, Dorchester	DT1 2NZ	West Dorset	South West	2019/2020	7	Development started	WD/D/19/001365	28/05/2019	29/07/2019	Residential	No	7	19/03/2012	0	5	Unknown	No	0	0	0	0	0	5	0	0	0	0	2	3	0
PSLR1440	PLHP 2	DHSC	Northern Moor Combined Clinic	Moorcroft Road, Manchester	M23 0AT	Manchester	North West	2019/2020	9	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1441	PLHP 2	DHSC	The Gate Lodge	43 High Street, Amblecote	DY8 4DG	Dudley	West Midlands	2019/2020	1	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1442	PLHP 2	DfT	2&4 Ellison Road	1 & 4 Ellison Road, Lambeth, London	SW16 5BY	Lambeth	London	2019/2020	9	Planning stage	19/02453/FUL	08/07/2019	x	Mixed	No	9	x	x	x	Unknown	No	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1443	PLHP 2	MoJ	Stroud, The Firs	The Firs, 118 Cainscross Road, Stroud, Gloucestershire	GL5 4HN	Stroud	South West	2019/2020	9	Planning stage	S.17/0220/FUL	28/01/2017	30/03/2017	Residential	No	9	x	0	0	Unknown	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1444	PLHP 2	Homes England	Eastbourne Magistrates' Court		BN21 1DD	Eastbourne	South East	2019/2020	35	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1445	PLHP 2	Homes England	Halifax Magistrates' Court		HX1 2AN	Calderdale	Yorkshire and The Humber	2019/2020	5	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1446	PLHP 2	DfT	Chobham Farm North Zone 3	Leyton Road, Stratford, London	E15 1DH	Newham	London	2019/2020	36	Development completed	12/00146/FUM	12/09/2012	28/02/2014	Mixed	Yes	173	x	x	x	No	Yes	0	23	15	0	0	x	x	x	x	x	x	x	x
PSLR1447	PLHP 2	DfT	Air Space over Stratford Bus layover	Adjacent to Stratford International Station, International Way, Stratford, London	E20 1YY	Newham	London	2019/2020	369	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1448	PLHP 2	DHSC	296 Drayton High Road	296 Drayton High Road Norwich	NR6 5BJ	Broadland	East	2019/2020	1	Planning stage	20190343	06/03/2019	07/06/2019	Residential	No	1	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1449	PLHP 2	MoD	MERSEYSIDE VOLUNTEER ESTATE-ALEXANDRA COURT	Alexandra Court, 28 Alexandra Road	L17 8YE	Liverpool	North West	2019/2020	53	Development started	19F/1157	20/05/2019	12/11/2019	Residential	Yes	73	21/02/2012	0	2	No	Unknown	0	0	0	0	0	0	0	2	0	0	0	2	0
PSLR1450	PLHP 2	MoD	JSCS ASHCHURCH-JSCS ASHCHURCH	A.46,	GL20 8LZ	Tewkesbury	South West	2019/2020	350	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1451	PLHP 2	MoD	DIO ALDERSHOT-BLANDFORD HOUSE	Shoe Lane	GU11 2HA	Rushmoor	South East	2019/2020	160	Development started	17/00914/OUTPP	31/10/2017	24/11/2017	Residential	No	180	21/02/2012	0	3	Yes	Yes	38	0	16	0	0	0	0	3	1	1	0	1	0
PSLR1452	PLHP 2	Homes England	Blessed Robert Johnson Phase I		TF1 3GD	Telford and Wrekin	West Midlands	2019/2020	54	Planning stage	TWC/2018/0658	08/08/2018	03/07/2019	Residential	No	54	x	0	0	Unknown	Yes	2	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1453	PLHP 2	Homes England	CBX3 Central Milton Keynes		MK9 2GA	Milton Keynes	South East	2019/2020	294	Planning stage	18/02822/OUT	21/09/2018	31/07/2019	Mixed	No	294	x	0	0	Unknown	Mix of pay and houses	0	0	0	0	29	0	0	0	0	0	0	0	0
PSLR1454	PLHP 2	Homes England	Land At Cowling Brow Greenside Euxton		PR6 9EA	Chorley	North West	2019/2020	17	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1455	PLHP 2	Homes England	Site C Pool Hill Road		TF4 3AS	Telford and Wrekin	West Midlands	2019/2020	5	Planning stage	TWC/2018/0657	08/08/2018	05/10/2018	Residential	No	5	x	0	0	Unknown	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1456	PLHP 2	DHSC	The Newlands	Newlands Balderton Hospital Great North Road Fernwood Newark On Trent Nottinghamshire	NG24 3JX	Newark and Sherwood	East Midlands	2019/2020	9	Planning stage	18/02304/FUL	14/12/2018	29/01/2019	Residential	No	9	x	0	0	Unknown	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1457	PLHP 2	DHSC	Broomfield Lane Clinic	9 & 11 Broomfield Lane Medical Centre, Broomfield Lane, Hale, Altrincham	WA15 9AP	Trafford	North West	2019/2020	2	Development completed	95461/FUL/18	17/08/2018	04/12/2018	Residential	No	2	03/10/2019	0	2	Unknown	Unknown	0	0	0	0	0	1	0	1	0	2	0	0	0
PSLR1459	PLHP 2	DHSC	Exeter Road Cottages Langdon Hospital	Exeter Road, Dawlish, Devon	EX7 0NS	Teignbridge	South West	2019/2020	200	Planning stage	19/01767/MAJ	06/09/2019	30/04/2020	Mixed	No	190	x	0	0	Unknown	Yes	34	x	14	x	x	0	0	0	0	0	0	0	0
PSLR1460	PLHP 2	BBC	Roselands Resource Centre	163 Kingston Road, New Malden	KT3 3NN	Kingston upon Thames	London	2019/2020	37	Planning stage	18/14633/FUL	06/07/2018	08/03/2019	Residential	No	37	x	0	0	Unknown	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1461	PLHP 2	DHSC	Stoney Ridge Hospital	Stoney Ridge Road, Bingley	BD16 1UL	Bradford	Yorkshire and The Humber	2019/2020	13	Planning stage	19/02265/MAO	24/05/2019	30/05/2019	Residential	No	13	x	0	0	Unknown	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1462	PLHP 2	DHSC	Castle Lodge	28 Castle Road, Sandal, Wakefield	WF2 7LZ	Wakefield	Yorkshire and The Humber	2019/2020	16	Development started	18/02276/FUL	08/10/2018	12/07/2019	Residential institute	No	17	21/02/2012	0	1	Unknown	Unknown	0	0	0	0	0	0	0	1	1	0	0	0	0
PSLR1463	PLHP 2	DHSC	Audrey House	17 Vernon Street, Derby	DE1 1FT	Derby	East Midlands	2019/2020	13	Development started	09/18/01375	11/09/2018	27/02/2019	Residential	No	13	21/02/2012	0	1	Unknown	No	0	0	0	0	0	0	0	1	0	0	1	0	0
PSLR1464	PLHP 2	DHSC	117-123 Sydney Street	117-123 Sydney Street	SW3 6NR	Kensington and Chelsea	London	2019/2020	4	Development started	PP/16/04269	06/07/2016	17/11/2017	Mixed	No	4	18/03/2015	0	2	Not applicable	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	0	2	0	0	0	2	0
PSLR1465	PLHP 2	DHSC	Bluebell House	Royal George Road, Burgess Hill	RH15 9NZ	Mid Sussex	South East	2019/2020	8	Planning stage	DM/18/5068	18/12/2018	09/08/2019	Residential	No	8	x	0	0	Not applicable	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1466	PLHP 2	DHSC	Northgate Hospital	Northgate Street, Great Yarmouth	NR31 1BU	Great Yarmouth	East	2019/2020	66	Planning stage	06/18/0582/F	05/10/2018	x	Residential	Yes	76	x	x	x	Unknown	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1467	PLHP 2	DHSC	21 Silver Street	21 Silver Street, Bury	BL9 0EN	Bury	North West	2019/2020	19	Planning stage	63606	18/12/2018	26/02/2019	Residential	No	19	x	0	0	Unknown	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1468	PLHP 2	DHSC	Brackley Cottage Hospital	Pebble Lane Brackley	NN13 7DA	South Northamptonshire	East Midlands	2019/2020	2	Planning stage	S/2019/1084/FUL	30/05/2019	27/09/2019	Residential	No	2	x	0	0	Unknown	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1469	PLHP 2	DHSC	Canterbury Street Surgery	Canterbury Street Kent, Gillingham	ME7 5LF	Medway	South East	2019/2020	13	Planning stage	MC/17/2872	17/08/2017	15/03/2018	Residential	No	13	x	0	0	Unknown	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1470	PLHP 2	DHSC	Former Ambulance Station	Northgate Street, Great Yarmouth	NR30 1BU	Great Yarmouth	East	2019/2020	3	Planning stage	06/18/0582/F	05/10/2018	x	Residential	Yes	76	x	x	x	Unknown	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1471	PLHP 2	DHSC	Holly Park Clinic	Holly Park Road, Barnet	N11 3HB	Barnet	London	2019/2020	9	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1472	PLHP 2	DHSC	Horden Clinic	Blackhilss Road, Horden, Peterlee	SR8 4LQ	County Durham	North East	2019/2020	1	Planning stage	DM/17/02549/FPA	27/07/2017	21/12/2017	Residential	No	1	x	0	0	Unknown	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1473	PLHP 2	DHSC	Lyngford House	Selworthy Road, Taunton	TA2 7LJ	Somerset West and Taunton	South West	2019/2020	45	Development started	38/18/0108	20/03/2018	03/07/2020	Residential	No	45	x	0	1	Unknown	Unknown	0	0	0	0	0	0	0	1	1	0	0	0	0
PSLR1474	PLHP 2	DHSC	Poltair Hospital	Penzance	TR20 8SR	Cornwall	South West	2019/2020	12	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1475	PLHP 2	DHSC	Rochester Road Clinic	Rochester Road, Gravesend	DA12 2HU	Gravesham	South East	2019/2020	9	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1476	PLHP 2	DHSC	Sedlescombe Road North	Sedlescombe Road North, St Leonards on Sea	TN37 7EJ	Hastings	South East	2019/2020	2	Development completed	HS/PR/17/010141	30/11/2017	01/02/2018	Residential	No	2	04/12/2018	0	2	Unknown	No	0	0	0	0	0	0	0	2	0	0	0	2	0
PSLR1477	PLHP 2	DHSC	St Bartholomews Hospital	St Bartholomew's, New Road, Rochester	ME1 1DS	Medway	South East	2019/2020	103	Planning stage	MC/19/2709	28/10/2019	x	Residential	Unknown	155	x	x	x	Unknown	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1478	PLHP 2	DHSC	Suttons Drive Community Unit	Suttons Drive, Birmingham	B43 7BB	Walsall	West Midlands	2019/2020	2	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1479	PLHP 2	DHSC	Lingdale Clinic	High Street, Lingdale, Saltburn-by-Sea	TS12 3EX	Redcar and Cleveland	North East	2019/2020	6	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1480	PLHP 2	DHSC	Ettingshall Lodge	Ettingshall Road, Wolverhampton	WV2 2LA	Wolverhampton	West Midlands	2019/2020	10	Development started	19/00990/PAOCOU	15/08/2019	02/09/2019	Residential	No	10	x	0	1	Unknown	No	0	0	0	0	0	1	0	0	1	0	0	0	0
PSLR1481	PLHP 2	DfT	Manchester Collyhurst Redbank Sidings	Land off Collyhurst Road	M40 7RT	Manchester	North West	2019/2020	1130	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1482	PLHP 2	MoJ	Devon House	Devon House, 123 Whitehall Road, Bristol	BS5 9BG	Bristol	South West	2019/2020	15	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1483	PLHP 2	MoJ	Totnes Magistrates Court	Ashburton Road, Totnes, Devon	TQ9 5JY	South Hams	South West	2019/2020	4	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1484	PLHP 2	MoD	Lugershall, Bulford and Larkhill SFA New Build	Various Locations		x	x	2019/2020	199	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1485	PLHP 2	MoD	SLA New Build	Various Locations		x	x	2019/2020	92	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1486	PLHP 2	MoD	Headley Court SFA	Various Locations		x	x	2019/2020	63	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1487	PLHP 2	MoD	SFA Sub-let	Various Locations		x	x	2019/2020	46	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1488	PLHP 2	MoD	RAF LAKENHEATH-ELY FAMILY QUARTERS	Ely	CB7 4US	East Cambridgeshire	East	2019/2020	88	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1489	PLHP 2	Homes England	Former Lea Castle Hospital Site	Former Lea Castle Hospital Site	DY10 3PP	Wyre Forest	West Midlands	2019/2020	600	Planning stage	17/0205/OUTL	31/03/2017	27/06/2019	Mixed	No	600	x	0	0	Yes	Yes	65	x	35	x	x	0	0	0	0	0	0	0	0
PSLR1490	PLHP 2	Homes England	Land at Horton Lane, Plot C - Lot 1	Land at Horton Lane, Plot C - Lot 1	TF6 6DT	Telford and Wrekin	West Midlands	2019/2020	1	Planning stage	TWC/2019/0561	09/07/2019	07/10/2019	Residential	No	1	x	0	0	Yes	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1491	PLHP 2	Homes England	Malmo Quay, Ouseburn	Malmo Quay, Ouseburn	NE6 1BU	Newcastle upon Tyne	North East	2019/2020	70	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1492	PLHP 2	DHSC	Overton House	Overton House	LE8 4GD	Blaby	East Midlands	2019/2020	2	Planning stage	20/0061/CLASSO	22/01/2020	x	Residential	No	8	x	x	x	Unknown	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1493	PLHP 2	DHSC	St Paul's Way Medical Centre	St Paul's Way Medical Centre	E3 4AJ	Tower Hamlets	London	2019/2020	23	Planning stage	PA/19/00828/A1	16/04/2019	17/07/2019	Mixed	No	23	x	0	0	Yes	Yes	12	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1494	PLHP 2	DHSC	The Lodge	The Lodge	LU1 2BJ	Luton	East	2019/2020	10	Planning stage	20/00203/FUL	17/02/2020	x	Residential	No	10	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1495	PLHP 2	DHSC	Wandle Valley Health Centre	Wandle Valley Health Centre	CR4 4AX	Sutton	London	2019/2020	3	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1496	PLHP 2	DHSC	1-12 MacMillan Close	1-12 MacMillan Close	NG3 6GJ	Nottingham	East Midlands	2019/2020	12	Development completed	19/01775/PFUL3	12/08/2019	15/11/2019	Residential	No	12	21/02/2012	0	12	Yes	No	0	0	0	0	0	11	0	1	0	0	12	0	0
PSLR1497	PLHP 2	DHSC	Buckland Hospital	Buckland Hospital	CT17 0HD	Dover	South East	2019/2020	150	Development started	17/01523	21/12/2017	23/12/2017	Residential	No	150	15/11/2018	0	0	Not applicable	Developer paid local authority to put them somewhere else	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1498a	PLHP 2	DHSC	Springfield University Hospital - Plots B-E and L-M (Phase 1)	Springfield University Hospital - Plots B-E and L-M (Phase 1)	SW17 7DJ	Wandsworth	London	2019/2020	422	Planning stage	2020/1779	29/05/2020	x	Mixed	No	227	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1498b	PLHP 2	DHSC	Springfield University Hospital - Plots B-E and L-M (Phase 1)	Springfield University Hospital - Plots B-E and L-M (Phase 1)	SW17 7DJ	Wandsworth	London	2019/2020	422†	Planning stage	2020/1780	01/06/2020	x	Residential	No	71	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1499	PLHP 2	DHSC	Springfield University Hospital - Plot R and S (Phase 2)	Springfield University Hospital - Plot R and S (Phase 2)	SW17 7DJ	Wandsworth	London	2019/2020	467	Planning stage	2020/1490	13/05/2020	x	Residential	No	72	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1500	PLHP 2	DHSC	Vinery Road	Vinery Road	CB1 3DX	Cambridge	East	2019/2020	9	Planning stage	19/0769/PIP	04/06/2019	04/11/2019	Residential	No	9	x	0	0	Unknown	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1501	PLHP 2	MoD	LARKHILL SFA-ALLANBROOKE SFA ESTATE	Various Locations		x	x	2019/2020	133	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1502	PLHP 2	MoD	HUNTINGDON SFA-WYTON ESTATE	Various Locations		x	x	2019/2020	58	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1503	PLHP 2	MoD	RAF WYTON-RAF WYTON (MAIN SITE) SLA	Various Locations		x	x	2019/2020	34	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1504	PLHP 2	MoD	SOUTHWICK PARK-DEFENCE COLLEGE OF POLICING AND GUARDING	Various Locations	PO17 6EJ	Winchester	South East	2019/2020	12	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1505	PLHP 2	MoJ	Grantham Magistrates Court	Grantham Magistrates Court	NG31 7SB	South Kesteven	East Midlands	2019/2020	17	Planning stage	S19/1390	01/08/2019	12/12/2019	Residential institute	No	68	x	0	0	Not applicable	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1506a	PLHP 2	MoJ	Oswestrey Magistrates and County Court	Oswestrey Magistrates and County Court	SY11 1RP	Shropshire	West Midlands	2019/2020	10	Planning stage	18/03113/FUL	05/07/2018	21/06/2019	Residential	No	10	x	0	0	Yes	Yes	1	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1506b	PLHP 2	MoJ	Oswestrey Magistrates and County Court	Oswestrey Magistrates and County Court	SY11 1RP	Shropshire	West Midlands	2019/2020	10†	Planning stage	18/02928/FUL	05/07/2018	21/06/2019	Residential	No	10	x	0	0	Not applicable	No	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1508	PLHP 2	DfT	Witan Street, Bethnal Green	Witan Street, Bethnal Green	E2 6JT	Tower Hamlets	London	2019/2020	19	Planning stage	PA/17/01808/A1	22/06/2017	02/08/2019	Mixed	No	62	x	0	0	Unknown	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1509	PLHP 2	DfT	Guildford	Guildford	GU1 4UT	Guildford	South East	2019/2020	438	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1510	PLHP 2	DfT	Bishopsgate Goodsyard	Shoreditch High Street, Spitalfields, London	E1 6GY	Tower Hamlets	London	2019/2020	500	Planning stage	PA/14/02011/A1	09/09/2014	x	Mixed	No	500	x	x	x	Yes	Unknown	0	0	0	0	x	x	x	x	x	x	x	x	x
PSLR1511	PLHP 2	DfT	Exmouth Junction	Land off Mount Pleasant Road, Exeter	EX4 7AE	Exeter	South West	2019/2020	400	Planning stage	19/0650/OUT	10/05/2019	x	Residential	No	465	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1512	PLHP 2	MoJ	37 Groom Crescent site	37 Groom Crescent, Wandsworth	SW18 3JB	Wandsworth	London	2019/2020	7	Planning stage	2019/51110	25/11/2019	21/02/2020	Residential	No	7	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1513	PLHP 2	MoD	ANNINGTON HOMES SFA - 2 YEAR SUB-LETS AND AHL RELEASES AT VARIOUS LOCATIONS 19/20 Q4	Various Locations		x	x	2019/2020	179	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1514	PLHP 2	MoD	SLA NEW BUILD 19/20 - Q4	Various Locations		x	x	2019/2020	5	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1515	PLHP 2	MoD	SLA NEW BUILD 19/20 - Q4	Various Locations		x	x	2019/2020	146	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1516	PLHP 2	HE Transfers	Ida Darwin Hospital	Ida Darwin Hospital Fulbourn Old Drift Fulbourn Cambridge Cambridgeshire	CB21 5EE	South Cambridgeshire	East	2019/2020	203	Planning stage	S/0670/17/OL	24/02/2017	07/11/2019	Residential	No	203	x	0	0	Yes	Yes	57	0	24	0	0	0	0	0	0	0	0	0	0
PSLR1517	PLHP 2	HE Transfers	Ribbleton Hospital	Ribbleton Hospital, Miller Road, Preston	PR2 6LP	Preston	North West	2019/2020	139	Planning stage	06/2018/1282	23/11/2018	28/03/2019	Residential	No	139	x	0	0	Yes	Yes	30	0	12	0	0	0	0	0	0	0	0	0	0
PSLR1518	PLHP 2	HE Transfers	Wealstun Phase 2	Land Off Walton Road Walton Wetherby	LS237AZ	Leeds	Yorkshire and The Humber	2019/2020	119	Planning stage	17/07970/OT	05/12/2017	10/12/2019	Permitted development	No	119	x	0	0	Yes	Yes	0	0	0	0	42	0	0	0	0	0	0	0	0
PSLR1519	PLHP 2	HE Transfers	St James Hospital, Portsmouth	St James' Hospital Locksway Road Southsea	PO4 8GA	Portsmouth	South East	2019/2020	107	Planning stage	18/00288/OUT	19/02/2018	x	Residential	No	107	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1520	PLHP 2	HE Transfers	Former Ridge Hill Hospital	RIDGE HILL, BRIERLEY HILL ROAD, WORDSLEY, STOURBRIDGE	DY8 5ST	Dudley	West Midlands	2019/2020	103	Planning stage	P19/1777	18/12/2019	x	Residential	No	103	x	x	x	Unknown	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1521	PLHP 2	HE Transfers	Walton Hospital Land		S40 3HW	Chesterfield	East Midlands	2019/2020	90	Planning stage	CHE/20/00305/FUL	13/05/2020	x	Residential	No	153	x	x	x	Unknown	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1522	PLHP 2	HE Transfers	Walton Land Harehill Road		S40 3HW	Chesterfield	East Midlands	2019/2020	60	Planning stage	CHE/20/00305/FUL	13/05/2020	x	Residential	No	153	x	x	x	Unknown	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1523	PLHP 2	HE Transfers	ST MARY'S HOSPTIAL, Part Hospital Site, Melton Mowbray	St Marys Hospital Thorpe Road Melton Mowbray	LE13 1SJ	Melton	East Midlands	2019/2020	46	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1524	PLHP 2	HE Transfers	5898 Peasley Cross, St Helens	Land To Rear Of 18 To 46 Broadgate Avenue And 64 To 94 Marshalls Cross Road St Helens	WA93BZ	St Helens	North West	2019/2020	46	Planning stage	P/2019/0693/FUL	11/09/2019	15/01/2020	Residential	No	32	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1525	PLHP 2	HE Transfers	Fairview House	Fairview House, Corporation Road, Bodmin, Cornwall	PL311FB	Cornwall	South West	2019/2020	13	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1526	PLHP 2	HE Transfers	Macclesfield Magistrates' Court	MACCLESFIELD LAW COURT, HIBEL ROAD, MACCLESFIELD, CHESHIRE	SK10 2AB	Cheshire East	North West	2019/2020	12	Planning stage	18/6014M	30/11/2018	04/02/2020	Residential	No	12	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1527	PLHP 2	Homes England	Gardiners Cl - Ford Sports Sth		SS143AN	Basildon	East	2019/2020	625	Planning stage	16/00829/FULL	15/06/2016	03/10/2017	Commercial	No	0	x	x	x	Yes	No	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1528	PLHP 2	Homes England	Norton Green, Stevenage		SG1 2TS	Stevenage	East	2019/2020	200	Planning stage	01/00423/OP	24/07/2001	x	Mixed	Yes	5000	x	x	x	No	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1529	PLHP 2	Homes England	Hadston Industrial Estate	Land north of Hartside Crescent, Hadston, Northumberland	NE659YG	Northumberland	North East	2019/2020	65	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1530	PLHP 2	Homes England	Cottam Hall Plot 14, Cottam, Preston	Land adjacent to Cottam between Hoyles Lane Sidgreaves Lane Lea Road and Lancaster Canal - Cottam Hall Lea Preston	PR4 0WD	Preston	North West	2019/2020	68	Planning stage	06/2019/1210	21/10/2019	14/01/2020	Residential	No	68	x	0	0	Yes	Yes	0	0	0	0	21	0	0	0	0	0	0	0	0
PSLR1531	PLHP 2	Homes England	Union Square (The Exchange)		SN1 2DP	Swindon	South West	2019/2020	205	Development started	S/11/06140	03/05/2011	03/05/2012	Mixed	Yes	450	x	0	0	Unknown	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1532	PLHP 2	Homes England	MKDP 2013 Land Transfer - Ladbroke Grove, Monkston	Land Off Ladbroke Grove, Monkston Ladbroke Grove Monkston Park Milton Keynes	MK10 9RD	Milton Keynes	South East	2019/2020	26	Planning stage	18/00735/FUL	21/03/2018	31/10/2018	Residential	No	x	x	x	x	Yes	Yes	6	0	2	0	0	x	x	x	x	x	x	x	x
PSLR1533	PLHP 2	Homes England	MKDP 2013 Land Transfer - Pascel Drive, Medbourne	Development Site B Pascal Drive Medbourne Milton Keynes	MK5 6LS	Milton Keynes	South East	2019/2020	19	Planning stage	19/01245/FUL	13/05/2019	05/12/2019	Residential	No	19	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1534	PLHP 2	Homes England	MKDP 2013 Land Transfer - Hindhead Knoll, Walnut Tree	Land Adjacent 146 Lichfield Down Walnut Tree Milton Keynes	MK7 7NR	Milton Keynes	South East	2019/2020	50	Planning stage	18/01280/FUL	24/05/2018	21/12/2018	Residential	No	50	x	0	0	Yes	Yes	x	x	15	x	x	0	0	0	0	0	0	0	0
PSLR1535	PLHP 2	Homes England	Hampstead Gate, Bradwell Common	Land At Hampstead Gate Bradwell Common Milton Keynes	MK13 8BN	Milton Keynes	South East	2019/2020	34	Planning stage	19/02347/FUL	14/09/2019	28/02/2020	Residential	No	34	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1536	PLHP 2	Homes England	Phase 2, Spencers Park	Land Between Three Cherry Trees Lane And Cherry Tree Lane Hemel Hempstead	HP2 7SZ	Dacorum	East	2019/2020	410	Planning stage	4/02539/16/MOA	19/09/2016	30/04/2019	Mixed	Yes	600	x	0	0	Unknown	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1537	PLHP 2	Homes England	Croston Road Phase 1, Farrington, Leyland	Land Off Croston Road - Between Moss Lane and Rear Of 394 Croston Road Farington Moss Lancashire	PR266PZ	South Ribble	North West	2019/2020	400	Development started	07/2014/0184/ORM	17/03/2014	11/03/2016	Residential	No	400	09/09/2016	0	0	Unknown	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1538	PLHP 2	Homes England	Phase 2, Grappenhall Heys	Land South of Astor Drive, East of Lichfield Avenue &, South of Witherwin Avenue, Grappenhall Heys, Warrington	WA4 3HJ	Warrington	North West	2019/2020	220	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1539	PLHP 2	Homes England	Old Park Phase 1 And 2, Telford	Land between, Colliers Way & Park Lane, Old Park, Telford, Shropshire	TF3 4TD	Telford and Wrekin	West Midlands	2019/2020	82	Planning stage	TWC/2019/0504	18/06/2019	09/03/2020	Residential	No	82	x	0	0	Yes	Yes	0	0	0	0	21	0	0	0	0	0	0	0	0
PSLR1540	PLHP 2	Homes England	Carrwood Road	Land off Carrwood Road, Preston	PR5 4LH	South Ribble	North West	2019/2020	63	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1541	PLHP 2	Homes England	Site V Cottam, Preston	Land adjacent to Cottam between Hoyles Lane Sidgreaves Lane Lea Road and Lancaster Canal - Cottam Hall Lea Preston	PR4 0WD	Preston	North West	2019/2020	124	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1542	PLHP 2	Homes England	Tower Street (904056)	Land at Tower Street, St Peter Street, East bank of the River Hull (South)	HU1 1QE	Kingston upon Hull	Yorkshire and The Humber	2019/2020	200	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1543	PLHP 2	Homes England	Rough Park 3	Land south of Newcomen Way, Woodside, Telford, Shropshire	TF7 5UB	Telford and Wrekin	West Midlands	2019/2020	55	Planning stage	TWC/2018/1019	26/03/2019	07/01/2020	Residential	No	55	x	0	0	Yes	Yes	x	x	x	x	14	0	0	0	0	0	0	0	0
PSLR1544	PLHP 2	Homes England	Plots- Moor Farm, Majestic Way	Land west of Lawford Close, Off Majestic Way, Aqueduct, Telford, Shropshire	TF4 3SN	Telford and Wrekin	West Midlands	2019/2020	39	Planning stage	TWC/2019/0487	14/06/2019	10/03/2020	Residential	No	39	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1545	PLHP 2	Homes England	Whittingham Employment Park	Former Whittingham Hospital Site, Whittingham Lane, Whittingham, Preston, Lancashire	PR3 2JE	Preston	North West	2019/2020	232	Planning stage	06/2019/0365	27/03/2019	x	Mixed	Yes	750	x	x	x	Unknown	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1546	PLHP 2	Homes England	Chatham Maritime - Interface Land		ME4 3ER	Medway	South East	2019/2020	274	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1547	PLHP 2	Homes England	Land at Horton Lane, Plot A - Lot 1	Land between Horton Farm, 35 & 36 Horton Lane, Horton, Telford	TF6 6DT	Telford and Wrekin	West Midlands	2019/2020	3	Development started	TWC/2017/0744	13/09/2017	08/11/2017	Residential	No	5	16/07/2018	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1548	PLHP 2	Homes England	East Sheepfolds Ind Est -Doyle (2387) No1 Hay Street (2388) 1 Stobart Street, (2403) 26 Wilson Street (2407)		SR5 1SN	Sunderland	North East	2019/2020	26	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1549	PLHP 2	Homes England	South Sheepfolds Ind Est Easington St Sunderland		SR5 1SN	Sunderland	North East	2019/2020	12	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1550	PLHP 2	Homes England	Site-South Sheepfolds Ind Est Parcel 3		SR5 1SN	Sunderland	North East	2019/2020	20	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1551	PLHP 2	Homes England	Plot L, Coney Green, Clay Cross	Land at, Plot L, Coney Green Business Park, Coney Green Road, Clay Cross	S45 9JW	North East Derbyshire	East Midlands	2019/2020	84	Planning stage	16/01260/OL	03/12/2016	15/04/2019	Residential	No	84	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1552	PLHP 2	Homes England	Laindon Link, Basildon		SS155AB	Basildon	East	2019/2020	14	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1553	PLHP 2	Homes England	Site C & E Paradise Fields		HP2 4LH	Dacorum	East	2019/2020	43	Planning stage	4/01255/01/OUT0	16/07/2001	x	Mixed	No	x	x	x	x	Unknown	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1554	PLHP 2	HE Transfers	Fareham Magistrates' Court		PO1 67SB	Fareham	South East	2019/2020	45	Planning stage	P/18/1261/OA	05/11/2018	x	Residential	No	45	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x
PSLR1555	PLHP 2	Homes England	Newbury Magistrates' Court		RG145QS	West Berkshire	South East	2019/2020	25	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1556	PLHP 2	Homes England	South Omega Zone 2		WA5 3XA	Warrington	North West	2019/2020	300	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1557	PLHP 2	Homes England	Sandymoor North Phase 4		WA7 1XJ	Halton	North West	2019/2020	43	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1558	PLHP 2	DHSC	Part of Central Middlesex Hospital	Central Middlesex Hospital, Acton Lane, London	NW10 7NS	Brent	London	2019/2020	158	Planning stage	20/0031/FUMOPDC	03/03/2020	x	Mixed	No	158	x	x	x	Yes	Yes	24	x	134	x	x	x	x	x	x	x	x	x	x
PSLR1559	PLHP 2	DHSC	Land previously known as Bramham Ambulance Station	Land previously known as Bramham Ambulance Station Bowcliffe Road, Almshouse Hill, Bramham North Yorkshire	LS23 6QY	Leeds	Yorkshire and The Humber	2019/2020	24	Planning stage	18/01609/FU	12/03/2018	07/02/2020	Residential	No	24	x	0	0	Yes	Yes	x	x	6	8	x	0	0	0	0	0	0	0	0
PSLR1560	PLHP 2	DHSC	Hawthorn Clinic	Hawthorn Clinic, Hawthorn Road, Rochester	, ME2 2HU	Medway	South East	2019/2020	9	Planning stage	MC/19/25400	25/09/2019	04/12/2019	Residential	No	9	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1561	PLHP 2	DHSC	Mandeville Health Centre	Saint Albans	AL1 2LE	St Albans	East	2019/2020	4	Planning stage	5/2019/3185	18/12/2019	14/02/2020	Residential	No	4	x	0	0	Yes	Unknown	0	0	0	0	0	0	0	0	0	0	0	0	0
PSLR1562	PLHP 2	DHSC	Sydervelt Lodge	2b Sydervelt Road, Canvey Island	SS8 9EG	Castle Point	East	2019/2020	1	Planning stage	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x	x
PSLR1564	PLHP 2	DHSC	Priory Day Park	Hawkeys Lane, North Shields	NE29 0SF	North Tyneside	North East	2019/2020	26	Planning stage	19/01388/FUL	26/10/2019	x	Mixed	No	18	x	x	x	Yes	Unknown	0	0	0	0	0	x	x	x	x	x	x	x	x

## Annex_D
Public Land for Housing Programme 2015-20 Concluding Summary Report 2022
Annex D: Basic information on 4% of sites sold through both the 2011-15 and 2015-20 Public Land for Housing Programmes up to the end of March 2020 with unvalidated data or data under further investigation.

Detailed site information is not provided where ambiguity existed around the exact extent of the public sector site boundary, these sites are listed here. For example where; / • The complex nature of the way sites are parcelled up and sold off means there is potential for listed sites to overlap and be double counted, or / • Identification of all relevant planning application documents, historic mapping, and Land Registry records, for a given site proved difficult. / Disposing departments and local authorities have been contacted on a site-by-site basis in instances where uncertainty as to correct site boundary or planning application exists. In many cases, but not all, this has led to a resolution.

Unique ref	Sold by dept	Site name	Site address	Site postcode	Local authority	Region	Disposal year	Forecast housing capacity	Known data issue	Actions being taken to resolve issue
PSLR0019a	MoD	Barracks, 5 sites: SITE C, Cavalry and Le Cateau Barracks: central section	Colchester, Essex	CO2 7AP	Colchester	East	Before 2011	4	Planning status unclear	Planning application being investigated
PSLR0019b	MoD	Barracks, 5 sites: SITE C, Cavalry and Le Cateau Barracks: central section	Colchester, Essex	CO2 7AP	Colchester	East	Before 2011	4†	Planning status unclear	Planning application being investigated
PSLR0023ab	MoD	Bordon Masterplanning, Bordon	Bordon Garrison, Bordon, Hampshire	GU35 9QE	East Hampshire	South East	2014/2015	2400†	Duplicate Site	These have been removed from over all numbers
PSLR0023ad	MoD	Bordon Masterplanning, Bordon	Bordon Garrison, Bordon, Hampshire	GU35 9QE	East Hampshire	South East	2014/2015	2400†	Duplicate Site	These have been removed from over all numbers
PSLR0057b	MoD	Government Pipeline Storage System, Swanvale, (combined Navy and BPA site)	Falmouth PSD, Hillside Road, Swanvale, Cornwall	TR115GD	Cornwall	South West	Before 2011	50†	Build out numbers are higher than those in the planning application	Build out is being reviewed
PSLR0091	MoD	Oxford TAC (The Slade), Slade Park, Headington	Slade Park, Headington, Oxford	OX3 8GE	Oxford	South East	Before 2011	3	Planning status unclear	Planning application being investigated
PSLR0134	MoD	RNAS Portland, Land at the Verne	Portland	DT5 1EY	Weymouth and Portland	South West	Before 2011	127	Site boundaries unknown	Further investigation into site boundary
PSLR0137	MoD	Salisbury SFA, Misc Land at Bulbridge	Bulbridge, Wilton, Wiltshire	SP2 0ND	Wiltshire	South West	2013/2014	45	Site boundaries unclear	Site boundary polygon is being reviewed
PSLR0145a	MoD	Tidworth Garrison, Wiltshire	Tidworth	SP9 7LX	Wiltshire	South West	Before 2011	500	Duplicate Site	These have been removed from over all numbers
PSLR0232	Homes England	Chatham Maritime	Chatham	ME4 3JG	Medway	South East	2012/2013	42	Planning status unclear	Planning application being investigated
PSLR0243b	Homes England	Graylingwell, Chichester	Chichester	PO196EA	Chichester	South East	2019/2020	4†	Site boundaries unknown	Further investigation into site boundary
PSLR0243c	Homes England	Graylingwell, Chichester	Chichester	PO196EA	Chichester	South East	2019/2020	4†	Site boundaries unknown	Further investigation into site boundary
PSLR0243d	Homes England	Graylingwell, Chichester	Chichester	PO196EA	Chichester	South East	2019/2020	4†	Site boundaries unknown	Further investigation into site boundary
PSLR0243e	Homes England	Graylingwell, Chichester	Chichester	PO196EA	Chichester	South East	2019/2020	4†	Site boundaries unknown	Further investigation into site boundary
PSLR0243f	Homes England	Graylingwell, Chichester	Chichester	PO196EA	Chichester	South East	2019/2020	4†	Site boundaries unknown	Further investigation into site boundary
PSLR0243g	Homes England	Graylingwell, Chichester	Chichester	PO196EA	Chichester	South East	2019/2020	4†	Site boundaries unknown	Further investigation into site boundary
PSLR0264	Homes England	Trevenson Park South - Custom Build	Redruth	TR15 3SP	Cornwall	South West	2014/2015	144	Duplicate Site	These have been removed from over all numbers
PSLR0281	Homes England	Sandymoor North	Runcorn	WA7 1QU	Halton	North West	Unknown	30	Site boundaries unknown	Further investigation into site boundary
PSLR0301	DEFRA	Land at School Lane/Shay Lane, Walton,	Walton	WF2 6NY	Wakefield	Yorkshire and The Humber	2012/2013	150	Site boundaries unknown	Further investigation into site boundary
PSLR0302	DEFRA	Travis Perkins, Harrow Road,	Westminster	W2 6NA	Westminster	London	2012/2013	135	Site ownership	Clarification being sought from department
PSLR0328	DEFRA	Land at Ashton Basin, Preston	Preston	PR2 2DB	Preston	North West	2012/2013	12	Site boundaries unknown	Further investigation into site boundary
PSLR0346	DEFRA	Travis Perkins, Harrow Road,	Harrow Road	NW10 5NY	Brent	London	Before 2011	109	Site ownership	Clarification being sought from department
PSLR0349b	DEFRA	Land at HRI Littlehampton,	West Sussex	BN176FL	Arun	South East	Before 2011	65†	Build out numbers are higher than those in the planning application	Planning application and build out figures being reviewed.
PSLR0351	DEFRA	Yardley Wood Road, Birmingham	Birmingham	B14 4BS	Birmingham	West Midlands	Before 2011	15	Site boundaries unknown	Further investigation into site boundary
PSLR0352	DEFRA	Hanwell	Hanwell	W7 2QA	Ealing	London	Before 2011	10	Site boundaries unknown	Further investigation into site boundary
PSLR0353	DEFRA	Fields at Littleton, Shepperton, Weybridge	Shepperton	TW170QG	Spelthorne	South East	Before 2011	5	Site boundaries unknown	Further investigation into site boundary
PSLR0373	DfT	Woodgrange Road	Woodgrange Road, Forest Gate, London	E7Ã‚Â 0QR	Newham	London	2013/2014	20	Site boundaries unknown	Further investigation into site boundary
PSLR0393	DfT	Land off Sheffield Road	Penistone	S36 6BF	Barnsley	Yorkshire and The Humber	Before 2011	43	Site boundaries unknown	Further investigation into site boundary
PSLR0429	GLA	Catford	Lewisham	SE6 4BS	Lewisham	London	2013/2014	589	Build out numbers are higher than those in the planning application	Planning application number being investigated
PSLR0480	DHSC	Almond Villa	31- 33 The Broadway, Almond Villa, Knaphill Woking	GU21 2DR	Woking	South East	2012/2013	10	Duplicate Site	These have been removed from over all numbers
PSLR0485	DHSC	Ash House	Brimble Hill, Wroughton, Swindon	SN4 0RA	Swindon	South West	2012/2013	6	Planning polygons are not accurate	Planning polygon boundaries are being investigated
PSLR0497	DHSC	Bartlet Hospital & Bartlet Annex, Felixstowe	Felixstowe	IP11 7SN	Suffolk Coastal	East	Before 2011	40	Build out numbers are higher than those in the planning application	Reviewing build out numbers
PSLR0498	DHSC	Bartlett Hospital and Annexe	Undercliff Road East, Felixstowe, Suffolk	IP11 7LT	Suffolk Coastal	East	2012/2013	31	Duplicate Site	These have been removed from over all numbers
PSLR0524	DHSC	Buckingham Park	Weedon Hill, Buckingham Road, Aylesbury	HP199BU	Aylesbury Vale	South East	Before 2011	200	Site boundaries unknown	Further investigation into site boundary
PSLR0552	DHSC	Darlington Memorial Hospital	Woodland Road, Darlington	DL3 6RT	Darlington	North East	2013/2014	10	Site boundaries unknown	Further investigation into site boundary
PSLR0562	DHSC	East Ardsley Health Centre	Wakefield	WF3 2DN	Wakefield	Yorkshire and The Humber	Before 2011	10	Duplicate Site	These have been removed from over all numbers
PSLR0624	DHSC	Kingswood Land	Land on the east side of Barnes way, Richmond way, Kingswood	HU7 3JQ	Kingston upon Hull	Yorkshire and The Humber	2014/2015	65	Site boundaries unknown	Further investigation into site boundary
PSLR0632	DHSC	Land at Brambletye Park Road, Redhill	Land at Brambletye Park Road, Redhill	RH1 6RR	Reigate and Banstead	South East	2012/2013	5	Site boundaries unknown	Further investigation into site boundary
PSLR0634	DHSC	Land at Harps Close	Waldingfield Road, Sudbury	CO10 1YU	Babergh	East	2014/2015	25	Duplicate Site	These have been removed from over all numbers
PSLR0635a	DHSC	Land at Haygate Road, Wellington	Telford	TF1 1RU	Telford and Wrekin	West Midlands	2011/2012	2	Build out numbers are higher than those in the planning application	Planning application and build out figures being reviewed.
PSLR0635b	DHSC	Land at Haygate Road, Wellington	Telford	TF1 1RU	Telford and Wrekin	West Midlands	2011/2012	2†	Backwards move in planning status	Planning status being investigated.
PSLR0648	DHSC	Lavender Road	Middlesbrough	TS3 7AG	Middlesbrough	North East	2013/2014	1	Site boundaries unknown	Further investigation into site boundary
PSLR0655	DHSC	Little Plumstead Hospital	Norwich	NR135GA	Broadland	East	Before 2011	75	Duplicate Site	These have been removed from over all numbers
PSLR0656a	DHSC	London Road Community Hospital 2	London Road, Derby	DE1 2QY	Derby	East Midlands	2014/2015	290	Duplicate Site	These have been removed from over all numbers
PSLR0656b	DHSC	London Road Community Hospital 2	London Road, Derby	DE1 2QY	Derby	East Midlands	2014/2015	290†	Duplicate Site	These have been removed from over all numbers
PSLR0657a	DHSC	London Road Community Hospital 2	London Road, Derby	DE1 2QY	Derby	East Midlands	2014/2015	280	Duplicate Site	These have been removed from over all numbers
PSLR0657b	DHSC	London Road Community Hospital 2	London Road, Derby	DE1 2QY	Derby	East Midlands	2014/2015	280†	Duplicate Site	These have been removed from over all numbers
PSLR0678a	DHSC	Moneyhull Hospital (earlier sale)	Birmingham	B30 3PS	Birmingham	West Midlands	Before 2011	170	Build out numbers are higher than those in the planning application	Planning application and build out figures being reviewed.
PSLR0678c	DHSC	Moneyhull Hospital (earlier sale)	Birmingham	B30 3PS	Birmingham	West Midlands	Before 2011	170†	Build out numbers are higher than those in the planning application	Planning application and build out figures being reviewed.
PSLR0689	DHSC	Norfolk & Norwich Hospital	Norwich	NR2 2TA	Norwich	East	Before 2011	199	Build out numbers are higher than those in the planning application	Planning application number being investigated
PSLR0691	DHSC	North Tyneside General Hospital	Rake Lane, North Shields, Tyne & Wear	NE29 9QL	North Tyneside	North East	2014/2015	58	Duplicate Site	These have been removed from over all numbers
PSLR0692	DHSC	Northern View, Rodley Avenue, Bradford	Rodley Avenue, Bradford	BD6 1AA	Bradford	Yorkshire and The Humber	Before 2011	150	Duplicate Site	These have been removed from over all numbers
PSLR0697	DHSC	Oak House (Ground Floor)	Brimble Hill, Wroughton, Swindon	SN4 0RA	Swindon	South West	2012/2013	4	Planning polygons are not accurate	Planning polygon boundaries are being investigated
PSLR0715	DHSC	Pershore Cottage Hospital	Defford Road, Pershore, Worcestershire	WR10 1HZ	Wychavon	West Midlands	2014/2015	25	Duplicate Site	These have been removed from over all numbers
PSLR0754a	DHSC	Shelton Hospital	Bicton Heath, Shrewsbury, Shropshire	SY3 8DN	Shropshire	West Midlands	2013/2014	194	Duplicate Site	These have been removed from over all numbers
PSLR0754c	DHSC	Shelton Hospital	Bicton Heath, Shrewsbury, Shropshire	SY3 8DN	Shropshire	West Midlands	2013/2014	194†	Duplicate Site	These have been removed from over all numbers
PSLR0754d	DHSC	Shelton Hospital	Bicton Heath, Shrewsbury, Shropshire	SY3 8DN	Shropshire	West Midlands	2013/2014	194†	Duplicate Site	These have been removed from over all numbers
PSLR0768	DHSC	St Bernards Wing 2	St Bernards Site, Uxbridge Road, Southall	UB1 3EU	Ealing	London	2014/2015	93	Build out numbers are higher than those in the planning application	Planning application and build out figures being reviewed.
PSLR0835	DHSC	Warley Hospital	Pastoral Way	CM14 5GG	Brentwood	East	Before 2011	13	Build out numbers are higher than those in the planning application	Site polygon needs to be reviewed in line with planning application.
PSLR0862	Thurrock Council	Schoolfield Road Part 2	Thurrock	RM20 3AP	Thurrock	East	2012/2013	200	Duplicate Site	These have been removed from over all numbers
PSLR0867	LLDC	Sugar House Lane	Newham	E15 2QS	Newham	London	Before 2011	600	Site boundaries unknown	Further investigation into site boundary
PSLR0874	MoJ	Latchmere House	Church Road, Ham Common, Richmond, Surrey	TW10 5HH	Richmond upon Thames	London	2012/2013	40	Build out numbers are higher than those in the planning application	Planning application and build out figures being reviewed.
PSLR0940	Royal Mail	Sutton Coldfield Delivery Office	Sutton Park Station, Sutton Coldfield, Birmingham	B73 6AE	Birmingham	West Midlands	2013/2014	27	Build out numbers are higher than those in the planning application	Planning application and build out figures being reviewed.
PSLR0949	DfE	Castle View House	Castle View House East Lane Runcorn Cheshire WA7 2DN	WA7 2DN	Halton	North West	2015/2016	188	Build out numbers are higher than those in the planning application	Planning application and build out figures being reviewed.
PSLR0975	DHSC	70-71 Swanmore Road	70-71 SWANMORE ROAD RYDE ISLE OF WIGHT PO33 2TF	PO33 2TF	Isle of Wight	South East	2015/2016	3	Build out numbers are higher than those in the planning application	Planning application and build out figures being reviewed.
PSLR0997	DHSC	GROVES CHAPEL	GROVES CHAPEL UNION TERRACE YORK YO31 7EW	YO317EW	York	Yorkshire and The Humber	2016/2017	16	Backwards move in planning status	Planning status being investigated.
PSLR1008	DHSC	Postern House	POSTERN HOUSE CHERRY ORCHARD MARLBOROUGH SN8 4AS	SN8 4AS	Wiltshire	South West	2016/2017	13	Build out numbers are higher than those in the planning application	Planning application and build out figures being reviewed.
PSLR1050	Homes England	Chatham Maritime - SMI Final Sectors	ME4 3ER	ME4 3ER	Medway	South East	2016/2017	309	Build out numbers are higher than those in the planning application	Planning application and build out figures being reviewed.
PSLR1112	Homes England	Severalls Hospital - Colchester - Phase 2	CO4 5HG	CO4 5HG	Colchester	East	2015/2016	202	Partial overlap with another site	Other site, PSLR1006, included while sites are further investigated
PSLR1117	Homes England	Spittal Quay, Berwick-Upon-Tweed	TD151RE	TD151RE	Northumberland	North East	2016/2017	15	Site boundaries unknown	Further investigation into site boundary
PSLR1290	DHSC	Fulbeck Grange	Fulbeck Grange Fulbeck Morpeth Northumberland	NE61 3JU	Northumberland	North East	2018/2019	13	Duplicate Site	These have been removed from over all numbers
PSLR1433b	DHSC	DRI London Road Derby	Derbyshire Royal Infirmary N H S Trust, London Road, Derby	DE1 2QY	Derby	East Midlands	2019/2020	796	Duplicate Site	These have been removed from over all numbers
PSLR1433c	DHSC	DRI London Road Derby	Derbyshire Royal Infirmary N H S Trust, London Road, Derby	DE1 2QY	Derby	East Midlands	2019/2020	796†	Duplicate Site	These have been removed from over all numbers

## Annex_E
Public Land for Housing Programme 2015-20 Concluding Summary Report 2022
Annex E: Explanations for sites with double underline

Unique ref	Sold by dept	Site name	Site address	Site postcode	Local authority	Region	Disposal year	Forecast housing capacity	Known data issue	Actions being taken to resolve issue
PSLR0016c	MoD	Barracks, 5 sites: Balance of units	Colchester, Essex	CO2 7QG	Colchester	East	Before 2011	400†	Build out numbers are higher than those in the planning application	Planning application being investigated
PSLR0045	MoD	Deysbrook Barracks	Liverpool	L12 4YW	Liverpool	North West	Before 2011	27	Build out numbers are higher than those in the planning application	Planning application being investigated
PSLR0051c	MoD	Farnborough, Queens Gate, Government House Road, Aldershot	Aldershot	GU146FD	Rushmoor	South East	Before 2011	200†	Appears to have started	Status being reviewed
PSLR0063	MoD	Hilton JV	Hilton, Derby	DE655HY	South Derbyshire	East Midlands	Before 2011	165	Corrected from last publication	This amendment resulted in the planning category being changed
PSLR0074	MoD	Main site Ensleigh	Lansdown Road, Bath, Avon	BA1 5AB	Bath & NE Somerset	South West	2012/2013	300	Affordable housing data unclear	Clarification on type of affordable housing being sought
PSLR0089a	MoD	OSU Liphook,	Midhurst Road, Liphook	GU307TG	East Hampshire	South East	Before 2011	128	Build out numbers are higher than those in the planning application	Planning application being investigated
PSLR0098a	MoD	RAF Cardington, Bedford (first phases)Ã‚Â	Bedford	MK420GL	Bedford	East	Before 2011	200	Marked as incomplete but seems complete	Status being reviewed
PSLR0105	MoD	RAF HendonÃ‚Â	East Camp tranches, Barnet	NW9 5JE	Barnet	London	Before 2011	200	Marked as incomplete but seems complete	Status being reviewed
PSLR0126	MoD	RAF West Drayton	West Drayton	UB7 9FR	Hillingdon	London	Before 2011	200	Build out numbers are higher than those in the planning application	Planning application being investigated
PSLR0133	MoD	RM Turnchapel, Barton Road, Plymouth	Plymouth	PL9 9SY	Plymouth	South West	2013/2014	20	Site boundary polygon showing government land	Amendments to polygon being made
PSLR0136b	MoD	Saighton Camp (future phases)	Chester	CH3 6DH	Cheshire West and Chester	North West	Before 2011	200†	Planning status unclear	Planning application being investigated
PSLR0142	MoD	Three Rivers Volunteer Est, HMS Wildfire (Brackenhill House)	The Woods, Northwood, Hertfordshire	HA6 3EX	Three Rivers	East	2011/2012	2	Marked as incomplete but seems complete	Status being reviewed
PSLR0207	Homes England	Manor/Kingsway Hospital,	Derby	DE223XB	Derby	East Midlands	2013/2014	700	Backwards move in planning status	Planning application number to be updated with new one.
PSLR0227	Homes England	Mere Bank	Greenbank Drive, Liverpool	L17 1AE	Liverpool	North West	2013/2014	73	Build out numbers are higher than those in the planning application	Planning application being investigated
PSLR0339d	DEFRA	Diglis Basin, Worcester phase 2	Worcester	WR5 3BX	Worcester	West Midlands	Before 2011	323†	Build out numbers are higher than those in the planning application	Planning application being investigated
PSLR0339f	DEFRA	Diglis Basin, Worcester phase 2	Worcester	WR5 3BX	Worcester	West Midlands	Before 2011	323†	Build out numbers are higher than those in the planning application	Planning application being investigated
PSLR0348	DEFRA	Tower Wharf, Chester	Chester	CH1 4EJ	Cheshire West and Chester	North West	Before 2011	88	Build out numbers are higher than those in the planning application	Planning application being investigated
PSLR0364a	DfT	400 Caledonian Road	400 Caledonian Road, Islington	N1 1DN	Islington	London	2012/2013	23	Build out numbers are higher than those in the planning application	Planning application being investigated
PSLR0385	DfT	Plot J (2)	King's Cross Opportunity Area, York Way	N1C 4AA	Camden	London	Before 2011	104	Build out numbers are higher than those in the planning application	Planning application being investigated
PSLR0426	GLA	Saint Clements	Tower Hamlets	E3 4QL	Tower Hamlets	London	2012/2013	223	Build out numbers are higher than those in the planning application	Planning application being investigated
PSLR0435	DHSC	1 - 21 Heatherstones	Queensgate, Halifax	HX3 0DH	Calderdale	Yorkshire and The Humber	2013/2014	21	Build out numbers are higher than those in the planning application	Planning application being investigated
PSLR0464	DHSC	69 Oakley Square	69 Oakley Square, London. Greater London	NW1 1NJ	Camden	London	2013/2014	6	Marked as incomplete but seems complete	Status being reviewed
PSLR0528	DHSC	Cavendish House	18 Victoria Road, Southsea, Portsmouth,	PO5 2BZ	Portsmouth	South East	2014/2015	15	Planning status states witdrawn	Site being investigated
PSLR0546	DHSC	Constable Road	Constable Road, Felixstowe	IP11 7HJ	Suffolk Coastal	East	2014/2015	5	Build out numbers are higher than those in the planning application	Planning application being investigated
PSLR0592	DHSC	Hackney Nurses Home	Kenworthy Rd, Hackney	E9 5GX	Hackney	London	Before 2011	200	Build out higher than planning	Planning application being investigated
PSLR0665a	DHSC	Macclesfield District General Hospital	Macclesfield	SK103GR	Cheshire East	North West	Before 2011	50	Build out numbers are higher than those in the planning application	Planning application number being investigated
PSLR0735	DHSC	Redcliffe Day Hospital	49-51 Hatton Park Road, Wellingborough, Northamptonshire	NN8 5AH	Wellingborough	East Midlands	2014/2015	4	Marked as incomplete but seems complete	Status being reviewed
PSLR0779a	DHSC	St Mary's Hospital, Green Lane, Stannington	Stannington	NE61 6BL	Northumberland	North East	Before 2011	172	Partial overlap with 779c	Further investigation into site boundary
PSLR0779c	DHSC	St Mary's Hospital, Green Lane, Stannington	Stannington	NE61 6BL	Northumberland	North East	Before 2011	172†	Partial overlap with 779a	Further investigation into site boundary
PSLR0864a	LLDC	ODA Olympic Village including 6 development plots	Newham	E20 1YY	Newham	London	2013/2014	4893	Build out numbers are higher than those in the planning application	Residential sales as part of site polygon, site build out is being reviewed
PSLR0864d	LLDC	ODA Olympic Village including 6 development plots	Newham	E20 1YY	Newham	London	2013/2014	4893†	Build out numbers are higher than those in the planning application	Planning application being investigated
PSLR0865a	LLDC	Olympic: Phase 1 (Chobham Manor)	Newham	E15 2EE	Newham	London	2013/2014	828	Build out numbers are higher than those in the planning application	Planning application being investigated
PSLR0866	LLDC	Olympic: Phase 2	Newham	E15 2EE	Newham	London	2014/2015	1500	Affordable housing data unclear	Clarification on type of affordable housing being sought
PSLR0929	Royal Mail	Coton House	Coton House, Rugby, Warwickshire	CV23 0AA	Rugby	West Midlands	2012/2013	30	Build out numbers are higher than those in the planning application	Planning application being investigated
PSLR0944a	Crown Estate	Dunster Marsh	Dunster, Minehead, Somerset	TA24 6PH	Somerset West and Taunton	South West	2014/2015	54	Build out numbers are higher than those in the planning application	Planning application being investigated
PSLR0996	DHSC	Frimley Children's Centre	FRIMLEY CHILDREN'S CENTRE CHURCH ROAD GU16 7AD	GU16 7AD	Surrey Heath	South East	2015/2016	63	Affordable housing data unclear	Clarification on type of affordable housing being sought
PSLR1006	DHSC	Old Severalls Hospital	OLD SEVERALLS HOSPITAL BOXTED ROAD COLCHESTER	C04 5HG	Colchester	East	2015/2016	547	Partial overlap with PSLR1112	fUrther investigation into site boundary. PSLR1112 not included.
PSLR1283	MoJ	Wigston, Station Road	26-28 Station Road, Wigston, Leicestershire	LE18 2DH	Oadby and Wigston	East Midlands	2017/2018	6	Build out numbers are higher than those in the planning application	Planning application being investigated