Public Service Delivery Review Board minutes of meeting

Meeting date: 07 Dec 2021, hosted remotely via Google Meet.
Attended: Sue Bateman (CDDO), Heather Neate (CDDO), Patrick Kiernan (CDDO), Ebru Yilmaz (CDDO), Albert King (Scottish Government), Jack Ramsden (BEIS), Mark Brewin (HMRC), Glyn Jones (Welsh Government), Ross Young (UKSA), Stephen Mak (DLUHC), Tom Griffiths (DLUHC), Edgar Whitley (PCAG), Debra Heaton (ICO), Andy Gregory (Home Office), Louise Bennett (PCAG), Vicky Chico (NDG, Emma Wharram (DfE), Jennifer Boon (NHSX/DHSC)
Speakers: Patrick Kiernan (CDDO), Cath Halas (ICO), Eve Wright (ICO)
Apologies: Helen Walker (DWP), Harry Lee (DCMS), Tim Adams (LGA)

1	Welcome and introduction from the Chair
1.1	The Chair welcomed Members to the meeting
2	Conflicts of interest, minutes, and actions brought forward
2.1	Members reported no conflict of interests. / Minutes from the last meeting on 14 September 2021 were approved. / Action points 23, 24, 26 were closed. / Action points 39, 41, 42, 45, 46, 48, 49, 50 were agenda items. / Action points 43 carried forward to the next meeting. / Action point 51: Secretariat to publish minutes from September 14 2021 meeting
3	Paper 4 (Work programme update)
3.1	Members heard an update on the Scottish early learning and childcare objective proposal. The public consultation is expected to start on 10th January 2022, running for a period of 8 weeks until 7th March 2022.
3.2	Members heard an update on identity verification services proposal submitted by GDS. Members are in agreement that the proposal should be recommended to the Minister to take forward into legislation. The next stage is to seek Ministerial approval. / Action point 52: Secretariat to keep members informed of the Minister’s decision on the identity verification services proposal.
3.3	Members heard an update on the potential new objectives for early help and prevention and pre and post emergency planning. Secretariat informed members of work being undertaken to gather use cases and to define the criteria for future data sharing.
3.4	The secretariat continues to work with departments to define data sharing criteria for a potential objective to re-unite citizens with their dormant assets.
3.5	The secretariat provided an update to members on the review of the process to establish a new objective in regulations and the supporting glossary of terms. / Action point 53: Secretariat to publish the process review glossary to gov.uk when complete.
3.6	The public consultation on Data: a new direction closed on 19 November 2021. DCMS expects to publish the government response in early 2022, this will include the government response to the proposed amendment to include business outcomes in the scope of the public service delivery power.
3.7	Members heard an update of the work of the Digital Economy Act 2017 Policy Leads, including the agreed terms of reference.
3.8	Members agreed Review Board meeting dates for 2022.
4	Risk register
4.1	Members approved new risk to reflect public authorities may under- or overestimate the metrics of data sharing outcomes, leading to reputational damage. / Action point 54: Secretariat to consider adding an additional risk to the register addressing reluctance of some government departments to engage in data sharing / Action point 55: Secretariat to review the National Audit Office report; Evaluating Government Spending
5	ICO update
5.1	Members heard an update from the Information Commissioner's Office in relation to the review of the public service delivery powers. ICO anticipates publishing a report on the review in July 2022. / Action point 56: Secretariat to arrange a separate meeting for members to review the report in due course.
6	Public register presentation
6.1	The Secretariat gave an overview of the 55 new entries to the register of information sharing agreements in quarter two 2021/2022. The analysis provided an update on the use of the public service delivery, civil registration, debt and fraud powers.
6.2	Following a query raised by a Review Board member, the secretariat has established that Camden Council’s entry relates to a forthcoming data share, with the entry being made early in order to fulfil the transparency requirements of the DEA. The secretariat will continue to liaise with Camden to agree the appropriate course of action regarding the entry on the register. / Action Point 57: Secretariat to continue to liaise with Camden council and agree the appropriate course of action regarding their entry on the register of information sharing agreements.
7	AOB
7.1	None raised.
8	DONM 10 March 2022