## Cover_sheet
Annex 1: Humber RBD Flood Risk Management Plan (FRMP) – Summary of progress of implementing the first cycle measures
This spreadsheet states the progress for the first cycle of the Flood risk management plan (FRMP) (2015-2021). The spreadsheet contains the status of each FRMP plan measure, the measure ID, the action owner, the implementation status as of the 31 March 2021. As well as reasons for not progressing if relevant.
Status of the measures
First cycle measures that comprise of the day-to-day work by the Environment Agency and Lead Local Flood Authorities (LLFAs) are transitioned to this second cycle FRMP as ongoing national-level measures. This may be as an individual measure or aggregated with other measures. More information on these measures can be found in Flood Plan Explorer. / Measures may appear differently in the second cycle compared with the first cycle, for example an individual measure in the first cycle may appear as part of a wider programme of work in the second cycle. / Measures that are not transitioned to the second cycle FRMP will continue to be developed or kept under review by the Environment Agency, LLFA and other risk management authorities. This will be done in accordance with the current Flood and Coastal Erosion Risk Management appraisal guidance and funding rules. / Column D contains blank cells when a measure is 'completed' or 'ongoing' in FRMP cycle 1. / Column F contains blank cells when a measure is 'completed' or not transitioned to FRMP cycle 2.
Links to other FRMP resources
Flood Plan Explorer
Humber river basin district flood risk management plan

## FRMP1_annex
Humber FRMP 1 annex
This worksheet contains one table.
Measure ID	Measure Owner	Implementation Status	Reason for not progressing	Transitioned to FRMP2?	Transitioned locally or nationally
ACT017	Rutland Unitary Authority	Superseded	It has been replaced by another measure	N/A
ACT1111	Environment Agency	Completed		N/A
ACT1112	Environment Agency	Ongoing - construction		Yes	Local
ACT1113	Environment Agency	Completed		N/A
ACT1115	Environment Agency	Not started - proposed		Yes	Local
ACT1116	Environment Agency	Not started - proposed		Yes	Local
ACT1117	Environment Agency	Not started - proposed		Yes	Local
ACT1118	Environment Agency	Not started - proposed		Yes	Local
ACT1119	Environment Agency	Not started - proposed		Yes	Local
ACT1120	Environment Agency	Cancelled		N/A
ACT1121	Environment Agency	Cancelled		N/A
ACT1122	Environment Agency	Not started - proposed		Yes	Local
ACT1123	Environment Agency	Ongoing		Yes	Local
ACT1124	Environment Agency	Completed		N/A
ACT1126	Environment Agency	Completed		N/A
ACT1127	Environment Agency	Completed		N/A
ACT1128	Environment Agency	Completed		N/A
ACT1129	Environment Agency	Completed		N/A
ACT1130	Environment Agency	Ongoing		Yes	Local
ACT1131	Environment Agency	Ongoing		Yes	Local
ACT1132	Environment Agency	Ongoing		Yes	Local
ACT1133	Environment Agency	Completed		N/A
ACT1134	Environment Agency	Completed		N/A
ACT1135	Environment Agency	Completed		N/A
ACT1136	Environment Agency	Completed		N/A
ACT1137	Environment Agency	Not started - proposed		Yes	Local
ACT1142	Environment Agency	Ongoing		Yes	Local
ACT1143	Environment Agency	Superseded		N/A
ACT1144	Environment Agency	Not started - proposed		Yes	Local
ACT1145	Environment Agency	Completed		N/A
ACT1149	Environment Agency	Not started - proposed		Yes	Local
ACT1151	Environment Agency	Completed		N/A
ACT1152	Environment Agency	Completed		N/A
ACT1154	Environment Agency	Completed		N/A
ACT1155	Environment Agency	Completed		N/A
ACT1156	Environment Agency	Superseded		N/A
ACT1160	Environment Agency	Ongoing		Yes	Local
ACT1161	Environment Agency	Completed		N/A
ACT1162	Environment Agency	Ongoing - construction		Yes	Local
ACT1163	Environment Agency	Ongoing		Yes	Local
ACT1164	Environment Agency	Ongoing		Yes	Local
ACT1165	Environment Agency	Superseded		N/A
ACT1166	Environment Agency	Ongoing		Yes	Local
ACT1167	Environment Agency	Ongoing		Yes	Local
ACT1174	Environment Agency	Completed		N/A
ACT1178	Environment Agency	Completed		N/A
ACT1180	Environment Agency	Completed		N/A
ACT1181	Environment Agency	Not started - proposed		Yes	Local
ACT1183	Environment Agency	Completed		N/A
ACT1184	Environment Agency	Ongoing - construction		Yes	Local
ACT1185	Environment Agency	Ongoing		Yes	Local
ACT1186	Environment Agency	Ongoing		Yes	Local
ACT1188	Environment Agency	Ongoing		Yes	Local
ACT1191	Environment Agency	Ongoing		Yes	Local
ACT1192	Environment Agency	Ongoing - construction		Yes	Local
ACT1194	Environment Agency	Completed		N/A
ACT1195	Environment Agency	Ongoing		Yes	Local
ACT1198	Environment Agency	Ongoing		Yes	Local
ACT1200	Environment Agency	Completed		N/A
ACT1202	Environment Agency	Ongoing		Yes	Local
ACT1204	Environment Agency	Completed		N/A
ACT1205	Environment Agency	Ongoing - construction		Yes	Local
ACT1207	Environment Agency	Not started - proposed		Yes	Local
ACT1246	Environment Agency	Completed		N/A
ACT1247	Environment Agency	Ongoing	BAU	No
ACT1248	Environment Agency	Ongoing	All reservoirs should have these anyway	No
ACT1249	Environment Agency	Ongoing	Not all the LAs in Yorkshire saw this as a priority	No
ACT1250	Environment Agency	Superseded	Carried forward in most/all of the Yorkshire areas but written in local context	N/A
ACT1251	Environment Agency	Superseded	National to look at	N/A
ACT1252	Environment Agency	Superseded	National to look at & some areas include a measure about working in parternship with YW	N/A
ACT1253	Environment Agency	Ongoing	Not a priority measure	No
ACT1254	Environment Agency	Ongoing	BAU	No
ACT1255	Environment Agency	Superseded	Some LAs included measure re:telemetry - others didn’t see it as a priority	N/A
ACT1256	Environment Agency	Superseded	Some LAs included it as a neasure - others didn’t see it as a priority/BAU	N/A
ACT1257	Environment Agency	Superseded	Included as part of other more strategic measures	N/A
ACT1808	Environment Agency	Completed		N/A
ACT1809	Environment Agency	Completed		N/A
ACT1810	Environment Agency	Superseded		N/A
ACT1811	Environment Agency	Not started - proposed		Yes	Local
ACT1812	Environment Agency	Not started - proposed		Yes	Local
ACT1815	Environment Agency	Not started - proposed		Yes	Local
ACT1816	Environment Agency	Ongoing		Yes	Local
ACT1817	Environment Agency	Ongoing		Yes	Local
ACT1818	Environment Agency	Ongoing		Yes	Local
ACT1819	Environment Agency	Not started - proposed		Yes	Local
ACT1820	Environment Agency	Superseded		N/A
ACT1821	Environment Agency	Completed		N/A
ACT1822	Environment Agency	Superseded		N/A
ACT1823	Environment Agency	Superseded		N/A
ACT1825	Environment Agency	Superseded		N/A
ACT1826	Environment Agency	Superseded		N/A
ACT1828	Environment Agency	Superseded		N/A
ACT1829	Environment Agency	Ongoing - construction		Yes	Local
ACT1831	Environment Agency	Superseded		N/A
ACT1832	Environment Agency	Not started - proposed		Yes	Local
ACT1833	Environment Agency	Completed		N/A
ACT1835	Environment Agency	Not started - proposed		Yes	Local
ACT1836	Environment Agency	Superseded		N/A
ACT1842	Environment Agency	Completed		N/A
ACT1849	Environment Agency	Superseded		N/A
ACT1850	Environment Agency	Superseded		N/A
ACT1851	Environment Agency	Superseded	Part of more strategic measures on Bentley and FR asset improvements	N/A
ACT1852	Environment Agency	Superseded	Part of more strategic measures on Bentley and FR asset improvements	N/A
ACT1853	Environment Agency	Superseded	Combined as part of a more strategic measure	N/A
ACT1854	Environment Agency	Completed		N/A
ACT1855	Environment Agency	Superseded	Combined as part of a more strategic measure	N/A
ACT1856	Environment Agency	Superseded	Combined as part of a more strategic measure	N/A
ACT1857	Environment Agency	Superseded	Combined as part of a more strategic measure	N/A
ACT1858	Environment Agency	Superseded	Combined as part of a more strategic measure	N/A
ACT1859	Environment Agency	Completed		N/A
ACT1860	Environment Agency	Superseded	Combined as part of a more strategic measure	N/A
ACT1861	Environment Agency	Completed		N/A
ACT1863	Environment Agency	Completed		N/A
ACT1864	Environment Agency	Ongoing - construction		Yes	Local
ACT1865	Environment Agency	Superseded	Combined as part of a more strategic measure	N/A
ACT1866	Environment Agency	Superseded	Combined as part of a more strategic measure	N/A
ACT1867	Environment Agency	Superseded		N/A
ACT1868	Environment Agency	Ongoing	Slightly reworded	Yes	Local
ACT1869	Environment Agency	Superseded		N/A
ACT1870	Environment Agency	Not started - proposed		No
ACT1871	Environment Agency	Not started - proposed	Not a priority measure	No
ACT1877	Environment Agency	Superseded	Part of wider measure for modelling to better understand FR in South Yorkshire	N/A
ACT1878	Environment Agency	Not started - proposed	Re-written for FRMP2	Yes	Local
ACT1879	Environment Agency	Not started - proposed	Re-written for FRMP2	Yes	Local
ACT1881	Environment Agency	Superseded	Part of wider measure for modelling to better understand FR in South Yorkshire	N/A
ACT1882	Environment Agency	Not started - proposed		Yes	Local
ACT1883	Environment Agency	Superseded	Combined as part of a more strategic measure	N/A
ACT1884	Environment Agency	Superseded	Part of wider measure for modelling to better understand FR in South Yorkshire	N/A
ACT1890	Environment Agency	Ongoing		Yes	Local
ACT1891	Environment Agency	Not started - proposed		No
ACT1892	Environment Agency	Superseded		N/A
ACT1893	Environment Agency	Superseded		N/A
ACT1894	Environment Agency	Superseded		N/A
ACT1895	Environment Agency	Superseded		N/A
ACT1896	Environment Agency	Not started - proposed		No
ACT1897	Environment Agency	Superseded		N/A
ACT1898	Environment Agency	Superseded		N/A
ACT1899	Environment Agency	Superseded		N/A
ACT1901	Environment Agency	Completed		N/A
ACT2305	Birmingham Metropolitan District	Ongoing		Yes	National
ACT2306	Birmingham Metropolitan District	Superseded	It has been replaced by another measure	N/A
ACT2307	Birmingham Metropolitan District	Ongoing		Yes	National
ACT2308	Birmingham Metropolitan District	Ongoing		Yes	National
ACT2321	Dudley Metropolitan District	Ongoing		Yes	National and Local
ACT2322	Sandwell Metropolitan District	Ongoing		Yes	National and Local
ACT2323	Walsall Metropolitan District	Ongoing		Yes	National and Local
ACT2324	Wolverhampton Metropolitan District	Ongoing		Yes	National and Local
ACT2325	Dudley Metropolitan District	Ongoing		Yes	National and Local
ACT2326	Sandwell Metropolitan District	Ongoing		Yes	National and Local
ACT2327	Walsall Metropolitan District	Ongoing		Yes	National and Local
ACT2328	Wolverhampton Metropolitan District	Ongoing		Yes	National and Local
ACT2333	Dudley Metropolitan District	Ongoing		Yes	National and Local
ACT2334	Sandwell Metropolitan District	Ongoing		Yes	National and Local
ACT2335	Walsall Metropolitan District	Ongoing		Yes	National and Local
ACT2336	Wolverhampton Metropolitan District	Ongoing		Yes	National and Local
ACT2337	Dudley Metropolitan District	Ongoing		Yes	National and Local
ACT2338	Sandwell Metropolitan District	Ongoing		Yes	National and Local
ACT2339	Walsall Metropolitan District	Ongoing		Yes	National and Local
ACT2340	Wolverhampton Metropolitan District	Ongoing		Yes	National and Local
ACT2373	Dudley Metropolitan District	Ongoing		Yes	National and Local
ACT2374	Sandwell Metropolitan District	Ongoing		Yes	National and Local
ACT2375	Walsall Metropolitan District	Ongoing		Yes	National and Local
ACT2376	Wolverhampton Metropolitan District	Ongoing		Yes	National and Local
ACT2381	Dudley Metropolitan District	Ongoing		Yes	National and Local
ACT2382	Sandwell Metropolitan District	Ongoing		Yes	National and Local
ACT2383	Walsall Metropolitan District	Ongoing		Yes	National and Local
ACT2384	Wolverhampton Metropolitan District	Ongoing		Yes	National and Local
ACT2394	Cannock Chase District	Ongoing		No
ACT2395	Cannock Chase District	Ongoing		No
ACT2396	Cannock Chase District	Ongoing		No
ACT2397	Cannock Chase District	Ongoing		No
ACT2398	Cannock Chase District	Ongoing		No
ACT2399	Cannock Chase District	Ongoing		No
ACT2402	Cannock Chase District	Ongoing		No
ACT2403	Cannock Chase District	Ongoing		No
ACT2404	Cannock Chase District	Ongoing		No
ACT2405	Cannock Chase District	Ongoing		No
ACT2406	Cannock Chase District	Ongoing		No
ACT2407	Cannock Chase District	Ongoing		No
ACT2408	Cannock Chase District	Ongoing		No
ACT2409	Cannock Chase District	Ongoing		No
ACT2411	Cannock Chase District	Ongoing		No
ACT2412	Cannock Chase District	Ongoing		No
ACT2413	Cannock Chase District	Ongoing		No
ACT2414	Cannock Chase District	Ongoing		No
ACT2415	Cannock Chase District	Ongoing		No
ACT2416	Cannock Chase District	Ongoing		No
ACT2417	Cannock Chase District	Ongoing		No
ACT2418	Cannock Chase District	Ongoing		No
ACT2419	Cannock Chase District	Ongoing		No
ACT2420	East Staffordshire District (B)	Ongoing		No
ACT2421	East Staffordshire District (B)	Ongoing		No
ACT2422	Environment Agency	Ongoing		Yes	National and Local
ACT2423	Environment Agency	Ongoing		Yes	National and Local
ACT2424	Staffordshire Moorlands District	Ongoing		No
ACT2425	Environment Agency	Completed		N/A
ACT2426	Staffordshire County	Completed		N/A
ACT2427	Environment Agency	Ongoing		Yes	Local
ACT2428	Birmingham Metropolitan District	Completed		N/A
ACT2429	Birmingham Metropolitan District	Completed		N/A
ACT2430	Staffordshire County	Ongoing		Yes	Local
ACT2431	Staffordshire Moorlands District	Ongoing		No
ACT2432	Environment Agency	Ongoing		Yes	Local
ACT2433	Staffordshire County	Completed		N/A
ACT2434	Environment Agency	Not started - proposed	It has been postponed	Yes	National
ACT2435	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT2436	Staffordshire County	Not started - proposed	It has been postponed	Yes	Local
ACT2437	Warwickshire County	Ongoing - construction		Yes	Local
ACT2438	Birmingham Metropolitan District	Completed		N/A
ACT2439	Environment Agency	Completed		N/A
ACT2440	Stoke-on-Trent Unitary Authority	Ongoing		Yes	Local
ACT2441	Birmingham Metropolitan District	Superseded	Further work showed it was not viable	N/A
ACT2442	Staffordshire County	Ongoing		Yes	Local
ACT2443	Staffordshire County	Completed		N/A
ACT2444	Staffordshire County	Completed		N/A
ACT2445	Environment Agency	Completed		N/A
ACT2446	Environment Agency	Ongoing		Yes	Local
ACT2447	Staffordshire County	Ongoing - construction		Yes	Local
ACT2448	Staffordshire County	Ongoing		Yes	Local
ACT2449	Staffordshire County	Superseded	It has been included in another piece of work	N/A
ACT2450	Staffordshire County	Not started - proposed	Other - Negotiated improvements through planning role - awaiting confirmation of commencement of development	Yes
ACT2451	Environment Agency	Ongoing - construction		No
ACT2452	Birmingham Metropolitan District	Completed		N/A
ACT2453	Staffordshire County	Completed		N/A
ACT2454	Environment Agency	Ongoing		Yes	Local
ACT2455	Birmingham Metropolitan District	Completed		N/A
ACT2456	Birmingham Metropolitan District	Completed		N/A
ACT2457	Staffordshire County	Ongoing		Yes	Local
ACT2458	Environment Agency	Completed		N/A
ACT2459	Warwickshire County	Completed		N/A
ACT2460	Environment Agency	Ongoing - construction		No
ACT2461	Staffordshire County	Ongoing - construction		Yes	Local
ACT2462	Environment Agency	Ongoing		Yes	Local
ACT2463	Environment Agency	Completed		N/A
ACT2464	Environment Agency	Completed		N/A
ACT2465	Environment Agency	Ongoing		Yes	Local
ACT2466	Birmingham Metropolitan District	Superseded	It has been included in another piece of work	N/A
ACT2467	Environment Agency	Completed		N/A
ACT2468	Environment Agency	Ongoing		Yes	Local
ACT2469	Staffordshire County	Completed		N/A
ACT2470	Environment Agency	Ongoing		Yes	Local
ACT2471	Environment Agency	Ongoing		Yes	National
ACT2472	Environment Agency	Ongoing		Yes	Local
ACT2473	Environment Agency	Ongoing		Yes	Local
ACT2474	Derbyshire County	Ongoing		Yes
ACT2475	Environment Agency	Completed		N/A
ACT2476	Environment Agency	Ongoing		Yes	National
ACT2477	Environment Agency	Ongoing		Yes	Local
ACT2478	Environment Agency	Ongoing		Yes	National
ACT2479	Environment Agency	Ongoing		Yes	National
ACT2480	Environment Agency	Ongoing		Yes	National
ACT2481	Environment Agency	Ongoing		Yes	National
ACT2482	Environment Agency	Completed		N/A
ACT2483	Environment Agency	Ongoing		Yes	National
ACT2484	Environment Agency	Ongoing		Yes	National and Local
ACT2485	Environment Agency	Ongoing		Yes	National
ACT2486	Environment Agency	Ongoing		Yes	National
ACT2487	Environment Agency	Ongoing		Yes	National and Local
ACT2488	Environment Agency	Ongoing		Yes	National
ACT2489	Environment Agency	Ongoing		Yes	National and Local
ACT2490	Environment Agency	Ongoing		Yes	National and Local
ACT2491	Environment Agency	Ongoing		Yes	National and Local
ACT2492	Environment Agency	Ongoing		Yes	National and Local
ACT2493	Environment Agency	Ongoing		Yes	National and Local
ACT2494	Environment Agency	Ongoing		Yes	National and Local
ACT2495	Environment Agency	Ongoing		Yes	National and Local
ACT2496	Environment Agency	Ongoing		Yes	National
ACT2497	Environment Agency	Ongoing		Yes	National and Local
ACT2498	Environment Agency	Ongoing		Yes	National
ACT2499	Environment Agency	Ongoing		Yes	National and Local
ACT2500	Environment Agency	Ongoing		Yes	National
ACT2501	Environment Agency	Ongoing		Yes	National and Local
ACT2502	Environment Agency	Ongoing		Yes	National
ACT2544	Staffordshire Moorlands District	Ongoing		No
ACT2555	Staffordshire Moorlands District	Ongoing		No
ACT2878	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT3842	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT3843	Environment Agency	Not started - proposed		Yes
ACT3844	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT3845	Environment Agency	Completed		N/A
ACT3846	Environment Agency	Completed		N/A
ACT3847	Environment Agency	Completed		N/A
ACT3848	Environment Agency	Completed		N/A
ACT3849	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT3850	Environment Agency	Not started - proposed	It has been replaced by another measure	Yes
ACT3851	Environment Agency	Not started - proposed	It has been replaced by another measure	Yes
ACT3853	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT3854	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT3855	Environment Agency	Completed		N/A
ACT3856	Nottingham Unitary Authority	Completed		N/A
ACT3857	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT3858	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT3859	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT3860	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT3861	Environment Agency	Not started - proposed	It does not yet have funding	Yes
ACT3862	Environment Agency	Ongoing - construction		No
ACT3863	Environment Agency	Ongoing	It has been replaced by another measure	Yes
ACT3864	Environment Agency	Completed		N/A
ACT3865	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT3866	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT3867	Environment Agency	Completed		N/A
ACT3868	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT3869	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT3870	Nottinghamshire County	Completed		N/A
ACT3871	Nottinghamshire County	Completed		N/A
ACT3872	Nottinghamshire County	Completed		N/A
ACT3873	Environment Agency	Not started - proposed	It does not yet have funding	Yes
ACT3874	Environment Agency	Completed		N/A
ACT3875	Environment Agency	Completed		N/A
ACT3876	Environment Agency	Completed		N/A
ACT3877	Leicestershire County	Superseded	Further work showed it was not viable	N/A
ACT3878	Leicestershire County	Not started - proposed	It has been replaced by another measure	Yes
ACT3879	Leicestershire County	Superseded	Further work showed it was not viable	N/A
ACT3880	Leicestershire County	Superseded	It has been replaced by another measure	N/A
ACT3881	Leicester Unitary Authority	Ongoing	It has been replaced by another measure	Yes
ACT3882	Leicester Unitary Authority	Ongoing	It has been replaced by another measure	Yes
ACT3883	Leicester Unitary Authority	Ongoing	It has been replaced by another measure	Yes
ACT3884	Leicester Unitary Authority	Ongoing	It has been replaced by another measure	Yes
ACT3885	Leicester Unitary Authority	Ongoing	It has been replaced by another measure	Yes
ACT3886	Leicester Unitary Authority	Not started - proposed	It has been replaced by another measure	Yes
ACT3887	Leicester Unitary Authority	Not started - proposed	It has been replaced by another measure	Yes
ACT3888	Leicester Unitary Authority	Not started - proposed	It has been replaced by another measure	Yes
ACT3889	Environment Agency	Ongoing	It has been replaced by another measure	Yes
ACT3890	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT3891	Environment Agency	Completed		N/A
ACT3892	Environment Agency	Completed		N/A
ACT3893	Derby Unitary Authority	Not started - proposed	It has been replaced by another measure	Yes
ACT3894	Derby Unitary Authority	Not started - proposed	It has been replaced by another measure	Yes
ACT3895	Derby Unitary Authority	Not started - proposed	It has been replaced by another measure	Yes
ACT3896	Derby Unitary Authority	Not started - proposed	It has been replaced by another measure	Yes
ACT3897	Derby Unitary Authority	Completed		N/A
ACT3957	Environment Agency	Not started - proposed		No
ACT3958	Environment Agency	Not started - proposed		No
ACT3959	Environment Agency	Superseded		N/A
ACT3961	Environment Agency	Completed		N/A
ACT3962	Environment Agency	Completed		N/A
ACT3964	Environment Agency	Completed		N/A
ACT3976	Environment Agency	Superseded		N/A
ACT3977	Environment Agency	Superseded		N/A
ACT3978	Environment Agency	Superseded		N/A
ACT3979	Environment Agency	Not started - proposed		No
ACT3980	Environment Agency	Superseded		N/A
ACT3981	Environment Agency	Not started - proposed		No
ACT3982	Environment Agency	Superseded		N/A
ACT3983	Environment Agency	Superseded		N/A
ACT3984	Environment Agency	Superseded		N/A
ACT3985	Environment Agency	Superseded		N/A
ACT3986	Environment Agency	Not started - proposed		No
ACT3987	Environment Agency	Not started - proposed		No
ACT3988	Environment Agency	Completed		N/A
ACT3989	Environment Agency	Superseded		N/A
ACT3990	Environment Agency	Superseded		N/A
ACT3994	Environment Agency	Completed		N/A
ACT3995	Environment Agency	Superseded		N/A
ACT3996	Environment Agency	Not started - proposed		Yes	Local
ACT4015	Environment Agency	Not started - proposed		Yes	Local
ACT4017	Environment Agency	Not started - proposed		Yes	Local
ACT4018	Environment Agency	Completed		N/A
ACT4019	Environment Agency	Not started - proposed		Yes	Local
ACT4020	Environment Agency	Completed		N/A
ACT4021	Environment Agency	Completed		N/A
ACT4024	Environment Agency	Ongoing		Yes	Local
ACT4028	East Staffordshire District (B)	Ongoing		No
ACT4029	East Staffordshire District (B)	Ongoing		No
ACT4030	East Staffordshire District (B)	Ongoing		No
ACT4031	East Staffordshire District (B)	Ongoing		No
ACT4032	East Staffordshire District (B)	Ongoing		No
ACT4033	East Staffordshire District (B)	Ongoing		No
ACT4035	Dudley Metropolitan District	Ongoing		Yes	National and Local
ACT4036	Lichfield District	Ongoing		No
ACT4037	Lichfield District	Ongoing		No
ACT4191	Environment Agency	Not started - proposed		Yes	Local
ACT4201	Environment Agency	Ongoing		Yes	Local
ACT4202	Environment Agency	Not started - proposed		Yes	Local
ACT4203	Environment Agency	Not started - proposed		Yes	Local
ACT4204	Environment Agency	Ongoing		Yes	Local
ACT4207	Environment Agency	Not started - proposed		No
ACT4658	Lichfield District	Ongoing		No
ACT4659	Lichfield District	Ongoing		No
ACT4660	Lichfield District	Ongoing		No
ACT4661	Lichfield District	Ongoing		No
ACT4662	Lichfield District	Ongoing		No
ACT4663	Tamworth District (B)	Ongoing		No
ACT4664	Tamworth District (B)	Ongoing		No
ACT4665	Tamworth District (B)	Ongoing		No
ACT4666	Tamworth District (B)	Ongoing		No
ACT4667	Newcastle-under-Lyme District (B)	Ongoing		No
ACT4668	Tamworth District (B)	Ongoing		No
ACT4669	Tamworth District (B)	Ongoing		No
ACT4670	Tamworth District (B)	Ongoing		No
ACT4671	Tamworth District (B)	Ongoing		No
ACT4672	Tamworth District (B)	Ongoing		No
ACT4673	Tamworth District (B)	Ongoing		No
ACT4674	Cannock Chase District	Ongoing		No
ACT4675	Tamworth District (B)	Ongoing		No
ACT4676	Tamworth District (B)	Ongoing		No
ACT4677	Tamworth District (B)	Ongoing		No
ACT4678	Tamworth District (B)	Ongoing		No
ACT4679	Tamworth District (B)	Ongoing		No
ACT4680	Tamworth District (B)	Ongoing		No
ACT4686	Solihull Metropolitan District	Ongoing		Yes	National
ACT4687	Cannock Chase District	Ongoing		No
ACT4688	Solihull Metropolitan District	Ongoing		Yes	National
ACT4689	Cannock Chase District	Ongoing		No
ACT4690	Cannock Chase District	Ongoing		No
ACT4691	Solihull Metropolitan District	Ongoing		Yes	National
ACT4692	Cannock Chase District	Ongoing		No
ACT4693	Cannock Chase District	Ongoing		No
ACT4694	Cannock Chase District	Ongoing		No
ACT4695	Cannock Chase District	Ongoing		No
ACT4696	Cannock Chase District	Ongoing		No
ACT4697	Cannock Chase District	Ongoing		No
ACT4698	Cannock Chase District	Ongoing		No
ACT4699	Solihull Metropolitan District	Ongoing		Yes	National
ACT4700	Cannock Chase District	Ongoing		No
ACT4701	Cannock Chase District	Ongoing		No
ACT4702	Cannock Chase District	Ongoing		No
ACT4704	Cannock Chase District	Ongoing		No
ACT4706	Solihull Metropolitan District	Ongoing		Yes	National
ACT4708	Solihull Metropolitan District	Ongoing		Yes	National
ACT4709	North Warwickshire District (B)	Ongoing		No
ACT4710	Solihull Metropolitan District	Ongoing		Yes	National
ACT4711	North Warwickshire District (B)	Ongoing		No
ACT4712	North Warwickshire District (B)	Ongoing		No
ACT4713	Solihull Metropolitan District	Ongoing		Yes	National
ACT4714	North Warwickshire District (B)	Ongoing		No
ACT4715	North Warwickshire District (B)	Ongoing		No
ACT4717	North Warwickshire District (B)	Ongoing		No
ACT4719	North Warwickshire District (B)	Ongoing		No
ACT4720	North Warwickshire District (B)	Ongoing		No
ACT4722	North Warwickshire District (B)	Ongoing		No
ACT4723	North Warwickshire District (B)	Ongoing		No
ACT4724	North Warwickshire District (B)	Ongoing		No
ACT4725	North Warwickshire District (B)	Ongoing		No
ACT4726	South Staffordshire District	Ongoing		No
ACT4727	South Staffordshire District	Ongoing		No
ACT4728	South Staffordshire District	Ongoing		No
ACT4729	South Staffordshire District	Ongoing		No
ACT4730	South Staffordshire District	Ongoing		No
ACT4731	South Staffordshire District	Ongoing		No
ACT4732	South Staffordshire District	Ongoing		No
ACT4733	South Staffordshire District	Ongoing		No
ACT4734	South Staffordshire District	Ongoing		No
ACT4735	North Warwickshire District (B)	Ongoing		No
ACT4736	North Warwickshire District (B)	Ongoing		No
ACT4737	North Warwickshire District (B)	Ongoing		No
ACT4738	North Warwickshire District (B)	Ongoing		No
ACT4739	North Warwickshire District (B)	Ongoing		No
ACT4740	Derbyshire Dales District	Superseded		N/A
ACT4741	Derbyshire Dales District	Superseded		N/A
ACT4742	Derbyshire Dales District	Superseded		N/A
ACT4743	Derbyshire Dales District	Superseded		N/A
ACT4744	Derbyshire Dales District	Superseded		N/A
ACT4745	Newcastle-under-Lyme District (B)	Ongoing		No
ACT4746	Newcastle-under-Lyme District (B)	Ongoing		No
ACT4747	South Staffordshire District	Ongoing		No
ACT4748	Newcastle-under-Lyme District (B)	Ongoing		No
ACT4749	South Staffordshire District	Ongoing		No
ACT4750	Newcastle-under-Lyme District (B)	Ongoing		No
ACT4751	Newcastle-under-Lyme District (B)	Ongoing		No
ACT4752	South Staffordshire District	Ongoing		No
ACT4753	South Staffordshire District	Ongoing		No
ACT4754	South Staffordshire District	Ongoing		No
ACT4755	Newcastle-under-Lyme District (B)	Ongoing		No
ACT4756	South Staffordshire District	Ongoing		No
ACT4757	Newcastle-under-Lyme District (B)	Ongoing		No
ACT4758	South Staffordshire District	Ongoing		No
ACT4759	Newcastle-under-Lyme District (B)	Ongoing		No
ACT4761	Stafford District (B)	Ongoing		No
ACT4762	Stafford District (B)	Ongoing		No
ACT4763	Stafford District (B)	Ongoing		No
ACT4764	Stafford District (B)	Ongoing		No
ACT4765	Stafford District (B)	Ongoing		No
ACT4766	Stafford District (B)	Ongoing		No
ACT4767	Stafford District (B)	Ongoing		No
ACT4768	Stafford District (B)	Ongoing		No
ACT4769	Stafford District (B)	Ongoing		No
ACT4770	Stafford District (B)	Ongoing		No
ACT4771	Stafford District (B)	Ongoing		No
ACT4772	Stafford District (B)	Ongoing		No
ACT4773	Stafford District (B)	Ongoing		No
ACT4774	Stafford District (B)	Ongoing		No
ACT4775	Stoke-on-Trent Unitary Authority	Ongoing		Yes	National
ACT4776	Stafford District (B)	Ongoing		No
ACT4777	Stoke-on-Trent Unitary Authority	Ongoing		Yes	National
ACT4779	Staffordshire Moorlands District	Ongoing		No
ACT4781	Stoke-on-Trent Unitary Authority	Ongoing		Yes	National
ACT4782	Staffordshire Moorlands District	Ongoing		No
ACT4783	Stoke-on-Trent Unitary Authority	Ongoing		Yes	National
ACT4784	Stoke-on-Trent Unitary Authority	Ongoing		Yes	National
ACT4785	Staffordshire Moorlands District	Ongoing		No
ACT4786	Stoke-on-Trent Unitary Authority	Ongoing		Yes	National
ACT4787	Stoke-on-Trent Unitary Authority	Ongoing		Yes	National
ACT4789	Stoke-on-Trent Unitary Authority	Ongoing		Yes	National
ACT4790	Staffordshire Moorlands District	Ongoing		No
ACT4791	Staffordshire Moorlands District	Ongoing		No
ACT4792	Staffordshire Moorlands District	Ongoing		No
ACT4793	Staffordshire Moorlands District	Ongoing		No
ACT4794	Staffordshire Moorlands District	Ongoing		No
ACT4795	Staffordshire Moorlands District	Ongoing		No
ACT4796	Staffordshire Moorlands District	Ongoing		No
ACT4797	Staffordshire Moorlands District	Ongoing		No
ACT4798	Staffordshire Moorlands District	Ongoing		No
ACT4799	Staffordshire Moorlands District	Ongoing		No
ACT4803	Staffordshire	Ongoing		Yes	National
ACT5484	Environment Agency	Ongoing		Yes	Local
ACT5486	Environment Agency	Ongoing		Yes	Local
ACT5488	Environment Agency	Ongoing		Yes	Local
ACT5489	Environment Agency	Ongoing		Yes	Local
ACT5490	Environment Agency	Ongoing		Yes	Local
ACT5491	Environment Agency	Ongoing		Yes	Local
ACT5495	Environment Agency	Ongoing		Yes	Local
ACT5497	Environment Agency	Ongoing		Yes	Local
ACT5498	Environment Agency	Superseded		N/A
ACT5504	Environment Agency	Ongoing		Yes	Local
ACT5505	Environment Agency	Ongoing		Yes	Local
ACT5506	Environment Agency	Ongoing		Yes	Local
ACT5508	Environment Agency	Ongoing		Yes	Local
ACT5662	Anglian Water	Ongoing		Yes	National
ACT5663	Anglian Water	Ongoing		Yes	National
ACT5664	Anglian Water	Ongoing		Yes	National
ACT5673	Anglian Water	Ongoing		Yes	National
ACT5681	Anglian Water	Ongoing		Yes	National
ACT5682	Anglian Water	Ongoing		Yes	National
ACT5683	Anglian Water	Ongoing		Yes	National
ACT5836	Birmingham Metropolitan District	Ongoing		Yes	National
ACT6061	Environment Agency	Ongoing	It has been included in another piece of work	Yes
ACT6062	Environment Agency	Completed		N/A
ACT6063	Leicester Unitary Authority	Ongoing	It has been replaced by another measure	Yes
ACT6262	Environment Agency	Ongoing		Yes	Local
ACT6264	Environment Agency	Ongoing		Yes	Local
ACT6265	Environment Agency	Ongoing		Yes	Local
ACT6266	Environment Agency	Ongoing		Yes	Local
ACT6267	Environment Agency	Completed		N/A
ACT6268	Environment Agency	Ongoing		Yes	Local
ACT6269	Environment Agency	Ongoing		Yes	Local
ACT6270	Environment Agency	Ongoing		Yes	Local
ACT6271	Environment Agency	Ongoing		Yes	Local
ACT6272	North Yorkshire County	Ongoing		Yes	Local
ACT6273	Environment Agency	Ongoing		Yes	Local
ACT6274	Environment Agency	Ongoing		Yes	Local
ACT6275	Environment Agency	Not started - proposed		Yes	Local
ACT6276	Environment Agency	Ongoing		Yes	Local
ACT6277	Environment Agency	Ongoing		Yes	Local
ACT6278	Environment Agency	Ongoing		Yes	Local
ACT6279	Environment Agency	Ongoing		Yes	Local
ACT6280	Environment Agency	Ongoing		Yes	Local
ACT6281	Environment Agency	Ongoing		Yes	Local
ACT6282	Environment Agency	Superseded	Combined as part of a more strategic measure	N/A
ACT6283	Environment Agency	Ongoing	Not a priority measure	No
ACT6284	Environment Agency	Ongoing		Yes	Local
ACT6285	Environment Agency	Ongoing		Yes	Local
ACT6286	Environment Agency	Ongoing		Yes	Local
ACT6289	North Yorkshire County	Ongoing		Yes	Local
ACT6290	Environment Agency	Ongoing		Yes	Local
ACT6291	Environment Agency	Ongoing		Yes	Local
ACT6297	Environment Agency	Ongoing		No
ACT6300	Environment Agency	Ongoing		No
ACT6302	Kirklees Metropolitan District	Ongoing		No
ACT6304	Environment Agency	Completed	Part of wider measure for modelling to better understand FR in South Yorkshire	N/A
ACT6306	Kirklees Metropolitan District	Completed		N/A
ACT6308	Kirklees Metropolitan District	Not started - proposed		No
ACT6310	Kirklees Metropolitan District	Ongoing		No
ACT6311	Environment Agency	Completed		N/A
ACT6313	Leeds Metropolitan District	Ongoing		No
ACT6315	Kirklees Metropolitan District	Ongoing		No
ACT6316	Kirklees Metropolitan District	Ongoing		No
ACT6317	Kirklees Metropolitan District	Ongoing		No
ACT6318	Kirklees Metropolitan District	Completed		N/A
ACT6319	Kirklees Metropolitan District	Ongoing		No
ACT6321	Kirklees Metropolitan District	Ongoing		No
ACT6323	Kirklees Metropolitan District	Ongoing		No
ACT6325	Environment Agency	Superseded	Part of wider measure for modelling to better understand FR in South Yorkshire	N/A
ACT6328	Kirklees Metropolitan District	Ongoing		No
ACT6329	Environment Agency	Superseded	Part of wider measure for modelling to better understand FR in South Yorkshire	N/A
ACT6330	Kirklees Metropolitan District	Ongoing		No
ACT6332	Kirklees Metropolitan District	Completed		N/A
ACT6333	Kirklees Metropolitan District	Completed		N/A
ACT6334	Kirklees Metropolitan District	Completed		N/A
ACT6335	Kirklees Metropolitan District	Not started - proposed		No
ACT6336	Environment Agency	Superseded	Part of wider measure for modelling to better understand FR in South Yorkshire	N/A
ACT6337	Kirklees Metropolitan District	Completed		N/A
ACT6338	Kirklees Metropolitan District	Ongoing		No
ACT6339	Kirklees Metropolitan District	Ongoing		No
ACT6340	Environment Agency	Superseded		N/A
ACT6341	Kirklees Metropolitan District	Ongoing		No
ACT6342	Environment Agency	Superseded		N/A
ACT6343	Kirklees Metropolitan District	Not started - proposed		No
ACT6344	Environment Agency	Superseded		N/A
ACT6345	Kirklees Metropolitan District	Not started - proposed		No
ACT6346	Environment Agency	Not started - proposed		Yes	Local
ACT6347	Kirklees Metropolitan District	Not started - proposed		No
ACT6348	Environment Agency	Not started - proposed		Yes	Local
ACT6349	Kirklees Metropolitan District	Ongoing		No
ACT6351	Environment Agency	Superseded	Part of wider measure for modelling to better understand FR in South Yorkshire	N/A
ACT6353	Environment Agency	Not started - proposed	Combined as part of a more strategic measure	No
ACT6354	Environment Agency	Ongoing		No
ACT6355	Environment Agency	Ongoing		No
ACT6357	Environment Agency	Completed		N/A
ACT6358	Kirklees Metropolitan District	Completed		N/A
ACT6359	Environment Agency	Superseded		N/A
ACT6360	Environment Agency	Ongoing		No
ACT6362	Environment Agency	Superseded		N/A
ACT6363	Environment Agency	Ongoing		Yes	Local
ACT6364	Kirklees Metropolitan District	Ongoing		No
ACT6365	Environment Agency	Ongoing		Yes	Local
ACT6366	Environment Agency	Completed		N/A
ACT6367	Kirklees Metropolitan District	Ongoing		No
ACT6368	Leeds Metropolitan District	Completed		N/A
ACT6369	Leeds Metropolitan District	Completed		N/A
ACT6371	Kirklees Metropolitan District	Completed		N/A
ACT6395	Environment Agency	Superseded		N/A
ACT6397	Environment Agency	Ongoing		Yes	Local
ACT6399	Environment Agency	Ongoing		Yes	Local
ACT6400	Environment Agency	Ongoing		Yes	Local
ACT6401	Environment Agency	Ongoing		Yes	Local
ACT6402	Environment Agency	Superseded	Incorporated into other measures in some of the Yorkshire LA areas	N/A
ACT6404	Environment Agency	Superseded	Incorporated into other measures in some of the Yorkshire LA areas	N/A
ACT6451	York Unitary Authority	Ongoing		Yes	Local
ACT6454	York Unitary Authority	Not started - agreed		Yes	Local
ACT6455	York Unitary Authority	Completed		N/A
ACT6460	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6463	Scarborough District (B)	Not started - agreed		Yes	Local
ACT6465	Environment Agency	Not started - agreed		Yes	Local
ACT6473	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6475	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6477	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6478	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6479	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6480	North York Moors National Park	Not started- agreed		Yes	Local
ACT6481	Scarborough District (B)	Not started- agreed		Yes	Local
ACT6482	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6483	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6485	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6489	Scarborough District (B)	Ongoing		Yes	Local
ACT6490	North Yorkshire County	Not started - agreed		Yes	Local
ACT6491	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6495	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6498	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6499	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6500	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6503	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6505	Scarborough District (B)	Completed		N/A
ACT6506	North Yorkshire County	Completed		N/A
ACT6507	Scarborough District (B)	Completed		N/A
ACT6511	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6515	Scarborough District (B)	Completed		N/A
ACT6517	Environment Agency	Superseded	Part of wider measure for modelling to better understand FR in South Yorkshire	N/A
ACT6518	Environment Agency	Ongoing		Yes	Local
ACT6519	East Riding of Yorkshire Unitary Authority	Completed		N/A
ACT6522	East Riding of Yorkshire Unitary Authority	Completed		N/A
ACT6523	Scarborough District (B)	Ongoing		Yes	Local
ACT6525	Scarborough District (B)	Completed		N/A
ACT6526	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT6527	Scarborough District (B)	Completed		N/A
ACT6528	Scarborough District (B)	Ongoing		Yes	Local
ACT6529	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT6530	North York Moors National Park	Ongoing		Yes	Local
ACT6531	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT6532	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT6533	Environment Agency	Superseded	Part of wider measure for modelling to better understand FR in South Yorkshire	N/A
ACT6534	Scarborough District (B)	Ongoing		Yes	Local
ACT6536	Environment Agency	Superseded	Combined as part of a more strategic measure	N/A
ACT6537	Environment Agency	Ongoing - construction		Yes	Local
ACT6539	Scarborough District (B)	Ongoing		Yes	Local
ACT6542	Scarborough District (B)	Ongoing		Yes	Local
ACT6544	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6546	Scarborough District (B)	Ongoing		Yes	Local
ACT6547	Environment Agency	Superseded	Combined as part of a more strategic measure	N/A
ACT6548	Environment Agency	Superseded		N/A
ACT6549	Scarborough District (B)	Not started - agreed		Yes	Local
ACT6550	Environment Agency	Ongoing		Yes	Local
ACT6551	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6552	Environment Agency	Not started - proposed		Yes	Local
ACT6554	Scarborough District (B)	Ongoing		Yes	Local
ACT6555	Environment Agency	Completed		N/A
ACT6557	Scarborough District (B)	Ongoing		Yes	Local
ACT6558	Scarborough District (B)	Not started - agreed		Yes	Local
ACT6580	Environment Agency	Ongoing		Yes	Local
ACT6582	Environment Agency	Not started - agreed		Yes	Local
ACT6583	Environment Agency	Not started - agreed		Yes	Local
ACT6584	Environment Agency	Completed		N/A
ACT6587	Environment Agency	Ongoing		Yes	Local
ACT6591	Environment Agency	Not started - agreed		Yes	Local
ACT6592	Environment Agency	Superseded		N/A
ACT6595	Scarborough District (B)	Completed		N/A
ACT6596	Environment Agency	Ongoing		Yes	Local
ACT6599	Scarborough District (B)	Ongoing		Yes	Local
ACT6600	Scarborough District (B)	Completed		N/A
ACT6601	Environment Agency	Ongoing		Yes	Local
ACT6602	Environment Agency	Not started - agreed		Yes	Local
ACT6604	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6606	Environment Agency	Ongoing		Yes	Local
ACT6608	Environment Agency	Ongoing		Yes	Local
ACT6609	Environment Agency	Completed		N/A
ACT6610	North York Moors National Park	Not started - agreed		Yes	Local
ACT6611	Environment Agency	Superseded		N/A
ACT6612	Scarborough District (B)	Ongoing		Yes	Local
ACT6613	Environment Agency	Ongoing		Yes	Local
ACT6614	Environment Agency	Ongoing		Yes	Local
ACT6615	Environment Agency	Superseded	Incorporated into other measures in some of the Yorkshire LA areas	N/A
ACT6616	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6617	Scarborough District (B)	Ongoing		Yes	Local
ACT6618	North Yorkshire County	Completed		N/A
ACT6619	Environment Agency	Not started - agreed		Yes	Local
ACT6620	Scarborough District (B)	Completed		N/A
ACT6621	North Yorkshire County	Completed		N/A
ACT6622	Environment Agency	Not started - agreed		Yes	Local
ACT6623	North Yorkshire County	Completed		N/A
ACT6624	North Yorkshire County	Not started - agreed		Yes	Local
ACT6625	North Yorkshire County	Completed		N/A
ACT6626	Scarborough District (B)	Ongoing		Yes	Local
ACT6627	North Yorkshire County	Ongoing		Yes	Local
ACT6628	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6629	North Yorkshire County	Ongoing		Yes	Local
ACT6630	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6631	North Yorkshire County	Ongoing		Yes	Local
ACT6632	Scarborough District (B)	Ongoing		Yes	Local
ACT6633	North Yorkshire County	Ongoing		Yes	Local
ACT6634	Scarborough District (B)	Ongoing		Yes	Local
ACT6635	North Yorkshire County	Completed		N/A
ACT6636	Scarborough District (B)	Ongoing		Yes	Local
ACT6637	North Yorkshire County	Superseded		N/A
ACT6638	Scarborough District (B)	Ongoing		Yes	Local
ACT6639	North Yorkshire County	Ongoing		Yes	Local
ACT6640	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6641	North Yorkshire County	Ongoing		Yes	Local
ACT6642	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6643	North Yorkshire County	Superseded		N/A
ACT6644	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6645	North Yorkshire County	Completed		N/A
ACT6646	Scarborough District (B)	Ongoing		Yes	Local
ACT6647	Scarborough District (B)	Ongoing		Yes	Local
ACT6648	North Yorkshire County	Completed		N/A
ACT6649	Scarborough District (B)	Ongoing		Yes	Local
ACT6650	North Yorkshire County	Not started - proposed		Yes	Local
ACT6651	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6652	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6653	North Yorkshire County	Superseded		N/A
ACT6654	Environment Agency	Completed		N/A
ACT6655	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6656	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6657	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6658	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6659	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6660	Environment Agency	Not started - proposed		Yes	Local
ACT6661	Scarborough District (B)	Ongoing		Yes	Local
ACT6662	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6663	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6664	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6665	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6666	Scarborough District (B)	Completed		N/A
ACT6667	Scarborough District (B)	Not started - proposed		Yes	Local
ACT6668	Environment Agency	Not started - proposed		Yes	Local
ACT6669	North York Moors National Park	Not started - proposed		Yes	Local
ACT6670	North York Moors National Park	Ongoing		Yes	Local
ACT6671	York Unitary Authority	Ongoing		Yes	Local
ACT6672	York Unitary Authority	Ongoing		Yes	Local
ACT6673	York Unitary Authority	Ongoing		Yes	Local
ACT6674	York Unitary Authority	Ongoing		Yes	Local
ACT6675	York Unitary Authority	Ongoing		Yes	Local
ACT6676	York Unitary Authority	Ongoing		Yes	Local
ACT6677	York Unitary Authority	Ongoing		Yes	Local
ACT6678	York Unitary Authority	Ongoing		Yes	Local
ACT6679	York Unitary Authority	Ongoing		Yes	Local
ACT6680	North Yorkshire County	Not started - proposed		Yes	Local
ACT6681	York Unitary Authority	Ongoing		Yes	Local
ACT6682	York Unitary Authority	Ongoing		Yes	Local
ACT6683	Scarborough District (B)	Ongoing		Yes	Local
ACT6684	Scarborough District (B)	Ongoing		Yes	Local
ACT6685	York Unitary Authority	Ongoing		Yes	Local
ACT6686	York Unitary Authority	Ongoing		Yes	Local
ACT6687	York Unitary Authority	Ongoing		Yes	Local
ACT6688	York Unitary Authority	Ongoing		Yes	Local
ACT6689	City of Kingston upon Hull Unitary Authority	Completed		N/A
ACT6690	York Unitary Authority	Ongoing		Yes	Local
ACT6691	York Unitary Authority	Ongoing		Yes	Local
ACT6692	York Unitary Authority	Ongoing		Yes	Local
ACT6693	York Unitary Authority	Ongoing		Yes	Local
ACT6695	City of Kingston upon Hull Unitary Authority	Completed		N/A
ACT6700	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT6701	Environment Agency	Completed		N/A
ACT6702	Environment Agency	Ongoing	It has been replaced by another measure	Yes
ACT6703	Environment Agency	Completed		N/A
ACT6704	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT6705	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT6707	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT6718	Environment Agency	Completed		N/A
ACT6719	Environment Agency	Ongoing		Yes
ACT6720	Environment Agency	Completed		N/A
ACT6721	Environment Agency	Ongoing	It has been replaced by another measure	Yes
ACT6722	Environment Agency	Completed		N/A
ACT6723	Environment Agency	Completed		N/A
ACT6731	City of Kingston upon Hull Unitary Authority	Ongoing		Yes	Local
ACT6733	City of Kingston upon Hull Unitary Authority	Ongoing		Yes	Local
ACT6735	City of Kingston upon Hull Unitary Authority	Ongoing		Yes	Local
ACT6736	City of Kingston upon Hull Unitary Authority	Ongoing		Yes	Local
ACT6738	City of Kingston upon Hull Unitary Authority	Completed		N/A
ACT6741	City of Kingston upon Hull Unitary Authority	Ongoing		Yes	Local
ACT6746	City of Kingston upon Hull Unitary Authority	Ongoing		Yes	Local
ACT6748	City of Kingston upon Hull Unitary Authority	Ongoing		Yes	Local
ACT6750	City of Kingston upon Hull Unitary Authority	Completed		N/A
ACT6751	City of Kingston upon Hull Unitary Authority	Ongoing		Yes	Local
ACT6752	City of Kingston upon Hull Unitary Authority	Ongoing		Yes	Local
ACT6755	City of Kingston upon Hull Unitary Authority	Completed		N/A
ACT6759	City of Kingston upon Hull Unitary Authority	Ongoing		Yes	Local
ACT6765	City of Kingston upon Hull Unitary Authority	Ongoing		Yes	Local
ACT6766	City of Kingston upon Hull Unitary Authority	Ongoing		Yes	Local
ACT6768	City of Kingston upon Hull Unitary Authority	Ongoing		Yes	Local
ACT6769	City of Kingston upon Hull Unitary Authority	Ongoing		Yes	Local
ACT6772	City of Kingston upon Hull Unitary Authority	Ongoing		Yes	Local
ACT6773	City of Kingston upon Hull Unitary Authority	Ongoing		Yes	Local
ACT6774	City of Kingston upon Hull Unitary Authority	Ongoing		Yes	Local
ACT6775	City of Kingston upon Hull Unitary Authority	Ongoing		Yes	Local
ACT6776	City of Kingston upon Hull Unitary Authority	Completed		N/A
ACT6777	City of Kingston upon Hull Unitary Authority	Ongoing		Yes	Local
ACT6780	City of Kingston upon Hull Unitary Authority	Ongoing		Yes	Local
ACT6781	City of Kingston upon Hull Unitary Authority	Ongoing		Yes	Local
ACT6783	City of Kingston upon Hull Unitary Authority	Ongoing		Yes	Local
ACT6784	City of Kingston upon Hull Unitary Authority	Ongoing		Yes	Local
ACT6786	City of Kingston upon Hull Unitary Authority	Ongoing		Yes	Local
ACT6787	City of Kingston upon Hull Unitary Authority	Ongoing		Yes	Local
ACT6793	Calderdale Metropolitan District	Ongoing		Yes	Local
ACT6794	Leeds Metropolitan District	Ongoing		No
ACT6795	Bradford Metropolitan District	Ongoing		Yes	Local
ACT6796	Wakefield Metropolitan District	Superseded		N/A
ACT6797	Derbyshire County	Ongoing		Yes	Local
ACT6798	Doncaster Metropolitan District	Ongoing		Yes	Local
ACT6799	Rotherham Metropolitan District	Completed		N/A
ACT6800	Sheffield Metropolitan District	Ongoing		Yes	Local
ACT6801	Barnsley Metropolitan District	Ongoing		Yes	Local
ACT6826	Environment Agency	Completed		N/A
ACT6870	Environment Agency	Not started - agreed		Yes	Local
ACT6902	Scarborough District (B)	Ongoing		Yes	Local
ACT6904	Environment Agency	Not started - proposed		Yes	Local
ACT6905	Environment Agency	Ongoing		Yes	Local
ACT6906	Environment Agency	Ongoing		Yes	Local
ACT6910	Environment Agency	Ongoing		Yes	Local
ACT6913	York Unitary Authority	Ongoing		Yes	Local
ACT6934	Environment Agency	Ongoing		N/A
ACT6935	Environment Agency	Ongoing	BAU	No
ACT6936	Environment Agency	Superseded	Incorporated into other measures in some of the Yorkshire LA areas	N/A
ACT6943	Environment Agency	Ongoing	Only Rotherham included something similar as a measure	No
ACT6948	Environment Agency	Superseded	Incorporated into other measures in some of the Yorkshire LA areas	N/A
ACT6959	Environment Agency	Superseded	Incorporated into other measures in some of the Yorkshire LA areas	N/A
ACT6962	Environment Agency	Superseded	Incorporated into other measures in some of the Yorkshire LA areas	N/A
ACT6963	Environment Agency	Superseded	Combined as part of a more strategic measure	N/A
ACT6964	Environment Agency	Superseded	Combined as part of a more strategic measure	N/A
ACT699	Environment Agency	Ongoing		No
ACT700	Environment Agency	Ongoing		No
ACT701	Environment Agency	Completed		N/A
ACT702	Environment Agency	Ongoing		Yes	National
ACT703	Environment Agency	Ongoing		Yes	National
ACT704	Environment Agency	Ongoing		Yes	National
ACT705	Environment Agency	Ongoing		Yes	National
ACT706	Environment Agency	Ongoing		Yes	National
ACT707	Environment Agency	Ongoing		Yes	National
ACT708	Environment Agency	Ongoing		Yes	National
ACT710	Environment Agency	Ongoing		Yes	National
ACT711	Environment Agency	Ongoing		Yes	National
ACT712	Environment Agency	Ongoing		Yes	National
ACT713	Environment Agency	Ongoing		Yes	National
ACT7136	Environment Agency	Ongoing		Yes	Local
ACT714	Environment Agency	Ongoing		Yes	National
ACT7145	Warwickshire County	Ongoing		Yes	National
ACT715	Environment Agency	Ongoing		Yes	National
ACT716	Environment Agency	Ongoing		Yes	National
ACT717	Environment Agency	Ongoing		Yes	National
ACT7149	Worcestershire County	Ongoing		Yes	National
ACT7490	Environment Agency	Ongoing		No
ACT7491	Lichfield District	Ongoing		No
ACT7493	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT821	Environment Agency	Ongoing		Yes	Local
ACT822	Environment Agency	Ongoing		Yes	Local
ACT823	Environment Agency	Completed		N/A
ACT825	Environment Agency	Ongoing		Yes	Local
ACT826	Environment Agency	Superseded	Other	N/A
ACT827	Environment Agency	Completed		N/A
ACT828	Environment Agency	Ongoing		Yes	Local
ACT829	Environment Agency	Not started - proposed	It has been postponed	No
ACT830	Environment Agency	Completed		N/A
ACT831	Environment Agency	Completed		N/A
ACT832	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT833	Environment Agency	Superseded	Other	N/A
ACT834	Environment Agency	Ongoing		Yes	Local
ACT835	Environment Agency	Not started - proposed	It has been postponed	No
ACT836	Environment Agency	Ongoing	It has been replaced by another measure	Yes	Local
ACT837	Environment Agency	Ongoing		Yes	National
ACT838	Environment Agency	Completed		N/A
ACT839	Environment Agency	Ongoing		Yes	National
ACT840	Environment Agency	Ongoing	It has been replaced by another measure	No
ACT841	Environment Agency	Ongoing		Yes	National
ACT842	Environment Agency	Ongoing		Yes	National
ACT843	Environment Agency	Ongoing	It has been replaced by another measure	No
ACT844	Environment Agency	Ongoing		Yes	Local
ACT845	Environment Agency	Ongoing		Yes	Local
ACT846	Environment Agency	Ongoing		Yes	National
ACT847	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT848	North East Lincolnshire Unitary Authority	Ongoing		Yes	National
ACT849	North East Lincolnshire Unitary Authority	Ongoing		Yes	National
ACT850	North East Lincolnshire Unitary Authority	Ongoing		Yes	National
ACT851	Environment Agency	Ongoing		Yes	Local
ACT852	Environment Agency	Ongoing		Yes	National
ACT853	Environment Agency	Ongoing		Yes	National
ACT854	Environment Agency	Ongoing		Yes	National
ACT855	Environment Agency	Ongoing		Yes	National
ACT856	Lincolnshire County	Ongoing		Yes	Local
ACT857	Lincolnshire County	Ongoing		Yes	Local
ACT858	Lincolnshire County	Ongoing		Yes	Local
ACT859	North Lincolnshire Unitary Authority	Ongoing		Yes	National
ACT860	North Lincolnshire Unitary Authority	Ongoing		Yes	National
ACT861	North Lincolnshire Unitary Authority	Ongoing		Yes	National