## Cover_sheet
Thames Flood risk management plan 1 annex
This spreadsheet states the progress for the first cycle of the Flood risk management plan (FRMP) (2015-2021). The spreadsheet contains the status of each FRMP plan measure, the measure ID, the action owner, the implementation status as of the 31 March 2021. As well as reasons for not progressing if relevant.
Status of the measures
First cycle measures that comprise of the day-to-day work by the Environment Agency and Lead Local Flood Authorities (LLFAs) are transitioned to this second cycle FRMP as ongoing national-level measures. This may be as an individual measure or aggregated with other measures. More information on these measures can be found in Flood Plan Explorer. / Measures may appear differently in the second cycle compared with the first cycle, for example an individual measure in the first cycle may appear as part of a wider programme of work in the second cycle. / Measures that are not transitioned to the second cycle FRMP will continue to be developed or kept under review by the Environment Agency, LLFA and other risk management authorities. This will be done in accordance with the current Flood and Coastal Erosion Risk Management appraisal guidance and funding rules. / Column D contains blank cells when a measure is 'completed' or 'ongoing' in FRMP cycle 1. / Column F contains blank cells when a measure is 'completed' or not transitioned to FRMP cycle 2.
Links to other FRMP resources
Flood Plan Explorer
Thames river basin district flood risk management plan

## FRMP1_annex
Thames FRMP 1 annex
This worksheet contains one table.
Measure ID	Measure Owner	Implementation Status	Reason for not progressing	Transitioned to FRMP2?	Transitioned Locally or Nationally?
ACT6287	Central Bedfordshire Unitary Authority	Ongoing		No
ACT6385	Central Bedfordshire Unitary Authority	Ongoing		No
ACT6388	Central Bedfordshire Unitary Authority	Ongoing		No
ACT6389	Central Bedfordshire Unitary Authority	Ongoing		No
ACT6391	Central Bedfordshire Unitary Authority	Ongoing		No
ACT6392	Central Bedfordshire Unitary Authority	Ongoing		No
ACT140	Environment Agency	Completed		No
ACT015	Northamptonshire County	Completed		No
ACT5662	Anglian Water	Ongoing		Yes	Locally
ACT5663	Anglian Water	Ongoing		Yes	Locally
ACT5664	Anglian Water	Ongoing		Yes	Locally
ACT5681	Anglian Water	Ongoing		Yes	Locally
ACT5682	Anglian Water	Ongoing		Yes	Locally
ACT5683	Anglian Water	Ongoing		Yes	Locally
ACT2302	Daventry District	Ongoing		Yes	Locally
ACT3494	Environment Agency	Ongoing		Yes	Nationally
ACT3495	Environment Agency	Ongoing		Yes	Nationally
ACT3496	Environment Agency	Ongoing		Yes	Nationally
ACT3497	Environment Agency	Ongoing		Yes	Nationally
ACT3498	Environment Agency	Ongoing		Yes	Nationally
ACT3499	Environment Agency	Completed		No
ACT3500	Environment Agency	Ongoing		Yes	Nationally
ACT3501	Environment Agency	Ongoing		Yes	Nationally
ACT3502	Environment Agency	Ongoing		Yes	Nationally
ACT3503	Environment Agency	Ongoing		Yes	Nationally
ACT3504	Environment Agency	Ongoing		Yes	Nationally
ACT3505	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT3506	Environment Agency	Ongoing		Yes	Nationally
ACT3507	Environment Agency	Ongoing		Yes	Locally
ACT3508	Environment Agency	Ongoing		Yes	Nationally
ACT3509	Environment Agency	Ongoing		Yes	Nationally
ACT3510	Environment Agency	Ongoing		Yes	Nationally
ACT3511	Environment Agency	Ongoing		Yes	Nationally
ACT3512	Environment Agency	Completed		No
ACT3513	Environment Agency	Ongoing		Yes	Nationally
ACT3514	Environment Agency	Ongoing		Yes	Locally
ACT3515	Environment Agency	Completed		No
ACT3516	Environment Agency	Ongoing		Yes	Nationally
ACT3517	Environment Agency	Ongoing		Yes	Nationally
ACT3518	Environment Agency	Ongoing		Yes	Nationally
ACT3519	Environment Agency	Completed		No
ACT3520	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT3521	Environment Agency	Completed		No
ACT3522	Environment Agency	Ongoing		Yes	Nationally
ACT3523	Environment Agency	Ongoing		Yes	Nationally
ACT3524	Environment Agency	Completed		No
ACT3525	Environment Agency	Ongoing		Yes	Nationally
ACT3526	Environment Agency	Completed		No
ACT3527	Environment Agency	Ongoing		Yes	Nationally
ACT3528	Environment Agency	Ongoing		Yes	Nationally
ACT3529	Environment Agency	Completed		No
ACT3530	Environment Agency	Ongoing		Yes	Nationally
ACT3531	Environment Agency	Ongoing		Yes	Nationally
ACT3532	Environment Agency	Ongoing		Yes	Nationally
ACT3533	Environment Agency	Ongoing		Yes	Nationally
ACT3534	Environment Agency	Ongoing		Yes	Nationally
ACT3535	Environment Agency	Ongoing		Yes	Nationally
ACT3536	Environment Agency	Ongoing		Yes	Nationally
ACT3537	Environment Agency	Ongoing		Yes	Nationally
ACT3538	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT3539	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT3540	Environment Agency	Ongoing		Yes	Nationally
ACT3541	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT3542	Environment Agency	Ongoing		Yes	Nationally
ACT3543	Environment Agency	Ongoing		Yes	Nationally
ACT3544	Environment Agency	Completed		No
ACT3545	Environment Agency	Ongoing		Yes	Nationally
ACT3546	Environment Agency	Ongoing		Yes	Nationally
ACT3547	Environment Agency	Ongoing		Yes	Nationally
ACT3548	Environment Agency	Ongoing		Yes	Nationally
ACT3549	Environment Agency	Superseded	Replaced by another measure	No
ACT3550	Environment Agency	Ongoing		Yes	Nationally
ACT3551	Environment Agency	Completed		No
ACT3552	Environment Agency	Ongoing		Yes	Nationally
ACT3553	Environment Agency	Ongoing		Yes	Nationally
ACT3554	Environment Agency	Ongoing		Yes	Nationally
ACT3555	Environment Agency	Ongoing		Yes	Nationally
ACT3556	Environment Agency	Ongoing		Yes	Nationally
ACT3557	Environment Agency	Ongoing		Yes	Nationally
ACT3558	Environment Agency	Ongoing		Yes	Nationally
ACT3559	Environment Agency	Completed		No
ACT3560	Environment Agency	Ongoing		Yes	Nationally
ACT3561	Environment Agency	Ongoing		Yes	Nationally
ACT3562	Environment Agency	Ongoing		Yes	Nationally
ACT3563	Environment Agency	Completed		No
ACT3564	Environment Agency	Ongoing		Yes	Nationally
ACT3565	Environment Agency	Ongoing		Yes	Nationally
ACT3567	Environment Agency	Ongoing		Yes	Nationally
ACT3568	Environment Agency	Ongoing		Yes	Nationally
ACT3569	Environment Agency	Ongoing		Yes	Nationally
ACT3570	Environment Agency	Ongoing		Yes	Nationally
ACT3571	Environment Agency	Completed		No
ACT3572	Environment Agency	Ongoing		Yes	Nationally
ACT3573	Environment Agency	Ongoing		Yes	Nationally
ACT3574	Environment Agency	Ongoing		Yes	Nationally
ACT3575	Environment Agency	Ongoing		Yes	Nationally
ACT3576	Environment Agency	Ongoing		Yes	Nationally
ACT3577	Environment Agency	Superseded	Replaced by another measure	No
ACT3578	Environment Agency	Ongoing		Yes	Nationally
ACT3579	Environment Agency	Ongoing		Yes	Nationally
ACT3580	Environment Agency	Ongoing		Yes	Nationally
ACT3581	Environment Agency	Ongoing		Yes	Nationally
ACT3582	Environment Agency	Ongoing		Yes	Locally
ACT5646	Environment Agency	Ongoing		Yes	Nationally
ACT5665	Environment Agency	Ongoing		Yes	Nationally
ACT5666	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT5667	Environment Agency	Ongoing		Yes	Nationally
ACT5668	Environment Agency	Completed		No
ACT5669	Environment Agency	Completed		No
ACT5670	Environment Agency	Completed		No
ACT5671	Environment Agency	Ongoing		Yes	Nationally
ACT5674	Environment Agency	Ongoing		Yes	Nationally
ACT5675	Environment Agency	Ongoing		Yes	Nationally
ACT5676	Environment Agency	Ongoing - construction		No
ACT5677	Environment Agency	Completed		No
ACT5678	Environment Agency	Ongoing		Yes	Nationally
ACT5679	Environment Agency	Ongoing		Yes	Nationally
ACT5680	Environment Agency	Ongoing		Yes	Nationally
ACT5724	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT5725	Environment Agency	Completed		No
ACT5726	Environment Agency	Completed		No
ACT5727	Environment Agency	Superseded	Included elsewhere	No
ACT5728	Environment Agency	Completed		No
ACT5729	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT5730	Environment Agency	Completed		No
ACT5731	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT5732	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT5733	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT5734	Environment Agency	Superseded	On Hold	No
ACT5735	Environment Agency	Superseded	On Hold	No
ACT5736	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT5737	Environment Agency	Completed		No
ACT5738	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT5739	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT5741	Environment Agency	Completed		No
ACT5752	Environment Agency	Ongoing		Yes	Nationally
ACT5753	Environment Agency	Ongoing		Yes	Nationally
ACT5754	Environment Agency	Ongoing		Yes	Nationally
ACT5755	Environment Agency	Ongoing		Yes	Nationally
ACT5756	Environment Agency	Ongoing		Yes	Nationally
ACT5757	Environment Agency	Ongoing		Yes	Nationally
ACT5758	Environment Agency	Ongoing		Yes	Nationally
ACT5759	Environment Agency	Ongoing		Yes	Nationally
ACT5760	Environment Agency	Ongoing		Yes	Nationally
ACT5762	Environment Agency	Completed		No
ACT5763	Environment Agency	Superseded	Postponed	No
ACT5764	Environment Agency	Completed		No
ACT5765	Environment Agency	Completed		No
ACT5808	Environment Agency	Completed		No
ACT5825	Environment Agency	Completed		No
ACT6133	Environment Agency	Ongoing		Yes	Nationally
ACT6134	Environment Agency	Ongoing		Yes	Nationally
ACT6135	Environment Agency	Ongoing		Yes	Nationally
ACT6136	Environment Agency	Ongoing		Yes	Nationally
ACT6137	Environment Agency	Ongoing		Yes	Nationally
ACT6138	Environment Agency	Ongoing		Yes	Nationally
ACT6139	Environment Agency	Ongoing		Yes	Nationally
ACT6140	Environment Agency	Ongoing		Yes	Nationally
ACT6141	Environment Agency	Ongoing		Yes	Nationally
ACT6142	Environment Agency	Ongoing		Yes	Nationally
ACT6143	Environment Agency	Ongoing		Yes	Nationally
ACT6144	Environment Agency	Ongoing		Yes	Nationally
ACT6145	Environment Agency	Ongoing		Yes	Nationally
ACT6146	Environment Agency	Ongoing		Yes	Nationally
ACT6147	Environment Agency	Ongoing		Yes	Nationally
ACT7138	Environment Agency	Ongoing		Yes	Nationally
ACT7139	Environment Agency	Completed		No
ACT2275	Northamptonshire	Completed		No
ACT014	Northamptonshire County	Ongoing		Yes	Nationally
ACT2248	Northamptonshire County	Ongoing		No
ACT2256	Northamptonshire County	Ongoing		Yes	Nationally
ACT2257	Northamptonshire County	Ongoing		Yes	Nationally
ACT2258	Northamptonshire County	Ongoing		Yes	Nationally
ACT2259	Northamptonshire County	Ongoing		Yes	Nationally
ACT2260	Northamptonshire County	Ongoing		Yes	Nationally
ACT2261	Northamptonshire County	Ongoing		Yes	Nationally
ACT2268	Northamptonshire County	Completed		No
ACT2270	Northamptonshire County	Ongoing		Yes	Nationally
ACT2271	Northamptonshire County	Completed		No
ACT2272	Northamptonshire County	Completed		No
ACT2273	Northamptonshire County	Ongoing		Yes	Nationally
ACT2274	Northamptonshire County	Ongoing		Yes	Nationally
ACT2276	Northamptonshire County	Ongoing		No
ACT2277	Northamptonshire County	Completed		No
ACT2292	Northamptonshire County	Ongoing		Yes	Nationally
ACT2293	Northamptonshire County	Completed		No
ACT2294	Northamptonshire County	Ongoing		Yes	Locally
ACT2295	Northamptonshire County	Ongoing		Yes	Nationally
ACT2296	Northamptonshire County	Ongoing		Yes	nationally
ACT2239	South Northamptonshire District	Completed		No
ACT2240	South Northamptonshire District	Completed		No
ACT2304	South Northamptonshire District	Ongoing		Yes	Locally
ACT6829	Surrey County	Ongoing		Yes	Nationally
ACT6867	Bexley London Borough	Ongoing		Yes	Locally
ACT6873	Bexley London Borough	Completed		No
ACT6874	Bexley London Borough	Ongoing		Yes	Locally
ACT6875	Bexley London Borough	Ongoing		Yes	Locally
ACT6876	Bexley London Borough	Completed		No
ACT6877	Bexley London Borough	Completed		No
ACT6878	Bexley London Borough	Ongoing		Yes	Locally
ACT6879	Bexley London Borough	Completed		No
ACT6880	Bexley London Borough	Superseded	No Funding	No
ACT6881	Bexley London Borough	Ongoing		Yes	Locally
ACT6882	Bexley London Borough	Completed		No
ACT6883	Bexley London Borough	Completed		No
ACT6884	Bexley London Borough	Completed		No
ACT6885	Bexley London Borough	Completed		No
ACT6886	Bexley London Borough	Ongoing		Yes	Locally
ACT6887	Bexley London Borough	Completed		No
ACT6888	Bexley London Borough	Completed		No
ACT6889	Bexley London Borough	Ongoing		Yes	Locally
ACT6890	Bexley London Borough	Completed		No
ACT6891	Bexley London Borough	Ongoing		Yes	Nationally
ACT6892	Bexley London Borough	Ongoing		Yes	Locally
ACT6893	Bexley London Borough	Completed		No
ACT6894	Bexley London Borough	Ongoing		Yes	Nationally
ACT6895	Bexley London Borough	Completed		No
ACT6896	Bexley London Borough	Completed		No
ACT6897	Bexley London Borough	Ongoing		Yes	Locally
ACT6899	Bexley London Borough	Completed		No
ACT6900	Bexley London Borough	Ongoing		Yes	Nationally
ACT6901	Bexley London Borough	Completed		No
ACT6694	Bromley London Borough	Ongoing		Yes	Locally
ACT6729	Bromley London Borough	Ongoing		Yes	Locally
ACT6730	Bromley London Borough	Ongoing		Yes	Locally
ACT6739	Bromley London Borough	Ongoing		Yes	Locally
ACT6740	Bromley London Borough	Ongoing		Yes	Locally
ACT6742	Bromley London Borough	Ongoing		Yes	Locally
ACT6744	Bromley London Borough	Ongoing		Yes	Locally
ACT6745	Bromley London Borough	Ongoing		Yes	Locally
ACT3446	Canterbury District (B)	Ongoing		Yes	Nationally
ACT5987	Canterbury District (B)	Not started - proposed	No Funding	Yes	Locally
ACT5988	Canterbury District (B)	Ongoing		Yes	Nationally
ACT264	Croydon London Borough	Completed		No
ACT265	Croydon London Borough	Ongoing		Yes	Nationally
ACT266	Croydon London Borough	Ongoing		Yes	Nationally
ACT267	Croydon London Borough	Ongoing		Yes	Nationally
ACT268	Croydon London Borough	Ongoing		Yes	Nationally
ACT269	Croydon London Borough	Ongoing		Yes	Nationally
ACT270	Croydon London Borough	Superseded	It has been replaced by another measure	Yes	Nationally
ACT271	Croydon London Borough	Ongoing		Yes	Nationally
ACT272	Croydon London Borough	Ongoing		Yes	Nationally
ACT273	Croydon London Borough	Ongoing		Yes	Nationally
ACT274	Croydon London Borough	Ongoing		Yes	Nationally
ACT275	Croydon London Borough	Completed		No
ACT276	Croydon London Borough	Ongoing		Yes	Nationally
ACT277	Croydon London Borough	Ongoing		Yes	Nationally
ACT278	Croydon London Borough	Ongoing		Yes	Nationally
ACT279	Croydon London Borough	Ongoing		Yes	Nationally
ACT280	Croydon London Borough	Ongoing		Yes	Nationally
ACT281	Croydon London Borough	Ongoing		Yes	Nationally
ACT282	Croydon London Borough	Ongoing		Yes	Nationally
ACT283	Croydon London Borough	Ongoing		Yes	Nationally
ACT284	Croydon London Borough	Ongoing		Yes	Nationally
ACT285	Croydon London Borough	Ongoing		Yes	Nationally
ACT286	Croydon London Borough	Completed		No
ACT287	Croydon London Borough	Ongoing		Yes	Nationally
ACT288	Croydon London Borough	Ongoing		Yes	Nationally
ACT289	Croydon London Borough	Ongoing		Yes	Nationally
ACT290	Croydon London Borough	Completed		No
ACT291	Croydon London Borough	Completed		No
ACT292	Croydon London Borough	Ongoing		Yes	Nationally
ACT293	Croydon London Borough	Ongoing		Yes	Nationally
ACT294	Croydon London Borough	Completed		No
ACT295	Croydon London Borough	Completed		No
ACT296	Croydon London Borough	Completed		No
ACT297	Croydon London Borough	Completed		No
ACT298	Croydon London Borough	Ongoing		Yes	Nationally
ACT299	Croydon London Borough	Ongoing		Yes	Nationally
ACT300	Croydon London Borough	Ongoing		Yes	Nationally
ACT301	Croydon London Borough	Ongoing		Yes	Nationally
ACT302	Croydon London Borough	Completed		No
ACT303	Croydon London Borough	Ongoing		Yes	Nationally
ACT305	Croydon London Borough	Superseded	It has been replaced by another measure	Yes	Nationally
ACT306	Croydon London Borough	Ongoing		Yes	Nationally
ACT307	Croydon London Borough	Ongoing		Yes	Nationally
ACT308	Croydon London Borough	Ongoing		Yes	Nationally
ACT309	Croydon London Borough	Completed		No
ACT310	Croydon London Borough	Completed		No
ACT311	Croydon London Borough	Ongoing		Yes	Nationally
ACT312	Croydon London Borough	Ongoing		Yes	Nationally
ACT313	Croydon London Borough	Ongoing		Yes	Nationally
ACT314	Croydon London Borough	Ongoing		Yes	Nationally
ACT315	Croydon London Borough	Not started - proposed	Included elsewhere	Yes	Nationally
ACT316	Croydon London Borough	Ongoing		Yes	Nationally
ACT317	Croydon London Borough	Not started - proposed	Included elsewhere	Yes	Nationally
ACT318	Croydon London Borough	Ongoing		Yes	Nationally
ACT319	Croydon London Borough	Ongoing		Yes	Nationally
ACT320	Croydon London Borough	Ongoing		Yes	Nationally
ACT321	Croydon London Borough	Ongoing		Yes	Nationally
ACT322	Croydon London Borough	Ongoing		Yes	Nationally
ACT323	Croydon London Borough	Ongoing		Yes	Nationally
ACT324	Croydon London Borough	Completed		No
ACT325	Croydon London Borough	Ongoing		Yes	Nationally
ACT326	Croydon London Borough	Ongoing		Yes	Nationally
ACT327	Croydon London Borough	Ongoing		Yes	Nationally
ACT328	Croydon London Borough	Not started - proposed	Included elsewhere	Yes	Nationally
ACT329	Croydon London Borough	Completed		No
ACT330	Croydon London Borough	Completed		No
ACT331	Croydon London Borough	Completed		No
ACT332	Croydon London Borough	Completed		No
ACT333	Croydon London Borough	Completed		No
ACT6863	Croydon London Borough	Ongoing		Yes	Nationally
ACT6868	Croydon London Borough	Ongoing		Yes	Nationally
ACT6872	Croydon London Borough	Ongoing		Yes	Nationally
ACT6898	Croydon London Borough	Ongoing		Yes	Nationally
ACT3463	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT3464	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT3465	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT3466	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT3467	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT3469	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT3475	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT3476	Environment Agency	Completed		No
ACT3477	Environment Agency	Completed		No
ACT3478	Environment Agency	Completed		No
ACT3479	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT3480	Environment Agency	Superseded	Further work showed it was not viable	No
ACT3482	Environment Agency	Completed		No
ACT3483	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT3484	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT3485	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT3486	Environment Agency	Completed		No
ACT3487	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT3488	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT3489	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT3490	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT3491	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT3492	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT3566	Environment Agency	Ongoing		Yes	Nationally
ACT5909	Environment Agency	Ongoing		Yes	Nationally
ACT5910	Environment Agency	Completed		No
ACT5911	Environment Agency	Superseded	Further work showed it was not viable	No
ACT5912	Environment Agency	Completed		No
ACT5913	Environment Agency	Not started - agreed	Other - Awaiting outcome of Public Inquiry to Leigh Expansion	Yes	Locally
ACT5914	Environment Agency	Superseded	Further work showed it was not viable	No
ACT5915	Environment Agency	Completed		No
ACT5916	Environment Agency	Completed		No
ACT5917	Environment Agency	Completed		No
ACT5918	Environment Agency	Ongoing		Yes	Nationally
ACT5919	Environment Agency	Completed		No
ACT5920	Environment Agency	Ongoing		Yes	Nationally
ACT5921	Environment Agency	Completed		No
ACT5922	Environment Agency	Completed		No
ACT5923	Environment Agency	Ongoing		Yes	Nationally
ACT5924	Environment Agency	Completed		No
ACT5925	Environment Agency	Completed		No
ACT5926	Environment Agency	Ongoing		Yes	Nationally
ACT5927	Environment Agency	Completed		No
ACT5928	Environment Agency	Ongoing		Yes	Nationally
ACT5929	Environment Agency	Completed		No
ACT5930	Environment Agency	Completed		No
ACT5931	Environment Agency	Ongoing		Yes	Nationally
ACT5932	Environment Agency	Ongoing		Yes	Nationally
ACT5933	Environment Agency	Completed		No
ACT5934	Environment Agency	Ongoing		Yes	Nationally
ACT5935	Environment Agency	Not started - proposed	No Funding	Yes	Locally
ACT5936	Environment Agency	Ongoing		Yes	Nationally
ACT5937	Environment Agency	Completed		No
ACT5938	Environment Agency	Completed		No
ACT5939	Environment Agency	Ongoing		Yes	Nationally
ACT5940	Environment Agency	Ongoing		Yes	Nationally
ACT5941	Environment Agency	Ongoing		Yes	Nationally
ACT5942	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT5943	Environment Agency	Completed		No
ACT5944	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT5945	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT5946	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT5947	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT5948	Environment Agency	Ongoing		Yes	Nationally
ACT5949	Environment Agency	Ongoing		Yes	Nationally
ACT5950	Environment Agency	Ongoing		Yes	Nationally
ACT5951	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT5952	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT5953	Environment Agency	Ongoing		Yes	Nationally
ACT5954	Environment Agency	Completed		No
ACT5955	Environment Agency	Ongoing		Yes	Nationally
ACT5956	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT5957	Environment Agency	Ongoing		Yes	Nationally
ACT5958	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT5959	Environment Agency	Completed		No
ACT5960	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT5961	Environment Agency	Ongoing		Yes	Nationally
ACT5962	Environment Agency	Superseded	Other	No
ACT5963	Environment Agency	Superseded	Other	No
ACT5964	Environment Agency	Ongoing		Yes	Nationally
ACT5965	Environment Agency	Superseded	Other	No
ACT5966	Environment Agency	Ongoing		Yes	Nationally
ACT5967	Environment Agency	Ongoing		Yes	Nationally
ACT5968	Environment Agency	Superseded	Further work showed it was not viable	No
ACT5969	Environment Agency	Completed		No
ACT5970	Environment Agency	Completed		No
ACT5971	Environment Agency	Completed		No
ACT5972	Environment Agency	Completed		No
ACT5973	Environment Agency	Ongoing		Yes	Nationally
ACT5974	Environment Agency	Completed		No
ACT5975	Environment Agency	Ongoing		Yes	Nationally
ACT5976	Environment Agency	Ongoing		Yes	Nationally
ACT5977	Environment Agency	Ongoing		Yes	Nationally
ACT5978	Environment Agency	Ongoing		Yes	Nationally
ACT5979	Environment Agency	Superseded	Further work showed it was not viable	No
ACT5980	Environment Agency	Superseded	Further work showed it was not viable	No
ACT5981	Environment Agency	Superseded	Further work showed it was not viable	No
ACT5982	Environment Agency	Superseded	Further work showed it was not viable	No
ACT5983	Environment Agency	Superseded	Further work showed it was not viable	No
ACT5984	Environment Agency	Superseded	Further work showed it was not viable	No
ACT5985	Environment Agency	Superseded	Further work showed it was not viable	No
ACT5986	Environment Agency	Completed		No
ACT5987	Environment Agency	Not started - proposed	No Funding	Yes	Locally
ACT5988	Environment Agency	Ongoing		Yes	Nationally
ACT5989	Environment Agency	Completed		No
ACT5990	Environment Agency	Ongoing		Yes	Nationally
ACT5991	Environment Agency	Superseded	Further work showed it was not viable	No
ACT5992	Environment Agency	Superseded	Further work showed it was not viable	No
ACT5993	Environment Agency	Superseded	Further work showed it was not viable	No
ACT5994	Environment Agency	Completed		No
ACT5995	Environment Agency	Superseded	Further work showed it was not viable	No
ACT5996	Environment Agency	Not started - proposed	No Funding	Yes	Locally
ACT5997	Environment Agency	Completed		No
ACT5998	Environment Agency	Completed		No
ACT5999	Environment Agency	Ongoing		Yes	Nationally
ACT6000	Environment Agency	Completed		No
ACT6001	Environment Agency	Completed		No
ACT6002	Environment Agency	Ongoing		Yes	Nationally
ACT6003	Environment Agency	Ongoing		Yes	Nationally
ACT6004	Environment Agency	Ongoing		Yes	Nationally
ACT6005	Environment Agency	Superseded	Further work showed it was not viable	No
ACT6006	Environment Agency	Completed		No
ACT6007	Environment Agency	Superseded	Further work showed it was not viable	No
ACT6008	Environment Agency	Ongoing		Yes	Nationally
ACT6009	Environment Agency	Completed		No
ACT6010	Environment Agency	Ongoing		Yes	Nationally
ACT6011	Environment Agency	Completed		No
ACT6012	Environment Agency	Ongoing		Yes	Nationally
ACT6013	Environment Agency	Ongoing		Yes	Nationally
ACT6014	Environment Agency	Ongoing		Yes	Nationally
ACT6064	Environment Agency	Ongoing		Yes	Nationally
ACT6065	Environment Agency	Ongoing		Yes	Nationally
ACT6066	Environment Agency	Ongoing		Yes	Nationally
ACT6067	Environment Agency	Completed		No
ACT6068	Environment Agency	Ongoing		Yes	Nationally
ACT6070	Environment Agency	Completed		No
ACT6071	Environment Agency	Completed		No
ACT6073	Environment Agency	Ongoing		Yes	Nationally
ACT6074	Environment Agency	Superseded	Further work showed it was not viable	No
ACT6075	Environment Agency	Ongoing		Yes	Nationally
ACT6076	Environment Agency	Ongoing		Yes	Nationally
ACT6078	Environment Agency	Ongoing		Yes	Nationally
ACT6079	Environment Agency	Completed		No
ACT6080	Environment Agency	Ongoing		Yes	Nationally
ACT6082	Environment Agency	Ongoing		Yes	Nationally
ACT640	Environment Agency	Ongoing		Yes	Nationally
ACT641	Environment Agency	Ongoing		Yes	Nationally
ACT642	Environment Agency	Ongoing		Yes	Nationally
ACT643	Environment Agency	Ongoing		Yes	Nationally
ACT644	Environment Agency	Ongoing		Yes	Nationally
ACT645	Environment Agency	Ongoing		Yes	Nationally
ACT646	Environment Agency	Ongoing		Yes	Nationally
ACT647	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT648	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT649	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT650	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT651	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT652	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT653	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT654	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT655	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT656	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT657	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT658	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT659	Environment Agency	Superseded	Further work showed it was not viable	No
ACT661	Environment Agency	Superseded	It has been replaced by another measure - Not within FRMP cycle 2 FRA	No
ACT662	Environment Agency	Superseded	It has been replaced by another measure - Not within FRMP cycle 2 FRA	No
ACT663	Environment Agency	Superseded	It has been replaced by another measure - Not within FRMP cycle 2 FRA	No
ACT664	Environment Agency	Superseded	It has been replaced by another measure - Not within FRMP cycle 2 FRA	No
ACT665	Environment Agency	Superseded	It has been replaced by another measure - Not within FRMP cycle 2 FRA	No
ACT666	Environment Agency	Ongoing		Yes	Nationally
ACT667	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT668	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT669	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT670	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT671	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT672	Environment Agency	Superseded	Further work showed it was not viable	No
ACT673	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT674	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT675	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT676	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT677	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT678	Environment Agency	Ongoing		Yes	Nationally
ACT679	Environment Agency	Ongoing		Yes	Nationally
ACT680	Environment Agency	Ongoing		Yes	Nationally
ACT681	Environment Agency	Ongoing		Yes	Nationally
ACT682	Environment Agency	Ongoing		Yes	Nationally
ACT683	Environment Agency	Ongoing		Yes	Nationally
ACT684	Environment Agency	Ongoing		Yes	Nationally
ACT685	Environment Agency	Ongoing		Yes	Nationally
ACT686	Environment Agency	Superseded	Further work showed it was not viable	No
ACT687	Environment Agency	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT660	Environment Agency	Superseded	Further work showed it was not viable	No
ACT6842	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6843	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6844	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6845	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6846	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6847	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6848	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6849	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6850	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6851	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6852	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6853	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6854	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6855	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6856	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6857	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6858	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6859	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6908	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6909	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6911	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6914	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6915	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6920	Greenwich London Borough	Completed		No
ACT6922	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6923	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6924	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6925	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6926	Greenwich London Borough	Ongoing		Yes	Nationally
ACT6927	Greenwich London Borough	Ongoing		Yes	Nationally
ACT5938	Kent	Completed		No
ACT5923	Kent County	Ongoing		Yes	Nationally
ACT5935	Kent County	Not started - proposed	No Funding	Yes	Locally
ACT6864	Kent County	Ongoing		Yes	Nationally
ACT6865	Kent County	Completed		No
ACT6866	Kent County	Ongoing		Yes	Nationally
ACT6869	Kent County	Completed		No
ACT6871	Kent County	Ongoing		Yes	Nationally
ACT501	Kingston upon Thames London Borough	Completed		No
ACT502	Kingston upon Thames London Borough	Completed		No
ACT503	Kingston upon Thames London Borough	Completed		No
ACT504	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT505	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT506	Kingston upon Thames London Borough	Completed		No
ACT507	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT508	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT509	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT510	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT511	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT512	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT513	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT514	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT515	Kingston upon Thames London Borough	Completed		No
ACT516	Kingston upon Thames London Borough	Completed		No
ACT517	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT518	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT519	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT520	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT521	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT522	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT523	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT524	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT525	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT526	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT527	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT528	Kingston upon Thames London Borough	Completed		No
ACT529	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT530	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT531	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT532	Kingston upon Thames London Borough	Completed		No
ACT533	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT534	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT535	Kingston upon Thames London Borough	Ongoing		Yes	Nationally
ACT6256	Lambeth London Borough	Ongoing		Yes	Nationally
ACT6257	Lambeth London Borough	Ongoing		Yes	Nationally
ACT6258	Lambeth London Borough	Ongoing - construction		Yes	Locally
ACT6259	Lambeth London Borough	Ongoing		Yes	Locally
ACT6789	Lambeth London Borough	Ongoing		Yes	Nationally
ACT6835	Lambeth London Borough	Ongoing		Yes	Nationally
ACT6860	Lambeth London Borough	Completed		No
ACT6861	Lambeth London Borough	Superseded	Other - Not within FRMP cycle 2 FRA or SA	No
ACT6862	Lambeth London Borough	Superseded	Further work showed it was not viable	No
ACT7131	Lewisham London Borough	Ongoing		Yes	Locally
ACT7158	Lewisham London Borough	Ongoing		Yes	Locally
ACT7159	Lewisham London Borough	Ongoing		Yes	Locally
ACT7160	Lewisham London Borough	Ongoing		Yes	Locally
ACT7161	Lewisham London Borough	Ongoing		Yes	Locally
ACT7162	Lewisham London Borough	Completed		No
ACT7163	Lewisham London Borough	Completed		No
ACT7164	Lewisham London Borough	Superseded	Further work showed it was not viable	No
ACT7165	Lewisham London Borough	Ongoing		Yes	Nationally
ACT5939	Maidstone District (B)	Ongoing		Yes	Nationally
ACT5941	Maidstone District (B)	Ongoing		Yes	Nationally
ACT6077	Maidstone District (B)	Ongoing		Yes	Nationally
ACT5953	Medway Unitary Authority	Ongoing		Yes	Nationally
ACT5955	Medway Unitary Authority	Ongoing		Yes	Nationally
ACT5971	Medway Unitary Authority	Completed		No
ACT5972	Medway Unitary Authority	Completed		No
ACT5982	Medway Unitary Authority	Superseded	Further work showed it was not viable	No
ACT5983	Medway Unitary Authority	Superseded	Further work showed it was not viable	No
ACT6014	Medway Unitary Authority	Ongoing		Yes	Nationally
ACT6044	Medway Unitary Authority	Ongoing		Yes	Nationally
ACT6045	Medway Unitary Authority	Ongoing		Yes	Nationally
ACT6046	Medway Unitary Authority	Ongoing		Yes	Nationally
ACT6047	Medway Unitary Authority	Ongoing		Yes	Nationally
ACT6048	Medway Unitary Authority	Ongoing		Yes	Nationally
ACT6049	Medway Unitary Authority	Ongoing		Yes	Nationally
ACT6050	Medway Unitary Authority	Ongoing		Yes	Nationally
ACT6051	Medway Unitary Authority	Ongoing		Yes	Nationally
ACT6052	Medway Unitary Authority	Ongoing		Yes	Nationally
ACT6053	Medway Unitary Authority	Ongoing		Yes	Nationally
ACT6054	Medway Unitary Authority	Ongoing		Yes	Nationally
ACT436	Merton London Borough	Completed		No
ACT437	Merton London Borough	Completed		No
ACT438	Merton London Borough	Completed		No
ACT439	Merton London Borough	Ongoing		Yes	Nationally
ACT440	Merton London Borough	Ongoing		Yes	Nationally
ACT441	Merton London Borough	Ongoing		Yes	Nationally
ACT442	Merton London Borough	Completed		No
ACT443	Merton London Borough	Completed		No
ACT444	Merton London Borough	Completed		No
ACT445	Merton London Borough	Completed		No
ACT446	Merton London Borough	Completed		No
ACT447	Merton London Borough	Completed		No
ACT448	Merton London Borough	Completed		No
ACT449	Merton London Borough	Completed		No
ACT450	Merton London Borough	Ongoing		Yes	Nationally
ACT451	Merton London Borough	Ongoing		Yes	Nationally
ACT452	Merton London Borough	Completed		No
ACT453	Merton London Borough	Completed		No
ACT454	Merton London Borough	Completed		No
ACT455	Merton London Borough	Ongoing		Yes	Nationally
ACT456	Merton London Borough	Ongoing		Yes	Nationally
ACT457	Merton London Borough	Completed		No
ACT458	Merton London Borough	Ongoing		Yes	Nationally
ACT459	Merton London Borough	Ongoing		Yes	Nationally
ACT460	Merton London Borough	Ongoing		Yes	Nationally
ACT461	Merton London Borough	Ongoing		Yes	Nationally
ACT462	Merton London Borough	Ongoing		Yes	Nationally
ACT463	Merton London Borough	Ongoing		Yes	Nationally
ACT464	Merton London Borough	Ongoing		Yes	Nationally
ACT465	Merton London Borough	Ongoing		Yes	Nationally
ACT466	Merton London Borough	Ongoing		Yes	Nationally
ACT467	Merton London Borough	Ongoing		Yes	Nationally
ACT468	Merton London Borough	Ongoing		Yes	Nationally
ACT469	Merton London Borough	Completed		No
ACT470	Merton London Borough	Completed		No
ACT471	Merton London Borough	Completed		No
ACT472	Merton London Borough	Completed		No
ACT473	Merton London Borough	Completed		No
ACT474	Merton London Borough	Ongoing		Yes	Nationally
ACT475	Merton London Borough	Completed		No
ACT476	Merton London Borough	Ongoing		Yes	Nationally
ACT477	Merton London Borough	Completed		No
ACT478	Merton London Borough	Completed		No
ACT479	Merton London Borough	Completed		No
ACT480	Merton London Borough	Completed		No
ACT481	Merton London Borough	Completed		No
ACT482	Merton London Borough	Completed		No
ACT483	Merton London Borough	Ongoing		Yes	Nationally
ACT484	Merton London Borough	Completed		No
ACT485	Merton London Borough	Ongoing		Yes	Nationally
ACT486	Merton London Borough	Ongoing		Yes	Nationally
ACT487	Merton London Borough	Completed		No
ACT488	Merton London Borough	Completed		No
ACT489	Merton London Borough	Completed		No
ACT490	Merton London Borough	Ongoing		Yes	Nationally
ACT491	Merton London Borough	Completed		No
ACT492	Merton London Borough	Completed		No
ACT493	Merton London Borough	Completed		No
ACT494	Merton London Borough	Completed		No
ACT495	Merton London Borough	Completed		No
ACT496	Merton London Borough	Completed		No
ACT497	Merton London Borough	Completed		No
ACT498	Merton London Borough	Ongoing		Yes	Nationally
ACT499	Merton London Borough	Completed		No
ACT500	Merton London Borough	Completed		No
ACT334	Richmond upon Thames London Borough	Ongoing		Yes	Nationally
ACT335	Richmond upon Thames London Borough	Ongoing		Yes	Nationally
ACT336	Richmond upon Thames London Borough	Ongoing		Yes	Nationally
ACT337	Richmond upon Thames London Borough	Ongoing		Yes	Nationally
ACT338	Richmond upon Thames London Borough	Ongoing		Yes	Nationally
ACT339	Richmond upon Thames London Borough	Ongoing		Yes	Nationally
ACT340	Richmond upon Thames London Borough	Ongoing		Yes	Nationally
ACT341	Richmond upon Thames London Borough	Ongoing		Yes	Nationally
ACT342	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT343	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT344	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT345	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT346	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT347	Richmond upon Thames London Borough	Ongoing		Yes	Nationally
ACT348	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT349	Richmond upon Thames London Borough	Ongoing		Yes	Nationally
ACT350	Richmond upon Thames London Borough	Ongoing		Yes	Nationally
ACT351	Richmond upon Thames London Borough	Ongoing		Yes	Nationally
ACT352	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT353	Richmond upon Thames London Borough	Ongoing		Yes	Nationally
ACT354	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT355	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT356	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT357	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT358	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT359	Richmond upon Thames London Borough	Ongoing		Yes	Nationally
ACT360	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT361	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT362	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT363	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT364	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT365	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT366	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT367	Richmond upon Thames London Borough	Ongoing		Yes	Nationally
ACT368	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT369	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT370	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT371	Richmond upon Thames London Borough	Ongoing		Yes	Nationally
ACT372	Richmond upon Thames London Borough	Ongoing		Yes	Nationally
ACT373	Richmond upon Thames London Borough	Ongoing		Yes	Nationally
ACT3736	Richmond upon Thames London Borough	Ongoing		Yes	Nationally
ACT374	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT3740	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT375	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT376	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT377	Richmond upon Thames London Borough	Ongoing		Yes	Nationally
ACT378	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT379	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT380	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT381	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT382	Richmond upon Thames London Borough	Not started - proposed	No Funding	Yes	Locally
ACT6069	Sevenoaks District	Completed		No
ACT3493	Southwark London Borough	Completed		No
ACT6820	Southwark London Borough	Completed		No
ACT6821	Southwark London Borough	Completed		No
ACT6822	Southwark London Borough	Completed		No
ACT6823	Southwark London Borough	Ongoing		Yes	Nationally
ACT6824	Southwark London Borough	Ongoing		Yes	Locally
ACT6825	Southwark London Borough	Ongoing		Yes	Locally
ACT6827	Southwark London Borough	Ongoing		Yes	Locally
ACT6828	Southwark London Borough	Ongoing		Yes	Locally
ACT6830	Southwark London Borough	Ongoing		Yes	Nationally
ACT6831	Southwark London Borough	Ongoing		Yes	Locally
ACT6832	Southwark London Borough	Ongoing		Yes	Locally
ACT6833	Southwark London Borough	Not started - proposed	No Funding	Yes	Locally
ACT6834	Southwark London Borough	Ongoing		Yes	Locally
ACT6836	Southwark London Borough	Ongoing		Yes	Nationally
ACT6837	Southwark London Borough	Not started - proposed	No Funding	Yes	Locally
ACT6838	Southwark London Borough	Ongoing		Yes	Locally
ACT6839	Southwark London Borough	Ongoing		Yes	Locally
ACT6840	Southwark London Borough	Ongoing		Yes	Locally
ACT6841	Southwark London Borough	Ongoing		Yes	Locally
ACT383	Sutton London Borough	Ongoing		Yes	Nationally
ACT384	Sutton London Borough	Ongoing		Yes	Nationally
ACT385	Sutton London Borough	Ongoing		Yes	Nationally
ACT386	Sutton London Borough	Ongoing		Yes	Nationally
ACT387	Sutton London Borough	Completed		No
ACT388	Sutton London Borough	Completed		No
ACT389	Sutton London Borough	Ongoing		Yes	Nationally
ACT390	Sutton London Borough	Ongoing		Yes	Nationally
ACT391	Sutton London Borough	Completed		No
ACT392	Sutton London Borough	Completed		No
ACT393	Sutton London Borough	Ongoing		Yes	Nationally
ACT394	Sutton London Borough	Ongoing		Yes	Nationally
ACT395	Sutton London Borough	Ongoing		Yes	Nationally
ACT396	Sutton London Borough	Ongoing		Yes	Nationally
ACT397	Sutton London Borough	Ongoing		Yes	Nationally
ACT398	Sutton London Borough	Not started - agreed	No Funding	Yes	Locally
ACT399	Sutton London Borough	Not started - agreed	No Funding	Yes	Locally
ACT400	Sutton London Borough	Not started - agreed	No Funding	Yes	Locally
ACT401	Sutton London Borough	Completed		No
ACT402	Sutton London Borough	Completed		No
ACT403	Sutton London Borough	Completed		No
ACT404	Sutton London Borough	Completed		No
ACT405	Sutton London Borough	Completed		No
ACT406	Sutton London Borough	Ongoing		Yes	Nationally
ACT407	Sutton London Borough	Not started - agreed	No Funding	Yes	Locally
ACT408	Sutton London Borough	Completed		No
ACT409	Sutton London Borough	Completed		No
ACT410	Sutton London Borough	Not started - agreed	No Funding	Yes	Locally
ACT411	Sutton London Borough	Ongoing		Yes	Nationally
ACT412	Sutton London Borough	Ongoing		Yes	Nationally
ACT413	Sutton London Borough	Not started - agreed	No Funding	Yes	Locally
ACT414	Sutton London Borough	Ongoing		Yes	Nationally
ACT415	Sutton London Borough	Ongoing		Yes	Nationally
ACT416	Sutton London Borough	Ongoing		Yes	Nationally
ACT417	Sutton London Borough	Ongoing		Yes	Nationally
ACT418	Sutton London Borough	Ongoing		Yes	Nationally
ACT419	Sutton London Borough	Ongoing		Yes	Nationally
ACT420	Sutton London Borough	Ongoing		Yes	Nationally
ACT421	Sutton London Borough	Ongoing		Yes	Nationally
ACT422	Sutton London Borough	Ongoing		Yes	Nationally
ACT423	Sutton London Borough	Completed		No
ACT424	Sutton London Borough	Ongoing		Yes	Nationally
ACT425	Sutton London Borough	Ongoing		Yes	Nationally
ACT426	Sutton London Borough	Completed		No
ACT427	Sutton London Borough	Ongoing		Yes	Nationally
ACT428	Sutton London Borough	Completed		No
ACT429	Sutton London Borough	Not started - agreed	No Funding	Yes	Locally
ACT430	Sutton London Borough	Ongoing		Yes	Nationally
ACT431	Sutton London Borough	Ongoing		Yes	Nationally
ACT432	Sutton London Borough	Not started - agreed	No Funding	Yes	Locally
ACT433	Sutton London Borough	Not started - agreed	No Funding	Yes	Locally
ACT434	Sutton London Borough	Completed		No
ACT435	Sutton London Borough	Ongoing		Yes	Nationally
ACT6457	Sutton London Borough	Ongoing		Yes	Nationally
ACT5948	Swale District (B)	Ongoing		Yes	Nationally
ACT5949	Swale District (B)	Ongoing		Yes	Nationally
ACT5950	Swale District (B)	Ongoing		Yes	Nationally
ACT5968	Swale District (B)	Superseded	Further work showed it was not viable	No
ACT5969	Swale District (B)	Completed		No
ACT5970	Swale District (B)	Completed		No
ACT5974	Swale District (B)	Completed		No
ACT5975	Swale District (B)	Ongoing		Yes	Nationally
ACT5984	Swale District (B)	Superseded	Further work showed it was not viable	No
ACT5985	Swale District (B)	Superseded	Further work showed it was not viable	No
ACT5991	Swale District (B)	Superseded	Further work showed it was not viable	No
ACT5992	Swale District (B)	Superseded	Further work showed it was not viable	No
ACT5996	Swale District (B)	Not started - proposed	No Funding	Yes	Locally
ACT6009	Swale District (B)	Completed		No
ACT6010	Swale District (B)	Ongoing		Yes	Nationally
ACT6907	Thurrock Unitary Authority	Ongoing		Yes	Nationally
ACT6912	Thurrock Unitary Authority	Ongoing		Yes	Nationally
ACT6916	Thurrock Unitary Authority	Completed		No
ACT6917	Thurrock Unitary Authority	Ongoing		Yes	Nationally
ACT6918	Thurrock Unitary Authority	Ongoing		Yes	Nationally
ACT6919	Thurrock Unitary Authority	Ongoing		Yes	Nationally
ACT6921	Thurrock Unitary Authority	Not started - proposed	No Funding	No
ACT7070	Thurrock Unitary Authority	Ongoing		Yes	Nationally
ACT7071	Thurrock Unitary Authority	Ongoing		Yes	Nationally
ACT7072	Thurrock Unitary Authority	Not started - proposed	Postponed	No
ACT7073	Thurrock Unitary Authority	Ongoing		Yes	Nationally
ACT7074	Thurrock Unitary Authority	Not started - proposed	No Funding	No
ACT7075	Thurrock Unitary Authority	Not started - proposed	No Funding	No
ACT7076	Thurrock Unitary Authority	Not started - proposed	No Funding	No
ACT7077	Thurrock Unitary Authority	Not started - proposed	No Funding	No
ACT7078	Thurrock Unitary Authority	Not started - proposed	No Funding	No
ACT7079	Thurrock Unitary Authority	Not started - proposed	No Funding	No
ACT7080	Thurrock Unitary Authority	Ongoing		Yes	Nationally
ACT7081	Thurrock Unitary Authority	Not started - proposed	No Funding	No
ACT5926	Tonbridge and Malling District (B)	Ongoing		Yes	Nationally
ACT5922	Tunbridge Wells District (B)	Completed		No
ACT5931	Tunbridge Wells District (B)	Ongoing		Yes	Nationally
ACT5934	Upper Medway IDB	Ongoing		Yes	Nationally
ACT590	Wandsworth London Borough	Completed		No
ACT591	Wandsworth London Borough	Not started - proposed	No Funding	Yes	Locally
ACT592	Wandsworth London Borough	Ongoing		Yes	Nationally
ACT593	Wandsworth London Borough	Not started - proposed	No Funding	Yes	Locally
ACT594	Wandsworth London Borough	Completed		No
ACT595	Wandsworth London Borough	Completed		No
ACT596	Wandsworth London Borough	Completed		No
ACT597	Wandsworth London Borough	Superseded	Postponed	Yes	Locally
ACT598	Wandsworth London Borough	Not started - proposed	No Funding	Yes	Locally
ACT599	Wandsworth London Borough	Not started - proposed	No Funding	Yes	Locally
ACT600	Wandsworth London Borough	Not started - proposed	No Funding	Yes	Locally
ACT601	Wandsworth London Borough	Not started - proposed	No Funding	Yes	Locally
ACT602	Wandsworth London Borough	Not started - proposed	No Funding	Yes	Locally
ACT603	Wandsworth London Borough	Not started - proposed	No Funding	Yes	Locally
ACT604	Wandsworth London Borough	Ongoing		Yes	Nationally
ACT605	Wandsworth London Borough	Ongoing		Yes	Nationally
ACT606	Wandsworth London Borough	Ongoing		Yes	Nationally
ACT607	Wandsworth London Borough	Ongoing		Yes	Locally
ACT608	Wandsworth London Borough	Ongoing		Yes	Locally
ACT609	Wandsworth London Borough	Ongoing		Yes	Locally
ACT610	Wandsworth London Borough	Ongoing		Yes	Locally
ACT611	Wandsworth London Borough	Ongoing		Yes	Locally
ACT612	Wandsworth London Borough	Ongoing		Yes	Locally
ACT613	Wandsworth London Borough	Ongoing		Yes	Locally
ACT614	Wandsworth London Borough	Ongoing		Yes	Locally
ACT615	Wandsworth London Borough	Completed		No
ACT616	Wandsworth London Borough	Not started - proposed	No Funding	Yes	Locally
ACT617	Wandsworth London Borough	Ongoing		Yes	Nationally
ACT618	Wandsworth London Borough	Ongoing		Yes	Nationally
ACT619	Wandsworth London Borough	Ongoing		Yes	Nationally
ACT620	Wandsworth London Borough	Ongoing		Yes	Nationally
ACT621	Wandsworth London Borough	Ongoing		Yes	Nationally
ACT622	Wandsworth London Borough	Ongoing		Yes	Nationally
ACT623	Wandsworth London Borough	Completed		No
ACT624	Wandsworth London Borough	Not started - proposed	No Funding	Yes	Locally
ACT625	Wandsworth London Borough	Completed		No
ACT626	Wandsworth London Borough	Not started - proposed	No Funding	Yes	Locally
ACT627	Wandsworth London Borough	Ongoing		Yes	Nationally
ACT628	Wandsworth London Borough	Not started - proposed	No Funding	No
ACT629	Wandsworth London Borough	Not started - proposed	No Funding	Yes	Locally
ACT630	Wandsworth London Borough	Ongoing		Yes	Nationally
ACT631	Wandsworth London Borough	Completed		No
ACT632	Wandsworth London Borough	Not started - proposed	No Funding	Yes	Locally
ACT633	Wandsworth London Borough	Not started - proposed	No Funding	Yes	Locally
ACT634	Wandsworth London Borough	Not started - proposed	No Funding	Yes	Locally
ACT635	Wandsworth London Borough	Not started - proposed	No Funding	Yes	Locally
ACT636	Wandsworth London Borough	Not started - proposed	No Funding	Yes	Locally
ACT637	Wandsworth London Borough	Not started - proposed	No Funding	Yes	Locally
ACT638	Wandsworth London Borough	Not started - proposed	No Funding	Yes	Locally
ACT639	Wandsworth London Borough	Not started - proposed	No Funding	Yes	Locally
ACT5916	Wealden District	Completed		No
ACT7154	Barking and Dagenham London Borough	Completed		No
ACT3709	Barnet London Borough	Ongoing		Yes	Locally
ACT7142	Barnet London Borough	Ongoing		Yes	Locally
ACT7143	Barnet London Borough	Ongoing		Yes	Locally
ACT7144	Barnet London Borough	Ongoing		Yes	Locally
ACT7146	Barnet London Borough	Ongoing		Yes	Locally
ACT7147	Barnet London Borough	Ongoing		Yes	Nationally
ACT7148	Barnet London Borough	Ongoing		Yes	Nationally
ACT7150	Barnet London Borough	Superseded	Included elsewhere	Yes	Nationally
ACT7151	Barnet London Borough	Completed		No
ACT7152	Barnet London Borough	Ongoing		Yes	Nationally
ACT7153	Barnet London Borough	Ongoing		Yes	Nationally
ACT6208	Brent London Borough	Ongoing		Yes	Nationally
ACT6209	Brent London Borough	Completed		No
ACT6210	Brent London Borough	Completed		No
ACT6211	Brent London Borough	Ongoing		Yes	Nationally
ACT6212	Brent London Borough	Ongoing		Yes	Nationally
ACT6213	Brent London Borough	Ongoing		Yes	Locally
ACT6214	Brent London Borough	Ongoing		Yes	Locally
ACT6215	Brent London Borough	Ongoing		Yes	Nationally
ACT6216	Brent London Borough	Completed		No
ACT6217	Brent London Borough	Ongoing		Yes	Nationally
ACT6218	Brent London Borough	Ongoing		Yes	Locally
ACT6219	Brent London Borough	Completed		No
ACT1594	Camden London Borough	Ongoing		Yes	Locally
ACT1596	Camden London Borough	Completed		No
ACT1597	Camden London Borough	Completed		No
ACT1599	Camden London Borough	Completed		No
ACT152	City of London Borough	Completed		No
ACT153	City of London Borough	Ongoing		Yes	Locally
ACT154	City of London Borough	Ongoing		Yes	Locally
ACT155	City of London Borough	Ongoing		Yes	Locally
ACT156	City of London Borough	Ongoing		Yes	Locally
ACT157	City of London Borough	Ongoing		Yes	Locally
ACT158	City of London Borough	Ongoing		Yes	Nationally
ACT1598	City of London Borough	Completed		No
ACT241	Ealing London Borough	Ongoing		Yes	Nationally
ACT242	Ealing London Borough	Ongoing		Yes	Locally
ACT243	Ealing London Borough	Ongoing		Yes	Nationally
ACT244	Ealing London Borough	Ongoing		Yes	Locally
ACT245	Ealing London Borough	Ongoing		Yes	Nationally
ACT246	Ealing London Borough	Ongoing		Yes	Locally
ACT247	Ealing London Borough	Ongoing		Yes	Locally
ACT248	Ealing London Borough	Ongoing		Yes	Nationally
ACT249	Ealing London Borough	Ongoing		Yes	Locally
ACT250	Ealing London Borough	Ongoing		Yes	Locally
ACT251	Ealing London Borough	Completed		No
ACT252	Ealing London Borough	Ongoing		Yes	Locally
ACT253	Ealing London Borough	Completed		No
ACT254	Ealing London Borough	Ongoing		Yes	Locally
ACT255	Ealing London Borough	Ongoing		Yes	Nationally
ACT256	Ealing London Borough	Ongoing		Yes	Nationally
ACT257	Ealing London Borough	Completed		No
ACT258	Ealing London Borough	Ongoing		Yes	Locally
ACT259	Ealing London Borough	Ongoing		Yes	Nationally
ACT260	Ealing London Borough	Ongoing		Yes	Nationally
ACT261	Ealing London Borough	Completed		No
ACT262	Ealing London Borough	Completed		No
ACT263	Ealing London Borough	Completed		No
ACT954	Enfield London Borough	Completed		No
ACT955	Enfield London Borough	Ongoing		Yes	Locally
ACT956	Enfield London Borough	Ongoing		Yes	Locally
ACT957	Enfield London Borough	Superseded	Further work showed it was not viable	No
ACT958	Enfield London Borough	Ongoing		Yes	Locally
ACT959	Enfield London Borough	Superseded	Further work showed it was not viable	No
ACT960	Enfield London Borough	Ongoing		Yes	Locally
ACT961	Enfield London Borough	Ongoing		Yes	Locally
ACT962	Enfield London Borough	Superseded	Included elsewhere	No
ACT963	Enfield London Borough	Ongoing		Yes	Locally
ACT964	Enfield London Borough	Ongoing		Yes	Locally
ACT965	Enfield London Borough	Completed		No
ACT966	Enfield London Borough	Completed		No
ACT967	Enfield London Borough	Ongoing		Yes	Locally
ACT968	Enfield London Borough	Ongoing		No
ACT969	Enfield London Borough	Ongoing		Yes	Locally
ACT970	Enfield London Borough	Ongoing		Yes	Locally
ACT971	Enfield London Borough	Ongoing		Yes	Locally
ACT3685	Environment Agency	Ongoing		Yes	Locally
ACT3686	Environment Agency	Ongoing		Yes	Locally
ACT3687	Environment Agency	Completed		No
ACT3688	Environment Agency	Ongoing		Yes	Locally
ACT3689	Environment Agency	Superseded	Postponed	No
ACT3690	Environment Agency	Ongoing		Yes	Locally
ACT3691	Environment Agency	Ongoing		Yes	Locally
ACT3692	Environment Agency	Superseded	Further work showed it was not viable	No
ACT3693	Environment Agency	Ongoing		Yes	Locally
ACT3694	Environment Agency	Ongoing		Yes	Locally
ACT3695	Environment Agency	Ongoing		Yes	Locally
ACT3696	Environment Agency	Ongoing		Yes	Locally
ACT3697	Environment Agency	Ongoing		Yes	Locally
ACT3698	Environment Agency	Ongoing		Yes	Locally
ACT3699	Environment Agency	Ongoing		Yes	Locally
ACT3700	Environment Agency	Completed		No
ACT3701	Environment Agency	Ongoing		Yes	Locally
ACT3702	Environment Agency	Ongoing		Yes	Nationally
ACT3703	Environment Agency	Cancelled	Included elsewhere	No
ACT3704	Environment Agency	Ongoing		Yes	Locally
ACT3705	Environment Agency	Ongoing		Yes	Locally
ACT3706	Environment Agency	Ongoing		Yes	Nationally
ACT3707	Environment Agency	Ongoing		Yes	Locally
ACT3708	Environment Agency	Ongoing		Yes	Locally
ACT3710	Environment Agency	Superseded	Further work showed it was not viable	No
ACT3711	Environment Agency	Superseded	Included elsewhere	No
ACT3713	Environment Agency	Superseded	Included elsewhere	No
ACT3714	Environment Agency	Superseded	Further work showed it was not viable	No
ACT3715	Environment Agency	Superseded	Further work showed it was not viable	No
ACT3716	Environment Agency	Ongoing		Yes	Locally
ACT3717	Environment Agency	Ongoing		Yes	Locally
ACT3718	Environment Agency	Ongoing		Yes	Locally
ACT3719	Environment Agency	Ongoing		Yes	Nationally
ACT3720	Environment Agency	Ongoing		Yes	Nationally
ACT3721	Environment Agency	Ongoing		Yes	Locally
ACT3722	Environment Agency	Ongoing		Yes	Nationally
ACT3723	Environment Agency	Ongoing		Yes	Locally
ACT3724	Environment Agency	Ongoing		Yes	Locally
ACT3725	Environment Agency	Completed		No
ACT3726	Environment Agency	Ongoing		Yes	Locally
ACT3727	Environment Agency	Ongoing		Yes	Locally
ACT3728	Environment Agency	Completed		No
ACT3729	Environment Agency	Completed		No
ACT3730	Environment Agency	Ongoing		Yes	Locally
ACT3731	Environment Agency	Ongoing		Yes	Locally
ACT3732	Environment Agency	Superseded	Included elsewhere	No
ACT3733	Environment Agency	Ongoing		Yes	Locally
ACT3734	Environment Agency	Ongoing		Yes	Nationally
ACT3735	Environment Agency	Ongoing		Yes	Locally
ACT3737	Environment Agency	Superseded	Included elsewhere	No
ACT3738	Environment Agency	Ongoing		Yes	Nationally
ACT3742	Environment Agency	Completed		No
ACT3743	Environment Agency	Ongoing		Yes	Nationally
ACT3744	Environment Agency	Ongoing		Yes	Nationally
ACT3745	Environment Agency	Ongoing		Yes	Nationally
ACT3746	Environment Agency	Completed		No
ACT3747	Environment Agency	Completed		No
ACT3748	Environment Agency	Ongoing		Yes	Nationally
ACT3749	Environment Agency	Ongoing		Yes	Nationally
ACT3750	Environment Agency	Ongoing		Yes	Locally
ACT3751	Environment Agency	Ongoing		Yes	Nationally
ACT3752	Environment Agency	Completed		No
ACT3753	Environment Agency	Completed		No
ACT3754	Environment Agency	Ongoing		Yes	Locally
ACT3898	Environment Agency	Ongoing		Yes	Nationally
ACT3899	Environment Agency	Ongoing		Yes	Nationally
ACT3900	Environment Agency	Ongoing		Yes	Nationally
ACT3901	Environment Agency	Ongoing		Yes	Nationally
ACT3902	Environment Agency	Ongoing		Yes	Nationally
ACT3903	Environment Agency	Ongoing		Yes	Nationally
ACT3904	Environment Agency	Superseded	No Funding	No
ACT3905	Environment Agency	Ongoing		Yes	Nationally
ACT3906	Environment Agency	Completed		No
ACT3907	Environment Agency	Ongoing		Yes	Nationally
ACT3908	Environment Agency	Ongoing		Yes	Nationally
ACT3909	Environment Agency	Ongoing		Yes	Nationally
ACT3910	Environment Agency	Completed		No
ACT3911	Environment Agency	Ongoing		Yes	Nationally
ACT3912	Environment Agency	Ongoing		Yes	Nationally
ACT3913	Environment Agency	Ongoing		Yes	Nationally
ACT3914	Environment Agency	Completed		No
ACT3915	Environment Agency	Ongoing		Yes	Nationally
ACT3916	Environment Agency	Completed		No
ACT3917	Environment Agency	Ongoing		Yes	Nationally
ACT3918	Environment Agency	Ongoing		Yes	Nationally
ACT3919	Environment Agency	Ongoing		Yes	Locally
ACT3920	Environment Agency	Ongoing		Yes	Nationally
ACT3921	Environment Agency	Completed		No
ACT3922	Environment Agency	Superseded	Further work showed it was not viable	No
ACT3923	Environment Agency	Ongoing		Yes	Locally
ACT3924	Environment Agency	Ongoing		Yes	Nationally
ACT3926	Environment Agency	Completed		No
ACT3927	Environment Agency	Ongoing		Yes	Locally
ACT3928	Environment Agency	Ongoing		Yes	Nationally
ACT3929	Environment Agency	Superseded	Further work showed it was not viable	No
ACT3930	Environment Agency	Ongoing		Yes	Nationally
ACT3931	Environment Agency	Completed		No
ACT3932	Environment Agency	Superseded	Included elsewhere	No
ACT3933	Environment Agency	Ongoing		Yes	Locally
ACT3934	Environment Agency	Completed		No
ACT3935	Environment Agency	Ongoing		Yes	Locally
ACT3936	Environment Agency	Superseded	Further work showed it was not viable	No
ACT3937	Environment Agency	Completed		No
ACT3938	Environment Agency	Ongoing		Yes	Locally
ACT3939	Environment Agency	Ongoing		Yes	Nationally
ACT3940	Environment Agency	Ongoing		Yes	Locally
ACT3941	Environment Agency	Ongoing		Yes	Locally
ACT3942	Environment Agency	Completed		No
ACT3943	Environment Agency	Ongoing		Yes	Locally
ACT3944	Environment Agency	Ongoing		Yes	Nationally
ACT3945	Environment Agency	Completed		No
ACT3946	Environment Agency	Ongoing		Yes	Locally
ACT3947	Environment Agency	Ongoing		Yes	Nationally
ACT3948	Environment Agency	Superseded	Further work showed it was not viable	No
ACT3949	Environment Agency	Ongoing		Yes	Nationally
ACT3950	Environment Agency	Ongoing		Yes	Nationally
ACT3951	Environment Agency	Ongoing		Yes	Nationally
ACT3952	Environment Agency	Ongoing		Yes	Nationally
ACT3953	Environment Agency	Superseded	Further work showed it was not viable	No
ACT3954	Environment Agency	Superseded	Further work showed it was not viable	No
ACT3955	Environment Agency	Ongoing		Yes	Nationally
ACT4603	Environment Agency	Superseded	Further work showed it was not viable	No
ACT4604	Environment Agency	Superseded	Further work showed it was not viable	No
ACT4605	Environment Agency	Ongoing		Yes	Locally
ACT4606	Environment Agency	Completed		No
ACT4607	Environment Agency	Ongoing		Yes	Nationally
ACT4608	Environment Agency	Superseded	Further work showed it was not viable	No
ACT4609	Environment Agency	Superseded	Further work showed it was not viable	No
ACT4610	Environment Agency	Completed		No
ACT4611	Environment Agency	Completed		No
ACT4612	Environment Agency	Ongoing		Yes	Nationally
ACT4613	Environment Agency	Completed		No
ACT4614	Environment Agency	Superseded	Further work showed it was not viable	No
ACT4615	Environment Agency	Completed		No
ACT4616	Environment Agency	Completed		No
ACT4617	Environment Agency	Completed		No
ACT4618	Environment Agency	Completed		No
ACT4619	Environment Agency	Completed		No
ACT4620	Environment Agency	Completed		No
ACT4622	Environment Agency	Completed		No
ACT7494	Environment Agency	Ongoing		Yes	Locally
ACT7495	Environment Agency	Completed		No
ACT3588	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3589	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3590	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3591	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3592	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3593	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3594	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3595	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3596	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3597	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3598	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3599	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3600	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3601	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3602	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3603	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3604	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3605	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3606	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3607	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3608	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3609	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3610	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3611	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3612	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3613	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3614	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3615	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3616	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3617	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3618	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3619	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3620	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3621	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3622	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3623	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3624	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3625	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3626	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3627	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3628	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3629	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3630	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3631	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3632	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3633	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3634	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3635	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3636	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3637	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3638	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3639	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3640	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3641	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3642	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3643	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3644	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3645	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3646	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3647	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3648	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3649	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3650	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3651	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3652	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3653	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3654	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3655	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3656	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3657	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3658	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3659	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3660	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3661	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3662	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3663	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3664	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3665	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3666	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3667	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3668	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3669	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3670	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3671	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3672	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3673	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3674	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT3675	Environment Agency, TE2100	Superseded	Included elsewhere	No
ACT187	Hackney London Borough	Ongoing		Yes	Nationally
ACT188	Hackney London Borough	Ongoing		Yes	Nationally
ACT189	Hackney London Borough	Completed		No
ACT190	Hackney London Borough	Completed		No
ACT191	Hackney London Borough	Completed		No
ACT192	Hackney London Borough	Completed		No
ACT193	Hackney London Borough	Ongoing		Yes	Nationally
ACT194	Hackney London Borough	Ongoing		Yes	Nationally
ACT195	Hackney London Borough	Ongoing		Yes	Nationally
ACT196	Hackney London Borough	Ongoing		Yes	Nationally
ACT197	Hackney London Borough	Ongoing		Yes	Nationally
ACT198	Hackney London Borough	Completed		No
ACT199	Hackney London Borough	Ongoing		Yes	Locally
ACT200	Hackney London Borough	Ongoing		Yes	Nationally
ACT201	Hackney London Borough	Ongoing		Yes	Nationally
ACT202	Hackney London Borough	Ongoing		Yes	Nationally
ACT203	Hackney London Borough	Ongoing		Yes	Nationally
ACT204	Hackney London Borough	Ongoing		Yes	Locally
ACT205	Hackney London Borough	Ongoing		Yes	Locally
ACT206	Hackney London Borough	Ongoing		Yes	Nationally
ACT207	Hackney London Borough	Ongoing		Yes	Nationally
ACT208	Hackney London Borough	Ongoing		Yes	Nationally
ACT209	Hackney London Borough	Ongoing		Yes	Nationally
ACT210	Hackney London Borough	Completed		No
ACT211	Hackney London Borough	Ongoing		Yes	Nationally
ACT212	Hackney London Borough	Ongoing		Yes	Nationally
ACT213	Hackney London Borough	Ongoing		Yes	Nationally
ACT214	Hackney London Borough	Ongoing		Yes	Locally
ACT215	Hackney London Borough	Ongoing		Yes	Nationally
ACT216	Hackney London Borough	Ongoing		Yes	Nationally
ACT217	Hackney London Borough	Ongoing		Yes	Nationally
ACT218	Hackney London Borough	Ongoing		Yes	Locally
ACT219	Hackney London Borough	Ongoing		Yes	Locally
ACT220	Hackney London Borough	Ongoing		Yes	Locally
ACT221	Hackney London Borough	Ongoing		Yes	Locally
ACT222	Hackney London Borough	Ongoing		Yes	Nationally
ACT223	Hackney London Borough	Ongoing		Yes	Locally
ACT224	Hackney London Borough	Ongoing		Yes	Nationally
ACT225	Hackney London Borough	Ongoing		Yes	Nationally
ACT226	Hackney London Borough	Ongoing		Yes	Locally
ACT227	Hackney London Borough	Completed		No
ACT228	Hackney London Borough	Completed		No
ACT229	Hackney London Borough	Ongoing		Yes	Locally
ACT230	Hackney London Borough	Ongoing		Yes	Nationally
ACT231	Hackney London Borough	Ongoing		Yes	Locally
ACT232	Hackney London Borough	Ongoing		Yes	Locally
ACT233	Hackney London Borough	Ongoing		Yes	Nationally
ACT234	Hackney London Borough	Ongoing		Yes	Nationally
ACT235	Hackney London Borough	Ongoing		Yes	Nationally
ACT236	Hackney London Borough	Ongoing		Yes	Nationally
ACT237	Hackney London Borough	Ongoing		Yes	Locally
ACT238	Hackney London Borough	Ongoing		Yes	Locally
ACT239	Hackney London Borough	Ongoing		Yes	Nationally
ACT240	Hackney London Borough	Ongoing		Yes	Locally
ACT688	Hammersmith and Fulham London Borough	Ongoing		Yes	Locally
ACT689	Hammersmith and Fulham London Borough	Superseded	Included elsewhere	No
ACT690	Hammersmith and Fulham London Borough	Ongoing		Yes	Nationally
ACT691	Hammersmith and Fulham London Borough	Ongoing		Yes	Locally
ACT692	Hammersmith and Fulham London Borough	Ongoing		Yes	Locally
ACT693	Hammersmith and Fulham London Borough	Ongoing		Yes	Locally
ACT694	Hammersmith and Fulham London Borough	Ongoing		Yes	Locally
ACT695	Hammersmith and Fulham London Borough	Completed		No
ACT696	Hammersmith and Fulham London Borough	Ongoing		Yes	Nationally
ACT697	Hammersmith and Fulham London Borough	Completed		No
ACT698	Hammersmith and Fulham London Borough	Completed		No
ACT2202	Haringey London Borough	Ongoing		Yes	Locally
ACT2203	Haringey London Borough	Ongoing		Yes	Locally
ACT2204	Haringey London Borough	Ongoing		Yes	Locally
ACT2205	Haringey London Borough	Ongoing		Yes	Locally
ACT2206	Haringey London Borough	Ongoing		Yes	Locally
ACT2207	Haringey London Borough	Ongoing		Yes	Locally
ACT2208	Haringey London Borough	Ongoing		Yes	Locally
ACT2209	Haringey London Borough	Ongoing		Yes	Locally
ACT2210	Haringey London Borough	Ongoing		Yes	Locally
ACT2211	Haringey London Borough	Ongoing		Yes	Locally
ACT2212	Haringey London Borough	Ongoing		Yes	Locally
ACT6148	Harrow London Borough	Completed		No
ACT6149	Harrow London Borough	Ongoing		Yes	Locally
ACT6150	Harrow London Borough	Completed		No
ACT6151	Harrow London Borough	Ongoing		Yes	Locally
ACT6152	Harrow London Borough	Ongoing		Yes	Locally
ACT6153	Harrow London Borough	Ongoing		Yes	Locally
ACT6154	Harrow London Borough	Ongoing		Yes	Locally
ACT6155	Harrow London Borough	Ongoing		Yes	Locally
ACT6156	Harrow London Borough	Ongoing		Yes	Locally
ACT6157	Harrow London Borough	Completed		No
ACT6158	Harrow London Borough	Completed		No
ACT6159	Harrow London Borough	Completed		No
ACT6161	Harrow London Borough	Completed		No
ACT6164	Harrow London Borough	Completed		No
ACT6165	Harrow London Borough	Ongoing		Yes	Nationally
ACT6167	Harrow London Borough	Ongoing		Yes	Nationally
ACT6172	Harrow London Borough	Ongoing		Yes	Nationally
ACT6173	Harrow London Borough	Ongoing		Yes	Nationally
ACT6174	Harrow London Borough	Ongoing		Yes	Locally
ACT6175	Harrow London Borough	Ongoing		Yes	Locally
ACT6176	Harrow London Borough	Ongoing		Yes	Locally
ACT6177	Harrow London Borough	Completed		No
ACT6178	Harrow London Borough	Completed		No
ACT6179	Harrow London Borough	Ongoing		Yes	Nationally
ACT6180	Harrow London Borough	Completed		No
ACT6181	Harrow London Borough	Completed		No
ACT6182	Harrow London Borough	Completed		No
ACT6183	Harrow London Borough	Completed		No
ACT6184	Harrow London Borough	Ongoing		Yes	Locally
ACT6185	Harrow London Borough	Ongoing		Yes	Locally
ACT5624	Havering London Borough	Ongoing		Yes	Locally
ACT5625	Havering London Borough	Completed		No
ACT5629	Havering London Borough	Completed		No
ACT5630	Havering London Borough	Completed		No
ACT5631	Havering London Borough	Completed		No
ACT5632	Havering London Borough	Completed		No
ACT5633	Havering London Borough	Superseded	No Funding	No
ACT5650	Havering London Borough	Completed		No
ACT5651	Havering London Borough	Ongoing		Yes	Locally
ACT5652	Havering London Borough	Ongoing		Yes	Locally
ACT5653	Havering London Borough	Superseded	Other - TWU asset. Regularly maintained.	No
ACT5655	Havering London Borough	Superseded	Postponed	No
ACT5869	Havering London Borough	Completed		No
ACT4621	Hertfordshire County	Completed		No
ACT6202	Hillingdon London Borough	Ongoing		Yes	Nationally
ACT6203	Hillingdon London Borough	Completed		No
ACT6204	Hillingdon London Borough	Completed		No
ACT6205	Hillingdon London Borough	Ongoing		Yes	Nationally
ACT6206	Hillingdon London Borough	Completed		No
ACT6749	Hounslow London Borough	Completed		No
ACT6753	Hounslow London Borough	Ongoing		Yes	Nationally
ACT6756	Hounslow London Borough	Ongoing		Yes	Nationally
ACT6757	Hounslow London Borough	Ongoing		Yes	Locally
ACT6758	Hounslow London Borough	Ongoing		Yes	Locally
ACT6760	Hounslow London Borough	Ongoing		Yes	Nationally
ACT6761	Hounslow London Borough	Ongoing		Yes	Nationally
ACT6763	Hounslow London Borough	Ongoing		Yes	Locally
ACT6770	Hounslow London Borough	Ongoing		Yes	Locally
ACT863	Islington London Borough	Superseded	Included elsewhere	No
ACT864	Islington London Borough	Completed		No
ACT865	Islington London Borough	Ongoing		Yes	Locally
ACT866	Islington London Borough	Ongoing		Yes	Locally
ACT867	Islington London Borough	Completed		No
ACT868	Islington London Borough	Completed		No
ACT869	Islington London Borough	Completed		No
ACT870	Islington London Borough	Ongoing		Yes	Locally
ACT4623	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT4624	Kensington and Chelsea London Borough	Ongoing		Yes	Nationally
ACT4625	Kensington and Chelsea London Borough	Ongoing		Yes	Nationally
ACT4626	Kensington and Chelsea London Borough	Ongoing		Yes	Nationally
ACT4627	Kensington and Chelsea London Borough	Superseded	Included elsewhere	No
ACT4628	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT4629	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT4630	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT4631	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT4632	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT4633	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT4634	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT4635	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT4636	Kensington and Chelsea London Borough	Completed		No
ACT4637	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT4638	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT4639	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT4640	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT4641	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT4642	Kensington and Chelsea London Borough	Ongoing		Yes	Nationally
ACT4643	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT4644	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT4645	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT4646	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT4647	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT4648	Kensington and Chelsea London Borough	Ongoing		Yes	Nationally
ACT4649	Kensington and Chelsea London Borough	Ongoing		Yes	Nationally
ACT4650	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT4651	Kensington and Chelsea London Borough	Ongoing		Yes	Nationally
ACT4652	Kensington and Chelsea London Borough	Completed		No
ACT4653	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT4654	Kensington and Chelsea London Borough	Completed		No
ACT4655	Kensington and Chelsea London Borough	Superseded	Included elsewhere	No
ACT4656	Kensington and Chelsea London Borough	Ongoing		No
ACT4657	Kensington and Chelsea London Borough	Superseded	Other - No longer necessary.	No
ACT6790	Kensington and Chelsea London Borough	Ongoing		Yes	Nationally
ACT6791	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT6792	Kensington and Chelsea London Borough	Ongoing		Yes	Nationally
ACT6802	Kensington and Chelsea London Borough	Ongoing		Yes	Nationally
ACT6804	Kensington and Chelsea London Borough	Ongoing		Yes	Nationally
ACT6805	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT6806	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT6808	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT6810	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT6811	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT6815	Kensington and Chelsea London Borough	Completed		No
ACT6817	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT6818	Kensington and Chelsea London Borough	Ongoing		Yes	Locally
ACT6819	Kensington and Chelsea London Borough	Ongoing		Yes	Nationally
ACT159	Newham London Borough	Superseded	No Funding	No
ACT160	Newham London Borough	Ongoing		Yes	Locally
ACT161	Newham London Borough	Ongoing		Yes	Locally
ACT162	Newham London Borough	Ongoing		Yes	Locally
ACT163	Newham London Borough	Superseded	No Funding	No
ACT164	Newham London Borough	Superseded	No Funding	No
ACT165	Newham London Borough	Superseded	No Funding	No
ACT166	Newham London Borough	Superseded	No Funding	No
ACT167	Newham London Borough	Superseded	No Funding	No
ACT536	Redbridge London Borough	Completed		No
ACT537	Redbridge London Borough	Completed		No
ACT538	Redbridge London Borough	Ongoing		Yes	Nationally
ACT539	Redbridge London Borough	Ongoing		Yes	Locally
ACT540	Redbridge London Borough	Ongoing		Yes	Locally
ACT541	Redbridge London Borough	Ongoing		Yes	Locally
ACT542	Redbridge London Borough	Ongoing		Yes	Nationally
ACT543	Redbridge London Borough	Completed		No
ACT544	Redbridge London Borough	Completed		No
ACT545	Redbridge London Borough	Ongoing		Yes	Nationally
ACT546	Redbridge London Borough	Ongoing		Yes	Nationally
ACT547	Redbridge London Borough	Ongoing		Yes	Locally
ACT548	Redbridge London Borough	Ongoing		Yes	Locally
ACT549	Redbridge London Borough	Ongoing		Yes	Locally
ACT1595	Thames Water	Completed		No
ACT3739	Thames Water	Superseded	Other - Works completed in November 2020 (including desilting outfall area and greasing the river flap, surface water sewer cleaning, flap maintenance.) TWUL have stated this is no longer a priority area for them. TWUL have agreed to class this cycle 1 measures as superseded. This area has been flagged and may be included within the Drainage and Wastewater Management Plans (DWMPs) in the future.	No
ACT3741	Thames Water	Superseded	Other - Works completed in November 2020 (including desilting outfall area and greasing the river flap, surface water sewer cleaning, flap maintenance.) TWUL have stated this is no longer a priority area for them. TWUL have agreed to class this cycle 1 measures as superseded. This area has been flagged and may be included within the Drainage and Wastewater Management Plans (DWMPs) in the future.	No
ACT6706	Tower Hamlets London Borough	Ongoing		Yes	Locally
ACT6708	Tower Hamlets London Borough	Ongoing		Yes	Locally
ACT6709	Tower Hamlets London Borough	Ongoing		Yes	Nationally
ACT6710	Tower Hamlets London Borough	Ongoing		Yes	Nationally
ACT6711	Tower Hamlets London Borough	Ongoing		Yes	Locally
ACT6712	Tower Hamlets London Borough	Completed		No
ACT6713	Tower Hamlets London Borough	Ongoing		Yes	Locally
ACT6714	Tower Hamlets London Borough	Completed		No
ACT6715	Tower Hamlets London Borough	Ongoing		Yes	Nationally
ACT6716	Tower Hamlets London Borough	Ongoing		Yes	Nationally
ACT6717	Tower Hamlets London Borough	Ongoing		Yes	Locally
ACT563	Waltham Forest London Borough	Ongoing		Yes	Nationally
ACT564	Waltham Forest London Borough	Completed		No
ACT565	Waltham Forest London Borough	Completed		No
ACT566	Waltham Forest London Borough	Completed		No
ACT567	Waltham Forest London Borough	Completed		No
ACT568	Waltham Forest London Borough	Completed		No
ACT569	Waltham Forest London Borough	Superseded	Included elsewhere	No
ACT570	Waltham Forest London Borough	Completed		No
ACT571	Waltham Forest London Borough	Ongoing		Yes	Nationally
ACT572	Waltham Forest London Borough	Ongoing		Yes	Nationally
ACT573	Waltham Forest London Borough	Superseded	Further work showed it was not viable	No
ACT574	Waltham Forest London Borough	Superseded	Included elsewhere	No
ACT575	Waltham Forest London Borough	Ongoing		Yes	Nationally
ACT576	Waltham Forest London Borough	Ongoing		Yes	Locally
ACT577	Waltham Forest London Borough	Ongoing		Yes	Locally
ACT578	Waltham Forest London Borough	Superseded	Included elsewhere	No
ACT579	Waltham Forest London Borough	Completed		No
ACT580	Waltham Forest London Borough	Ongoing		Yes	Locally
ACT581	Waltham Forest London Borough	Ongoing		Yes	Locally
ACT582	Waltham Forest London Borough	Ongoing		Yes	Locally
ACT583	Waltham Forest London Borough	Ongoing		Yes	Nationally
ACT584	Waltham Forest London Borough	Superseded	Included elsewhere	No
ACT585	Waltham Forest London Borough	Ongoing		Yes	Nationally
ACT586	Waltham Forest London Borough	Superseded	No Funding	No
ACT587	Waltham Forest London Borough	Superseded	Included elsewhere	No
ACT588	Waltham Forest London Borough	Superseded	No Funding	No
ACT589	Waltham Forest London Borough	Ongoing		Yes	Locally
ACT3583	Westminster London Borough	Ongoing		Yes	Locally
ACT3584	Westminster London Borough	Ongoing		Yes	Locally
ACT3585	Westminster London Borough	Ongoing		Yes	Locally
ACT3586	Westminster London Borough	Ongoing		Yes	Nationally
ACT3587	Westminster London Borough	Completed		No
ACT5673	Anglian Water	Ongoing		Yes	Locally
ACT136	Environment Agency - Anglian Area	Ongoing		Yes	Nationally
ACT137	Environment Agency - Anglian Area	Ongoing		Yes	Nationally
ACT138	Environment Agency - Anglian Area	Ongoing		Yes	Nationally
ACT141	Environment Agency - Anglian Area	Ongoing		Yes	Nationally
ACT142	Environment Agency - Anglian Area	Ongoing		Yes	Nationally
ACT143	Environment Agency - Anglian Area	Ongoing		Yes	Nationally
ACT5185	Environment Agency - Anglian Area	Ongoing		Yes	Nationally
ACT5580	Environment Agency - Anglian Area	Not started - proposed	Postponed to cycle 2	Yes	Locally
ACT5658	Environment Agency - Anglian Area	Ongoing		No
ACT5659	Environment Agency - Anglian Area	Ongoing		No
ACT139	Environment Agency - Anglian Area	Not started - proposed	Postponed	No
ACT5635	Environment Agency - Anglian Area	Ongoing		Yes	Nationally
ACT5636	Environment Agency - Anglian Area	Ongoing		Yes	Nationally
ACT5637	Environment Agency - Anglian Area	Ongoing		Yes	Nationally
ACT5638	Environment Agency - Anglian Area	Ongoing		Yes	Nationally
ACT5639	Environment Agency - Anglian Area	Not started - proposed	Further work showed it was not viable	No
ACT5717	Environment Agency - Anglian Area	Completed		No
ACT5718	Environment Agency - Anglian Area	Ongoing		Yes	Locally
ACT5275	Essex County	Completed		No
ACT5276	Essex County	Completed		No
ACT5277	Essex County	Ongoing		Yes	Nationally
ACT5278	Essex County	Ongoing		Yes	Nationally
ACT5279	Essex County	Ongoing		Yes	Nationally
ACT5280	Essex County	Ongoing		Yes	Nationally
ACT5281	Essex County	Ongoing		Yes	Nationally
ACT5282	Essex County	Ongoing		Yes	Nationally
ACT5283	Essex County	Ongoing		Yes	Nationally
ACT5284	Essex County	Ongoing		Yes	Nationally
ACT5285	Essex County	Ongoing		Yes	Nationally
ACT5286	Essex County	Ongoing		Yes	Nationally
ACT5287	Essex County	Ongoing		Yes	Nationally
ACT5288	Essex County	Not started - agreed		Yes	Nationally