## Cover_sheet
Severn flood risk management plan annex 1
This spreadsheet states the progress for the first cycle of the Flood risk management plan (FRMP) (2015-2021). The spreadsheet contains the status of each FRMP plan measure, the measure ID, the action owner, the implementation status as of the 31 March 2021. As well as reasons for not progressing if relevant.
Status of the measures
First cycle measures that comprise of the day-to-day work by the Environment Agency and Lead Local Flood Authorities (LLFAs) are transitioned to this second cycle FRMP as ongoing national-level measures. This may be as an individual measure or aggregated with other measures. More information on these measures can be found in Flood Plan Explorer. / Measures may appear differently in the second cycle compared with the first cycle, for example an individual measure in the first cycle may appear as part of a wider programme of work in the second cycle. / Measures that are not transitioned to the second cycle FRMP will continue to be developed or kept under review by the Environment Agency, LLFA and other risk management authorities. This will be done in accordance with the current Flood and Coastal Erosion Risk Management appraisal guidance and funding rules. / Column D contains blank cells when a measure is 'completed' or 'ongoing' in FRMP cycle 1. / Column F contains blank cells when a measure is 'completed' or not transitioned to FRMP cycle 2.
Links to other FRMP resources
Flood Plan Explorer
Severn river basin district flood risk management plan

## FRMP1_annex
Severn FRMP 1 annex
This worksheet contains one table.
Measure ID	Measure Owner	Implementation Status	Reason for Not progressing	Transitioned to FRMP2?	Transitioned Local or National?
ACT015	Northamptonshire County	Completed	N/A	N/A
ACT016	Northamptonshire County	Completed	N/A	N/A
ACT2262	Northamptonshire County	Ongoing	N/A	Yes	Local
ACT2263	Northamptonshire County	Ongoing	N/A	Yes	National
ACT2264	Northamptonshire County	Ongoing	N/A	Yes	National
ACT2265	Northamptonshire County	Ongoing	N/A	Yes	National
ACT2266	Northamptonshire County	Ongoing	N/A	Yes	National
ACT2267	Northamptonshire County	Ongoing	N/A	Yes	National
ACT2269	Northamptonshire County	Completed	N/A	N/A
ACT2278	Northamptonshire County	Ongoing	N/A	Yes	National
ACT2279	Northamptonshire County	Completed	N/A	N/A
ACT2280	Northamptonshire County	Completed	N/A	N/A
ACT2281	Northamptonshire County	Ongoing	N/A	Yes	National
ACT2282	Northamptonshire County	Ongoing	N/A	Yes	National and Local
ACT2283	Northamptonshire County	Completed	N/A	N/A
ACT2284	Northamptonshire County	Ongoing	N/A	No
ACT2285	Northamptonshire County	Completed	N/A	N/A
ACT2297	Northamptonshire County	Superseded	Other - Relevant legislation not implemented	N/A
ACT2298	Northamptonshire County	Completed	N/A	N/A
ACT2299	Northamptonshire County	Ongoing	N/A	Yes	National
ACT2300	Northamptonshire County	Ongoing	N/A	Yes	National
ACT2301	Northamptonshire County	Ongoing	N/A	Yes	National
ACT2303	Daventry District	Ongoing	N/A	No
ACT2321	Dudley Metropolitan District	Ongoing	N/A	Yes	National and Local
ACT2322	Sandwell Metropolitan District	Ongoing	N/A	Yes	National and Local
ACT2324	Wolverhampton Metropolitan District	Ongoing	N/A	Yes	National and Local
ACT2325	Dudley Metropolitan District	Ongoing	N/A	Yes	National and Local
ACT2326	Sandwell Metropolitan District	Ongoing	N/A	Yes	National and Local
ACT2328	Wolverhampton Metropolitan District	Ongoing	N/A	Yes	National and Local
ACT2333	Dudley Metropolitan District	Ongoing	N/A	Yes	National and Local
ACT2334	Sandwell Metropolitan District	Ongoing	N/A	Yes	National and Local
ACT2336	Wolverhampton Metropolitan District	Ongoing	N/A	Yes	National and Local
ACT2337	Dudley Metropolitan District	Ongoing	N/A	Yes	National and Local
ACT2338	Sandwell Metropolitan District	Ongoing	N/A	Yes	National and Local
ACT2340	Wolverhampton Metropolitan District	Ongoing	N/A	Yes	National and Local
ACT2373	Dudley Metropolitan District	Ongoing	N/A	Yes	National and Local
ACT2374	Sandwell Metropolitan District	Ongoing	N/A	Yes	National and Local
ACT2376	Wolverhampton Metropolitan District	Ongoing	N/A	Yes	National and Local
ACT2381	Dudley Metropolitan District	Ongoing	N/A	Yes	National and Local
ACT2382	Sandwell Metropolitan District	Ongoing	N/A	Yes	National and Local
ACT2480	Environment Agency	Ongoing	N/A	Yes	National
ACT2481	Environment Agency	Ongoing	N/A	Yes	National
ACT2482	Environment Agency	Completed	N/A	N/A
ACT2483	Environment Agency	Ongoing	N/A	Yes	National
ACT2484	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2485	Environment Agency	Ongoing	N/A	Yes	National
ACT2486	Environment Agency	Ongoing	N/A	Yes	National
ACT2487	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2488	Environment Agency	Ongoing	N/A	Yes	National
ACT2489	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2490	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2491	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2492	Environment Agency	Ongoing	N/A	Yes	National and local
ACT2493	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2494	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2495	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2496	Environment Agency	Ongoing	N/A	Yes	National
ACT2497	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2498	Environment Agency	Ongoing	N/A	Yes	National
ACT2499	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2500	Environment Agency	Ongoing	N/A	Yes	National
ACT2501	Environment Agency	Ongoing	N/A	Yes	National
ACT2502	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2503	Redditch District (B)	Ongoing	N/A	Yes	National and Local
ACT2504	Redditch District (B)	Ongoing	N/A	Yes	National and Local
ACT2505	Redditch District (B)	Ongoing	N/A	Yes	Local
ACT2506	Redditch District (B)	Ongoing	N/A	Yes	National and Local
ACT2507	Redditch District (B)	Ongoing	N/A	Yes	National and Local
ACT2508	Redditch District (B)	Ongoing	N/A	Yes	National and Local
ACT2509	Redditch District (B)	Ongoing	N/A	Yes	National and Local
ACT2510	Redditch District (B)	Ongoing	N/A	Yes	National and Local
ACT2511	Redditch District (B)	Ongoing	N/A	Yes	National and Local
ACT2512	Redditch District (B)	Ongoing	N/A	Yes	National and Local
ACT2513	Redditch District (B)	Ongoing	N/A	Yes	National and Local
ACT2514	Redditch District (B)	Ongoing	N/A	Yes	Local
ACT2515	Redditch District (B)	Ongoing	N/A	Yes	National and Local
ACT2516	Redditch District (B)	Ongoing	N/A	Yes	National and Local
ACT2517	Rugby District (B)	Ongoing	N/A	No
ACT2518	Rugby District (B)	Ongoing	N/A	No
ACT2519	Rugby District (B)	Ongoing	N/A	No
ACT2521	Rugby District (B)	Ongoing	N/A	No
ACT2522	Rugby District (B)	Ongoing	N/A	No
ACT2526	Rugby District (B)	Ongoing	N/A	No
ACT2527	Rugby District (B)	Ongoing	N/A	No
ACT2528	Rugby District (B)	Ongoing	N/A	No
ACT2529	Rugby District (B)	Ongoing	N/A	No
ACT2530	Rugby District (B)	Ongoing	N/A	No
ACT2531	Rugby District (B)	Ongoing	N/A	No
ACT2532	Rugby District (B)	Ongoing	N/A	No
ACT2535	Rugby District (B)	Ongoing	N/A	No
ACT2536	Rugby District (B)	Ongoing	N/A	No
ACT2537	Rugby District (B)	Ongoing	N/A	No
ACT2538	Rugby District (B)	Ongoing	N/A	No
ACT2539	Rugby District (B)	Ongoing	N/A	No
ACT2540	Rugby District (B)	Ongoing	N/A	No
ACT2541	Environment Agency	Ongoing	N/A	Yes	National
ACT2542	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2543	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2545	Warwickshire County	Ongoing - construction	N/A	Yes	Local
ACT2546	Coventry Metropolitan District	Superseded	It has been replaced by another measure	N/A
ACT2547	Environment Agency	Ongoing - construction	N/A	Yes	Local
ACT2548	Warwickshire County	Completed	N/A	N/A
ACT2549	Warwickshire County	Ongoing	N/A	Yes	Local
ACT2550	Environment Agency	Not started - proposed	It does not yet have funding	Yes	Local
ACT2551	Staffordshire County	Completed	N/A	N/A
ACT2552	Warwickshire County	Completed	N/A	N/A
ACT2553	Warwickshire County	Completed	N/A	N/A
ACT2554	Dudley Metropolitan District	Completed	N/A	N/A
ACT2556	Warwickshire County	Not started - agreed	It has been postponed	Yes	Local
ACT2557	Environment Agency	Completed	N/A	N/A
ACT2558	Environment Agency	Ongoing	N/A	Yes	Local
ACT2559	Environment Agency	Ongoing	N/A	Yes	Local
ACT2560	Severn Trent Water	Completed	N/A	N/A
ACT2561	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2562	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2563	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2564	Environment Agency	Ongoing	N/A	Yes	National
ACT2565	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2566	Environment Agency	Ongoing	N/A	Yes	National
ACT2567	Environment Agency	Ongoing	N/A	Yes	National
ACT2568	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2569	Environment Agency	Ongoing	N/A	Yes	National
ACT2570	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2571	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2572	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2573	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2574	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2575	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2576	Environment Agency	Completed	N/A	N/A
ACT2577	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2578	Environment Agency	Ongoing	N/A	Yes	National
ACT2579	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2581	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT2582	Environment Agency	Ongoing	N/A	Yes	National
ACT2583	Environment Agency	Ongoing	N/A	Yes	National
ACT2584	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT3201	Environment Agency	Completed	N/A	N/A
ACT3202	Environment Agency	Completed	N/A	N/A
ACT3203	Environment Agency	Completed	N/A	N/A
ACT3204	Environment Agency	Ongoing	N/A	Yes	Local
ACT3205	Environment Agency	Ongoing	N/A	Yes	Local
ACT3206	Environment Agency	Ongoing	N/A	Yes	Local
ACT3207	Environment Agency	Ongoing	N/A	Yes	National
ACT3208	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT3209	Environment Agency	Completed	N/A	N/A
ACT3210	Environment Agency	Completed	N/A	N/A
ACT3211	Environment Agency	Completed	N/A	N/A
ACT3212	Environment Agency	Ongoing	N/A	Yes	National
ACT3213	Environment Agency	Not started - proposed	It has been included in another piece of work	Yes	Local
ACT3214	Environment Agency	Completed	N/A	N/A
ACT3215	Environment Agency	Completed	N/A	N/A
ACT3216	Environment Agency	Completed	N/A	N/A
ACT3217	Environment Agency	Ongoing	N/A	Yes	Local
ACT3218	Environment Agency	Completed	N/A	N/A
ACT3219	Environment Agency	Ongoing	N/A	Yes	Local
ACT3220	Environment Agency	Ongoing	N/A	Yes	Local
ACT3221	Environment Agency	Completed	N/A	No
ACT3222	Environment Agency	Not started - proposed	It does not yet have funding	Yes	Local
ACT3223	Environment Agency	Completed	N/A	N/A
ACT3224	Environment Agency	Not started - proposed	It does not yet have funding	Yes	Local
ACT3225	Environment Agency	Ongoing	N/A	Yes	Local
ACT3226	Environment Agency	Completed	N/A	N/A
ACT3227	Environment Agency	Completed	N/A	N/A
ACT3228	Environment Agency	Ongoing	N/A	Yes	Local
ACT3230	Environment Agency	Ongoing	N/A	Yes	Local
ACT3231	Environment Agency	Ongoing	N/A	Yes	Local
ACT3232	Environment Agency	Ongoing	N/A	Yes	Local
ACT3233	Environment Agency	Ongoing	N/A	Yes	Local
ACT3234	Environment Agency	Not started - proposed	It has been included in another piece of work	Yes	Local
ACT3235	Environment Agency	Ongoing	N/A	Yes	Local
ACT3236	Environment Agency	Completed	N/A	N/A
ACT3237	Environment Agency	Ongoing	N/A	Yes	Local
ACT3238	Environment Agency	Completed	N/A	N/A
ACT3242	Environment Agency	Ongoing	N/A	Yes	Local
ACT3243	Environment Agency	Ongoing	N/A	Yes	Local
ACT3244	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT3245	Environment Agency	Ongoing	N/A	Yes	Local
ACT3246	Environment Agency	Ongoing	N/A	Yes	Local
ACT3250	Environment Agency	Ongoing	N/A	Yes	Local
ACT3251	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT3252	Environment Agency	Ongoing	N/A	Yes	Local
ACT3253	Environment Agency	Ongoing	N/A	No
ACT3254	Environment Agency	Not started - proposed	It does not yet have funding	Yes	Local
ACT3255	Environment Agency	Completed	N/A	N/A
ACT3257	Environment Agency	Completed	N/A	N/A
ACT3258	Environment Agency	Not started - agreed	It does not yet have funding	Yes	Local
ACT3259	Environment Agency	Ongoing	N/A	Yes	National
ACT3260	Environment Agency	Not started - agreed	It has been postponed	No
ACT3261	Environment Agency	Ongoing	N/A	Yes	Local
ACT3262	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT3265	Environment Agency	Ongoing	N/A	Yes	National
ACT3266	Environment Agency	Ongoing	N/A	Yes	National
ACT3267	Environment Agency	Ongoing	N/A	Yes	National
ACT3268	Environment Agency	Ongoing	N/A	Yes	Local
ACT3269	Environment Agency	Completed	N/A	N/A
ACT3270	Environment Agency	Ongoing	N/A	Yes	Local
ACT3271	Environment Agency	Ongoing	N/A	Yes	Local
ACT3272	Environment Agency	Completed	N/A	N/A
ACT3273	Environment Agency	Ongoing	N/A	Yes	Local
ACT3274	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT3275	Environment Agency	Completed	N/A	N/A
ACT3277	Environment Agency	Ongoing	N/A	Yes	National
ACT3278	Environment Agency	Ongoing	N/A	Yes	National
ACT3279	Environment Agency	Ongoing	N/A	Yes	Local
ACT3280	Environment Agency	Ongoing	N/A	Yes	National
ACT3281	Environment Agency	Not started - proposed	It has been included in another piece of work	Yes	Local
ACT3282	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT3284	Environment Agency	Completed	N/A	N/A
ACT3285	Environment Agency	Ongoing	N/A	Yes	National
ACT3286	Environment Agency	Ongoing	N/A	Yes	National
ACT3287	Environment Agency	Ongoing	N/A	Yes	National
ACT3288	Environment Agency	Ongoing	N/A	Yes	National
ACT3290	Environment Agency	Completed	N/A	N/A
ACT3291	Environment Agency	Ongoing	N/A	Yes	National
ACT3292	Environment Agency	Ongoing	N/A	Yes	National
ACT3293	Environment Agency	Ongoing	N/A	Yes	Local
ACT3294	Environment Agency	Ongoing	N/A	Yes	Local
ACT3296	Environment Agency	Ongoing	N/A	Yes	National
ACT3297	Environment Agency	Ongoing	N/A	Yes	National
ACT3298	Environment Agency	Ongoing	N/A	Yes	National
ACT3299	Environment Agency	Completed	N/A	N/A
ACT3300	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT3301	Environment Agency	Ongoing	N/A	Yes	National
ACT3302	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT3303	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT3304	Environment Agency	Ongoing	N/A	Yes	Local
ACT3306	Environment Agency	Ongoing	N/A	Yes	Local
ACT3307	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT3308	Environment Agency	Completed	N/A	N/A
ACT3309	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT3310	Environment Agency	Ongoing	N/A	Yes	National
ACT3311	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT3312	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT3313	Environment Agency	Ongoing	N/A	Yes	National
ACT3314	Environment Agency	Ongoing	N/A	Yes	National
ACT3316	Environment Agency	Completed	N/A	N/A
ACT3318	Environment Agency	Completed	N/A	N/A
ACT3319	Environment Agency	Ongoing	N/A	Yes	National
ACT3320	Environment Agency	Ongoing	N/A	Yes	National
ACT3321	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT3322	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT3323	Environment Agency	Not started - agreed	Other - Point not reached where the measure is needed	Yes	National
ACT3324	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT3325	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT3326	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT3327	Environment Agency	Ongoing	N/A	Yes	National
ACT3328	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT3329	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT3330	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT3331	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT3332	Environment Agency	Completed	N/A	N/A
ACT3333	Environment Agency	Completed	N/A	N/A
ACT3334	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT3335	Environment Agency	Completed	N/A	N/A
ACT3336	Environment Agency	Ongoing	N/A	Yes	National
ACT3337	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT3338	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT3339	Environment Agency	Ongoing	N/A	Yes	National
ACT3340	Environment Agency	Not started - agreed	It has been postponed	Yes	Local
ACT3341	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT3342	Environment Agency	Not started - proposed	It has been postponed	Yes	National
ACT3343	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT3344	Environment Agency	Ongoing	N/A	Yes	National
ACT3345	Environment Agency	Ongoing	N/A	Yes	National
ACT3346	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT4034	Dudley Metropolitan District	Ongoing	N/A	Yes	National and Local
ACT4035	Dudley Metropolitan District	Ongoing	N/A	Yes	National and Local
ACT4760	Environment Agency	Ongoing	N/A	Yes	National
ACT4803	Staffordshire County	Ongoing	N/A	Yes	National
ACT5814	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT5898	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT5899	Environment Agency	Ongoing	N/A	Yes	National
ACT5900	Environment Agency	Ongoing	N/A	Yes	National
ACT5901	Environment Agency	Ongoing	N/A	Yes	National
ACT5902	Environment Agency	Ongoing	N/A	Yes	National
ACT5903	Environment Agency	Ongoing	N/A	Yes	National
ACT5904	Environment Agency	Completed	N/A	N/A
ACT5905	Environment Agency	Ongoing	N/A	Yes	National
ACT6903	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT6930	Environment Agency	Ongoing	N/A	Yes	National
ACT6931	Environment Agency	Completed	N/A	N/A
ACT7133	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT7134	Environment Agency	Ongoing	N/A	Yes	National
ACT7145	Warwickshire County	Ongoing	N/A	Yes	National
ACT7149	Worcestershire County	Ongoing	N/A	Yes	National
ACT7166	Severn Trent Water	Ongoing	N/A	Yes	Local
ACT7167	Severn Trent Water	Ongoing	N/A	Yes	Local
ACT7168	Severn Trent Water	Ongoing	N/A	Yes	Local
ACT7169	Severn Trent Water	Ongoing	N/A	Yes	Local
ACT7170	Severn Trent Water	Ongoing	N/A	Yes	Local
ACT7171	Severn Trent Water	Ongoing	N/A	Yes	Local
ACT7175	Environment Agency	Ongoing	N/A	Yes	Local
ACT1000	Environment Agency	Ongoing	N/A	Yes	Local
ACT1001	Environment Agency	Ongoing	N/A	Yes	Local
ACT1005	Environment Agency	Ongoing	N/A	Yes	Local
ACT1007	Environment Agency	Completed	N/A	N/A
ACT1008	Environment Agency	Completed	N/A	N/A
ACT1009	Environment Agency	Ongoing	N/A	Yes	Local
ACT1010	Environment Agency	Ongoing - construction	N/A	Yes	Local
ACT1016	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT1017	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT1018	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT1019	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT1020	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT1021	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT1022	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT1023	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT1024	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT1025	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT1026	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT1027	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT1028	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT1029	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT1030	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT1031	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT1032	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT1033	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT1034	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT1035	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT1036	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT1037	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT1038	Environment Agency	Ongoing	N/A	Yes	National
ACT1039	Environment Agency	Completed	N/A	N/A
ACT1040	Environment Agency	Ongoing	N/A	Yes	National
ACT1041	Environment Agency	Completed	N/A	N/A
ACT1042	Environment Agency	Ongoing	N/A	Yes	National
ACT1043	Environment Agency	Completed	N/A	N/A
ACT1044	Environment Agency	Ongoing	N/A	Yes	National
ACT1045	Environment Agency	Completed	N/A	N/A
ACT1046	Environment Agency	Ongoing	N/A	Yes	National
ACT1047	Environment Agency	Completed	N/A	N/A
ACT1048	Environment Agency	Completed	N/A	N/A
ACT1049	Environment Agency	Completed	N/A	N/A
ACT1050	Environment Agency	Completed	N/A	N/A
ACT1051	Environment Agency	Ongoing	N/A	Yes	National
ACT1052	Environment Agency	Completed	N/A	N/A
ACT1053	Environment Agency	Completed	N/A	N/A
ACT1054	Environment Agency	Ongoing	N/A	Yes	National
ACT1055	Environment Agency	Ongoing	N/A	Yes	National
ACT1056	Environment Agency	Completed	N/A	N/A
ACT1057	Environment Agency	Completed	N/A	N/A
ACT1058	Environment Agency	Ongoing	N/A	Yes	National
ACT1059	Environment Agency	Completed	N/A	N/A
ACT1060	Environment Agency	Ongoing	N/A	Yes	National
ACT1061	Environment Agency	Completed	N/A	N/A
ACT1062	Environment Agency	Ongoing	N/A	Yes	National
ACT1063	Environment Agency	Ongoing	N/A	Yes	National
ACT1064	Environment Agency	Completed	N/A	N/A
ACT1065	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT1066	Environment Agency	Completed	N/A	N/A
ACT1067	Environment Agency	Completed	N/A	N/A
ACT1068	Environment Agency	Completed	N/A	N/A
ACT1069	Environment Agency	Completed	N/A	N/A
ACT1070	Environment Agency	Ongoing	N/A	Yes	National
ACT1071	Environment Agency	Completed	N/A	N/A
ACT1072	Environment Agency	Ongoing	N/A	Yes	National
ACT1073	Environment Agency	Completed	N/A	N/A
ACT1074	Environment Agency	Completed	N/A	N/A
ACT1075	Environment Agency	Ongoing	N/A	Yes	National
ACT1076	Environment Agency	Ongoing	N/A	Yes	National
ACT1077	Environment Agency	Completed	N/A	N/A
ACT1078	Environment Agency	Ongoing	N/A	Yes	National
ACT1079	Environment Agency	Completed	N/A	N/A
ACT1080	Environment Agency	Completed	N/A	N/A
ACT1095	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT1096	Environment Agency	Ongoing	N/A	Yes	Local
ACT1097	Environment Agency	Completed	N/A	N/A
ACT1098	Environment Agency	Completed	N/A	N/A
ACT1099	Environment Agency	Completed	N/A	N/A
ACT1100	Environment Agency	Completed	N/A	N/A
ACT1101	Environment Agency	Completed	N/A	N/A
ACT1102	Environment Agency	Ongoing	N/A	Yes	Local
ACT1103	Environment Agency	Completed	N/A	N/A
ACT1104	Environment Agency	Completed	N/A	N/A
ACT1105	Environment Agency	Completed	N/A	N/A
ACT1106	Environment Agency	Completed	N/A	N/A
ACT1107	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT1108	Environment Agency	Ongoing - construction	N/A	Yes	Local
ACT1109	Environment Agency	Completed	N/A	N/A
ACT1110	Environment Agency	Ongoing	N/A	Yes	National and Local
ACT1902	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1903	South Gloucestershire Unitary Authority	Completed	N/A	N/A
ACT1904	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1905	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1906	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1907	South Gloucestershire Unitary Authority	Completed	N/A	N/A
ACT1908	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1909	South Gloucestershire Unitary Authority	Superseded	Further work showed it was not viable	N/A
ACT1910	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1911	South Gloucestershire Unitary Authority	Completed	N/A	N/A
ACT1912	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1913	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1915	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1916	South Gloucestershire Unitary Authority	Completed	N/A	N/A
ACT1917	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1918	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1919	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1920	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1921	South Gloucestershire Unitary Authority	Not started - proposed	It has been postponed	Yes	Local
ACT1922	South Gloucestershire Unitary Authority	Not started - proposed	It has been postponed	Yes	Local
ACT1923	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1924	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1925	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1926	South Gloucestershire Unitary Authority	Completed	N/A	N/A
ACT1927	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1928	South Gloucestershire Unitary Authority	Completed	N/A	N/A
ACT1929	South Gloucestershire Unitary Authority	Completed	N/A	N/A
ACT1930	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1932	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1933	South Gloucestershire Unitary Authority	Superseded	Further work showed it was not viable	N/A
ACT1934	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1935	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1936	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1937	South Gloucestershire Unitary Authority	Completed	N/A	N/A
ACT1938	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1939	South Gloucestershire Unitary Authority	Completed	N/A	N/A
ACT1940	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1941	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1942	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1943	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1944	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1946	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1947	South Gloucestershire Unitary Authority	Completed	N/A	N/A
ACT1948	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1949	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1950	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1951	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1952	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1953	South Gloucestershire Unitary Authority	Superseded	It has been replaced by another measure	N/A
ACT1955	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1956	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1959	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1960	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1961	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1962	South Gloucestershire Unitary Authority	Ongoing	N/A	Yes	Local
ACT1963	North Somerset Unitary Authority	Ongoing	N/A	Yes	Local
ACT1964	North Somerset Unitary Authority	Ongoing	N/A	Yes	Local
ACT1965	North Somerset Unitary Authority	Not started - agreed	It has been postponed	Yes	Local
ACT1966	North Somerset Unitary Authority	Ongoing	N/A	Yes	Local
ACT1967	North Somerset Unitary Authority	Ongoing	N/A	Yes	Local
ACT1968	North Somerset Unitary Authority	Completed	N/A	N/A
ACT1969	North Somerset Unitary Authority	Ongoing	N/A	Yes	Local
ACT1970	North Somerset Unitary Authority	Ongoing	N/A	Yes	Local
ACT1971	North Somerset Unitary Authority	Ongoing	N/A	Yes	Local
ACT1972	North Somerset Unitary Authority	Ongoing	N/A	Yes	Local
ACT1973	North Somerset Unitary Authority	Not started - agreed	It does not yet have funding	Yes	Local
ACT1974	North Somerset Unitary Authority	Completed	N/A	N/A
ACT1975	North Somerset Unitary Authority	Completed	N/A	N/A
ACT1976	North Somerset Unitary Authority	Not started - agreed	It does not yet have funding	Yes	Local
ACT1977	North Somerset Unitary Authority	Not started - proposed	It has been included in another piece of work	Yes	Local
ACT1979	North Somerset Unitary Authority	Not started - proposed	It has been replaced by another measure	Yes	Local
ACT1980	North Somerset Unitary Authority	Ongoing	N/A	Yes	Local
ACT1981	North Somerset Unitary Authority	Ongoing	N/A	Yes	Local
ACT1987	North Somerset Unitary Authority	Not started - proposed	It has been postponed	Yes	Local
ACT1988	North Somerset Unitary Authority	Not started - agreed	It does not yet have funding	Yes	Local
ACT1989	North Somerset Unitary Authority	Ongoing	N/A	Yes	Local
ACT1990	North Somerset Unitary Authority	Not started - proposed	It has been postponed	Yes	Local
ACT1991	North Somerset Unitary Authority	Not started - proposed	It has been postponed	Yes	Local
ACT1992	North Somerset Unitary Authority	Not started - proposed	It has been postponed	Yes	Local
ACT1993	North Somerset Unitary Authority	Not started - proposed	It has been postponed	Yes	Local
ACT1997	North Somerset Unitary Authority	Ongoing	N/A	Yes	Local
ACT1998	North Somerset Unitary Authority	Not started - proposed	It has been postponed	Yes	Local
ACT1999	North Somerset Unitary Authority	Not started - proposed	It has been postponed	Yes	Local
ACT2000	North Somerset Unitary Authority	Not started - proposed	It has been postponed	Yes	Local
ACT2001	North Somerset Unitary Authority	Not started - proposed	It has been postponed	Yes	Local
ACT2002	North Somerset Unitary Authority	Ongoing	N/A	Yes	Local
ACT2003	North Somerset Unitary Authority	Not started - proposed	It has been postponed	Yes	Local
ACT2004	North Somerset Unitary Authority	Not started - agreed	It does not yet have funding	Yes	Local
ACT2005	North Somerset Unitary Authority	Not started - agreed	It does not yet have funding	Yes	Local
ACT2006	North Somerset Unitary Authority	Not started - agreed	It does not yet have funding	Yes	Local
ACT2012	North Somerset Unitary Authority	Not started - agreed	It does not yet have funding	Yes	Local
ACT2013	North Somerset Unitary Authority	Not started - agreed	It does not yet have funding	Yes	Local
ACT2014	North Somerset Unitary Authority	Not started - agreed	It does not yet have funding	Yes	Local
ACT2015	North Somerset Unitary Authority	Not started - agreed	It does not yet have funding	Yes	Local
ACT2017	North Somerset Unitary Authority	Not started - proposed	It has been postponed	Yes	Local
ACT2020	North Somerset Unitary Authority	Not started - proposed	It has been postponed	Yes	Local
ACT2028	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT2030	Environment Agency	Superseded	It has been included in another piece of work	N/A
ACT2035	City of Bristol Unitary Authority	Ongoing	N/A	Yes	Local
ACT2036	City of Bristol Unitary Authority	Ongoing	N/A	Yes	Local
ACT2037	City of Bristol Unitary Authority	Ongoing	N/A	Yes	Local
ACT2038	City of Bristol Unitary Authority	Not started - proposed	It has been postponed	Yes	Local
ACT2039	City of Bristol Unitary Authority	Completed	N/A	N/A
ACT2040	City of Bristol Unitary Authority	Not started - proposed	It has been postponed	Yes	Local
ACT2041	City of Bristol Unitary Authority	Not started - proposed	It has been postponed	Yes	Local
ACT2042	City of Bristol Unitary Authority	Completed	N/A	N/A
ACT2043	City of Bristol Unitary Authority	Completed	N/A	N/A
ACT2044	City of Bristol Unitary Authority	Completed	N/A	N/A
ACT2045	City of Bristol Unitary Authority	Completed	N/A	N/A
ACT2046	North Somerset Unitary Authority	Not started - proposed	It has been postponed	Yes	Local
ACT2047	North Somerset Unitary Authority	Not started - proposed	It has been postponed	Yes	Local
ACT2048	North Somerset Unitary Authority	Ongoing	N/A	Yes	Local
ACT2049	North Somerset Unitary Authority	Not started - proposed	It has been postponed	Yes	Local
ACT2050	North Somerset Unitary Authority	Not started - proposed	It has been postponed	Yes	Local
ACT2051	North Somerset Unitary Authority	Not started - proposed	It has been postponed	Yes	Local
ACT2052	City of Bristol Unitary Authority	Ongoing	N/A	Yes	Local
ACT2053	City of Bristol Unitary Authority	Ongoing	N/A	Yes	Local
ACT2054	City of Bristol Unitary Authority	Ongoing	N/A	Yes	Local
ACT2055	City of Bristol Unitary Authority	Ongoing	N/A	Yes	Local
ACT2056	City of Bristol Unitary Authority	Ongoing	N/A	Yes	Local
ACT2057	City of Bristol Unitary Authority	Ongoing	N/A	Yes	Local
ACT2058	City of Bristol Unitary Authority	Ongoing	N/A	Yes	Local
ACT2059	City of Bristol Unitary Authority	Ongoing	N/A	Yes	Local
ACT2060	City of Bristol Unitary Authority	Completed	N/A	N/A
ACT2061	City of Bristol Unitary Authority	Ongoing	N/A	Yes	Local
ACT2062	City of Bristol Unitary Authority	Completed	N/A	N/A
ACT2063	City of Bristol Unitary Authority	Completed	N/A	N/A
ACT2064	City of Bristol Unitary Authority	Ongoing	N/A	Yes	Local
ACT2065	City of Bristol Unitary Authority	Ongoing	N/A	Yes	Local
ACT2066	City of Bristol Unitary Authority	Completed	N/A	N/A
ACT2067	City of Bristol Unitary Authority	Ongoing	N/A	Yes	Local
ACT2068	City of Bristol Unitary Authority	Ongoing	N/A	Yes	Local
ACT2069	City of Bristol Unitary Authority	Superseded	It has been included in another piece of work	N/A
ACT2070	City of Bristol Unitary Authority	Ongoing	N/A	Yes	Local
ACT2071	City of Bristol Unitary Authority	Ongoing	N/A	Yes	Local
ACT2072	City of Bristol Unitary Authority	Ongoing	N/A	Yes	Local
ACT2073	City of Bristol Unitary Authority	Ongoing	N/A	Yes	Local
ACT2074	City of Bristol Unitary Authority	Ongoing	N/A	Yes	Local
ACT2075	City of Bristol Unitary Authority	Completed	N/A	N/A
ACT2076	Bath and North East Somerset Unitary Authority	Completed	N/A	N/A
ACT2077	Bath and North East Somerset Unitary Authority	Completed	N/A	N/A
ACT2078	Bath and North East Somerset Unitary Authority	Completed	N/A	N/A
ACT2079	Bath and North East Somerset Unitary Authority	Completed	N/A	N/A
ACT2080	South Gloucestershire Unitary Authority	Superseded	Other - This is a duplicate measure that should have been removed from the database. It is same as ACT2081. PK 2nd Mar17	N/A
ACT2081	Bath and North East Somerset Unitary Authority	Completed	N/A	N/A
ACT2082	Bath and North East Somerset Unitary Authority	Completed	N/A	N/A
ACT2083	Bath and North East Somerset Unitary Authority	Completed	N/A	N/A
ACT2085	Bath and North East Somerset Unitary Authority	Completed	N/A	N/A
ACT2088	Bath and North East Somerset Unitary Authority	Completed	N/A	N/A
ACT972	Environment Agency	Ongoing	N/A	Yes	Local
ACT973	Environment Agency	Ongoing	N/A	Yes	Local
ACT974	Environment Agency	Ongoing	N/A	Yes	Local
ACT975	Environment Agency	Ongoing	N/A	Yes	Local
ACT976	Environment Agency	Ongoing	N/A	No
ACT977	Environment Agency	Ongoing	N/A	Yes	Local
ACT978	Environment Agency	Completed	N/A	N/A
ACT979	Environment Agency	Ongoing	N/A	Yes	Local
ACT980	Environment Agency	Ongoing - construction	N/A	No
ACT981	Environment Agency	Ongoing - construction	N/A	Yes	Local & National
ACT982	Environment Agency	Ongoing - construction	N/A	Yes	Local
ACT983	Environment Agency	Ongoing	N/A	Yes	Local
ACT985	Environment Agency	Ongoing	N/A	Yes	Local
ACT986	Environment Agency	Completed	N/A	N/A
ACT987	Environment Agency	Completed	N/A	N/A
ACT988	Environment Agency	Ongoing	N/A	Yes	Local
ACT989	Environment Agency	Ongoing	N/A	Yes	National
ACT990	Environment Agency	Completed	N/A	N/A
ACT991	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT992	Environment Agency	Ongoing	N/A	Yes	Local
ACT993	Environment Agency	Ongoing	N/A	Yes	Local
ACT994	Environment Agency	Ongoing	N/A	Yes	National
ACT995	Environment Agency	Superseded	Further work showed it was not viable	N/A
ACT996	Environment Agency	Ongoing	N/A	Yes	Local
ACT997	Environment Agency	Superseded	It has been replaced by another measure	N/A
ACT998	Environment Agency	Completed	N/A	N/A
ACT999	Environment Agency	Completed	N/A	N/A