## Cover_sheet
Social Housing Decarbonisation Fund (SHDF) Wave 1 Statistics

This spreadsheet contains a selection of data tables to provide an overview of the progression of the SHDF scheme.
The Government launched Wave 1 of the SHDF in August 2021. It has awarded around £179m of grant funding for delivery from 2022 into 2023, and will see energy performance improvements to up to 20,000 social housing properties.

Publication dates
The data tables in this spreadsheet were published at 09:30am Thursday 26th January 2023.

Data Coverage
Data covered in this release is for Wave 1 delivery to the end of November 2022.
Data covered in this release is for England only, as the scheme only operated in England.

Units, notes and no data
Some cells in the tables refer to notes which can be found beneath the tables on each worksheet. Note markers are presented in square brackets, for example: [n1]. / Some cells have no data, when this is the case cell is left blank. An explanation of why there is no data is given at the top of the worksheet. / Some column headings give units, when this is the case the units are presented in round brackets to differentiate them from note markers.

Contact Details
Press Enquiries to the Press Officer: 020 7215 5975; or the news desk: 020 7215 1000
Responsible Statisticians: Isi Avbulimen and Christine Cheung
EnergyEfficiency.Stats@beis.gov.uk
07927 579551

This workbook was updated on:	26 January 2023
The next update for these statistics is:	23 February 2023

## Contents
Table of contents
Publication date:	Thursday, January 26, 2023
Data Period	1 March 2022 to 30 November 2022
Geographical Coverage	England only
All figures are provisional and subject to revision.
These table numbers are subject to change in future releases, as additional and more detailed analysis are included.
Worksheet number	Worksheet Title	Date the data was last updated	Next publication date
Summary	Summary	26 January 2023	23 February 2023
T1	Table 1 - Number of Measures Installed by month	26 January 2023	23 February 2023
T2	Table 2 - Number of Households Upgraded by Month	26 January 2023	23 February 2023
T3	Table 3 - Number of Measures Installed and Average Measure Cost by Measure Type	26 January 2023	23 February 2023
T4	Table 4 - Number of Households upgraded and Measures installed by signed-up LA	26 January 2023	23 February 2023
T5	Table 5 - Number of Households Upgraded and Measures installed by English geographic region	26 January 2023	23 February 2023
T6	Table 6 - Number of Measures Installed and Households Upgraded by Parliamentary Constituency	26 January 2023	23 February 2023
T7	Table 7 - Number of Measures Installed by Measure Group and Property Type	26 January 2023	23 February 2023

## About_Release
Further information
Methodology
• BEIS receive a monthly delivery of GHGV data from the scheme delivery partner. This contains three raw data extracts on: applications, vouchers and installers. This monthly update means that each monthly publication are subject to revisions as the scheme progresses.

## Glossary
Glossary
This sheet provides definitions of key terms used within this publication.
Key Term	Description

## Notes
Notes Related to Data in this Spreadsheet
Footnote Number	Footnote Text
[n1]
[n2]
[n3]
[n4]
[n5]
[n6]
[n7]
[n8]

## Summary
Summary of Key Trends
This worksheet summarises the key trends presented in the tables within this release.

Introduction
This release presents the latest statistics on the Social Housing Decarbonisation Scheme (SHDF) Wave 1.
This release of statistics contains a selection of tables covering key metrics to monitor the scheme. In future releases, additional analysis tables will be included, so the table numbers will change.
The data contained in the analysis is based on returns submitted by mid December 2022, covering measure installations to the end of November 2022.
The data is based on returns from 66 Local Authorities, with completed installations reported by 11 Local Authorities.
The scheme is only available in England. For more information on the scheme, please see the
Social Housing Decarbonisation Fund Scheme Wave 1 (opens in new window).

Key points
• To the end of November 2022, there were 1,430 measures installed in 920 households, with 774 (54 per cent) measures installed in November 2022.
• Of these, the majority were Insulation measures (1,077 measures, 75 per cent), with Electricity Related measures accounting for 24 per cent (341 measures) of measures installed. (Table 3).
• The most common measure installed was Loft Insulation (640 measures, 45 per cent), with 311 Cavity Wall Insulation measures (22 per cent) and 299 Energy Efficient Lighting measures (21 per cent) also installed. (Table 3).
• The highest average measure cost was for External Solid Wall Insulation at an average of £17,000 per measure, with the lowest average cost being for Energy Efficient Lighting at £300 per measure (Table 3).
• Of the 1,430 measures installed and notified to BEIS, the majority were installed in the North East region (816 measures, 57 per cent), with 265 measures installed in Yorkshire and The Humber (19 per cent) and 184 measures in North West (13 per cent). (Table 5).
• To the end of November 2022, 920 households have been upgraded under the scheme, meaning they have had at least one measure installed. Of these, 454 households were upgraded in the North East (49 per cent), 249 in Yorkshire and The Humber (27 per cent), and 117 in North West (13 per cent). (Table 5).
• The majority of measures were installed in Houses (989 measures, 69 per cent), followed by Bungalows (381 measures, 27 per cent) (Table 7).
• An additional 473 ventilation measures have been installed over the period. These have not been included in the statistical tables while we consider their treatment in the statistics.

## Charts
Charts visualising key statistics
This worksheet contains six charts. The charts visualise some of the key statistics within the release.
This worksheet contains blank rows and columns to aid the presentation of the charts.
Chart 1: Number of Measures Installed by Installation Month	Chart 2: Number of Households Upgraded by First Installation Month

Chart 3: Number of Measures Installed by Measure Type	Chart 4: Proportion of Measures Installed by English Region

Chart 5: Proportion of Households Upgraded by English Region	Chart 6: Number of Measures Installed by Property Type

## T1
Table 1: Number of Measures Installed by month
This worksheet contains one table. The table presents the number of measures installed by installation month.
Some cells refer to notes, which can be found below the table.
Tables may contain blank cells. These indicate that there is no data but are kept to allow easy comparisons between tables.
Freeze panes are used in this table. To turn them off, go to View, Freeze Panes, Unfreeze panes.

Installation Month	Number of Measures Installed [n1] [n2]
March 2022	44
April 2022	59
May 2022	96
June 2022	75
July 2022	90
August 2022	66
September 2022	83
October 2022	143
November 2022	774
Total	1,430
[n1] Number of measures installed is a count of the number of energy efficiency measures installed in a household under the SHDF scheme. It includes measures where a date of completed installation is provided.
Installation month is based on the Date of Completed Installation.
[n2] 473 ventilation related measures have been installed but are not included in these tables while we consider their treatment in the statistics.

Last updated	26 January 2023
Next update	23 February 2023

## T2
Table 2: Number of Households Upgraded by Month
This worksheet contains one table. The table presents the number of households upgraded by first installation month.
Some cells refer to notes, which can be found below the table.
Tables may contain blank cells. These indicate that there is no data but are kept to allow easy comparisons between tables.
Freeze panes are used in this table. To turn them off, go to View, Freeze Panes, Unfreeze panes.

First Installation Month	Number of Households Upgraded [n1]
March 2022	44
April 2022	58
May 2022	90
June 2022	61
July 2022	62
August 2022	38
September 2022	53
October 2022	93
November 2022	421
Total	920
[n1] Number of households upgraded is a count of the number of households where at least one energy efficiency measures has been installed.
The date that the household is upgraded is taken as the completed installation of the first measure installed. For example, if a household had a measure installed in March 2022 and May 2022 then the date that the household is upgraded would be March 2022.

Last updated	26 January 2023
Next update	23 February 2023

## T3
Table 3: Number of Measures Installed and Average Measure Cost by Measure Type
This worksheet contains one table. The table presents the number of measures installed and average measure cost by measure type.
Some cells refer to notes, which can be found below the table.
Tables may contain blank cells. These indicate that there is no data but are kept to allow easy comparisons between tables.
Freeze panes are used in this table. To turn them off, go to View, Freeze Panes, Unfreeze panes.

Measure Group	Measure Type [n1]	Number of Measures Installed	Percentage of Total Measures Installed	Average (Mean) Measure Cost (£) [n2][n3]
Insulation	All Insulation Measures	1,077	75%	4,200
Insulation	Cavity Wall Insulation	311	22%	1,700
Insulation	External Solid Wall Insulation	117	8%	17,000
Insulation	Internal Solid Wall Insulation	7	0%	5,200
Insulation	Loft Insulation	640	45%	600
Insulation	Pitched Roof Insulation	0	0%	0
Insulation	Flat Roof Insulation	1	0%	#
Insulation	Bay Roof Insulation	1	0%	#
Insulation	Room in Roof Insulation	0	0%	0
Insulation	Solid Floor Insulation	0	0%	0
Insulation	Suspended Floor Insulation	0	0%	0
Insulation	Park Home Insulation	0	0%	0
Low Carbon Heat	All Low Carbon Heat Measures	0	0%	0
Low Carbon Heat	Air Source Heat Pump	0	0%	0
Low Carbon Heat	Ground Source Heat Pump	0	0%	0
Low Carbon Heat	Hybrid Heat Pump	0	0%	0
Low Carbon Heat	Biomass Boiler	0	0%	0
Low Carbon Heat	Solar Thermal	0	0%	0
Low Carbon Heat	Electric Storage Heating	0	0%	0
Heating Controls	All Heating Control Measures	3	0%	0
Heating Controls	Heating Controls	3	0%
Heating Controls	Hot Water Tank Insulation	0	0%	0
Heating Controls	Hot Water Tank Thermostat	0	0%	0
Windows and Doors	All Window and Door Measures	9	1%	11,700
Windows and Doors	Double or Triple Glazing	9	1%	11,700
Windows and Doors	Draught Proofing	0	0%	0
Windows and Doors	Energy Efficient Windows and Doors	0	0%	0
Windows and Doors	Secondary Glazing	0	0%	0
Electricity Related	All Electricity Related Measures	341	24%	1,700
Electricity Related	Solar PV	42	3%	5,300
Electricity Related	Energy Efficient Lighting	299	21%	300
Total	All Measures	1,430	100%	3,600

[n1] 473 ventilation related measures have been installed but are not included in these tables while we consider their treatment in the statistics.
[n2] The average measure cost is based on measures where the cost has been reported by the local authority.
[n3] # refers to values between 1 and 4 inclusive which have been supressed to prevent disclosure.

Last updated	26 January 2023
Next update	23 February 2023

## T3_X
Table - Measures Installed, Mean Allocated Government Funding, Mean LA Funding, Mean Self Funding and Mean Total Measure Cost by Measure Type
This worksheet contains one table. The table presents the number of measures installed, average government contribution value, average LA contribution value, average self-funding and average total measure cost by measure type.
Some cells refer to notes, which can be found below the table.
Tables may contain blank cells. These indicate that there is no data but are kept to allow easy comparisons between tables.
Freeze panes are used in this table. To turn them off, go to View, Freeze Panes, Unfreeze panes.
Table : Measures Installed, Mean Allocated Government Funding, Mean LA Funding, Mean Self Funding and Mean Total Measure Cost by Measure Type
Measure Group	Measure Type	Number of Measures Installed	Percentage of Total Measures Installed	Average (Mean) Government Contribution Value (£)	Average (Mean) LA Contribution Value (£) / 2	Average (Mean) Self funding (£) / 3	Average (Mean) Total Measure Cost (£)
Insulation	All Insulation Measures	0	#REF!	N/A	N/A	N/A	N/A
Insulation	Cavity Wall Insulation	0	#REF!	N/A	N/A	N/A	N/A
Insulation	External Solid Wall Insulation	0	#REF!	N/A	N/A	N/A	N/A
Insulation	Internal Solid Wall Insulation	0	#REF!	N/A	N/A	N/A	N/A
Insulation	Loft Insulation	0	#REF!	N/A	N/A	N/A	N/A
Insulation	Pitched Roof Insulation	0	#REF!	N/A	N/A	N/A	N/A
Insulation	Flat Roof Insulation	0	#REF!	N/A	N/A	N/A	N/A
Insulation	Room in Roof Insulation	0	#REF!	N/A	N/A	N/A	N/A
Insulation	Solid Floor Insulation	0	#REF!	N/A	N/A	N/A	N/A
Insulation	Suspended Floor Insulation	0	#REF!	N/A	N/A	N/A	N/A
Insulation	Park Home Insulation	0	#REF!	N/A	N/A	N/A	N/A
Low Carbon Heat	All Low Carbon Heat Measures	0	#REF!	N/A	N/A	N/A	N/A
Low Carbon Heat	Air Source Heat Pump	0	#REF!	N/A	N/A	N/A	N/A
Low Carbon Heat	Ground Source Heat Pump	0	#REF!	N/A	N/A	N/A	N/A
Low Carbon Heat	Hybrid Heat Pump	0	#REF!	N/A	N/A	N/A	N/A
Low Carbon Heat	Biomass Boiler	0	#REF!	N/A	N/A	N/A	N/A
Low Carbon Heat	Solar Thermal	0	#REF!	N/A	N/A	N/A	N/A
Low Carbon Heat	Electric Storage Heating	0	#REF!	N/A	N/A	N/A	N/A
Heating Controls	All Heating Control Measures	0	#REF!	N/A	N/A	N/A	N/A
Heating Controls	Heating Controls	0	#REF!	N/A	N/A	N/A	N/A
Heating Controls	Hot Water Tank Insulation	0	#REF!	N/A	N/A	N/A	N/A
Heating Controls	Hot Water Tank Thermostat	0	#REF!	N/A	N/A	N/A	N/A
Windows and Doors	All Window and Door Measures	0	#REF!	N/A	N/A	N/A	N/A
Windows and Doors	Double or Triple Glazing	0	#REF!	N/A	N/A	N/A	N/A
Windows and Doors	Draught Proofing	0	#REF!	N/A	N/A	N/A	N/A
Windows and Doors	Energy Efficient Windows and Doors	0	#REF!	N/A	N/A	N/A	N/A
Windows and Doors	Secondary Glazing	0	#REF!	N/A	N/A	N/A	N/A
Electricity Related	All Electricity Related Measures	0	#REF!	N/A	N/A	N/A	N/A
Electricity Related	Solar PV	0	#REF!	N/A	N/A	N/A	N/A
Electricity Related	Energy Efficient Lighting	0	#REF!	N/A	N/A	N/A	N/A
Other	All Other Measures	#REF!	#REF!	N/A	N/A	N/A	N/A
Other	Extractor Fan	#REF!	#REF!	N/A	N/A	N/A	N/A
Other	Mechanical Ventilation	#REF!	#REF!	N/A	N/A	N/A	N/A
Other	Roof Replacement	#REF!	#REF!	N/A	N/A	N/A	N/A
Other	Ventilation	#REF!	#REF!	N/A	N/A	N/A	N/A
Unknown	Unknown Measures	0	#REF!	N/A	N/A	N/A	N/A
Total	All Measures	#REF!	#REF!	N/A	N/A	N/A	N/A

Last updated
Next update

## T4
Table 4: Number of Households upgraded and Measures installed by signed-up LA
This worksheet contains one table. The table presents the number of households upgraded and measures installed across the whole scheme by signed-up LA.
Some cells refer to notes, which can be found below the table.
Tables may contain blank cells. These indicate that there is no data but are kept to allow easy comparisons between tables.
Freeze panes are used in this table. To turn them off, go to View, Freeze Panes, Unfreeze panes.

Area Code	LA [n1]	Number of Measures Installed [n2][n3]	Number of Households Upgraded [n2][n3]
E06000009	Blackpool Borough Council	133	67
E06000047	Durham County Council	793	431
E07000026	Allerdale Borough Council	^	^
E07000109	Gravesham Borough Council	43	41
E07000240	St Albans City & District	48	26
E08000017	Doncaster Council	82	66
E08000024	Sunderland City Council	23	23
E09000031	London Borough of Waltham Forest	^	^
E09000033	Westminster Council	#	#
E47000003	West Yorkshire Combined Authority	183	183
E47000004	Liverpool City Region Combined Authority	#	#

[n1] Only areas where completed installations have been reported are included.
[n2] # refers to values between 1 and 4 inclusive which have been supressed to prevent disclosure.
[n3] ^ refers to values of 5 or more which have been supressed where another value within the group was suppressed to prevent disclosure.

Last updated	26 January 2023
Next update	23 February 2023

## T5
Table 5: Number of Households Upgraded and Measures installed by English geographic region
This worksheet contains one table. The table presents the number of households upgraded and measures installed across the whole scheme by English geographic region.
Some cells refer to notes, which can be found below the table.
Tables may contain blank cells. These indicate that there is no data but are kept to allow easy comparisons between tables.
Freeze panes are used in this table. To turn them off, go to View, Freeze Panes, Unfreeze panes.

Geographic Region Code	Region Name [n1]	Number of Measures Installed	Percentage of Total Measures Installed	Number of Households Upgraded	Percentage of Total Households Upgraded
E12000001	North East	816	57%	454	49%
E12000002	North West	184	13%	117	13%
E12000003	Yorkshire and The Humber	265	19%	249	27%
E12000004	East Midlands	0	0%	0	0%
E12000005	West Midlands	0	0%	0	0%
E12000006	East	48	3%	26	3%
E12000007	London	74	5%	33	4%
E12000008	South East	43	3%	41	4%
E12000009	South West	0	0%	0	0%
E92000001	England Total	1,430	100%	920	100%

[n1] There have been no reported completed installations in East Midlands, West Midlands or South West.

Last updated	26 January 2023
Next update	23 February 2023

## T6
Table 6: Number of Measures Installed and Households Upgraded by Parliamentary Constituency
This worksheet contains one table. The table presents the number of households upgraded and measures installed across the whole scheme by parliamentary constituency.
Some cells refer to notes, which can be found below the table.
Tables may contain blank cells. These indicate that there is no data but are kept to allow easy comparisons between tables.
Freeze panes are used in this table. To turn them off, go to View, Freeze Panes, Unfreeze panes.

Area Code	Parliamentary Constituency Name [n1]	Number of Measures Installed [n2][n3]	Number of Households Upgraded [n2][n3]
E14000548	Batley and Spen	18	18
E14000581	Bootle	#	#
E14000634	Chingford and Woodford Green	24	11
E14000641	City of Durham	462	254
E14000668	Doncaster Central	82	66
E14000677	Easington	331	177
E14000715	Gravesham	43	41
E14000740	Hemsworth	15	15
E14000749	Hitchin and Harpenden	14	9
E14000754	Houghton and Sunderland South	6	6
E14000776	Lancaster and Fleetwood	133	67
E14000790	Leyton and Wanstead	^	#
E14000826	Morley and Outwood	30	30
E14000836	Normanton, Pontefract and Castleford	113	113
E14000960	St Albans	34	17
E14000982	Sunderland Central	8	8
E14001009	Wakefield	7	7
E14001013	Walthamstow	37	16
E14001020	Washington and Sunderland West	9	9
E14001036	Westminster North	#	#
E14001053	Workington	^	^

[n1] Only areas where completed installations have been reported are included.
[n2] # refers to values between 1 and 4 inclusive which have been supressed to prevent disclosure.
[n3] ^ refers to values of 5 or more which have been supressed where another value within the group was suppressed to prevent disclosure.

Last updated	26 January 2023
Next update	23 February 2023

## T7
Table 7: Number of Measures Installed by Measure Group and Property Type
This worksheet contains one table. The table presents the number of measures installed across the whole scheme by measure type and property type.
Some cells refer to notes, which can be found below the table.
Tables may contain blank cells. These indicate that there is no data but are kept to allow easy comparisons between tables.
Freeze panes are used in this table. To turn them off, go to View, Freeze Panes, Unfreeze panes.

		Property Type
Measure Group	Measure Type [n1]	Bungalow	House	Flat	Maisonette	Total Measures Installed	Percentage Measures Installed
Insulation	All Insulation Measures	243	775	55	4	1,077	75%
Insulation	Cavity Wall Insulation	42	236	32	1	311	22%
Insulation	External Solid Wall Insulation	0	109	8	0	117	8%
Insulation	Internal Solid Wall Insulation	0	4	3	0	7	0%
Insulation	Loft Insulation	201	424	12	3	640	45%
Insulation	Pitched Roof Insulation	0	0	0	0	0	0%
Insulation	Flat Roof Insulation	0	1	0	0	1	0%
Insulation	Bay Roof Insulation	0	1	0	0	1	0%
Insulation	Room in Roof Insulation	0	0	0	0	0	0%
Insulation	Solid Floor Insulation	0	0	0	0	0	0%
Insulation	Suspended Floor Insulation	0	0	0	0	0	0%
Insulation	Park Home Insulation	0	0	0	0	0	0%
Low Carbon Heat	All Low Carbon Heat Measures	0	0	0	0	0	0%
Low Carbon Heat	Air Source Heat Pump	0	0	0	0	0	0%
Low Carbon Heat	Ground Source Heat Pump	0	0	0	0	0	0%
Low Carbon Heat	Hybrid Heat Pump	0	0	0	0	0	0%
Low Carbon Heat	Biomass Boiler	0	0	0	0	0	0%
Low Carbon Heat	Solar Thermal	0	0	0	0	0	0%
Low Carbon Heat	Electric Storage Heating	0	0	0	0	0	0%
Heating Controls	All Heating Control Measures	0	3	0	0	3	0%
Heating Controls	Heating Controls	0	3	0	0	3	0%
Heating Controls	Hot Water Tank Insulation	0	0	0	0	0	0%
Heating Controls	Hot Water Tank Thermostat	0	0	0	0	0	0%
Windows and Doors	All Window and Door Measures	1	7	1	0	9	1%
Windows and Doors	Double or Triple Glazing	1	7	1	0	9	1%
Windows and Doors	Draught Proofing	0	0	0	0	0	0%
Windows and Doors	Energy Efficient Windows and Doors	0	0	0	0	0	0%
Windows and Doors	Secondary Glazing	0	0	0	0	0	0%
Electricity Related	All Electricity Related Measures	137	204	0	0	341	24%
Electricity Related	Solar PV	0	42	0	0	42	3%
Electricity Related	Energy Efficient Lighting	137	162	0	0	299	21%
Total	All Measures	381	989	56	4	1,430	100%

[n1] 473 ventilation related measures have been installed but are not included in these tables while we consider their treatment in the statistics.

Last updated	26 January 2023
Next update	23 February 2023

## SHDF_LA_List
SHDF LA List - LAs that have signed up to the scheme

Local Authorities [n1]	LA Code	Region Code	Region Name
Blackpool Borough Council	E06000009	E12000002	North West
Hull City Council	E06000010	E12000003	Yorkshire and The Humber
City of York Council	E06000014	E12000003	Yorkshire and The Humber
Leicester City Council	E06000016	E12000004	East Midlands
Nottingham City Council	E06000018	E12000004	East Midlands
Stoke-on-Trent City Council	E06000021	E12000005	West Midlands
Plymouth City Council	E06000026	E12000009	South West
Thurrock Council	E06000034	E12000006	East of England
Milton Keynes	E06000042	E12000008	South East
Durham County Council	E06000047	E12000001	North East
Cheshire East Borough Council	E06000049	E12000002	North West
Cheshire West and Chester Borough Council	E06000050	E12000002	North West
Shropshire Council	E06000051	E12000005	West Midlands
Bedford Borough Council	E06000055	E12000006	East of England
Northumberland County Council	E06000057	E12000001	North East
West Northamptonshire Council	E06000062	E12000004	East Midlands
Fenland District Council	E07000010	E12000006	East of England
Allerdale Borough Council	E07000026	E12000002	North West
South Derbyshire District Council	E07000039	E12000004	East Midlands
East Devon District Council	E07000040	E12000009	South West
Stroud District Council	E07000082	E12000009	South West
Dacorum Borough Council	E07000096	E12000006	East of England
Three Rivers District Council	E07000102	E12000006	East of England
Gravesham Borough Council	E07000109	E12000008	South East
Folkestone & Hythe District Council	E07000112	E12000008	South East
Broadland District Council	E07000144	E12000006	East of England
Great Yarmouth	E07000145	E12000006	East of England
Norwich	E07000148	E12000006	East of England
Ashfield District Council	E07000170	E12000004	East Midlands
Newcastle under Lyme Borough Council	E07000195	E12000005	West Midlands
Stafford Borough Council	E07000197	E12000005	West Midlands
Tamworth Borough Council	E07000199	E12000005	West Midlands
Reigate and Banstead Borough Council	E07000211	E12000008	South East
Stratford-on-Avon District Council	E07000221	E12000005	West Midlands
Crawley Borough Council	E07000226	E12000008	South East
St Albans City & District	E07000240	E12000006	East of England
Stevenage Borough Council	E07000243	E12000006	East of England
West Suffolk Council	E07000245	E12000006	East of England
Greater Manchester Combined Authority	E08000003	E12000002	North West
Barnsley Council	E08000016	E12000003	Yorkshire and The Humber
Doncaster Council	E08000017	E12000003	Yorkshire and The Humber
Rotherham Metropolitan Borough Council	E08000018	E12000003	Yorkshire and The Humber
Newcastle City Council	E08000021	E12000001	North East
Sunderland City Council	E08000024	E12000001	North East
Coventry City Council	E08000026	E12000005	West Midlands
Walsall Metropolitan Borough	E08000030	E12000005	West Midlands
Leeds City Council	E08000035	E12000003	Yorkshire and The Humber
City of London	E09000001	E12000007	London
London Borough of Camden	E09000007	E12000007	London
Enfield Council	E09000010	E12000007	London
London Borough of Havering	E09000016	E12000007	London
London Borough of Hillingdon	E09000017	E12000007	London
London Borough of Hounslow	E09000018	E12000007	London
Islington Council	E09000019	E12000007	London
Royal Borough of Kensington & Chelsea	E09000020	E12000007	London
London Borough of Lambeth	E09000022	E12000007	London
London Borough of Sutton	E09000029	E12000007	London
London Borough of Waltham Forest	E09000031	E12000007	London
Westminster Council	E09000033	E12000007	London
Essex County Council	E10000012	E12000006	East of England
Nottinghamshire County Council	E10000024	E12000004	East Midlands
West Yorkshire Combined Authority	E47000003	E12000003	Yorkshire and The Humber
Liverpool City Region Combined Authority	E47000004	E47000004	North West
Tees Valley Combined Authority	E47000006	E47000006	North East
West Midlands Combined Authority	E47000007	E47000007	West Midlands
West of England Combined Authority	E47000009	E47000009	South West

[n1] Each local authority is leading one project except for Leeds City Council, Islington Council and London Borough of Hounslow that are leading two projects.