## JZC DG Two-Year Plan
Jet Zero Council Delivery Group Two-Year Plan: February - December 2023 | [12 empty] | Jet Zero Council Delivery Group Two-Year Plan: January - December 2024
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
SAF Delivery Group Objective: To provide advice on how government and industry can work together to establish UK production facilities and accelerate the delivery of the fuel to market | [12 empty] | SAF Delivery Group Objective: To provide advice on how government and industry can work together to establish UK production facilities and accelerate the delivery of the fuel to market
ZEF Delivery Group Objective: To provide advice on how government and industry can work together to best accelerate the adoption of zero emission flight and put the UK in a leading position in the race to achieve zero emission flight. | [12 empty] | ZEF Delivery Group Objective: To provide advice on how government and industry can work together to best accelerate the adoption of zero emission flight and put the UK in a leading position in the race to achieve zero emission flight.
Joint workstreams: - international coordination - addressing non-CO2 - increasing awareness | [12 empty] | Joint workstreams: - international coordination - addressing non-CO2 - increasing awareness
Industry Events | [12 empty] | Industry Events
N.B. Key provided on second tab
Confirm full detail of SAF mandate policy
Recycled Carbon Fuels policy details clarified
Launch Low Carbon Fuels Strategy
World's first 100% SAF Transatlantic flight
SAF Mandate second consultation launched
SAF Mandate Consultation open for responses
Assessing potential mechanisms to secure a long term sustainable UK SAF industry
Publish independent review on development of UK SAF industry
SAF Mandate legislated - ready to start in 2025
SAF Supply Chain Initiative
Sustainable Skies Summit
Review data from 100% SAF Transatlantic flight
SAF Supply Chain Initiative
Confirm full detail of SAF mandate policy
Reflect on full details of SAF Mandate & confirm next steps
Support the legislation process for the SAF Mandate
Assessing required action to secure feedstocks for SAF
Identify and deliver on the actions required to achieving 100% SAF
Developing potential mechanisms to secure a long term sustainable UK SAF industry
Developing potential mechanisms to secure a long term sustainable UK SAF industry
Support other nations in the development of their Jet Zero Strategies / Collaboration
Support other nations in the development of their Jet Zero Strategies / Collaboration
Understanding the role of carbon removals & SAF production towards net zero aviation
Understanding the role of carbon removals + SAF production towards net zero aviation
ICAO CAEP Steering Group
Aviation Carbon
Work to scope potential HMG research programme
Support Non-CO2 programme implementation
Paris Airshow
ATI Conference
ZEFI Phase 2 Roadmap Published
HMG Hydrogen
Modelling
Develop and publish long term milestones for whole ZEF system to 2050 and beyond - infrastructure, hydrogen & electricity demand, technology & regulation, building on ATI market intelligence & strategy
Feed into DfT Call for Evidence on 2040 Domestic Net Zero Aviation
Highlight factors and potential market measures to influence commercialisation of ZEF
Propose measures & bring forward programmes required to commercialise
Potential airport infrastructure R&D
Improve wider industry understanding of pathways to net zero aviation
Continue Engagement
Decision Point
Estimate potential aircraft & infrastructure hydrogen leakage & suggest mitigations
Approval of ASTM D7566 Annex 4 + 6 for use as 100% SAF
At least five commercial-scale SAF plants under construction by 2025
ATI Hydrogen Capability Network - planning and preparation
ATI Hydrogen Capability Network - initial launch and low cost pilot activities
Develop understanding of the required energy for Jet Zero Strategy scenarios
ATI Programme
funding opportunity
ATI Programme
funding opportunity
Estimate potential aircraft & infrastructure hydrogen leakage & suggest mitigations
Review impact of airport infrastructure R&D to recommend any further need
Inform the case for future convergence of an aerospace and airport infrastructure centre(s)
Define UK certification programme for hydrogen powered large commercial air transport
International regulation engagement priorities identified
Cranfield Aerospace first flight
Sustainable Skies Summit
Royal International Air Tattoo
CAA: Cranfield / ZeroAvia, permit to fly testing regime and certification plan
Potential airport infrastructure R&D
Developing potential mechanisms to secure a long term sustainable UK SAF industry
Farnborough International Airshow
Universal Hydrogen first flight
Review findings from Philip New Report
Developing potential mechanisms to secure a long term sustainable UK SAF industry
Propose measures & bring forward programmes required to commercialise ZEF​
Engage with industry to support emerging outcomes from Hydrogen Capability Network
Justify and define airport integrated infrastructure demonstrators
Advise on investment opportunities for further R&D on airport readiness for ZEF
Engage with industry to highlight airport infrastructure planning and investment considerations
Regulatory landscape review and gap analysis
Plan and engage with industry and UK/international regulatory bodies to address priority areas of focus
DfT Public Attitudes research
Establish joint SAF / ZEF DG Non-CO2 Task & Finish group to advance knowledge and mitigation options
IATA Aviation Energy Forum
ICAO Stocktaking
World Economic Forum Target True Zero
ICAO CAAF
IRA meeting at EU Council
Clean Aviation funding opportunity
ATI Programme
funding opportunity
ATI Programme
funding opportunity
ATI Hydrogen Capability Network - planning and preparation
CAA: Cranfield / ZeroAvia, permit to fly testing regime and certification plan
Regular drumbeat engagement - highlighting activity and findings, dispelling myths, understanding of key issues
Regular drumbeat engagement - highlighting activity and findings, dispelling myths, understanding of key issues
DfT Public Attitudes research
Joint SAF/ZEF DG Non-CO2 Task & Finish group to advance knowledge and mitigation options
Feed into scope of second consultation on SAF Mandate
Feedback on responses from second consultation on SAF Mandate
Assessing required action to secure feedstocks for SAF
Advise and seek alignment with ATI and benefits to whole ZEF system - airport infrastructure and regulation
Consider findings of 2023 non-CO2 activity and scope further industry and HMG work on evidence building
Support Non-CO2 programme implementation
Industry group on price stability mechanism
ZeroAvia first flight
Propose measures and bring forward programmes required to commercialise ZEF, and review need for dedicated commercialisation subgroup in ZEF DG
Highlight factors and potential market measures to influence commercialisation of ZEF​
SAF clearing house launch
Sustainable Aviation Roadmap
ATI Programme
funding opportunity
ICAO Stocktaking
Royal International Air Tattoo
Aviation Carbon
ATI Conference

## Key
Acronyms
ATI | Aerospace Technology Institute
CAAF | Conference on Aviation and Alternative Fuels
CAEP | Committee on Aviation Environmental Protection
DG | Delivery Group
ICAO | International Civil Aviation Organisation
IRA | Inflation Reduction Act
SAF | Sustainable Aviation Fuels
ZEF | Zero Emission Flight
ZEFI | Zero Emission Flight Infrastructure project
Key
Dependancies:
Activities the ZEF DG are undertaking
Relevant activities delivered outside of the ZEF DG
Potential relevant activity outside of the ZEF DG
SAF mandate
SAF transatlantic flight
SAF price stability
SAF production
ZEF commercialisation
Hydrogen modelling
ZEF infrastructure
DfT Call for Evidence on 2040 Domestic Net Zero Aviation
Regulation
International coordination
Adressing non-CO2
Increasing awareness
Industry events