### Annex 10 – Information required to support Grant claims

Milestone Report Template
The following template will be emailed to you at project kick-off stage.

Enabling Technologies Programme Call Three

Project lead	[insert project lead organisation here]
Project number	[insert project number here]
Project name	[insert project title here]
UK consortium	[insert project partner organisation/s here]
Milestone Report	[insert MS number here]
Milestone description	[insert brief description of the milestone activities here]
Milestone due date	[insert the expected date of completion here]
Expected milestone value	[insert the expected value of the milestone here]
Invoice amount	[insert the actual cost and invoice amount of the milestone here]
Reason for variance	[specify the reasons for any variance against the expected milestone value here]

Continued

 Cost Breakdown
Please provide a breakdown of the expenditure for this milestone and add further partner organisations within the table where necessary.

Budget Category	Project Cost	Grant Cost

Project Lead {insert name]
Pay costs
Contingent labour / subcontractor
T&S
Software / licences
Data
Hardware / assets
Other
Overheads

Partner Organisation [insert name]
Pay costs
Contingent labour / subcontractor
T&S
Software / licences
Data
Hardware / assets
Other
Overheads

Total

Continued

Milestone Table

Please insert your milestone table here and comment on any expected or potential variances to the schedule.

Milestone Details
Number		0 of X
Title
Proposed milestone Completion (Kick off + week)
Milestone Grant Value (£)
Total Milestone Value (£)
Description of milestone activities	Milestone event: / Overview: / Scope:
Key risks to achieve milestone	Please identify high level risks that you currently anticipate to meeting this milestone. / Risk 1. / 2. / Please also identify what project risk will be mitigated by this milestone having been achieved? Mitigations

Continued
Potential critical impacts if milestone is not achieved at stated date.	It is recognised that any delay to milestone payments will have an impact on the financial position and schedule of the programme. Please outline any particular critical impacts that would be incurred if the milestone was not met (e.g., financial, schedule, technical, stakeholder relations….)
Describe key dependencies with other stakeholders with specific reference to this milestone	Linking to the impacts listed above, it is understood that there will be dependencies linked to this milestone. Please identify what dependencies are on this milestone to enable it to be met as planned. / Key dependencies for this milestone
List deliverables that confirm milestone has been met. Include justification for deliverables.	Deliverable	Justification (i.e., describe why the deliverable(s) is suitable for measuring the milestone)

 Risk Update

Please insert your project risk table, including any updates on risks, issues and mitigation measures.

Before submitting the invoice to UK Space Agency I confirm that as the lead organisation, we have undertaken our own due diligence on all partner claims.

Signed:
_______________________

Project Lead name/date/signature

Signed: ________________________

 Finance/Accountable Officer name/date/signature

Continued
Supporting Evidence Guidance
We require projects to submit evidence which will support each milestone claim. This should be submitted alongside each milestone report and UK SPACE AGENCY may ask for additional evidence at our own discretion.
Mandatory
- Proof of milestone deliverables– comprehensive report on work completed
- Notification of any non-material project changes regarding costs, rescope or other
- Notification of any other project concerns
- Review of schedule, key milestones/deliverables
- Invoices from project partners (project lead must complete due diligence on these invoices)
- Invoices for hardware and consumables (e.g., any data purchases, licenses, equipment etc.)
- Timesheets for the project lead
- Updated project risk register

Upon Request
- Breakdown of overhead costs
- Breakdown of staff costs, including contractors
- T&S receipts
- Other additional evidence at our own discretion

Invoicing Guidance
Invoices should be emailed to etp@ukspaceagency.gov.uk once your allocated ETP Project Manager has confirmed approval of your milestone report. Invoices are linked to milestones, therefore can only be submitted when the milestone is completed and will only be paid once all supporting evidence has been provided and approved by UK Space Agency. Please also note:
- The invoice amount must not include VAT
- Invoices need to contain your project PO number (provided at the start of the
     project
Invoices must state the milestone number