## Overview
Barriers and Mitigating Actions Grid

The Barrier & Mitigating Actions Grid provides greater detail on the strategies which can be undertaken to overcome barriers to deployment within intervention areas. To be used in conjunction with the Barrier Busting Handbook

Contents Page
Street Works
Wayleaves and Access Issues
Poles/Passive Infrastructure
Installing in /over/ under OGD Land
Supplier Delivery Pledge
BDUK Broadband Delivery Guidance

## Street_works1
	Barriers to broadband delivery & mitigating actions - Street Works (England Only)		HA - highways authority / LA - local authority broadband officers

No.	Barrier to delivery	Impact / risk of delay	Mitigating actions	Supporting legislation / guidance	Comments	Link 1	Link 2	Link3
1.0	Street works
1.1	Permits refused by HA due to poor quality reinstatements by contractor. Contractors will need to rectify defects when gangs could be otherwise spent undertaking installation works.	High	The supplier will be most likely put on an improvement notice or remedial plan by the HA if reinstatements do not improve. 90% of reinstatement inspections will need to pass for the improvement notice to be removed. The supplier must address defect issues with their contractor and get build back on track asap. Quality plans should be submitted related to permitting, signing and guarding and reinstatements including details of testing regimes in place and how results will be shared. / Since 1 April 2023, performance based inspection comes into force. Suppliers with high defect rates will be inspected (and will need to pay for) more. Performance is assessed each quarter with companies moving up and down bands - there is no maximum/cap on the number of inspections. Suppliers have to repair all defects which means having to do a job 2 or 3 times, incurring further costs and meaning gangs can't move to other sites. New escalation processes also means those who continue to fail defects will be put on an improvement plan by the HA if reinstatements do not improve. / 90% of reinstatement inspections will need to pass for companies to reduce their number of inspections - down to a minimum of 20% sample rate. Improvement plans will have numbers of defects to be repaired before being removed. The supplier must address defect issues with their contractor and get build back on track asap. They should also ensure they are familiar with the legislation and standards set out in the SROH; that they monitor quality and performance of contractors; and that they promote compliance within all levels of the management chain. / (Scotland only). Quality plans should be submitted related to permitting, signing and guarding and reinstatements including details of testing regimes in place and how results will be shared.	Broadband suppliers should work to all DFT statutory guidance and legislation / Supplier / contractor should be working to the Specification for Reinstatement of Openings in the Highway 4th Edition.	As outlined in the Supplier Delivery Pledge all reinstatements must be compliant with the SROH (Specification for Reinstatement of Openings in the Highway) 4th edition and the supplier should form a good working relationship with the HAs. Local Delivery Leads in BDUK can assist with any relations between suppliers and HAs which may have broken down. Supplier / contractor should also be working to the safety code for street works and road works, the statutory inspections code of practice, and understand the Street Works (Inspection fees) regulations.	DFT statutory guidance and legislation	Specification for Reinstatement of Openings in the Highway 4th Edition.	Supplier Delivery Pledge
1.2	HA refusing permits due to other utilities works in same location. Not all street works can be coordinated due to location of infrastructure, however HAs must coordinate works where they can.	High	The supplier and contractor should use one.network and other resources to understand the likely location of other utilities when planning works. The supplier should also share future build plans with HAs and encourage collaborative works where possible with other utilities if road space can be shared in a safe manner. Suppliers and / or contractors should attend regular coordination meetings held by the HA. Suppliers can identify their own coordination opportunities through one.network. Early applications should be encouraged from suppliers. The supplier and contractor should use Street Manager and other resources (should not be promoting and linking just to one third party supplier - others are available - they all have to use Street Manager) to understand the likely location/planned works of other utilities when planning works. The supplier should also share future build plans with HAs and encourage collaborative works where possible with other utilities if road space can be shared in a safe manner. Suppliers and / or contractors should attend regular coordination meetings held by the HA. Suppliers can identify their own coordination opportunities (should not be promoting one third party/commercial supplier). Early applications should be encouraged from suppliers.	Section 59 of New Roads and Streetworks Act 1991, outlines the duty HAs have in coordinating works. Section 60 of New Roads and Streetworks Act 1991, outlines duty of companies to co-operate	This is a difficult barrier to overcome especially if a utility has a longstanding road closure in place already. Suppliers should be fully aware the activities of other utilities through use of one.network and plan accordingly. HA should offer up coordination opportunities and suppliers should be attending regular coordination meetings and offering Single Point of Contract (SPOC) to work with HA to manage broadband rollout.	one.network	Street Manager	New Roads and Streetworks Act 1991,
1.3	HA not signing off permits or road closures in a timely manner causing delays.	High	There can occasionally be a tendency for suppliers and HAs to blame each other over untimely agreement of permits. LA broadband officer should investigate this matter to understand who is at fault and how the relationship can be improved to ensure efficient submission and agreement of permits. Suppliers should ensure effective planning and timely prior notification of works to the HA to avoid conflict. Early starts should not be relied upon to large extent as mentioned in 1.5 below.	N/A	LA broadband officer should verify that there are no internal issues within the HA affecting agreement of permits If the fault is found to be on the supplier side, their permitting approach should be investigated with a view to improving their performance. The statutory co-ordination code of practice has lots of advice about planning, co-ordination and communication that can help build and maintain good working relationships with HA permitting officers. The permit scheme guidance for response times offers good practice approaches which suppliers should adhere to.	The statutory co-ordination code of practice	Permit scheme guidance for response times
1.4	Permit classification for broadband works. There have been some recent changes to DfT regs in this area. All broadband works should come under standard or minor works unless a road closure (TTRO) is needed, which is then classed as major works.	High	Where major permits are being requested by HA and there is no TTRO in place, standard or minor permits should be granted in line with HAUC & JAG guidance - who are the representative body for all HAs.	Section 3.19 - 3.25 of the Permit Scheme Statutory Guidance provides clear definition of permit categories and when they should apply	In cases where issues persist, it may be best for HA to speak with HAUC & JAG David.Capon@geoplace.co.uk or david.latham@kent.gov.uk.	permit scheme guidance for response times
1.5	Suppliers often ask HAs for "early starts" on site. Early starts come in handy where works need to be completed quickly but too many early starts are being requested, giving the HA no notice of works, which causes problems in managing stakeholder expectations (especially Councillors) and erodes trust. This promotes poor last minute planning around street works which causes issues for HAs. If supplier's works are under a minor permit work can begin within 3 days and so lead times between permit and start date are small (see 1.4 above).	High	Suppliers and contractors need to plan works better and share longer term build plans with HAs as soon as possible. HAs will be more helpful and supportive of rollout if they see suppliers working with them, offering forward plans for works and agree permits in a timely manner, not constantly asking for early starts.	Page 16 of the Street Works toolkit 2.0 covers this matter in detail. The statutory co-ordination code of practice also has lots of advice about planning, co-ordination and communication that can help build good working relationships with HA permitting officers.		Street Works toolkit 2.0	Statutory co-ordination code of practice
1.6	Section 58s, embargoes and special events	High	HAs will be interested in as much forward notification of build plans as possible to make suppliers aware of embargos, Section 58s, special events etc and other restrictions to street works, most of which should all be available on Street Manager. This will also give HAs the best possible chance of being able to offer coordination opportunities and earlier starts by gaining longer prior visibility and coordinating rollout with other works already booked in. Suppliers should build special events, embargoes and other events rollout plans so that delays do not come as a surprise to them and cause delays to commercially funded or BDUK subsidised rollout.	The statutory co-ordination code of practice also has lots of advice about planning, co-ordination and communication that can help build good working relationships with HA permitting officers. See page 4 - 6 of Street Works Toolkit 2.0		Street Works toolkit 2.0	Statutory co-ordination code of practice
1.7	Poor working relationship between supplier and HA.	High	HAs are under significant pressure due to manage commercial rollout of broadband and other utilities works. Suppliers should look to build a positive working relationship directly with the HA and not subcontract this responsibility to their contractors, in particular with street works inspectors, permitting and traffic management officers. Suppliers should where possible offer a single point of contact SPOC who can ideally work within the HA to capitalise on coordination opportunities and to improve fibre planning and rollout. LAs and HAs should look to build on the kick off meetings with suppliers, and in drawing together required skill sets within council to enable and facilitate timely rollout of gigabit broadband.	The statutory co-ordination code of practice also has lots of advice about planning, co-ordination and communication that can help build good working relationships with HA permitting officers. See Annexe 3 of Street Works Toolkit 2.0 Pre Build Meeting Agenda Template.	This is referred to in to in the street works section of the Supplier Delivery Pledge. BDUK Local Delivery Leads should look to repair any relations between suppliers and HAs that may have broken down.	Statutory co-ordination code of practice	Street Works toolkit 2.0	Supplier Delivery Pledge
1.8	Supplier / contractor's poor understanding of Street Manager leading to permits being submitted incorrectly and subsequently refused by the HA.	High	Suppliers must ensure that their staff or their contractors have a strong working understanding of Street Manager (the government portal used for submitting of permits).	See DfT guidance on Street Manager	Contractor's lack of awareness of Street Manager may place a burden on HAs, This is mentioned in the Street Works section of the Supplier Delivery Pledge.	DfT guidance on Street Manager	Supplier Delivery Pledge
1.9	HA does not approving use of micro trenching	Medium	Some HAs have previously not approved micro trenching, however its use is now supported by the Specifications for Road Openings in the Highway (SROH) 4th edition (May 2020), which officially commenced in May 2021.	Micro trenching is supported and specified in section S6.6 of the Specification for Reinstatement of Openings in the Highway 4th Edition.		Specification for Reinstatement of Openings in the Highway 4th Edition.
1.11	Siting of infrastructure (cabinets / poles).	Medium	Suppliers have powers to install site cabinets and poles on the public highway under the General Permitted Development Order 2015 (GPDO), however should consider the Code of Practice for cabinet and pole siting.	General Permitted Development Order 2015 / Code of Practice for Cabinet and Pole siting (Nov 2016)	Suppliers should ensure that the HA is given sufficient notification of works and that the 28 day notices have been sent on time.	General Permitted Development Order 2015	Code of Practice for Cabinet and Pole siting
1.12	Encourage best practice approaches from LAs in drawing together required skill sets within council to enable and facilitate timely rollout of gigabit broadband	Medium	LAs should encourage ongoing support of legal and highways colleagues to quickly turn around street works permits and wayleaves.	See letter to local authorities from Minister for Digital Infrastructure		Letter to local authorities

## Wayleaves_&_access_issues
	Barriers to delivery and mitigating actions - wayleaves		LA - local authority broadband officer / HA - highways authority / OGD - Other Government Department / ALB - Arm's Length Body

No.	Barrier to delivery	Impact	Mitigating actions	Supporting legislation / guidance	Comments	Link 1	Link 2	Link 3
2.0	Wayleaves

2.1	The landlord of a multi dwelling unit (MDU) has not responded to a wayleave request from supplier to install in multi dwelling unit or land posing risk of delays / descope.	High	If the supplier has contacted the landlord a number of times without response, the LA should write to the landlord explaining that the wayleave relates to a government funded project to serve communities with gigabit fibre (see template) Mention that if the wayleave cannot be agreed x number of premises may be descoped.	The Telecoms Leasehold Property Act (TILPA) will allow suppliers to serve landlords with a warrant to install in private property, with the Product Security Telecoms Infrastructure Act PSTI Act allowing suppliers the same powers for land.	LAs should consider writing to the landlord on behalf of the supplier.	The Telecoms Leasehold Property Act (TILPA)	Product Security Telecommunications Infrastructure (PSTI) Act
2.2	Landlords of MDUs have refused wayleave requests to install in multi dwelling unit or land.	High	Landlords can refuse a wayleave, however the supplier can serve notice under the Electronic Communications Code (although this rarely happens due to lengthy waiting time for cases to be heard in the Upper Lands Tribunal). LA should write to the landlord to try to use local relationships to unlock wayleave dispute. BDUK Local Delivery lead can write to the landlord as a last resort to try to unlock the issue should supplier and LA have been unsuccessful.	Electronic Communications Code 2017		Electronic Communications Code 2017
2.3	Landlord trying to charge exorbitant sums of money for wayleave to install broadband infrastructure in a multi dwelling unit (MDU) or in private land.	High	If landowner is a public sector organisation, the LA should write to them referring to Annexe 3 of Digital Infrastructure Toolkit shows guidance for OGDs / ALB landowners. "Financial terms of agreements under the Electronic Communications Code". / If seeking consent from a private landlord, the supplier must ensure that approach is in line with the Annexe A "Electronic Communications Code: An Approach to assessing consideration & compensation under paragraph's 24 & 25"	"Financial terms of agreements under the Electronic Communications Code"	This a matter between the supplier and the landlord but the LA should make landlord / landowner aware of the guidance around valuations.	"Financial terms of agreements under the Electronic Communications Code"
2.4	Supplier is struggling to agree wayleave with government department (OGD) / arm's length body (ALB).	High	Most OGD / ALBs have regional team contacts which should be known to LAs and suppliers. Suppliers should follow guidance shown in supplier toolkit in engaging OGDs / ALBs. If wayleave dispute continues the Local Delivery Lead should write to the OGD / ALB seeking cooperation.	N/A	E-mail Local Delivery Lead at BDUK if matters persist
2.5	Standardised wayleaves speed up negotiating of wayleaves as the supplier landlord / owner work from an agreed template which saves time and money.	High	Most suppliers and landowners should be using standardised wayleaves so that once agreed only the Risk Assessment and Method Statement (RAMS) will need modification. An example of the CLA / NFU wayleave is shown to the right. See wayleaves library sheet for standardised wayleaves for OGDS / ALBs	Country Land and Business Association and National Farmers Union wayleave		Country Land and Business Association and National Farmers Union wayleave
2.6	Where a wayleave is being requested from a freeholder who owns property or land and there is a long leaseholder.	Medium	In cases where there is a long leaseholder, there must be a tripartite wayleave agreement between the freeholder, the long leaseholder and the supplier, otherwise if the freeholder grants the wayleave directly to the supplier, they will be in breach of the lease with the long leaseholder.	N/A	Supplier / freeholder should seek legal advice before proceeding with wayleave. This situation has a tendency to extend the length of time it takes to agree wayleaves.
2.7	Survey assumptions may cause errors or delays in delivery - these need to be precise at exchange, street and premises level.	Medium	Survey assumptions could relate to lack of power connections, no available locations within building for terminating equipment, issues with proposed duct locations or routes due to supplier not physically inspecting premises, building entry points. A safety file detailing presence of utilities, asbestos, existing ducts, fire compartmentation, fire stopping requirements and other building specific details should be shared with supplier / contractor as part of the wayleave discussions to update supplier Risk Assessment and Method Statement (RAMS). BDUK / LA should seek to understand whether supplier is engaging building managers, and whether physical survey of the building has been undertaken.	N/A	More relevant to MDUS installation / public buildings
2.8	Drawings of land / building or floor plans should be sent to the supplier by the landlord / land owner ahead of wayleave being drawn up	Medium	Incorrect location or inaccurate drawings / maps are a common reason for wayleaves being refused. Drawings should be sent to the supplier who should then mark on the drawings cable routes so that building surveyors can check whether the planned routes affect utilities or any other building issue.	N/A
2.9	Resource capacity within local authorities and OGDs to progress wayleaves (surveyors / lawyers).	Medium	LDL to write to supplier encouraging LAs to support completion of wayleaves in line with letter from Minister to all English LAs (August 2020)	See letter to local authorities from Minister for Digital Infrastructure		Letter to Local Authorities

## Poles__passive_infrastructure
	Barriers to delivery & mitigating actions - poles / passive infrastructure		LA - local authority / HA - highways authority / OGD - Other Government Department / ALB - Arm's Length Body

No.	Barrier to delivery	Impact	Mitigating actions	Supporting legislation / guidance	Comments	Link 1	Link 2	Link 3
3.0	Poles / passive infrastructure
3.1	Supplier struggling to get Openreach to replace defective pole.	High	Suppliers should be able to address this matter under Openreach's network adjustment process. If the supplier is not getting the required cooperation from Openreach then the Local Delivery Lead at BDUK should speak with DCMS with a view to approaching the Office for Telecoms Adjudicator (OTA)	Physical Infrastructure Access (PIA)	Network Adjustment process is known to be a complicated procedure which some suppliers often choose to avoid. Discussions with OTA should be sought through DCMS Barrier Busting Task Force.	Physical Infrastructure Access (PIA)
3.2	Installation of new poles in National Parks	High	Suppliers have powers to use existing poles and cabinets in National Parks under the General Permitted Development Order 2015 (below). Suppliers have powers to install ducts under the public highway within National Parks under the New Roads and Street Works Act 1991. If installing new poles in National Parks it is advisable to speak with the National Park Authority first to ensure that the rollout runs smoothly. Suppliers should discuss installation plans with National Park Authorities as soon as possible to reduce any visual impact.	New Roads and Street Works Act 1991 / Code of Practice for cabinet and pole siting (Nov 2016)	The National Parks Accord outlines the steps which suppliers should take in working within National Parks	New Roads and Street Works Act 1991	Code of Practice for cabinet and pole siting	National Parks Accord
3.3	Resistance from local communities to the installation of new poles on the public highway due to visual aspects.	High	As mentioned in 1.11 suppliers have powers to site cabinets and poles on the public highway under the GPDO 2015, however should consider the Code of Practice for cabinet and pole siting. Suppliers bids will have been costed on use of poles which are easier, faster and cheaper to install. Government policy supports wider installation and sharing of poles. Suppliers and if needed, LAs should write back to residents who oppose use of poles. In extreme cases suppliers may need to consider alternative methods of installation if cost allows, however this is unlikely. LAs may be asked for a response on this matter and should liaise with BDUK on a general response.	General Permitted Development Order 2015 / Code of practice for Cabinet and Pole siting	This is very difficult issue and suppliers should decide on whether use of poles will have a negative impact on take up within the area being served and whether an affordable alternative method of installation can be found and there is a valid reason for doing so.	General Permitted Development Order 2015	Code of practice for Cabinet and Pole siting
3.4	Resistance or lack of cooperation from electricity District Network Operators (DNOs) in allowing access to "joint user" electricity poles to install broadband infrastructure.	High	Suppliers have a right to use electricity poles and other utilities assets to provide broadband under the Access to Infrastructure (ATI) Regulations 2016. BDUK has worked with DNOs and broadband suppliers to agree the EB TP v4 document which outlines all processes which suppliers need to take in accessing DNO electricity pole assets to delivery broadband. Suppliers should cite this document in the event of DNOs not cooperating in offering their assets for broadband provision. If DNOs are not responding to supplier requests they should inform BDUK who can write to DNOs reminding them of their obligations under the ATI regs. If this is unsuccessful, suppliers can follow the approach outlined in 3.3. of appealing to Ofcom. BDUK / DSIT is considering options to facilitate faster access to joint user poles.	Access to Infrastructure Regulations 2016	BDUK and DCMS is considering options to expedite access to joint user poles.	Access to Infrastructure Regulations 2016

## Installing_in__over__under_OGD_
	Barriers to delivery & mitigating actions - installing in / over / on OGD land		LA - local authority / HA - highways authority / OGD - Other Government Department / ALB - Arm's Length Body

No.	Barrier to delivery	Impact	Mitigating actions	Supporting legislation / guidance	Comments	Link 1	Link 2	Link 3

4	Installing near to or in / under / over OGD or ALB land
4.1	Building broadband networks in National Parks can be challenging for suppliers. The National Parks Accord clarifies planning requirements in English National Parks and encourages early engagement with National Parks Authorities.	High	Suppliers should follow the National Parks Accord and ensure early engagement and sharing of build plans around 3 - 6 month's in advance with National Park's Authorities. Particularly sensitive locations should be identified and alternative delivery methods considered if required.	The National Parks Accord	If problems persist speak to Local Delivery Lead at BDUK who can write to the relevant National Park Authority	The National Parks Accord
4.2	Suppliers seeking consent from a government department or arm's length body to install underneath road or within bridge or structure. Likely to be long lead times for regional teams to consider proposals and structural implications	High	The BDUK Broadband Delivery Toolkit outlines guidance and contacts for suppliers in delivering in protected areas and around national infrastructure such as railways and major roads. Suppliers should allow for longer lead times, however if the supplier is not getting sufficient response after having followed required procedures from the government department or arm's length body, LAs should write to them on behalf of the supplier. If no progress is made, BDUK Local Delivery Lead should write to the government department / arm's length body at a strategic level outlining the number of premises that could be affected if the consent is not agreed, and outlining that the supplier is acting on behalf of BDUK in connecting rural communities.	The BDUK broadband delivery guidance, which includes specialist guidance from Natural England, Historic England, Network Rail, and others.	If problems persist speak to Local Delivery Lead at BDUK who can write to government department / arm's length body.	BDUK broadband delivery guidance	Natural England guidance for delivering broadband in / near to protected sites	Historic England guidance for delivering broadband in / near to historic sites
4.3	Suppliers struggling to gain wayleaves to build across land owned by large (non government) organisations who are landowners.	High	Most suppliers do not wish to exercise their rights under the Electronic Communications Code 2017 if access cannot be agreed across land. LA should try to use local influence to unlock disputes with local teams with the organisations. If problems persist the Local Delivery Lead within BDUK can approach the landowner.	N/A	If problems persist speak to Local Delivery Lead at BDUK who can write to landowner

## Supplier_Delivery_Pledge
Supplier Delivery Pledge

## Broadband_Delivery_Toolkit
BDUK Broadband delivery guidance