Programme Completion Review (C19 Vers.) - Summary Sheet

PROGRAMME TITLE: Africa Peace and Security (APS) Programme
Country and Region:		Africa Regional
IATI Unique ID:		CSSF-03-000017
HMG Partners (LEAD in bold)		FCO, MoD
Total Budget:		ODA: £10.236m				Non-ODA: £10.865m
Total Spend:		ODA: £10.375m				Non-ODA: £10.618m
Original Programme Start Date: April 2018				End Date: March 2021
Outputs					Score
1. Improved capability of Troops Contributing and Police Contributing Countries on AU/UN missions					4
2. Effective peace support centres providing relevant training and with clear path to being self-sustaining					3
3. Strengthened AU Peace Security Department					4
4. Improved capability of Regional Security Mechanisms and AU/UN missions					3
5. Improved capability of targeted member state actors					3
6. Strengthened AU capability to respond to conflict through well-developed preventative diplomacy strategies and early warning information					4
Overall output score					4
Outcome Assessment: Over the course of three years, APS has successfully delivered against objectives under two capability and capacity development strands. Under the first strand, large-scale Pre-Deployment Training delivered by the British Peace Support Team (Africa) (BPST (A)) to African troops deploying on AU/UN Peace and Security Operations contributed to the improvement of unit performance and to the ability of key host nations to deliver their own training, thus advancing sustainability of the overall Pre-Deployment Training effort. Under the second strand, APS has contributed to significant capability changes at different levels within Africa’s security and governance architecture. This has been through the new Peace and Security Operations policy development and approval; technical support to African Union departments, leading to their improved ability to engage in upstream conflict prevention; through Implementing Partner training activities; and support to development of standards, particularly at the Regional Security Mechanisms and Member State levels.
Final Outcome Score: 4					Risk: Medium
Year	2016/17		2017/18				2018/19*		2019/20*		2020/21*
Programme Score	African Union: B / BPST: B		African Union: A / BPST: B				A	A	A	A	4	4
Risk Rating -	Medium		Medium				Medium		Medium		Medium
*output/outcome scores; Risk rating: low/medium/high

What support did the UK provide?
- Pre-deployment training for African forces deploying on AU/UN operations and enhancement of African Pre-Deployment Training in order to improve local training capabilities and capacities.
- Technical assistance through embedded UK military officers from BPST(A) to ensure better efficiency of Ethiopia’s Peace Support Training Institute and Kenyan International Peace Support Training Centre, and to promote greater inter-operability between African nations part of the African Standby Force and Regional Security Mechanisms.
- Technical assistance on policy and standards (with a specific focus on the Protection of Civilians) and provision of financial support to enhance AU Commission’s oversight and delivery of Peace and Security Operations.
- Support for the development and implementation of the Djibouti Code of Conduct (repression of piracy and armed robbery against ships in the western Indian Ocean and the Gulf of Aden) to improve regional maritime security capability in Eastern Africa.
- Funded activities to enable Regional Security Mechanisms (cooperation among governments in the region to counter security issues) and AU/UN missions to manage emergency force response, improve weapons and ammunition accountability and better manage small arms and light weapons.
- Support to the African Union’s Department for Political Affairs to prevent and mitigate conflict through more focused early warning and preventive diplomacy.
- Support to the African Union political and security departments to assist with a more proactive and joined up approach to mitigate conflict.

What results did the programme deliver? Will they be sustained?
- Evidence of improved capability of AU/UN troop contributing countries. This was achieved through Pre-Deployment Training aligned with AU/UN policy and sustained through increasing inclusion of local trainers. Pre-Deployment Training is now being embedded in local training institutions following support from the programme and will be sustain by other donor funding.
- The monitoring and evaluation framework, Training Assessment System for Evaluation and Reporting (TASER), was developed to capture the quality and application of BPST (A) training. This was piloted and integrated into the training planning and implementing cycle.
- Increased focus on incorporating gender into programme activities, including introduction of a structured approach to delivering gender within training and pushing gender to be included within policy and standards development.
- Facilitated the completion of the design of a new African Union Peace and Security Operations policy, fully ratified by African Union states. Also advanced African Union police Peace and Security Operations policy and elements of tactical policy used in Pre-deployment training such as civilian/military relations.
- Analytical products generated by implementing partners have led to increased awareness and better-informed debate at different levels of the African Union Commission (the AU's secretariat) which in turn has impacted on decision making. Targeted member state engagement has also led to notable areas of support including the development of the Gambian constitution and the consolidation of the South Sudan Peace Agreement. The African Union Commission currently remains reliant on the implementing partners to generate this analysis due to limited internal capacity. This implementing partners IPs however are multi-funded allowing this work will continue without further HMG support.
- The increased collaboration of the African Union’s Political Affairs and Peace and Security Departments, which has been support by the programme, has led to greater cohesion and efficiency in delivery across both departments.
- Supported regional maritime security mechanisms in the Indian Ocean in reaching operating capability.
- The development of policy on physical security and stockpile management has been assisted through the delivery of training on Weapons and Ammunition Accountability Management and engagement with the Regional Centre on Small Arms (based in Nairobi) and AU Peace and Security Department.
- The reduction of weapons losses from Peace and Security Operations. Training was delivered to the AU mission in Somalia (AMISOM) and to the Economic Community of West African States (ECOWAS). Standard operating procedures were also developed and signed off for AMISOM, Multi-National Joint Task Force and ECOWAS.

What lessons have been learned?
- Monitoring and Evaluation. The programme has expanded its M&E capabilities through the development of TASER. Effective tracking of the outcome and impact level has become increasingly important. However, the ability to capture outcome and impact level data has remained challenging, particularly for the political side of the programme. Deep dives, outcome stories and political access and influence case studies have assisted. This would have been further enhanced by ensuring implementing partners had robust M&E processes to track outcomes and impact from the start of implementation and would have benefited in tracking the complex political changes related to the programme.
- Relationships. Establishing effective relationships, particularly with Regional Economic Communities, Regional Security Mechanisms and the African Union Commission, was seen as critical to ensuring the effective delivery of programming by all implementing partners. International IDEA, for example, recognised the need to reinforce coordination with other bodies involved in structural preventive diplomacy, particularly the regional centres and the Panel of the Wise (a consultative body of the African Union). They also highlighted the need to engage with other key actors in the African governance landscape, including civil society organisations, women and youth organisations in programme activities.
- Programme partnerships. All implementing partners highlighted the importance of open and regular communications between programme partners in order to create greater efficiencies within delivery, enhancing organisation’s strengths and mutually reinforcing activity.
- Gender Mainstreaming. The programme integrated gender, assisted by the development of a strategic approach developed by BPST (A). This identified how to best integrate gender into a diverse training set and in a more coherent way in programme activity.
- Flexibility in programming: Flexibility in the programme was critical. Adjustments to programme activities proved invaluable following the challenges of Covid-19 and assisted reducing impact of the pandemic. In total only around 40% of planned programme activity could not be delivered.