Programme Completion Review (20/21 Ver.) - Summary Sheet

Programme Title:				East Africa Crime and Justice Programme
Programme ID:				C-AFR-0004
Country and Region:				Kenya
IATI Unique ID:				CSSF-03-000019
HMG Partners (Lead in bold):				FCDO, NCA
Total Budget		ODA: £9.105m							Non-ODA: £1.0m
Spend this FY		ODA: £ 8.005m							Non-ODA: £ 0.065m
Time Frame		Start Date: April 2015							End Date: March 2021
Outputs									Score
Casework and Operations									4
Tactical Capacity Building									4
Strategic Access and Influence									4
Leverage and Exit									3
Cross-cutting: Conflict and Gender Sensitivity									2
Final Overall Scale of Output Delivery									3
Outcome Assessment: The programme focussed on high profile operations and investigations across a range of SOC cases of Kenya and UK interest and delivered strong tactical outputs. There were efforts to increase end-to-end collaboration, with notable improvements on asset recovery. A key challenge was the closure of Criminal Courts twice this year due to Covid which significantly impacted on case progression to trial. There was increasingly independent working in some areas (e.g. Mutual Legal Assistance). The programme continued to contribute to wider UK objectives on CT and the UK Kenya Security Compact. However overall, a high dependence on UK support remains and while there is evidence that UK advisers are influencing process/actions there is less to demonstrate that this is leading to more systemic or sustainable change. CSSF catalysed work through the Senior Leadership Development Programme which has the potential to deliver strategic and sustainable benefits in the longer-term. In line with previous reviews, it is less obvious that the programme’s outcomes – which can be viewed as tactical advances – produced strategic and sustainable effects due to a lack of an end-to-end approach to strengthening criminal justice outcomes.
Final Outcome Score: 3								Risk Rating: Medium
Year	2015/16 a		2016/17a		2017/18b		2018/19b			2019/20b		2020/21c
Programme Rating	NA		B		A	A	B		B	A	B	3		3
Risk Rating	MED		MED		MED		MED			MED		MED
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide in FY 20/21?
 In FY 20/21 CSSF provided support for:
- Criminal case work and casework mentoring.
- Training and mentoring for Kenyan criminal justice actors (including police, prosecutors).
- Work to support improved case management procedures and investigative techniques.
- Improving mutual legal assistance protocol and casework with a UK interest.
- The establishment of a Kenyan Crime Hotline.
- Development of Senior Leadership Training for the police.
- Construction of shelters for victims of sexual and gender-based violence (SGBV) and community awareness raising on SGBV.
- Scoping, relationship building and initial support to enhance Kenyan counter-terrorism (CT) prosecutions and UK/Kenya collaboration on CT casework (to hand over to CTPF from FY 21/22).

What results did the programme deliver?
- Increased effectiveness of serious crime related operations and investigations (counter-narcotics, human trafficking, child sexual exploitation, anti-corruption).
- Strengthened coordination between targeted criminal justice and law enforcement actors/institutions.
- Enhanced international and regional cooperation on serious crime cases and operations, including with the UK, and strengthened mutual legal assistance processes.
- Strengthened prosecution capability, notably in relation to anti-corruption in Kenya.
- A changed attitude to case progression within the judiciary in Kenya.

However, in line with the last PCR, it is less obvious that the programme’s outcomes – which can be viewed as tactical advances – produced sustainable effects.

Lessons Learnt
Important to ensure complementarity across the criminal justice activity with strong linkages across NCA/CJA activity.
- Exit and sustainability should have been considered earlier. Sustainability for the Kenyan Transnational Organised Crime Unit (TOCU) has now been secured to continue work through NCA core departmental budgets.
- X-HMG strategic direction. The previous review found that the “programme isn’t nested into an HMG strategic approach to criminal justice approaches to SOC and this has hampered its ability to deliver an end-to-end approach”. This remained relevant and, with future NCA and CJA work being taken forward under different programmes/departments there is a risk of greater splintering.
- Role of HMG advisers. An ongoing issue had been complications caused by advisers reporting to - and taking (sometimes differing) steers from - home departments and CSSF.
- UK influence could have been leveraged better on a couple of key issues which hampered progress this year (for example, lack of Kenyan prosecutors to take TOCU cases, lack of government shelter for victims of human trafficking).
- The absence of a programme board below the Local Strategy Board meant that, while different projects were managed effectively by the project team, there wasn’t a forum to drive forward strategic management of the programme.
- Weightings should be indicated in results frameworks and this should be a routine part of any results framework refresh process. The lack of weightings meant the review team needed to assume equal weighting across results areas.
- Results of ODA cuts elsewhere during the last year of the programme had a direct impact (for example, the programme absorbed the anti-corruption work and was unable to handover the SLDP project to another part of HMG). For HMG programmes moving forward, with a backdrop of budget pressures, it is increasingly important to regularly review the wider dependencies for the success of a programme and check these are still in place (or consider course correction if they have changed). Review of wider dependencies could be undertaken alongside regular review of risks and assumptions.