Programme Completion Review (20/21 Ver.) - Summary Sheet

Programme Title	Conflict Stability and Security Fund – Ethiopia
Programme ID	C-AFR-0037
Country and Region	Ethiopia, East Africa
IATI Unique ID	CSSF-03-000033
HMG Partners / (Lead in bold)	FCDO (FCO), (DFID), MoD, NCA, CJ
Total Budget	ODA: £ 1.677m	Non-ODA: £0.00
Total Spend	ODA: £ 1.432m	Non-ODA: £0.00
Time Frame	Start Date: November 2019	End Date: 31 March 2021

Outputs	Scale of Delivery
Identification of hate speech and disinformation on social media	4
Political transition, conflict management and victim support mechanisms built and tested in Somali Regional State (SRS), with increasing gender inclusion	4
Integration of conflict and gender sensitivity, contribution to gender equality, including to further HMG learning and understanding.	3
Final Overall Scale of Output Delivery	4

Outcome Assessment	The programme’s ambition significantly scaled down in 2020/21 due to limited Government of Ethiopia buy-in, a lack of clarity on needs and a change in risk appetite. Notable progress was made in the development and implementation of key mechanisms and processes to support reconciliation and an inclusive political transition process in the Somali Regional State. However, there was limited evidence of improvement in engagement of marginalised groups in the process. There was good evidence of mitigating social media threats to electoral integrity.
Final Overall Scale of Outcome Achievement:		3
Overall Risk Rating:		Medium-Low

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	-	-	-	-	-	B	B	3	3
Risk Rating	-	-		-		Medium		Medium-Low
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide?
- The CSSF Ethiopia programme was established in November 2019 and intended to be a two-year programme to support a peaceful political transition in the country, supporting short-term activity to promote stability as well as testing and piloting approaches to reform which could be handed over to FCDO in the longer-term.
- In FY 2019/20, the programme focused on scoping and initiating activities in support of its key objectives to support the political transition in Ethiopia; identify opportunities to strengthen the capacity of Security and Justice Sectors, and to mitigate ethnic tensions. Interventions included support to enable the Ogaden National Liberation Front (ONLF) to become a political party, wider reconciliation efforts in Somali Regional State (SRS) and a social media monitoring mechanism on disinformation and hate speech in the context of the planned 2020 general elections.
- In FY 2020/21 the programme supported peace and reconciliation work in SRS, and monitoring of social media threats to the integrity of the general elections. In addition, two further discrete projects were delivered to support conflict and humanitarian monitoring and analysis in Tigray and a desk review and mapping analysis to help the British Embassy Addis to strengthen its political and diplomatic engagement on gender equality and women, peace and security.
- In December 2020, a decision was taken to close the programme early (at the end of March 2021) with a view to transitioning priority activity to FCDO. This was due to pressures on the UK’s ODA budget rather than any concerns with performance.

What Results Did the Programme Deliver? Will they be sustained?
- Supported reconciliation and inclusive political transition work in SRS, contributing to the region developing into a rare ‘bright spot’ in an overall deteriorating country context. This work is fairly well established with adequate support structures to sustain it beyond the end of CSSF funding.
- Draft reconciliation strategy and law developed for the SRS, and the framework for a truth and reconciliation commission put in place. The strategy, law, commission, and victims’ network created potential for a coherent and sustainable architecture for effective reconciliation in SRS.
- Social media monitoring supported preparations for national elections and generated valuable situational awareness on the elections.
- The work on conflict and humanitarian monitoring and analysis in Tigray had catalytic effect with UK’s international partners informing responses to the Tigray crisis. This generated interest from the US for a joint international partners analysis.
- Analysis of gender sensitive diplomacy strengthened the British Embassy Ethiopia’s political and diplomatic engagement on gender equality and women, peace and security in Ethiopia.

What Lessons Have Been Learnt?
- The importance of programmes being positioned to ensure the right strategic and operational direction. The programme was Ethiopia based, aligned to the country plan and with policy and technical leadership from the British Embassy Ethiopia. However, it was included in the CSSF East Africa regional portfolio led from Nairobi, Kenya with limited strategic fit and policy coherence with the rest of the East Africa programme portfolio.
- Centralising technical leadership in Addis Ababa improved the programme’s performance and helped to overcome cross-departmental complexities and dynamics in the programme’s governance and decision-making.
- Establishing support for the programme from other international development partners was important to improve the potential for sustainability and to share risks.