Programme Completion Review (20/21 Ver.) - Summary Sheet

Programme Title	Nigeria Security and Justice Reform Programme (SJRP)
Programme ID	C-AFR-0018
Country and Region	Nigeria, West Africa
IATI Unique ID	CSSF-03-000007
HMG Partners	FCDO, MoD (ended FY 18/19)
Total Budget	ODA: £18.0m	Non-ODA: £1.5m
Total Spend	ODA: £16.5m	Non-ODA: £1.47m
Time Frame	Start Date: April 2016	End Date: March 2021

Outputs (scored for the last FY 20/21)	Scale of Delivery
Output 1: Improving public awareness on the amended Police Act and/or Regulation.	4
Output 2: Improved capacity of civil society organisations and media organisations to communicate the content of the revised Police Act	4
Output 3: Improved awareness and capacity of key government agencies, and civil society on the revised Police Act and related regulations	4
Output 4: Improved public awareness on the Police Act 2020	4
Final Overall Scale of Output Delivery	4

Outcome Assessment / During its lifetime, the SJRP scored 4 against its stated outcomes, as the targets for the programme have been met or exceeded. In FY 20/21, the programme has been successful in increasing public accountability, facilitated significant improvements in policing quality, helped build partnerships, strengthened the relationship with the Inspector General Police and has secured achievements relating to gender. Notable achievements include the passing of the police Reform Bill which provided a framework for the modernisation of the Nigerian Police Force and an important role in supporting regulation corresponding to the new Police Act.
Final Overall Scale of Outcome Achievement:	4
Overall Risk Rating:	Medium

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	A	A	A	A	A	A	A	4	4
Risk Rating	Medium	Medium		Medium		Medium		Medium
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide?
The programme focused primarily on legislative and executive oversight and accountability of the security sector; promoting constructive dialogue on security and justice; and policing. Early project components focused on prison and defence reform were completed in FY 18/19. One new outcome pillar focused on improved coordination, political engagement and learning and adaptation. This was added for financial year (FY) 19/20 and was extended to bridge the February 2019 elections and to consolidate the programme’s gains immediately following the elections. It was extended again in FY 20/21 to allow for delayed passage of the Police Reform Act following the 2019 elections and the strengthening of introduced policing procedures and reforms.

What Results Did the Programme Deliver? Will they be Sustained?
- Supporting the passage of the Police Reform Bill in the House of Representatives and the Senate in May and June 2020. This piece of legislation has provided the framework for the modernisation of the Nigerian Police Force.
- Creating platforms and mechanisms for more informed, inclusive, and constructive public dialogue on security and justice. SJRP played a major role in legitimizing security as an issue upon which civil society and media actors could and should engage.
- Support to develop, implement and adopt the Federal Community Policing Strategy.
- Support to a reform process which resulted in the scrapping of the Special Anti-Robbery Squad (SARS), a police unit notorious for human rights violations.
- Building strong partnerships and information sharing across a wide range of stakeholders, bringing together civil society organisations and successfully building a trusted relationship with the Inspector General of Police (IGP) which benefitted wider UK objectives.
- Promoting the adoption of the Violence Against Persons Prohibition (VAPP) Act in Enugu State; more meaningful participation of women in policing at a community level, including via more women in senior positions within police-community relations committees; greater representation of women within the Nigerian Police Force; dedicated Nigerian Police Force gender units in Lagos, Enugu, Kano and Nigerian Police Force; and increased reporting of sexual and gender-based violence (SGBV) cases.

Sustainability is in doubt in some areas. The original intention was for some of the programme’s achievements to be further developed by a new FCDO Security and Justice Programme. Unfortunately, resource pressures mean this is no longer the case.

What Lessons Have Been Learnt?

Ahead of the project completion review process, a lessons exercise was conducted by the British High Commission, which identified the following headline lessons from SJRP design and implementation. This has been complemented by the PCR findings.
- Focus on specific, time-bound problems to maximise programmatic coherence.
- Be clear about the desired objectives, but be flexible regarding the ways and means to achieve them.
- Embed monitoring, evaluation and learning (MEL) from the outset, be clear what you want to monitor, evaluate, and learn, and do not over-complicate the process of doing so.
- Partnerships and collaboration need to be nurtured, they cannot be forced.
- Learning and planning events are not a luxury, but a necessity.
- Proactive, targeted and relevant communications are essential for perception management.
- Choose your contracting and reporting modalities carefully.