Programme Completion Review (20/21 Ver.) - Summary Sheet

Programme Title	Somalia - Counter Extremism Programme
Programme ID	C-AFR-0024
Country and Region	Somalia Africa
IATI Unique ID	CSSF-03-000026
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO)
Total Budget	ODA: £12.811m	Non-ODA: £0
Total Spend	ODA: £3.207m	Non-ODA: £0
Time Frame	Start Date: March 2015	End Date: September 2021

Outputs	Scale of Delivery
Support to Federal Government of Somalia (FGS): FGS enhances its capacity to deliver the National Programme	4
Rehabilitation: Beneficiaries develop / enhance knowledge, skills and attitudes in an environment conducive to positive change	4
Support to reintegration: Beneficiaries enhance their prospects for sustained socio-economic reintegration	3
Promoting Moderate Islamic Voices (MIV)	4
Final Overall Scale of Output Delivery	4

Outcome Assessment / The programme made substantial progress in improving service delivery at the low level defector facility in Serendi, despite the high risk nature of the project and operating environment. However, concerns remain around the nature and scale of its overall strategic impact, including on al Shabaab capability. Data to support an assessment of reintegration of beneficiaries was limited. Further progress is also needed before the FGS Defectors Rehabilitation Programme’s (DRP) has capability to take sole responsibility. / The Moderate Islamic Voices (MIV) pilot project has shown considerable potential and the ability to adapt. However, this element has not been fully captured in the programme's Theory of Change or Results Framework outcomes.
Final Overall Scale of Outcome Achievement:	3
Overall Risk Rating:	Medium-High

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	A	A	A	A	B	A	B	4	3
Risk Rating	High	High		Medium-High		Medium-High		Medium-High
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide?

- Funding a low-level defector rehabilitation centre in Mogadishu (Serendi Rehabilitation Centre) to provide a means by which rank and file fighters looking to leave al Shabaab can defect and reintegrate into their home communities, co-managed with the Defectors Rehabilitation Programme (DRP) under FGS Ministry of Internal Security (MoIS).
- Continuing to support the FGS to implement its National Programme for Treatment and Handling of Disengaged Combatants (“the National Programme”).
- Supporting promotion of a peaceful interpretation of Islam, by establishing local networks of like-minded religious leaders, and developing mechanisms to identify and pacify extremist religious leaders and actors.

What Results Did the Programme Deliver? Will they be Sustained?

- Substantial improvements in service delivery in Serendi, operating a high-risk project in a high-risk environment.
- Serendi has received 397 beneficiaries since the start of the UK’s support in 2015, including 148 in FY20/21. Of these, 360 have now exited including 78 in FY20/21. Monitoring data suggests that only a minority had successfully achieved economic reintegration after 12 months. Information on recidivism was not available.
- The FGS DRP continued to receive technical and material support from the UK via the Serendi project during the review year.
- The transfer of responsibility for the Serendi project to the FGS DRP is still to be confirmed. The likelihood of sustainability post-UK support will depend upon the FGS’s ability to fund the project. The transition plan must explicitly acknowledge its consequences for existing beneficiaries, and the broader signal it may send about al Shabaab and the UK’s support for the FGS.
- The MIV project led by UNDP, originally aimed to counter extremism and radicalisation was realigned to address COVID-19 disinformation. This was a highly adaptive response to the pandemic and demonstrated some positive outcomes, such as calls for pausing public gatherings. Going forward the project has demonstrated potential to influence religious discourse as aligned to its original objective.

What Lessons Have Been Learnt?

- Formal defections are not the primary means of low-level defection from al Shabaab, nor do defections follow a single pathway. Women play an important role through the process. Future programming should take this into account, and be adaptive to emerging evidence.
- HMG and British Embassy Mogadishu plays a critical, positive leadership role in setting expectations for cooperation between the host government and implementing partners, but it should not be responsible for managing these relationships on an ongoing basis.
- A grassroots approach to preventing and countering violent extremism that understands and embeds local perceptions of the roots of violent extremism, rather than uncritically imposing international definitions, has a greater chance of success.