Programme Completion Review (20/21 Ver.) - Summary Sheet

Programme Title	Zimbabwe Security and Justice Programme (ZSJP)
Programme ID	C-AFR-0039
Country and Region	Zimbabwe (administered under the HQ programme)
IATI Unique ID	CSSF-03-000032
HMG Partners / (Lead in bold)	DFID (FCDO following the merger)
Total Budget	ODA: £0.55m	Non-ODA: £0.050m
Total Spend	ODA: £0.218m	Non-ODA: £0.0m
Time Frame	Start Date: April 2019	End Date: March 2021

Outputs	Scale of Delivery
Dialogue on improving security and justice is inclusive of key stakeholders.	2
Key institutions have greater capacity to improve and scrutinise the performance of the security sector.	2
Research and analysis enables effective engagement and coordination on security sector accountability by UK and DPs.	3
Mechanism and staffing in place to drive the project forward tailored to the Zimbabwean operating context and regional experience.	2

Final Overall Scale of Output Delivery	2

Outcome Assessment / The programme aimed to contribute to the outcome that “Key stakeholders cooperate to improve nationally-owned processes for building peace and institutions for holding the security sector to account”. A solid start was made during the first year of ZSJP. Activities had started to deepen understanding of security sector dynamics, build relationships and establish networks in Harare and Bulawayo. Doors were opened to parliament and ZSJP was in position to align with and influence workplans of key scrutiny committees. / In March 2020, however, the first effects of the CV19 pandemic in Zimbabwe were felt. The activities essential to the programme’s incremental coalition-building approach were cancelled. With funding scheduled for the outer years, ZSJP struggled to make further progress when resources were reduced by 90% in July 2020 and the programme did not achieve the outcome contribution originally envisaged.
Final Overall Scale of Outcome Achievement:	2
Overall Risk Rating:	Medium

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	N/A	N/A		N/A		B	B	2	2
Risk Rating	N/A	N/A		N/A		Medium		Medium
Note: a output scores; b output / outcome scores; c scale of output delivery / scale of outcome achievement

What Support Did the UK Provide?
- ZSJP was designed to provide £0.4m over two years from April 2019 to March 2021, building on the findings of a CSSF-funded 2018 scoping study on security and justice (S&J) and inception work in Q4 18-19.
- After almost £0.2m of support in FY19-20, ZSJP only invested £0.030m in FY20/21 due to a major budget cut.
- Much work had been done in the first half of 2019 to build understanding and key relationships, in particular supporting a political economy analysis of the security sector. The programme also initiated discussions with the Speaker of Parliament which enabled the funding of an assessment of parliamentary capacity to oversee the security and justice sectors. This was carried out by UK parliamentary clerks with a Zimbabwean expert, offering peer-to-peer support and opening a potential door to further UK engagement with key Parliamentary Committees. Continuing engagement also took place with senior police officers, although a decision to pause this was taken in mid-2019 in light of the deteriorating human rights context.
- From late 2019, the majority of the programme (£0.14m) was implemented through the United Nations Office for Project Services (UNOPS) to administer and manage processes for inclusive dialogue for peace, security and justice and strengthen the evidence base on security service provision.
- Over FY20-21, this included setting up a tracker of human rights violations to enable analysis of patterns and trajectories. In response to CV19 risks from March 2020, UNOPS funds were diverted to provide Personal Protective Equipment (PPE).
- In addition, the programme supported the Zimbabwe Council of Churches (ZCC)’s work on dialogue. However, with the advent of the pandemic, this was also rapidly adapted towards personal safety in communities facing the threat of COVID 19.

What Results Did the Programme Deliver? Will they be Sustained?
- Whilst unable to meet its original ambition, the programme made a good start on its objective to build networks and collective action across different institutions involved in security sector accountability. Careful preparatory steps in 2019 (such as the parliamentary assessment) were helpful in initiating discussions with key individuals; a further connection between the British Embassy Harare (BEH), civil society and parliament was made in January 2021, with goals that were well-aligned with the work plans of the key oversight committees.
- ZSJP’s initial coalition-building proved helpful in strengthening advocacy efforts in early 2021 on the law-making process to create an Independent Complaints Mechanism on the security sector.
- The plan to drive forward efforts to establish ongoing dialogue on security sector performance and enhance oversight capabilities could not be sustained in FY21-22 due to Covid impacts and lack of funding. The envisaged follow-on DFID programme was not possible due to necessary CV19-related budget reprioritisation. An ongoing Swiss-funded initiative may, however, be able to take this forward.
- ZSJP investment laid an important foundation for tracking human rights violations in real-time through an interactive dashboard. This has already started to provide a useful evidence base for UK Human Rights monitoring and reporting – a significant contribution to UK objectives in Zimbabwe. The tracker is also underpinning a step-change in how human rights defenders in the country go about collecting, recording and analysing patterns and trends in violations.

What Lessons Have Been Learnt?
- ZSJP’s experience underscores how important it is to approach entrenched governance challenges with a step-by-step process informed by political economy understanding. Design that builds in flexibility and is based on the correct level of ambition is a pre-requisite for any success in establishing relationships and achieving buy-in. These efforts also cannot be rushed.
- The mobilisation of CSSF funds for ZSJP was a good example of a joined-up x-HMG approach to see whether advantage could be taken of a possible route to reform of the security sector.
- A programme like ZSJP will significantly improve prospects for success by investing up-front, and on an ongoing basis, in political economy analysis. ZSJP’s investment in political economy analysis (PEA), alongside work to assess institutional capacity, laid a strong foundation for understanding the historical, structural and contemporary factors that determine security sector performance.
- The importance of continued relationship building, alongside any programmatic work, is critical for security sector development and an implementer must also be able to accommodate the network-building and influencing objectives of the British Embassy in parallel to their other work.