Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Colombia Peace and Stabilisation Programme (CPSP)
Programme ID
Country and Region	Colombia, Americas
IATI Unique ID
HMG Partners (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO)
Total Budget	ODA: £63,102,149 since 201516	Non-ODA: 0
Budget this FY	ODA: £10,402,149	Non-ODA: 0
Spend this FY	ODA: £10,334,317	Non-ODA: 0
Time Frame	Start Date: 1 April 2020	End Date: 31 March 2021

Outputs	Scale of Delivery
1. Support the Colombian State to effectively implement the peace agreement	4
2. Enhance the participation of civil society in the implementation of the peace accords	4
3. Build the capacity and capability of the Government of Colombia (GoC) and civil society to tackle threats to peace, particularly human rights abuses and environmental crime	4
Overall Scale of Output Delivery	4

Outcome Assessment	The programme has demonstrated resilience, adaptiveness, flexibility and catalytic impact in this reporting year. Despite the challenging and changing context, the programme continued to support the delivery of critical outcomes in support of peace, stability and security in Colombia, as evidenced by this Review.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Medium-low

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme / Rating	A	A	A	A	A+	A	A	4	Green
Risk Rating	Medium	Medium		Medium		Medium		Medium-Low
Programme changes during this period		The programme and its implementers successfully managed to adapt to the ongoing Covid-19 pandemic and associated restrictions and security dynamics.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?

In FY20-21, the UK provided £10.4m of support to Colombia. CSSF funding continued to be aimed at supporting Colombia’s efforts to achieve long-term peace by implementing the peace agreement with the Revolutionary Armed Forces of Colombia (FARC-EP) and tackling the underlying causes of conflict. The programme team continued coordinating and aligning its interventions with the regional Countering Illicit Economies Programme (CIEP), Department for Business, Energy and Industrial Strategy (BEIS)
International Climate Finance (ICF) work, as well as Ministry of Defence (MOD) and National Crime Agency (NCA) activities aimed at tackling and addressing serious and organised crime. During the period under review, the UK funded 12 bilateral and multilateral projects that were delivered by different implementing partners. This included support for: i) Colombian institutions tasked with implementing and overseeing the elements of the peace agreement; ii) The UN Trust Fund supporting reintegration, rural development and assistance to victims; iii) The designated peace monitoring mission of the Organisation of American States; iv) The International Organisation for Migration, including work with the police, transitional justice mechanism and improving community security and respect for human rights; v) The UN Office on Drugs and Crime’s work supporting investigations and prosecutions; vi) Three Colombian and international NGOs and foundations working on peace and stability.

Key Results for FY 20/21:

1. Despite Covid-19 and a deteriorating security situation, the political and financial support from the UK contributed to the continued implementation of the peace agreement during the reporting period, as evidenced by the KROC Institute’s independent progress reports.
2. The UK encouraged and supported the launch of the Government’s Green Development Programs with a Territorial Focus (PDET in Spanish) portfolio, marking a major milestone in climate-sensitising development activities.
3. Through UK and international diplomatic lobbying and programmatic support, the Government of Colombia (GoC) improved the security guarantees plan and enhanced coordination between relevant peace and security institutions.
4. Building on previous pilot work and intra-Embassy coordination to improve programming and policy work on deforestation, environmental crime and conflict, BEIS and CSSF launched the TEFOS programme in 2020. This is a key result showcasing cross-HMG innovation and delivery, with the CSSF is co-funding the TEFOS pillar on strengthening the environmental rule of law in regions affected by the conflict.

Key Lessons (see B6)

Funding through the Multi-Partner Trust Fund (MPTF) as well as bilateral programming allows the UK to adopt a flexible and wide-ranging approach to supporting the peace process: the MPTF continues to enable the UK to shape critical interventions, leverage other donor funding and deliver at scale. The UK has undertaken the role of donor coordinator of the MPTF during this review period. While this has been a challenge given the numerous stakeholders and interests involved, the programme team has responded admirably and this function has ultimately permitted greater influence over proposals and decisions of the $180m Fund. In turn, additional bilateral CSSF programming that compliments MPTF activities allows for a wide-reaching and extensive approach to supporting the peace process.

Continued and increased cross-embassy working has further expanded the UK’s ability to support the peace process: The team has continued to work closely with teams across the Embassy to help deliver HMG objectives. The biggest achievement was the launch and implementation of the five-year TEFOS programme, which was the result of the joint initiative between BEIS ICF and the CSSF team. The programme combines a focus on delivering UK climate change objectives with environmental crime and peace and this innovative collaboration was nominated for a Civil Service Award.

The CSSF has continued to ensure clear alignment between policy engagement and programme delivery, helping to further strengthen our position as a key partner of the Government of Colombia on peace and security. The flexible nature of the CSSF has enabled the Embassy to advise and support key GoC institutions and interlocutors in terms of accelerating the delivery of the peace accords. Notable achievements have been made on peace and the environment, gender, security guarantees and communications.

The Programme team invested heavily in developing new approaches to monitoring, evaluation and learning (MEL) to further improve and develop the programme: This focused on working with implementing partners to develop outcome harvesting: MEL methodology used to identify, describe, verify and analyse the changes brought about through a development intervention. It was necessary to invest considerable time in the short term to facilitate the roll-out of this MEL methodology, working closely with implementing partners to establish. These efforts have improved team relationships with implementing partners, and have allowed the programme to capture results that were not envisioned, confirming the importance of their work.

Key Recommendations for FY 21/22

Conduct a rapid stock-take of the available evidence and analysis to ensure the programme is sufficiently focused on addressing the key drivers of conflict, insecurity and instability, including those related to the 2021 protests. In addition, ensure programme is aligned with the Integrated Review and thematic priorities.

Evaluate the risks, opportunities and potential responses related to the forthcoming political transition associated with upcoming elections, with a view to ensuring sustainability of peace agenda.

In light of the upcoming fifth anniversary of the peace agreement, maximise any opportunities to highlight progress made and challenges remaining, engaging both UK and Colombian audiences.

Given the Programme Team’s approach to gender mainstreaming and its success across the programme, the team should seek to share its experience and lessons learnt across the embassy to improve overall HMG capacity in this space, using for example the recently created Gender Taskforce.

Continue to refine outcome harvesting methodology to ensure the team and implementing partners capture the real impact of their interventions and are able to communicate these effectively internally and externally. The approach should also look to ensure both positive as well as unintended outcomes are captured fully.

Continue implementing positive synergies where possible with BEIS ICF to take advantage of Government of Colombia’s commitment to environmental sustainability.