Annual Review (20/21 Ver.) - Summary Sheet
This Summary Sheet captures the headlines on programme performance, lessons and recommendations over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme. NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Commonwealth Marine Economies (CME) Programme
Programme ID	N/A
Country and Region	Commonwealth SIDS in Caribbean (Antigua and Barbuda, Belize, Dominica, Grenada, Guyana, Jamaica, St Lucia, and St Vincent & the Grenadines), and Pacific (Fiji, PNG, Kiribati, Nauru, Samoa, Solomon Islands, Tonga, Tuvalu, Vanuatu
IATI Unique ID	N/A
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office
Total Budget	ODA: £28.875m	Non-ODA: £0
Budget this FY	ODA: £2.285m	Non-ODA: £0
Spend this FY	ODA: £2.202m	Non-ODA: £0
Time Frame	Start Date: September 2020	End Date: March 2021

Outputs	Scale of Delivery
Reports, new and improved data models, and training sessions for Small Island Developing States (SIDS) institutions.	4
Commonwealth SIDS Government commitments (announcements and letters).	4
Sector studies including sector mapping, sector analysis, opportunity identification, constraint identification, and recommendations for SIDS.	4
Overall Scale of Output Delivery	4

Outcome Assessment	Launched by the Prime Minister at the Commonwealth Heads of Government Meeting (CHOGM) in 2016, the aim of the CME Programme is to support 17 Commonwealth Small Island Developing States (SIDS) in identifying the potential of, and developing, their marine economies in a sustainable, resilient and integrated way. / The Programme Outcome, as stated in the FY 2020/21 Theory of Change (ToC), is “Governments of Commonwealth SIDS work in partnership with the UK Government to develop Maritime Economy Plans (MEPs), with an improved understanding of the growth potential of their maritime economies and the environmental and sustainability context.” / Despite the significantly delayed start to Programme delivery and the policy decision not to engage with Pacific SIDS this year due to the impact of Covid-19, strong progress has been made in the delivery of MEPs for those Caribbean countries we have continued to engage with, with close personal involvement of SIDS Ministers and Prime Ministers. After just a few months of operation, 4 MEPs were close to finalisation which is a significant achievement against the backdrop of the pandemic and associated constraints.
Overall Outcome Progress Rating:		Green / Amber
Overall Risk Rating:		Low

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c
Programme Rating	N/A	‘B’		Amber		Green		3	Green / Amber
Risk Rating		Amber/Moderate		Moderate		Moderate		Low
Programme changes during this period		Financial Year 2020/21 saw programme funding split between two new sources for the CME programme: CSSF Americas and CSSF Asia Pacific. However, shortly after setting up a split-funded programme, the Pacific element of the programme was halted due to Covid-19 challenges in the region; and shortly after that the whole programme was put on pause. When the CME programme resumed in September 2020, it was only for the Caribbean element of the Programme, via Americas CSSF. Previous years has seen CME programme funding come from other sources (FYs 16/17 and 17/18 – Prosperity Fund and FYs 18/19 and 19/20 – CSSF Commonwealth Sustainability Fund). There have been consequent changes to reporting requirements.
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support did the UK Provide in FY 20/21?

In close partnership with SIDS governments, the Programme has continued to develop and implement bespoke national Maritime Economy Plans (MEPs) for 4 Caribbean SIDS (Antigua and Barbuda, Belize, Grenada, and Guyana) to ensure the Programme leaves a lasting legacy. The MEPs assess the existing national maritime economies and identify the opportunities and obstacles to development, which individual countries can address to drive economic growth and alleviate poverty.

The Programme has also continued to showcase UK expertise in ocean science through research and capacity building projects carried out by UKHO, Cefas and NOC. These projects have provided SIDS governments with a more comprehensive knowledge base of their maritime resources, and greater capacity to manage and monitor them responsibly

Due to the Covid-19 pandemic in FY 2020-21, CME Programme activity was paused from April to August 2020. Following advice from the British High Commission in Suva, it was not possible to undertake any Pacific region activity during FY 20-21 due to the pandemic.

Key Results for FY 20/21:

The CME Programme continues to help deliver the UK’s global commitments to the marine environment and tackling climate change (SDG 14, Paris Climate Change Agreement, UN Convention on Biological Diversity, Commonwealth Blue Charter), in addition to meeting the UK’s commitment to supporting development of 17 Commonwealth Small Island Developing States (SIDS), although work in Pacific SIDS during FY 2020/21 was paused due to the Covid-19 pandemic.
The Maritime Economy Plans of Antigua & Barbuda and Grenada are the first of their kind and place the UK at the forefront of work on blue economy action plans for SIDS. Maritime Economy / Blue Economy is now a major topic on the global stage, attracting a lot of interest from the UN, European Commission and other IFIs who have recently signed up to Blue Economy Principles and are trying to design Blue Economy indicators against which to evaluate their projects. The CME Programme’s MEPs are almost complete, with both Antigua and Barbuda, and Grenada, recently endorsing these national documents. Along with the strong progress made during this limited year in progressing the MEPs, the programme has also continued to support all 8 Caribbean SIDS in scope of the programme by helping grow the development and understanding of their marine economies through targeted projects led by our UK scientific agencies.

An independent review of the science and capacity building element of the CME Programme was finalised in March 2021. The review summarised the programme as “one of the best examples the reviewer has seen of how to deliver a scientific programme which has a specific aim to create the largest impact possible” and “The approach to co-development and co-delivery of projects with CME nations, and between delivery agencies, has been exemplary and should be held up as example of how to deliver complex science to inform challenging policy and management issues within challenging timescales.” The review was undertaken by a respected industry expert.

Key Lessons

The Covid-19 pandemic resulted in the CME Programme having to adapt the way in which delivery was achieved. Given the complete pause in programme activity from April to August 2020, the programme team had to move quickly to get things back up and running and ready for re-launch in September.
Key lessons learned in this period included:

- The use of technology for remote events can deliver greater knowledge-sharing and capacity building between countries and regions, as well as a higher profile for HMG and cost savings for the programme. During the Covid-19 restrictions on international travel, the CME-funded Caribbean workshop on coastal monitoring and modelling for SIDS was held via Teams video-conference rather than face to face. The event attracted participation from across the Caribbean (including non-CME SIDS) as well as participation from the Pacific region. The virtual event was achieved at a fraction of the cost of holding an in-person conference and yet included many more participants. Feedback from the event has been positive.
- Having strong and trusted working relationships delivers a stronger, more efficient and effective operation. The contacts built up by the CME Programme Team with SIDS government stakeholders and delivery partners over the years resulted in a one-team effort with all stakeholders pulling together to achieve a quick and seamless programme re-start in September.

Key Recommendations for FY 21/22
The late confirmation (on 22 March 2021) that funding will continue next FY is likely to result in a short hiatus while contracts and work streams are agreed early in the new FY. A short extension to the on-going contract with our Commercial partners has been organised to enable the continuation of consultations with SIDS Government Ministers on the Maritime Economy Plans for Antigua and Barbuda and Grenada.
The following set of key recommendations will continue to be considered and incorporated for next year. They are based on the lessons learned in FY 2020/21 and in previous years of managing the CME programme and feedback from across the HMG network.

1. Governance. High-level oversight increases programme quality and impact. Senior policy ownership is key for optimal impact. It is hoped that the planned move of the programme to the new FCDO Americas/SIDS hub will bring about new opportunities for the programme to expand its reach and profile.
2. Communications. Continually being engaged and creative with Comms products will ensure increased appetite and maximum impact with key stakeholders in promoting the programme. We will maintain our Communications strategy to ensure the Programme continues to receive high-level buy-in and proactive support, and which is pitched to as large and as diverse an audience as possible. COP26 also provides us with a strong opportunity to showcase the work of the programme to a wider audience.
3. Monitoring and Evaluation. Monitoring and evaluation frameworks, including the ToC and Results Framework need to be developed and updated on an on-going basis to reflect the continuing evolution of the programme. On-going review is essential for continuous learning and improvement.

The requirement in 2020/21 to compress the programme’s work into 7 months and deliver through a pandemic led to additional challenges, including the need to adapt changes of delivery method (remote training/meetings, etc.). We will continue to enhance and grow our new ways to deliver the programme through this continued period of wider change/remote working.

Looking forward to FY 21-22, it will be crucial to continue to build on this success by ensuring that our small amounts of funding are targeted only to those areas that will deliver the best value for money, legacy and UK profile in what will prove to be an important year for HMG’s international profile on ocean and climate change issues.